## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Town Square | 1 |  |  | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 | 1151.375
1 | Gemeenteraadsbeslissing 1 | 1.1 |  | FS2 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 0.375
2 | Collegebeslissing 1 | 1.2 | 1FS | FS3 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 0.375
3 | Collegebeslissing 2 | 1.3 | 2FS | FS4 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 0.375
4 | Gemeenteraadsbeslissing 2 | 1.4 | 3FS | FS5 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 0.375
5 | Collegebeslissing 3 | 1.5 | 4FS | FS6 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 0.375
6 | Gemeenteraadsbeslissing 3 | 1.6 | 5FS | FS7 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 0.375
7 | Begin werken | 1.7 | 6FS |  | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
8 | Werfinrichting | 1.8 |  |  | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 4.375
9 | Bemaling | 1.9 |  | SS13 | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 17.375
12 | Halfondergrondse parking | 1.10 |  |  | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 | 387
11 | Constructie PK (moot 1) | 1.10.1 |  |  | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 | 133
10 | Afgifte plannen | 1.10.1.1 | 17SF-3w 4d |  | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
14 | Grondwerk | 1.10.1.2 |  |  | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 | 20.375
13 | Graafwerken | 1.10.1.2.1 | 9SS | FS32;SS15 | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 20.375
16 | Vloerplaat | 1.10.1.3 |  |  | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 | 16.375
15 | Werkvloer | 1.10.1.3.1 | 13SS | SS17 | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 10.375
17 | Wapening vloerplaat | 1.10.1.3.2 | 15SS | SF10-3w 4d;SS18 | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 13.375
18 | Vloerplaat | 1.10.1.3.3 | 17SS | SS22;SS21;SS19 | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 8.375
20 | Wanden/kolommen | 1.10.1.4 |  |  | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 | 27.375
19 | Kolommen | 1.10.1.4.1 | 18SS | FS25;FS38 | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 7.375
21 | Wapening wanden | 1.10.1.4.2 | 18SS | FS23 | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 5.375
22 | Wanden | 1.10.1.4.3 | 18SS | SS27;FS41 | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 27.375
23 | Wapening talud | 1.10.1.4.4 | 21FS | FS24;FS36 | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 1.375
24 | Betontalud | 1.10.1.4.5 | 23FS |  | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 0.375
26 | Dakplaat | 1.10.1.5 |  |  | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 | 86.375
25 | Balken | 1.10.1.5.1 | 19FS | FS27;FS38 | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 7.375
27 | Dakplaat | 1.10.1.5.2 | 22SS;25FS | SS28;FS46 | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 55.375
28 | Wapening dakplaat | 1.10.1.5.3 | 27SS | SS29 | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 51.375
29 | Beton dakplaat | 1.10.1.5.4 | 28SS |  | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 50.375
31 | Constructie PK (moot 2) | 1.10.2 |  |  | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 | 122
30 | Afgifte plannen | 1.10.2.1 | 36SF-3w 4d |  | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
33 | Grondwerk | 1.10.2.2 |  |  | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 | 2.375
32 | Graafwerken | 1.10.2.2.1 | 13FS | FS34;FS51 | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2.375
35 | Vloerplaat | 1.10.2.3 |  |  | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 | 9.375
34 | Werkvloer | 1.10.2.3.1 | 32FS |  | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
36 | Wapening vloerplaat | 1.10.2.3.2 | 23FS | FS37;FS55;SF30-3w 4d | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 4.375
37 | Vloerplaat | 1.10.2.3.3 | 36FS |  | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
39 | Wanden/kolommen | 1.10.2.4 |  |  | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 | 14.375
38 | Kolommen | 1.10.2.4.1 | 19FS;25FS | FS44;FS57 | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 1.375
40 | Wapening wanden | 1.10.2.4.2 | 41SF | FS42-1h | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 1
41 | Wanden | 1.10.2.4.3 | 22FS | SF40;FS60 | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 6.375
42 | Wapening talud | 1.10.2.4.4 | 40FS-1h |  | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 1.375
43 | Betontalud | 1.10.2.4.5 |  |  | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 0.375
45 | Dakplaat | 1.10.2.5 |  |  | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 | 81.375
44 | Balken | 1.10.2.5.1 | 38FS | FS63 | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 5.375
46 | Dakplaat | 1.10.2.5.2 | 27FS | SS47;FS65 | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 13.375
47 | Wapening dakplaat | 1.10.2.5.3 | 46SS | SS48 | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 13.375
48 | Beton dakplaat | 1.10.2.5.4 | 47SS |  | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 13.375
50 | Constructie PK (moot 3) | 1.10.3 |  |  | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 | 152
49 | Afgifte plannen | 1.10.3.1 | 55SF-3w 4d |  | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
52 | Grondwerk | 1.10.3.2 |  |  | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 | 2.375
51 | Graafwerken | 1.10.3.2.1 | 32FS | FS53 | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2.375
54 | Vloerplaat | 1.10.3.3 |  |  | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 | 11.375
53 | Werkvloer | 1.10.3.3.1 | 51FS |  | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
55 | Wapening vloerplaat | 1.10.3.3.2 | 36FS | FS56;SF49-3w 4d | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2.375
56 | Vloerplaat | 1.10.3.3.3 | 55FS |  | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
58 | Wanden/kolommen | 1.10.3.4 |  |  | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 | 19.375
57 | Kolommen | 1.10.3.4.1 | 38FS |  | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 5.375
59 | Wapening wanden | 1.10.3.4.2 | 60SF | FS61-1h | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 1
60 | Wanden | 1.10.3.4.3 | 41FS | SF59 | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 6.375
61 | Wapening talud | 1.10.3.4.4 | 59FS-1h | FS62 | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 1.375
62 | Betontalud | 1.10.3.4.5 | 61FS |  | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 0.375
64 | Dakplaat | 1.10.3.5 |  |  | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 | 110.375
63 | Balken | 1.10.3.5.1 | 44FS |  | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 1.375
65 | Dakplaat | 1.10.3.5.2 | 46FS | SS66;FS84 | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 13.375
66 | Wapening dakplaat | 1.10.3.5.3 | 65SS | SS67 | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 13.375
67 | Beton dakplaat | 1.10.3.5.4 | 66SS |  | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 34.375
69 | Constructie PK (moot 4) | 1.10.4 |  |  | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 | 105
68 | Afgifte plannen | 1.10.4.1 | 74SF-5w 4d |  | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
71 | Grondwerken | 1.10.4.2 |  |  | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 | 7.375
70 | Graafwerken | 1.10.4.2.1 |  | SS72;FS89 | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 7.375
73 | Vloerplaat | 1.10.4.3 |  |  | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 | 10.375
72 | Werkvloer | 1.10.4.3.1 | 70SS | SS74 | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
74 | Wapening vloerplaat | 1.10.4.3.2 | 72SS;150FS | FS75;SF68-5w 4d | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 7.375
75 | Vloerplaat | 1.10.4.3.3 | 74FS | FS76;FS78 | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
77 | Wanden/kolommen | 1.10.4.4 |  |  | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 | 16.375
76 | Kolommen | 1.10.4.4.1 | 75FS | FS82 | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2.375
78 | Wapening wanden | 1.10.4.4.2 | 75FS | FS79;FS80 | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2.375
79 | Wanden | 1.10.4.4.3 | 78FS | FS98 | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 13.375
80 | Wapening talud | 1.10.4.4.4 | 78FS | FS81 | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 3.375
81 | Betontalud | 1.10.4.4.5 | 80FS |  | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 0.375
83 | Dakplaat | 1.10.4.5 |  |  | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 | 45.375
82 | Balken | 1.10.4.5.1 | 76FS |  | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 4.375
84 | Dakplaat | 1.10.4.5.2 | 65FS | SS85;FS103 | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 34.375
85 | Wapening dakplaat | 1.10.4.5.3 | 84SS | FS86 | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 28.375
86 | Beton dakplaat | 1.10.4.5.4 | 85FS |  | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 3.375
88 | Constructie PK (moot 5,6) | 1.10.5 |  |  | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 | 113
87 | Afgifte plannen | 1.10.5.1 | 93SF-3w 4d |  | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
90 | Grondwerk | 1.10.5.2 |  |  | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 | 7.375
89 | Graafwerken | 1.10.5.2.1 | 70FS | FS91 | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 7.375
92 | Vloerplaat | 1.10.5.3 |  |  | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 | 17.375
91 | Werkvloer | 1.10.5.3.1 | 89FS | FS93 | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 1.375
93 | Wapening vloerplaat | 1.10.5.3.2 | 91FS | FS94;SF87-3w 4d | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 7.375
94 | Vloerplaat | 1.10.5.3.3 | 93FS | FS95;FS97 | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 7.375
96 | Wanden/kolommen | 1.10.5.4 |  |  | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 | 32.375
95 | Kolommen | 1.10.5.4.1 | 94FS | FS101 | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 25.375
97 | Wapening wanden | 1.10.5.4.2 | 94FS | FS99 | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 24.375
98 | Wanden | 1.10.5.4.3 | 79FS |  | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 27.375
99 | Wapening talud | 1.10.5.4.4 | 97FS | FS100 | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 3.375
100 | Betontalud | 1.10.5.4.5 | 99FS |  | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 1.375
102 | Dakplaat | 1.10.5.5 |  |  | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 | 42.375
101 | Balken | 1.10.5.5.1 | 95FS |  | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 5.375
103 | Dakplaat | 1.10.5.5.2 | 84FS | FS104-4d | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 35.375
104 | Wapening dakplaat | 1.10.5.5.3 | 103FS-4d | FS105 | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 7.375
105 | Beton dakplaat | 1.10.5.5.4 | 104FS |  | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 1.375
126 | Constructie PK (moot 7) | 1.10.6 |  |  | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 | 74
125 | Afgifte plannen | 1.10.6.1 | 131SF-3w 4d |  | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
128 | Grondwerk | 1.10.6.2 |  |  | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 | 1.375
127 | Graafwerk | 1.10.6.2.1 | 172FF | SS129 | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 1.375
130 | Vloerplaat | 1.10.6.3 |  |  | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 | 12.375
129 | Werkvloer | 1.10.6.3.1 | 127SS | FS131 | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
131 | Wapening vloerplaat | 1.10.6.3.2 | 129FS | FS132;SF125-3w 4d | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 4.375
132 | Vloerplaat | 1.10.6.3.3 | 131FS | FS133;FS135 | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 1.375
134 | Wanden/kolommen | 1.10.6.4 |  |  | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 | 15.375
133 | Kolommen | 1.10.6.4.1 | 132FS | FS139 | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 1.375
135 | Wapening wanden | 1.10.6.4.2 | 132FS | FS136;FS137 | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 1.375
136 | Wanden | 1.10.6.4.3 | 135FS | FS141 | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 11.375
137 | Wapening talud | 1.10.6.4.4 | 135FS | FS138 | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2.375
138 | Betontalud | 1.10.6.4.5 | 137FS |  | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2.375
140 | Dakplaat | 1.10.6.5 |  |  | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 | 32.375
139 | Balken | 1.10.6.5.1 | 133FS |  | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 8.375
141 | Dakplaat | 1.10.6.5.2 | 136FS | FS142 | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 11.375
142 | Dakplaat wapening | 1.10.6.5.3 | 141FS | FS143 | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 3.375
143 | Dakplaat beton | 1.10.6.5.4 | 142FS |  | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 0.375
145 | Constructie PK (uitrit) | 1.10.7 |  |  | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 | 50
144 | Afgifte plannen | 1.10.7.1 | 150SF-3w 4d |  | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
147 | Grondwerk | 1.10.7.2 |  |  | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 | 0.375
146 | Graafwerk | 1.10.7.2.1 | 228FF | FS148 | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 0.375
149 | Vloerplaat | 1.10.7.3 |  |  | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 | 6.375
148 | Werkvloer | 1.10.7.3.1 | 146FS | FS150 | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
150 | Wapening vloerplaat | 1.10.7.3.2 | 148FS | FS74;FS151;SF144-3w 4d | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 4.375
151 | Beton vloerplaat | 1.10.7.3.3 | 150FS | FS152;FS154 | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
153 | Wanden | 1.10.7.4 |  |  | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 | 13.375
152 | Wanden | 1.10.7.4.1 | 151FS | SS155 | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 13.375
154 | Wapening wanden | 1.10.7.4.2 | 151FS |  | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 5.375
156 | Dakplaat | 1.10.7.5 |  |  | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 | 5.375
155 | Dakplaat | 1.10.7.5.1 | 152SS | FS157 | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 1.375
157 | Wapening dakplaat | 1.10.7.5.2 | 155FS | FS158 | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 0.375
158 | Beton dakplaat | 1.10.7.5.3 | 157FS | FS236;FS232-4d | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 0.375
160 | Constructie PK (inrit) | 1.10.8 |  |  | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 | 41
159 | Afgifte plannen | 1.10.8.1 | 165SF-3d;241FS |  | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
162 | Grondwerk | 1.10.8.2 |  |  | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 | 1.375
161 | Graafwerk | 1.10.8.2.1 | 241FS | FS163 | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 1.375
164 | Vloerplaat | 1.10.8.3 |  |  | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 | 21.375
163 | Werkvloer | 1.10.8.3.1 | 161FS | FS165 | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
165 | Tech. kelder | 1.10.8.3.2 | 163FS | FS166;SF159-3d | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 9.375
166 | Wapening vloerplaat | 1.10.8.3.3 | 165FS | FS167 | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2.375
167 | Beton vloerplaat | 1.10.8.3.4 | 166FS | FS168;FS170 | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 0.375
169 | Wanden | 1.10.8.4 |  |  | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 | 14.375
168 | Wapening wanden | 1.10.8.4.1 | 167FS | SS171;SS172 | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 1.375
170 | Wapening waterpartij | 1.10.8.4.2 | 167FS |  | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 1.375
171 | Wanden | 1.10.8.4.3 | 168SS | FS173 | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 7.375
172 | Waterpartij | 1.10.8.4.4 | 168SS | FF127 | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 13.375
174 | Dakplaat | 1.10.8.5 |  |  | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 | 5.375
173 | Dakplaat | 1.10.8.5.1 | 171FS | FS175 | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 1.375
175 | Wapening dakplaat | 1.10.8.5.2 | 173FS | FS176 | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 0.375
176 | Beton dakplaat | 1.10.8.5.3 | 175FS |  | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 0.375
282 | Afwerking parking - technieken | 1.10.9 |  |  | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 | 214.375
281 | Technieken | 1.10.9.1 |  |  | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 | 214.375
280 | Elektriciteit en parkeerbeheersysteem | 1.10.9.1.1 |  |  | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 214.375
283 | Sanitair | 1.10.9.1.2 |  | FF289 | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 | 32.375
284 | Waterpartij | 1.10.9.1.3 |  |  | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 | 11.375
286 | Afwerking | 1.10.9.2 |  |  | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 | 65.375
285 | Bedrijfsvloer | 1.10.9.2.1 |  | FS287;FS288 | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 | 8.375
287 | Harsgietmortelvloer | 1.10.9.2.2 | 285FS |  | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 | 5.375
288 | Schilderwerken | 1.10.9.2.3 | 285FS | FS290 | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 | 27.375
289 | Afwerking sanitair | 1.10.9.2.4 | 283FF |  | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 | 15.375
290 | Belijning en pictogrammen | 1.10.9.2.5 | 288FS |  | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 | 28.375
291 | Talud bekleding | 1.10.9.3 |  |  | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 70.375
192 | Wegenis- en rioleringswerken | 1.11 |  |  | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 | 399.375
191 | Fase 1 | 1.11.1 |  |  | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 | 29.375
190 | Fase 1.1 | 1.11.1.1 |  |  | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 | 8.375
189 | Openbreken verharding straat A | 1.11.1.1.1 |  | SS193;FS194;SS203 | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 4.375
193 | RW bypass | 1.11.1.1.2 | 189SS | FS194 | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 5.375
195 | Fase 1.2 | 1.11.1.2 |  |  | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 | 5.375
194 | Openbreken riolering bypass (aan O1) | 1.11.1.2.1 | 189FS;193FS | FS196;SS197 | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 1.375
196 | Demontage standbeeld | 1.11.1.2.2 | 194FS |  | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 3.375
198 | Fase 1.3 | 1.11.1.3 |  |  | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 | 5.375
197 | Bouwput O1 | 1.11.1.3.1 | 194SS | FS199 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 5.375
200 | Fase 1.4 | 1.11.1.4 |  |  | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 | 29.375
199 | Constructie O1 (gedeeltelijke prefab) | 1.11.1.4.1 | 197FS | SS201 | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 13.375
201 | Aanleg riolering D11 - O1 | 1.11.1.4.2 | 199SS | FS202;FS204 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 3.375
202 | Constructie V3 en V4 | 1.11.1.4.3 | 201FS | FS210 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 7.375
203 | Openbreken verharding stadsplein (PK) | 1.11.1.4.4 | 189SS |  | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 9.375
206 | Fase 2 | 1.11.2 |  |  | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 | 59.375
205 | Fase 2.1 | 1.11.2.1 |  |  | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 | 9.375
204 | Aanleg riolering O1 - D8' | 1.11.2.1.1 | 201FS | FS207;FS208 | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 1.375
207 | Constructie V1 | 1.11.2.1.2 | 204FS | FS209 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 4.375
208 | Aanleg riolering O1 - D10 | 1.11.2.1.3 | 204FS |  | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 4.375
209 | Constructie V2 | 1.11.2.1.4 | 207FS | FS211 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2.375
210 | Openbreken verharding straat B | 1.11.2.1.5 | 202FS |  | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 0.375
212 | Fase 2.2 | 1.11.2.2 |  |  | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 | 3.375
211 | Opschuimen/opbreken D10 - D11 | 1.11.2.2.1 | 209FS | FS213 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 0.375
213 | Opschuimen/opbreken D1 - D8' | 1.11.2.2.2 | 211FS | FS214 | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 0.375
215 | Fase 2.3 | 1.11.2.3 |  |  | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 | 45.375
214 | Aanleg riolering O1 - wacht | 1.11.2.3.1 | 213FS | FS216 | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2.375
216 | Aanleg riolering D8 - D7 | 1.11.2.3.2 | 214FS | FS217 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 3.375
217 | Aanleg riolering D7 - D6 | 1.11.2.3.3 | 216FS | FS218 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 0.375
218 | Aanleg riolering O1 - R1 | 1.11.2.3.4 | 217FS | FS219;SS220 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 6.375
219 | Aanleg riolering O1 - D2 | 1.11.2.3.5 | 218FS | FS221 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 8.375
220 | Aanleg def verharding kruispunt | 1.11.2.3.6 | 218SS | FS225 | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 37.375
223 | Fase 3 | 1.11.3 |  |  | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 | 5.375
222 | Fase 3.1 | 1.11.3.1 |  |  | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 | 5.375
221 | Aanleg riolering R1 - R2 | 1.11.3.1.1 | 219FS | FS224 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 3.375
224 | Aanleg riolering D2 - D3 | 1.11.3.1.2 | 221FS |  | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 1.375
227 | Fase 4 | 1.11.4 |  |  | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 | 113.375
226 | Fase 4.1 | 1.11.4.1 |  |  | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 | 45.375
225 | Opbraak verharding straat C | 1.11.4.1.1 | 220FS | FS229 | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 3.375
228 | Start werken straat aan uitrit | 1.11.4.1.2 | 230SS | FF146 | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
229 | Aanleg riolering R2 - R3 | 1.11.4.1.3 | 225FS | FS230 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 12.375
230 | Aanleg riolering R3 - O2 - wacht | 1.11.4.1.4 | 229FS | SS228;FS231;FS233 | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 11.375
231 | Aanleg riolering D3 - D4 | 1.11.4.1.5 | 230FS | SS234;SS239;FS232 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 6.375
232 | Aanleg riolering D4 - D5 - aansluiting | 1.11.4.1.6 | 158FS-4d;231FS | FS236 | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 7.375
233 | Constructie O2 | 1.11.4.1.7 | 230FS |  | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 13.375
235 | Fase 4.2 | 1.11.4.2 |  |  | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 | 27.375
234 | Opbraak en aansluitingen bestaande riolering | 1.11.4.2.1 | 231SS |  | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 27.375
237 | Fase 4.3 | 1.11.4.3 |  |  | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 | 11.375
236 | Aanleg riolering O2 - R4 | 1.11.4.3.1 | 158FS;232FS | FS238 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 5.375
238 | Aanleg riolering R4 - R5 | 1.11.4.3.2 | 236FS | FS261 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 5.375
240 | Fase 4.5 | 1.11.4.4 |  |  | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 | 77.375
239 | Aanleg verharding straat C | 1.11.4.4.1 | 231SS | FS241;FS261 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 77.375
241 | Openstelling straat C | 1.11.5 | 239FS | FS161;FS242;FS159 | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
244 | Fase 5 + 6 | 1.11.6 |  |  | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 | 92.375
243 | Fase 5.1 | 1.11.6.1 |  |  | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 | 25.375
242 | Sonderen bestaande leidingen | 1.11.6.1.1 | 241FS | FS245 | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 6.375
245 | Opbraak rest. riolering stadsplein | 1.11.6.1.2 | 242FS | FS246 | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 0.375
246 | Opbraak verharding stadsplein (PK) | 1.11.6.1.3 | 245FS | FS247 | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 7.375
247 | Opbraak wegverharding NO stadsplein | 1.11.6.1.4 | 246FS | FS248;FS251 | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 7.375
249 | Fase 5.2 | 1.11.6.2 |  |  | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 | 7.375
248 | Aanleg riolering R15 - R17 | 1.11.6.2.1 | 247FS | FS250 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2.375
250 | Aanleg riolering D6 - D7 | 1.11.6.2.2 | 248FS | FS251 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 4.375
252 | Fase 5.3 | 1.11.6.3 |  |  | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 | 58.375
251 | Aanleg wegverharding NO stadsplein | 1.11.6.3.1 | 247FS;250FS | FS253 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 58.375
255 | Fase 7 | 1.11.7 |  |  | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 | 74.375
254 | Fase 7.1 | 1.11.7.1 |  |  | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 | 4.375
253 | Opbraak wegverharding N stadsplein | 1.11.7.1.1 | 251FS | FS256 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 4.375
257 | Fase 7.2 | 1.11.7.2 |  |  | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 | 10.375
256 | Aanleg riolering R7 - R6 - R5 | 1.11.7.2.1 | 253FS | FS258 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 4.375
258 | Aanleg riolering D12 - D12' | 1.11.7.2.2 | 256FS | FS259 | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 3.375
260 | Fase 7.3 | 1.11.7.3 |  |  | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 | 39.375
259 | Aanleg wegverharding N stadsplein | 1.11.7.3.1 | 258FS |  | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 39.375
262 | Pleinafwerking | 1.11.8 |  |  | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 | 180.375
261 | Hoofdkant | 1.11.8.1 | 238FS;239FS | FS263 | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 70.375
263 | Overige | 1.11.8.2 | 261FS | FS264 | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 105.375
264 | Straatmeubilair en aanplanting | 1.11.9 | 263FS |  | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 | 20.375
293 | Liften | 1.11.10 |  |  | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 | 49.375
292 | Constructie | 1.11.10.1 |  |  | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 | 9.375
294 | Glas | 1.11.10.2 |  | FS295 | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 | 7.375
295 | Liftkooi | 1.11.10.3 | 294FS |  | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 | 41.375
297 | Promenade | 1.11.11 |  |  | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 | 140.375
296 | Dakdichting | 1.11.11.1 |  | FS301 | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 22.375
298 | Beschermbeton | 1.11.11.2 |  |  | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 19.375
299 | Zitbanken | 1.11.11.3 |  |  | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 0.375
300 | Bevestigingsprofielen glazen leuningen | 1.11.11.4 |  |  | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 20.375
301 | Houten promenade | 1.11.11.5 | 296FS |  | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 117.375
302 | Glazen leuningen | 1.11.11.6 |  |  | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 70.375
303 | Plaatsen prefabtrappen | 1.11.11.7 |  |  | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 | 8.375
305 | Bruggen + luifels | 1.11.12 |  |  | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 | 86.375
304 | Constructie | 1.11.12.1 |  | FS306 | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 41.375
306 | Glas | 1.11.12.2 | 304FS |  | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 | 44.375
308 | Straat A | 1.11.13 |  |  | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 | 34.375
307 | Uitbreken wegverharding + maken koffer | 1.11.13.1 |  | FS309 | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 6.375
309 | Riolering + huisaansluitingen | 1.11.13.2 | 307FS | FS310 | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 | 20.375
310 | Kantstroken | 1.11.13.3 | 309FS | FS311 | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 | 1.375
311 | Wegverharding | 1.11.13.4 | 310FS |  | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 | 4.375
312 | Herstellen voetpad verharding aan bouwwerven | 1.11.13.5 |  |  | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 | 6.375
314 | Busperrons | 1.11.14 |  |  | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 | 28.375
313 | Vrijgraven fundering kant | 1.11.14.1 |  | FS315 | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 | 2.375
315 | Boren ankers | 1.11.14.2 | 313FS | FS316 | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 | 2.375
316 | Plaatsen constructie + ondergieten | 1.11.14.3 | 315FS | SS317 | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 | 20.375
317 | Leggen klinkers | 1.11.14.4 | 316SS |  | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 | 13.375
318 | Plaatsen glas | 1.11.14.5 |  |  | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 | 13.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Town Square | 6288h |  |  |  |  | 99 | 100 | 101
1 | Gemeenteraadsbeslissing 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Collegebeslissing 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Collegebeslissing 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Gemeenteraadsbeslissing 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Collegebeslissing 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Gemeenteraadsbeslissing 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Begin werken | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Werfinrichting | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Bemaling | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Halfondergrondse parking | 1928h |  |  |  |  | 99 | 100 | 101
11 | Constructie PK (moot 1) | 712h |  |  |  |  | 99 | 100 | 101
10 | Afgifte plannen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Grondwerk | 120h |  |  |  |  | 99 | 100 | 101
13 | Graafwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Vloerplaat | 104h |  |  |  |  | 99 | 100 | 101
15 | Werkvloer | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Wapening vloerplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Vloerplaat | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Wanden/kolommen | 144h |  |  |  |  | 99 | 100 | 101
19 | Kolommen | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Wapening wanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Wanden | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Wapening talud | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Betontalud | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Dakplaat | 456h |  |  |  |  | 99 | 100 | 101
25 | Balken | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Dakplaat | 272h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Wapening dakplaat | 272h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Beton dakplaat | 272h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Constructie PK (moot 2) | 640h |  |  |  |  | 99 | 100 | 101
30 | Afgifte plannen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Grondwerk | 24h |  |  |  |  | 99 | 100 | 101
32 | Graafwerken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Vloerplaat | 64h |  |  |  |  | 99 | 100 | 101
34 | Werkvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Wapening vloerplaat | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Wanden/kolommen | 72h |  |  |  |  | 99 | 100 | 101
38 | Kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Wapening wanden | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Wanden | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Wapening talud | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Betontalud | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Dakplaat | 416h |  |  |  |  | 99 | 100 | 101
44 | Balken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Dakplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Wapening dakplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Beton dakplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Constructie PK (moot 3) | 696h |  |  |  |  | 99 | 100 | 101
49 | Afgifte plannen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Grondwerk | 24h |  |  |  |  | 99 | 100 | 101
51 | Graafwerken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Vloerplaat | 64h |  |  |  |  | 99 | 100 | 101
53 | Werkvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Wapening vloerplaat | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Wanden/kolommen | 96h |  |  |  |  | 99 | 100 | 101
57 | Kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Wapening wanden | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Wanden | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Wapening talud | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Betontalud | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Dakplaat | 480h |  |  |  |  | 99 | 100 | 101
63 | Balken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Dakplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Wapening dakplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Beton dakplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Constructie PK (moot 4) | 448h |  |  |  |  | 99 | 100 | 101
68 | Afgifte plannen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Grondwerken | 48h |  |  |  |  | 99 | 100 | 101
70 | Graafwerken | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | Vloerplaat | 56h |  |  |  |  | 99 | 100 | 101
72 | Werkvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Wapening vloerplaat | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | Vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | Wanden/kolommen | 104h |  |  |  |  | 99 | 100 | 101
76 | Kolommen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | Wapening wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | Wanden | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | Wapening talud | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | Betontalud | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Dakplaat | 136h |  |  |  |  | 99 | 100 | 101
82 | Balken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | Dakplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | Wapening dakplaat | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | Beton dakplaat | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | Constructie PK (moot 5,6) | 512h |  |  |  |  | 99 | 100 | 101
87 | Afgifte plannen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | Grondwerk | 48h |  |  |  |  | 99 | 100 | 101
89 | Graafwerken | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | Vloerplaat | 112h |  |  |  |  | 99 | 100 | 101
91 | Werkvloer | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Wapening vloerplaat | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | Vloerplaat | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | Wanden/kolommen | 64h |  |  |  |  | 99 | 100 | 101
95 | Kolommen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | Wapening wanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | Wanden | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | Wapening talud | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | Betontalud | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | Dakplaat | 240h |  |  |  |  | 99 | 100 | 101
101 | Balken | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | Dakplaat | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | Wapening dakplaat | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | Beton dakplaat | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | Constructie PK (moot 7) | 408h |  |  |  |  | 99 | 100 | 101
125 | Afgifte plannen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | Grondwerk | 16h |  |  |  |  | 99 | 100 | 101
127 | Graafwerk | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | Vloerplaat | 64h |  |  |  |  | 99 | 100 | 101
129 | Werkvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | Wapening vloerplaat | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | Vloerplaat | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | Wanden/kolommen | 80h |  |  |  |  | 99 | 100 | 101
133 | Kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | Wapening wanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | Wanden | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | Wapening talud | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | Betontalud | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | Dakplaat | 184h |  |  |  |  | 99 | 100 | 101
139 | Balken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | Dakplaat | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | Dakplaat wapening | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | Dakplaat beton | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | Constructie PK (uitrit) | 264h |  |  |  |  | 99 | 100 | 101
144 | Afgifte plannen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | Grondwerk | 8h |  |  |  |  | 99 | 100 | 101
146 | Graafwerk | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | Vloerplaat | 40h |  |  |  |  | 99 | 100 | 101
148 | Werkvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | Wapening vloerplaat | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | Beton vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | Wanden | 80h |  |  |  |  | 99 | 100 | 101
152 | Wanden | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | Wapening wanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | Dakplaat | 32h |  |  |  |  | 99 | 100 | 101
155 | Dakplaat | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | Wapening dakplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | Beton dakplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | Constructie PK (inrit) | 232h |  |  |  |  | 99 | 100 | 101
159 | Afgifte plannen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | Grondwerk | 16h |  |  |  |  | 99 | 100 | 101
161 | Graafwerk | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | Vloerplaat | 128h |  |  |  |  | 99 | 100 | 101
163 | Werkvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | Tech. kelder | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
166 | Wapening vloerplaat | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
167 | Beton vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
169 | Wanden | 88h |  |  |  |  | 99 | 100 | 101
168 | Wapening wanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
170 | Wapening waterpartij | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
171 | Wanden | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
172 | Waterpartij | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
174 | Dakplaat | 32h |  |  |  |  | 99 | 100 | 101
173 | Dakplaat | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
175 | Wapening dakplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
176 | Beton dakplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
282 | Afwerking parking - technieken | 1120h |  |  |  |  | 99 | 100 | 101
281 | Technieken | 1120h |  |  |  |  | 99 | 100 | 101
280 | Elektriciteit en parkeerbeheersysteem | 1120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
283 | Sanitair | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
284 | Waterpartij | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
286 | Afwerking | 280h |  |  |  |  | 99 | 100 | 101
285 | Bedrijfsvloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
287 | Harsgietmortelvloer | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
288 | Schilderwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
289 | Afwerking sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
290 | Belijning en pictogrammen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
291 | Talud bekleding | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
192 | Wegenis- en rioleringswerken | 2000h |  |  |  |  | 99 | 100 | 101
191 | Fase 1 | 176h |  |  |  |  | 99 | 100 | 101
190 | Fase 1.1 | 56h |  |  |  |  | 99 | 100 | 101
189 | Openbreken verharding straat A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
193 | RW bypass | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
195 | Fase 1.2 | 32h |  |  |  |  | 99 | 100 | 101
194 | Openbreken riolering bypass (aan O1) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
196 | Demontage standbeeld | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
198 | Fase 1.3 | 32h |  |  |  |  | 99 | 100 | 101
197 | Bouwput O1 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
200 | Fase 1.4 | 176h |  |  |  |  | 99 | 100 | 101
199 | Constructie O1 (gedeeltelijke prefab) | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
201 | Aanleg riolering D11 - O1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
202 | Constructie V3 en V4 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
203 | Openbreken verharding stadsplein (PK) | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
206 | Fase 2 | 328h |  |  |  |  | 99 | 100 | 101
205 | Fase 2.1 | 64h |  |  |  |  | 99 | 100 | 101
204 | Aanleg riolering O1 - D8' | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
207 | Constructie V1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
208 | Aanleg riolering O1 - D10 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
209 | Constructie V2 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
210 | Openbreken verharding straat B | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
212 | Fase 2.2 | 16h |  |  |  |  | 99 | 100 | 101
211 | Opschuimen/opbreken D10 - D11 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
213 | Opschuimen/opbreken D1 - D8' | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
215 | Fase 2.3 | 248h |  |  |  |  | 99 | 100 | 101
214 | Aanleg riolering O1 - wacht | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
216 | Aanleg riolering D8 - D7 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
217 | Aanleg riolering D7 - D6 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
218 | Aanleg riolering O1 - R1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
219 | Aanleg riolering O1 - D2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
220 | Aanleg def verharding kruispunt | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
223 | Fase 3 | 32h |  |  |  |  | 99 | 100 | 101
222 | Fase 3.1 | 32h |  |  |  |  | 99 | 100 | 101
221 | Aanleg riolering R1 - R2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
224 | Aanleg riolering D2 - D3 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
227 | Fase 4 | 504h |  |  |  |  | 99 | 100 | 101
226 | Fase 4.1 | 248h |  |  |  |  | 99 | 100 | 101
225 | Opbraak verharding straat C | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
228 | Start werken straat aan uitrit | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
229 | Aanleg riolering R2 - R3 | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
230 | Aanleg riolering R3 - O2 - wacht | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
231 | Aanleg riolering D3 - D4 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
232 | Aanleg riolering D4 - D5 - aansluiting | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
233 | Constructie O2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
235 | Fase 4.2 | 160h |  |  |  |  | 99 | 100 | 101
234 | Opbraak en aansluitingen bestaande riolering | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
237 | Fase 4.3 | 64h |  |  |  |  | 99 | 100 | 101
236 | Aanleg riolering O2 - R4 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
238 | Aanleg riolering R4 - R5 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
240 | Fase 4.5 | 320h |  |  |  |  | 99 | 100 | 101
239 | Aanleg verharding straat C | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
241 | Openstelling straat C | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
244 | Fase 5 + 6 | 512h |  |  |  |  | 99 | 100 | 101
243 | Fase 5.1 | 144h |  |  |  |  | 99 | 100 | 101
242 | Sonderen bestaande leidingen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
245 | Opbraak rest. riolering stadsplein | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
246 | Opbraak verharding stadsplein (PK) | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
247 | Opbraak wegverharding NO stadsplein | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
249 | Fase 5.2 | 48h |  |  |  |  | 99 | 100 | 101
248 | Aanleg riolering R15 - R17 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
250 | Aanleg riolering D6 - D7 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
252 | Fase 5.3 | 320h |  |  |  |  | 99 | 100 | 101
251 | Aanleg wegverharding NO stadsplein | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
255 | Fase 7 | 352h |  |  |  |  | 99 | 100 | 101
254 | Fase 7.1 | 40h |  |  |  |  | 99 | 100 | 101
253 | Opbraak wegverharding N stadsplein | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
257 | Fase 7.2 | 72h |  |  |  |  | 99 | 100 | 101
256 | Aanleg riolering R7 - R6 - R5 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
258 | Aanleg riolering D12 - D12' | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
260 | Fase 7.3 | 240h |  |  |  |  | 99 | 100 | 101
259 | Aanleg wegverharding N stadsplein | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
262 | Pleinafwerking | 920h |  |  |  |  | 99 | 100 | 101
261 | Hoofdkant | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
263 | Overige | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
264 | Straatmeubilair en aanplanting | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
293 | Liften | 288h |  |  |  |  | 99 | 100 | 101
292 | Constructie | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
294 | Glas | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
295 | Liftkooi | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
297 | Promenade | 696h |  |  |  |  | 99 | 100 | 101
296 | Dakdichting | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
298 | Beschermbeton | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
299 | Zitbanken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
300 | Bevestigingsprofielen glazen leuningen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
301 | Houten promenade | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
302 | Glazen leuningen | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
303 | Plaatsen prefabtrappen | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
305 | Bruggen + luifels | 480h |  |  |  |  | 99 | 100 | 101
304 | Constructie | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
306 | Glas | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
308 | Straat A | 200h |  |  |  |  | 99 | 100 | 101
307 | Uitbreken wegverharding + maken koffer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
309 | Riolering + huisaansluitingen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
310 | Kantstroken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
311 | Wegverharding | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
312 | Herstellen voetpad verharding aan bouwwerven | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
314 | Busperrons | 168h |  |  |  |  | 99 | 100 | 101
313 | Vrijgraven fundering kant | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
315 | Boren ankers | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
316 | Plaatsen constructie + ondergieten | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
317 | Leggen klinkers | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
318 | Plaatsen glas | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2004-04-04 17:00 |  | TP Name | 04/04, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 571d | [5 empty] | 784812.4297 |  | 16.79% |  | 1917382.2775 | 2432704.33
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 111555.2266 | 0 | 123688.3467 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1019.4274 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 111555.2266 | 0 | 123688.3467 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1019.4274 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 111555.2266 | 0 | 123688.3467 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1019.4274 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 111555.2266 | 0 | 123688.3467 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1019.4274 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 111555.2266 | 0 | 123688.3467 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1019.4274 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 111555.2266 | 0 | 123688.3467 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1019.4274 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -448174 | 0 | 38218.0938 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 7.8575 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -80575.8672 | 0 | 449.6406 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 0.55494 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 23d | [5 empty] | 1091.9873 |  | 12.48% |  | 619369.2402 | 1119045.4128
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 23d | [5 empty] | 1091.9873 |  | 55.08% |  | 619369.2402 | 782234.2086
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 481.75 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -157040.8281 | 0 | 481.75 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 0.30583 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 10d | [5 empty] | 610.2373 |  | 97.95% |  | 461846.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 2d | -12107.7998 | 0 | 289.0498 | 0 | 85.71% | Started | 12396.8496 | 12396.8496 | 100 | 133.3333 | 85.7143 | 100 | 2.3316 | 85.7143
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 7d | -449128.625 | 0 | 321.1875 | 0 | 58.82% | Started | 449449.8125 | 449449.8125 | 100 | 100 | 58.8235 | 100 | 0.071462 | 58.8235
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 |  | 0 | 0 | 9642 | 7d | 0 | 0 | 0 | 9642 | 0% | Not Started | 0 | 9642 | 100 |  | 0 | 100 |  | 0
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 |  | 0 | 0 | 11706.1602 | 6d | 0 | 0 | 0 | 11706.1602 | 0% | Not Started | 0 | 11706.1602 | 100 |  | 0 | 100 |  | 0
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 37948.4688 | 100 |  | 0 | 100 |  | 0
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 |  | 0 | 0 | 57553.0703 | 18d | 0 | 0 | 0 | 57553.0703 | 0% | Not Started | 0 | 57553.0703 | 100 |  | 0 | 100 |  | 0
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 34975.1992 | 100 |  | 0 | 100 |  | 0
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 1245.9 | 100 |  | 0 | 100 |  | 0
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 9794.1699
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 |  | 0 | 0 | 9794.1699 | 6d | 0 | 0 | 0 | 9794.1699 | 0% | Not Started | 0 | 9794.1699 | 100 |  | 0 | 100 |  | 0
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 |  | 0 | 0 | 275874.625 | 34d | 0 | 0 | 0 | 275874.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 8d | [5 empty] | 0 |  | 0% |  | 0 | 169094.3171
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 |  | 0 | 0 | 31504.5195 | 3d | 0 | 0 | 0 | 31504.5195 | 0% | Not Started | 0 | 31504.5195 | 100 |  | 0 | 100 |  | 0
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 134834.9375 | 100 |  | 0 | 100 |  | 0
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 |  | 0 | 0 | 9487.1201 | 1d | 0 | 0 | 0 | 9487.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 |  | 0 | 0 | 3264.72 | 2d | 0 | 0 | 0 | 3264.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 5d | [5 empty] | 0 |  | 0% |  | 0 | 167716.8871
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 |  | 0 | 0 | 31504.5195 | 3d | 0 | 0 | 0 | 31504.5195 | 0% | Not Started | 0 | 31504.5195 | 100 |  | 0 | 100 |  | 0
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 136212.3676
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 134834.9375 | 100 |  | 0 | 100 |  | 0
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 |  | 0 | 0 | 9487.1201 | 1d | 0 | 0 | 0 | 9487.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 |  | 0 | 0 | 3264.72 | 2d | 0 | 0 | 0 | 3264.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 |  | 0 | 0 | 28461.3496 | 3d | 0 | 0 | 0 | 28461.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 |  | 0 | 0 | 4897.0898 | 3d | 0 | 0 | 0 | 4897.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 |  | 0 | 0 | 10501.5098 | 1d | 0 | 0 | 0 | 10501.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 35d | [5 empty] | 2922.6279 |  | 11.31% |  | 657796.715 | 673442.5949
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 35d | [5 empty] | 1316.7708 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 289.041 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -29115.0605 | 0 | 160.5801 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 0.54851 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -27601.6699 | 0 | 128.4609 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 0.46325 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 28d | [5 empty] | 64.23 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | -1313.72 | 0 | 64.23 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 4.6613 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 128.46 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -12237.0703 | 0 | 128.46 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 1.0389 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 835.0399 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -62168.1914 | 0 | 321.168 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 0.51396 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -24240.5703 | 0 | 64.2305 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 0.26427 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | -265.22 | 0 | 192.7 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 42.0816 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -54625.8594 | 0 | 256.9414 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 0.46816 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 19d | [5 empty] | 1605.8571 |  | 91.35% |  | 444912.5823 | 444912.5823
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 385.4016 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -17884.4102 | 0 | 64.2305 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 0.35786 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | -107.8 | 0 | 96.35 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 47.1957 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -29527.5293 | 0 | 96.3516 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 0.32525 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | -107.8 | 0 | 96.35 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 47.1957 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -5814.7402 | 0 | 32.1196 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 0.54935 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 64.2299 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -5333.9302 | 0 | 32.1099 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 0.59839 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -1771.24 | 0 | 32.12 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 1.7811 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 9d | [5 empty] | 1156.2256 |  | 90.11% |  | 383915.501 | 383915.501
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -23821.8301 | 0 | 96.3496 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 0.40283 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -16504.2891 | 0 | 64.2402 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 0.38772 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -7568 | 0 | 32.1201 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 0.42263 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 2d | -46264.7812 | 0 | 160.5781 | 0 | 71.43% | Started | 46425.3594 | 46425.3594 | 100 | 100 | 71.4286 | 100 | 0.34588 | 71.4286
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 |  | 0 | 0 | 42138.1211 | 5d | 0 | 0 | 0 | 42138.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 22d | -288600.375 | 0 | 802.9375 | 0 | 53.19% | Started | 289403.3125 | 289403.3125 | 100 | 100 | 53.1915 | 100 | 0.27745 | 53.1915
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 |  | 0 | 0 | 19158.5 | 2d | 0 | 0 | 0 | 19158.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 |  | 0 | 0 | 16777.9492 | 2d | 0 | 0 | 0 | 16777.9492 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 |  | 0 | 0 | 21329.0703 | 4d | 0 | 0 | 0 | 21329.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 |  | 0 | 0 | 63674.7188 | 7d | 0 | 0 | 0 | 63674.7188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 |  | 0 | 0 | 61943.1289 | 7d | 0 | 0 | 0 | 61943.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 |  | 0 | 0 | 38520.6914 | 5d | 0 | 0 | 0 | 38520.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 |  | 0 | 0 | 47025.7695 | 6d | 0 | 0 | 0 | 47025.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 |  | 0 | 0 | 52921.0703 | 10d | 0 | 0 | 0 | 52921.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 |  | 0 | 0 | 39283.5117 | 20d | 0 | 0 | 0 | 39283.5117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 |  | 0 | 0 | 40901.25 | 4d | 0 | 0 | 0 | 40901.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 |  | 0 | 0 | 41464.0195 | 4d | 0 | 0 | 0 | 41464.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 |  | 0 | 0 | 461553.0938 | 40d | 0 | 0 | 0 | 461553.0938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2004-05-04 17:00 |  | TP Name | 04/05, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 590d | [5 empty] | 865058.8487 |  | 22.07% |  | 2520738.6305 | 2992104.5572
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -446435.8125 | 0 | 39956.2812 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 8.2148 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -75709.0078 | 0 | 5316.5 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 6.5615 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 42d | [5 empty] | 37595.2219 |  | 23.06% |  | 1144651.0229 | 1600371.0697
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 42d | [5 empty] | 29240.7314 |  | 69.45% |  | 780988.3086 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 5696.25 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -151826.3281 | 0 | 5696.25 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 3.6161 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 9873.4893 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | -8979.1104 | 0 | 3417.7393 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 27.5694 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -445652.3125 | 0 | 3797.5 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 0.84492 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | -6983.75 | 0 | 2658.25 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 27.5695 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 14d | [5 empty] | 11392.4922 |  | 99.13% |  | 142182.8984 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 1d | -9427.6602 | 0 | 2278.5 | 0 | 93.75% | Started | 11706.1602 | 11706.1602 | 100 | 250 | 93.75 | 100 | 19.4641 | 93.75
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -36429.4688 | 0 | 1519 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 4.0028 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -50717.5781 | 0 | 6835.4922 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 11.8769 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 2d | -34215.6992 | 0 | 759.5 | 0 | 71.43% | Started | 34975.1992 | 34975.1992 | 100 | 250 | 71.4286 | 100 | 2.1715 | 71.4286
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 1245.9 | 100 |  | 0 | 100 |  | 0
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 6d | [5 empty] | 2278.5 |  | 2.782% |  | 9794.1699 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | -7515.6699 | 0 | 2278.5 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 23.2638 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 |  | 0 | 0 | 275874.625 | 34d | 0 | 0 | 0 | 275874.625 | 0% | Not Started | 0 | 275874.625 | 100 |  | 0 | 100 |  | 0
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 27d | [5 empty] | 5316.4904 |  | 57.46% |  | 194568.3972 | 237956.2665
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 1139.25 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -30365.2695 | 0 | 1139.25 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 3.6161 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 1898.7501 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 27.5695 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -133695.6875 | 0 | 1139.25 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 0.84492 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 27.5695 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 1d | [5 empty] | 2278.4902 |  | 38.83% |  | 25474.0801 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 3902.05 | 100 |  | 0 | 100 |  | 0
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -9107.3701 | 0 | 379.75 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 4.0028 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 1d | -14088.2197 | 0 | 1898.7402 | 0 | 66.67% | Started | 15986.96 | 15986.96 | 100 | 40 | 66.6667 | 100 | 11.8768 | 66.6667
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 34975.1992 | 100 |  | 0 | 100 |  | 0
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 1245.9 | 100 |  | 0 | 100 |  | 0
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3264.72
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 |  | 0 | 0 | 3264.72 | 2d | 0 | 0 | 0 | 3264.72 | 0% | Not Started | 0 | 3264.72 | 100 |  | 0 | 100 |  | 0
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 24d | [5 empty] | 3038.0001 |  | 49.94% |  | 169094.3171 | 237956.2665
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 1139.25 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -30365.2695 | 0 | 1139.25 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 3.6161 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 1898.7501 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 27.5695 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -133695.6875 | 0 | 1139.25 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 0.84492 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 27.5695 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 3902.05 | 100 |  | 0 | 100 |  | 0
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 |  | 0 | 0 | 9487.1201 | 1d | 0 | 0 | 0 | 9487.1201 | 0% | Not Started | 0 | 9487.1201 | 100 |  | 0 | 100 |  | 0
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 15986.96 | 100 |  | 0 | 100 |  | 0
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 34975.1992 | 100 |  | 0 | 100 |  | 0
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 1245.9 | 100 |  | 0 | 100 |  | 0
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3264.72
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 |  | 0 | 0 | 3264.72 | 2d | 0 | 0 | 0 | 3264.72 | 0% | Not Started | 0 | 3264.72 | 100 |  | 0 | 100 |  | 0
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 5d | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 |  | 0 | 0 | 28461.3496 | 3d | 0 | 0 | 0 | 28461.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 |  | 0 | 0 | 4897.0898 | 3d | 0 | 0 | 0 | 4897.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 |  | 0 | 0 | 10501.5098 | 1d | 0 | 0 | 0 | 10501.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 54d | [5 empty] | 37974.9686 |  | 12.65% |  | 735871.2853 | 751517.1652
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 54d | [5 empty] | 15569.7382 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 3417.75 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -27376.8906 | 0 | 1898.75 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 6.4858 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -26211.1309 | 0 | 1519 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 5.4778 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 47d | [5 empty] | 759.4999 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | -618.45 | 0 | 759.4999 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 55.1181 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 1519 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -10846.5303 | 0 | 1519 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 12.2841 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 9873.4883 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -58691.8711 | 0 | 3797.4883 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 6.077 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -23545.3008 | 0 | 759.5 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 3.1249 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 1820.58 | 0 | 2278.5 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 497.576 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -51844.8008 | 0 | 3038 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 5.5354 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 38d | [5 empty] | 20886.2411 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 4556.9999 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -17189.1406 | 0 | 759.5 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 4.2315 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 935.1 | 0 | 1139.25 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 558.0456 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -28484.6309 | 0 | 1139.25 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 3.8457 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 935.1 | 0 | 1139.25 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 558.0456 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -5467.1099 | 0 | 379.75 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 6.4949 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 759.5 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -4986.29 | 0 | 379.75 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 7.0769 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -1423.61 | 0 | 379.75 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 21.0579 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 28d | [5 empty] | 15569.7412 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -22778.9297 | 0 | 1139.25 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 4.7631 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -15809.0303 | 0 | 759.499 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 4.584 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -7220.3701 | 0 | 379.75 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 4.9966 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -44526.6094 | 0 | 1898.75 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 4.0899 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -40239.3789 | 0 | 1898.7422 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 4.506 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 3d | -279909.5625 | 0 | 9493.75 | 0 | 89.29% | Started | 289403.3125 | 289403.3125 | 100 | 100 | 89.2857 | 100 | 3.2805 | 89.2857
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 1518.9893 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 1518.9893 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -18399.0098 | 0 | 759.4902 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 3.9642 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -16018.4502 | 0 | 759.499 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 4.5268 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 |  | 0 | 0 | 21329.0703 | 4d | 0 | 0 | 0 | 21329.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 |  | 0 | 0 | 63674.7188 | 7d | 0 | 0 | 0 | 63674.7188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 |  | 0 | 0 | 61943.1289 | 7d | 0 | 0 | 0 | 61943.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 |  | 0 | 0 | 38520.6914 | 5d | 0 | 0 | 0 | 38520.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 |  | 0 | 0 | 47025.7695 | 6d | 0 | 0 | 0 | 47025.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 |  | 0 | 0 | 52921.0703 | 10d | 0 | 0 | 0 | 52921.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 |  | 0 | 0 | 39283.5117 | 20d | 0 | 0 | 0 | 39283.5117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 |  | 0 | 0 | 40901.25 | 4d | 0 | 0 | 0 | 40901.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 |  | 0 | 0 | 41464.0195 | 4d | 0 | 0 | 0 | 41464.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 |  | 0 | 0 | 461553.0938 | 40d | 0 | 0 | 0 | 461553.0938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2004-05-07 17:00 |  | TP Name | 07/05, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 593d | [5 empty] | 869236.089 |  | 22.64% |  | 2586335.8599 | 2992104.5572
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -446435.8125 | 0 | 39956.2812 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 8.2148 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -75709.0078 | 0 | 5316.5 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 6.5615 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 45d | [5 empty] | 41772.4622 |  | 24.38% |  | 1210248.2523 | 1600371.0697
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 45d | [5 empty] | 29620.4814 |  | 69.57% |  | 782234.2086 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 5696.25 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -151826.3281 | 0 | 5696.25 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 3.6161 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 9873.4893 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | -8979.1104 | 0 | 3417.7393 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 27.5694 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -445652.3125 | 0 | 3797.5 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 0.84492 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | -6983.75 | 0 | 2658.25 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 27.5695 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 11772.2422 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -9427.6602 | 0 | 2278.5 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 19.4641 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -36429.4688 | 0 | 1519 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 4.0028 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -50717.5781 | 0 | 6835.4922 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 11.8769 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -34215.6992 | 0 | 759.5 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 2.1715 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | -866.15 | 0 | 379.75 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 30.48 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 9d | [5 empty] | 2278.5 |  | 2.782% |  | 9794.1699 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | -7515.6699 | 0 | 2278.5 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 23.2638 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 |  | 0 | 0 | 275874.625 | 34d | 0 | 0 | 0 | 275874.625 | 0% | Not Started | 0 | 275874.625 | 100 |  | 0 | 100 |  | 0
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 30d | [5 empty] | 6075.9904 |  | 58.61% |  | 198470.4473 | 237956.2665
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 1139.25 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -30365.2695 | 0 | 1139.25 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 3.6161 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 1898.7501 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 27.5695 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -133695.6875 | 0 | 1139.25 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 0.84492 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 27.5695 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 4d | [5 empty] | 3037.9902 |  | 44.78% |  | 29376.1301 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 2d | -3142.55 | 0 | 759.5 | 0 | 66.67% | Started | 3902.05 | 3902.05 | 100 | 200 | 66.6667 | 100 | 19.4641 | 66.6667
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -9107.3701 | 0 | 379.75 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 4.0028 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -14088.2197 | 0 | 1898.7402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 11.8768 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 34975.1992 | 100 |  | 0 | 100 |  | 0
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 1245.9 | 100 |  | 0 | 100 |  | 0
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3264.72
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 |  | 0 | 0 | 3264.72 | 2d | 0 | 0 | 0 | 3264.72 | 0% | Not Started | 0 | 3264.72 | 100 |  | 0 | 100 |  | 0
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 27d | [5 empty] | 6075.9904 |  | 67.79% |  | 229543.5964 | 237956.2665
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 1139.25 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -30365.2695 | 0 | 1139.25 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 3.6161 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 1898.7501 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 27.5695 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -133695.6875 | 0 | 1139.25 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 0.84492 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 27.5695 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 2d | [5 empty] | 3037.9902 |  | 92.15% |  | 60449.2793 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 3902.05 | 100 |  | 0 | 100 |  | 0
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -9107.3701 | 0 | 379.75 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 4.0028 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -14088.2197 | 0 | 1898.7402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 11.8768 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 1d | -34215.6992 | 0 | 759.5 | 0 | 66.67% | Started | 34975.1992 | 34975.1992 | 100 | 100 | 66.6667 | 100 | 2.1715 | 66.6667
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 1245.9 | 100 |  | 0 | 100 |  | 0
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3264.72
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 |  | 0 | 0 | 3264.72 | 2d | 0 | 0 | 0 | 3264.72 | 0% | Not Started | 0 | 3264.72 | 100 |  | 0 | 100 |  | 0
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 8d | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 |  | 0 | 0 | 28461.3496 | 3d | 0 | 0 | 0 | 28461.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 |  | 0 | 0 | 4897.0898 | 3d | 0 | 0 | 0 | 4897.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 |  | 0 | 0 | 10501.5098 | 1d | 0 | 0 | 0 | 10501.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 57d | [5 empty] | 37974.9686 |  | 12.65% |  | 735871.2853 | 751517.1652
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 57d | [5 empty] | 15569.7382 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 3417.75 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -27376.8906 | 0 | 1898.75 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 6.4858 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -26211.1309 | 0 | 1519 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 5.4778 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 50d | [5 empty] | 759.4999 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | -618.45 | 0 | 759.4999 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 55.1181 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 1519 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -10846.5303 | 0 | 1519 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 12.2841 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 9873.4883 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -58691.8711 | 0 | 3797.4883 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 6.077 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -23545.3008 | 0 | 759.5 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 3.1249 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 1820.58 | 0 | 2278.5 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 497.576 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -51844.8008 | 0 | 3038 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 5.5354 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 20886.2411 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 4556.9999 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -17189.1406 | 0 | 759.5 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 4.2315 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 935.1 | 0 | 1139.25 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 558.0456 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -28484.6309 | 0 | 1139.25 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 3.8457 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 935.1 | 0 | 1139.25 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 558.0456 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -5467.1099 | 0 | 379.75 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 6.4949 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 759.5 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -4986.29 | 0 | 379.75 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 7.0769 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -1423.61 | 0 | 379.75 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 21.0579 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 15569.7412 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -22778.9297 | 0 | 1139.25 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 4.7631 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -15809.0303 | 0 | 759.499 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 4.584 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -7220.3701 | 0 | 379.75 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 4.9966 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -44526.6094 | 0 | 1898.75 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 4.0899 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -40239.3789 | 0 | 1898.7422 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 4.506 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -279909.5625 | 0 | 9493.75 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 3.2805 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 1518.9893 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 1518.9893 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -18399.0098 | 0 | 759.4902 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 3.9642 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -16018.4502 | 0 | 759.499 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 4.5268 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 |  | 0 | 0 | 21329.0703 | 4d | 0 | 0 | 0 | 21329.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 |  | 0 | 0 | 63674.7188 | 7d | 0 | 0 | 0 | 63674.7188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 |  | 0 | 0 | 61943.1289 | 7d | 0 | 0 | 0 | 61943.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 |  | 0 | 0 | 38520.6914 | 5d | 0 | 0 | 0 | 38520.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 |  | 0 | 0 | 47025.7695 | 6d | 0 | 0 | 0 | 47025.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 |  | 0 | 0 | 52921.0703 | 10d | 0 | 0 | 0 | 52921.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 |  | 0 | 0 | 39283.5117 | 20d | 0 | 0 | 0 | 39283.5117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 |  | 0 | 0 | 40901.25 | 4d | 0 | 0 | 0 | 40901.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 |  | 0 | 0 | 41464.0195 | 4d | 0 | 0 | 0 | 41464.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 |  | 0 | 0 | 461553.0938 | 40d | 0 | 0 | 0 | 461553.0938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2004-05-14 17:00 |  | TP Name | 14/05, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 598d | [5 empty] | 875312.0792 |  | 23.46% |  | 2679752.319 | 3077108.3462
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 111902.8594 | 0 | 124035.9795 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1022.2925 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -446435.8125 | 0 | 39956.2812 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 8.2148 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -75709.0078 | 0 | 5316.5 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 6.5615 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 50d | [5 empty] | 43671.2122 |  | 24.55% |  | 1218660.9224 | 1600371.0697
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 50d | [5 empty] | 29620.4814 |  | 69.57% |  | 782234.2086 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 5696.25 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -151826.3281 | 0 | 5696.25 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 3.6161 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 9873.4893 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | -8979.1104 | 0 | 3417.7393 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 27.5694 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -445652.3125 | 0 | 3797.5 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 0.84492 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | -6983.75 | 0 | 2658.25 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 27.5695 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 11772.2422 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -9427.6602 | 0 | 2278.5 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 19.4641 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -36429.4688 | 0 | 1519 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 4.0028 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -50717.5781 | 0 | 6835.4922 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 11.8769 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -34215.6992 | 0 | 759.5 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 2.1715 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | -866.15 | 0 | 379.75 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 30.48 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 14d | [5 empty] | 2278.5 |  | 2.782% |  | 9794.1699 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | -7515.6699 | 0 | 2278.5 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 23.2638 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 |  | 0 | 0 | 275874.625 | 34d | 0 | 0 | 0 | 275874.625 | 0% | Not Started | 0 | 275874.625 | 100 |  | 0 | 100 |  | 0
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 35d | [5 empty] | 6835.4904 |  | 59.58% |  | 201735.1672 | 237956.2665
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 1139.25 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -30365.2695 | 0 | 1139.25 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 3.6161 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 1898.7501 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 27.5695 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -133695.6875 | 0 | 1139.25 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 0.84492 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 27.5695 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 9d | [5 empty] | 3037.9902 |  | 44.78% |  | 29376.1301 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | -3142.55 | 0 | 759.5 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 19.4641 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -9107.3701 | 0 | 379.75 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 4.0028 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -14088.2197 | 0 | 1898.7402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 11.8768 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 34975.1992 | 100 |  | 0 | 100 |  | 0
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 1245.9 | 100 |  | 0 | 100 |  | 0
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 3d | [5 empty] | 759.5 |  | 3.142% |  | 3264.72 | 3264.72
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | -2505.22 | 0 | 759.5 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 23.2639 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 32d | [5 empty] | 7215.2404 |  | 69.31% |  | 234691.5465 | 237956.2665
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 1139.25 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -30365.2695 | 0 | 1139.25 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 3.6161 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 1898.7501 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 27.5695 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -133695.6875 | 0 | 1139.25 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 0.84492 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | -997.68 | 0 | 379.7501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 27.5695 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 4177.2402 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | -3142.55 | 0 | 759.5 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 19.4641 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -9107.3701 | 0 | 379.75 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 4.0028 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -14088.2197 | 0 | 1898.7402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 11.8768 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -34215.6992 | 0 | 759.5 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 2.1715 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | -866.15 | 0 | 379.75 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 30.48 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3264.72
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 |  | 0 | 0 | 3264.72 | 2d | 0 | 0 | 0 | 3264.72 | 0% | Not Started | 0 | 3264.72 | 100 |  | 0 | 100 |  | 0
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 13d | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 |  | 0 | 0 | 28461.3496 | 3d | 0 | 0 | 0 | 28461.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 |  | 0 | 0 | 4897.0898 | 3d | 0 | 0 | 0 | 4897.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 |  | 0 | 0 | 10501.5098 | 1d | 0 | 0 | 0 | 10501.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 62d | [5 empty] | 42152.2088 |  | 14.11% |  | 820875.0744 | 836520.9543
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 62d | [5 empty] | 15569.7382 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 3417.75 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -27376.8906 | 0 | 1898.75 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 6.4858 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -26211.1309 | 0 | 1519 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 5.4778 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 55d | [5 empty] | 759.4999 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | -618.45 | 0 | 759.4999 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 55.1181 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 1519 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -10846.5303 | 0 | 1519 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 12.2841 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 9873.4883 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -58691.8711 | 0 | 3797.4883 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 6.077 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -23545.3008 | 0 | 759.5 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 3.1249 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 1820.58 | 0 | 2278.5 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 497.576 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -51844.8008 | 0 | 3038 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 5.5354 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 20886.2411 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 4556.9999 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -17189.1406 | 0 | 759.5 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 4.2315 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 935.1 | 0 | 1139.25 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 558.0456 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -28484.6309 | 0 | 1139.25 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 3.8457 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 935.1 | 0 | 1139.25 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 558.0456 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -5467.1099 | 0 | 379.75 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 6.4949 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 759.5 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -4986.29 | 0 | 379.75 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 7.0769 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -1423.61 | 0 | 379.75 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 21.0579 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 15569.7412 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -22778.9297 | 0 | 1139.25 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 4.7631 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -15809.0303 | 0 | 759.499 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 4.584 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -7220.3701 | 0 | 379.75 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 4.9966 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -44526.6094 | 0 | 1898.75 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 4.0899 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -40239.3789 | 0 | 1898.7422 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 4.506 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -279909.5625 | 0 | 9493.75 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 3.2805 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 1518.9893 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 1518.9893 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -18399.0098 | 0 | 759.4902 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 3.9642 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -16018.4502 | 0 | 759.499 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 4.5268 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 5d | [5 empty] | 4177.2402 |  | 9.786% |  | 85003.7891 | 85003.7891
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 5d | [5 empty] | 4177.2402 |  | 29.78% |  | 85003.7891 | 85003.7891
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -19810.0801 | 0 | 1518.9902 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 7.1217 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 6d | -61016.4688 | 0 | 2658.25 | 0 | 53.85% | Started | 63674.7188 | 63674.7188 | 100 | 100 | 53.8462 | 100 | 4.1747 | 53.8462
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 |  | 0 | 0 | 61943.1289 | 7d | 0 | 0 | 0 | 61943.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 |  | 0 | 0 | 38520.6914 | 5d | 0 | 0 | 0 | 38520.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 |  | 0 | 0 | 47025.7695 | 6d | 0 | 0 | 0 | 47025.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 |  | 0 | 0 | 52921.0703 | 10d | 0 | 0 | 0 | 52921.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 |  | 0 | 0 | 39283.5117 | 20d | 0 | 0 | 0 | 39283.5117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 |  | 0 | 0 | 40901.25 | 4d | 0 | 0 | 0 | 40901.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 |  | 0 | 0 | 41464.0195 | 4d | 0 | 0 | 0 | 41464.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 |  | 0 | 0 | 461553.0938 | 40d | 0 | 0 | 0 | 461553.0938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2004-06-01 17:00 |  | TP Name | 01/06, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 607d | [5 empty] | 1041153.1014 |  | 24.9% |  | 2844190.2984 | 3139051.4751
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -443480.3438 | 0 | 42911.75 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 8.8225 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -67433.6328 | 0 | 13591.875 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 16.7748 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 59d | [5 empty] | 122326.9152 |  | 26.61% |  | 1321155.7728 | 1600371.0697
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 59d | [5 empty] | 75726.1935 |  | 69.57% |  | 782234.2086 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 14562.7344 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -142959.8438 | 0 | 14562.7344 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 9.2449 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 25242.0696 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | -3659.22 | 0 | 8737.6296 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 70.4827 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -439741.3125 | 0 | 9708.5 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 2.1601 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | -2846.0601 | 0 | 6795.9399 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 70.4827 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 30096.2997 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -5881.0698 | 0 | 5825.0903 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 49.7609 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -34065.0781 | 0 | 3883.3906 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 10.2333 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -40077.8008 | 0 | 17475.2695 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 30.3637 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 5.5516 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 77.9236 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 23d | [5 empty] | 5825.0898 |  | 2.782% |  | 9794.1699 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | -3969.0801 | 0 | 5825.0898 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 59.4751 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 |  | 0 | 0 | 275874.625 | 34d | 0 | 0 | 0 | 275874.625 | 0% | Not Started | 0 | 275874.625 | 100 |  | 0 | 100 |  | 0
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 44d | [5 empty] | 20387.8159 |  | 70.27% |  | 237956.2665 | 237956.2665
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 2912.5488 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -28591.9707 | 0 | 2912.5488 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 9.2449 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 4854.247 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 70.4827 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -131922.3906 | 0 | 2912.5469 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.1601 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 70.4827 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 10679.3301 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | -1960.36 | 0 | 1941.6901 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 49.7608 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -8516.2695 | 0 | 970.8506 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 10.2334 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -11132.7197 | 0 | 4854.2402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 30.3637 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 5.5516 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 77.9236 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 12d | [5 empty] | 1941.6899 |  | 3.142% |  | 3264.72 | 3264.72
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | -1323.03 | 0 | 1941.6899 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 59.4749 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 41d | [5 empty] | 20387.8159 |  | 70.27% |  | 237956.2665 | 237956.2665
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 2912.5488 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -28591.9707 | 0 | 2912.5488 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 9.2449 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 4854.247 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 70.4827 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -131922.3906 | 0 | 2912.5469 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.1601 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 70.4827 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 10679.3301 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | -1960.36 | 0 | 1941.6901 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 49.7608 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -8516.2695 | 0 | 970.8506 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 10.2334 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -11132.7197 | 0 | 4854.2402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 30.3637 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 5.5516 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 77.9236 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 9d | [5 empty] | 1941.6899 |  | 3.142% |  | 3264.72 | 3264.72
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | -1323.03 | 0 | 1941.6899 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 59.4749 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 22d | [5 empty] | 5825.0898 |  | 12.52% |  | 63009.0312 | 0
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 1d | [5 empty] | 5825.0898 |  | 100% |  | 63009.0312 | 0
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 9d | 63009.0312 | 0 | 8d | -57183.9414 | 0 | 5825.0898 | 0 | 52.94% | Started | 63009.0312 | 0 | 100 | 150 | 52.9412 | 100 | 9.2448 | 52.9412
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 |  | 0 | 0 | 28461.3496 | 3d | 0 | 0 | 0 | 28461.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 |  | 0 | 0 | 4897.0898 | 3d | 0 | 0 | 0 | 4897.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 9d | [5 empty] | 0 |  | 0% |  | 0 | 0
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 |  | 0 | 0 | 10501.5098 | 1d | 0 | 0 | 0 | 10501.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 71d | [5 empty] | 114560.0749 |  | 15.18% |  | 882818.2033 | 898464.0832
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 71d | [5 empty] | 39804.7721 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 8737.6309 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -24421.4004 | 0 | 4854.2402 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 16.5812 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -23846.7402 | 0 | 3883.3906 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 14.0042 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 64d | [5 empty] | 1941.6899 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 563.74 | 0 | 1941.6899 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 140.9115 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 3883.3906 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -8482.1396 | 0 | 3883.3906 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 31.405 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 25242.0606 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -52780.8789 | 0 | 9708.4805 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 15.5362 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -22363.0996 | 0 | 1941.7012 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 7.989 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 5367.1699 | 0 | 5825.0899 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 1272.0759 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -47116.0117 | 0 | 7766.7891 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 14.1516 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 53396.6583 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 11650.1808 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -16006.9404 | 0 | 1941.7002 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 10.8181 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 2708.3899 | 0 | 2912.5399 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1426.6667 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -26711.3301 | 0 | 2912.5508 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 9.8318 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 2708.3899 | 0 | 2912.5399 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1426.6667 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -4876.0098 | 0 | 970.8501 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 16.6046 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 1941.6898 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -4395.2002 | 0 | 970.8398 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 18.0923 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -832.51 | 0 | 970.85 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 53.8356 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 39804.7876 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -21005.6406 | 0 | 2912.5391 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 12.1771 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -14626.8301 | 0 | 1941.6992 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 11.7192 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -6629.27 | 0 | 970.8501 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 12.7741 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -41571.1211 | 0 | 4854.2383 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 10.456 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -37283.8789 | 0 | 4854.2422 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 11.5198 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -265132.0938 | 0 | 24271.2188 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 8.3866 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 3883.3789 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 3883.3789 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -17216.8105 | 0 | 1941.6895 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 10.1349 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -14836.2598 | 0 | 1941.6895 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 11.5729 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 14d | [5 empty] | 17475.2656 |  | 16.92% |  | 146946.918 | 146946.918
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 14d | [5 empty] | 17475.2656 |  | 51.49% |  | 146946.918 | 146946.918
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -17445.6797 | 0 | 3883.3906 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 18.207 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -56878.7812 | 0 | 6795.9375 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 10.6729 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 4d | -55147.1914 | 0 | 6795.9375 | 0 | 63.64% | Started | 61943.1289 | 61943.1289 | 100 | 100 | 63.6364 | 100 | 10.9713 | 63.6364
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 |  | 0 | 0 | 38520.6914 | 5d | 0 | 0 | 0 | 38520.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 |  | 0 | 0 | 47025.7695 | 6d | 0 | 0 | 0 | 47025.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 |  | 0 | 0 | 52921.0703 | 10d | 0 | 0 | 0 | 52921.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 |  | 0 | 0 | 39283.5117 | 20d | 0 | 0 | 0 | 39283.5117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 |  | 0 | 0 | 40901.25 | 4d | 0 | 0 | 0 | 40901.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 |  | 0 | 0 | 41464.0195 | 4d | 0 | 0 | 0 | 41464.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 |  | 0 | 0 | 461553.0938 | 40d | 0 | 0 | 0 | 461553.0938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2004-06-07 17:00 |  | TP Name | 07/06, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 611d | [5 empty] | 1074161.953 |  | 25.19% |  | 2877365.1499 | 3358531.6933
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -443480.3438 | 0 | 42911.75 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 8.8225 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -67433.6328 | 0 | 13591.875 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 16.7748 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 63d | [5 empty] | 155335.7668 |  | 27.28% |  | 1354330.6244 | 1819851.2878
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 63d | [5 empty] | 108735.0451 |  | 72.52% |  | 815409.0602 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 14562.7344 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -142959.8438 | 0 | 14562.7344 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 9.2449 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 25242.0696 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | -3659.22 | 0 | 8737.6296 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 70.4827 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -439741.3125 | 0 | 9708.5 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 2.1601 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | -2846.0601 | 0 | 6795.9399 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 70.4827 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 30096.2997 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -5881.0698 | 0 | 5825.0903 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 49.7609 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -34065.0781 | 0 | 3883.3906 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 10.2333 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -40077.8008 | 0 | 17475.2695 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 30.3637 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 5.5516 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 77.9236 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 27d | [5 empty] | 38833.9414 |  | 12.21% |  | 42969.0215 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | -3969.0801 | 0 | 5825.0898 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 59.4751 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 20d | 33174.8516 | 0 | 19d | -166 | 0 | 33008.8516 | 0 | 51.28% | Started | 33174.8516 | 33174.8516 | 100 | 58.8235 | 51.2821 | 100 | 99.4996 | 51.2821
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 |  | 0 | 0 | 275874.625 | 34d | 0 | 0 | 0 | 275874.625 | 0% | Not Started | 0 | 275874.625 | 100 |  | 0 | 100 |  | 0
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 48d | [5 empty] | 20387.8159 |  | 70.27% |  | 237956.2665 | 247713.576
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 2912.5488 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -28591.9707 | 0 | 2912.5488 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 9.2449 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 4854.247 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 70.4827 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -131922.3906 | 0 | 2912.5469 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.1601 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 70.4827 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 10679.3301 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | -1960.36 | 0 | 1941.6901 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 49.7608 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -8516.2695 | 0 | 970.8506 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 10.2334 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -11132.7197 | 0 | 4854.2402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 30.3637 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 5.5516 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 77.9236 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 16d | [5 empty] | 1941.6899 |  | 3.142% |  | 3264.72 | 13022.0295
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | -1323.03 | 0 | 1941.6899 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 59.4749 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 45d | [5 empty] | 20387.8159 |  | 70.27% |  | 237956.2665 | 237956.2665
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 2912.5488 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -28591.9707 | 0 | 2912.5488 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 9.2449 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 4854.247 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 70.4827 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -131922.3906 | 0 | 2912.5469 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.1601 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 70.4827 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 10679.3301 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | -1960.36 | 0 | 1941.6901 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 49.7608 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -8516.2695 | 0 | 970.8506 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 10.2334 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -11132.7197 | 0 | 4854.2402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 30.3637 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 5.5516 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 77.9236 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 13d | [5 empty] | 1941.6899 |  | 3.142% |  | 3264.72 | 3264.72
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | -1323.03 | 0 | 1941.6899 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 59.4749 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 26d | [5 empty] | 5825.0898 |  | 12.52% |  | 63009.0312 | 63009.0312
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 5d | [5 empty] | 5825.0898 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 9d | 63009.0312 | 0 | 4d | -57183.9414 | 0 | 5825.0898 | 0 | 69.23% | Started | 63009.0312 | 63009.0312 | 100 | 150 | 69.2308 | 100 | 9.2448 | 69.2308
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 |  | 0 | 0 | 28461.3496 | 3d | 0 | 0 | 0 | 28461.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 |  | 0 | 0 | 4897.0898 | 3d | 0 | 0 | 0 | 4897.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 13d | [5 empty] | 0 |  | 0% |  | 0 | 146713.8773
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 |  | 0 | 0 | 10501.5098 | 1d | 0 | 0 | 0 | 10501.5098 | 0% | Not Started | 0 | 10501.5098 | 100 |  | 0 | 100 |  | 0
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 136212.3676
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 134834.9375 | 100 |  | 0 | 100 |  | 0
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 75d | [5 empty] | 114560.0749 |  | 15.18% |  | 882818.2033 | 898464.0832
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 75d | [5 empty] | 39804.7721 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 8737.6309 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -24421.4004 | 0 | 4854.2402 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 16.5812 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -23846.7402 | 0 | 3883.3906 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 14.0042 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 68d | [5 empty] | 1941.6899 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 563.74 | 0 | 1941.6899 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 140.9115 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 3883.3906 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -8482.1396 | 0 | 3883.3906 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 31.405 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 25242.0606 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -52780.8789 | 0 | 9708.4805 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 15.5362 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -22363.0996 | 0 | 1941.7012 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 7.989 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 5367.1699 | 0 | 5825.0899 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 1272.0759 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -47116.0117 | 0 | 7766.7891 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 14.1516 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 53396.6583 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 11650.1808 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -16006.9404 | 0 | 1941.7002 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 10.8181 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 2708.3899 | 0 | 2912.5399 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1426.6667 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -26711.3301 | 0 | 2912.5508 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 9.8318 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 2708.3899 | 0 | 2912.5399 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1426.6667 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -4876.0098 | 0 | 970.8501 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 16.6046 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 1941.6898 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -4395.2002 | 0 | 970.8398 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 18.0923 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -832.51 | 0 | 970.85 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 53.8356 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 39804.7876 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -21005.6406 | 0 | 2912.5391 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 12.1771 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -14626.8301 | 0 | 1941.6992 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 11.7192 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -6629.27 | 0 | 970.8501 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 12.7741 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -41571.1211 | 0 | 4854.2383 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 10.456 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -37283.8789 | 0 | 4854.2422 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 11.5198 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -265132.0938 | 0 | 24271.2188 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 8.3866 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 3883.3789 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 3883.3789 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -17216.8105 | 0 | 1941.6895 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 10.1349 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -14836.2598 | 0 | 1941.6895 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 11.5729 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 18d | [5 empty] | 17475.2656 |  | 16.92% |  | 146946.918 | 146946.918
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 18d | [5 empty] | 17475.2656 |  | 51.49% |  | 146946.918 | 146946.918
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -17445.6797 | 0 | 3883.3906 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 18.207 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -56878.7812 | 0 | 6795.9375 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 10.6729 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -55147.1914 | 0 | 6795.9375 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 10.9713 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 |  | 0 | 0 | 38520.6914 | 5d | 0 | 0 | 0 | 38520.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 |  | 0 | 0 | 47025.7695 | 6d | 0 | 0 | 0 | 47025.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 |  | 0 | 0 | 52921.0703 | 10d | 0 | 0 | 0 | 52921.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 |  | 0 | 0 | 39283.5117 | 20d | 0 | 0 | 0 | 39283.5117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 |  | 0 | 0 | 40901.25 | 4d | 0 | 0 | 0 | 40901.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 |  | 0 | 0 | 41464.0195 | 4d | 0 | 0 | 0 | 41464.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 |  | 0 | 0 | 461553.0938 | 40d | 0 | 0 | 0 | 461553.0938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2004-06-13 17:00 |  | TP Name | 13/06, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 615d | [5 empty] | 1109112.4984 |  | 26.35% |  | 3009467.8534 | 3975752.7253
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 112493.9609 | 0 | 124627.0811 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1027.1643 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -443480.3438 | 0 | 42911.75 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 8.8225 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -67433.6328 | 0 | 13591.875 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 16.7748 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 67d | [5 empty] | 156306.6169 |  | 27.31% |  | 1355708.0544 | 2306347.0464
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 67d | [5 empty] | 108735.0451 |  | 72.52% |  | 815409.0602 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 14562.7344 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -142959.8438 | 0 | 14562.7344 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 9.2449 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 25242.0696 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | -3659.22 | 0 | 8737.6296 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 70.4827 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -439741.3125 | 0 | 9708.5 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 2.1601 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | -2846.0601 | 0 | 6795.9399 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 70.4827 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 30096.2997 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -5881.0698 | 0 | 5825.0903 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 49.7609 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -34065.0781 | 0 | 3883.3906 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 10.2333 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -40077.8008 | 0 | 17475.2695 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 30.3637 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 5.5516 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 77.9236 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 31d | [5 empty] | 38833.9414 |  | 12.21% |  | 42969.0215 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | -3969.0801 | 0 | 5825.0898 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 59.4751 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 20d | 33174.8516 | 0 | 15d | -166 | 0 | 33008.8516 | 0 | 57.14% | Started | 33174.8516 | 33174.8516 | 100 | 58.8235 | 57.1429 | 100 | 99.4996 | 57.1429
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 |  | 0 | 0 | 275874.625 | 34d | 0 | 0 | 0 | 275874.625 | 0% | Not Started | 0 | 275874.625 | 100 |  | 0 | 100 |  | 0
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 |  | 0 | 0 | 33174.8516 | 34d | 0 | 0 | 0 | 33174.8516 | 0% | Not Started | 0 | 33174.8516 | 100 |  | 0 | 100 |  | 0
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 52d | [5 empty] | 20387.8159 |  | 70.27% |  | 237956.2665 | 328853.1698
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 2912.5488 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -28591.9707 | 0 | 2912.5488 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 9.2449 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 4854.247 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 70.4827 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -131922.3906 | 0 | 2912.5469 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.1601 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 70.4827 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 10679.3301 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | -1960.36 | 0 | 1941.6901 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 49.7608 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -8516.2695 | 0 | 970.8506 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 10.2334 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -11132.7197 | 0 | 4854.2402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 30.3637 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 5.5516 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 77.9236 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 20d | [5 empty] | 1941.6899 |  | 3.142% |  | 3264.72 | 94161.6233
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | -1323.03 | 0 | 1941.6899 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 59.4749 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 81139.5938 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 49d | [5 empty] | 20387.8159 |  | 70.27% |  | 237956.2665 | 237956.2665
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 2912.5488 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -28591.9707 | 0 | 2912.5488 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 9.2449 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 4854.247 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 70.4827 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -131922.3906 | 0 | 2912.5469 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.1601 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | -406.58 | 0 | 970.8501 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 70.4827 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 10679.3301 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | -1960.36 | 0 | 1941.6901 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 49.7608 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -8516.2695 | 0 | 970.8506 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 10.2334 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -11132.7197 | 0 | 4854.2402 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 30.3637 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -33033.5 | 0 | 1941.6992 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 5.5516 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | -275.05 | 0 | 970.85 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 77.9236 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 17d | [5 empty] | 1941.6899 |  | 3.142% |  | 3264.72 | 3264.72
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | -1323.03 | 0 | 1941.6899 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 59.4749 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 30d | [5 empty] | 6795.9399 |  | 12.79% |  | 64386.4613 | 334056.3363
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 9d | [5 empty] | 5825.0898 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 5d | -57183.9414 | 0 | 5825.0898 | 0 | 73.68% | Started | 63009.0312 | 63009.0312 | 100 | 233.3333 | 73.6842 | 100 | 9.2448 | 73.6842
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 2d | [5 empty] | 970.8501 |  | 0.5056% |  | 1377.4301 | 271047.3051
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 6d | -406.58 | 0 | 970.8501 | 0 | 57.14% | Started | 1377.4301 | 1377.4301 | 100 | 800 | 57.1429 | 100 | 70.4827 | 57.1429
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 269669.875 | 100 |  | 0 | 100 |  | 0
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 |  | 0 | 0 | 28461.3496 | 3d | 0 | 0 | 0 | 28461.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 |  | 0 | 0 | 4897.0898 | 3d | 0 | 0 | 0 | 4897.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 63009.0312
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 63009.0312 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 17d | [5 empty] | 0 |  | 0% |  | 0 | 218013.7058
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 |  | 0 | 0 | 10501.5098 | 1d | 0 | 0 | 0 | 10501.5098 | 0% | Not Started | 0 | 10501.5098 | 100 |  | 0 | 100 |  | 0
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 134834.9375 | 100 |  | 0 | 100 |  | 0
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 31973.9297 | 100 |  | 0 | 100 |  | 0
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 37948.4688 | 100 |  | 0 | 100 |  | 0
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 79d | [5 empty] | 148539.7702 |  | 17.42% |  | 1013543.4767 | 1029189.3566
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 79d | [5 empty] | 39804.7721 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 8737.6309 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -24421.4004 | 0 | 4854.2402 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 16.5812 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -23846.7402 | 0 | 3883.3906 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 14.0042 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 72d | [5 empty] | 1941.6899 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 563.74 | 0 | 1941.6899 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 140.9115 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 3883.3906 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -8482.1396 | 0 | 3883.3906 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 31.405 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 25242.0606 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -52780.8789 | 0 | 9708.4805 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 15.5362 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -22363.0996 | 0 | 1941.7012 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 7.989 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 5367.1699 | 0 | 5825.0899 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 1272.0759 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -47116.0117 | 0 | 7766.7891 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 14.1516 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 53396.6583 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 11650.1808 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -16006.9404 | 0 | 1941.7002 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 10.8181 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 2708.3899 | 0 | 2912.5399 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1426.6667 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -26711.3301 | 0 | 2912.5508 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 9.8318 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 2708.3899 | 0 | 2912.5399 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1426.6667 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -4876.0098 | 0 | 970.8501 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 16.6046 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 1941.6898 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -4395.2002 | 0 | 970.8398 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 18.0923 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -832.51 | 0 | 970.85 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 53.8356 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 39804.7876 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -21005.6406 | 0 | 2912.5391 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 12.1771 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -14626.8301 | 0 | 1941.6992 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 11.7192 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -6629.27 | 0 | 970.8501 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 12.7741 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -41571.1211 | 0 | 4854.2383 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 10.456 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -37283.8789 | 0 | 4854.2422 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 11.5198 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -265132.0938 | 0 | 24271.2188 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 8.3866 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 3883.3789 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 3883.3789 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -17216.8105 | 0 | 1941.6895 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 10.1349 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -14836.2598 | 0 | 1941.6895 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 11.5729 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 22d | [5 empty] | 51454.9609 |  | 31.97% |  | 277672.1914 | 277672.1914
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 22d | [5 empty] | 32037.9883 |  | 83.52% |  | 238388.6797 | 238388.6797
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -17445.6797 | 0 | 3883.3906 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 18.207 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -56878.7812 | 0 | 6795.9375 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 10.6729 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -55147.1914 | 0 | 6795.9375 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 10.9713 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 1d | -33666.4492 | 0 | 4854.2422 | 0 | 83.33% | Started | 38520.6914 | 38520.6914 | 100 | 100 | 83.3333 | 100 | 12.6016 | 83.3333
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 |  | 0 | 0 | 47025.7695 | 6d | 0 | 0 | 0 | 47025.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 6d | -43212.5898 | 0 | 9708.4805 | 0 | 62.5% | Started | 52921.0703 | 52921.0703 | 100 | 100 | 62.5 | 100 | 18.3452 | 62.5
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 2d | [5 empty] | 19416.9727 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 18d | -19866.5391 | 0 | 19416.9727 | 0 | 52.63% | Started | 39283.5117 | 39283.5117 | 100 | 100 | 52.6316 | 100 | 49.4278 | 52.6316
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 |  | 0 | 0 | 40901.25 | 4d | 0 | 0 | 0 | 40901.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 |  | 0 | 0 | 41464.0195 | 4d | 0 | 0 | 0 | 41464.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 |  | 0 | 0 | 461553.0938 | 40d | 0 | 0 | 0 | 461553.0938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2004-06-21 17:00 |  | TP Name | 21/06, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 621d | [5 empty] | 1372464.0621 |  | 37.16% |  | 4244857.3756 | 4518043.9178
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 112797.2422 | 0 | 124930.3623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1029.6639 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 112797.2422 | 0 | 124930.3623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1029.6639 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 112797.2422 | 0 | 124930.3623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1029.6639 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 112797.2422 | 0 | 124930.3623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1029.6639 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 112797.2422 | 0 | 124930.3623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1029.6639 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 112797.2422 | 0 | 124930.3623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1029.6639 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -441963.9375 | 0 | 44428.1562 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 9.1342 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -63187.7305 | 0 | 17837.7773 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 22.015 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 73d | [5 empty] | 307064.6481 |  | 41.95% |  | 2082518.7134 | 2340059.3756
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 73d | [5 empty] | 229342.8947 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 19111.9062 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -138410.6719 | 0 | 19111.9062 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 12.1328 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 33127.3109 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | -929.71 | 0 | 11467.1396 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 92.5004 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -436708.5312 | 0 | 12741.2812 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 2.8349 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | -723.11 | 0 | 8918.89 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 92.5004 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 39497.9469 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -4061.3999 | 0 | 7644.7603 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 65.3054 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -32851.9609 | 0 | 5096.5078 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 13.4301 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -34618.7812 | 0 | 22934.2891 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 39.8489 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -32426.9395 | 0 | 2548.2598 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 7.2859 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 28.23 | 0 | 1274.13 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 102.2658 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 37d | [5 empty] | 137605.7307 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | -2149.4099 | 0 | 7644.76 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 78.0542 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 20d | 33174.8516 | 0 | 9d | 10145.4697 | 0 | 43320.3213 | 0 | 68.97% | Started | 33174.8516 | 33174.8516 | 100 | 58.8235 | 68.9655 | 100 | 130.5818 | 68.9655
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 11d | -232554.2969 | 0 | 43320.3281 | 0 | 60.71% | Started | 275874.625 | 275874.625 | 100 | 50 | 60.7143 | 100 | 15.7029 | 60.7143
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 12d | 10145.4697 | 0 | 43320.3213 | 0 | 52% | Started | 33174.8516 | 33174.8516 | 100 | 38.2353 | 52 | 100 | 130.5818 | 52
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 58d | [5 empty] | 26756.6733 |  | 70.27% |  | 237956.2665 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 3822.3887 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -27682.1309 | 0 | 3822.3887 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 12.1328 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 6370.6351 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | -103.3 | 0 | 1274.1301 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 92.5005 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -131012.5625 | 0 | 3822.375 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.8349 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | -103.3 | 0 | 1274.1301 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 92.5005 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 14015.3996 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | -1353.8 | 0 | 2548.25 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 65.3054 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -8212.9902 | 0 | 1274.1299 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 13.4301 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -9616.3301 | 0 | 6370.6299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 39.8489 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -32426.9395 | 0 | 2548.2598 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 7.2859 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 28.23 | 0 | 1274.13 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 102.2658 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 26d | [5 empty] | 2548.25 |  | 3.142% |  | 3264.72 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | -716.47 | 0 | 2548.25 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 78.0542 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 81139.5938 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 55d | [5 empty] | 26756.6733 |  | 70.27% |  | 237956.2665 | 247713.576
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 3822.3887 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -27682.1309 | 0 | 3822.3887 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 12.1328 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 6370.6351 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | -103.3 | 0 | 1274.1301 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 92.5005 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -131012.5625 | 0 | 3822.375 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.8349 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | -103.3 | 0 | 1274.1301 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 92.5005 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 14015.3996 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | -1353.8 | 0 | 2548.25 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 65.3054 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -8212.9902 | 0 | 1274.1299 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 13.4301 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -9616.3301 | 0 | 6370.6299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 39.8489 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -32426.9395 | 0 | 2548.2598 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 7.2859 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 28.23 | 0 | 1274.13 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 102.2658 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 23d | [5 empty] | 2548.25 |  | 3.142% |  | 3264.72 | 13022.0295
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | -716.47 | 0 | 2548.25 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 78.0542 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 36d | [5 empty] | 16563.6418 |  | 66.38% |  | 334056.3363 | 335433.7664
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 7644.7617 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -55364.2695 | 0 | 7644.7617 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 12.1328 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 8d | [5 empty] | 8918.8801 |  | 99.49% |  | 271047.3051 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | -103.3 | 0 | 1274.1301 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 92.5005 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 1d | -262025.125 | 0 | 7644.75 | 0 | 85.71% | Started | 269669.875 | 269669.875 | 100 | 100 | 85.7143 | 100 | 2.8349 | 85.7143
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 |  | 0 | 0 | 28461.3496 | 3d | 0 | 0 | 0 | 28461.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 |  | 0 | 0 | 34975.1992 | 2d | 0 | 0 | 0 | 34975.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 |  | 0 | 0 | 1245.9 | 1d | 0 | 0 | 0 | 1245.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 |  | 0 | 0 | 4897.0898 | 3d | 0 | 0 | 0 | 4897.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 65763.8914
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 63009.0312 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2754.8601
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 2754.8601 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 23d | [5 empty] | 7644.765 |  | 64.65% |  | 148091.3074 | 228079.1257
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 1274.1299 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -9227.3799 | 0 | 1274.1299 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 12.1328 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 6370.6351 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | -103.3 | 0 | 1274.1301 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 92.5005 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -131012.5625 | 0 | 3822.375 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 2.8349 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | -103.3 | 0 | 1274.1301 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 92.5005 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 |  | 0 | 0 | 31973.9297 | 10d | 0 | 0 | 0 | 31973.9297 | 0% | Not Started | 0 | 31973.9297 | 100 |  | 0 | 100 |  | 0
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 |  | 0 | 0 | 37948.4688 | 4d | 0 | 0 | 0 | 37948.4688 | 0% | Not Started | 0 | 37948.4688 | 100 |  | 0 | 100 |  | 0
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10065.4199
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 1951.46 | 100 |  | 0 | 100 |  | 0
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 8113.96 | 100 |  | 0 | 100 |  | 0
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 85d | [5 empty] | 253551.3065 |  | 26.16% |  | 1522122.34 | 1537768.2199
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 85d | [5 empty] | 52239.2232 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 11467.1523 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -22905 | 0 | 6370.6406 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 21.7609 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -22633.6191 | 0 | 5096.5117 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 18.379 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 78d | [5 empty] | 2548.25 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 1170.3 | 0 | 2548.25 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 184.9305 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 5096.5103 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -7269.02 | 0 | 5096.5103 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 41.2155 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 33127.3106 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -49748.0898 | 0 | 12741.2695 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 20.3895 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -21756.5391 | 0 | 2548.2617 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 10.4846 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 7186.8398 | 0 | 7644.7599 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 1669.4531 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -44689.7812 | 0 | 10193.0195 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 18.5723 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 70076.9993 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 15289.5314 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -15400.3799 | 0 | 2548.2607 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 14.1975 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 3618.23 | 0 | 3822.38 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1872.339 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -25801.5 | 0 | 3822.3809 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 12.903 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 3618.23 | 0 | 3822.38 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1872.339 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -4572.73 | 0 | 1274.1299 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 21.7917 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 2548.2501 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -4091.9199 | 0 | 1274.1201 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 23.7441 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -529.23 | 0 | 1274.13 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 70.6531 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 52239.2178 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -20095.8008 | 0 | 3822.3789 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 15.9811 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -14020.2695 | 0 | 2548.2598 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 15.3801 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -6325.9902 | 0 | 1274.1299 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 16.7646 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -40054.7305 | 0 | 6370.6289 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 13.7223 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -35767.4883 | 0 | 6370.6328 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 15.1185 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -257550.125 | 0 | 31853.1875 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 11.0065 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 5096.499 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 5096.499 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -16610.25 | 0 | 2548.25 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 13.3009 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -14229.7002 | 0 | 2548.249 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 15.1881 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 28d | [5 empty] | 126138.585 |  | 90.52% |  | 786251.0547 | 786251.0547
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 28d | [5 empty] | 49690.9492 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -16232.5703 | 0 | 5096.5 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 23.8946 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -54755.8281 | 0 | 8918.8906 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 14.007 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -53024.2383 | 0 | 8918.8906 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 14.3985 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -32150.0508 | 0 | 6370.6406 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 16.5382 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 1d | -39381.0117 | 0 | 7644.7578 | 0 | 85.71% | Started | 47025.7695 | 47025.7695 | 100 | 100 | 85.7143 | 100 | 16.2565 | 85.7143
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -40179.8008 | 0 | 12741.2695 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 24.076 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 8d | [5 empty] | 25482.542 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 12d | -13800.9697 | 0 | 25482.542 | 0 | 62.5% | Started | 39283.5117 | 39283.5117 | 100 | 100 | 62.5 | 100 | 64.8683 | 62.5
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 |  | 0 | 0 | 40901.25 | 4d | 0 | 0 | 0 | 40901.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 |  | 0 | 0 | 41464.0195 | 4d | 0 | 0 | 0 | 41464.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 5d | [5 empty] | 50965.0938 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 35d | -410588 | 0 | 50965.0938 | 0 | 53.33% | Started | 461553.0938 | 461553.0938 | 100 | 100 | 53.3333 | 100 | 11.0421 | 53.3333
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2004-07-08 17:00 |  | TP Name | 08/07, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 634d | [5 empty] | 1456930.4426 |  | 39.55% |  | 4516970.172 | 5136063.8857
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 112840.1094 | 0 | 124973.2295 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1030.0172 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 112840.1094 | 0 | 124973.2295 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1030.0172 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 112840.1094 | 0 | 124973.2295 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1030.0172 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 112840.1094 | 0 | 124973.2295 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1030.0172 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 112840.1094 | 0 | 124973.2295 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1030.0172 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 112840.1094 | 0 | 124973.2295 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1030.0172 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -441749.5938 | 0 | 44642.5 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 9.1783 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -62587.5781 | 0 | 18437.9297 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 22.7557 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 86d | [5 empty] | 371392.6667 |  | 45.77% |  | 2272266.2402 | 2875714.074
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 86d | [5 empty] | 237059.1196 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 19754.9219 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -137767.6562 | 0 | 19754.9219 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 12.541 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 34241.8883 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | -543.9 | 0 | 11852.9496 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 95.6126 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -436279.8438 | 0 | 13169.9688 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 2.9302 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | -423.03 | 0 | 9218.97 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 95.6126 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 40826.8472 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -3804.1899 | 0 | 7901.9702 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 67.5027 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -32680.4902 | 0 | 5267.9785 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 13.8819 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -33847.1602 | 0 | 23705.9102 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 41.1897 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -32341.2109 | 0 | 2633.9883 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 7.531 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 71.1 | 0 | 1317 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 105.7067 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 50d | [5 empty] | 142235.4622 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | -1892.2 | 0 | 7901.97 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 80.6803 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 1d | 11602.9805 | 0 | 44777.832 | 0 | 96.15% | Started | 33174.8516 | 33174.8516 | 100 | 73.5294 | 96.1538 | 100 | 134.9752 | 96.1538
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -231096.7969 | 0 | 44777.8281 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 16.2312 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 11602.9805 | 0 | 44777.832 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 134.9752 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 71d | [5 empty] | 27656.9127 |  | 70.27% |  | 237956.2665 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 3950.9902 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -27553.5293 | 0 | 3950.9902 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 12.541 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 6584.9845 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | -60.43 | 0 | 1317.0001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 95.6128 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -130883.9531 | 0 | 3950.9844 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.9302 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | -60.43 | 0 | 1317.0001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 95.6128 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 14486.948 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | -1268.0601 | 0 | 2633.99 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 67.5027 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -8170.1201 | 0 | 1317 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 13.882 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -9401.9902 | 0 | 6584.9697 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 41.1896 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -32341.2109 | 0 | 2633.9883 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 7.531 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 71.1 | 0 | 1317 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 105.7067 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 39d | [5 empty] | 2633.99 |  | 3.142% |  | 3264.72 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | -630.73 | 0 | 2633.99 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 80.6804 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 81139.5938 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 68d | [5 empty] | 27656.9127 |  | 70.27% |  | 237956.2665 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 3950.9902 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -27553.5293 | 0 | 3950.9902 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 12.541 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 6584.9845 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | -60.43 | 0 | 1317.0001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 95.6128 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -130883.9531 | 0 | 3950.9844 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 2.9302 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | -60.43 | 0 | 1317.0001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 95.6128 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 14486.948 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | -1268.0601 | 0 | 2633.99 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 67.5027 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -8170.1201 | 0 | 1317 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 13.882 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -9401.9902 | 0 | 6584.9697 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 41.1896 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -32341.2109 | 0 | 2633.9883 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 7.531 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 71.1 | 0 | 1317 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 105.7067 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 36d | [5 empty] | 2633.99 |  | 3.142% |  | 3264.72 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | -630.73 | 0 | 2633.99 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 80.6804 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 81139.5938 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 49d | [5 empty] | 47411.8295 |  | 88% |  | 442840.3148 | 501281.3861
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 7901.9727 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -55107.0586 | 0 | 7901.9727 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 12.541 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 10535.9689 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | -60.43 | 0 | 1317.0001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 95.6128 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -261767.9062 | 0 | 7901.9688 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 2.9302 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | -60.43 | 0 | 1317.0001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 95.6128 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 9d | [5 empty] | 25022.8981 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | -1902.1 | 0 | 3950.9801 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 67.5026 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -24510.3691 | 0 | 3950.9805 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 13.8819 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 1d | -18803.9805 | 0 | 13169.9492 | 0 | 83.33% | Started | 31973.9297 | 31973.9297 | 100 | 50 | 83.3333 | 100 | 41.1896 | 83.3333
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -32341.2109 | 0 | 2633.9883 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 7.531 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 71.1 | 0 | 1317 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 105.7067 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 3d | [5 empty] | 3950.9899 |  | 7.501% |  | 4897.0898 | 63338.1611
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | -946.1 | 0 | 3950.9899 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 80.6804 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 48683.7617 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 8d | [5 empty] | 0 |  | 0% |  | 0 | 343698.3367
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 |  | 0 | 0 | 63009.0312 | 6d | 0 | 0 | 0 | 63009.0312 | 0% | Not Started | 0 | 63009.0312 | 100 |  | 0 | 100 |  | 0
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 2754.8601 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 269669.875 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 8264.5703 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 1d | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 31607.8922 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 1317 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -9184.5098 | 0 | 1317 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 12.5411 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 6584.9845 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | -60.43 | 0 | 1317.0001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 95.6128 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -130883.9531 | 0 | 3950.9844 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 2.9302 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | -60.43 | 0 | 1317.0001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 95.6128 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 18437.9277 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -18803.9805 | 0 | 13169.9492 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 41.1896 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -32680.4902 | 0 | 5267.9785 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 13.8819 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 5267.98 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 682.53 | 0 | 2633.99 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 134.9754 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -6796.96 | 0 | 1317 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 16.2313 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 341.26 | 0 | 1316.99 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 134.9748 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 98d | [5 empty] | 272617.9693 |  | 27.58% |  | 1604487.6095 | 1620133.4894
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 98d | [5 empty] | 53996.8016 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 11852.9609 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -22690.6602 | 0 | 6584.9805 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 22.493 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -22462.1504 | 0 | 5267.9805 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 18.9973 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 91d | [5 empty] | 2633.99 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 1256.04 | 0 | 2633.99 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 191.1528 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 5267.9805 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -7097.5498 | 0 | 5267.9805 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 42.6021 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 34241.8702 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -49319.4102 | 0 | 13169.9492 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 21.0755 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -21670.8105 | 0 | 2633.9902 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 10.8373 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 7444.0498 | 0 | 7901.9698 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 1725.6223 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -44346.8398 | 0 | 10535.9609 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 19.1972 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 72434.7067 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 15803.9406 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -15314.6504 | 0 | 2633.9902 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 14.6752 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 3746.8301 | 0 | 3950.9801 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1935.332 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -25672.8906 | 0 | 3950.9902 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 13.3372 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 3746.8301 | 0 | 3950.9801 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 1935.332 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -4529.8599 | 0 | 1317 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 22.5249 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 2633.98 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -4049.05 | 0 | 1316.99 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 24.5431 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | -486.37 | 0 | 1316.99 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 73.0298 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 53996.7861 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -19967.1992 | 0 | 3950.9805 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 16.5187 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -13934.54 | 0 | 2633.9893 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 15.8975 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -6283.1201 | 0 | 1317 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 17.3287 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -39840.3906 | 0 | 6584.9688 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 14.184 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -35553.1484 | 0 | 6584.9727 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 15.6271 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -256478.4375 | 0 | 32924.875 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 11.3768 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 5267.9795 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 5267.9795 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -16524.5098 | 0 | 2633.9902 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 13.7484 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -14143.96 | 0 | 2633.9893 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 15.6991 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 41d | [5 empty] | 140918.4814 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 51362.8066 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -16061.0898 | 0 | 5267.9805 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 24.6986 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -54455.75 | 0 | 9218.9688 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 14.4782 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -52724.1602 | 0 | 9218.9688 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 14.883 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -31935.7207 | 0 | 6584.9707 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 17.0946 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -39123.8008 | 0 | 7901.9688 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 16.8035 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -39751.1211 | 0 | 13169.9492 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 24.886 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 26339.9014 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | -12943.6104 | 0 | 26339.9014 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 67.0508 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 10535.9609 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -35633.2695 | 0 | 5267.9805 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 12.8798 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -36196.0391 | 0 | 5267.9805 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 12.7049 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 18d | [5 empty] | 52679.8125 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 22d | -408873.2812 | 0 | 52679.8125 | 0 | 64.52% | Started | 461553.0938 | 461553.0938 | 100 | 100 | 64.5161 | 100 | 11.4136 | 64.5161
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2004-08-05 17:00 |  | TP Name | 05/08, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 639d | [5 empty] | 1779426.6272 |  | 40.18% |  | 4589736.5128 | 6138893.1357
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -438905.9688 | 0 | 47486.125 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 9.7629 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -54625.4219 | 0 | 26400.0859 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 32.5824 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 91d | [5 empty] | 561944.6439 |  | 47.24% |  | 2345032.5811 | 3878543.324
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 339429.6668 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 28285.8047 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -129236.7734 | 0 | 28285.8047 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 17.9567 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 49028.7383 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 4574.6299 | 0 | 16971.4795 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 136.9016 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -430592.5938 | 0 | 18857.2188 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 4.1956 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 3558.04 | 0 | 13200.04 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 136.9015 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 58457.3195 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -391.84 | 0 | 11314.3202 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 96.6527 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -30405.5898 | 0 | 7542.8789 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 19.8766 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -23610.1094 | 0 | 33942.9609 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 58.9768 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -31203.7598 | 0 | 3771.4395 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 10.7832 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 639.82 | 0 | 1885.72 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 151.354 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 203657.8043 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 1520.15 | 0 | 11314.3199 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 115.521 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 30939.6406 | 0 | 64114.4922 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 193.2623 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -211760.125 | 0 | 64114.5 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 23.2404 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 30939.6406 | 0 | 64114.4922 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 193.2623 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 76d | [5 empty] | 58457.3253 |  | 73.16% |  | 247713.576 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 5657.1699 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -25847.3496 | 0 | 5657.1699 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 17.9567 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 9428.5964 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 136.9013 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -129177.7812 | 0 | 5657.1562 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.1956 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 136.9013 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 20742.9198 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | -130.61 | 0 | 3771.44 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 96.6528 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -7601.3999 | 0 | 1885.7202 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 19.8766 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -6558.3599 | 0 | 9428.6001 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 58.9768 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -31203.7598 | 0 | 3771.4395 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 10.7832 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 639.82 | 0 | 1885.72 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 151.354 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 44d | [5 empty] | 22628.6392 |  | 12.53% |  | 13022.0295 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 506.72 | 0 | 3771.44 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 115.5211 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 2d | 9099.8896 | 0 | 18857.1992 | 0 | 75% | Started | 9757.3096 | 9757.3096 | 100 | 60 | 75 | 100 | 193.2623 | 75
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 81139.5938 | 100 |  | 0 | 100 |  | 0
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 73d | [5 empty] | 39600.1261 |  | 70.27% |  | 237956.2665 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 5657.1699 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -25847.3496 | 0 | 5657.1699 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 17.9567 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 9428.5964 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 136.9013 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -129177.7812 | 0 | 5657.1562 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.1956 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 136.9013 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 20742.9198 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | -130.61 | 0 | 3771.44 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 96.6528 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -7601.3999 | 0 | 1885.7202 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 19.8766 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -6558.3599 | 0 | 9428.6001 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 58.9768 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -31203.7598 | 0 | 3771.4395 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 10.7832 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 639.82 | 0 | 1885.72 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 151.354 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 41d | [5 empty] | 3771.44 |  | 3.142% |  | 3264.72 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 506.72 | 0 | 3771.44 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 115.5211 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 81139.5938 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 54d | [5 empty] | 67885.9217 |  | 88% |  | 442840.3148 | 501281.3861
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 11314.3203 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -51694.7109 | 0 | 11314.3203 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 17.9567 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 15085.7526 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 136.9013 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -258355.5625 | 0 | 11314.3125 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 4.1956 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 136.9013 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 35828.6789 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | -195.92 | 0 | 5657.1601 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 96.6527 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -22804.1895 | 0 | 5657.1602 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 19.8766 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -13116.7305 | 0 | 18857.1992 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 58.9768 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -31203.7598 | 0 | 3771.4395 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 10.7832 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 639.82 | 0 | 1885.72 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 151.354 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 8d | [5 empty] | 5657.1699 |  | 7.501% |  | 4897.0898 | 63338.1611
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 760.08 | 0 | 5657.1699 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 115.5211 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 48683.7617 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 13d | [5 empty] | 11314.3203 |  | 11.7% |  | 63009.0312 | 485385.7273
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 1d | [5 empty] | 11314.3203 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 12d | -51694.7109 | 0 | 11314.3203 | 0 | 52% | Started | 63009.0312 | 63009.0312 | 100 | 216.6667 | 52 | 100 | 17.9567 | 52
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 2754.8601 | 100 |  | 0 | 100 |  | 0
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 |  | 0 | 0 | 269669.875 | 6d | 0 | 0 | 0 | 269669.875 | 0% | Not Started | 0 | 269669.875 | 100 |  | 0 | 100 |  | 0
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 |  | 0 | 0 | 8264.5703 | 6d | 0 | 0 | 0 | 8264.5703 | 0% | Not Started | 0 | 8264.5703 | 100 |  | 0 | 100 |  | 0
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 110764.6709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 5853.0801 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 18974.2402 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 15986.96 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 69950.3906 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 30922.7197
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 6529.4502 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 24393.2695 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 6d | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 45257.2836 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 1885.7295 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -8615.7803 | 0 | 1885.7295 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 17.9567 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 9428.5964 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 136.9013 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -129177.7812 | 0 | 5657.1562 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 4.1956 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 136.9013 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 26400.0781 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -13116.7305 | 0 | 18857.1992 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 58.9768 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -30405.5898 | 0 | 7542.8789 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 19.8766 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 7542.8796 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 1819.98 | 0 | 3771.4399 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 193.2625 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -6228.2402 | 0 | 1885.7197 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 23.2404 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 909.99 | 0 | 1885.72 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 193.2625 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 861141.8594
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 412876.7344
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 |  | 0 | 0 | 388148.375 | 140d | 0 | 0 | 0 | 388148.375 | 0% | Not Started | 0 | 388148.375 | 100 |  | 0 | 100 |  | 0
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 103d | [5 empty] | 390344.0829 |  | 27.58% |  | 1604487.6095 | 1620133.4894
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 103d | [5 empty] | 77314.5255 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 16971.4824 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -19847.0391 | 0 | 9428.6016 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 32.2063 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -20187.25 | 0 | 7542.8809 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 27.201 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 96d | [5 empty] | 3771.4399 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 2393.49 | 0 | 3771.4399 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 273.6993 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 7542.8804 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -4822.6499 | 0 | 7542.8804 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 60.9992 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 49028.7227 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -43632.1602 | 0 | 18857.1992 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 30.1767 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -20533.3594 | 0 | 3771.4414 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 15.5173 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 10856.4004 | 0 | 11314.3204 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 2470.8071 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -39797.0391 | 0 | 15085.7617 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 27.4872 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 103714.6147 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 22628.6401 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -14177.2002 | 0 | 3771.4404 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 21.0124 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 5453.0098 | 0 | 5657.1598 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 2771.0801 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -23966.7207 | 0 | 5657.1602 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 19.0966 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 5453.0098 | 0 | 5657.1598 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 2771.0801 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -3961.1399 | 0 | 1885.72 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 32.2518 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 3771.44 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -3480.3201 | 0 | 1885.72 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 35.1417 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 82.36 | 0 | 1885.72 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 104.567 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 77314.5347 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -18261.0195 | 0 | 5657.1602 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 23.6521 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -12797.0898 | 0 | 3771.4395 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 22.7627 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -5714.3999 | 0 | 1885.7202 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 24.8117 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -36996.7617 | 0 | 9428.5977 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 20.3092 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -32709.5195 | 0 | 9428.6016 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 22.3755 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -242260.2969 | 0 | 47143.0156 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 16.2897 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 7542.8799 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 7542.8799 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -15387.0596 | 0 | 3771.4404 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 19.6855 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -13006.5098 | 0 | 3771.4395 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 22.4785 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 46d | [5 empty] | 201772.0629 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 73543.0908 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -13786.1904 | 0 | 7542.8799 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 35.3643 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -50474.6797 | 0 | 13200.0391 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 20.7304 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -48743.0781 | 0 | 13200.0508 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 21.31 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -29092.0898 | 0 | 9428.6016 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 24.4767 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -35711.4492 | 0 | 11314.3203 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 24.0598 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -34063.8711 | 0 | 18857.1992 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 35.6327 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 37714.4017 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | -1569.11 | 0 | 37714.4017 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 96.0057 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 15085.7578 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -33358.3711 | 0 | 7542.8789 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 18.4417 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -33921.1406 | 0 | 7542.8789 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 18.1914 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 23d | [5 empty] | 75428.8125 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 17d | -386124.2812 | 0 | 75428.8125 | 0 | 70.18% | Started | 461553.0938 | 461553.0938 | 100 | 100 | 70.1754 | 100 | 16.3424 | 70.1754
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2004-08-19 17:00 |  | TP Name | 19/08, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 648d | [5 empty] | 2130513.1533 |  | 46.92% |  | 5359228.4062 | 6143336.3957
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 113408.8281 | 0 | 125541.9482 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1034.7046 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -438905.9688 | 0 | 47486.125 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 9.7629 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -54625.4219 | 0 | 26400.0859 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 32.5824 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 100d | [5 empty] | 913031.17 |  | 62.74% |  | 3114524.4744 | 3882986.584
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 339429.6668 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 28285.8047 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -129236.7734 | 0 | 28285.8047 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 17.9567 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 49028.7383 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 4574.6299 | 0 | 16971.4795 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 136.9016 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -430592.5938 | 0 | 18857.2188 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 4.1956 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 3558.04 | 0 | 13200.04 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 136.9015 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 58457.3195 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | -391.84 | 0 | 11314.3202 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 96.6527 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -30405.5898 | 0 | 7542.8789 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 19.8766 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -23610.1094 | 0 | 33942.9609 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 58.9768 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -31203.7598 | 0 | 3771.4395 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 10.7832 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 639.82 | 0 | 1885.72 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 151.354 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 203657.8043 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 1520.15 | 0 | 11314.3199 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 115.521 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 30939.6406 | 0 | 64114.4922 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 193.2623 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -211760.125 | 0 | 64114.5 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 23.2404 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 30939.6406 | 0 | 64114.4922 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 193.2623 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 85d | [5 empty] | 96171.7277 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 5657.1699 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -25847.3496 | 0 | 5657.1699 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 17.9567 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 9428.5964 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 136.9013 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -129177.7812 | 0 | 5657.1562 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.1956 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 136.9013 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 20742.9198 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | -130.61 | 0 | 3771.44 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 96.6528 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -7601.3999 | 0 | 1885.7202 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 19.8766 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -6558.3599 | 0 | 9428.6001 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 58.9768 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -31203.7598 | 0 | 3771.4395 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 10.7832 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 639.82 | 0 | 1885.72 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 151.354 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 53d | [5 empty] | 60343.0415 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 506.72 | 0 | 3771.44 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 115.5211 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 9099.8896 | 0 | 18857.1992 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 193.2623 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 2d | -62282.3906 | 0 | 18857.2031 | 0 | 83.33% | Started | 81139.5938 | 81139.5938 | 100 | 100 | 83.3333 | 100 | 23.2404 | 83.3333
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 5d | 9099.8896 | 0 | 18857.1992 | 0 | 66.67% | Started | 9757.3096 | 9757.3096 | 100 | 100 | 66.6667 | 100 | 193.2623 | 66.6667
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 82d | [5 empty] | 58457.3253 |  | 73.16% |  | 247713.576 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 5657.1699 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -25847.3496 | 0 | 5657.1699 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 17.9567 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 9428.5964 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 136.9013 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -129177.7812 | 0 | 5657.1562 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.1956 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 136.9013 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 20742.9198 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | -130.61 | 0 | 3771.44 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 96.6528 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -7601.3999 | 0 | 1885.7202 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 19.8766 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -6558.3599 | 0 | 9428.6001 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 58.9768 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -31203.7598 | 0 | 3771.4395 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 10.7832 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 639.82 | 0 | 1885.72 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 151.354 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 50d | [5 empty] | 22628.6392 |  | 12.53% |  | 13022.0295 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 506.72 | 0 | 3771.44 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 115.5211 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 3d | 9099.8896 | 0 | 18857.1992 | 0 | 66.67% | Started | 9757.3096 | 9757.3096 | 100 | 60 | 66.6667 | 100 | 193.2623 | 66.6667
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 |  | 0 | 0 | 81139.5938 | 10d | 0 | 0 | 0 | 81139.5938 | 0% | Not Started | 0 | 81139.5938 | 100 |  | 0 | 100 |  | 0
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 63d | [5 empty] | 67885.9217 |  | 88% |  | 442840.3148 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 11314.3203 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -51694.7109 | 0 | 11314.3203 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 17.9567 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 15085.7526 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 136.9013 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -258355.5625 | 0 | 11314.3125 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 4.1956 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 136.9013 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 35828.6789 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | -195.92 | 0 | 5657.1601 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 96.6527 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -22804.1895 | 0 | 5657.1602 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 19.8766 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -13116.7305 | 0 | 18857.1992 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 58.9768 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -31203.7598 | 0 | 3771.4395 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 10.7832 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 639.82 | 0 | 1885.72 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 151.354 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 17d | [5 empty] | 5657.1699 |  | 7.501% |  | 4897.0898 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 760.08 | 0 | 5657.1699 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 115.5211 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 9757.3096 | 100 |  | 0 | 100 |  | 0
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 48683.7617 | 100 |  | 0 | 100 |  | 0
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 1951.46 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 22d | [5 empty] | 37714.3932 |  | 63.82% |  | 343698.3367 | 487877.5273
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 10d | [5 empty] | 11314.3203 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 3d | -51694.7109 | 0 | 11314.3203 | 0 | 81.25% | Started | 63009.0312 | 63009.0312 | 100 | 216.6667 | 81.25 | 100 | 17.9567 | 81.25
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 4d | [5 empty] | 26400.0729 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 1016.58 | 0 | 3771.4401 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 136.9013 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 3d | -258355.5625 | 0 | 11314.3125 | 0 | 66.67% | Started | 269669.875 | 269669.875 | 100 | 100 | 66.6667 | 100 | 4.1956 | 66.6667
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 4d | 3049.75 | 0 | 11314.3203 | 0 | 60% | Started | 8264.5703 | 8264.5703 | 100 | 100 | 60 | 100 | 136.9015 | 60
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 |  | 0 | 0 | 5853.0801 | 3d | 0 | 0 | 0 | 5853.0801 | 0% | Not Started | 0 | 5853.0801 | 100 |  | 0 | 100 |  | 0
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 18974.2402 | 100 |  | 0 | 100 |  | 0
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 |  | 0 | 0 | 15986.96 | 5d | 0 | 0 | 0 | 15986.96 | 0% | Not Started | 0 | 15986.96 | 100 |  | 0 | 100 |  | 0
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 |  | 0 | 0 | 69950.3906 | 4d | 0 | 0 | 0 | 69950.3906 | 0% | Not Started | 0 | 69950.3906 | 100 |  | 0 | 100 |  | 0
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 |  | 0 | 0 | 2491.8 | 2d | 0 | 0 | 0 | 2491.8 | 0% | Not Started | 0 | 2491.8 | 100 |  | 0 | 100 |  | 0
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 30922.7197
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 |  | 0 | 0 | 6529.4502 | 4d | 0 | 0 | 0 | 6529.4502 | 0% | Not Started | 0 | 6529.4502 | 100 |  | 0 | 100 |  | 0
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 24393.2695 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 15d | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 45257.2836 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 1885.7295 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -8615.7803 | 0 | 1885.7295 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 17.9567 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 9428.5964 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 136.9013 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -129177.7812 | 0 | 5657.1562 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 4.1956 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 508.29 | 0 | 1885.7201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 136.9013 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 26400.0781 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -13116.7305 | 0 | 18857.1992 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 58.9768 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -30405.5898 | 0 | 7542.8789 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 19.8766 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 7542.8796 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 1819.98 | 0 | 3771.4399 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 193.2625 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -6228.2402 | 0 | 1885.7197 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 23.2404 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 909.99 | 0 | 1885.72 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 193.2625 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 3d | [5 empty] | 268114.8516 |  | 32.58% |  | 388148.375 | 861141.8594
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 3d | [5 empty] | 268114.8516 |  | 91.6% |  | 388148.375 | 412876.7344
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 137d | -120033.5234 | 0 | 268114.8516 | 0 | 50.54% | Started | 388148.375 | 388148.375 | 100 | 100 | 50.5415 | 100 | 69.0754 | 50.5415
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 112d | [5 empty] | 390344.0829 |  | 27.58% |  | 1604487.6095 | 1620133.4894
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 112d | [5 empty] | 77314.5255 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 16971.4824 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -19847.0391 | 0 | 9428.6016 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 32.2063 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -20187.25 | 0 | 7542.8809 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 27.201 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 105d | [5 empty] | 3771.4399 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 2393.49 | 0 | 3771.4399 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 273.6993 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 7542.8804 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -4822.6499 | 0 | 7542.8804 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 60.9992 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 49028.7227 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -43632.1602 | 0 | 18857.1992 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 30.1767 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -20533.3594 | 0 | 3771.4414 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 15.5173 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 10856.4004 | 0 | 11314.3204 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 2470.8071 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -39797.0391 | 0 | 15085.7617 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 27.4872 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 103714.6147 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 22628.6401 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -14177.2002 | 0 | 3771.4404 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 21.0124 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 5453.0098 | 0 | 5657.1598 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 2771.0801 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -23966.7207 | 0 | 5657.1602 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 19.0966 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 5453.0098 | 0 | 5657.1598 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 2771.0801 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -3961.1399 | 0 | 1885.72 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 32.2518 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 3771.44 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -3480.3201 | 0 | 1885.72 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 35.1417 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 82.36 | 0 | 1885.72 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 104.567 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 77314.5347 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -18261.0195 | 0 | 5657.1602 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 23.6521 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -12797.0898 | 0 | 3771.4395 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 22.7627 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -5714.3999 | 0 | 1885.7202 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 24.8117 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -36996.7617 | 0 | 9428.5977 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 20.3092 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -32709.5195 | 0 | 9428.6016 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 22.3755 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -242260.2969 | 0 | 47143.0156 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 16.2897 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 7542.8799 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 7542.8799 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -15387.0596 | 0 | 3771.4404 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 19.6855 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -13006.5098 | 0 | 3771.4395 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 22.4785 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 55d | [5 empty] | 201772.0629 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 73543.0908 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -13786.1904 | 0 | 7542.8799 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 35.3643 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -50474.6797 | 0 | 13200.0391 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 20.7304 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -48743.0781 | 0 | 13200.0508 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 21.31 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -29092.0898 | 0 | 9428.6016 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 24.4767 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -35711.4492 | 0 | 11314.3203 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 24.0598 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -34063.8711 | 0 | 18857.1992 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 35.6327 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 37714.4017 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | -1569.11 | 0 | 37714.4017 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 96.0057 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 15085.7578 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -33358.3711 | 0 | 7542.8789 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 18.4417 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -33921.1406 | 0 | 7542.8789 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 18.1914 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 32d | [5 empty] | 75428.8125 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 8d | -386124.2812 | 0 | 75428.8125 | 0 | 83.33% | Started | 461553.0938 | 461553.0938 | 100 | 100 | 83.3333 | 100 | 16.3424 | 83.3333
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 |  | 0 | 0 | 451.94 | 5d | 0 | 0 | 0 | 451.94 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 |  | 0 | 0 | 450.25 | 1d | 0 | 0 | 0 | 450.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 |  | 0 | 0 | 24597.8691 | 3d | 0 | 0 | 0 | 24597.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 |  | 0 | 0 | 22867.3594 | 3d | 0 | 0 | 0 | 22867.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2004-09-09 17:00 |  | TP Name | 09/09, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 663d | [5 empty] | 2406220.726 |  | 49.7% |  | 5676719.7204 | 7489932.3092
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -438077 | 0 | 48315.0938 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 9.9334 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -52304.3398 | 0 | 28721.168 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 35.4471 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 115d | [5 empty] | 1107827.4779 |  | 68.16% |  | 3383648.3701 | 3952673.3555
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 369272.1754 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 30772.6797 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -126749.8984 | 0 | 30772.6797 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 19.5354 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 53339.3145 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 6066.75 | 0 | 18463.5996 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 148.9378 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -428934.6875 | 0 | 20515.125 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 4.5645 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 4718.5898 | 0 | 14360.5898 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 148.9379 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 63596.8692 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 602.91 | 0 | 12309.0701 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 105.1504 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -29742.4199 | 0 | 8206.0488 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 21.6242 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -20625.8594 | 0 | 36927.2109 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 64.162 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 11.7313 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 221563.312 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 2514.8999 | 0 | 12309.0698 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 125.6775 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 36576.5586 | 0 | 69751.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 210.2539 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -206123.2031 | 0 | 69751.4219 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 25.2837 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 36576.5586 | 0 | 69751.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 210.2539 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 104627.1112 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 6154.5391 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -25349.9805 | 0 | 6154.5391 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 19.5354 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 148.9375 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.5645 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 22566.6297 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 200.97 | 0 | 4103.0201 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 105.1504 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -7435.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 21.6242 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 64.162 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 11.7313 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 164.6609 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 65648.3832 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 838.3 | 0 | 4103.02 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 125.6775 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 210.2539 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -60624.4688 | 0 | 20515.125 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 25.2837 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 210.2539 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 97d | [5 empty] | 104627.1112 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 6154.5391 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -25349.9805 | 0 | 6154.5391 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 19.5354 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 148.9375 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.5645 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 22566.6297 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 200.97 | 0 | 4103.0201 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 105.1504 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -7435.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 21.6242 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 64.162 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 11.7313 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 65d | [5 empty] | 65648.3832 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 838.3 | 0 | 4103.02 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 125.6775 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 210.2539 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 1d | -60624.4688 | 0 | 20515.125 | 0 | 90.91% | Started | 81139.5938 | 81139.5938 | 100 | 100 | 90.9091 | 100 | 25.2837 | 90.9091
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 4d | 10757.8096 | 0 | 20515.1191 | 0 | 71.43% | Started | 9757.3096 | 9757.3096 | 100 | 100 | 71.4286 | 100 | 210.2539 | 71.4286
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 78d | [5 empty] | 106678.6127 |  | 99.61% |  | 501281.3861 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 12309.0703 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -50699.9609 | 0 | 12309.0703 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 19.5354 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 16412.0826 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 148.9375 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -257360.8125 | 0 | 12309.0625 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 4.5645 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 148.9375 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 38978.7188 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 301.45 | 0 | 6154.5301 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 105.1503 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -22306.8203 | 0 | 6154.5293 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 21.6242 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -11458.8096 | 0 | 20515.1201 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 64.162 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 11.7313 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 32d | [5 empty] | 38978.741 |  | 97.01% |  | 63338.1611 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 1257.45 | 0 | 6154.5398 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 125.6775 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 3d | 10757.8096 | 0 | 20515.1191 | 0 | 83.33% | Started | 9757.3096 | 9757.3096 | 100 | 150 | 83.3333 | 100 | 210.2539 | 83.3333
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 4d | -36374.6797 | 0 | 12309.082 | 0 | 60% | Started | 48683.7617 | 48683.7617 | 100 | 100 | 60 | 100 | 25.2838 | 60
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 1951.46 | 100 |  | 0 | 100 |  | 0
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 37d | [5 empty] | 82060.4847 |  | 86.07% |  | 463484.2578 | 536561.2891
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 12309.0703 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -50699.9609 | 0 | 12309.0703 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 19.5354 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 28721.163 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 1348.17 | 0 | 4103.0302 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 148.9379 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -257360.8125 | 0 | 12309.0625 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 4.5645 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 4044.5 | 0 | 12309.0703 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 148.9378 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 32824.2012 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 301.45 | 0 | 6154.5301 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 105.1503 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -14871.21 | 0 | 4103.0303 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 21.6242 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 64.162 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -61744.3398 | 0 | 8206.0508 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 11.7312 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 1611.23 | 0 | 4103.03 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 164.6613 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 9d | [5 empty] | 8206.0502 |  | 8.006% |  | 6529.4502 | 79606.4814
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 1676.6 | 0 | 8206.0502 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 125.6775 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 |  | 0 | 0 | 24393.2695 | 25d | 0 | 0 | 0 | 24393.2695 | 0% | Not Started | 0 | 24393.2695 | 100 |  | 0 | 100 |  | 0
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 48683.7617 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 30d | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 49236.2875 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 2051.5195 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -8449.9902 | 0 | 2051.5195 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 19.5355 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 4.5645 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 28721.1689 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -11458.8096 | 0 | 20515.1201 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 64.162 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -29742.4199 | 0 | 8206.0488 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 21.6242 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 8206.0398 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 2151.5601 | 0 | 4103.02 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 210.2539 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -6062.4502 | 0 | 2051.5098 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 25.2837 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 1075.78 | 0 | 2051.51 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 210.2539 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 13d | [5 empty] | 0 |  | 0% |  | 0 | 21003.0098
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 21003.0098 | 100 |  | 0 | 100 |  | 0
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 18d | [5 empty] | 291325.6953 |  | 32.58% |  | 388148.375 | 861141.8594
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 18d | [5 empty] | 291325.6953 |  | 91.6% |  | 388148.375 | 412876.7344
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 122d | -96822.6797 | 0 | 291325.6953 | 0 | 53.44% | Started | 388148.375 | 388148.375 | 100 | 100 | 53.4351 | 100 | 75.0552 | 53.4351
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 127d | [5 empty] | 467110.4688 |  | 28.41% |  | 1652855.028 | 2897042.6314
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 127d | [5 empty] | 84111.9859 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 18463.6113 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -19018.0801 | 0 | 10257.5605 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 35.0379 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -19524.0801 | 0 | 8206.0508 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 29.5925 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 120d | [5 empty] | 4103.02 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 2725.0701 | 0 | 4103.02 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 297.7626 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 8206.04 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -4159.4902 | 0 | 8206.04 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 66.3622 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 53339.3145 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -41974.2383 | 0 | 20515.1211 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 32.8298 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -20201.7793 | 0 | 4103.0215 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 16.8815 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 11851.1504 | 0 | 12309.0704 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 2688.0394 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -38470.6992 | 0 | 16412.1016 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 29.9039 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 112833.1613 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 24618.1408 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -13845.6104 | 0 | 4103.0303 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 22.8598 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 5950.3799 | 0 | 6154.5299 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 3014.7098 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -23469.3398 | 0 | 6154.541 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 20.7756 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 5950.3799 | 0 | 6154.5299 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 3014.7098 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -3795.3501 | 0 | 2051.5098 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 35.0874 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 4103.02 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -3314.53 | 0 | 2051.51 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 38.2314 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 248.15 | 0 | 2051.51 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 113.7604 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 84112.0005 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -17763.6504 | 0 | 6154.5293 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 25.7316 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -12465.5 | 0 | 4103.0293 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 24.764 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -5548.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 26.9931 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -36167.8008 | 0 | 10257.5586 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 22.0947 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -31880.5605 | 0 | 10257.5605 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 24.3427 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -238115.5 | 0 | 51287.8125 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 17.7219 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 8206.0391 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 8206.0391 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -15055.4805 | 0 | 4103.0195 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 21.4162 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -12674.9297 | 0 | 4103.0195 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 24.4548 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 219511.8032 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 80008.9717 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -13123.0303 | 0 | 8206.04 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 38.4735 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -49314.1289 | 0 | 14360.5898 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 22.553 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -47582.5391 | 0 | 14360.5898 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 23.1835 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -28263.1309 | 0 | 10257.5605 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 26.6287 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -34716.6992 | 0 | 12309.0703 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 26.1752 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -32405.9492 | 0 | 20515.1211 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 38.7655 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 41030.2417 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 1746.73 | 0 | 41030.2417 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 104.4465 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 16412.0898 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -32695.1992 | 0 | 8206.0508 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 20.0631 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -33257.9805 | 0 | 8206.0391 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 19.7907 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 82060.5 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -379492.5938 | 0 | 82060.5 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 17.7792 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 6d | [5 empty] | 42447.4793 |  | 4.715% |  | 48367.4185 | 902.19
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 6d | [5 empty] | 30138.4207 |  | 1.082% |  | 902.19 | 902.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 27634.9707 | 0 | 28086.9107 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 6214.7432 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 1601.26 | 0 | 2051.51 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 455.638 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 5d | [5 empty] | 12309.0586 |  | 100% |  | 47465.2285 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -18443.3398 | 0 | 6154.5293 | 0 | 100% | Finished | 24597.8691 | 0 | 100 | 100 | 100 | 100 | 25.0206 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 1d | -16712.8301 | 0 | 6154.5293 | 0 | 75% | Started | 22867.3594 | 0 | 100 | 100 | 75 | 100 | 26.914 | 75
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 31664.5605
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 |  | 0 | 0 | 31664.5605 | 50d | 0 | 0 | 0 | 31664.5605 | 0% | Not Started | 0 | 31664.5605 | 100 |  | 0 | 100 |  | 0
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 634906.0886
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 12038.2695 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 3083.78 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 31102.0195 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 132006.2031 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 322152.7812
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 85276.1921
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2004-09-16 17:00 |  | TP Name | 16/09, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 668d | [5 empty] | 2612996.8828 |  | 50.75% |  | 5796978.5202 | 7549460.8496
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -438077 | 0 | 48315.0938 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 9.9334 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -52304.3398 | 0 | 28721.168 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 35.4471 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 120d | [5 empty] | 1167321.3163 |  | 69.11% |  | 3430996.1094 | 3970955.3959
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 369272.1754 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 30772.6797 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -126749.8984 | 0 | 30772.6797 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 19.5354 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 53339.3145 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 6066.75 | 0 | 18463.5996 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 148.9378 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -428934.6875 | 0 | 20515.125 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 4.5645 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 4718.5898 | 0 | 14360.5898 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 148.9379 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 63596.8692 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 602.91 | 0 | 12309.0701 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 105.1504 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -29742.4199 | 0 | 8206.0488 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 21.6242 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -20625.8594 | 0 | 36927.2109 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 64.162 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 11.7313 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 221563.312 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 2514.8999 | 0 | 12309.0698 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 125.6775 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 36576.5586 | 0 | 69751.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 210.2539 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -206123.2031 | 0 | 69751.4219 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 25.2837 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 36576.5586 | 0 | 69751.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 210.2539 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 104627.1112 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 6154.5391 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -25349.9805 | 0 | 6154.5391 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 19.5354 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 148.9375 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.5645 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 22566.6297 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 200.97 | 0 | 4103.0201 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 105.1504 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -7435.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 21.6242 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 64.162 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 11.7313 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 164.6609 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 65648.3832 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 838.3 | 0 | 4103.02 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 125.6775 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 210.2539 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -60624.4688 | 0 | 20515.125 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 25.2837 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 210.2539 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 104627.1112 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 6154.5391 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -25349.9805 | 0 | 6154.5391 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 19.5354 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 148.9375 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.5645 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 22566.6297 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 200.97 | 0 | 4103.0201 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 105.1504 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -7435.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 21.6242 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 64.162 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 11.7313 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 65648.3832 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 838.3 | 0 | 4103.02 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 125.6775 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 210.2539 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -60624.4688 | 0 | 20515.125 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 25.2837 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 210.2539 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 83d | [5 empty] | 110781.6328 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 12309.0703 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -50699.9609 | 0 | 12309.0703 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 19.5354 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 16412.0826 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 148.9375 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -257360.8125 | 0 | 12309.0625 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 4.5645 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 148.9375 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 38978.7188 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 301.45 | 0 | 6154.5301 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 105.1503 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -22306.8203 | 0 | 6154.5293 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 21.6242 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -11458.8096 | 0 | 20515.1201 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 64.162 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 11.7313 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 37d | [5 empty] | 43081.761 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 1257.45 | 0 | 6154.5398 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 125.6775 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 210.2539 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -36374.6797 | 0 | 12309.082 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 25.2838 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 1d | 2151.5601 | 0 | 4103.02 | 0 | 66.67% | Started | 1951.46 | 1951.46 | 100 | 100 | 66.6667 | 100 | 210.2539 | 66.6667
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 42d | [5 empty] | 133348.2835 |  | 90.6% |  | 487877.5273 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 12309.0703 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -50699.9609 | 0 | 12309.0703 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 19.5354 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 28721.163 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 1348.17 | 0 | 4103.0302 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 148.9379 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -257360.8125 | 0 | 12309.0625 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 4.5645 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 4044.5 | 0 | 12309.0703 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 148.9378 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 32824.2012 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 301.45 | 0 | 6154.5301 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 105.1503 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -14871.21 | 0 | 4103.0303 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 21.6242 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 64.162 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -61744.3398 | 0 | 8206.0508 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 11.7312 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 1611.23 | 0 | 4103.03 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 164.6613 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 14d | [5 empty] | 59493.849 |  | 37.92% |  | 30922.7197 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 1676.6 | 0 | 8206.0502 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 125.6775 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 5d | 26894.5293 | 0 | 51287.7988 | 0 | 58.33% | Started | 24393.2695 | 24393.2695 | 100 | 28 | 58.3333 | 100 | 210.2539 | 58.3333
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 |  | 0 | 0 | 48683.7617 | 6d | 0 | 0 | 0 | 48683.7617 | 0% | Not Started | 0 | 48683.7617 | 100 |  | 0 | 100 |  | 0
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 1951.46 | 100 |  | 0 | 100 |  | 0
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 35d | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 49236.2875 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 2051.5195 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -8449.9902 | 0 | 2051.5195 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 19.5355 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 4.5645 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 28721.1689 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -11458.8096 | 0 | 20515.1201 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 64.162 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -29742.4199 | 0 | 8206.0488 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 21.6242 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 8206.0398 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 2151.5601 | 0 | 4103.02 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 210.2539 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -6062.4502 | 0 | 2051.5098 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 25.2837 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 1075.78 | 0 | 2051.51 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 210.2539 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 18d | [5 empty] | 4103.0195 |  | 7.128% |  | 21003.0098 | 37333.5902
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 1d | [5 empty] | 4103.0195 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 1d | -16899.9902 | 0 | 4103.0195 | 0 | 66.67% | Started | 21003.0098 | 21003.0098 | 100 | 100 | 66.6667 | 100 | 19.5354 | 66.6667
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 16330.5804
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 |  | 0 | 0 | 14953.1504 | 8d | 0 | 0 | 0 | 14953.1504 | 0% | Not Started | 0 | 14953.1504 | 100 |  | 0 | 100 |  | 0
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 23d | [5 empty] | 291325.6953 |  | 32.58% |  | 388148.375 | 861141.8594
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 23d | [5 empty] | 291325.6953 |  | 91.6% |  | 388148.375 | 412876.7344
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 117d | -96822.6797 | 0 | 291325.6953 | 0 | 54.47% | Started | 388148.375 | 388148.375 | 100 | 100 | 54.4747 | 100 | 75.0552 | 54.4747
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 132d | [5 empty] | 614392.7872 |  | 29.67% |  | 1725766.0886 | 2938289.1314
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 132d | [5 empty] | 84111.9859 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 18463.6113 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -19018.0801 | 0 | 10257.5605 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 35.0379 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -19524.0801 | 0 | 8206.0508 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 29.5925 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 125d | [5 empty] | 4103.02 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 2725.0701 | 0 | 4103.02 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 297.7626 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 8206.04 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -4159.4902 | 0 | 8206.04 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 66.3622 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 53339.3145 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -41974.2383 | 0 | 20515.1211 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 32.8298 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -20201.7793 | 0 | 4103.0215 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 16.8815 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 11851.1504 | 0 | 12309.0704 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 2688.0394 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -38470.6992 | 0 | 16412.1016 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 29.9039 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 112833.1613 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 24618.1408 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -13845.6104 | 0 | 4103.0303 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 22.8598 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 5950.3799 | 0 | 6154.5299 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 3014.7098 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -23469.3398 | 0 | 6154.541 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 20.7756 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 5950.3799 | 0 | 6154.5299 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 3014.7098 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -3795.3501 | 0 | 2051.5098 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 35.0874 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 4103.02 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -3314.53 | 0 | 2051.51 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 38.2314 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 248.15 | 0 | 2051.51 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 113.7604 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 84112.0005 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -17763.6504 | 0 | 6154.5293 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 25.7316 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -12465.5 | 0 | 4103.0293 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 24.764 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -5548.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 26.9931 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -36167.8008 | 0 | 10257.5586 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 22.0947 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -31880.5605 | 0 | 10257.5605 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 24.3427 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -238115.5 | 0 | 51287.8125 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 17.7219 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 8206.0391 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 8206.0391 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -15055.4805 | 0 | 4103.0195 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 21.4162 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -12674.9297 | 0 | 4103.0195 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 24.4548 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 219511.8032 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 80008.9717 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -13123.0303 | 0 | 8206.04 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 38.4735 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -49314.1289 | 0 | 14360.5898 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 22.553 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -47582.5391 | 0 | 14360.5898 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 23.1835 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -28263.1309 | 0 | 10257.5605 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 26.6287 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -34716.6992 | 0 | 12309.0703 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 26.1752 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -32405.9492 | 0 | 20515.1211 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 38.7655 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 41030.2417 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 1746.73 | 0 | 41030.2417 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 104.4465 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 16412.0898 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -32695.1992 | 0 | 8206.0508 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 20.0631 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -33257.9805 | 0 | 8206.0391 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 19.7907 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 82060.5 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -379492.5938 | 0 | 82060.5 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 17.7792 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 11d | [5 empty] | 54756.5496 |  | 8.736% |  | 89613.9185 | 42148.69
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 11d | [5 empty] | 42447.491 |  | 50.54% |  | 42148.69 | 42148.69
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 27634.9707 | 0 | 28086.9107 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 6214.7432 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 1601.26 | 0 | 2051.51 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 455.638 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 1d | -28937.4297 | 0 | 12309.0703 | 0 | 85.71% | Started | 41246.5 | 41246.5 | 100 | 100 | 85.7143 | 100 | 29.8427 | 85.7143
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 |  | 0 | 0 | 41246.5 | 6d | 0 | 0 | 0 | 41246.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 12309.0586 |  | 100% |  | 47465.2285 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -18443.3398 | 0 | 6154.5293 | 0 | 100% | Finished | 24597.8691 | 0 | 100 | 100 | 100 | 100 | 25.0206 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -16712.8301 | 0 | 6154.5293 | 0 | 100% | Finished | 22867.3594 | 0 | 100 | 100 | 100 | 100 | 26.914 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 4d | [5 empty] | 134973.248 |  | 15.34% |  | 31664.5605 | 31664.5605
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 46d | 103308.6875 | 0 | 134973.248 | 0 | 52.08% | Started | 31664.5605 | 31664.5605 | 100 | 100 | 52.0833 | 100 | 426.2597 | 52.0833
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 634906.0886
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 12038.2695 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 3083.78 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 31102.0195 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 132006.2031 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 322152.7812
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 85276.1921
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2004-09-24 17:00 |  | TP Name | 24/09, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 674d | [5 empty] | 2660787.2593 |  | 51.7% |  | 5905190.8224 | 8004084.4121
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 113574.6328 | 0 | 125707.7529 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1036.0711 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -437471.4062 | 0 | 48920.6875 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 10.0579 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -52304.3398 | 0 | 28721.168 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 35.4471 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 126d | [5 empty] | 1202197.0287 |  | 70.46% |  | 3497961.9115 | 3970955.3959
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 369272.1754 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 30772.6797 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -126749.8984 | 0 | 30772.6797 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 19.5354 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 53339.3145 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 6066.75 | 0 | 18463.5996 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 148.9378 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -428934.6875 | 0 | 20515.125 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 4.5645 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 4718.5898 | 0 | 14360.5898 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 148.9379 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 63596.8692 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 602.91 | 0 | 12309.0701 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 105.1504 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -29742.4199 | 0 | 8206.0488 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 21.6242 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -20625.8594 | 0 | 36927.2109 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 64.162 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 11.7313 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 221563.312 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 2514.8999 | 0 | 12309.0698 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 125.6775 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 36576.5586 | 0 | 69751.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 210.2539 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -206123.2031 | 0 | 69751.4219 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 25.2837 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 36576.5586 | 0 | 69751.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 210.2539 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 104627.1112 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 6154.5391 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -25349.9805 | 0 | 6154.5391 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 19.5354 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 148.9375 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.5645 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 22566.6297 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 200.97 | 0 | 4103.0201 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 105.1504 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -7435.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 21.6242 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 64.162 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 11.7313 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 164.6609 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 65648.3832 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 838.3 | 0 | 4103.02 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 125.6775 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 210.2539 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -60624.4688 | 0 | 20515.125 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 25.2837 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 210.2539 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 104627.1112 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 6154.5391 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -25349.9805 | 0 | 6154.5391 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 19.5354 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 148.9375 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 4.5645 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 22566.6297 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 200.97 | 0 | 4103.0201 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 105.1504 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -7435.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 21.6242 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 64.162 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 11.7313 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 65648.3832 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 838.3 | 0 | 4103.02 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 125.6775 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 210.2539 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -60624.4688 | 0 | 20515.125 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 25.2837 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 210.2539 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 110781.6328 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 12309.0703 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -50699.9609 | 0 | 12309.0703 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 19.5354 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 16412.0826 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 148.9375 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -257360.8125 | 0 | 12309.0625 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 4.5645 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 148.9375 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 38978.7188 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 301.45 | 0 | 6154.5301 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 105.1503 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -22306.8203 | 0 | 6154.5293 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 21.6242 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -11458.8096 | 0 | 20515.1201 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 64.162 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -30872.1699 | 0 | 4103.0293 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 11.7313 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 805.61 | 0 | 2051.51 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 164.6609 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 43081.761 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 1257.45 | 0 | 6154.5398 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 125.6775 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 10757.8096 | 0 | 20515.1191 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 210.2539 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -36374.6797 | 0 | 12309.082 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 25.2838 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 2151.5601 | 0 | 4103.02 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 210.2539 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 149760.3856 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 12309.0703 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -50699.9609 | 0 | 12309.0703 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 19.5354 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 28721.163 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 1348.17 | 0 | 4103.0302 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 148.9379 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -257360.8125 | 0 | 12309.0625 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 4.5645 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 4044.5 | 0 | 12309.0703 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 148.9378 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 32824.2012 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 301.45 | 0 | 6154.5301 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 105.1503 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -14871.21 | 0 | 4103.0303 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 21.6242 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | -5729.3999 | 0 | 10257.5601 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 64.162 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -61744.3398 | 0 | 8206.0508 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 11.7312 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 1611.23 | 0 | 4103.03 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 164.6613 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 75905.951 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 1676.6 | 0 | 8206.0502 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 125.6775 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 26894.5293 | 0 | 51287.7988 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 210.2539 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -36374.6797 | 0 | 12309.082 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 25.2838 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 2151.5601 | 0 | 4103.02 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 210.2539 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 41d | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 49236.2875 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 2051.5195 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -8449.9902 | 0 | 2051.5195 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 19.5355 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 10257.5592 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -128680.3984 | 0 | 6154.5391 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 4.5645 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 28721.1689 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -11458.8096 | 0 | 20515.1201 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 64.162 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -29742.4199 | 0 | 8206.0488 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 21.6242 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 8206.0398 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 2151.5601 | 0 | 4103.02 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 210.2539 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -6062.4502 | 0 | 2051.5098 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 25.2837 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 1075.78 | 0 | 2051.51 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 210.2539 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 24d | [5 empty] | 22566.6299 |  | 12.67% |  | 37333.5902 | 37333.5902
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 4103.0195 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -16899.9902 | 0 | 4103.0195 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 19.5354 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 5d | [5 empty] | 18463.6104 |  | 10.71% |  | 16330.5804 | 16330.5804
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 674.08 | 0 | 2051.5101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 148.9375 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 4d | 1458.95 | 0 | 16412.1003 | 0 | 66.67% | Started | 14953.1504 | 14953.1504 | 100 | 100 | 66.6667 | 100 | 109.7568 | 66.6667
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 29d | [5 empty] | 291325.6953 |  | 32.58% |  | 388148.375 | 861141.8594
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 29d | [5 empty] | 291325.6953 |  | 91.6% |  | 388148.375 | 412876.7344
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 111d | -96822.6797 | 0 | 291325.6953 | 0 | 55.78% | Started | 388148.375 | 388148.375 | 100 | 100 | 55.7769 | 100 | 75.0552 | 55.7769
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 138d | [5 empty] | 626701.8575 |  | 30.37% |  | 1767012.5886 | 3392912.6939
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 138d | [5 empty] | 84111.9859 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 18463.6113 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -19018.0801 | 0 | 10257.5605 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 35.0379 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -19524.0801 | 0 | 8206.0508 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 29.5925 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 131d | [5 empty] | 4103.02 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 2725.0701 | 0 | 4103.02 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 297.7626 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 8206.04 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -4159.4902 | 0 | 8206.04 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 66.3622 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 53339.3145 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -41974.2383 | 0 | 20515.1211 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 32.8298 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -20201.7793 | 0 | 4103.0215 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 16.8815 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 11851.1504 | 0 | 12309.0704 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 2688.0394 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -38470.6992 | 0 | 16412.1016 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 29.9039 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 112833.1613 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 24618.1408 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -13845.6104 | 0 | 4103.0303 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 22.8598 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 5950.3799 | 0 | 6154.5299 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 3014.7098 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -23469.3398 | 0 | 6154.541 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 20.7756 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 5950.3799 | 0 | 6154.5299 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 3014.7098 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -3795.3501 | 0 | 2051.5098 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 35.0874 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 4103.02 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -3314.53 | 0 | 2051.51 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 38.2314 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 248.15 | 0 | 2051.51 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 113.7604 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 84112.0005 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -17763.6504 | 0 | 6154.5293 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 25.7316 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -12465.5 | 0 | 4103.0293 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 24.764 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -5548.6099 | 0 | 2051.5103 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 26.9931 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -36167.8008 | 0 | 10257.5586 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 22.0947 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -31880.5605 | 0 | 10257.5605 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 24.3427 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -238115.5 | 0 | 51287.8125 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 17.7219 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 8206.0391 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 8206.0391 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -15055.4805 | 0 | 4103.0195 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 21.4162 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -12674.9297 | 0 | 4103.0195 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 24.4548 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 219511.8032 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 80008.9717 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -13123.0303 | 0 | 8206.04 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 38.4735 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -49314.1289 | 0 | 14360.5898 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 22.553 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -47582.5391 | 0 | 14360.5898 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 23.1835 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -28263.1309 | 0 | 10257.5605 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 26.6287 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -34716.6992 | 0 | 12309.0703 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 26.1752 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -32405.9492 | 0 | 20515.1211 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 38.7655 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 41030.2417 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 1746.73 | 0 | 41030.2417 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 104.4465 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 16412.0898 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -32695.1992 | 0 | 8206.0508 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 20.0631 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -33257.9805 | 0 | 8206.0391 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 19.7907 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 82060.5 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -379492.5938 | 0 | 82060.5 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 17.7792 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 17d | [5 empty] | 67065.6199 |  | 12.76% |  | 130860.4185 | 83395.19
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 17d | [5 empty] | 54756.5613 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 27634.9707 | 0 | 28086.9107 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 6214.7432 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 1601.26 | 0 | 2051.51 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 455.638 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -28937.4297 | 0 | 12309.0703 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 29.8427 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 1d | -28937.4297 | 0 | 12309.0703 | 0 | 85.71% | Started | 41246.5 | 41246.5 | 100 | 100 | 85.7143 | 100 | 29.8427 | 85.7143
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 12309.0586 |  | 100% |  | 47465.2285 | 0
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -18443.3398 | 0 | 6154.5293 | 0 | 100% | Finished | 24597.8691 | 0 | 100 | 100 | 100 | 100 | 25.0206 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -16712.8301 | 0 | 6154.5293 | 0 | 100% | Finished | 22867.3594 | 0 | 100 | 100 | 100 | 100 | 26.914 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 10d | [5 empty] | 134973.248 |  | 15.34% |  | 31664.5605 | 31664.5605
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 40d | 103308.6875 | 0 | 134973.248 | 0 | 55.56% | Started | 31664.5605 | 31664.5605 | 100 | 100 | 55.5556 | 100 | 426.2597 | 55.5556
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 12038.2695 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 3083.78 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 31102.0195 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 132006.2031 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 413377.0625 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 322152.7812
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 85276.1921
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2004-10-01 17:00 |  | TP Name | 01/10, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 679d | [5 empty] | 3304855.851 |  | 51.7% |  | 5905190.8224 | 8205959.5986
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 114297.1875 | 0 | 126430.3076 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.0263 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 114297.1875 | 0 | 126430.3076 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.0263 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 114297.1875 | 0 | 126430.3076 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.0263 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 114297.1875 | 0 | 126430.3076 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.0263 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 114297.1875 | 0 | 126430.3076 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.0263 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 114297.1875 | 0 | 126430.3076 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.0263 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -433858.625 | 0 | 52533.4688 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 10.8006 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -41399.2305 | 0 | 39626.2773 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 48.9059 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 131d | [5 empty] | 1624171.6149 |  | 70.46% |  | 3497961.9115 | 4105790.3334
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 499332.8479 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 41611.0703 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -115911.5078 | 0 | 41611.0703 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 26.4159 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 72125.8584 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 12569.79 | 0 | 24966.6396 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 201.395 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -421709.0938 | 0 | 27740.7188 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 6.1722 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 9776.5 | 0 | 19418.5 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 201.3949 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 85996.2083 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 4938.27 | 0 | 16644.4302 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 142.1852 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -26852.1895 | 0 | 11096.2793 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 29.2404 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -7619.79 | 0 | 49933.2803 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 86.7604 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -29427.0508 | 0 | 5548.1484 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 15.8631 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 1528.17 | 0 | 2774.0701 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 222.6559 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 299599.7109 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 6850.2598 | 0 | 16644.4297 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 169.9422 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 61143.5781 | 0 | 94318.4297 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 284.307 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -181556.2031 | 0 | 94318.4219 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 34.1889 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 61143.5781 | 0 | 94318.4297 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 284.307 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 141477.6232 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 8322.2188 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -23182.3008 | 0 | 8322.2188 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 26.416 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 13870.3511 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 201.3946 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -126512.7266 | 0 | 8322.2109 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.1721 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 201.3946 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 30514.7787 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 1646.09 | 0 | 5548.14 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 142.1853 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -6713.0498 | 0 | 2774.0703 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 29.2404 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -2116.6101 | 0 | 13870.3499 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 86.7604 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -29427.0508 | 0 | 5548.1484 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 15.8631 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 1528.17 | 0 | 2774.0701 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 222.6559 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 88770.2747 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 2283.4199 | 0 | 5548.1399 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 169.9423 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 17983.4004 | 0 | 27740.71 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 284.307 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -53398.8789 | 0 | 27740.7148 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 34.1889 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 17983.4004 | 0 | 27740.71 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 284.307 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 141477.6232 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 8322.2188 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -23182.3008 | 0 | 8322.2188 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 26.416 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 13870.3511 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 201.3946 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -126512.7266 | 0 | 8322.2109 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.1721 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 201.3946 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 30514.7787 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 1646.09 | 0 | 5548.14 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 142.1853 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -6713.0498 | 0 | 2774.0703 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 29.2404 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -2116.6101 | 0 | 13870.3499 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 86.7604 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -29427.0508 | 0 | 5548.1484 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 15.8631 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 1528.17 | 0 | 2774.0701 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 222.6559 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 88770.2747 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 2283.4199 | 0 | 5548.1399 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 169.9423 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 17983.4004 | 0 | 27740.71 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 284.307 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -53398.8789 | 0 | 27740.7148 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 34.1889 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 17983.4004 | 0 | 27740.71 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 284.307 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 149799.8398 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 16644.4297 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -46364.6016 | 0 | 16644.4297 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 26.4159 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 22192.562 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 201.3946 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -253025.4531 | 0 | 16644.4219 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 6.1721 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 201.3946 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 52707.3469 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 2469.1299 | 0 | 8322.21 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 142.1851 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -20139.1406 | 0 | 8322.209 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 29.2404 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -4233.2202 | 0 | 27740.7095 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 86.7604 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -29427.0508 | 0 | 5548.1484 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 15.8631 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 1528.17 | 0 | 2774.0701 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 222.6559 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 58255.5012 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 3425.1299 | 0 | 8322.2197 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 169.9421 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 17983.4004 | 0 | 27740.71 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 284.307 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -32039.3301 | 0 | 16644.4316 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 34.1889 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 3596.6799 | 0 | 5548.1399 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 284.3071 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 202507.2168 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 16644.4297 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -46364.6016 | 0 | 16644.4297 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 26.4159 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 38837.0027 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 2793.29 | 0 | 5548.1501 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 201.395 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -253025.4531 | 0 | 16644.4219 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 6.1721 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 8379.8604 | 0 | 16644.4307 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 201.395 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 44385.1416 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 2469.1299 | 0 | 8322.21 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 142.1851 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -13426.0898 | 0 | 5548.1504 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 29.2404 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | -2116.6101 | 0 | 13870.3499 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 86.7604 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -58854.1094 | 0 | 11096.2812 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 15.8631 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 3056.3501 | 0 | 5548.1501 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 222.6563 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 102640.6428 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 4566.8398 | 0 | 11096.29 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 169.9422 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 44958.5117 | 0 | 69351.7812 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 284.307 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -32039.3301 | 0 | 16644.4316 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 34.1889 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 3596.6799 | 0 | 5548.1399 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 284.3071 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 46d | [5 empty] | 0 |  | 0% |  | 0 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 |  | 0 | 0 | 21003.0098 | 2d | 0 | 0 | 0 | 21003.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 66577.6991 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 2774.0796 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -7727.4302 | 0 | 2774.0796 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 26.416 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 13870.3511 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 201.3946 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -126512.7266 | 0 | 8322.2109 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 6.1721 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 201.3946 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 38836.9888 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -4233.2202 | 0 | 27740.7095 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 86.7604 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -26852.1895 | 0 | 11096.2793 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 29.2404 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 11096.2797 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 3596.6799 | 0 | 5548.1399 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 284.3071 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -5339.8901 | 0 | 2774.0698 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 34.1889 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 1798.34 | 0 | 2774.0699 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 284.3071 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 29d | [5 empty] | 30514.78 |  | 12.67% |  | 37333.5902 | 172168.5277
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 5548.1396 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -15454.8701 | 0 | 5548.1396 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 26.4159 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 10d | [5 empty] | 24966.6404 |  | 10.71% |  | 16330.5804 | 151165.5179
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 1396.64 | 0 | 2774.0701 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 201.3946 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 7239.4199 | 0 | 22192.5703 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 148.414 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 |  | 0 | 0 | 134834.9375 | 3d | 0 | 0 | 0 | 134834.9375 | 0% | Not Started | 0 | 134834.9375 | 100 |  | 0 | 100 |  | 0
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 34d | [5 empty] | 392483.9849 |  | 32.58% |  | 388148.375 | 861141.8594
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 34d | [5 empty] | 392483.9849 |  | 91.6% |  | 388148.375 | 412876.7344
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 106d | 4335.6099 | 0 | 392483.9849 | 0 | 56.91% | Started | 388148.375 | 388148.375 | 100 | 100 | 56.9106 | 100 | 101.117 | 56.9106
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 143d | [5 empty] | 829942.6443 |  | 30.37% |  | 1767012.5886 | 3459952.943
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 143d | [5 empty] | 113736.9134 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 24966.6416 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -15405.2803 | 0 | 13870.3604 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 47.3785 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -16633.8496 | 0 | 11096.2812 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 40.0153 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 136d | [5 empty] | 5548.1399 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 4170.1899 | 0 | 5548.1399 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 402.6373 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 11096.2803 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -1269.25 | 0 | 11096.2803 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 89.7356 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 72125.8517 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -34748.6484 | 0 | 27740.7109 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 44.3927 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -18756.6602 | 0 | 5548.1406 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 22.8273 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 16186.5098 | 0 | 16644.4298 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 3634.7898 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -32690.2305 | 0 | 22192.5703 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 40.4363 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 152573.9093 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 33288.8415 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -12400.5 | 0 | 5548.1406 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 30.9112 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 8118.0601 | 0 | 8322.2101 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 4076.5174 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -21301.6699 | 0 | 8322.2109 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 28.0929 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 8118.0601 | 0 | 8322.2101 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 4076.5174 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -3072.79 | 0 | 2774.0698 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 47.4455 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 5548.1401 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -2591.97 | 0 | 2774.0701 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 51.6968 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 970.71 | 0 | 2774.07 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 153.8279 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 113736.9277 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -15595.9697 | 0 | 8322.21 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 34.7945 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -11020.3799 | 0 | 5548.1494 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 33.4861 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -4826.0498 | 0 | 2774.0703 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 36.5003 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -32555.0098 | 0 | 13870.3496 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 29.8767 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -28267.7695 | 0 | 13870.3516 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 32.9164 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -220051.5156 | 0 | 69351.7969 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 23.9637 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 11096.2793 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 11096.2793 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -13610.3604 | 0 | 5548.1396 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 28.9592 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -11229.8096 | 0 | 5548.1396 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 33.068 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 296825.6475 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 108188.7822 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -10232.79 | 0 | 11096.2803 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 52.0242 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -44256.2188 | 0 | 19418.5 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 30.4964 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -42524.6289 | 0 | 19418.5 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 31.3489 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -24650.3301 | 0 | 13870.3613 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 36.0076 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -30381.3398 | 0 | 16644.4297 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 35.3943 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -25180.3594 | 0 | 27740.7109 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 52.419 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 55481.4219 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 16197.9102 | 0 | 55481.4219 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 141.2334 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 22192.5684 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -29804.9609 | 0 | 11096.2891 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 27.1295 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -30367.7402 | 0 | 11096.2793 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 26.7612 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 110962.875 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -350590.2188 | 0 | 110962.875 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 24.0412 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 22d | [5 empty] | 84407.0374 |  | 12.76% |  | 130860.4185 | 130860.4185
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 67762.6194 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 31247.7695 | 0 | 31699.7095 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 7014.1411 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 2323.8201 | 0 | 2774.0701 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 616.1177 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -24602.0801 | 0 | 16644.4199 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 40.3535 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -24602.0801 | 0 | 16644.4199 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 40.3535 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 16644.418 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -16275.6602 | 0 | 8322.209 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 33.833 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -14545.1504 | 0 | 8322.209 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 36.3934 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 |  | 0 | 0 | 894965.9375 | 40d | 0 | 0 | 0 | 894965.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 15d | [5 empty] | 171302.8574 |  | 15.34% |  | 31664.5605 | 31664.5605
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 35d | 139638.2969 | 0 | 171302.8574 | 0 | 58.82% | Started | 31664.5605 | 31664.5605 | 100 | 100 | 58.8235 | 100 | 540.9924 | 58.8235
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 12038.2695 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 3083.78 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 31102.0195 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 132006.2031 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 413377.0625 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 322152.7812
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2004-10-07 17:00 |  | TP Name | 07/10, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 683d | [5 empty] | 3450093.5508 |  | 60.9% |  | 6955994.7071 | 9212381.1576
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -433749.5 | 0 | 52642.5938 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 10.8231 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -41093.6992 | 0 | 39931.8086 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 49.283 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 135d | [5 empty] | 1650895.7561 |  | 73.6% |  | 3653799.8588 | 4217245.9548
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 503260.9537 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 41938.4062 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -115584.1719 | 0 | 41938.4062 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 26.6237 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 72693.2373 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 12766.1904 | 0 | 25163.04 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 202.9793 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -421490.875 | 0 | 27958.9375 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 6.2207 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 9929.2598 | 0 | 19571.2598 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 202.9793 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 86672.7081 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 5069.2002 | 0 | 16775.3604 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 143.3037 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -26764.9004 | 0 | 11183.5684 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 29.4704 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -7226.98 | 0 | 50326.0903 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 87.4429 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -29383.4102 | 0 | 5591.7891 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 15.9879 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 1550 | 0 | 2795.9 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 224.4081 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 301956.6021 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 6981.1899 | 0 | 16775.3599 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 171.279 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 61885.5586 | 0 | 95060.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 286.5436 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -180814.2031 | 0 | 95060.4219 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 34.4578 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 61885.5586 | 0 | 95060.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 286.5436 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 142590.6144 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 8387.6895 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -23116.8301 | 0 | 8387.6895 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 26.6238 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 13979.4797 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 202.9795 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -126447.2578 | 0 | 8387.6797 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.2207 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 30754.839 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 1689.73 | 0 | 5591.78 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 143.3036 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -6691.2202 | 0 | 2795.8999 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 29.4705 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -2007.49 | 0 | 13979.47 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 87.443 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -29383.4102 | 0 | 5591.7891 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 15.9879 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 1550 | 0 | 2795.9 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 224.4081 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 89468.6062 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 2327.0601 | 0 | 5591.78 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 171.279 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 286.5435 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -53180.6484 | 0 | 27958.9453 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 34.4578 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 286.5435 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 142590.6144 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 8387.6895 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -23116.8301 | 0 | 8387.6895 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 26.6238 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 13979.4797 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 202.9795 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -126447.2578 | 0 | 8387.6797 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.2207 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 30754.839 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 1689.73 | 0 | 5591.78 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 143.3036 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -6691.2202 | 0 | 2795.8999 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 29.4705 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -2007.49 | 0 | 13979.47 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 87.443 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -29383.4102 | 0 | 5591.7891 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 15.9879 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 1550 | 0 | 2795.9 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 224.4081 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 89468.6062 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 2327.0601 | 0 | 5591.78 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 171.279 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 286.5435 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -53180.6484 | 0 | 27958.9453 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 34.4578 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 286.5435 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 150978.299 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 16775.3594 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -46233.6719 | 0 | 16775.3594 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 26.6237 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 22367.1594 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 202.9795 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -252894.5156 | 0 | 16775.3594 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 6.2207 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 202.9795 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 53121.9886 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 2534.6001 | 0 | 8387.6802 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 143.3037 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -20073.6699 | 0 | 8387.6797 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 29.4704 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -4014.99 | 0 | 27958.9397 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 87.4429 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -29383.4102 | 0 | 5591.7891 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 15.9879 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 1550 | 0 | 2795.9 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 224.4081 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 58713.7915 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 3490.6001 | 0 | 8387.6899 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 171.2791 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 286.5435 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -31908.3906 | 0 | 16775.3711 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 34.4578 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 3640.3301 | 0 | 5591.79 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 286.5439 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 204100.2917 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 16775.3594 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -46233.6719 | 0 | 16775.3594 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 26.6237 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 39142.5195 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 2836.9299 | 0 | 5591.79 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 202.9791 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -252894.5156 | 0 | 16775.3594 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 6.2207 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 8510.7998 | 0 | 16775.3701 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 202.9793 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 44734.3123 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 2534.6001 | 0 | 8387.6802 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 143.3037 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -13382.4502 | 0 | 5591.79 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 29.4704 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | -2007.49 | 0 | 13979.47 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 87.443 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -58766.8086 | 0 | 11183.582 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 15.9879 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 3099.99 | 0 | 5591.79 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 224.4077 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 103448.1006 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 4654.1299 | 0 | 11183.5801 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 171.279 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 45504.0898 | 0 | 69897.3594 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 286.5436 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -31908.3906 | 0 | 16775.3711 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 34.4578 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 3640.3301 | 0 | 5591.79 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 286.5439 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 50d | [5 empty] | 5591.79 |  | 5.175% |  | 21003.0098 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 5591.79 |  | 100% |  | 21003.0098 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 3d | 21003.0098 | 0 | 1d | -15411.2197 | 0 | 5591.79 | 0 | 75% | Started | 21003.0098 | 0 | 100 | 150 | 75 | 100 | 26.6238 | 75
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 |  | 0 | 0 | 2754.8601 | 2d | 0 | 0 | 0 | 2754.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 |  | 0 | 0 | 3902.05 | 2d | 0 | 0 | 0 | 3902.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 |  | 0 | 0 | 25579.1406 | 8d | 0 | 0 | 0 | 25579.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 |  | 0 | 0 | 52462.7891 | 3d | 0 | 0 | 0 | 52462.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 67101.4579 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 2795.8999 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -7705.6099 | 0 | 2795.8999 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 26.6238 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 13979.4797 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -126447.2578 | 0 | 8387.6797 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 6.2207 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 39142.5081 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -4014.99 | 0 | 27958.9397 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 87.4429 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -26764.9004 | 0 | 11183.5684 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 29.4704 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 11183.5702 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 3640.3301 | 0 | 5591.79 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 286.5439 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -5318.0698 | 0 | 2795.8901 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 34.4578 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 1820.16 | 0 | 2795.89 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 286.5434 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 33d | [5 empty] | 39142.5299 |  | 58.43% |  | 172168.5277 | 283624.1492
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 5591.79 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -15411.2197 | 0 | 5591.79 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 26.6238 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 14d | [5 empty] | 33550.7399 |  | 99.1% |  | 151165.5179 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 7414.0098 | 0 | 22367.1602 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 149.5816 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 1d | -126447.2578 | 0 | 8387.6797 | 0 | 75% | Started | 134834.9375 | 134834.9375 | 100 | 100 | 75 | 100 | 6.2207 | 75
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 |  | 0 | 0 | 1377.4301 | 1d | 0 | 0 | 0 | 1377.4301 | 0% | Not Started | 0 | 1377.4301 | 100 |  | 0 | 100 |  | 0
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 |  | 0 | 0 | 18974.2402 | 2d | 0 | 0 | 0 | 18974.2402 | 0% | Not Started | 0 | 18974.2402 | 100 |  | 0 | 100 |  | 0
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 |  | 0 | 0 | 21883.9902 | 2d | 0 | 0 | 0 | 21883.9902 | 0% | Not Started | 0 | 21883.9902 | 100 |  | 0 | 100 |  | 0
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 |  | 0 | 0 | 19184.3594 | 6d | 0 | 0 | 0 | 19184.3594 | 0% | Not Started | 0 | 19184.3594 | 100 |  | 0 | 100 |  | 0
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 |  | 0 | 0 | 50035.6016 | 10d | 0 | 0 | 0 | 50035.6016 | 0% | Not Started | 0 | 50035.6016 | 100 |  | 0 | 100 |  | 0
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 38d | [5 empty] | 395539.2051 |  | 32.58% |  | 388148.375 | 861141.8594
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 38d | [5 empty] | 395539.2051 |  | 91.6% |  | 388148.375 | 412876.7344
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 102d | 7390.8301 | 0 | 395539.2051 | 0 | 57.85% | Started | 388148.375 | 388148.375 | 100 | 100 | 57.8512 | 100 | 101.9041 | 57.8512
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 147d | [5 empty] | 947910.6247 |  | 45.76% |  | 2661978.5261 | 4354918.8805
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 147d | [5 empty] | 114631.6405 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 25163.041 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -15296.1699 | 0 | 13979.4707 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 47.7512 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -16546.5605 | 0 | 11183.5703 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 40.33 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 140d | [5 empty] | 5591.78 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 4213.8301 | 0 | 5591.78 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 405.8043 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 11183.5703 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -1181.96 | 0 | 11183.5703 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 90.4415 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 72693.2491 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -34530.4219 | 0 | 27958.9375 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 44.7419 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -18713.0098 | 0 | 5591.791 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 23.0069 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 16317.4404 | 0 | 16775.3604 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 3663.3822 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -32515.6406 | 0 | 22367.1602 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 40.7544 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 153774.1954 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 33550.7321 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -12356.8496 | 0 | 5591.791 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 31.1544 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 8183.5298 | 0 | 8387.6798 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 4108.5868 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -21236.1992 | 0 | 8387.6816 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 28.3139 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 8183.5298 | 0 | 8387.6798 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 4108.5868 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -3050.96 | 0 | 2795.8999 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 47.8188 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 5591.7802 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -2570.1499 | 0 | 2795.8901 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 52.1034 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 992.53 | 0 | 2795.89 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 155.0378 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 114631.6831 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -15530.5 | 0 | 8387.6797 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 35.0682 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -10976.7402 | 0 | 5591.7891 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 33.7495 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -4804.2202 | 0 | 2795.8999 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 36.7876 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -32445.8906 | 0 | 13979.4688 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 30.1117 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -28158.6504 | 0 | 13979.4707 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 33.1754 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -219505.9375 | 0 | 69897.375 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 24.1522 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 11183.5693 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 11183.5693 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -13566.7197 | 0 | 5591.7803 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 29.1869 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -11186.1602 | 0 | 5591.7891 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 33.3282 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 299160.668 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 109039.8555 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -10145.5 | 0 | 11183.5703 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 52.4335 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -44103.4609 | 0 | 19571.2578 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 30.7363 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -42371.8711 | 0 | 19571.2578 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 31.5955 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -24541.2207 | 0 | 13979.4707 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 36.2908 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -30250.4102 | 0 | 16775.3594 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 35.6727 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -24962.1309 | 0 | 27958.9395 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 52.8314 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 55917.8809 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 16634.3691 | 0 | 55917.8809 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 142.3444 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 22367.1504 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -29717.6699 | 0 | 11183.5801 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 27.3429 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -30280.4492 | 0 | 11183.5703 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 26.9717 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 111835.7812 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -349717.3125 | 0 | 111835.7812 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 24.2303 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 26d | [5 empty] | 196766.5379 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 68155.4295 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 31356.8809 | 0 | 31808.8209 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 7038.284 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 2345.6399 | 0 | 2795.8899 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 620.9639 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -24471.1406 | 0 | 16775.3594 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 40.671 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -24471.1406 | 0 | 16775.3594 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 40.671 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 16775.3584 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -16210.1904 | 0 | 8387.6787 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 34.0992 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -14479.6797 | 0 | 8387.6797 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 36.6797 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 2d | [5 empty] | 111835.75 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 38d | -783130.1875 | 0 | 111835.75 | 0 | 51.28% | Started | 894965.9375 | 894965.9375 | 100 | 100 | 51.2821 | 100 | 12.4961 | 51.2821
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 19d | [5 empty] | 172394.0137 |  | 15.34% |  | 31664.5605 | 31664.5605
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 31d | 140729.4531 | 0 | 172394.0137 | 0 | 61.73% | Started | 31664.5605 | 31664.5605 | 100 | 100 | 61.7284 | 100 | 544.4384 | 61.7284
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 12038.2695 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 3083.78 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 31102.0195 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 132006.2031 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 413377.0625 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 322152.7812
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2004-10-14 17:00 |  | TP Name | 14/10, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 688d | [5 empty] | 3559133.4419 |  | 62.8% |  | 7172500.8387 | 9487887.3988
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 114319.0078 | 0 | 126452.1279 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.2062 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -433749.5 | 0 | 52642.5938 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 10.8231 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -41093.6992 | 0 | 39931.8086 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 49.283 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 140d | [5 empty] | 1759935.6472 |  | 77.96% |  | 3870305.9904 | 4219197.4148
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 503260.9537 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 41938.4062 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -115584.1719 | 0 | 41938.4062 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 26.6237 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 72693.2373 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 12766.1904 | 0 | 25163.04 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 202.9793 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -421490.875 | 0 | 27958.9375 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 6.2207 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 9929.2598 | 0 | 19571.2598 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 202.9793 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 86672.7081 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 5069.2002 | 0 | 16775.3604 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 143.3037 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -26764.9004 | 0 | 11183.5684 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 29.4704 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -7226.98 | 0 | 50326.0903 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 87.4429 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -29383.4102 | 0 | 5591.7891 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 15.9879 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 1550 | 0 | 2795.9 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 224.4081 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 301956.6021 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 6981.1899 | 0 | 16775.3599 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 171.279 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 61885.5586 | 0 | 95060.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 286.5436 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -180814.2031 | 0 | 95060.4219 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 34.4578 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 61885.5586 | 0 | 95060.4102 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 286.5436 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 142590.6144 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 8387.6895 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -23116.8301 | 0 | 8387.6895 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 26.6238 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 13979.4797 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 202.9795 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -126447.2578 | 0 | 8387.6797 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.2207 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 30754.839 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 1689.73 | 0 | 5591.78 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 143.3036 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -6691.2202 | 0 | 2795.8999 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 29.4705 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -2007.49 | 0 | 13979.47 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 87.443 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -29383.4102 | 0 | 5591.7891 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 15.9879 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 1550 | 0 | 2795.9 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 224.4081 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 89468.6062 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 2327.0601 | 0 | 5591.78 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 171.279 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 286.5435 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -53180.6484 | 0 | 27958.9453 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 34.4578 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 286.5435 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 142590.6144 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 8387.6895 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -23116.8301 | 0 | 8387.6895 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 26.6238 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 13979.4797 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 202.9795 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -126447.2578 | 0 | 8387.6797 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.2207 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 30754.839 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 1689.73 | 0 | 5591.78 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 143.3036 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -6691.2202 | 0 | 2795.8999 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 29.4705 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -2007.49 | 0 | 13979.47 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 87.443 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -29383.4102 | 0 | 5591.7891 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 15.9879 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 1550 | 0 | 2795.9 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 224.4081 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 89468.6062 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 2327.0601 | 0 | 5591.78 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 171.279 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 286.5435 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -53180.6484 | 0 | 27958.9453 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 34.4578 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 286.5435 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 150978.299 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 16775.3594 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -46233.6719 | 0 | 16775.3594 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 26.6237 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 22367.1594 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 202.9795 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -252894.5156 | 0 | 16775.3594 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 6.2207 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 202.9795 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 53121.9886 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 2534.6001 | 0 | 8387.6802 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 143.3037 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -20073.6699 | 0 | 8387.6797 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 29.4704 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -4014.99 | 0 | 27958.9397 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 87.4429 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -29383.4102 | 0 | 5591.7891 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 15.9879 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 1550 | 0 | 2795.9 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 224.4081 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 58713.7915 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 3490.6001 | 0 | 8387.6899 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 171.2791 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 18201.6309 | 0 | 27958.9404 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 286.5435 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -31908.3906 | 0 | 16775.3711 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 34.4578 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 3640.3301 | 0 | 5591.79 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 286.5439 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 204100.2917 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 16775.3594 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -46233.6719 | 0 | 16775.3594 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 26.6237 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 39142.5195 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 2836.9299 | 0 | 5591.79 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 202.9791 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -252894.5156 | 0 | 16775.3594 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 6.2207 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 8510.7998 | 0 | 16775.3701 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 202.9793 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 44734.3123 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 2534.6001 | 0 | 8387.6802 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 143.3037 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -13382.4502 | 0 | 5591.79 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 29.4704 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | -2007.49 | 0 | 13979.47 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 87.443 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -58766.8086 | 0 | 11183.582 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 15.9879 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 3099.99 | 0 | 5591.79 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 224.4077 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 103448.1006 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 4654.1299 | 0 | 11183.5801 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 171.279 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 45504.0898 | 0 | 69897.3594 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 286.5436 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -31908.3906 | 0 | 16775.3711 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 34.4578 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 3640.3301 | 0 | 5591.79 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 286.5439 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 55d | [5 empty] | 55917.8805 |  | 31.06% |  | 126053.5199 | 0
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 5591.79 |  | 100% |  | 21003.0098 | 0
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -15411.2197 | 0 | 5591.79 | 0 | 100% | Finished | 21003.0098 | 0 | 100 | 350 | 100 | 100 | 26.6238 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 2d | [5 empty] | 8387.6901 |  | 1.806% |  | 4132.2902 | 0
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 0 | 100 | 100 | 100 | 100 | 202.9795 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 |  | 0 | 0 | 224724.9062 | 5d | 0 | 0 | 0 | 224724.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 2836.9299 | 0 | 5591.79 | 0 | 100% | Finished | 2754.8601 | 0 | 100 | 50 | 100 | 100 | 202.9791 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 1d | [5 empty] | 41938.4004 |  | 96.43% |  | 100918.22 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 3d | 1689.73 | 0 | 5591.78 | 0 | 57.14% | Started | 3902.05 | 0 | 100 | 200 | 57.1429 | 100 | 143.3036 | 57.1429
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 1d | -13382.4502 | 0 | 5591.79 | 0 | 66.67% | Started | 18974.2402 | 0 | 100 | 100 | 66.6667 | 100 | 29.4704 | 66.6667
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 2d | -3211.99 | 0 | 22367.1506 | 0 | 60% | Started | 25579.1406 | 0 | 100 | 37.5 | 60 | 100 | 87.4429 | 60
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 2d | -44075.1094 | 0 | 8387.6797 | 0 | 60% | Started | 52462.7891 | 0 | 100 | 100 | 60 | 100 | 15.9879 | 60
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 |  | 0 | 0 | 3737.7 | 3d | 0 | 0 | 0 | 3737.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 |  | 0 | 0 | 8161.8101 | 5d | 0 | 0 | 0 | 8161.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 |  | 0 | 0 | 9757.3096 | 10d | 0 | 0 | 0 | 9757.3096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 67101.4579 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 2795.8999 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -7705.6099 | 0 | 2795.8999 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 26.6238 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 13979.4797 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -126447.2578 | 0 | 8387.6797 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 6.2207 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 39142.5081 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -4014.99 | 0 | 27958.9397 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 87.4429 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -26764.9004 | 0 | 11183.5684 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 29.4704 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 11183.5702 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 3640.3301 | 0 | 5591.79 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 286.5439 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -5318.0698 | 0 | 2795.8901 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 34.4578 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 1820.16 | 0 | 2795.89 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 286.5434 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 38d | [5 empty] | 97856.3306 |  | 96.25% |  | 283624.1492 | 285575.6091
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 5591.79 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -15411.2197 | 0 | 5591.79 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 26.6238 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 36346.6399 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 7414.0098 | 0 | 22367.1602 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 149.5816 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -126447.2578 | 0 | 8387.6797 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.2207 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 1418.47 | 0 | 2795.9 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 202.9795 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 3d | [5 empty] | 55917.9006 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -13382.4502 | 0 | 5591.79 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 29.4704 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -16292.2002 | 0 | 5591.79 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 25.552 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 4d | -2408.99 | 0 | 16775.3694 | 0 | 60% | Started | 19184.3594 | 19184.3594 | 100 | 100 | 60 | 100 | 87.4429 | 60
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 10d | 50035.6016 | 0 | 8d | -22076.6504 | 0 | 27958.9512 | 0 | 55.56% | Started | 50035.6016 | 50035.6016 | 100 | 100 | 55.5556 | 100 | 55.8781 | 55.5556
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1951.46
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 |  | 0 | 0 | 1951.46 | 2d | 0 | 0 | 0 | 1951.46 | 0% | Not Started | 0 | 1951.46 | 100 |  | 0 | 100 |  | 0
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 |  | 0 | 0 | 8113.96 | 1d | 0 | 0 | 0 | 8113.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 43d | [5 empty] | 395539.2051 |  | 32.58% |  | 388148.375 | 861141.8594
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 43d | [5 empty] | 395539.2051 |  | 91.6% |  | 388148.375 | 412876.7344
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 97d | 7390.8301 | 0 | 395539.2051 | 0 | 59.07% | Started | 388148.375 | 388148.375 | 100 | 100 | 59.0717 | 100 | 101.9041 | 59.0717
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 152d | [5 empty] | 947910.6247 |  | 45.76% |  | 2661978.5261 | 4628473.6618
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 152d | [5 empty] | 114631.6405 |  | 93.15% |  | 212884.1327 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 25163.041 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -15296.1699 | 0 | 13979.4707 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 47.7512 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -16546.5605 | 0 | 11183.5703 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 40.33 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 145d | [5 empty] | 5591.78 |  | 8.094% |  | 1377.95 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 4213.8301 | 0 | 5591.78 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 405.8043 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 |  | 0 | 0 | 15645.8799 | 2d | 0 | 0 | 0 | 15645.8799 | 0% | Not Started | 0 | 15645.8799 | 100 |  | 0 | 100 |  | 0
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 11183.5703 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -1181.96 | 0 | 11183.5703 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 90.4415 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 72693.2491 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -34530.4219 | 0 | 27958.9375 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 44.7419 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -18713.0098 | 0 | 5591.791 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 23.0069 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 16317.4404 | 0 | 16775.3604 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 3663.3822 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -32515.6406 | 0 | 22367.1602 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 40.7544 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 153774.1954 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 33550.7321 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -12356.8496 | 0 | 5591.791 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 31.1544 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 8183.5298 | 0 | 8387.6798 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 4108.5868 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -21236.1992 | 0 | 8387.6816 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 28.3139 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 8183.5298 | 0 | 8387.6798 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 4108.5868 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -3050.96 | 0 | 2795.8999 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 47.8188 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 5591.7802 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -2570.1499 | 0 | 2795.8901 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 52.1034 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 992.53 | 0 | 2795.89 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 155.0378 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 114631.6831 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -15530.5 | 0 | 8387.6797 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 35.0682 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -10976.7402 | 0 | 5591.7891 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 33.7495 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -4804.2202 | 0 | 2795.8999 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 36.7876 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -32445.8906 | 0 | 13979.4688 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 30.1117 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -28158.6504 | 0 | 13979.4707 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 33.1754 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -219505.9375 | 0 | 69897.375 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 24.1522 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 11183.5693 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 11183.5693 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -13566.7197 | 0 | 5591.7803 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 29.1869 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -11186.1602 | 0 | 5591.7891 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 33.3282 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 299160.668 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 109039.8555 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -10145.5 | 0 | 11183.5703 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 52.4335 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -44103.4609 | 0 | 19571.2578 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 30.7363 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -42371.8711 | 0 | 19571.2578 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 31.5955 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -24541.2207 | 0 | 13979.4707 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 36.2908 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -30250.4102 | 0 | 16775.3594 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 35.6727 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -24962.1309 | 0 | 27958.9395 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 52.8314 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 55917.8809 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 16634.3691 | 0 | 55917.8809 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 142.3444 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 22367.1504 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -29717.6699 | 0 | 11183.5801 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 27.3429 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -30280.4492 | 0 | 11183.5703 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 26.9717 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 111835.7812 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -349717.3125 | 0 | 111835.7812 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 24.2303 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 31d | [5 empty] | 196766.5379 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 68155.4295 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 31356.8809 | 0 | 31808.8209 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 7038.284 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 2345.6399 | 0 | 2795.8899 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 620.9639 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -24471.1406 | 0 | 16775.3594 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 40.671 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -24471.1406 | 0 | 16775.3594 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 40.671 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 16775.3584 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -16210.1904 | 0 | 8387.6787 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 34.0992 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -14479.6797 | 0 | 8387.6797 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 36.6797 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 7d | [5 empty] | 111835.75 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 33d | -783130.1875 | 0 | 111835.75 | 0 | 54.79% | Started | 894965.9375 | 894965.9375 | 100 | 100 | 54.7945 | 100 | 12.4961 | 54.7945
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 24d | [5 empty] | 172394.0137 |  | 15.34% |  | 31664.5605 | 31664.5605
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 26d | 140729.4531 | 0 | 172394.0137 | 0 | 65.79% | Started | 31664.5605 | 31664.5605 | 100 | 100 | 65.7895 | 100 | 544.4384 | 65.7895
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 12038.2695 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 3083.78 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 31102.0195 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 132006.2031 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 413377.0625 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2004-10-29 17:00 |  | TP Name | 29/10, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 699d | [5 empty] | 3714857.258 |  | 65.19% |  | 7445569.5943 | 9754945.6946
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 114393.4297 | 0 | 126526.5498 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.8196 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 114393.4297 | 0 | 126526.5498 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.8196 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 114393.4297 | 0 | 126526.5498 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.8196 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 114393.4297 | 0 | 126526.5498 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.8196 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 114393.4297 | 0 | 126526.5498 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.8196 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 114393.4297 | 0 | 126526.5498 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1042.8196 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -433377.4062 | 0 | 53014.6875 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 10.8996 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -40051.8281 | 0 | 40973.6797 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 50.5689 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 151d | [5 empty] | 1884169.6685 |  | 83.15% |  | 4127728.8661 | 4486255.7106
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 516656.4998 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 43054.7109 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -114467.8672 | 0 | 43054.7109 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 27.3324 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 74628.1758 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 13435.9697 | 0 | 25832.8193 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 208.3821 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -420746.6562 | 0 | 28703.1562 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 6.3863 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 10450.2002 | 0 | 20092.2002 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 208.3821 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 88979.7175 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 5515.7202 | 0 | 17221.8804 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 147.1181 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -26467.2207 | 0 | 11481.248 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 30.2548 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | -5887.4302 | 0 | 51665.6401 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 89.7704 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -29234.5703 | 0 | 5740.6289 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 16.4134 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 1624.42 | 0 | 2870.3201 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 230.3813 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 309993.8955 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 7427.71 | 0 | 17221.8799 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 175.8381 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 64415.8203 | 0 | 97590.6719 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 294.1706 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -178283.9531 | 0 | 97590.6719 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 35.375 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 64415.8203 | 0 | 97590.6719 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 294.1706 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 146386.0081 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 8610.9492 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -22893.5703 | 0 | 8610.9492 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 27.3324 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 14351.5776 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 208.3823 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -126224 | 0 | 8610.9375 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.3863 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 208.3823 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 31573.4492 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 1838.5699 | 0 | 5740.62 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 147.1181 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -6616.7998 | 0 | 2870.3203 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 30.2549 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | -1635.4 | 0 | 14351.5599 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 89.7704 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -29234.5703 | 0 | 5740.6289 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 16.4134 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 1624.42 | 0 | 2870.3201 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 230.3813 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 91850.032 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 2475.8999 | 0 | 5740.6199 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 175.838 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 18945.8301 | 0 | 28703.1396 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 294.1706 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -52436.4609 | 0 | 28703.1328 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 35.375 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 18945.8301 | 0 | 28703.1396 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 294.1706 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 146386.0081 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 8610.9492 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -22893.5703 | 0 | 8610.9492 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 27.3324 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 14351.5776 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 208.3823 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -126224 | 0 | 8610.9375 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.3863 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 208.3823 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 31573.4492 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 1838.5699 | 0 | 5740.62 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 147.1181 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -6616.7998 | 0 | 2870.3203 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 30.2549 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | -1635.4 | 0 | 14351.5599 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 89.7704 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -29234.5703 | 0 | 5740.6289 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 16.4134 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 1624.42 | 0 | 2870.3201 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 230.3813 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 91850.032 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 2475.8999 | 0 | 5740.6199 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 175.838 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 18945.8301 | 0 | 28703.1396 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 294.1706 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -52436.4609 | 0 | 28703.1328 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 35.375 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 18945.8301 | 0 | 28703.1396 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 294.1706 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 154996.9783 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 17221.8828 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -45787.1484 | 0 | 17221.8828 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 27.3324 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 22962.5151 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 208.3823 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -252448 | 0 | 17221.875 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 6.3863 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 208.3823 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 54535.9683 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 2757.8601 | 0 | 8610.9402 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 147.1181 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -19850.4102 | 0 | 8610.9395 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 30.2549 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | -3270.79 | 0 | 28703.1396 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 89.7704 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -29234.5703 | 0 | 5740.6289 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 16.4134 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 1624.42 | 0 | 2870.3201 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 230.3813 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 60276.6121 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 3713.8601 | 0 | 8610.95 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 175.8381 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 18945.8301 | 0 | 28703.1396 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 294.1706 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -31461.8691 | 0 | 17221.8926 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 35.375 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 3789.1699 | 0 | 5740.6299 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 294.171 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 209532.9005 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 17221.8828 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -45787.1484 | 0 | 17221.8828 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 27.3324 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 40184.385 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 2985.77 | 0 | 5740.6301 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 208.3819 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -252448 | 0 | 17221.875 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 6.3863 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 8957.3096 | 0 | 17221.8799 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 208.382 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 45925.0101 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 2757.8601 | 0 | 8610.9402 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 147.1181 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -13233.6104 | 0 | 5740.6299 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 30.2549 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | -1635.4 | 0 | 14351.5599 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 89.7704 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -58469.1406 | 0 | 11481.25 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 16.4134 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 3248.8301 | 0 | 5740.6301 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 230.3808 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 106201.6226 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 4951.8101 | 0 | 11481.2603 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 175.8381 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 47364.5703 | 0 | 71757.8398 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 294.1707 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -31461.8691 | 0 | 17221.8926 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 35.375 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 3789.1699 | 0 | 5740.6299 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 294.171 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 66d | [5 empty] | 123423.5558 |  | 91.76% |  | 372435.2457 | 247105.3461
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 5740.6299 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -15262.3799 | 0 | 5740.6299 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 27.3324 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 22962.5283 |  | 100% |  | 228857.1964 | 226102.3363
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 208.3823 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -210373.3281 | 0 | 14351.5781 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 6.3863 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 2985.77 | 0 | 5740.6301 | 0 | 100% | Finished | 2754.8601 | 0 | 100 | 50 | 100 | 100 | 208.3819 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 51665.6881 |  | 100% |  | 104655.9199 | 0
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 1838.5699 | 0 | 5740.62 | 0 | 100% | Finished | 3902.05 | 0 | 100 | 200 | 100 | 100 | 147.1181 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -13233.5703 | 0 | 5740.6699 | 0 | 100% | Finished | 18974.2402 | 0 | 100 | 100 | 100 | 100 | 30.2551 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | -2616.6299 | 0 | 22962.5107 | 0 | 100% | Finished | 25579.1406 | 0 | 100 | 37.5 | 100 | 100 | 89.7705 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -43851.8516 | 0 | 8610.9375 | 0 | 100% | Finished | 52462.7891 | 0 | 100 | 100 | 100 | 100 | 16.4134 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 4873.25 | 0 | 8610.95 | 0 | 100% | Finished | 3737.7 | 0 | 100 | 100 | 100 | 100 | 230.381 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 9d | [5 empty] | 43054.7095 |  | 34.9% |  | 17919.1196 | 0
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 6189.7598 | 0 | 14351.5698 | 0 | 100% | Finished | 8161.8101 | 0 | 100 | 100 | 100 | 100 | 175.8381 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 18945.8301 | 0 | 28703.1396 | 0 | 100% | Finished | 9757.3096 | 0 | 100 | 50 | 100 | 100 | 294.1706 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 |  | 0 | 0 | 32455.8398 | 4d | 0 | 0 | 0 | 32455.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 |  | 0 | 0 | 975.73 | 1d | 0 | 0 | 0 | 975.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 68887.535 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 2870.3198 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -7631.1899 | 0 | 2870.3198 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 27.3324 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 14351.5776 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 208.3823 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -126224 | 0 | 8610.9375 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 6.3863 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 208.3823 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 40184.3877 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | -3270.79 | 0 | 28703.1396 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 89.7704 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -26467.2207 | 0 | 11481.248 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 30.2548 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 11481.2499 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 3789.1699 | 0 | 5740.6299 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 294.171 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -5243.6499 | 0 | 2870.3101 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 35.375 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 1894.58 | 0 | 2870.3099 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 294.1705 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 49d | [5 empty] | 111942.2474 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 5740.6299 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -15262.3799 | 0 | 5740.6299 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 27.3324 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 37314.0879 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 208.3823 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 8009.3599 | 0 | 22962.5103 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 153.563 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -126224 | 0 | 8610.9375 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 6.3863 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 1492.89 | 0 | 2870.3201 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 208.3823 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 14d | [5 empty] | 57406.2798 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -13233.6104 | 0 | 5740.6299 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 30.2549 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -16143.3604 | 0 | 5740.6299 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 26.2321 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | -1962.48 | 0 | 17221.8794 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 89.7704 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 1d | -21332.4609 | 0 | 28703.1406 | 0 | 93.33% | Started | 50035.6016 | 50035.6016 | 100 | 140 | 93.3333 | 100 | 57.3654 | 93.3333
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 11481.2499 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 3789.1699 | 0 | 5740.6299 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 294.171 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -5243.6499 | 0 | 2870.3101 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 35.375 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 1894.58 | 0 | 2870.3099 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 294.1705 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 54d | [5 empty] | 405957.9355 |  | 32.58% |  | 388148.375 | 872005.1191
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 54d | [5 empty] | 405957.9355 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 86d | 17809.5605 | 0 | 405957.9355 | 0 | 61.95% | Started | 388148.375 | 388148.375 | 100 | 100 | 61.9469 | 100 | 104.5883 | 61.9469
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 163d | [5 empty] | 977539.9236 |  | 46.03% |  | 2677624.406 | 4628473.6618
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 123423.4854 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 25832.8213 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -14924.0703 | 0 | 14351.5703 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 49.0222 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -16248.8799 | 0 | 11481.251 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 41.4035 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 11481.2498 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 4362.6699 | 0 | 5740.6199 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 416.6058 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -9905.25 | 0 | 5740.6299 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 36.691 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 11481.2502 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | -884.28 | 0 | 11481.2502 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 92.8488 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 74628.1642 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -33786.2188 | 0 | 28703.1406 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 45.9328 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -18564.1699 | 0 | 5740.6309 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 23.6193 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 16763.9609 | 0 | 17221.881 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 3760.8928 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -31920.2891 | 0 | 22962.5117 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 41.8392 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 157867.2711 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 34443.7722 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -12208.0098 | 0 | 5740.6309 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 31.9837 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 8406.79 | 0 | 8610.94 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 4217.9477 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -21012.9395 | 0 | 8610.9414 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 29.0676 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 8406.79 | 0 | 8610.94 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 4217.9477 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -2976.54 | 0 | 2870.3198 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 49.0916 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 5740.62 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -2495.73 | 0 | 2870.3101 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 53.4903 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 1066.95 | 0 | 2870.3099 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 159.1646 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 117682.8789 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -15307.2402 | 0 | 8610.9395 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 36.0017 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -10827.9004 | 0 | 5740.6289 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 34.6478 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -4729.7998 | 0 | 2870.3203 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 37.7668 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -32073.7891 | 0 | 14351.5703 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 30.9132 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -27786.5605 | 0 | 14351.5605 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 34.0584 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -217645.4531 | 0 | 71757.8594 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 24.7951 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 11481.2393 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 11481.2393 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -13417.8799 | 0 | 5740.6201 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 29.9638 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -11037.3301 | 0 | 5740.6191 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 34.2153 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 307123.5742 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 111942.2305 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -9847.8203 | 0 | 11481.25 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 53.8291 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -43582.5195 | 0 | 20092.1992 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 31.5544 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -41850.9297 | 0 | 20092.1992 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 32.4365 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -24169.1191 | 0 | 14351.5723 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 37.2568 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -29803.8906 | 0 | 17221.8789 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 36.6222 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -24217.9395 | 0 | 28703.1309 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 54.2376 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 57406.2715 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 18122.7598 | 0 | 57406.2715 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 146.1332 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 22962.5098 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -29419.9902 | 0 | 11481.2598 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 28.0707 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -29982.7695 | 0 | 11481.25 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 27.6897 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 114812.5625 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -346740.5312 | 0 | 114812.5625 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 24.8753 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 42d | [5 empty] | 201529.3712 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 69494.9922 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 31728.9805 | 0 | 32180.9205 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 7120.6178 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 2420.0601 | 0 | 2870.3101 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 637.4925 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -24024.6191 | 0 | 17221.8809 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 41.7536 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -24024.6191 | 0 | 17221.8809 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 41.7536 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 17221.8789 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -15986.9297 | 0 | 8610.9395 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 35.0069 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -14256.4199 | 0 | 8610.9395 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 37.656 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 18d | [5 empty] | 114812.5 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 22d | -780153.4375 | 0 | 114812.5 | 0 | 64.52% | Started | 894965.9375 | 894965.9375 | 100 | 100 | 64.5161 | 100 | 12.8287 | 64.5161
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 35d | [5 empty] | 176114.9824 |  | 15.34% |  | 31664.5605 | 31664.5605
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 15d | 144450.4219 | 0 | 176114.9824 | 0 | 76.92% | Started | 31664.5605 | 31664.5605 | 100 | 100 | 76.9231 | 100 | 556.1896 | 76.9231
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 |  | 0 | 0 | 12038.2695 | 17d | 0 | 0 | 0 | 12038.2695 | 0% | Not Started | 0 | 12038.2695 | 100 |  | 0 | 100 |  | 0
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 |  | 0 | 0 | 3083.78 | 14d | 0 | 0 | 0 | 3083.78 | 0% | Not Started | 0 | 3083.78 | 100 |  | 0 | 100 |  | 0
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 31102.0195 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 132006.2031 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 |  | 0 | 0 | 413377.0625 | 70d | 0 | 0 | 0 | 413377.0625 | 0% | Not Started | 0 | 413377.0625 | 100 |  | 0 | 100 |  | 0
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2004-11-09 17:00 |  | TP Name | 09/11, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 705d | [5 empty] | 4734178.3375 |  | 69.23% |  | 7907500.2762 | 10046107.7185
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -429718.6875 | 0 | 56673.4062 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 11.6518 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -31030.3398 | 0 | 49995.168 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 61.703 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 157d | [5 empty] | 2323820.1344 |  | 83.82% |  | 4161160.4359 | 4777417.7345
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 632647.0992 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 52720.5859 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -104801.9922 | 0 | 52720.5859 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 33.4686 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 91382.3525 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 19235.5 | 0 | 31632.3496 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 255.1644 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -414302.75 | 0 | 35147.0625 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 7.82 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 14960.9404 | 0 | 24602.9404 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 255.1643 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 108955.8893 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 9382.0703 | 0 | 21088.2305 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 180.1464 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -23889.6504 | 0 | 14058.8184 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 37.0471 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 5711.6401 | 0 | 63264.7104 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 109.9241 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 20.0983 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 379588.2715 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 11294.0703 | 0 | 21088.2402 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 215.3142 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 86325.1562 | 0 | 119500.0078 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 360.2126 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -156374.6094 | 0 | 119500.0156 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 43.3168 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 86325.1562 | 0 | 119500.0078 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 360.2126 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 179250.0281 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 10544.1191 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -20960.4004 | 0 | 10544.1191 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 33.4686 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 255.1643 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 38661.78 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 180.1466 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -5972.4102 | 0 | 3514.71 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 37.0472 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 109.9242 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 20.0983 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 282.1021 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 112470.5916 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 3764.6899 | 0 | 7029.4099 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 215.3143 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 360.2126 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -45992.5312 | 0 | 35147.0625 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 43.3168 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 360.2126 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 179250.0281 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 10544.1191 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -20960.4004 | 0 | 10544.1191 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 33.4686 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 255.1643 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 38661.78 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 180.1466 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -5972.4102 | 0 | 3514.71 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 37.0472 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 109.9242 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 20.0983 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 112470.5916 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 3764.6899 | 0 | 7029.4099 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 215.3143 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 360.2126 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -45992.5312 | 0 | 35147.0625 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 43.3168 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 360.2126 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 189794.1356 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 21088.2305 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -41920.8008 | 0 | 21088.2305 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 33.4686 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 28117.6545 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 255.1643 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -248581.6406 | 0 | 21088.2344 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 7.82 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 255.1643 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 66779.4191 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 4691.04 | 0 | 10544.1201 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 180.1465 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -17917.2402 | 0 | 10544.1094 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 37.0471 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 3173.1299 | 0 | 35147.0596 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 109.9241 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 20.0983 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 73808.8315 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 5647.0298 | 0 | 10544.1196 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 215.314 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 360.2126 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -27595.5195 | 0 | 21088.2422 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 43.3168 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 256573.5665 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 21088.2305 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -41920.8008 | 0 | 21088.2305 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 33.4686 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 49205.8948 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 4274.5601 | 0 | 7029.4202 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 255.1643 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -248581.6406 | 0 | 21088.2344 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 7.82 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 12823.6699 | 0 | 21088.2402 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 255.1644 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 56235.3104 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 4691.04 | 0 | 10544.1201 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 180.1465 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 109.9242 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -55891.5703 | 0 | 14058.8203 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 20.0983 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 4537.6201 | 0 | 7029.4202 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 282.1021 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 130044.1309 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 7529.3799 | 0 | 14058.8301 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 215.3141 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 63474.3789 | 0 | 87867.6484 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 360.2127 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -27595.5195 | 0 | 21088.2422 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 43.3168 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 360.2129 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 168705.911 |  | 100% |  | 405866.8156 | 358940.2362
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 7029.4102 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -13973.5996 | 0 | 7029.4102 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 33.4686 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 28117.6615 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -207151.375 | 0 | 17573.5312 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 7.82 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 4274.5601 | 0 | 7029.4202 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 255.1643 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 63264.71 |  | 100% |  | 104655.9199 | 100918.22
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 180.1466 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 2538.51 | 0 | 28117.6506 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 109.9241 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -41918.6797 | 0 | 10544.1094 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 20.0983 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 6806.4199 | 0 | 10544.1199 | 0 | 100% | Finished | 3737.7 | 0 | 100 | 100 | 100 | 100 | 282.1018 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 70294.1294 |  | 100% |  | 51350.6895 | 8161.8101
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 9411.7197 | 0 | 17573.5298 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 215.3141 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 0 | 100 | 50 | 100 | 100 | 360.2126 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -18397.0098 | 0 | 14058.8301 | 0 | 100% | Finished | 32455.8398 | 0 | 100 | 75 | 100 | 100 | 43.3168 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 0 | 100 | 100 | 100 | 100 | 360.2134 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 84352.9553 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 3514.71 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -6986.7998 | 0 | 3514.71 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 33.4686 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 7.82 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 49205.8779 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 3173.1299 | 0 | 35147.0596 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 109.9241 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -23889.6504 | 0 | 14058.8184 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 37.0471 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 14058.8301 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -4599.25 | 0 | 3514.71 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 43.3168 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 360.2134 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 137073.559 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 7029.4102 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -13973.5996 | 0 | 7029.4102 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 33.4686 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 45691.1877 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 13164.5 | 0 | 28117.6504 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 188.0383 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 70294.131 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -14854.5801 | 0 | 7029.4102 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 32.1212 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 1903.88 | 0 | 21088.2394 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 109.9241 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -14888.54 | 0 | 35147.0615 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 70.2441 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 14058.8301 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -4599.25 | 0 | 3514.71 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 43.3168 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 360.2134 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 60d | [5 empty] | 496172.8516 |  | 32.58% |  | 388148.375 | 1051332.2529
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 60d | [5 empty] | 496172.8516 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 80d | 108024.4766 | 0 | 496172.8516 | 0 | 63.64% | Started | 388148.375 | 388148.375 | 100 | 100 | 63.6364 | 100 | 127.8307 | 63.6364
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 179327.1338
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 175400.3438 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 169d | [5 empty] | 1540663.9863 |  | 53.39% |  | 3106123.518 | 4628473.6618
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 151132.3416 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 31632.3516 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -11702.1104 | 0 | 17573.5303 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 60.0278 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -13671.3096 | 0 | 14058.8213 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 50.6987 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 14058.8201 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 5651.46 | 0 | 7029.4099 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 510.1354 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -8616.4697 | 0 | 7029.4102 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 44.9282 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 14058.8203 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 1693.29 | 0 | 14058.8203 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 113.6936 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 91382.3497 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -27342.3008 | 0 | 35147.0586 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 56.2449 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -17275.3906 | 0 | 7029.4102 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 28.9219 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 20630.3105 | 0 | 21088.2306 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 4605.2214 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -26765.1504 | 0 | 28117.6504 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 51.2322 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 193308.837 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 42176.4807 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -10919.2305 | 0 | 7029.4102 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 39.164 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 10339.9697 | 0 | 10544.1197 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5164.8886 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -19079.7598 | 0 | 10544.1211 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 35.5933 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 10339.9697 | 0 | 10544.1197 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5164.8886 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -2332.1499 | 0 | 3514.71 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 60.1128 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 7029.4 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -1851.34 | 0 | 3514.7001 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 65.499 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 1711.34 | 0 | 3514.7 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 194.8973 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 144102.9563 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -13374.0596 | 0 | 10544.1201 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 44.0841 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -9539.1201 | 0 | 7029.4092 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 42.4263 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -4085.4099 | 0 | 3514.7102 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 46.2455 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -28851.8301 | 0 | 17573.5293 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 37.8533 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -24564.5898 | 0 | 17573.5312 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 41.7046 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -201535.6562 | 0 | 87867.6562 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 30.3617 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 14058.8193 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 14058.8193 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -12129.0898 | 0 | 7029.4102 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 36.6908 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -9748.54 | 0 | 7029.4092 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 41.8967 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 376073.5508 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 137073.5293 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -7270.25 | 0 | 14058.8203 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 65.9139 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -39071.7812 | 0 | 24602.9375 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 38.6385 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -37340.1797 | 0 | 24602.9492 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 39.7186 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -20947.1602 | 0 | 17573.5312 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 45.621 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -25937.5391 | 0 | 21088.2305 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 44.844 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -17774.0098 | 0 | 35147.0605 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 66.4141 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 70294.1211 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 31010.6094 | 0 | 70294.1211 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 178.9405 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 28117.6504 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -26842.4199 | 0 | 14058.8301 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 34.3726 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -27405.1992 | 0 | 14058.8203 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 33.9061 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 140588.25 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -320964.8438 | 0 | 140588.25 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 30.4598 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 48d | [5 empty] | 242770.511 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 81094.0423 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 34950.9414 | 0 | 35402.8814 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 7833.5357 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 3064.45 | 0 | 3514.7 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 780.6108 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -20158.2695 | 0 | 21088.2305 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 51.1273 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -20158.2695 | 0 | 21088.2305 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 51.1273 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 21088.2188 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -14053.7598 | 0 | 10544.1094 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 42.8659 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -12323.25 | 0 | 10544.1094 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 46.1099 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 24d | [5 empty] | 140588.25 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 16d | -754377.6875 | 0 | 140588.25 | 0 | 71.43% | Started | 894965.9375 | 894965.9375 | 100 | 100 | 71.4286 | 100 | 15.7088 | 71.4286
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 41d | [5 empty] | 208334.6074 |  | 15.34% |  | 31664.5605 | 31664.5605
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 9d | 176670.0469 | 0 | 208334.6074 | 0 | 84.75% | Started | 31664.5605 | 31664.5605 | 100 | 100 | 84.7458 | 100 | 657.9425 | 84.7458
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 6d | [5 empty] | 354985.3191 |  | 40.88% |  | 428499.1121 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 11d | 47711.7305 | 0 | 59750 | 0 | 60.71% | Started | 12038.2695 | 12038.2695 | 100 | 100 | 60.7143 | 100 | 496.3338 | 60.7143
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 14d | 3083.78 | 0 | 11d | 46122.1016 | 0 | 49205.8816 | 0 | 56% | Started | 3083.78 | 3083.78 | 100 | 100 | 56 | 100 | 1595.6353 | 56
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 |  | 0 | 0 | 31102.0195 | 1d | 0 | 0 | 0 | 31102.0195 | 0% | Not Started | 0 | 31102.0195 | 100 |  | 0 | 100 |  | 0
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 |  | 0 | 0 | 132006.2031 | 15d | 0 | 0 | 0 | 132006.2031 | 0% | Not Started | 0 | 132006.2031 | 100 |  | 0 | 100 |  | 0
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 70d | 413377.0625 | 0 | 68d | -167347.625 | 0 | 246029.4375 | 0 | 50.72% | Started | 413377.0625 | 413377.0625 | 100 | 100 | 50.7246 | 100 | 59.517 | 50.7246
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2004-11-18 17:00 |  | TP Name | 18/11, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 710d | [5 empty] | 4790413.6383 |  | 70.66% |  | 8070608.4989 | 10332341.481
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -429718.6875 | 0 | 56673.4062 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 11.6518 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -31030.3398 | 0 | 49995.168 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 61.703 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 162d | [5 empty] | 2323820.1344 |  | 83.82% |  | 4161160.4359 | 4888891.7938
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 632647.0992 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 52720.5859 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -104801.9922 | 0 | 52720.5859 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 33.4686 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 91382.3525 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 19235.5 | 0 | 31632.3496 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 255.1644 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -414302.75 | 0 | 35147.0625 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 7.82 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 14960.9404 | 0 | 24602.9404 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 255.1643 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 108955.8893 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 9382.0703 | 0 | 21088.2305 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 180.1464 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -23889.6504 | 0 | 14058.8184 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 37.0471 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 5711.6401 | 0 | 63264.7104 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 109.9241 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 20.0983 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 379588.2715 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 11294.0703 | 0 | 21088.2402 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 215.3142 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 86325.1562 | 0 | 119500.0078 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 360.2126 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -156374.6094 | 0 | 119500.0156 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 43.3168 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 86325.1562 | 0 | 119500.0078 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 360.2126 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 179250.0281 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 10544.1191 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -20960.4004 | 0 | 10544.1191 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 33.4686 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 255.1643 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 38661.78 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 180.1466 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -5972.4102 | 0 | 3514.71 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 37.0472 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 109.9242 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 20.0983 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 282.1021 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 112470.5916 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 3764.6899 | 0 | 7029.4099 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 215.3143 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 360.2126 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -45992.5312 | 0 | 35147.0625 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 43.3168 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 360.2126 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 179250.0281 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 10544.1191 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -20960.4004 | 0 | 10544.1191 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 33.4686 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 255.1643 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 38661.78 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 180.1466 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -5972.4102 | 0 | 3514.71 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 37.0472 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 109.9242 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 20.0983 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 112470.5916 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 3764.6899 | 0 | 7029.4099 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 215.3143 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 360.2126 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -45992.5312 | 0 | 35147.0625 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 43.3168 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 360.2126 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 189794.1356 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 21088.2305 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -41920.8008 | 0 | 21088.2305 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 33.4686 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 28117.6545 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 255.1643 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -248581.6406 | 0 | 21088.2344 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 7.82 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 255.1643 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 66779.4191 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 4691.04 | 0 | 10544.1201 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 180.1465 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -17917.2402 | 0 | 10544.1094 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 37.0471 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 3173.1299 | 0 | 35147.0596 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 109.9241 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 20.0983 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 73808.8315 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 5647.0298 | 0 | 10544.1196 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 215.314 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 360.2126 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -27595.5195 | 0 | 21088.2422 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 43.3168 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 256573.5665 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 21088.2305 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -41920.8008 | 0 | 21088.2305 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 33.4686 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 49205.8948 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 4274.5601 | 0 | 7029.4202 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 255.1643 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -248581.6406 | 0 | 21088.2344 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 7.82 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 12823.6699 | 0 | 21088.2402 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 255.1644 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 56235.3104 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 4691.04 | 0 | 10544.1201 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 180.1465 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 109.9242 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -55891.5703 | 0 | 14058.8203 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 20.0983 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 4537.6201 | 0 | 7029.4202 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 282.1021 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 130044.1309 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 7529.3799 | 0 | 14058.8301 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 215.3141 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 63474.3789 | 0 | 87867.6484 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 360.2127 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -27595.5195 | 0 | 21088.2422 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 43.3168 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 360.2129 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 168705.911 |  | 100% |  | 405866.8156 | 362677.9362
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 7029.4102 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -13973.5996 | 0 | 7029.4102 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 33.4686 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 28117.6615 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -207151.375 | 0 | 17573.5312 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 7.82 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 4274.5601 | 0 | 7029.4202 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 255.1643 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 63264.71 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 180.1466 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 2538.51 | 0 | 28117.6506 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 109.9241 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -41918.6797 | 0 | 10544.1094 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 20.0983 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 6806.4199 | 0 | 10544.1199 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 282.1018 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 70294.1294 |  | 100% |  | 51350.6895 | 8161.8101
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 9411.7197 | 0 | 17573.5298 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 215.3141 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 0 | 100 | 50 | 100 | 100 | 360.2126 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -18397.0098 | 0 | 14058.8301 | 0 | 100% | Finished | 32455.8398 | 0 | 100 | 75 | 100 | 100 | 43.3168 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 0 | 100 | 100 | 100 | 100 | 360.2134 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 84352.9553 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 3514.71 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -6986.7998 | 0 | 3514.71 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 33.4686 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 7.82 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 49205.8779 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 3173.1299 | 0 | 35147.0596 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 109.9241 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -23889.6504 | 0 | 14058.8184 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 37.0471 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 14058.8301 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -4599.25 | 0 | 3514.71 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 43.3168 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 360.2134 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 137073.559 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 7029.4102 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -13973.5996 | 0 | 7029.4102 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 33.4686 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 45691.1877 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 13164.5 | 0 | 28117.6504 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 188.0383 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 70294.131 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -14854.5801 | 0 | 7029.4102 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 32.1212 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 1903.88 | 0 | 21088.2394 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 109.9241 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -14888.54 | 0 | 35147.0615 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 70.2441 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 14058.8301 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -4599.25 | 0 | 3514.71 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 43.3168 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 360.2134 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 65d | [5 empty] | 496172.8516 |  | 32.58% |  | 388148.375 | 1159068.6123
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 65d | [5 empty] | 496172.8516 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 75d | 108024.4766 | 0 | 496172.8516 | 0 | 65.12% | Started | 388148.375 | 388148.375 | 100 | 100 | 65.1163 | 100 | 127.8307 | 65.1163
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 287063.4932
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 175400.3438 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 174d | [5 empty] | 1596899.2871 |  | 56.2% |  | 3269231.7407 | 4803233.3649
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 151132.3416 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 31632.3516 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -11702.1104 | 0 | 17573.5303 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 60.0278 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -13671.3096 | 0 | 14058.8213 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 50.6987 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 14058.8201 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 5651.46 | 0 | 7029.4099 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 510.1354 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -8616.4697 | 0 | 7029.4102 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 44.9282 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 14058.8203 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 1693.29 | 0 | 14058.8203 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 113.6936 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 91382.3497 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -27342.3008 | 0 | 35147.0586 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 56.2449 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -17275.3906 | 0 | 7029.4102 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 28.9219 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 20630.3105 | 0 | 21088.2306 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 4605.2214 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -26765.1504 | 0 | 28117.6504 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 51.2322 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 193308.837 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 42176.4807 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -10919.2305 | 0 | 7029.4102 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 39.164 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 10339.9697 | 0 | 10544.1197 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5164.8886 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -19079.7598 | 0 | 10544.1211 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 35.5933 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 10339.9697 | 0 | 10544.1197 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5164.8886 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -2332.1499 | 0 | 3514.71 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 60.1128 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 7029.4 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -1851.34 | 0 | 3514.7001 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 65.499 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 1711.34 | 0 | 3514.7 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 194.8973 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 144102.9563 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -13374.0596 | 0 | 10544.1201 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 44.0841 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -9539.1201 | 0 | 7029.4092 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 42.4263 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -4085.4099 | 0 | 3514.7102 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 46.2455 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -28851.8301 | 0 | 17573.5293 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 37.8533 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -24564.5898 | 0 | 17573.5312 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 41.7046 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -201535.6562 | 0 | 87867.6562 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 30.3617 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 14058.8193 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 14058.8193 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -12129.0898 | 0 | 7029.4102 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 36.6908 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -9748.54 | 0 | 7029.4092 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 41.8967 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 376073.5508 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 137073.5293 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -7270.25 | 0 | 14058.8203 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 65.9139 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -39071.7812 | 0 | 24602.9375 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 38.6385 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -37340.1797 | 0 | 24602.9492 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 39.7186 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -20947.1602 | 0 | 17573.5312 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 45.621 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -25937.5391 | 0 | 21088.2305 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 44.844 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -17774.0098 | 0 | 35147.0605 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 66.4141 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 70294.1211 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 31010.6094 | 0 | 70294.1211 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 178.9405 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 28117.6504 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -26842.4199 | 0 | 14058.8301 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 34.3726 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -27405.1992 | 0 | 14058.8203 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 33.9061 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 140588.25 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -320964.8438 | 0 | 140588.25 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 30.4598 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 53d | [5 empty] | 242770.511 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 81094.0423 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 34950.9414 | 0 | 35402.8814 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 7833.5357 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 3064.45 | 0 | 3514.7 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 780.6108 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -20158.2695 | 0 | 21088.2305 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 51.1273 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -20158.2695 | 0 | 21088.2305 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 51.1273 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 21088.2188 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -14053.7598 | 0 | 10544.1094 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 42.8659 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -12323.25 | 0 | 10544.1094 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 46.1099 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 29d | [5 empty] | 140588.25 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 11d | -754377.6875 | 0 | 140588.25 | 0 | 78.43% | Started | 894965.9375 | 894965.9375 | 100 | 100 | 78.4314 | 100 | 15.7088 | 78.4314
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 46d | [5 empty] | 208334.6074 |  | 15.34% |  | 31664.5605 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 4d | 176670.0469 | 0 | 208334.6074 | 0 | 92.59% | Started | 31664.5605 | 31664.5605 | 100 | 100 | 92.5926 | 100 | 657.9425 | 92.5926
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 |  | 0 | 0 | 174759.7031 | 65d | 0 | 0 | 0 | 174759.7031 | 0% | Not Started | 0 | 174759.7031 | 100 |  | 0 | 100 |  | 0
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 11d | [5 empty] | 411220.6199 |  | 56.44% |  | 591607.3347 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 6d | 47711.7305 | 0 | 59750 | 0 | 73.91% | Started | 12038.2695 | 12038.2695 | 100 | 100 | 73.913 | 100 | 496.3338 | 73.913
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 9d | 46122.1016 | 0 | 49205.8816 | 0 | 65.38% | Started | 3083.78 | 3083.78 | 100 | 121.4286 | 65.3846 | 100 | 1595.6353 | 65.3846
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 16d | -27587.3203 | 0 | 3514.6992 | 0 | 55.56% | Started | 31102.0195 | 31102.0195 | 100 | 2000 | 55.5556 | 100 | 11.3005 | 55.5556
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 15d | 132006.2031 | 0 | 11d | -79285.6016 | 0 | 52720.6016 | 0 | 57.69% | Started | 132006.2031 | 132006.2031 | 100 | 100 | 57.6923 | 100 | 39.938 | 57.6923
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 70d | 413377.0625 | 0 | 63d | -167347.625 | 0 | 246029.4375 | 0 | 52.63% | Started | 413377.0625 | 413377.0625 | 100 | 100 | 52.6316 | 100 | 59.517 | 52.6316
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2004-11-25 17:00 |  | TP Name | 25/11, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 715d | [5 empty] | 5061248.5992 |  | 72.19% |  | 8245368.202 | 10342098.7905
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 115037.8203 | 0 | 127170.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1048.1306 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -429718.6875 | 0 | 56673.4062 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 11.6518 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -31030.3398 | 0 | 49995.168 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 61.703 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 167d | [5 empty] | 2323820.1344 |  | 83.82% |  | 4161160.4359 | 4898649.1034
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 632647.0992 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 52720.5859 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -104801.9922 | 0 | 52720.5859 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 33.4686 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 91382.3525 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 19235.5 | 0 | 31632.3496 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 255.1644 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -414302.75 | 0 | 35147.0625 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 7.82 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 14960.9404 | 0 | 24602.9404 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 255.1643 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 108955.8893 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 9382.0703 | 0 | 21088.2305 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 180.1464 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -23889.6504 | 0 | 14058.8184 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 37.0471 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 5711.6401 | 0 | 63264.7104 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 109.9241 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 20.0983 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 379588.2715 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 11294.0703 | 0 | 21088.2402 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 215.3142 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 86325.1562 | 0 | 119500.0078 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 360.2126 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -156374.6094 | 0 | 119500.0156 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 43.3168 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 86325.1562 | 0 | 119500.0078 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 360.2126 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 179250.0281 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 10544.1191 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -20960.4004 | 0 | 10544.1191 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 33.4686 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 255.1643 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 38661.78 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 180.1466 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -5972.4102 | 0 | 3514.71 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 37.0472 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 109.9242 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 20.0983 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 282.1021 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 112470.5916 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 3764.6899 | 0 | 7029.4099 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 215.3143 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 360.2126 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -45992.5312 | 0 | 35147.0625 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 43.3168 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 360.2126 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 179250.0281 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 10544.1191 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -20960.4004 | 0 | 10544.1191 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 33.4686 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 255.1643 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 38661.78 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 180.1466 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -5972.4102 | 0 | 3514.71 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 37.0472 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 109.9242 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 20.0983 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 112470.5916 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 3764.6899 | 0 | 7029.4099 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 215.3143 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 360.2126 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -45992.5312 | 0 | 35147.0625 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 43.3168 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 360.2126 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 189794.1356 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 21088.2305 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -41920.8008 | 0 | 21088.2305 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 33.4686 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 28117.6545 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 255.1643 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -248581.6406 | 0 | 21088.2344 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 7.82 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 255.1643 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 66779.4191 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 4691.04 | 0 | 10544.1201 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 180.1465 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -17917.2402 | 0 | 10544.1094 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 37.0471 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 3173.1299 | 0 | 35147.0596 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 109.9241 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -27945.7793 | 0 | 7029.4199 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 20.0983 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 2268.8101 | 0 | 3514.7101 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 282.1021 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 73808.8315 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 5647.0298 | 0 | 10544.1196 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 215.314 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 360.2126 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -27595.5195 | 0 | 21088.2422 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 43.3168 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 256573.5665 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 21088.2305 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -41920.8008 | 0 | 21088.2305 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 33.4686 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 49205.8948 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 4274.5601 | 0 | 7029.4202 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 255.1643 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -248581.6406 | 0 | 21088.2344 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 7.82 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 12823.6699 | 0 | 21088.2402 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 255.1644 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 56235.3104 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 4691.04 | 0 | 10544.1201 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 180.1465 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 1586.5699 | 0 | 17573.5299 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 109.9242 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -55891.5703 | 0 | 14058.8203 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 20.0983 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 4537.6201 | 0 | 7029.4202 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 282.1021 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 130044.1309 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 7529.3799 | 0 | 14058.8301 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 215.3141 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 63474.3789 | 0 | 87867.6484 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 360.2127 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -27595.5195 | 0 | 21088.2422 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 43.3168 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 360.2129 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 168705.911 |  | 100% |  | 405866.8156 | 372435.2457
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 7029.4102 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -13973.5996 | 0 | 7029.4102 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 33.4686 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 28117.6615 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -207151.375 | 0 | 17573.5312 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 7.82 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 4274.5601 | 0 | 7029.4202 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 255.1643 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 63264.71 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 3127.3601 | 0 | 7029.4102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 180.1466 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 2538.51 | 0 | 28117.6506 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 109.9241 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -41918.6797 | 0 | 10544.1094 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 20.0983 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 6806.4199 | 0 | 10544.1199 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 282.1018 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 70294.1294 |  | 100% |  | 51350.6895 | 17919.1196
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 9411.7197 | 0 | 17573.5298 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 215.3141 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 25389.75 | 0 | 35147.0596 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 360.2126 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -18397.0098 | 0 | 14058.8301 | 0 | 100% | Finished | 32455.8398 | 0 | 100 | 75 | 100 | 100 | 43.3168 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 0 | 100 | 100 | 100 | 100 | 360.2134 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 84352.9553 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 3514.71 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -6986.7998 | 0 | 3514.71 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 33.4686 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 17573.5374 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 7.82 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 49205.8779 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 3173.1299 | 0 | 35147.0596 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 109.9241 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -23889.6504 | 0 | 14058.8184 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 37.0471 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 14058.8301 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -4599.25 | 0 | 3514.71 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 43.3168 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 360.2134 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 137073.559 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 7029.4102 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -13973.5996 | 0 | 7029.4102 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 33.4686 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 45691.1877 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 13164.5 | 0 | 28117.6504 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 188.0383 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -124290.8203 | 0 | 10544.1172 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 7.82 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 2137.28 | 0 | 3514.7101 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 255.1643 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 70294.131 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -11944.8203 | 0 | 7029.4199 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 37.0472 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -14854.5801 | 0 | 7029.4102 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 32.1212 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 1903.88 | 0 | 21088.2394 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 109.9241 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -14888.54 | 0 | 35147.0615 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 70.2441 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 14058.8301 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 5077.9502 | 0 | 7029.4102 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 360.2129 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -4599.25 | 0 | 3514.71 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 43.3168 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 2538.98 | 0 | 3514.71 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 360.2134 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 70d | [5 empty] | 496172.8516 |  | 32.58% |  | 388148.375 | 1159068.6123
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 70d | [5 empty] | 496172.8516 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 70d | 108024.4766 | 0 | 496172.8516 | 0 | 66.67% | Started | 388148.375 | 388148.375 | 100 | 100 | 66.6667 | 100 | 127.8307 | 66.6667
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 287063.4932
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 175400.3438 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 179d | [5 empty] | 1867734.248 |  | 59.2% |  | 3443991.4438 | 4803233.3649
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 151132.3416 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 31632.3516 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -11702.1104 | 0 | 17573.5303 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 60.0278 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -13671.3096 | 0 | 14058.8213 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 50.6987 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 14058.8201 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 5651.46 | 0 | 7029.4099 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 510.1354 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -8616.4697 | 0 | 7029.4102 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 44.9282 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 14058.8203 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 1693.29 | 0 | 14058.8203 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 113.6936 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 91382.3497 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -27342.3008 | 0 | 35147.0586 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 56.2449 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -17275.3906 | 0 | 7029.4102 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 28.9219 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 20630.3105 | 0 | 21088.2306 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 4605.2214 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -26765.1504 | 0 | 28117.6504 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 51.2322 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 193308.837 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 42176.4807 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -10919.2305 | 0 | 7029.4102 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 39.164 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 10339.9697 | 0 | 10544.1197 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5164.8886 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -19079.7598 | 0 | 10544.1211 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 35.5933 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 10339.9697 | 0 | 10544.1197 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5164.8886 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -2332.1499 | 0 | 3514.71 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 60.1128 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 7029.4 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -1851.34 | 0 | 3514.7001 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 65.499 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 1711.34 | 0 | 3514.7 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 194.8973 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 144102.9563 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -13374.0596 | 0 | 10544.1201 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 44.0841 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -9539.1201 | 0 | 7029.4092 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 42.4263 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -4085.4099 | 0 | 3514.7102 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 46.2455 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -28851.8301 | 0 | 17573.5293 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 37.8533 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -24564.5898 | 0 | 17573.5312 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 41.7046 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -201535.6562 | 0 | 87867.6562 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 30.3617 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 14058.8193 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 14058.8193 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -12129.0898 | 0 | 7029.4102 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 36.6908 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -9748.54 | 0 | 7029.4092 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 41.8967 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 376073.5508 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 137073.5293 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -7270.25 | 0 | 14058.8203 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 65.9139 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -39071.7812 | 0 | 24602.9375 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 38.6385 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -37340.1797 | 0 | 24602.9492 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 39.7186 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -20947.1602 | 0 | 17573.5312 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 45.621 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -25937.5391 | 0 | 21088.2305 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 44.844 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -17774.0098 | 0 | 35147.0605 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 66.4141 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 70294.1211 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 31010.6094 | 0 | 70294.1211 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 178.9405 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 28117.6504 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -26842.4199 | 0 | 14058.8301 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 34.3726 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -27405.1992 | 0 | 14058.8203 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 33.9061 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 140588.25 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -320964.8438 | 0 | 140588.25 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 30.4598 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 58d | [5 empty] | 242770.511 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 81094.0423 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 34950.9414 | 0 | 35402.8814 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 7833.5357 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 3064.45 | 0 | 3514.7 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 780.6108 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -20158.2695 | 0 | 21088.2305 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 51.1273 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -20158.2695 | 0 | 21088.2305 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 51.1273 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 21088.2188 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -14053.7598 | 0 | 10544.1094 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 42.8659 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -12323.25 | 0 | 10544.1094 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 46.1099 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 34d | [5 empty] | 140588.25 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 6d | -754377.6875 | 0 | 140588.25 | 0 | 86.96% | Started | 894965.9375 | 894965.9375 | 100 | 100 | 86.9565 | 100 | 15.7088 | 86.9565
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 |  | 0 | 0 | 33920.1484 | 5d | 0 | 0 | 0 | 33920.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 51d | [5 empty] | 479169.5684 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 176670.0469 | 0 | 208334.6074 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 657.9425 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 60d | 174759.7031 | 0 | 56d | 96075.2578 | 0 | 270834.9609 | 0 | 51.72% | Started | 174759.7031 | 174759.7031 | 100 | 92.3077 | 51.7241 | 100 | 154.9756 | 51.7241
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 16d | [5 empty] | 411220.6199 |  | 56.44% |  | 591607.3347 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 1d | 47711.7305 | 0 | 59750 | 0 | 94.44% | Started | 12038.2695 | 12038.2695 | 100 | 100 | 94.4444 | 100 | 496.3338 | 94.4444
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 4d | 46122.1016 | 0 | 49205.8816 | 0 | 80.95% | Started | 3083.78 | 3083.78 | 100 | 121.4286 | 80.9524 | 100 | 1595.6353 | 80.9524
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 11d | -27587.3203 | 0 | 3514.6992 | 0 | 64.52% | Started | 31102.0195 | 31102.0195 | 100 | 2000 | 64.5161 | 100 | 11.3005 | 64.5161
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 15d | 132006.2031 | 0 | 6d | -79285.6016 | 0 | 52720.6016 | 0 | 71.43% | Started | 132006.2031 | 132006.2031 | 100 | 100 | 71.4286 | 100 | 39.938 | 71.4286
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 70d | 413377.0625 | 0 | 58d | -167347.625 | 0 | 246029.4375 | 0 | 54.69% | Started | 413377.0625 | 413377.0625 | 100 | 100 | 54.6875 | 100 | 59.517 | 54.6875
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2004-12-09 17:00 |  | TP Name | 09/12, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 725d | [5 empty] | 5512538.1821 |  | 72.49% |  | 8279288.3504 | 10408474.7788
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 115400.7578 | 0 | 127533.8779 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1219 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 115400.7578 | 0 | 127533.8779 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1219 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 115400.7578 | 0 | 127533.8779 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1219 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 115400.7578 | 0 | 127533.8779 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1219 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 115400.7578 | 0 | 127533.8779 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1219 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 115400.7578 | 0 | 127533.8779 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1219 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -427903.9688 | 0 | 58488.125 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 12.0249 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -25949.1504 | 0 | 55076.3574 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 67.9741 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 177d | [5 empty] | 2563362.0638 |  | 83.82% |  | 4161160.4359 | 4931104.9432
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 697976.7545 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 58164.7266 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -99357.8516 | 0 | 58164.7266 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 36.9247 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 100818.8691 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 22501.9805 | 0 | 34898.8301 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 281.5137 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -410673.3125 | 0 | 38776.5 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 8.6275 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 17501.5391 | 0 | 27143.5391 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 281.5136 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 120207.0973 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 11559.7305 | 0 | 23265.8906 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 198.7491 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -22437.8809 | 0 | 15510.5879 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 40.8728 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 12244.5996 | 0 | 69797.6699 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 121.2753 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -27219.9004 | 0 | 7755.2988 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 22.1737 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 2631.75 | 0 | 3877.65 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 311.2328 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 418786.0615 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 13471.7197 | 0 | 23265.8896 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 237.5484 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 98665.2031 | 0 | 131840.0547 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 397.4096 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -144034.5625 | 0 | 131840.0625 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 47.7898 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 98665.2031 | 0 | 131840.0547 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 397.4096 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 197760.076 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 11632.9492 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -19871.5703 | 0 | 11632.9492 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 36.9247 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 19388.2454 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 281.5134 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -123201.9922 | 0 | 11632.9453 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 8.6275 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 281.5134 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 42654.1288 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 3853.24 | 0 | 7755.29 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 198.7491 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -5609.4702 | 0 | 3877.6499 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 40.8728 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 3401.28 | 0 | 19388.24 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 121.2753 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -27219.9004 | 0 | 7755.2988 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 22.1737 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 2631.75 | 0 | 3877.65 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 311.2328 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 124084.7527 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 4490.5698 | 0 | 7755.2898 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 237.5484 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 29019.1797 | 0 | 38776.4893 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 397.4096 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -42363.1094 | 0 | 38776.4844 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 47.7898 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 29019.1797 | 0 | 38776.4893 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 397.4096 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 197760.076 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 11632.9492 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -19871.5703 | 0 | 11632.9492 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 36.9247 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 19388.2454 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 281.5134 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -123201.9922 | 0 | 11632.9453 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 8.6275 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 281.5134 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 42654.1288 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 3853.24 | 0 | 7755.29 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 198.7491 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -5609.4702 | 0 | 3877.6499 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 40.8728 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 3401.28 | 0 | 19388.24 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 121.2753 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -27219.9004 | 0 | 7755.2988 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 22.1737 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 2631.75 | 0 | 3877.65 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 311.2328 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 124084.7527 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 4490.5698 | 0 | 7755.2898 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 237.5484 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 29019.1797 | 0 | 38776.4893 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 397.4096 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -42363.1094 | 0 | 38776.4844 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 47.7898 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 29019.1797 | 0 | 38776.4893 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 397.4096 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 209393.0204 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 23265.8906 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -39743.1406 | 0 | 23265.8906 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 36.9247 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 31021.1907 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 281.5134 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -246403.9844 | 0 | 23265.8906 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 8.6275 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 281.5134 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 73675.3077 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 5779.8599 | 0 | 11632.9399 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 198.749 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -16828.4102 | 0 | 11632.9395 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 40.8728 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 6802.5498 | 0 | 38776.4795 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 121.2753 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -27219.9004 | 0 | 7755.2988 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 22.1737 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 2631.75 | 0 | 3877.65 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 311.2328 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 81430.6313 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 6735.8599 | 0 | 11632.9497 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 237.5482 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 29019.1797 | 0 | 38776.4893 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 397.4096 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -25417.8691 | 0 | 23265.8926 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 47.7898 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 5803.8398 | 0 | 7755.2998 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 397.4101 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 283068.3416 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 23265.8906 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -39743.1406 | 0 | 23265.8906 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 36.9247 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 54287.0813 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 5000.4399 | 0 | 7755.3 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 281.5134 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -246403.9844 | 0 | 23265.8906 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 8.6275 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 15001.3203 | 0 | 23265.8906 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 281.5136 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 62042.3696 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 5779.8599 | 0 | 11632.9399 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 198.749 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -11218.9404 | 0 | 7755.2998 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 40.8728 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 3401.28 | 0 | 19388.24 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 121.2753 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -54439.8008 | 0 | 15510.5898 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 22.1737 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 5263.5 | 0 | 7755.3 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 311.2328 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 143473 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 8981.1504 | 0 | 15510.6006 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 237.5483 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 72547.9375 | 0 | 96941.207 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 397.4096 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -25417.8691 | 0 | 23265.8926 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 47.7898 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 5803.8398 | 0 | 7755.2998 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 397.4101 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 186127.1364 |  | 100% |  | 405866.8156 | 404891.0856
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 7755.2998 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -13247.71 | 0 | 7755.2998 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 36.9247 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 31021.2001 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 281.5134 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -205336.6562 | 0 | 19388.25 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 8.6275 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 5000.4399 | 0 | 7755.3 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 281.5134 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 69797.658 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 3853.24 | 0 | 7755.29 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 198.7491 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -11218.9404 | 0 | 7755.2998 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 40.8728 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 5442.04 | 0 | 31021.1807 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 121.2753 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -40829.8516 | 0 | 11632.9375 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 22.1737 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 7895.25 | 0 | 11632.95 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 311.2328 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 77552.9785 |  | 100% |  | 51350.6895 | 50374.9595
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 11226.4297 | 0 | 19388.2397 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 237.5483 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 29019.1797 | 0 | 38776.4893 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 397.4096 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -16945.2402 | 0 | 15510.5996 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 47.7899 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 2901.9199 | 0 | 3877.6499 | 0 | 100% | Finished | 975.73 | 0 | 100 | 100 | 100 | 100 | 397.4101 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 93063.5623 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 3877.6499 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -6623.8599 | 0 | 3877.6499 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 36.9247 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 19388.2454 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 281.5134 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -123201.9922 | 0 | 11632.9453 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 8.6275 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 281.5134 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 54287.0674 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 6802.5498 | 0 | 38776.4795 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 121.2753 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -22437.8809 | 0 | 15510.5879 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 40.8728 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 15510.5996 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 5803.8398 | 0 | 7755.2998 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 397.4101 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -4236.3101 | 0 | 3877.6499 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 47.7899 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 2901.9199 | 0 | 3877.6499 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 397.4101 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 151228.3154 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 7755.2998 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -13247.71 | 0 | 7755.2998 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 36.9247 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 50409.4358 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 281.5134 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 16068.04 | 0 | 31021.1904 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 207.4559 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -123201.9922 | 0 | 11632.9453 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 8.6275 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 2500.22 | 0 | 3877.65 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 281.5134 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 77552.9802 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -11218.9404 | 0 | 7755.2998 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 40.8728 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -14128.6904 | 0 | 7755.2998 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 35.4382 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 4081.53 | 0 | 23265.8894 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 121.2753 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -11259.1104 | 0 | 38776.4912 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 77.4978 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 15510.5996 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 5803.8398 | 0 | 7755.2998 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 397.4101 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -4236.3101 | 0 | 3877.6499 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 47.7899 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 2901.9199 | 0 | 3877.6499 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 397.4101 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 80d | [5 empty] | 546984.7812 |  | 32.58% |  | 388148.375 | 1159068.6123
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 80d | [5 empty] | 546984.7812 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 60d | 158836.4062 | 0 | 546984.7812 | 0 | 70% | Started | 388148.375 | 388148.375 | 100 | 100 | 70 | 100 | 140.9216 | 70
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 287063.4932
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 175400.3438 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 189d | [5 empty] | 2070408.3683 |  | 59.78% |  | 3477911.5923 | 4837153.5133
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 166738.8724 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 34898.8311 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -9887.4004 | 0 | 19388.2402 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 66.2265 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -12219.54 | 0 | 15510.5908 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 55.9341 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 15510.5896 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 6377.3398 | 0 | 7755.2898 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 562.8136 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -7890.5801 | 0 | 7755.2998 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 49.5677 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 15510.5903 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 3145.0601 | 0 | 15510.5903 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 125.4341 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 100818.8614 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -23712.8809 | 0 | 38776.4785 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 62.0529 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -16549.5 | 0 | 7755.3008 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 31.9085 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 22807.9707 | 0 | 23265.8907 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 5080.7761 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -23861.6094 | 0 | 31021.1914 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 56.5226 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 213270.6596 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 46531.7819 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -10193.3398 | 0 | 7755.3008 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 43.2083 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 11428.79 | 0 | 11632.94 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5698.2319 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -17990.9297 | 0 | 11632.9512 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 39.2688 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 11428.79 | 0 | 11632.94 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5698.2319 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -1969.21 | 0 | 3877.6499 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 66.3202 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 7755.29 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -1488.4 | 0 | 3877.64 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 72.2626 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 2074.29 | 0 | 3877.65 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 215.0236 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 158983.5876 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -12285.2402 | 0 | 11632.9395 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 48.6364 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -8813.2305 | 0 | 7755.2988 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 46.8074 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -3722.47 | 0 | 3877.6501 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 51.0209 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -27037.1191 | 0 | 19388.2402 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 41.7622 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -22749.8809 | 0 | 19388.2402 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 46.0112 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -192462.0938 | 0 | 96941.2188 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 33.4969 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 15510.5791 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 15510.5791 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -11403.21 | 0 | 7755.29 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 40.4796 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -9022.6602 | 0 | 7755.2891 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 46.2231 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 414908.3794 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 151228.2798 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -5818.48 | 0 | 15510.5903 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 72.7204 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -36531.1797 | 0 | 27143.5391 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 42.6284 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -34799.5898 | 0 | 27143.5391 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 43.8201 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -19132.4492 | 0 | 19388.2422 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 50.332 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -23759.8809 | 0 | 23265.8887 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 49.4748 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -14144.5898 | 0 | 38776.4805 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 73.2723 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 77552.9727 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 38269.4609 | 0 | 77552.9727 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 197.4186 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 31021.1895 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -25390.6504 | 0 | 15510.5996 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 37.9221 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -25953.4297 | 0 | 15510.5898 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 37.4073 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 155105.9375 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -306447.1562 | 0 | 155105.9375 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 33.6052 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 265998.836 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 87627.0196 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 36765.6484 | 0 | 37217.5884 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 8235.0729 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 3427.3999 | 0 | 3877.6499 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 861.2215 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -17980.6094 | 0 | 23265.8906 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 56.4069 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -17980.6094 | 0 | 23265.8906 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 56.4069 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 23265.8789 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -12964.9297 | 0 | 11632.9395 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 47.2925 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -11234.4199 | 0 | 11632.9395 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 50.8714 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 155105.9375 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -739860 | 0 | 155105.9375 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 17.3309 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 4d | [5 empty] | 19388.2383 |  | 4.357% |  | 33920.1484 | 33920.1484
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 4d | [5 empty] | 19388.2383 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 1d | -14531.9102 | 0 | 19388.2383 | 0 | 83.33% | Started | 33920.1484 | 33920.1484 | 100 | 100 | 83.3333 | 100 | 57.1585 | 83.3333
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 |  | 0 | 0 | 46090.3906 | 5d | 0 | 0 | 0 | 46090.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 |  | 0 | 0 | 30019.4297 | 4d | 0 | 0 | 0 | 30019.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 61d | [5 empty] | 520907.9277 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 194817.1562 | 0 | 226481.7168 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 715.253 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 60d | 174759.7031 | 0 | 46d | 119666.5078 | 0 | 294426.2109 | 0 | 56.6% | Started | 174759.7031 | 174759.7031 | 100 | 92.3077 | 56.6038 | 100 | 168.4749 | 56.6038
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 26d | [5 empty] | 453684.8757 |  | 56.44% |  | 591607.3347 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 53881.75 | 0 | 65920.0195 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 547.5872 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 51203.3008 | 0 | 54287.0808 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 1760.407 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 1d | -27224.3691 | 0 | 3877.6504 | 0 | 95.24% | Started | 31102.0195 | 31102.0195 | 100 | 2000 | 95.2381 | 100 | 12.4675 | 95.2381
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 6d | -73841.4688 | 0 | 58164.7344 | 0 | 80.65% | Started | 132006.2031 | 132006.2031 | 100 | 166.6667 | 80.6452 | 100 | 44.0621 | 80.6452
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 70d | 413377.0625 | 0 | 48d | -141941.6719 | 0 | 271435.3906 | 0 | 59.32% | Started | 413377.0625 | 413377.0625 | 100 | 100 | 59.322 | 100 | 65.6629 | 59.322
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2004-12-21 17:00 |  | TP Name | 21/12, 2004
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 733d | [5 empty] | 5557797.7363 |  | 73.15% |  | 8355398.1707 | 10517686.8799
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 115409.3672 | 0 | 127542.4873 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1928 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 115409.3672 | 0 | 127542.4873 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1928 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 115409.3672 | 0 | 127542.4873 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1928 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 115409.3672 | 0 | 127542.4873 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1928 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 115409.3672 | 0 | 127542.4873 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1928 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 115409.3672 | 0 | 127542.4873 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1051.1928 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -427860.9375 | 0 | 58531.1562 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 12.0337 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -25828.6699 | 0 | 55196.8379 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 68.1228 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 185d | [5 empty] | 2569041.5248 |  | 83.82% |  | 4161160.4359 | 4964207.224
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 699525.6713 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 58293.7969 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -99228.7812 | 0 | 58293.7969 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 37.0066 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 101042.6211 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 22579.4297 | 0 | 34976.2793 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 282.1384 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -410587.25 | 0 | 38862.5625 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 8.6467 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 17561.7793 | 0 | 27203.7793 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 282.1383 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 120473.8588 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 11611.3604 | 0 | 23317.5205 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 199.1902 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -22403.4609 | 0 | 15545.0078 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 40.9635 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 12399.4902 | 0 | 69952.5605 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 121.5444 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -27202.6895 | 0 | 7772.5098 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 22.2229 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 2640.3601 | 0 | 3886.2601 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 311.9239 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 419715.3945 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 13523.3496 | 0 | 23317.5195 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 238.0755 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 98957.7734 | 0 | 132132.625 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 398.2915 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -143742 | 0 | 132132.625 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 47.8959 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 98957.7734 | 0 | 132132.625 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 398.2915 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 198198.943 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 11658.7598 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -19845.7598 | 0 | 11658.7598 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 37.0066 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 19431.2781 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 282.1385 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -123176.1797 | 0 | 11658.7578 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 8.6467 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 282.1385 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 42748.7902 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 3870.45 | 0 | 7772.5 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 199.1902 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -5600.8599 | 0 | 3886.2603 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 40.9635 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 3444.3 | 0 | 19431.26 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 121.5444 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -27202.6895 | 0 | 7772.5098 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 22.2229 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 2640.3601 | 0 | 3886.2601 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 311.9239 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 124360.115 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 4507.7798 | 0 | 7772.4998 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 238.0755 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 29105.2305 | 0 | 38862.54 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 398.2916 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -42277.0586 | 0 | 38862.5352 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 47.8959 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 29105.2305 | 0 | 38862.54 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 398.2916 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 198198.943 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 11658.7598 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -19845.7598 | 0 | 11658.7598 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 37.0066 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 19431.2781 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 282.1385 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -123176.1797 | 0 | 11658.7578 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 8.6467 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 282.1385 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 42748.7902 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 3870.45 | 0 | 7772.5 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 199.1902 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -5600.8599 | 0 | 3886.2603 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 40.9635 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 3444.3 | 0 | 19431.26 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 121.5444 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -27202.6895 | 0 | 7772.5098 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 22.2229 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 2640.3601 | 0 | 3886.2601 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 311.9239 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 124360.115 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 4507.7798 | 0 | 7772.4998 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 238.0755 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 29105.2305 | 0 | 38862.54 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 398.2916 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -42277.0586 | 0 | 38862.5352 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 47.8959 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 29105.2305 | 0 | 38862.54 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 398.2916 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 209857.736 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 23317.5195 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -39691.5117 | 0 | 23317.5195 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 37.0066 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 31090.0359 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 282.1385 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -246352.3594 | 0 | 23317.5156 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 8.6467 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 282.1385 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 73838.8295 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 5805.6802 | 0 | 11658.7603 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 199.1902 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -16802.5898 | 0 | 11658.7598 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 40.9635 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 6888.6099 | 0 | 38862.5396 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 121.5445 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -27202.6895 | 0 | 7772.5098 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 22.2229 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 2640.3601 | 0 | 3886.2601 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 311.9239 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 81611.3511 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 6761.6802 | 0 | 11658.77 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 238.0755 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 29105.2305 | 0 | 38862.54 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 398.2916 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -25366.2305 | 0 | 23317.5312 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 47.8959 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 5821.0498 | 0 | 7772.5098 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 398.292 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 283696.5188 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 23317.5195 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -39691.5117 | 0 | 23317.5195 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 37.0066 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 54407.5461 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 5017.6499 | 0 | 7772.51 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 282.1381 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -246352.3594 | 0 | 23317.5156 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 8.6467 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 15052.9502 | 0 | 23317.5205 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 282.1383 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 62180.0518 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 5805.6802 | 0 | 11658.7603 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 199.1902 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -11201.7305 | 0 | 7772.5098 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 40.9635 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 3444.3 | 0 | 19431.26 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 121.5444 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -54405.3789 | 0 | 15545.0117 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 22.2229 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 5280.71 | 0 | 7772.51 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 311.9235 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 143791.4014 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 9015.5703 | 0 | 15545.0205 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 238.0755 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 72763.0703 | 0 | 97156.3398 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 398.2916 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -25366.2305 | 0 | 23317.5312 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 47.8959 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 5821.0498 | 0 | 7772.5098 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 398.292 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 186540.2089 |  | 100% |  | 405866.8156 | 405866.8156
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 7772.5098 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -13230.5 | 0 | 7772.5098 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 37.0066 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 31090.0514 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 282.1385 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -205293.625 | 0 | 19431.2812 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 8.6467 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 5017.6499 | 0 | 7772.51 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 282.1381 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 69952.5681 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 3870.45 | 0 | 7772.5 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 199.1902 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -11201.7305 | 0 | 7772.5098 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 40.9635 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 5510.8901 | 0 | 31090.0308 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 121.5445 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -40804.0312 | 0 | 11658.7578 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 22.2229 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 7921.0698 | 0 | 11658.7698 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 311.9236 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 77725.0796 |  | 100% |  | 51350.6895 | 51350.6895
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 11269.46 | 0 | 19431.27 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 238.0755 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 29105.2305 | 0 | 38862.54 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 398.2916 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -16910.8203 | 0 | 15545.0195 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 47.8959 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 2910.52 | 0 | 3886.25 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 398.2915 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 93270.095 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 3886.2598 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -6615.25 | 0 | 3886.2598 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 37.0067 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 19431.2781 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 282.1385 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -123176.1797 | 0 | 11658.7578 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 8.6467 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 282.1385 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 54407.5474 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 6888.6099 | 0 | 38862.5396 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 121.5445 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -22403.4609 | 0 | 15545.0078 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 40.9635 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 15545.0098 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 5821.0498 | 0 | 7772.5098 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 398.292 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -4227.71 | 0 | 3886.25 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 47.8958 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 2910.52 | 0 | 3886.25 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 398.2915 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 151563.9089 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 7772.5098 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -13230.5 | 0 | 7772.5098 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 37.0066 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 50521.3083 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 282.1385 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 16136.8799 | 0 | 31090.0303 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 207.9163 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -123176.1797 | 0 | 11658.7578 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 8.6467 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 2508.8301 | 0 | 3886.2601 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 282.1385 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 77725.0811 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -11201.7305 | 0 | 7772.5098 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 40.9635 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -14111.4805 | 0 | 7772.5098 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 35.5169 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 4133.1602 | 0 | 23317.5195 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 121.5444 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -11173.0596 | 0 | 38862.542 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 77.6698 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 15545.0098 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 5821.0498 | 0 | 7772.5098 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 398.292 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -4227.71 | 0 | 3886.25 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 47.8958 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 2910.52 | 0 | 3886.25 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 398.2915 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 88d | [5 empty] | 548189.5 |  | 32.58% |  | 388148.375 | 1191195.1631
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 88d | [5 empty] | 548189.5 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 52d | 160041.125 | 0 | 548189.5 | 0 | 72.92% | Started | 388148.375 | 388148.375 | 100 | 100 | 72.9167 | 100 | 141.2319 | 72.9167
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 319190.0439
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 175400.3438 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 32126.5508 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 |  | 0 | 0 | 448265.125 | 50d | 0 | 0 | 0 | 448265.125 | 0% | Not Started | 0 | 448265.125 | 100 |  | 0 | 100 |  | 0
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 197d | [5 empty] | 2109773.2935 |  | 61.09% |  | 3554021.4126 | 4913263.3336
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 167108.8929 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 34976.2812 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -9844.3701 | 0 | 19431.2705 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 66.3735 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -12185.1201 | 0 | 15545.0107 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 56.0582 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 15545.0095 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 6394.5498 | 0 | 7772.4998 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 564.0626 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -7873.3701 | 0 | 7772.5098 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 49.6777 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 15545.0103 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 3179.48 | 0 | 15545.0103 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 125.7124 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 101042.5919 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -23626.8301 | 0 | 38862.5293 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 62.1906 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -16532.2891 | 0 | 7772.5117 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 31.9793 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 22859.5996 | 0 | 23317.5196 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 5092.0508 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -23792.7695 | 0 | 31090.0312 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 56.648 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 213743.9731 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 46635.053 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -10176.1299 | 0 | 7772.5107 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 43.3042 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 11454.6104 | 0 | 11658.7603 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5710.8796 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -17965.1191 | 0 | 11658.7617 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 39.356 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 11454.6104 | 0 | 11658.7603 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 5710.8796 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -1960.6 | 0 | 3886.2599 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 66.4675 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 7772.4999 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -1479.79 | 0 | 3886.25 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 72.4231 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 2082.8899 | 0 | 3886.2499 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 215.5005 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 159336.4202 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -12259.4199 | 0 | 11658.7598 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 48.7443 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -8796.0195 | 0 | 7772.5098 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 46.9113 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -3713.8601 | 0 | 3886.26 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 51.1342 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -26994.0898 | 0 | 19431.2695 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 41.8549 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -22706.8594 | 0 | 19431.2617 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 46.1133 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -192246.9531 | 0 | 97156.3594 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 33.5713 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 15544.999 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 15544.999 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -11386 | 0 | 7772.5 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 40.5695 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -9005.4502 | 0 | 7772.499 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 46.3257 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 415829.1421 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 151563.8862 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -5784.0601 | 0 | 15545.0103 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 72.8818 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -36470.9414 | 0 | 27203.7773 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 42.723 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -34739.3516 | 0 | 27203.7773 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 43.9173 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -19089.4199 | 0 | 19431.2715 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 50.4437 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -23708.25 | 0 | 23317.5195 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 49.5846 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -14058.54 | 0 | 38862.5303 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 73.4349 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 77725.0703 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 38441.5586 | 0 | 77725.0703 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 197.8567 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 31090.0293 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -25356.2305 | 0 | 15545.0195 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 38.0062 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -25919.0098 | 0 | 15545.0098 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 37.4904 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 155450.1562 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -306102.9375 | 0 | 155450.1562 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 33.6798 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 266549.5523 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 87781.9088 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 36808.6797 | 0 | 37260.6197 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 8244.5943 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 3436 | 0 | 3886.25 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 863.1316 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -17928.9805 | 0 | 23317.5195 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 56.5321 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -17928.9805 | 0 | 23317.5195 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 56.5321 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 23317.5186 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -12939.1104 | 0 | 11658.7588 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 47.3974 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -11208.5996 | 0 | 11658.7598 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 50.9843 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 155450.125 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -739515.8125 | 0 | 155450.125 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 17.3694 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 12d | [5 empty] | 54407.5498 |  | 14.13% |  | 110029.9688 | 110029.9688
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 19431.2686 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | -14488.8799 | 0 | 19431.2686 | 0 | 100% | Finished | 33920.1484 | 33920.1484 | 100 | 100 | 100 | 100 | 57.2853 | 100
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 7d | [5 empty] | 34976.2812 |  | 100% |  | 76109.8203 | 76109.8203
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -26659.1191 | 0 | 19431.2715 | 0 | 100% | Finished | 46090.3906 | 46090.3906 | 100 | 100 | 100 | 100 | 42.1591 | 100
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 2d | -14474.4199 | 0 | 15545.0098 | 0 | 66.67% | Started | 30019.4297 | 30019.4297 | 100 | 100 | 66.6667 | 100 | 51.7832 | 66.6667
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 |  | 0 | 0 | 668512.8125 | 30d | 0 | 0 | 0 | 668512.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 69d | [5 empty] | 521897.5137 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 195247.4062 | 0 | 226911.9668 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 716.6118 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 60d | 174759.7031 | 0 | 38d | 120225.8438 | 0 | 294985.5469 | 0 | 61.22% | Started | 174759.7031 | 174759.7031 | 100 | 92.3077 | 61.2245 | 100 | 168.7949 | 61.2245
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 34d | [5 empty] | 454691.6707 |  | 56.44% |  | 591607.3347 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 54028.0391 | 0 | 66066.3086 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 548.8024 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 51323.7695 | 0 | 54407.5496 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 1764.3136 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -27215.7695 | 0 | 3886.25 | 0 | 100% | Finished | 31102.0195 | 31102.0195 | 100 | 2000 | 100 | 100 | 12.4952 | 100
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -73712.3906 | 0 | 58293.8125 | 0 | 100% | Finished | 132006.2031 | 132006.2031 | 100 | 166.6667 | 100 | 100 | 44.1599 | 100
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 70d | 413377.0625 | 0 | 40d | -141339.3125 | 0 | 272037.75 | 0 | 63.64% | Started | 413377.0625 | 413377.0625 | 100 | 100 | 63.6364 | 100 | 65.8086 | 63.6364
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 |  | 0 | 0 | 440020.6562 | 50d | 0 | 0 | 0 | 440020.6562 | 0% | Not Started | 0 | 440020.6562 | 100 |  | 0 | 100 |  | 0
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 |  | 0 | 0 | 322152.7812 | 30d | 0 | 0 | 0 | 322152.7812 | 0% | Not Started | 0 | 322152.7812 | 100 |  | 0 | 100 |  | 0
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 |  | 0 | 0 | 3592.98 | 5d | 0 | 0 | 0 | 3592.98 | 0% | Not Started | 0 | 3592.98 | 100 |  | 0 | 100 |  | 0
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2005-01-13 17:00 |  | TP Name | 13/01, 2005
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 739d | [5 empty] | 6763672.7997 |  | 89.63% |  | 10237942.5257 | 11186199.6924
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 115821.8203 | 0 | 127954.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1054.5922 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 115821.8203 | 0 | 127954.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1054.5922 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 115821.8203 | 0 | 127954.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1054.5922 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 115821.8203 | 0 | 127954.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1054.5922 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 115821.8203 | 0 | 127954.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1054.5922 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 115821.8203 | 0 | 127954.9404 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1054.5922 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -425798.6875 | 0 | 60593.4062 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 12.4577 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -20054.3809 | 0 | 60971.127 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 75.2493 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 191d | [5 empty] | 3056193.1901 |  | 92.85% |  | 4609425.5609 | 4964207.224
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 773766.5692 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 64480.5469 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -93042.0312 | 0 | 64480.5469 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 40.9342 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 111766.2715 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 26291.4707 | 0 | 38688.3203 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 312.0819 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -406462.7812 | 0 | 42987.0312 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 9.5644 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 20448.9199 | 0 | 30090.9199 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 312.0817 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 133259.7889 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 14086.0596 | 0 | 25792.2197 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 220.3303 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -20753.6602 | 0 | 17194.8086 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 45.3109 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 19823.5801 | 0 | 77376.6504 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 134.444 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -26377.7891 | 0 | 8597.4102 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 24.5814 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 3052.8 | 0 | 4298.7001 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 345.0277 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 464259.9619 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 15998.0498 | 0 | 25792.2197 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 263.3426 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 112981.0625 | 0 | 146155.9141 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 440.5624 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -129718.7109 | 0 | 146155.9141 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 52.9791 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 112981.0625 | 0 | 146155.9141 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 440.5624 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 219233.8312 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 12896.1094 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -18608.4102 | 0 | 12896.1094 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 40.9342 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 21493.5095 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 312.0812 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -121938.8281 | 0 | 12896.1094 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 9.5644 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 312.0812 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 47285.7203 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 4695.3501 | 0 | 8597.4001 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 220.3303 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -5188.4199 | 0 | 4298.7002 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 45.3109 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 5506.5498 | 0 | 21493.5098 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 134.444 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -26377.7891 | 0 | 8597.4102 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 24.5814 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 3052.8 | 0 | 4298.7001 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 345.0277 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 137558.4919 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 5332.6802 | 0 | 8597.4001 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 263.3427 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 33229.7188 | 0 | 42987.0283 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 440.5623 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -38152.5586 | 0 | 42987.0352 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 52.9791 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 33229.7188 | 0 | 42987.0283 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 440.5623 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 219233.8312 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 12896.1094 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -18608.4102 | 0 | 12896.1094 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 40.9342 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 21493.5095 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 312.0812 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -121938.8281 | 0 | 12896.1094 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 9.5644 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 312.0812 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 47285.7203 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 4695.3501 | 0 | 8597.4001 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 220.3303 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -5188.4199 | 0 | 4298.7002 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 45.3109 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 5506.5498 | 0 | 21493.5098 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 134.444 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -26377.7891 | 0 | 8597.4102 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 24.5814 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 3052.8 | 0 | 4298.7001 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 345.0277 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 137558.4919 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 5332.6802 | 0 | 8597.4001 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 263.3427 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 33229.7188 | 0 | 42987.0283 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 440.5623 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -38152.5586 | 0 | 42987.0352 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 52.9791 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 33229.7188 | 0 | 42987.0283 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 440.5623 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 232129.9513 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 25792.2227 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -37216.8086 | 0 | 25792.2227 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 40.9342 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 34389.6189 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 312.0812 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -243877.6562 | 0 | 25792.2188 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 9.5644 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 312.0812 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 81675.349 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 7043.0298 | 0 | 12896.1099 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 220.3303 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -15565.25 | 0 | 12896.0996 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 45.3109 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 11013.0996 | 0 | 42987.0293 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 134.444 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -26377.7891 | 0 | 8597.4102 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 24.5814 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 3052.8 | 0 | 4298.7001 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 345.0277 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 90272.7607 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 7999.02 | 0 | 12896.1099 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 263.3423 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 33229.7188 | 0 | 42987.0283 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 440.5623 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -22891.5391 | 0 | 25792.2227 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 52.9791 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 6645.9399 | 0 | 8597.3999 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 440.5625 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 313805.3491 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 25792.2227 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -37216.8086 | 0 | 25792.2227 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 40.9342 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 60181.8494 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 5842.5498 | 0 | 8597.4099 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 312.0815 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -243877.6562 | 0 | 25792.2188 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 9.5644 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 17527.6504 | 0 | 25792.2207 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 312.0818 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 68779.2522 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 7043.0298 | 0 | 12896.1099 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 220.3303 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -10376.8301 | 0 | 8597.4102 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 45.311 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 5506.5498 | 0 | 21493.5098 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 134.444 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -52755.5781 | 0 | 17194.8125 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 24.5814 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 6105.6099 | 0 | 8597.4099 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 345.0281 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 159052.0249 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 10665.3701 | 0 | 17194.8203 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 263.3425 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 83074.3125 | 0 | 107467.582 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 440.5624 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -22891.5391 | 0 | 25792.2227 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 52.9791 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 6645.9399 | 0 | 8597.3999 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 440.5625 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 206337.7601 |  | 100% |  | 405866.8156 | 405866.8156
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 8597.4102 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -12405.5996 | 0 | 8597.4102 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 40.9342 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 34389.6412 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 312.0812 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -203231.375 | 0 | 21493.5312 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 9.5644 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 5842.5498 | 0 | 8597.4099 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 312.0815 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 77376.6509 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 4695.3501 | 0 | 8597.4001 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 220.3303 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -10376.8301 | 0 | 8597.4102 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 45.311 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 8810.4805 | 0 | 34389.6211 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 134.444 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -39566.6797 | 0 | 12896.1094 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 24.5814 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 9158.4102 | 0 | 12896.1101 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 345.028 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 85974.0579 |  | 100% |  | 51350.6895 | 51350.6895
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 13331.71 | 0 | 21493.52 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 263.3426 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 33229.7188 | 0 | 42987.0283 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 440.5623 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -15261.0303 | 0 | 17194.8096 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 52.9791 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 3322.97 | 0 | 4298.7 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 440.5625 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 103168.8572 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 4298.71 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -6202.7998 | 0 | 4298.71 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 40.9342 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 21493.5095 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 312.0812 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -121938.8281 | 0 | 12896.1094 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 9.5644 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 312.0812 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 60181.8379 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 11013.0996 | 0 | 42987.0293 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 134.444 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -20753.6602 | 0 | 17194.8086 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 45.3109 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 17194.7998 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 6645.9399 | 0 | 8597.3999 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 440.5625 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -3815.26 | 0 | 4298.7 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 52.9791 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 3322.97 | 0 | 4298.7 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 440.5625 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 167649.4314 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 8597.4102 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -12405.5996 | 0 | 8597.4102 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 40.9342 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 55883.1404 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 312.0812 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 19436.4805 | 0 | 34389.6309 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 229.9825 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -121938.8281 | 0 | 12896.1094 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 9.5644 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 2921.27 | 0 | 4298.7001 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 312.0812 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 85974.0811 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -10376.8301 | 0 | 8597.4102 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 45.311 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -13286.5801 | 0 | 8597.4102 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 39.2863 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 6607.8599 | 0 | 25792.2192 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 134.444 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -7048.5601 | 0 | 42987.0415 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 85.9129 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 17194.7998 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 6645.9399 | 0 | 8597.3999 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 440.5625 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -3815.26 | 0 | 4298.7 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 52.9791 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 3322.97 | 0 | 4298.7 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 440.5625 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 94d | [5 empty] | 820867.6094 |  | 70.22% |  | 836413.5 | 1191195.1631
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 94d | [5 empty] | 605932.4375 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 46d | 217784.0625 | 0 | 605932.4375 | 0 | 75.27% | Started | 388148.375 | 388148.375 | 100 | 100 | 75.2688 | 100 | 156.1085 | 75.2688
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 319190.0439
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 |  | 0 | 0 | 175400.3438 | 5d | 0 | 0 | 0 | 175400.3438 | 0% | Not Started | 0 | 175400.3438 | 100 |  | 0 | 100 |  | 0
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 32126.5508 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 2005-01-10 08:00 | 50d | 448265.125 | 0 | 46d | -233329.9531 | 0 | 214935.1719 | 0 | 52.08% | Started | 448265.125 | 448265.125 | 100 | 100 | 52.0833 | 100 | 47.9482 | 52.0833
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 203d | [5 empty] | 2818185.4338 |  | 85.75% |  | 4988300.6425 | 5581776.1461
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 184844.243 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 38688.3311 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -7782.1201 | 0 | 21493.5205 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 73.4178 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -10535.3203 | 0 | 17194.8105 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 62.0077 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 17194.8098 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 7219.4502 | 0 | 8597.4001 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 623.9269 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -7048.4702 | 0 | 8597.4097 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 54.95 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 17194.8101 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 4829.2798 | 0 | 17194.8101 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 139.0544 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 111766.2921 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -19502.3301 | 0 | 42987.0293 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 68.791 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -15707.3896 | 0 | 8597.4111 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 35.3733 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 25334.3008 | 0 | 25792.2208 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 5632.4729 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -20493.1699 | 0 | 34389.6309 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 62.6601 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 236428.6854 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 51584.4412 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -9351.2305 | 0 | 8597.4102 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 47.9001 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 12691.96 | 0 | 12896.11 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 6316.9779 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -16727.7695 | 0 | 12896.1113 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 43.5328 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 12691.96 | 0 | 12896.11 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 6316.9779 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -1548.16 | 0 | 4298.6998 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 73.5215 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 8597.4001 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -1067.34 | 0 | 4298.7001 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 80.1094 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 2495.3401 | 0 | 4298.7001 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 238.3717 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 176246.844 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -11022.0703 | 0 | 12896.1094 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 53.9176 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -7971.1201 | 0 | 8597.4092 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 51.89 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -3301.4099 | 0 | 4298.7102 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 56.5611 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -24931.8496 | 0 | 21493.5098 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 46.2969 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -20644.6094 | 0 | 21493.5117 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 51.0073 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -181935.7188 | 0 | 107467.5938 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 37.1342 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 17194.7998 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 17194.7998 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -10561.0996 | 0 | 8597.4004 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 44.8751 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -8180.5498 | 0 | 8597.3994 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 51.2423 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 459961.2354 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 167649.4287 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -4134.2598 | 0 | 17194.8105 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 80.6168 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -33583.8008 | 0 | 30090.918 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 47.2572 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -31852.1992 | 0 | 30090.9297 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 48.5783 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -17027.1699 | 0 | 21493.5215 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 55.7973 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -21233.5508 | 0 | 25792.2188 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 54.847 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -9934.04 | 0 | 42987.0303 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 81.2286 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 85974.0625 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 46690.5508 | 0 | 85974.0625 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 218.8553 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 34389.6191 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -23706.4395 | 0 | 17194.8105 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 42.0398 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -24269.2109 | 0 | 17194.8086 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 41.4692 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 171948.125 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -289604.9688 | 0 | 171948.125 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 37.2542 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 292946.3235 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 95205.9896 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 38870.9297 | 0 | 39322.8697 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 8700.9049 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 3848.45 | 0 | 4298.7 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 954.7362 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -15454.29 | 0 | 25792.21 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 62.5319 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -15454.29 | 0 | 25792.21 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 62.5319 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 25792.209 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -11701.7695 | 0 | 12896.0996 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 52.4277 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -9971.25 | 0 | 12896.1094 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 56.3953 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 171948.125 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -723017.8125 | 0 | 171948.125 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 19.2128 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 18d | [5 empty] | 189142.9004 |  | 100% |  | 778542.7812 | 778542.7812
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 21493.5186 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | -12426.6299 | 0 | 21493.5186 | 0 | 100% | Finished | 33920.1484 | 33920.1484 | 100 | 100 | 100 | 100 | 63.365 | 100
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 9d | [5 empty] | 38688.3193 |  | 100% |  | 76109.8203 | 76109.8203
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -24596.8809 | 0 | 21493.5098 | 0 | 100% | Finished | 46090.3906 | 46090.3906 | 100 | 100 | 100 | 100 | 46.6334 | 100
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 0 | -12824.6201 | 0 | 17194.8096 | 0 | 100% | Finished | 30019.4297 | 30019.4297 | 100 | 100 | 100 | 100 | 57.2789 | 100
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 4d | [5 empty] | 128961.0625 |  | 100% |  | 668512.8125 | 668512.8125
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 2005-01-10 08:00 | 26d | 668512.8125 | 0 | 22d | -539551.75 | 0 | 128961.0625 | 0 | 54.17% | Started | 668512.8125 | 668512.8125 | 100 | 86.6667 | 54.1667 | 100 | 19.2907 | 54.1667
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 75d | [5 empty] | 569329.2168 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 215869.8906 | 0 | 247534.4512 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 781.7397 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 60d | 174759.7031 | 0 | 32d | 147035.0625 | 0 | 321794.7656 | 0 | 65.22% | Started | 174759.7031 | 174759.7031 | 100 | 92.3077 | 65.2174 | 100 | 184.1356 | 65.2174
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 |  | 0 | 0 | 4644.7798 | 8d | 0 | 0 | 0 | 4644.7798 | 0% | Not Started | 0 | 4644.7798 | 100 |  | 0 | 100 |  | 0
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 40d | [5 empty] | 717883.4167 |  | 98.41% |  | 1031627.991 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 61039.6797 | 0 | 73077.9492 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 607.047 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 57098.0586 | 0 | 60181.8386 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 1951.5607 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -26803.3203 | 0 | 4298.6992 | 0 | 100% | Finished | 31102.0195 | 31102.0195 | 100 | 2000 | 100 | 100 | 13.8213 | 100
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -67525.6484 | 0 | 64480.5547 | 0 | 100% | Finished | 132006.2031 | 132006.2031 | 100 | 166.6667 | 100 | 100 | 48.8466 | 100
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 70d | 413377.0625 | 0 | 34d | -112467.8438 | 0 | 300909.2188 | 0 | 67.31% | Started | 413377.0625 | 413377.0625 | 100 | 100 | 67.3077 | 100 | 72.7929 | 67.3077
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 2005-01-10 08:00 | 45d | 440020.6562 | 0 | 41d | -225085.5 | 0 | 214935.1562 | 0 | 52.33% | Started | 440020.6562 | 440020.6562 | 100 | 90 | 52.3256 | 100 | 48.8466 | 52.3256
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 3d | [5 empty] | 128961.0938 |  | 54.08% |  | 322152.7812 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 2005-01-11 08:00 | 35d | 322152.7812 | 0 | 32d | -193191.6875 | 0 | 128961.0938 | 0 | 52.24% | Started | 322152.7812 | 322152.7812 | 100 | 116.6667 | 52.2388 | 100 | 40.031 | 52.2388
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 4d | [5 empty] | 21493.519 |  | 3.427% |  | 3592.98 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 2005-01-10 08:00 | 5d | 3592.98 | 0 | 1d | 17900.5391 | 0 | 21493.519 | 0 | 83.33% | Started | 3592.98 | 3592.98 | 100 | 100 | 83.3333 | 100 | 598.2087 | 83.3333
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2005-01-20 17:00 |  | TP Name | 20/01, 2005
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 744d | [5 empty] | 7247868.4651 |  | 91.21% |  | 10417987.6493 | 11186199.6924
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -424249.0938 | 0 | 62143 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 12.7763 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -15715.4697 | 0 | 65310.0381 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 80.6043 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 196d | [5 empty] | 3299281.1183 |  | 96.39% |  | 4784825.9047 | 4964207.224
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 829552.5343 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 69129.375 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -88393.2031 | 0 | 69129.375 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 43.8854 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 119824.25 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 29080.7695 | 0 | 41477.6191 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 334.5819 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -403363.5625 | 0 | 46086.25 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 10.2539 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 22618.3809 | 0 | 32260.3809 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 334.5818 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 142867.3781 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 15945.5898 | 0 | 27651.75 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 236.2154 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -19513.9707 | 0 | 18434.498 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 48.5777 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 25402.1797 | 0 | 82955.25 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 144.137 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 26.3537 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 497731.5312 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 17857.5801 | 0 | 27651.75 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 282.3287 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 123518.4062 | 0 | 156693.2578 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 472.3254 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -119181.3594 | 0 | 156693.2656 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 56.7987 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 123518.4062 | 0 | 156693.2578 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 472.3254 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 235039.8998 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 13825.8789 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -17678.6406 | 0 | 13825.8789 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 43.8854 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 334.5818 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 50694.8802 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 236.2156 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -4878.4902 | 0 | 4608.6299 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 48.5778 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 144.137 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 26.3537 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 369.9037 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 147476.0056 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 5952.5298 | 0 | 9217.2498 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 282.329 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 472.3254 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -35053.3398 | 0 | 46086.2539 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 56.7987 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 472.3254 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 235039.8998 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 13825.8789 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -17678.6406 | 0 | 13825.8789 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 43.8854 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 334.5818 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 50694.8802 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 236.2156 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -4878.4902 | 0 | 4608.6299 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 48.5778 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 144.137 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 26.3537 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 147476.0056 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 5952.5298 | 0 | 9217.2498 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 282.329 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 472.3254 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -35053.3398 | 0 | 46086.2539 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 56.7987 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 472.3254 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 248865.7719 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 27651.75 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -35357.2812 | 0 | 27651.75 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 43.8854 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 36869.01 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 334.5818 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -242018.125 | 0 | 27651.75 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 10.2539 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 334.5818 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 87563.8693 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 7972.79 | 0 | 13825.8701 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 236.2153 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -14635.4805 | 0 | 13825.8691 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 48.5777 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 14112.3203 | 0 | 46086.25 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 144.137 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 26.3537 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 96781.1426 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 8928.79 | 0 | 13825.8799 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 282.3285 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 472.3254 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -21032 | 0 | 27651.7617 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 56.7987 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 336429.6313 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 27651.75 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -35357.2812 | 0 | 27651.75 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 43.8854 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 64520.7502 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 6462.3901 | 0 | 9217.2502 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 334.5814 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -242018.125 | 0 | 27651.75 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 10.2539 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 19387.1797 | 0 | 27651.75 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 334.5818 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 73737.9905 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 7972.79 | 0 | 13825.8701 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 236.2153 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 144.137 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -51515.8906 | 0 | 18434.5 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 26.3537 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 6725.4502 | 0 | 9217.2502 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 369.9033 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 170519.1406 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 11905.0498 | 0 | 18434.5 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 282.3285 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 90822.3594 | 0 | 115215.6289 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 472.3255 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -21032 | 0 | 27651.7617 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 56.7987 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 472.3259 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 221214.0201 |  | 100% |  | 405866.8156 | 405866.8156
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 9217.25 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -11785.7598 | 0 | 9217.25 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 43.8854 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 36869.0209 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -201681.7656 | 0 | 23043.1406 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 10.2539 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 6462.3901 | 0 | 9217.2502 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 334.5814 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 82955.248 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 236.2156 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 11289.8604 | 0 | 36869.001 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 144.137 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -38636.9219 | 0 | 13825.8672 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 26.3537 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 10088.1797 | 0 | 13825.8796 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 369.9034 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 92172.5012 |  | 100% |  | 51350.6895 | 51350.6895
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 14881.3203 | 0 | 23043.1304 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 282.3287 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 472.3254 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -14021.3398 | 0 | 18434.5 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 56.7987 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 110607.0127 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 4608.6299 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -5892.8799 | 0 | 4608.6299 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 43.8854 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 10.2539 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 64520.748 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 14112.3203 | 0 | 46086.25 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 144.137 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -19513.9707 | 0 | 18434.498 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 48.5777 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 18434.4998 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -3505.3301 | 0 | 4608.6299 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 56.7988 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 179736.3953 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 9217.25 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -11785.7598 | 0 | 9217.25 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 43.8854 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 59912.135 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 21915.8496 | 0 | 36869 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 246.5634 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 92172.5105 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -12666.7402 | 0 | 9217.25 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 42.1187 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 8467.3896 | 0 | 27651.749 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 144.1369 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -3949.3401 | 0 | 46086.2615 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 92.1069 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 18434.4998 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -3505.3301 | 0 | 4608.6299 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 56.7988 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 99d | [5 empty] | 902795.9531 |  | 84.94% |  | 1011813.8438 | 1191195.1631
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 99d | [5 empty] | 649321.5625 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 41d | 261173.1875 | 0 | 649321.5625 | 0 | 77.35% | Started | 388148.375 | 388148.375 | 100 | 100 | 77.3481 | 100 | 167.2869 | 77.3481
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 2d | [5 empty] | 23043.1094 |  | 54.95% |  | 175400.3438 | 319190.0439
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 | 2005-01-19 08:00 | 9d | 175400.3438 | 0 | 7d | -152357.2344 | 0 | 23043.1094 | 0 | 56.25% | Started | 175400.3438 | 175400.3438 | 100 | 180 | 56.25 | 100 | 13.1374 | 56.25
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 32126.5508 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 2005-01-10 08:00 | 50d | 448265.125 | 0 | 41d | -217833.8438 | 0 | 230431.2812 | 0 | 54.95% | Started | 448265.125 | 448265.125 | 100 | 100 | 54.9451 | 100 | 51.4051 | 54.9451
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 208d | [5 empty] | 3051545.1349 |  | 85.83% |  | 4992945.4223 | 5581776.1461
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 198170.8831 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 41477.6318 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -6232.5098 | 0 | 23043.1309 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 78.7109 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -9295.6299 | 0 | 18434.501 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 66.4782 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 18434.4998 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 7839.2998 | 0 | 9217.2498 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 668.9103 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -6428.6299 | 0 | 9217.25 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 58.9117 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 18434.5005 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 6068.9702 | 0 | 18434.5005 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 149.0797 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 119824.2511 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -16403.1094 | 0 | 46086.25 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 73.7506 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -15087.5498 | 0 | 9217.251 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 37.9236 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 27193.8301 | 0 | 27651.7501 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 6038.5546 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -18013.8008 | 0 | 36869 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 67.1777 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 253474.3816 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 55303.5012 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -8731.3896 | 0 | 9217.251 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 51.3535 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 13621.7197 | 0 | 13825.8697 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 6772.4076 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -15798 | 0 | 13825.8809 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 46.6714 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 13621.7197 | 0 | 13825.8697 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 6772.4076 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -1238.23 | 0 | 4608.6299 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 78.8223 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 9217.2401 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -757.42 | 0 | 4608.6201 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 85.8849 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 2805.26 | 0 | 4608.62 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 255.5574 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 188953.6404 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -10092.3096 | 0 | 13825.8701 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 57.8049 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -7351.2798 | 0 | 9217.2495 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 55.6311 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -2991.49 | 0 | 4608.6301 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 60.6389 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -23382.2305 | 0 | 23043.1289 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 49.6348 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -19095 | 0 | 23043.1211 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 54.6847 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -174187.6719 | 0 | 115215.6406 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 39.8114 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 18434.499 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 18434.499 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -9941.25 | 0 | 9217.25 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 48.1105 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -7560.7002 | 0 | 9217.249 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 54.9367 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 493122.9216 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 179736.3904 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -2894.5701 | 0 | 18434.5002 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 86.429 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -31414.3398 | 0 | 32260.3789 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 50.6643 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -29682.75 | 0 | 32260.3789 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 52.0806 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -15477.5596 | 0 | 23043.1318 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 59.8201 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -19374.0195 | 0 | 27651.75 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 58.8013 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -6834.8198 | 0 | 46086.2505 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 87.0849 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 92172.5 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 52888.9883 | 0 | 92172.5 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 234.6341 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 36869 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -22466.75 | 0 | 18434.5 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 45.0707 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -23029.5195 | 0 | 18434.5 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 44.459 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 184345.0312 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -277208.0625 | 0 | 184345.0312 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 39.9402 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 312781.3375 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 100784.5992 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 40420.5391 | 0 | 40872.4791 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 9043.7843 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 4158.3701 | 0 | 4608.6201 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 1023.5692 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -13594.75 | 0 | 27651.75 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 67.0402 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -13594.75 | 0 | 27651.75 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 67.0402 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 27651.7383 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -10772 | 0 | 13825.8691 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 56.2076 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -9041.4902 | 0 | 13825.8691 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 60.4612 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 184345 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -710620.9375 | 0 | 184345 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 20.598 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 23d | [5 empty] | 202779.5 |  | 100% |  | 778542.7812 | 778542.7812
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 23043.1289 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | -10877.0195 | 0 | 23043.1289 | 0 | 100% | Finished | 33920.1484 | 33920.1484 | 100 | 100 | 100 | 100 | 67.9335 | 100
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 9d | [5 empty] | 41477.6211 |  | 100% |  | 76109.8203 | 76109.8203
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -23047.2695 | 0 | 23043.1211 | 0 | 100% | Finished | 46090.3906 | 46090.3906 | 100 | 100 | 100 | 100 | 49.9955 | 100
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 0 | -11584.9297 | 0 | 18434.5 | 0 | 100% | Finished | 30019.4297 | 30019.4297 | 100 | 100 | 100 | 100 | 61.4086 | 100
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 9d | [5 empty] | 138258.75 |  | 100% |  | 668512.8125 | 668512.8125
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 2005-01-10 08:00 | 31d | 668512.8125 | 0 | 22d | -530254.0625 | 0 | 138258.75 | 0 | 58.49% | Started | 668512.8125 | 668512.8125 | 100 | 103.3333 | 58.4906 | 100 | 20.6815 | 58.4906
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 80d | [5 empty] | 604970.2793 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 231366 | 0 | 263030.5605 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 830.6781 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 74d | 174759.7031 | 0 | 39d 4h | 167180.0156 | 0 | 341939.7188 | 0 | 65.22% | Started | 174759.7031 | 174759.7031 | 100 | 113.8462 | 65.2174 | 100 | 195.6628 | 65.2174
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 4d | [5 empty] | 36869.0103 |  | 18.7% |  | 4644.7798 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 | 2005-01-17 08:00 | 4d | 4644.7798 | 0 | 0 | 32224.2305 | 0 | 36869.0103 | 0 | 100% | Finished | 4644.7798 | 4644.7798 | 100 | 50 | 100 | 100 | 793.7731 | 100
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 45d | [5 empty] | 769640.4265 |  | 98.41% |  | 1031627.991 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 66308.3594 | 0 | 78346.6289 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 650.813 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 61436.9688 | 0 | 64520.7488 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 2092.2617 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -26493.4004 | 0 | 4608.6191 | 0 | 100% | Finished | 31102.0195 | 31102.0195 | 100 | 2000 | 100 | 100 | 14.8177 | 100
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -62876.8203 | 0 | 69129.3828 | 0 | 100% | Finished | 132006.2031 | 132006.2031 | 100 | 166.6667 | 100 | 100 | 52.3683 | 100
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 70d | 413377.0625 | 0 | 29d | -90773.2812 | 0 | 322603.7812 | 0 | 70.71% | Started | 413377.0625 | 413377.0625 | 100 | 100 | 70.7071 | 100 | 78.041 | 70.7071
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 2005-01-10 08:00 | 45d | 440020.6562 | 0 | 36d | -209589.3906 | 0 | 230431.2656 | 0 | 55.56% | Started | 440020.6562 | 440020.6562 | 100 | 90 | 55.5556 | 100 | 52.3683 | 55.5556
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 8d | [5 empty] | 138258.7656 |  | 54.08% |  | 322152.7812 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 2005-01-11 08:00 | 35d | 322152.7812 | 0 | 27d | -183894.0156 | 0 | 138258.7656 | 0 | 56.45% | Started | 322152.7812 | 322152.7812 | 100 | 116.6667 | 56.4516 | 100 | 42.9171 | 56.4516
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 9d | [5 empty] | 23043.1304 |  | 3.427% |  | 3592.98 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 2005-01-10 08:00 | 5d | 3592.98 | 0 | 0 | 19450.1504 | 0 | 23043.1304 | 0 | 100% | Finished | 3592.98 | 3592.98 | 100 | 100 | 100 | 100 | 641.3376 | 100
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 |  | 0 | 0 | 78335.2422 | 15d | 0 | 0 | 0 | 78335.2422 | 0% | Not Started | 0 | 78335.2422 | 100 |  | 0 | 100 |  | 0
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2005-01-28 17:00 |  | TP Name | 28/01, 2005
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 750d | [5 empty] | 7316997.847 |  | 91.9% |  | 10496322.8914 | 11186199.6924
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -424249.0938 | 0 | 62143 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 12.7763 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -15715.4697 | 0 | 65310.0381 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 80.6043 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 202d | [5 empty] | 3299281.1183 |  | 96.39% |  | 4784825.9047 | 4964207.224
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 829552.5343 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 69129.375 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -88393.2031 | 0 | 69129.375 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 43.8854 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 119824.25 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 29080.7695 | 0 | 41477.6191 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 334.5819 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -403363.5625 | 0 | 46086.25 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 10.2539 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 22618.3809 | 0 | 32260.3809 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 334.5818 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 142867.3781 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 15945.5898 | 0 | 27651.75 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 236.2154 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -19513.9707 | 0 | 18434.498 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 48.5777 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 25402.1797 | 0 | 82955.25 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 144.137 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 26.3537 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 497731.5312 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 17857.5801 | 0 | 27651.75 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 282.3287 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 123518.4062 | 0 | 156693.2578 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 472.3254 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -119181.3594 | 0 | 156693.2656 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 56.7987 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 123518.4062 | 0 | 156693.2578 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 472.3254 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 235039.8998 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 13825.8789 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -17678.6406 | 0 | 13825.8789 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 43.8854 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 334.5818 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 50694.8802 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 236.2156 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -4878.4902 | 0 | 4608.6299 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 48.5778 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 144.137 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 26.3537 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 369.9037 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 147476.0056 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 5952.5298 | 0 | 9217.2498 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 282.329 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 472.3254 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -35053.3398 | 0 | 46086.2539 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 56.7987 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 472.3254 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 235039.8998 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 13825.8789 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -17678.6406 | 0 | 13825.8789 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 43.8854 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 334.5818 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 50694.8802 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 236.2156 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -4878.4902 | 0 | 4608.6299 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 48.5778 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 144.137 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 26.3537 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 147476.0056 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 5952.5298 | 0 | 9217.2498 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 282.329 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 472.3254 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -35053.3398 | 0 | 46086.2539 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 56.7987 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 472.3254 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 248865.7719 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 27651.75 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -35357.2812 | 0 | 27651.75 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 43.8854 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 36869.01 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 334.5818 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -242018.125 | 0 | 27651.75 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 10.2539 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 334.5818 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 87563.8693 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 7972.79 | 0 | 13825.8701 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 236.2153 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -14635.4805 | 0 | 13825.8691 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 48.5777 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 14112.3203 | 0 | 46086.25 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 144.137 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 26.3537 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 96781.1426 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 8928.79 | 0 | 13825.8799 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 282.3285 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 472.3254 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -21032 | 0 | 27651.7617 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 56.7987 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 336429.6313 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 27651.75 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -35357.2812 | 0 | 27651.75 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 43.8854 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 64520.7502 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 6462.3901 | 0 | 9217.2502 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 334.5814 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -242018.125 | 0 | 27651.75 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 10.2539 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 19387.1797 | 0 | 27651.75 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 334.5818 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 73737.9905 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 7972.79 | 0 | 13825.8701 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 236.2153 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 144.137 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -51515.8906 | 0 | 18434.5 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 26.3537 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 6725.4502 | 0 | 9217.2502 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 369.9033 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 170519.1406 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 11905.0498 | 0 | 18434.5 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 282.3285 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 90822.3594 | 0 | 115215.6289 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 472.3255 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -21032 | 0 | 27651.7617 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 56.7987 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 472.3259 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 221214.0201 |  | 100% |  | 405866.8156 | 405866.8156
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 9217.25 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -11785.7598 | 0 | 9217.25 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 43.8854 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 36869.0209 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -201681.7656 | 0 | 23043.1406 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 10.2539 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 6462.3901 | 0 | 9217.2502 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 334.5814 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 82955.248 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 236.2156 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 11289.8604 | 0 | 36869.001 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 144.137 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -38636.9219 | 0 | 13825.8672 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 26.3537 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 10088.1797 | 0 | 13825.8796 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 369.9034 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 92172.5012 |  | 100% |  | 51350.6895 | 51350.6895
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 14881.3203 | 0 | 23043.1304 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 282.3287 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 472.3254 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -14021.3398 | 0 | 18434.5 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 56.7987 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 110607.0127 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 4608.6299 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -5892.8799 | 0 | 4608.6299 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 43.8854 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 10.2539 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 64520.748 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 14112.3203 | 0 | 46086.25 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 144.137 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -19513.9707 | 0 | 18434.498 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 48.5777 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 18434.4998 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -3505.3301 | 0 | 4608.6299 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 56.7988 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 179736.3953 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 9217.25 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -11785.7598 | 0 | 9217.25 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 43.8854 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 59912.135 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 21915.8496 | 0 | 36869 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 246.5634 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 92172.5105 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -12666.7402 | 0 | 9217.25 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 42.1187 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 8467.3896 | 0 | 27651.749 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 144.1369 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -3949.3401 | 0 | 46086.2615 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 92.1069 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 18434.4998 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -3505.3301 | 0 | 4608.6299 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 56.7988 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 105d | [5 empty] | 902795.9531 |  | 84.94% |  | 1011813.8438 | 1191195.1631
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 105d | [5 empty] | 649321.5625 |  | 91.6% |  | 388148.375 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 35d | 261173.1875 | 0 | 649321.5625 | 0 | 80% | Started | 388148.375 | 388148.375 | 100 | 100 | 80 | 100 | 167.2869 | 80
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 |  | 0 | 0 | 10863.2598 | 20d | 0 | 0 | 0 | 10863.2598 | 0% | Not Started | 0 | 10863.2598 | 100 |  | 0 | 100 |  | 0
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 8d | [5 empty] | 23043.1094 |  | 54.95% |  | 175400.3438 | 319190.0439
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 | 2005-01-19 08:00 | 13d | 175400.3438 | 0 | 5d | -152357.2344 | 0 | 23043.1094 | 0 | 72.22% | Started | 175400.3438 | 175400.3438 | 100 | 260 | 72.2222 | 100 | 13.1374 | 72.2222
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 32126.5508 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 2005-01-10 08:00 | 50d | 448265.125 | 0 | 35d | -217833.8438 | 0 | 230431.2812 | 0 | 58.82% | Started | 448265.125 | 448265.125 | 100 | 100 | 58.8235 | 100 | 51.4051 | 58.8235
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 214d | [5 empty] | 3120674.5168 |  | 87.17% |  | 5071280.6645 | 5581776.1461
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 198170.8831 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 41477.6318 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -6232.5098 | 0 | 23043.1309 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 78.7109 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -9295.6299 | 0 | 18434.501 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 66.4782 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 18434.4998 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 7839.2998 | 0 | 9217.2498 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 668.9103 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -6428.6299 | 0 | 9217.25 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 58.9117 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 18434.5005 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 6068.9702 | 0 | 18434.5005 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 149.0797 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 119824.2511 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -16403.1094 | 0 | 46086.25 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 73.7506 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -15087.5498 | 0 | 9217.251 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 37.9236 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 27193.8301 | 0 | 27651.7501 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 6038.5546 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -18013.8008 | 0 | 36869 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 67.1777 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 253474.3816 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 55303.5012 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -8731.3896 | 0 | 9217.251 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 51.3535 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 13621.7197 | 0 | 13825.8697 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 6772.4076 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -15798 | 0 | 13825.8809 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 46.6714 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 13621.7197 | 0 | 13825.8697 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 6772.4076 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -1238.23 | 0 | 4608.6299 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 78.8223 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 9217.2401 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -757.42 | 0 | 4608.6201 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 85.8849 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 2805.26 | 0 | 4608.62 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 255.5574 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 188953.6404 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -10092.3096 | 0 | 13825.8701 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 57.8049 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -7351.2798 | 0 | 9217.2495 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 55.6311 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -2991.49 | 0 | 4608.6301 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 60.6389 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -23382.2305 | 0 | 23043.1289 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 49.6348 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -19095 | 0 | 23043.1211 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 54.6847 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -174187.6719 | 0 | 115215.6406 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 39.8114 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 18434.499 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 18434.499 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -9941.25 | 0 | 9217.25 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 48.1105 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -7560.7002 | 0 | 9217.249 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 54.9367 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 493122.9216 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 179736.3904 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -2894.5701 | 0 | 18434.5002 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 86.429 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -31414.3398 | 0 | 32260.3789 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 50.6643 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -29682.75 | 0 | 32260.3789 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 52.0806 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -15477.5596 | 0 | 23043.1318 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 59.8201 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -19374.0195 | 0 | 27651.75 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 58.8013 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -6834.8198 | 0 | 46086.2505 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 87.0849 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 92172.5 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 52888.9883 | 0 | 92172.5 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 234.6341 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 36869 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -22466.75 | 0 | 18434.5 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 45.0707 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -23029.5195 | 0 | 18434.5 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 44.459 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 184345.0312 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -277208.0625 | 0 | 184345.0312 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 39.9402 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 312781.3375 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 100784.5992 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 40420.5391 | 0 | 40872.4791 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 9043.7843 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 4158.3701 | 0 | 4608.6201 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 1023.5692 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -13594.75 | 0 | 27651.75 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 67.0402 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -13594.75 | 0 | 27651.75 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 67.0402 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 27651.7383 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -10772 | 0 | 13825.8691 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 56.2076 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -9041.4902 | 0 | 13825.8691 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 60.4612 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 184345 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -710620.9375 | 0 | 184345 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 20.598 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 29d | [5 empty] | 202779.5 |  | 100% |  | 778542.7812 | 778542.7812
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 23043.1289 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | -10877.0195 | 0 | 23043.1289 | 0 | 100% | Finished | 33920.1484 | 33920.1484 | 100 | 100 | 100 | 100 | 67.9335 | 100
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 9d | [5 empty] | 41477.6211 |  | 100% |  | 76109.8203 | 76109.8203
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -23047.2695 | 0 | 23043.1211 | 0 | 100% | Finished | 46090.3906 | 46090.3906 | 100 | 100 | 100 | 100 | 49.9955 | 100
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 0 | -11584.9297 | 0 | 18434.5 | 0 | 100% | Finished | 30019.4297 | 30019.4297 | 100 | 100 | 100 | 100 | 61.4086 | 100
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 15d | [5 empty] | 138258.75 |  | 100% |  | 668512.8125 | 668512.8125
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 2005-01-10 08:00 | 31d | 668512.8125 | 0 | 16d | -530254.0625 | 0 | 138258.75 | 0 | 65.96% | Started | 668512.8125 | 668512.8125 | 100 | 103.3333 | 65.9574 | 100 | 20.6815 | 65.9574
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 86d | [5 empty] | 604970.2793 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 231366 | 0 | 263030.5605 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 830.6781 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 74d | 174759.7031 | 0 | 35d | 167180.0156 | 0 | 341939.7188 | 0 | 67.89% | Started | 174759.7031 | 174759.7031 | 100 | 113.8462 | 67.8899 | 100 | 195.6628 | 67.8899
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 10d | [5 empty] | 36869.0103 |  | 18.7% |  | 4644.7798 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 | 2005-01-17 08:00 | 4d | 4644.7798 | 0 | 0 | 32224.2305 | 0 | 36869.0103 | 0 | 100% | Finished | 4644.7798 | 4644.7798 | 100 | 50 | 100 | 100 | 793.7731 | 100
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 |  | 0 | 0 | 3364.77 | 6d | 0 | 0 | 0 | 3364.77 | 0% | Not Started | 0 | 3364.77 | 100 |  | 0 | 100 |  | 0
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 51d | [5 empty] | 769640.4265 |  | 98.41% |  | 1031627.991 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 66308.3594 | 0 | 78346.6289 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 650.813 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 61436.9688 | 0 | 64520.7488 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 2092.2617 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -26493.4004 | 0 | 4608.6191 | 0 | 100% | Finished | 31102.0195 | 31102.0195 | 100 | 2000 | 100 | 100 | 14.8177 | 100
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -62876.8203 | 0 | 69129.3828 | 0 | 100% | Finished | 132006.2031 | 132006.2031 | 100 | 166.6667 | 100 | 100 | 52.3683 | 100
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 70d | 413377.0625 | 0 | 23d | -90773.2812 | 0 | 322603.7812 | 0 | 75.27% | Started | 413377.0625 | 413377.0625 | 100 | 100 | 75.2688 | 100 | 78.041 | 75.2688
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 2005-01-10 08:00 | 45d | 440020.6562 | 0 | 30d | -209589.3906 | 0 | 230431.2656 | 0 | 60% | Started | 440020.6562 | 440020.6562 | 100 | 90 | 60 | 100 | 52.3683 | 60
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 14d | [5 empty] | 138258.7656 |  | 54.08% |  | 322152.7812 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 2005-01-11 08:00 | 35d | 322152.7812 | 0 | 21d | -183894.0156 | 0 | 138258.7656 | 0 | 62.5% | Started | 322152.7812 | 322152.7812 | 100 | 116.6667 | 62.5 | 100 | 42.9171 | 62.5
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 15d | [5 empty] | 92172.5122 |  | 78.14% |  | 81928.2222 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 2005-01-10 08:00 | 5d | 3592.98 | 0 | 0 | 19450.1504 | 0 | 23043.1304 | 0 | 100% | Finished | 3592.98 | 3592.98 | 100 | 100 | 100 | 100 | 641.3376 | 100
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 | 2005-01-24 08:00 | 15d | 78335.2422 | 0 | 10d | -9205.8604 | 0 | 69129.3818 | 0 | 60% | Started | 78335.2422 | 78335.2422 | 100 | 100 | 60 | 100 | 88.2481 | 60
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2005-02-03 17:00 |  | TP Name | 03/02, 2005
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 754d | [5 empty] | 7437030.7947 |  | 92.02% |  | 10510550.9212 | 11186199.6924
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 116131.7422 | 0 | 128264.8623 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1057.1466 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -424249.0938 | 0 | 62143 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 12.7763 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -15715.4697 | 0 | 65310.0381 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 80.6043 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 206d | [5 empty] | 3391453.6281 |  | 96.61% |  | 4795689.1644 | 4964207.224
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 829552.5343 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 69129.375 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -88393.2031 | 0 | 69129.375 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 43.8854 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 119824.25 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 29080.7695 | 0 | 41477.6191 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 334.5819 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -403363.5625 | 0 | 46086.25 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 10.2539 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 22618.3809 | 0 | 32260.3809 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 334.5818 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 142867.3781 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 15945.5898 | 0 | 27651.75 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 236.2154 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -19513.9707 | 0 | 18434.498 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 48.5777 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 25402.1797 | 0 | 82955.25 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 144.137 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 26.3537 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 497731.5312 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 17857.5801 | 0 | 27651.75 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 282.3287 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 123518.4062 | 0 | 156693.2578 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 472.3254 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -119181.3594 | 0 | 156693.2656 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 56.7987 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 123518.4062 | 0 | 156693.2578 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 472.3254 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 235039.8998 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 13825.8789 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -17678.6406 | 0 | 13825.8789 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 43.8854 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 334.5818 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 50694.8802 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 236.2156 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -4878.4902 | 0 | 4608.6299 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 48.5778 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 144.137 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 26.3537 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 369.9037 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 147476.0056 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 5952.5298 | 0 | 9217.2498 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 282.329 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 472.3254 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -35053.3398 | 0 | 46086.2539 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 56.7987 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 472.3254 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 235039.8998 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 13825.8789 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -17678.6406 | 0 | 13825.8789 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 43.8854 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 334.5818 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 50694.8802 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 236.2156 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -4878.4902 | 0 | 4608.6299 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 48.5778 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 144.137 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 26.3537 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 147476.0056 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 5952.5298 | 0 | 9217.2498 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 282.329 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 472.3254 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -35053.3398 | 0 | 46086.2539 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 56.7987 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 472.3254 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 248865.7719 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 27651.75 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -35357.2812 | 0 | 27651.75 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 43.8854 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 36869.01 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 334.5818 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -242018.125 | 0 | 27651.75 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 10.2539 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 334.5818 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 87563.8693 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 7972.79 | 0 | 13825.8701 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 236.2153 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -14635.4805 | 0 | 13825.8691 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 48.5777 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 14112.3203 | 0 | 46086.25 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 144.137 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -25757.9492 | 0 | 9217.25 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 26.3537 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 3362.73 | 0 | 4608.63 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 369.9037 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 96781.1426 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 8928.79 | 0 | 13825.8799 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 282.3285 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 472.3254 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -21032 | 0 | 27651.7617 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 56.7987 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 336429.6313 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 27651.75 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -35357.2812 | 0 | 27651.75 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 43.8854 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 64520.7502 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 6462.3901 | 0 | 9217.2502 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 334.5814 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -242018.125 | 0 | 27651.75 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 10.2539 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 19387.1797 | 0 | 27651.75 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 334.5818 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 73737.9905 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 7972.79 | 0 | 13825.8701 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 236.2153 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 7056.1602 | 0 | 23043.1201 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 144.137 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -51515.8906 | 0 | 18434.5 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 26.3537 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 6725.4502 | 0 | 9217.2502 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 369.9033 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 170519.1406 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 11905.0498 | 0 | 18434.5 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 282.3285 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 90822.3594 | 0 | 115215.6289 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 472.3255 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -21032 | 0 | 27651.7617 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 56.7987 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 472.3259 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 221214.0201 |  | 100% |  | 405866.8156 | 405866.8156
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 9217.25 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -11785.7598 | 0 | 9217.25 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 43.8854 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 36869.0209 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -201681.7656 | 0 | 23043.1406 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 10.2539 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 6462.3901 | 0 | 9217.2502 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 334.5814 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 82955.248 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 5315.2002 | 0 | 9217.2502 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 236.2156 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 11289.8604 | 0 | 36869.001 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 144.137 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -38636.9219 | 0 | 13825.8672 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 26.3537 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 10088.1797 | 0 | 13825.8796 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 369.9034 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 92172.5012 |  | 100% |  | 51350.6895 | 51350.6895
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 14881.3203 | 0 | 23043.1304 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 282.3287 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 36328.9414 | 0 | 46086.251 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 472.3254 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -14021.3398 | 0 | 18434.5 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 56.7987 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 110607.0127 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 4608.6299 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -5892.8799 | 0 | 4608.6299 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 43.8854 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 23043.135 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 10.2539 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 64520.748 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 14112.3203 | 0 | 46086.25 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 144.137 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -19513.9707 | 0 | 18434.498 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 48.5777 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 18434.4998 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -3505.3301 | 0 | 4608.6299 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 56.7988 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 179736.3953 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 9217.25 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -11785.7598 | 0 | 9217.25 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 43.8854 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 59912.135 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 21915.8496 | 0 | 36869 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 246.5634 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -121009.0625 | 0 | 13825.875 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 10.2539 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 3231.2 | 0 | 4608.63 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 334.5818 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 92172.5105 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -9756.9902 | 0 | 9217.25 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 48.5777 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -12666.7402 | 0 | 9217.25 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 42.1187 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 8467.3896 | 0 | 27651.749 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 144.1369 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | -3949.3401 | 0 | 46086.2615 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 92.1069 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 18434.4998 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 7265.79 | 0 | 9217.25 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 472.3259 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -3505.3301 | 0 | 4608.6299 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 56.7988 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 3632.8899 | 0 | 4608.6199 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 472.3253 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 109d | [5 empty] | 994968.4629 |  | 85.85% |  | 1022677.1035 | 1191195.1631
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 109d | [5 empty] | 741494.0723 |  | 94.16% |  | 399011.6348 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 31d | 261173.1875 | 0 | 649321.5625 | 0 | 81.87% | Started | 388148.375 | 388148.375 | 100 | 100 | 81.8713 | 100 | 167.2869 | 81.8713
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 | 2005-01-31 08:00 | 15d | 10863.2598 | 0 | 11d | 81309.25 | 0 | 92172.5098 | 0 | 57.69% | Started | 10863.2598 | 10863.2598 | 100 | 75 | 57.6923 | 100 | 848.4793 | 57.6923
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 12d | [5 empty] | 23043.1094 |  | 54.95% |  | 175400.3438 | 319190.0439
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 | 2005-01-19 08:00 | 13d | 175400.3438 | 0 | 1d | -152357.2344 | 0 | 23043.1094 | 0 | 92.86% | Started | 175400.3438 | 175400.3438 | 100 | 260 | 92.8571 | 100 | 13.1374 | 92.8571
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 |  | 0 | 0 | 3926.79 | 10d | 0 | 0 | 0 | 3926.79 | 0% | Not Started | 0 | 3926.79 | 100 |  | 0 | 100 |  | 0
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 32126.5508 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 2005-01-10 08:00 | 50d | 448265.125 | 0 | 31d | -217833.8438 | 0 | 230431.2812 | 0 | 61.73% | Started | 448265.125 | 448265.125 | 100 | 100 | 61.7284 | 100 | 51.4051 | 61.7284
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 218d | [5 empty] | 3148534.9547 |  | 87.23% |  | 5074645.4345 | 5581776.1461
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 198170.8831 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 41477.6318 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -6232.5098 | 0 | 23043.1309 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 78.7109 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -9295.6299 | 0 | 18434.501 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 66.4782 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 18434.4998 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 7839.2998 | 0 | 9217.2498 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 668.9103 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -6428.6299 | 0 | 9217.25 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 58.9117 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 18434.5005 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 6068.9702 | 0 | 18434.5005 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 149.0797 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 119824.2511 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -16403.1094 | 0 | 46086.25 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 73.7506 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -15087.5498 | 0 | 9217.251 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 37.9236 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 27193.8301 | 0 | 27651.7501 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 6038.5546 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -18013.8008 | 0 | 36869 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 67.1777 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 253474.3816 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 55303.5012 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -8731.3896 | 0 | 9217.251 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 51.3535 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 13621.7197 | 0 | 13825.8697 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 6772.4076 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -15798 | 0 | 13825.8809 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 46.6714 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 13621.7197 | 0 | 13825.8697 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 6772.4076 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -1238.23 | 0 | 4608.6299 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 78.8223 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 9217.2401 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -757.42 | 0 | 4608.6201 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 85.8849 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 2805.26 | 0 | 4608.62 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 255.5574 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 188953.6404 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -10092.3096 | 0 | 13825.8701 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 57.8049 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -7351.2798 | 0 | 9217.2495 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 55.6311 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -2991.49 | 0 | 4608.6301 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 60.6389 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -23382.2305 | 0 | 23043.1289 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 49.6348 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -19095 | 0 | 23043.1211 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 54.6847 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -174187.6719 | 0 | 115215.6406 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 39.8114 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 18434.499 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 18434.499 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -9941.25 | 0 | 9217.25 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 48.1105 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -7560.7002 | 0 | 9217.249 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 54.9367 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 493122.9216 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 179736.3904 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -2894.5701 | 0 | 18434.5002 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 86.429 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -31414.3398 | 0 | 32260.3789 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 50.6643 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -29682.75 | 0 | 32260.3789 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 52.0806 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -15477.5596 | 0 | 23043.1318 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 59.8201 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -19374.0195 | 0 | 27651.75 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 58.8013 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -6834.8198 | 0 | 46086.2505 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 87.0849 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 92172.5 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 52888.9883 | 0 | 92172.5 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 234.6341 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 36869 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -22466.75 | 0 | 18434.5 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 45.0707 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -23029.5195 | 0 | 18434.5 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 44.459 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 184345.0312 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -277208.0625 | 0 | 184345.0312 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 39.9402 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 312781.3375 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 100784.5992 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 40420.5391 | 0 | 40872.4791 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 9043.7843 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 4158.3701 | 0 | 4608.6201 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 1023.5692 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -13594.75 | 0 | 27651.75 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 67.0402 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -13594.75 | 0 | 27651.75 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 67.0402 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 27651.7383 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -10772 | 0 | 13825.8691 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 56.2076 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -9041.4902 | 0 | 13825.8691 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 60.4612 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 184345 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -710620.9375 | 0 | 184345 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 20.598 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 33d | [5 empty] | 202779.5 |  | 100% |  | 778542.7812 | 778542.7812
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 23043.1289 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | -10877.0195 | 0 | 23043.1289 | 0 | 100% | Finished | 33920.1484 | 33920.1484 | 100 | 100 | 100 | 100 | 67.9335 | 100
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 9d | [5 empty] | 41477.6211 |  | 100% |  | 76109.8203 | 76109.8203
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -23047.2695 | 0 | 23043.1211 | 0 | 100% | Finished | 46090.3906 | 46090.3906 | 100 | 100 | 100 | 100 | 49.9955 | 100
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 0 | -11584.9297 | 0 | 18434.5 | 0 | 100% | Finished | 30019.4297 | 30019.4297 | 100 | 100 | 100 | 100 | 61.4086 | 100
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 19d | [5 empty] | 138258.75 |  | 100% |  | 668512.8125 | 668512.8125
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 2005-01-10 08:00 | 31d | 668512.8125 | 0 | 12d | -530254.0625 | 0 | 138258.75 | 0 | 72.09% | Started | 668512.8125 | 668512.8125 | 100 | 103.3333 | 72.093 | 100 | 20.6815 | 72.093
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 90d | [5 empty] | 605178.9668 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 231456.7344 | 0 | 263121.2949 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 830.9646 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 74d | 174759.7031 | 0 | 31d | 167297.9688 | 0 | 342057.6719 | 0 | 70.48% | Started | 174759.7031 | 174759.7031 | 100 | 113.8462 | 70.4762 | 100 | 195.7303 | 70.4762
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 14d | [5 empty] | 64520.7607 |  | 32.25% |  | 8009.5498 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 | 2005-01-17 08:00 | 4d | 4644.7798 | 0 | 0 | 32224.2305 | 0 | 36869.0103 | 0 | 100% | Finished | 4644.7798 | 4644.7798 | 100 | 50 | 100 | 100 | 793.7731 | 100
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 | 2005-01-31 08:00 | 6d | 3364.77 | 0 | 2d | 24286.9805 | 0 | 27651.7505 | 0 | 75% | Started | 3364.77 | 3364.77 | 100 | 100 | 75 | 100 | 821.8021 | 75
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 |  | 0 | 0 | 16823.8691 | 30d | 0 | 0 | 0 | 16823.8691 | 0% | Not Started | 0 | 16823.8691 | 100 |  | 0 | 100 |  | 0
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 55d | [5 empty] | 769640.4265 |  | 98.41% |  | 1031627.991 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 66308.3594 | 0 | 78346.6289 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 650.813 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 61436.9688 | 0 | 64520.7488 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 2092.2617 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -26493.4004 | 0 | 4608.6191 | 0 | 100% | Finished | 31102.0195 | 31102.0195 | 100 | 2000 | 100 | 100 | 14.8177 | 100
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -62876.8203 | 0 | 69129.3828 | 0 | 100% | Finished | 132006.2031 | 132006.2031 | 100 | 166.6667 | 100 | 100 | 52.3683 | 100
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 80d | 413377.0625 | 0 | 26d 2h | -90773.2812 | 0 | 322603.7812 | 0 | 75.27% | Started | 413377.0625 | 413377.0625 | 100 | 114.2857 | 75.2688 | 100 | 78.041 | 75.2688
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 2005-01-10 08:00 | 45d | 440020.6562 | 0 | 26d | -209589.3906 | 0 | 230431.2656 | 0 | 63.38% | Started | 440020.6562 | 440020.6562 | 100 | 90 | 63.3803 | 100 | 52.3683 | 63.3803
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 |  | 0 | 0 | 16655.1602 | 7d | 0 | 0 | 0 | 16655.1602 | 0% | Not Started | 0 | 16655.1602 | 100 |  | 0 | 100 |  | 0
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 18d | [5 empty] | 138258.7656 |  | 54.08% |  | 322152.7812 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 2005-01-11 08:00 | 35d | 322152.7812 | 0 | 17d | -183894.0156 | 0 | 138258.7656 | 0 | 67.31% | Started | 322152.7812 | 322152.7812 | 100 | 116.6667 | 67.3077 | 100 | 42.9171 | 67.3077
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 |  | 0 | 0 | 273554.7812 | 30d | 0 | 0 | 0 | 273554.7812 | 0% | Not Started | 0 | 273554.7812 | 100 |  | 0 | 100 |  | 0
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 19d | [5 empty] | 92172.5122 |  | 78.14% |  | 81928.2222 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 2005-01-10 08:00 | 5d | 3592.98 | 0 | 0 | 19450.1504 | 0 | 23043.1304 | 0 | 100% | Finished | 3592.98 | 3592.98 | 100 | 100 | 100 | 100 | 641.3376 | 100
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 | 2005-01-24 08:00 | 15d | 78335.2422 | 0 | 6d | -9205.8604 | 0 | 69129.3818 | 0 | 71.43% | Started | 78335.2422 | 78335.2422 | 100 | 100 | 71.4286 | 100 | 88.2481 | 71.4286
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 |  | 0 | 0 | 1511.83 | 3d | 0 | 0 | 0 | 1511.83 | 0% | Not Started | 0 | 1511.83 | 100 |  | 0 | 100 |  | 0
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 |  | 0 | 0 | 655.73 | 3d | 0 | 0 | 0 | 655.73 | 0% | Not Started | 0 | 655.73 | 100 |  | 0 | 100 |  | 0
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2005-02-10 17:00 |  | TP Name | 10/02, 2005
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 759d | [5 empty] | 8646408.0067 |  | 94.76% |  | 10823679.0818 | 11186199.6924
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 116680.7812 | 0 | 128813.9014 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1061.6717 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 116680.7812 | 0 | 128813.9014 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1061.6717 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 116680.7812 | 0 | 128813.9014 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1061.6717 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 116680.7812 | 0 | 128813.9014 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1061.6717 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 116680.7812 | 0 | 128813.9014 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1061.6717 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 116680.7812 | 0 | 128813.9014 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1061.6717 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -421503.875 | 0 | 64888.2188 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 13.3407 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | -8028.8398 | 0 | 72996.668 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 90.091 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 211d | [5 empty] | 3846578.1821 |  | 96.68% |  | 4799615.9545 | 4964207.224
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 928380.631 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 77365.0469 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -80157.5312 | 0 | 77365.0469 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 49.1136 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 134099.4375 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 34022.1797 | 0 | 46419.0293 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 374.4421 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -397873.0938 | 0 | 51576.7188 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 11.4755 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 26461.6895 | 0 | 36103.6895 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 374.4419 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 159887.7677 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 19239.8594 | 0 | 30946.0195 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 264.3567 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -17317.7891 | 0 | 20630.6797 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 54.365 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 35284.9883 | 0 | 92838.0586 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 161.3086 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -24659.8594 | 0 | 10315.3398 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 29.4933 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 3911.77 | 0 | 5157.67 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 413.9714 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 557028.3789 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 21151.8496 | 0 | 30946.0195 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 315.9637 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 142185.9375 | 0 | 175360.7891 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 528.5955 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -100513.8438 | 0 | 175360.7812 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 63.5654 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 142185.9375 | 0 | 175360.7891 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 528.5955 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 263041.1708 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 15473.0098 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -16031.5098 | 0 | 15473.0098 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 49.1136 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 25788.3479 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 374.4415 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -119361.9297 | 0 | 15473.0078 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 11.4755 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 374.4415 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 56734.3695 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 6413.29 | 0 | 10315.3401 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 264.3569 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -4329.4502 | 0 | 5157.6699 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 54.365 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 9801.3896 | 0 | 25788.3496 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 161.3087 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -24659.8594 | 0 | 10315.3398 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 29.4933 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 3911.77 | 0 | 5157.67 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 413.9714 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 165045.4436 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 7050.6201 | 0 | 10315.3401 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 315.964 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 41819.3906 | 0 | 51576.7002 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 528.5955 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -29562.8906 | 0 | 51576.7031 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 63.5654 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 41819.3906 | 0 | 51576.7002 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 528.5955 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 263041.1708 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 15473.0098 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -16031.5098 | 0 | 15473.0098 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 49.1136 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 25788.3479 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 374.4415 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -119361.9297 | 0 | 15473.0078 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 11.4755 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 374.4415 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 56734.3695 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 6413.29 | 0 | 10315.3401 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 264.3569 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -4329.4502 | 0 | 5157.6699 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 54.365 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 9801.3896 | 0 | 25788.3496 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 161.3087 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -24659.8594 | 0 | 10315.3398 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 29.4933 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 3911.77 | 0 | 5157.67 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 413.9714 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 165045.4436 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 7050.6201 | 0 | 10315.3401 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 315.964 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 41819.3906 | 0 | 51576.7002 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 528.5955 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -29562.8906 | 0 | 51576.7031 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 63.5654 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 41819.3906 | 0 | 51576.7002 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 528.5955 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 278514.1771 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 30946.0215 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -32063.0098 | 0 | 30946.0215 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 49.1136 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 41261.3557 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 374.4415 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -238723.8594 | 0 | 30946.0156 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 11.4755 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 374.4415 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 97995.7286 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 9619.9297 | 0 | 15473.0098 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 264.3567 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -12988.3398 | 0 | 15473.0098 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 54.365 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 19602.7695 | 0 | 51576.6992 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 161.3086 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -24659.8594 | 0 | 10315.3398 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 29.4933 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 3911.77 | 0 | 5157.67 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 413.9714 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 108311.0713 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 10575.9199 | 0 | 15473.0098 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 315.9634 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 41819.3906 | 0 | 51576.7002 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 528.5955 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -17737.7402 | 0 | 30946.0215 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 63.5654 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 8363.8799 | 0 | 10315.3398 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 528.596 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 376509.9038 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 30946.0215 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -32063.0098 | 0 | 30946.0215 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 49.1136 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 72207.3752 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 7560.48 | 0 | 10315.3401 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 374.4415 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -238723.8594 | 0 | 30946.0156 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 11.4755 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 22681.4492 | 0 | 30946.0195 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 374.442 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 82522.719 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 9619.9297 | 0 | 15473.0098 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 264.3567 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -8658.9004 | 0 | 10315.3398 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 54.365 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 9801.3896 | 0 | 25788.3496 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 161.3087 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -49319.7109 | 0 | 20630.6797 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 29.4933 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 7823.54 | 0 | 10315.3401 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 413.9714 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 190833.7881 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 14101.2305 | 0 | 20630.6807 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 315.9635 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 104548.4766 | 0 | 128941.7461 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 528.5956 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -17737.7402 | 0 | 30946.0215 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 63.5654 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 8363.8799 | 0 | 10315.3398 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 528.596 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 247568.1659 |  | 100% |  | 405866.8156 | 405866.8156
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 10315.3398 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -10687.6699 | 0 | 10315.3398 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 49.1136 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 41261.3695 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 374.4415 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -198936.5469 | 0 | 25788.3594 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 11.4755 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 7560.48 | 0 | 10315.3401 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 374.4415 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 92838.0576 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 6413.29 | 0 | 10315.3401 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 264.3569 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -8658.9004 | 0 | 10315.3398 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 54.365 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 15682.2197 | 0 | 41261.3604 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 161.3086 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -36989.7812 | 0 | 15473.0078 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 29.4933 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 11735.3096 | 0 | 15473.0095 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 413.9714 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 103153.3989 |  | 100% |  | 51350.6895 | 51350.6895
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 17626.5391 | 0 | 25788.3491 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 315.9636 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 41819.3906 | 0 | 51576.7002 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 528.5955 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -11825.1602 | 0 | 20630.6797 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 63.5654 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 4181.9399 | 0 | 5157.6699 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 528.596 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 123784.0764 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 5157.6699 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -5343.8398 | 0 | 5157.6699 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 49.1136 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 25788.3479 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 374.4415 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -119361.9297 | 0 | 15473.0078 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 11.4755 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 374.4415 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 72207.3789 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 19602.7695 | 0 | 51576.6992 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 161.3086 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -17317.7891 | 0 | 20630.6797 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 54.365 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 20630.6797 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 8363.8799 | 0 | 10315.3398 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 528.596 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -2956.29 | 0 | 5157.6699 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 63.5654 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 4181.9399 | 0 | 5157.6699 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 528.596 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 201149.1295 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 10315.3398 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -10687.6699 | 0 | 10315.3398 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 49.1136 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 67049.7092 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 374.4415 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 26308.2109 | 0 | 41261.3613 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 275.9376 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -119361.9297 | 0 | 15473.0078 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 11.4755 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 3780.24 | 0 | 5157.67 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 374.4415 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 103153.4008 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -8658.9004 | 0 | 10315.3398 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 54.365 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -11568.6504 | 0 | 10315.3398 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 47.1365 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 11761.6602 | 0 | 30946.0195 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 161.3086 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | 1541.1 | 0 | 51576.7015 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 103.08 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 20630.6797 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 8363.8799 | 0 | 10315.3398 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 528.596 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -2956.29 | 0 | 5157.6699 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 63.5654 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 4181.9399 | 0 | 5157.6699 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 528.596 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 114d | [5 empty] | 1164589.7568 |  | 86.18% |  | 1026603.8936 | 1191195.1631
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 114d | [5 empty] | 829341.2129 |  | 94.16% |  | 399011.6348 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 26d | 338039.4375 | 0 | 726187.8125 | 0 | 84.34% | Started | 388148.375 | 388148.375 | 100 | 100 | 84.3373 | 100 | 187.0903 | 84.3373
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 | 2005-01-31 08:00 | 15d | 10863.2598 | 0 | 6d | 92290.1406 | 0 | 103153.4004 | 0 | 71.43% | Started | 10863.2598 | 10863.2598 | 100 | 75 | 71.4286 | 100 | 949.5621 | 71.4286
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 17d | [5 empty] | 77365.0439 |  | 56.18% |  | 179327.1338 | 319190.0439
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 | 2005-01-19 08:00 | 13d | 175400.3438 | 0 | 0 | -149612 | 0 | 25788.3438 | 0 | 100% | Finished | 175400.3438 | 175400.3438 | 100 | 260 | 100 | 100 | 14.7026 | 100
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 |  | 0 | 0 | 88628.0391 | 20d | 0 | 0 | 0 | 88628.0391 | 0% | Not Started | 0 | 88628.0391 | 100 |  | 0 | 100 |  | 0
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 | 2005-02-07 08:00 | 10d | 3926.79 | 0 | 6d | 47649.9102 | 0 | 51576.7002 | 0 | 62.5% | Started | 3926.79 | 3926.79 | 100 | 100 | 62.5 | 100 | 1313.457 | 62.5
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 32126.5508 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 2005-01-10 08:00 | 50d | 448265.125 | 0 | 26d | -190381.625 | 0 | 257883.5 | 0 | 65.79% | Started | 448265.125 | 448265.125 | 100 | 100 | 65.7895 | 100 | 57.5292 | 65.7895
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 223d | [5 empty] | 3889061.5296 |  | 92.55% |  | 5383846.805 | 5581776.1461
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 221779.8114 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 46419.0312 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -3487.29 | 0 | 25788.3506 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 88.0881 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -7099.4502 | 0 | 20630.6807 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 74.3981 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 20630.6794 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 8937.3896 | 0 | 10315.3396 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 748.6005 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -5330.54 | 0 | 10315.3398 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 65.9301 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 20630.6807 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 8265.1504 | 0 | 20630.6807 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 166.8402 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 134099.42 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -10912.6602 | 0 | 51576.6992 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 82.5368 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -13989.46 | 0 | 10315.3408 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 42.4416 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 30488.0996 | 0 | 30946.0196 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 6757.9531 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -13621.4404 | 0 | 41261.3604 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 75.1809 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 283671.8683 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 61892.0421 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -7633.2998 | 0 | 10315.3408 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 57.4714 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 15268.8604 | 0 | 15473.0103 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 7579.2363 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -14150.8701 | 0 | 15473.0107 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 52.2315 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 15268.8604 | 0 | 15473.0103 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 7579.2363 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -689.19 | 0 | 5157.6699 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 88.2126 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 10315.3401 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | -208.37 | 0 | 5157.67 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 96.1169 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 3354.3101 | 0 | 5157.67 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 286.0034 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 211464.4861 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -8445.1699 | 0 | 15473.0098 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 64.6914 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -6253.1899 | 0 | 10315.3394 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 62.2586 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -2442.45 | 0 | 5157.6702 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 67.863 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -20637.0098 | 0 | 25788.3496 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 55.548 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -16349.7695 | 0 | 25788.3516 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 61.1996 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -160461.5469 | 0 | 128941.7656 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 44.5544 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 20630.6792 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 20630.6792 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -8843.1602 | 0 | 10315.3398 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 53.8421 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -6462.6099 | 0 | 10315.3394 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 61.4815 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 551870.7048 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 201149.1306 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | -698.39 | 0 | 20630.6803 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 96.7256 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -27571.0293 | 0 | 36103.6895 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 56.7002 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -25839.4395 | 0 | 36103.6895 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 58.2852 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -12732.3398 | 0 | 25788.3516 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 66.9468 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -16079.75 | 0 | 30946.0195 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 65.8065 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | -1344.37 | 0 | 51576.7003 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 97.4597 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 103153.4023 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 63869.8906 | 0 | 103153.4023 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 262.587 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 41261.3594 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -20270.5703 | 0 | 20630.6797 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 50.4402 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -20833.3398 | 0 | 20630.6797 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 49.7556 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 206306.8125 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -255246.2812 | 0 | 206306.8125 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 44.6984 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 347920.1788 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 110667.4107 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 43165.7617 | 0 | 43617.7017 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 9651.2151 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 4707.4199 | 0 | 5157.6699 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 1145.5125 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -10300.4805 | 0 | 30946.0195 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 75.027 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -10300.4805 | 0 | 30946.0195 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 75.027 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 30946.0181 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -9124.8604 | 0 | 15473.0088 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 62.9039 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -7394.3501 | 0 | 15473.0093 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 67.6642 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 206306.75 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -688659.1875 | 0 | 206306.75 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 23.0519 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 38d | [5 empty] | 226937.4736 |  | 100% |  | 778542.7812 | 778542.7812
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 25788.3486 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | -8131.7998 | 0 | 25788.3486 | 0 | 100% | Finished | 33920.1484 | 33920.1484 | 100 | 100 | 100 | 100 | 76.0266 | 100
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 9d | [5 empty] | 46419.0312 |  | 100% |  | 76109.8203 | 76109.8203
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -20302.0391 | 0 | 25788.3516 | 0 | 100% | Finished | 46090.3906 | 46090.3906 | 100 | 100 | 100 | 100 | 55.9517 | 100
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 0 | -9388.75 | 0 | 20630.6797 | 0 | 100% | Finished | 30019.4297 | 30019.4297 | 100 | 100 | 100 | 100 | 68.7244 | 100
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 24d | [5 empty] | 154730.0938 |  | 100% |  | 668512.8125 | 668512.8125
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 2005-01-10 08:00 | 31d | 668512.8125 | 0 | 7d | -513782.7188 | 0 | 154730.0938 | 0 | 81.58% | Started | 668512.8125 | 668512.8125 | 100 | 103.3333 | 81.5789 | 100 | 23.1454 | 81.5789
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 95d | [5 empty] | 668319.1074 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 258908.9688 | 0 | 290573.5293 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 917.6617 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 74d | 174759.7031 | 0 | 26d | 202985.875 | 0 | 377745.5781 | 0 | 74% | Started | 174759.7031 | 174759.7031 | 100 | 113.8462 | 74 | 100 | 216.1514 | 74
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 19d | [5 empty] | 226937.4814 |  | 100% |  | 24833.4189 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 | 2005-01-17 08:00 | 4d | 4644.7798 | 0 | 0 | 36616.5781 | 0 | 41261.3579 | 0 | 100% | Finished | 4644.7798 | 4644.7798 | 100 | 50 | 100 | 100 | 888.3383 | 100
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 | 2005-01-31 08:00 | 6d | 3364.77 | 0 | 0 | 27581.25 | 0 | 30946.02 | 0 | 100% | Finished | 3364.77 | 3364.77 | 100 | 100 | 100 | 100 | 919.7068 | 100
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 | 2005-02-08 08:00 | 3d | 16823.8691 | 0 | 2d 5h | 137906.2344 | 0 | 154730.1035 | 0 | 53.33% | Started | 16823.8691 | 16823.8691 | 100 | 10 | 53.3333 | 100 | 919.7058 | 53.3333
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 60d | [5 empty] | 897434.5847 |  | 100% |  | 1048283.1511 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 75642.1172 | 0 | 87680.3867 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 728.3471 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 69123.6016 | 0 | 72207.3816 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 2341.5218 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -25944.3496 | 0 | 5157.6699 | 0 | 100% | Finished | 31102.0195 | 31102.0195 | 100 | 2000 | 100 | 100 | 16.5831 | 100
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -54641.1484 | 0 | 77365.0547 | 0 | 100% | Finished | 132006.2031 | 132006.2031 | 100 | 166.6667 | 100 | 100 | 58.6071 | 100
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 80d | 413377.0625 | 0 | 24d | -52340.1602 | 0 | 361036.9023 | 0 | 76.92% | Started | 413377.0625 | 413377.0625 | 100 | 114.2857 | 76.9231 | 100 | 87.3384 | 76.9231
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 2005-01-10 08:00 | 45d | 440020.6562 | 0 | 21d | -182137.1562 | 0 | 257883.5 | 0 | 68.18% | Started | 440020.6562 | 440020.6562 | 100 | 90 | 68.1818 | 100 | 58.6071 | 68.1818
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 | 2005-02-04 08:00 | 7d | 16655.1602 | 0 | 3d | 19448.5293 | 0 | 36103.6895 | 0 | 70% | Started | 16655.1602 | 16655.1602 | 100 | 100 | 70 | 100 | 216.7718 | 70
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 23d | [5 empty] | 309460.2188 |  | 100% |  | 595707.5625 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 2005-01-11 08:00 | 35d | 322152.7812 | 0 | 12d | -167422.6719 | 0 | 154730.1094 | 0 | 74.47% | Started | 322152.7812 | 322152.7812 | 100 | 116.6667 | 74.4681 | 100 | 48.03 | 74.4681
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 | 2005-02-10 08:00 | 27d | 273554.7812 | 0 | 26d | -118824.6719 | 0 | 154730.1094 | 0 | 50.94% | Started | 273554.7812 | 273554.7812 | 100 | 90 | 50.9434 | 100 | 56.5628 | 50.9434
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 24d | [5 empty] | 103153.4013 |  | 78.14% |  | 81928.2222 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 2005-01-10 08:00 | 5d | 3592.98 | 0 | 0 | 22195.3691 | 0 | 25788.3491 | 0 | 100% | Finished | 3592.98 | 3592.98 | 100 | 100 | 100 | 100 | 717.7426 | 100
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 | 2005-01-24 08:00 | 15d | 78335.2422 | 0 | 1d | -970.19 | 0 | 77365.0522 | 0 | 93.75% | Started | 78335.2422 | 78335.2422 | 100 | 100 | 93.75 | 100 | 98.7615 | 93.75
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 |  | 0 | 0 | 182.46 | 2d | 0 | 0 | 0 | 182.46 | 0% | Not Started | 0 | 182.46 | 100 |  | 0 | 100 |  | 0
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 |  | 0 | 0 | 19392.5605 | 3d | 0 | 0 | 0 | 19392.5605 | 0% | Not Started | 0 | 19392.5605 | 100 |  | 0 | 100 |  | 0
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 4d | [5 empty] | 30946.0199 |  | 1.223% |  | 2167.5599 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 | 2005-02-07 08:00 | 3d | 1511.83 | 0 | 0 | 13961.1797 | 0 | 15473.0096 | 0 | 100% | Finished | 1511.83 | 1511.83 | 100 | 100 | 100 | 100 | 1023.4623 | 100
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 | 2005-02-08 08:00 | 3d | 655.73 | 0 | 0 | 14817.2803 | 0 | 15473.0103 | 0 | 100% | Finished | 655.73 | 655.73 | 100 | 100 | 100 | 100 | 2359.6619 | 100
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP29
| TP Status Date | 2005-02-18 17:00 |  | TP Name | 18/02, 2005
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 765d | [5 empty] | 10048717.6545 |  | 95.71% |  | 10931882.1414 | 11186199.6924
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 141119.7031 | 0 | 153252.8232 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1263.0949 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 141119.7031 | 0 | 153252.8232 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1263.0949 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 141119.7031 | 0 | 153252.8232 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1263.0949 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 141119.7031 | 0 | 153252.8232 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1263.0949 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 141119.7031 | 0 | 153252.8232 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1263.0949 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 141119.7031 | 0 | 153252.8232 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1263.0949 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -414341.8438 | 0 | 72050.25 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 14.8132 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | 21021.3809 | 0 | 102046.8887 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 125.9442 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 217d | [5 empty] | 4636016.0164 |  | 98.47% |  | 4888243.9935 | 4964207.224
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 1128299.1569 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 82217.0391 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -75305.5391 | 0 | 82217.0391 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 52.1938 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 169159.7734 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 37560.8398 | 0 | 49957.6895 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 402.987 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -369103.7188 | 0 | 80346.0938 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 17.8765 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 29213.9902 | 0 | 38855.9902 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 402.9868 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 200027.4977 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 36501.4805 | 0 | 48207.6406 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 411.8143 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | -5810.04 | 0 | 32138.4287 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 84.6897 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 40605.8594 | 0 | 98158.9297 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 170.5538 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -18905.9805 | 0 | 16069.2188 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 45.9446 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 4207.3799 | 0 | 5453.2799 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 437.698 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 676894.8467 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 22925.4805 | 0 | 32719.6504 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 334.0727 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 152412.3438 | 0 | 185587.1953 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 559.4213 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | -2697.96 | 0 | 273176.665 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 99.022 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 152236.4844 | 0 | 185411.3359 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 558.8912 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 324911.4718 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 16443.4092 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -15061.1104 | 0 | 16443.4092 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 52.1938 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 35205.5408 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 4173.4302 | 0 | 5550.8602 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 402.9867 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -110731.1172 | 0 | 24103.8203 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 17.8765 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 4173.4302 | 0 | 5550.8602 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 402.9867 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 72892.6891 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 12167.1602 | 0 | 16069.2102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 411.8146 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | -1452.51 | 0 | 8034.6101 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 84.6897 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 11279.4102 | 0 | 27266.3701 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 170.5538 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -18905.9805 | 0 | 16069.2188 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 45.9446 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 4207.3799 | 0 | 5453.2799 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 437.698 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 200369.8328 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 7641.8301 | 0 | 10906.55 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 334.0731 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 44827.1602 | 0 | 54584.4697 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 559.4213 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | -793.52 | 0 | 80346.0737 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 99.022 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 44775.4297 | 0 | 54532.7393 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 558.8911 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 324911.4718 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 16443.4092 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -15061.1104 | 0 | 16443.4092 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 52.1938 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 35205.5408 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 4173.4302 | 0 | 5550.8602 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 402.9867 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -110731.1172 | 0 | 24103.8203 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 17.8765 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 4173.4302 | 0 | 5550.8602 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 402.9867 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 72892.6891 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 12167.1602 | 0 | 16069.2102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 411.8146 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | -1452.51 | 0 | 8034.6101 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 84.6897 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 11279.4102 | 0 | 27266.3701 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 170.5538 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -18905.9805 | 0 | 16069.2188 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 45.9446 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 4207.3799 | 0 | 5453.2799 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 437.698 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 200369.8328 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 7641.8301 | 0 | 10906.55 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 334.0731 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 44827.1602 | 0 | 54584.4697 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 559.4213 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | -793.52 | 0 | 80346.0737 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 99.022 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 44775.4297 | 0 | 54532.7393 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 558.8911 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 346517.5618 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 32886.8203 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -30122.2109 | 0 | 32886.8203 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 52.1938 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 59309.3611 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 4173.4302 | 0 | 5550.8602 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 402.9867 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -221462.2344 | 0 | 48207.6406 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 17.8765 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 4173.4302 | 0 | 5550.8602 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 402.9867 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 124262.879 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 18250.7402 | 0 | 24103.8203 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 411.8143 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | -4357.5298 | 0 | 24103.8198 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 84.6897 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 22558.8105 | 0 | 54532.7402 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 170.5538 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -18905.9805 | 0 | 16069.2188 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 45.9446 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 4207.3799 | 0 | 5453.2799 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 437.698 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 130058.5013 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 11462.7402 | 0 | 16359.8301 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 334.0725 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 44827.1602 | 0 | 54584.4697 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 559.4213 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | -476.11 | 0 | 48207.6517 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 99.022 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 8955.0898 | 0 | 10906.5498 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 558.8918 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 453374.162 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 32886.8203 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -30122.2109 | 0 | 32886.8203 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 52.1938 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 92614.4812 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 8346.8496 | 0 | 11101.7097 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 402.9863 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -221462.2344 | 0 | 48207.6406 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 17.8765 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 25040.5605 | 0 | 33305.1309 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 402.9868 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 110484.3904 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 18250.7402 | 0 | 24103.8203 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 411.8143 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | -2905.02 | 0 | 16069.2202 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 84.6897 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 11279.4102 | 0 | 27266.3701 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 170.5538 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -37811.9609 | 0 | 32138.4297 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 45.9446 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 8414.75 | 0 | 10906.55 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 437.6976 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 217388.4701 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 15283.6504 | 0 | 21813.1006 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 334.0725 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 112067.8984 | 0 | 136461.168 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 559.4214 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | -476.11 | 0 | 48207.6517 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 99.022 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 8955.0898 | 0 | 10906.5498 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 558.8918 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 303458.6966 |  | 100% |  | 405866.8156 | 405866.8156
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 10962.2695 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -10040.7402 | 0 | 10962.2695 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 52.1938 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 56825.6168 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 4173.4302 | 0 | 5550.8602 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 402.9867 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -184551.8594 | 0 | 40173.0469 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 17.8765 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 8346.8496 | 0 | 11101.7097 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 402.9863 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 116228.27 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 12167.1602 | 0 | 16069.2102 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 411.8146 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | -2905.02 | 0 | 16069.2202 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 84.6897 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 18047.0508 | 0 | 43626.1914 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 170.5538 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -28358.9707 | 0 | 24103.8184 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 45.9446 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 12622.1299 | 0 | 16359.8298 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 437.6978 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 119442.5402 |  | 100% |  | 51350.6895 | 51350.6895
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 19104.5605 | 0 | 27266.3706 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 334.0726 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 44827.1602 | 0 | 54584.4697 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 559.4213 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | -317.41 | 0 | 32138.4298 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 99.022 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 4477.54 | 0 | 5453.27 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 558.8913 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 152875.028 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 5531.5596 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -4969.9502 | 0 | 5531.5596 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 52.6739 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 35360.03 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 4223.8398 | 0 | 5601.2699 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 406.6464 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -110579.8672 | 0 | 24255.0703 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 17.9887 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 4126.2598 | 0 | 5503.6898 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 399.5622 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 87376.999 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 23062.9805 | 0 | 55036.9102 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 172.1306 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | -5608.3799 | 0 | 32340.0889 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 85.2211 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 24606.4394 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 9066.2695 | 0 | 11017.7295 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 564.5891 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | -28.94 | 0 | 8085.02 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 99.6433 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 4527.96 | 0 | 5503.6899 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 564.0587 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 251515.8631 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 10962.2695 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -10040.7402 | 0 | 10962.2695 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 52.1938 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 78734.1619 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 4173.4302 | 0 | 5550.8602 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 402.9867 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 28673.0508 | 0 | 43626.2012 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 291.7526 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -110731.1172 | 0 | 24103.8203 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 17.8765 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 4075.8501 | 0 | 5453.2802 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 395.9025 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 137414.6621 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | -2905.02 | 0 | 16069.2202 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 84.6897 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | -5814.77 | 0 | 16069.2202 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 73.4291 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 13535.29 | 0 | 32719.6494 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 170.5538 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | 22520.9707 | 0 | 72556.5723 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 145.0099 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 24404.7696 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 8965.4297 | 0 | 10916.8896 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 559.4217 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | -79.35 | 0 | 8034.61 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 99.0221 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 4477.54 | 0 | 5453.27 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 558.8913 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 120d | [5 empty] | 1350152.6045 |  | 93.62% |  | 1115231.9326 | 1191195.1631
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 120d | [5 empty] | 886136.3926 |  | 94.16% |  | 399011.6348 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 20d | 375310.0312 | 0 | 763458.4062 | 0 | 87.5% | Started | 388148.375 | 388148.375 | 100 | 100 | 87.5 | 100 | 196.6924 | 87.5
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 | 2005-01-31 08:00 | 15d | 10863.2598 | 0 | 0 | 111814.7266 | 0 | 122677.9863 | 0 | 100% | Finished | 10863.2598 | 10863.2598 | 100 | 75 | 100 | 100 | 1129.2926 | 100
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 |  | 0 | 0 | 24728.3594 | 10d | 0 | 0 | 0 | 24728.3594 | 0% | Not Started | 0 | 24728.3594 | 100 |  | 0 | 100 |  | 0
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 23d | [5 empty] | 191352.4932 |  | 83.95% |  | 267955.1729 | 319190.0439
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 | 2005-01-19 08:00 | 13d | 175400.3438 | 0 | 0 | -147646.0781 | 0 | 27754.2656 | 0 | 100% | Finished | 175400.3438 | 175400.3438 | 100 | 260 | 100 | 100 | 15.8234 | 100
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 |  | 0 | 0 | 19108.3203 | 4d | 0 | 0 | 0 | 19108.3203 | 0% | Not Started | 0 | 19108.3203 | 100 |  | 0 | 100 |  | 0
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 | 2005-02-14 08:00 | 20d | 88628.0391 | 0 | 15d | 20437.4492 | 0 | 109065.4883 | 0 | 57.14% | Started | 88628.0391 | 88628.0391 | 100 | 100 | 57.1429 | 100 | 123.0598 | 57.1429
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 | 2005-02-07 08:00 | 10d | 3926.79 | 0 | 0 | 50605.9492 | 0 | 54532.7393 | 0 | 100% | Finished | 3926.79 | 3926.79 | 100 | 100 | 100 | 100 | 1388.7358 | 100
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 |  | 0 | 0 | 32126.5508 | 10d | 0 | 0 | 0 | 32126.5508 | 0% | Not Started | 0 | 32126.5508 | 100 |  | 0 | 100 |  | 0
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 2005-01-10 08:00 | 50d | 448265.125 | 0 | 20d | -175601.4062 | 0 | 272663.7188 | 0 | 71.43% | Started | 448265.125 | 448265.125 | 100 | 100 | 71.4286 | 100 | 60.8264 | 71.4286
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 229d | [5 empty] | 4319087.5599 |  | 92.88% |  | 5403421.8256 | 5581776.1461
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 253452.4439 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 53074.4915 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | -2009.27 | 0 | 27266.3706 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 93.1367 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | -1922.01 | 0 | 25808.1208 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 93.0689 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 21813.0896 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 9528.5898 | 0 | 10906.5398 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 791.5048 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | -4739.3301 | 0 | 10906.5498 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 69.7088 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 33531.0811 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 21165.5508 | 0 | 33531.0811 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 271.1657 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 145033.7818 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | -6705.48 | 0 | 55783.8794 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 89.2694 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -11400.7402 | 0 | 12904.0605 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 53.0926 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 32261.7207 | 0 | 32719.6407 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 7145.2742 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | -11256.5996 | 0 | 43626.2012 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 79.4898 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 326715.6849 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 70433.0711 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -5044.5801 | 0 | 12904.0605 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 71.8944 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 16155.6699 | 0 | 16359.8199 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 8013.6274 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -10267.79 | 0 | 19356.0908 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 65.3395 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 16155.6699 | 0 | 16359.8199 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 8013.6274 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | -393.58 | 0 | 5453.2799 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 93.2685 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 10906.5399 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | 87.23 | 0 | 5453.27 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 101.6256 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 3649.9099 | 0 | 5453.2699 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 302.395 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 245376.0739 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | -4562.0898 | 0 | 19356.0898 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 80.9263 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | -3664.47 | 0 | 12904.0593 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 77.8829 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | -1148.09 | 0 | 6452.0302 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 84.8938 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -14165.21 | 0 | 32260.1494 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 69.4882 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -9877.9697 | 0 | 32260.1514 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 76.5581 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -147259.7188 | 0 | 142143.5938 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 49.1161 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 25808.1194 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 25808.1194 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -6254.4399 | 0 | 12904.0601 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 67.3542 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | -3873.8899 | 0 | 12904.0593 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 76.9108 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 627009.1836 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 238897.7295 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | 484.02 | 0 | 21813.0903 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 102.2693 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -18510.5098 | 0 | 45164.209 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 70.9296 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -16778.9102 | 0 | 45164.2188 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 72.9124 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | -6260.54 | 0 | 32260.1514 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 83.7476 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | -8313.5898 | 0 | 38712.1797 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 82.3212 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | 2862.8101 | 0 | 55783.8804 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 105.4096 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 109065.4805 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 69781.9688 | 0 | 109065.4805 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 277.6368 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 51616.2393 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -15093.1299 | 0 | 25808.1201 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 63.0986 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -15655.9004 | 0 | 25808.1191 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 62.2422 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 227429.7344 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -234123.3594 | 0 | 227429.7344 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 49.2749 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 382130.1368 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 115988.2706 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 44643.7812 | 0 | 45095.7213 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 9978.254 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 5003.02 | 0 | 5453.27 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 1211.1649 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | -8526.8604 | 0 | 32719.6396 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 79.3271 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | -8526.8604 | 0 | 32719.6396 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 79.3271 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 38712.1787 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | -5241.7798 | 0 | 19356.0894 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 78.6901 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | -3511.27 | 0 | 19356.0894 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 84.6451 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 227429.6875 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -667536.25 | 0 | 227429.6875 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 25.4121 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 44d | [5 empty] | 255906.9199 |  | 100% |  | 778542.7812 | 778542.7812
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 27266.3687 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | -6653.7798 | 0 | 27266.3687 | 0 | 100% | Finished | 33920.1484 | 33920.1484 | 100 | 100 | 100 | 100 | 80.384 | 100
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 9d | [5 empty] | 58068.27 |  | 100% |  | 76109.8203 | 76109.8203
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -13830.2402 | 0 | 32260.1504 | 0 | 100% | Finished | 46090.3906 | 46090.3906 | 100 | 100 | 100 | 100 | 69.9932 | 100
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 0 | -4211.3101 | 0 | 25808.1196 | 0 | 100% | Finished | 30019.4297 | 30019.4297 | 100 | 100 | 100 | 100 | 85.9714 | 100
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 30d | [5 empty] | 170572.2812 |  | 100% |  | 668512.8125 | 668512.8125
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 2005-01-10 08:00 | 31d | 668512.8125 | 0 | 1d | -497940.5312 | 0 | 170572.2812 | 0 | 96.88% | Started | 668512.8125 | 668512.8125 | 100 | 103.3333 | 96.875 | 100 | 25.5152 | 96.875
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 101d | [5 empty] | 748782.2637 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 273689.1875 | 0 | 305353.748 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 964.3391 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 74d | 174759.7031 | 0 | 20d | 268668.8125 | 0 | 443428.5156 | 0 | 78.72% | Started | 174759.7031 | 174759.7031 | 100 | 113.8462 | 78.7234 | 100 | 253.7361 | 78.7234
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 |  | 0 | 0 | 235690.6719 | 15d | 0 | 0 | 0 | 235690.6719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 25d | [5 empty] | 239944.0693 |  | 100% |  | 24833.4189 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 | 2005-01-17 08:00 | 4d | 4644.7798 | 0 | 0 | 38981.4219 | 0 | 43626.2017 | 0 | 100% | Finished | 4644.7798 | 4644.7798 | 100 | 50 | 100 | 100 | 939.2523 | 100
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 | 2005-01-31 08:00 | 6d | 3364.77 | 0 | 0 | 29354.8691 | 0 | 32719.6392 | 0 | 100% | Finished | 3364.77 | 3364.77 | 100 | 100 | 100 | 100 | 972.4183 | 100
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 | 2005-02-08 08:00 | 9d | 16823.8691 | 0 | 5d 5h | 146774.3594 | 0 | 163598.2285 | 0 | 61.54% | Started | 16823.8691 | 16823.8691 | 100 | 30 | 61.5385 | 100 | 972.4174 | 61.5385
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 66d | [5 empty] | 954919.7488 |  | 100% |  | 1048283.1511 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 80667.3906 | 0 | 92705.6602 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 770.0912 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 73262.0625 | 0 | 76345.8425 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 2475.7227 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -25648.75 | 0 | 5453.2695 | 0 | 100% | Finished | 31102.0195 | 31102.0195 | 100 | 2000 | 100 | 100 | 17.5335 | 100
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -50207.0781 | 0 | 81799.125 | 0 | 100% | Finished | 132006.2031 | 132006.2031 | 100 | 166.6667 | 100 | 100 | 61.9661 | 100
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 80d | 413377.0625 | 0 | 18d | -31647.8496 | 0 | 381729.2129 | 0 | 81.63% | Started | 413377.0625 | 413377.0625 | 100 | 114.2857 | 81.6327 | 100 | 92.3441 | 81.6327
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 2005-01-10 08:00 | 45d | 440020.6562 | 0 | 15d | -167356.9375 | 0 | 272663.7188 | 0 | 75% | Started | 440020.6562 | 440020.6562 | 100 | 90 | 75 | 100 | 61.9661 | 75
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 | 2005-02-04 08:00 | 7d | 16655.1602 | 0 | 0 | 27567.7598 | 0 | 44222.9199 | 0 | 100% | Finished | 16655.1602 | 16655.1602 | 100 | 100 | 100 | 100 | 265.5208 | 100
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 29d | [5 empty] | 327196.4766 |  | 100% |  | 595707.5625 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 2005-01-11 08:00 | 35d | 322152.7812 | 0 | 6d | -158554.5469 | 0 | 163598.2344 | 0 | 85.37% | Started | 322152.7812 | 322152.7812 | 100 | 116.6667 | 85.3659 | 100 | 50.7828 | 85.3659
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 | 2005-02-10 08:00 | 27d | 273554.7812 | 0 | 20d | -109956.5391 | 0 | 163598.2422 | 0 | 57.45% | Started | 273554.7812 | 273554.7812 | 100 | 90 | 57.4468 | 100 | 59.8046 | 57.4468
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 30d | [5 empty] | 144502.8731 |  | 96.81% |  | 101503.2427 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 2005-01-10 08:00 | 5d | 3592.98 | 0 | 0 | 23673.3906 | 0 | 27266.3706 | 0 | 100% | Finished | 3592.98 | 3592.98 | 100 | 100 | 100 | 100 | 758.879 | 100
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 | 2005-01-24 08:00 | 15d | 78335.2422 | 0 | 0 | 11067.1299 | 0 | 89402.3721 | 0 | 100% | Finished | 78335.2422 | 78335.2422 | 100 | 100 | 100 | 100 | 114.1279 | 100
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 | 2005-02-14 08:00 | 3d | 182.46 | 0 | 0 | 10724.0898 | 0 | 10906.5499 | 0 | 100% | Finished | 182.46 | 182.46 | 100 | 150 | 100 | 100 | 5977.5016 | 100
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 | 2005-02-17 08:00 | 2d | 19392.5605 | 0 | 0 | -2464.98 | 0 | 16927.5806 | 0 | 100% | Finished | 19392.5605 | 19392.5605 | 100 | 66.6667 | 100 | 100 | 87.289 | 100
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 |  | 0 | 0 | 3347.97 | 5d | 0 | 0 | 0 | 3347.97 | 0% | Not Started | 0 | 3347.97 | 100 |  | 0 | 100 |  | 0
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 10d | [5 empty] | 32719.64 |  | 1.223% |  | 2167.5599 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 | 2005-02-07 08:00 | 3d | 1511.83 | 0 | 0 | 14847.9902 | 0 | 16359.8202 | 0 | 100% | Finished | 1511.83 | 1511.83 | 100 | 100 | 100 | 100 | 1082.1204 | 100
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 | 2005-02-08 08:00 | 4d | 655.73 | 0 | 0 | 15704.0898 | 0 | 16359.8198 | 0 | 100% | Finished | 655.73 | 655.73 | 100 | 133.3333 | 100 | 100 | 2494.9019 | 100
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 |  | 0 | 0 | 14023.8896 | 15d | 0 | 0 | 0 | 14023.8896 | 0% | Not Started | 0 | 14023.8896 | 100 |  | 0 | 100 |  | 0
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 |  | 0 | 0 | 99261.0312 | 10d | 0 | 0 | 0 | 99261.0312 | 0% | Not Started | 0 | 99261.0312 | 100 |  | 0 | 100 |  | 0
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 |  | 0 | 0 | 61721.4297 | 10d | 0 | 0 | 0 | 61721.4297 | 0% | Not Started | 0 | 61721.4297 | 100 |  | 0 | 100 |  | 0

## TP30
| TP Status Date | 2005-03-31 17:00 |  | TP Name | 31/03, 2005
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Town Square | 2002-01-25 08:00 | 2005-03-21 17:00 | 786d |  |  | 11421890.3643 |  |  | 11421890.3643 |  | 785d | [5 empty] | 15218926.3789 |  | 100% |  | 11421890.3643 | 11421890.3643
1 | Gemeenteraadsbeslissing 1 | 2002-01-25 08:00 | 2002-01-25 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-01-25 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1289.7083 | 100
2 | Collegebeslissing 1 | 2002-06-03 08:00 | 2002-06-03 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2002-06-03 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1289.7083 | 100
3 | Collegebeslissing 2 | 2003-05-26 08:00 | 2003-05-26 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-05-26 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1289.7083 | 100
4 | Gemeenteraadsbeslissing 2 | 2003-08-29 08:00 | 2003-08-29 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-08-29 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1289.7083 | 100
5 | Collegebeslissing 3 | 2003-12-08 08:00 | 2003-12-08 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2003-12-08 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1289.7083 | 100
6 | Gemeenteraadsbeslissing 3 | 2004-01-30 08:00 | 2004-01-30 17:00 | 1d |  | 0 | 12133.1201 | 0 | 0 | 12133.1201 | 2004-01-30 08:00 | 1d | 12133.1201 | 0 | 0 | 144348.7344 | 0 | 156481.8545 | 0 | 100% | Finished | 12133.1201 | 12133.1201 | 100 | 100 | 100 | 100 | 1289.7083 | 100
7 | Begin werken | 2004-02-16 17:00 | 2004-02-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-02-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Werfinrichting | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 486392.0938 | 0 | 0 | 486392.0938 | 2004-02-16 08:00 | 5d | 486392.0938 | 0 | 0 | -397916.9375 | 0 | 88475.1562 | 0 | 100% | Finished | 486392.0938 | 486392.0938 | 100 | 100 | 100 | 100 | 18.1901 | 100
9 | Bemaling | 2004-02-16 08:00 | 2004-03-04 17:00 | 14d |  | 0 | 81025.5078 | 0 | 0 | 81025.5078 | 2004-02-16 08:00 | 14d | 81025.5078 | 0 | 0 | 62388.1914 | 0 | 143413.6992 | 0 | 100% | Finished | 81025.5078 | 81025.5078 | 100 | 100 | 100 | 100 | 176.9982 | 100
12 | Halfondergrondse parking | 2004-02-11 17:00 | 2005-03-04 17:00 | 241d |  |  | 4964207.224 |  |  | 4964207.224 |  | 237d | [5 empty] | 7123332.7389 |  | 100% |  | 4964207.224 | 4964207.224
11 | Constructie PK (moot 1) | 2004-02-11 17:00 | 2004-06-23 17:00 | 89d |  |  | 1124458.5367 |  |  | 1124458.5367 |  | 87d | [5 empty] | 1659909.796 |  | 100% |  | 1124458.5367 | 1124458.5367
10 | Afgifte plannen | 2004-02-11 17:00 | 2004-02-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | Grondwerk | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  |  | 157522.5781 |  |  | 157522.5781 |  | 18d | [5 empty] | 126120.6875 |  | 100% |  | 157522.5781 | 157522.5781
13 | Graafwerken | 2004-02-25 08:00 | 2004-03-16 17:00 | 15d |  | 0 | 157522.5781 | 0 | 0 | 157522.5781 | 2004-03-10 08:00 | 18d | 157522.5781 | 0 | 0 | -31401.8906 | 0 | 126120.6875 | 0 | 100% | Finished | 157522.5781 | 157522.5781 | 100 | 120 | 100 | 100 | 80.0651 | 100
16 | Vloerplaat | 2004-03-08 08:00 | 2004-03-24 17:00 | 13d |  |  | 471488.6621 |  |  | 471488.6621 |  | 21d | [5 empty] | 245983.8418 |  | 100% |  | 471488.6621 | 471488.6621
15 | Werkvloer | 2004-03-08 08:00 | 2004-03-18 17:00 | 9d |  | 0 | 12396.8496 | 0 | 0 | 12396.8496 | 2004-03-22 08:00 | 12d | 12396.8496 | 0 | 0 | 64153.7891 | 0 | 76550.6387 | 0 | 100% | Finished | 12396.8496 | 12396.8496 | 100 | 133.3333 | 100 | 100 | 617.5007 | 100
17 | Wapening vloerplaat | 2004-03-10 08:00 | 2004-03-23 17:00 | 10d |  | 0 | 449449.8125 | 0 | 0 | 449449.8125 | 2004-03-31 08:00 | 10d | 449449.8125 | 0 | 0 | -339556 | 0 | 109893.8125 | 0 | 100% | Finished | 449449.8125 | 449449.8125 | 100 | 100 | 100 | 100 | 24.4507 | 100
18 | Vloerplaat | 2004-03-16 08:00 | 2004-03-24 17:00 | 7d |  | 0 | 9642 | 0 | 0 | 9642 | 2004-04-13 08:00 | 7d | 9642 | 0 | 0 | 49897.3906 | 0 | 59539.3906 | 0 | 100% | Finished | 9642 | 9642 | 100 | 100 | 100 | 100 | 617.5004 | 100
20 | Wanden/kolommen | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  |  | 143428.7985 |  |  | 143428.7985 |  | 17d | [5 empty] | 291684.1437 |  | 100% |  | 143428.7985 | 143428.7985
19 | Kolommen | 2004-03-19 08:00 | 2004-03-26 17:00 | 6d |  | 0 | 11706.1602 | 0 | 0 | 11706.1602 | 2004-04-14 08:00 | 15d | 11706.1602 | 0 | 0 | 54230.1094 | 0 | 65936.2695 | 0 | 100% | Finished | 11706.1602 | 11706.1602 | 100 | 250 | 100 | 100 | 563.2613 | 100
21 | Wapening wanden | 2004-03-18 08:00 | 2004-03-23 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-04-15 08:00 | 4d | 37948.4688 | 0 | 0 | 6009.0498 | 0 | 43957.5186 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 115.8348 | 100
22 | Wanden | 2004-03-17 08:00 | 2004-04-13 17:00 | 18d |  | 0 | 57553.0703 | 0 | 0 | 57553.0703 | 2004-04-26 08:00 | 5d | 57553.0703 | 0 | 0 | 93850.4766 | 0 | 151403.5469 | 0 | 100% | Finished | 57553.0703 | 57553.0703 | 100 | 27.7778 | 100 | 100 | 263.0677 | 100
23 | Wapening talud | 2004-03-24 08:00 | 2004-03-25 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-04-29 08:00 | 5d | 34975.1992 | 0 | 0 | -12996.4404 | 0 | 21978.7588 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 250 | 100 | 100 | 62.841 | 100
24 | Betontalud | 2004-03-26 08:00 | 2004-03-26 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-07 08:00 | 1d | 1245.9 | 0 | 0 | 7162.1499 | 0 | 8408.0499 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 674.8575 | 100
26 | Dakplaat | 2004-03-29 08:00 | 2004-06-23 17:00 | 57d |  |  | 352018.498 |  |  | 352018.498 |  | 51d | [5 empty] | 996121.123 |  | 100% |  | 352018.498 | 352018.498
25 | Balken | 2004-03-29 08:00 | 2004-04-05 17:00 | 6d |  | 0 | 9794.1699 | 0 | 0 | 9794.1699 | 2004-04-26 08:00 | 6d | 9794.1699 | 0 | 0 | 40654.1094 | 0 | 50448.2793 | 0 | 100% | Finished | 9794.1699 | 9794.1699 | 100 | 100 | 100 | 100 | 515.0848 | 100
27 | Dakplaat | 2004-04-08 08:00 | 2004-06-02 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-07 08:00 | 25d | 33174.8516 | 0 | 0 | 252985.5156 | 0 | 286160.3672 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 73.5294 | 100 | 100 | 862.5822 | 100
28 | Wapening dakplaat | 2004-04-26 08:00 | 2004-06-16 17:00 | 34d |  | 0 | 275874.625 | 0 | 0 | 275874.625 | 2004-06-14 08:00 | 17d | 275874.625 | 0 | 0 | 97764.2812 | 0 | 373638.9062 | 0 | 100% | Finished | 275874.625 | 275874.625 | 100 | 50 | 100 | 100 | 135.4379 | 100
29 | Beton dakplaat | 2004-05-04 08:00 | 2004-06-23 17:00 | 34d |  | 0 | 33174.8516 | 0 | 0 | 33174.8516 | 2004-06-21 08:00 | 13d | 33174.8516 | 0 | 0 | 252698.7188 | 0 | 285873.5703 | 0 | 100% | Finished | 33174.8516 | 33174.8516 | 100 | 38.2353 | 100 | 100 | 861.7177 | 100
31 | Constructie PK (moot 2) | 2004-02-27 17:00 | 2004-06-28 17:00 | 80d |  |  | 338610.4794 |  |  | 338610.4794 |  | 90d | [5 empty] | 475570.1774 |  | 100% |  | 338610.4794 | 338610.4794
30 | Afgifte plannen | 2004-02-27 17:00 | 2004-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | Grondwerk | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 25224.1396 |  | 100% |  | 31504.5195 | 31504.5195
32 | Graafwerken | 2004-03-17 08:00 | 2004-03-19 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-05 08:00 | 3d | 31504.5195 | 0 | 0 | -6280.3799 | 0 | 25224.1396 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 80.0651 | 100
35 | Vloerplaat | 2004-03-22 08:00 | 2004-03-31 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 49979.4011 |  | 100% |  | 137589.7976 | 137589.7976
34 | Werkvloer | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-19 08:00 | 2d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 617.5 | 100
36 | Wapening vloerplaat | 2004-03-26 08:00 | 2004-03-30 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-23 08:00 | 3d | 134834.9375 | 0 | 0 | -101866.7969 | 0 | 32968.1406 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 24.4507 | 100
37 | Vloerplaat | 2004-03-31 08:00 | 2004-03-31 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-28 08:00 | 1d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 617.5 | 100
39 | Wanden/kolommen | 2004-04-06 08:00 | 2004-04-20 17:00 | 9d |  |  | 65597.2294 |  |  | 65597.2294 |  | 18d | [5 empty] | 105411.4781 |  | 100% |  | 65597.2294 | 65597.2294
38 | Kolommen | 2004-04-06 08:00 | 2004-04-07 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-06 08:00 | 4d | 3902.05 | 0 | 0 | 18076.6992 | 0 | 21978.7493 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 563.2616 | 100
40 | Wapening wanden | 2004-04-13 09:00 | 2004-04-14 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-04 08:00 | 1d | 9487.1201 | 0 | 0 | 1502.26 | 0 | 10989.3801 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 115.8347 | 100
41 | Wanden | 2004-04-14 08:00 | 2004-04-20 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-04 08:00 | 2d | 15986.96 | 0 | 0 | 26069.5801 | 0 | 42056.54 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 263.0678 | 100
42 | Wapening talud | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-25 08:00 | 3d | 34975.1992 | 0 | 0 | -12996.4404 | 0 | 21978.7588 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 150 | 100 | 100 | 62.841 | 100
43 | Betontalud | 2004-04-16 08:00 | 2004-04-16 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-28 08:00 | 2d | 1245.9 | 0 | 0 | 7162.1499 | 0 | 8408.0499 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 200 | 100 | 100 | 674.8575 | 100
45 | Dakplaat | 2004-04-08 08:00 | 2004-06-28 17:00 | 52d |  |  | 103918.9329 |  |  | 103918.9329 |  | 58d | [5 empty] | 294955.1584 |  | 100% |  | 103918.9329 | 103918.9329
44 | Balken | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-12 08:00 | 3d | 3264.72 | 0 | 0 | 13551.3701 | 0 | 16816.0901 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 150 | 100 | 100 | 515.0852 | 100
46 | Dakplaat | 2004-06-03 08:00 | 2004-06-16 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-02 08:00 | 6d | 9757.3096 | 0 | 0 | 74407.5078 | 0 | 84164.8174 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 862.5822 | 100
47 | Wapening dakplaat | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-09 08:00 | 10d | 81139.5938 | 0 | 0 | 28754.1992 | 0 | 109893.793 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 135.4379 | 100
48 | Beton dakplaat | 2004-06-15 08:00 | 2004-06-28 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-12 08:00 | 10d | 9757.3096 | 0 | 0 | 74323.1484 | 0 | 84080.458 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 861.7176 | 100
50 | Constructie PK (moot 3) | 2004-03-03 17:00 | 2004-08-02 17:00 | 87d |  |  | 338610.4794 |  |  | 338610.4794 |  | 101d | [5 empty] | 475570.4879 |  | 100% |  | 338610.4794 | 338610.4794
49 | Afgifte plannen | 2004-03-03 17:00 | 2004-03-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-03-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Grondwerk | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  |  | 31504.5195 |  |  | 31504.5195 |  | 3d | [5 empty] | 25224.1396 |  | 100% |  | 31504.5195 | 31504.5195
51 | Graafwerken | 2004-03-22 08:00 | 2004-03-24 17:00 | 3d |  | 0 | 31504.5195 | 0 | 0 | 31504.5195 | 2004-04-16 08:00 | 3d | 31504.5195 | 0 | 0 | -6280.3799 | 0 | 25224.1396 | 0 | 100% | Finished | 31504.5195 | 31504.5195 | 100 | 100 | 100 | 100 | 80.0651 | 100
54 | Vloerplaat | 2004-03-25 08:00 | 2004-04-05 17:00 | 8d |  |  | 137589.7976 |  |  | 137589.7976 |  | 8d | [5 empty] | 49979.4011 |  | 100% |  | 137589.7976 | 137589.7976
53 | Werkvloer | 2004-03-25 08:00 | 2004-03-25 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-04-22 08:00 | 2d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 200 | 100 | 100 | 617.5 | 100
55 | Wapening vloerplaat | 2004-03-31 08:00 | 2004-04-02 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-04-28 08:00 | 3d | 134834.9375 | 0 | 0 | -101866.7969 | 0 | 32968.1406 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 24.4507 | 100
56 | Vloerplaat | 2004-04-05 08:00 | 2004-04-05 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-05-04 08:00 | 1d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 617.5 | 100
58 | Wanden/kolommen | 2004-04-08 08:00 | 2004-04-27 17:00 | 12d |  |  | 65597.2294 |  |  | 65597.2294 |  | 7d | [5 empty] | 105411.4781 |  | 100% |  | 65597.2294 | 65597.2294
57 | Kolommen | 2004-04-08 08:00 | 2004-04-13 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-05-12 08:00 | 3d | 3902.05 | 0 | 0 | 18076.6992 | 0 | 21978.7493 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 150 | 100 | 100 | 563.2616 | 100
59 | Wapening wanden | 2004-04-20 09:00 | 2004-04-21 09:00 | 1d |  | 0 | 9487.1201 | 0 | 0 | 9487.1201 | 2004-05-06 08:00 | 1d | 9487.1201 | 0 | 0 | 1502.26 | 0 | 10989.3801 | 0 | 100% | Finished | 9487.1201 | 9487.1201 | 100 | 100 | 100 | 100 | 115.8347 | 100
60 | Wanden | 2004-04-21 08:00 | 2004-04-27 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-05-06 08:00 | 2d | 15986.96 | 0 | 0 | 26069.5801 | 0 | 42056.54 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 40 | 100 | 100 | 263.0678 | 100
61 | Wapening talud | 2004-04-21 08:00 | 2004-04-22 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-05-07 08:00 | 2d | 34975.1992 | 0 | 0 | -12996.4404 | 0 | 21978.7588 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 62.841 | 100
62 | Betontalud | 2004-04-23 08:00 | 2004-04-23 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-05-11 08:00 | 1d | 1245.9 | 0 | 0 | 7162.1499 | 0 | 8408.0499 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 674.8575 | 100
64 | Dakplaat | 2004-04-14 08:00 | 2004-08-02 17:00 | 60d |  |  | 103918.9329 |  |  | 103918.9329 |  | 69d | [5 empty] | 294955.469 |  | 100% |  | 103918.9329 | 103918.9329
63 | Balken | 2004-04-14 08:00 | 2004-04-15 17:00 | 2d |  | 0 | 3264.72 | 0 | 0 | 3264.72 | 2004-05-17 08:00 | 2d | 3264.72 | 0 | 0 | 13551.3701 | 0 | 16816.0901 | 0 | 100% | Finished | 3264.72 | 3264.72 | 100 | 100 | 100 | 100 | 515.0852 | 100
65 | Dakplaat | 2004-06-17 08:00 | 2004-06-30 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-17 08:00 | 6d | 9757.3096 | 0 | 0 | 74407.5078 | 0 | 84164.8174 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 60 | 100 | 100 | 862.5822 | 100
66 | Wapening dakplaat | 2004-06-24 08:00 | 2004-07-07 17:00 | 10d |  | 0 | 81139.5938 | 0 | 0 | 81139.5938 | 2004-08-30 08:00 | 10d | 81139.5938 | 0 | 0 | 28754.5098 | 0 | 109894.1035 | 0 | 100% | Finished | 81139.5938 | 81139.5938 | 100 | 100 | 100 | 100 | 135.4383 | 100
67 | Beton dakplaat | 2004-06-29 08:00 | 2004-08-02 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-09-02 08:00 | 10d | 9757.3096 | 0 | 0 | 74323.1484 | 0 | 84080.458 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 100 | 100 | 100 | 861.7176 | 100
69 | Constructie PK (moot 4) | 2004-04-26 17:00 | 2004-08-09 17:00 | 56d |  |  | 503232.8461 |  |  | 503232.8461 |  | 84d | [5 empty] | 505973.3207 |  | 100% |  | 503232.8461 | 503232.8461
68 | Afgifte plannen | 2004-04-26 17:00 | 2004-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Grondwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 14d | [5 empty] | 50448.2812 |  | 100% |  | 63009.0312 | 63009.0312
70 | Graafwerken | 2004-06-03 08:00 | 2004-06-10 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-06-01 08:00 | 14d | 63009.0312 | 0 | 0 | -12560.75 | 0 | 50448.2812 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 233.3333 | 100 | 100 | 80.0652 | 100
73 | Vloerplaat | 2004-06-11 08:00 | 2004-06-21 17:00 | 7d |  |  | 272424.7351 |  |  | 272424.7351 |  | 12d | [5 empty] | 82947.5417 |  | 100% |  | 272424.7351 | 272424.7351
72 | Werkvloer | 2004-06-11 08:00 | 2004-06-11 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-10 08:00 | 8d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 800 | 100 | 100 | 617.5 | 100
74 | Wapening vloerplaat | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-06-15 08:00 | 6d | 269669.875 | 0 | 0 | -203733.5938 | 0 | 65936.2812 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 24.4507 | 100
75 | Vloerplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-23 08:00 | 3d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 300 | 100 | 100 | 617.5 | 100
77 | Wanden/kolommen | 2004-06-22 08:00 | 2004-07-08 17:00 | 13d |  |  | 102509.4586 |  |  | 102509.4586 |  | 10d | [5 empty] | 180436.1686 |  | 100% |  | 102509.4586 | 102509.4586
76 | Kolommen | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-06-28 08:00 | 6d | 5853.0801 | 0 | 0 | 27115.0605 | 0 | 32968.1406 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 200 | 100 | 100 | 563.2614 | 100
78 | Wapening wanden | 2004-06-22 08:00 | 2004-06-24 17:00 | 3d |  | 0 | 28461.3496 | 0 | 0 | 28461.3496 | 2004-07-02 08:00 | 3d | 28461.3496 | 0 | 0 | 4506.7798 | 0 | 32968.1294 | 0 | 100% | Finished | 28461.3496 | 28461.3496 | 100 | 100 | 100 | 100 | 115.8347 | 100
79 | Wanden | 2004-06-25 08:00 | 2004-07-08 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-07-05 08:00 | 5d | 31973.9297 | 0 | 0 | 52139.1602 | 0 | 84113.0898 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 263.0677 | 100
80 | Wapening talud | 2004-06-25 08:00 | 2004-06-28 17:00 | 2d |  | 0 | 34975.1992 | 0 | 0 | 34975.1992 | 2004-07-01 08:00 | 2d | 34975.1992 | 0 | 0 | -12996.4404 | 0 | 21978.7588 | 0 | 100% | Finished | 34975.1992 | 34975.1992 | 100 | 100 | 100 | 100 | 62.841 | 100
81 | Betontalud | 2004-06-29 08:00 | 2004-06-29 17:00 | 1d |  | 0 | 1245.9 | 0 | 0 | 1245.9 | 2004-07-05 08:00 | 1d | 1245.9 | 0 | 0 | 7162.1499 | 0 | 8408.0499 | 0 | 100% | Finished | 1245.9 | 1245.9 | 100 | 100 | 100 | 100 | 674.8575 | 100
83 | Dakplaat | 2004-06-25 08:00 | 2004-08-09 17:00 | 17d |  |  | 65289.6211 |  |  | 65289.6211 |  | 38d | [5 empty] | 192141.3291 |  | 100% |  | 65289.6211 | 65289.6211
82 | Balken | 2004-06-25 08:00 | 2004-06-29 17:00 | 3d |  | 0 | 4897.0898 | 0 | 0 | 4897.0898 | 2004-07-06 08:00 | 3d | 4897.0898 | 0 | 0 | 20327.0508 | 0 | 25224.1406 | 0 | 100% | Finished | 4897.0898 | 4897.0898 | 100 | 100 | 100 | 100 | 515.0843 | 100
84 | Dakplaat | 2004-07-01 08:00 | 2004-08-04 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-08-25 08:00 | 15d | 9757.3096 | 0 | 0 | 74407.5078 | 0 | 84164.8174 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 150 | 100 | 100 | 862.5822 | 100
85 | Wapening dakplaat | 2004-07-08 08:00 | 2004-08-05 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-08 08:00 | 6d | 48683.7617 | 0 | 0 | 17252.5195 | 0 | 65936.2812 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 100 | 100 | 100 | 135.4379 | 100
86 | Beton dakplaat | 2004-08-06 08:00 | 2004-08-09 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-16 08:00 | 2d | 1951.46 | 0 | 0 | 14864.6299 | 0 | 16816.0898 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 861.7184 | 100
88 | Constructie PK (moot 5,6) | 2004-05-25 17:00 | 2004-09-15 17:00 | 64d |  |  | 538512.749 |  |  | 538512.749 |  | 47d | [5 empty] | 669003.2437 |  | 100% |  | 538512.749 | 538512.749
87 | Afgifte plannen | 2004-05-25 17:00 | 2004-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Grondwerk | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  |  | 63009.0312 |  |  | 63009.0312 |  | 13d | [5 empty] | 50448.2812 |  | 100% |  | 63009.0312 | 63009.0312
89 | Graafwerken | 2004-06-11 08:00 | 2004-06-18 17:00 | 6d |  | 0 | 63009.0312 | 0 | 0 | 63009.0312 | 2004-08-05 08:00 | 13d | 63009.0312 | 0 | 0 | -12560.75 | 0 | 50448.2812 | 0 | 100% | Finished | 63009.0312 | 63009.0312 | 100 | 216.6667 | 100 | 100 | 80.0652 | 100
92 | Vloerplaat | 2004-06-21 08:00 | 2004-07-08 17:00 | 14d |  |  | 280689.3054 |  |  | 280689.3054 |  | 8d | [5 empty] | 133981.3035 |  | 100% |  | 280689.3054 | 280689.3054
91 | Werkvloer | 2004-06-21 08:00 | 2004-06-22 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-08-13 08:00 | 2d | 2754.8601 | 0 | 0 | 14256.4004 | 0 | 17011.2605 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 100 | 100 | 100 | 617.5 | 100
93 | Wapening vloerplaat | 2004-06-23 08:00 | 2004-06-30 17:00 | 6d |  | 0 | 269669.875 | 0 | 0 | 269669.875 | 2004-08-17 08:00 | 6d | 269669.875 | 0 | 0 | -203733.5938 | 0 | 65936.2812 | 0 | 100% | Finished | 269669.875 | 269669.875 | 100 | 100 | 100 | 100 | 24.4507 | 100
94 | Vloerplaat | 2004-07-01 08:00 | 2004-07-08 17:00 | 6d |  | 0 | 8264.5703 | 0 | 0 | 8264.5703 | 2004-08-18 08:00 | 6d | 8264.5703 | 0 | 0 | 42769.1914 | 0 | 51033.7617 | 0 | 100% | Finished | 8264.5703 | 8264.5703 | 100 | 100 | 100 | 100 | 617.5005 | 100
96 | Wanden/kolommen | 2004-07-09 08:00 | 2004-08-10 17:00 | 8d |  |  | 113256.4709 |  |  | 113256.4709 |  | 8d | [5 empty] | 157777.0623 |  | 100% |  | 113256.4709 | 113256.4709
95 | Kolommen | 2004-07-09 08:00 | 2004-08-03 17:00 | 3d |  | 0 | 5853.0801 | 0 | 0 | 5853.0801 | 2004-08-26 08:00 | 3d | 5853.0801 | 0 | 0 | 27115.0605 | 0 | 32968.1406 | 0 | 100% | Finished | 5853.0801 | 5853.0801 | 100 | 100 | 100 | 100 | 563.2614 | 100
97 | Wapening wanden | 2004-07-09 08:00 | 2004-08-02 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-08-26 08:00 | 2d | 18974.2402 | 0 | 0 | 3004.52 | 0 | 21978.7603 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 115.8347 | 100
98 | Wanden | 2004-07-09 08:00 | 2004-08-05 17:00 | 5d |  | 0 | 15986.96 | 0 | 0 | 15986.96 | 2004-08-26 08:00 | 5d | 15986.96 | 0 | 0 | 26069.5801 | 0 | 42056.54 | 0 | 100% | Finished | 15986.96 | 15986.96 | 100 | 100 | 100 | 100 | 263.0678 | 100
99 | Wapening talud | 2004-08-03 08:00 | 2004-08-06 17:00 | 4d |  | 0 | 69950.3906 | 0 | 0 | 69950.3906 | 2004-08-30 08:00 | 4d | 69950.3906 | 0 | 0 | -25992.8691 | 0 | 43957.5215 | 0 | 100% | Finished | 69950.3906 | 69950.3906 | 100 | 100 | 100 | 100 | 62.841 | 100
100 | Betontalud | 2004-08-09 08:00 | 2004-08-10 17:00 | 2d |  | 0 | 2491.8 | 0 | 0 | 2491.8 | 2004-09-03 08:00 | 2d | 2491.8 | 0 | 0 | 14324.2998 | 0 | 16816.0999 | 0 | 100% | Finished | 2491.8 | 2491.8 | 100 | 100 | 100 | 100 | 674.8575 | 100
102 | Dakplaat | 2004-08-04 08:00 | 2004-09-15 17:00 | 30d |  |  | 81557.9414 |  |  | 81557.9414 |  | 19d | [5 empty] | 326796.5967 |  | 100% |  | 81557.9414 | 81557.9414
101 | Balken | 2004-08-04 08:00 | 2004-08-09 17:00 | 4d |  | 0 | 6529.4502 | 0 | 0 | 6529.4502 | 2004-08-30 08:00 | 4d | 6529.4502 | 0 | 0 | 27102.7402 | 0 | 33632.1904 | 0 | 100% | Finished | 6529.4502 | 6529.4502 | 100 | 100 | 100 | 100 | 515.0846 | 100
103 | Dakplaat | 2004-08-05 08:00 | 2004-09-09 17:00 | 25d |  | 0 | 24393.2695 | 0 | 0 | 24393.2695 | 2004-09-15 08:00 | 7d | 24393.2695 | 0 | 0 | 186018.7656 | 0 | 210412.0352 | 0 | 100% | Finished | 24393.2695 | 24393.2695 | 100 | 28 | 100 | 100 | 862.5823 | 100
104 | Wapening dakplaat | 2004-09-06 08:00 | 2004-09-13 17:00 | 6d |  | 0 | 48683.7617 | 0 | 0 | 48683.7617 | 2004-09-20 08:00 | 3d | 48683.7617 | 0 | 0 | 17252.5195 | 0 | 65936.2812 | 0 | 100% | Finished | 48683.7617 | 48683.7617 | 100 | 50 | 100 | 100 | 135.4379 | 100
105 | Beton dakplaat | 2004-09-14 08:00 | 2004-09-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-09-23 08:00 | 1d | 1951.46 | 0 | 0 | 14864.6299 | 0 | 16816.0898 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 50 | 100 | 100 | 861.7184 | 100
126 | Constructie PK (moot 7) | 2004-09-27 17:00 | 2004-12-10 17:00 | 51d |  |  | 405866.8156 |  |  | 405866.8156 |  | 70d | [5 empty] | 445290.7521 |  | 100% |  | 405866.8156 | 405866.8156
125 | Afgifte plannen | 2004-09-27 17:00 | 2004-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Grondwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 7d | [5 empty] | 16816.0898 |  | 100% |  | 21003.0098 | 21003.0098
127 | Graafwerk | 2004-10-20 08:00 | 2004-10-21 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-10-06 08:00 | 7d | 21003.0098 | 0 | 0 | -4186.9199 | 0 | 16816.0898 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 350 | 100 | 100 | 80.0651 | 100
130 | Vloerplaat | 2004-10-22 08:00 | 2004-11-03 17:00 | 8d |  |  | 228857.1964 |  |  | 228857.1964 |  | 5d | [5 empty] | 80463.797 |  | 100% |  | 228857.1964 | 228857.1964
129 | Werkvloer | 2004-10-22 08:00 | 2004-10-22 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-14 08:00 | 1d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 617.5 | 100
131 | Wapening vloerplaat | 2004-10-25 08:00 | 2004-10-29 17:00 | 5d |  | 0 | 224724.9062 | 0 | 0 | 224724.9062 | 2004-10-15 08:00 | 3d | 224724.9062 | 0 | 0 | -169778 | 0 | 54946.9062 | 0 | 100% | Finished | 224724.9062 | 224724.9062 | 100 | 60 | 100 | 100 | 24.4507 | 100
132 | Vloerplaat | 2004-11-02 08:00 | 2004-11-03 17:00 | 2d |  | 0 | 2754.8601 | 0 | 0 | 2754.8601 | 2004-10-13 08:00 | 1d | 2754.8601 | 0 | 0 | 14256.4004 | 0 | 17011.2605 | 0 | 100% | Finished | 2754.8601 | 2754.8601 | 100 | 50 | 100 | 100 | 617.5 | 100
134 | Wanden/kolommen | 2004-11-04 08:00 | 2004-11-19 17:00 | 10d |  |  | 104655.9199 |  |  | 104655.9199 |  | 9d | [5 empty] | 169440.2466 |  | 100% |  | 104655.9199 | 104655.9199
133 | Kolommen | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 3902.05 | 0 | 0 | 3902.05 | 2004-10-14 08:00 | 4d | 3902.05 | 0 | 0 | 18076.6992 | 0 | 21978.7493 | 0 | 100% | Finished | 3902.05 | 3902.05 | 100 | 200 | 100 | 100 | 563.2616 | 100
135 | Wapening wanden | 2004-11-04 08:00 | 2004-11-05 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-14 08:00 | 2d | 18974.2402 | 0 | 0 | 3004.52 | 0 | 21978.7603 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 115.8347 | 100
136 | Wanden | 2004-11-08 08:00 | 2004-11-19 17:00 | 8d |  | 0 | 25579.1406 | 0 | 0 | 25579.1406 | 2004-10-14 08:00 | 3d | 25579.1406 | 0 | 0 | 41711.3281 | 0 | 67290.4688 | 0 | 100% | Finished | 25579.1406 | 25579.1406 | 100 | 37.5 | 100 | 100 | 263.0677 | 100
137 | Wapening talud | 2004-11-08 08:00 | 2004-11-10 17:00 | 3d |  | 0 | 52462.7891 | 0 | 0 | 52462.7891 | 2004-10-14 08:00 | 3d | 52462.7891 | 0 | 0 | -19494.6602 | 0 | 32968.1289 | 0 | 100% | Finished | 52462.7891 | 52462.7891 | 100 | 100 | 100 | 100 | 62.841 | 100
138 | Betontalud | 2004-11-15 08:00 | 2004-11-17 17:00 | 3d |  | 0 | 3737.7 | 0 | 0 | 3737.7 | 2004-10-22 08:00 | 3d | 3737.7 | 0 | 0 | 21486.4395 | 0 | 25224.1394 | 0 | 100% | Finished | 3737.7 | 3737.7 | 100 | 100 | 100 | 100 | 674.8573 | 100
140 | Dakplaat | 2004-11-08 08:00 | 2004-12-10 17:00 | 23d |  |  | 51350.6895 |  |  | 51350.6895 |  | 13d | [5 empty] | 178570.6187 |  | 100% |  | 51350.6895 | 51350.6895
139 | Balken | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 8161.8101 | 0 | 0 | 8161.8101 | 2004-10-19 08:00 | 5d | 8161.8101 | 0 | 0 | 33878.4219 | 0 | 42040.2319 | 0 | 100% | Finished | 8161.8101 | 8161.8101 | 100 | 100 | 100 | 100 | 515.0847 | 100
141 | Dakplaat | 2004-11-22 08:00 | 2004-12-03 17:00 | 10d |  | 0 | 9757.3096 | 0 | 0 | 9757.3096 | 2004-10-20 08:00 | 5d | 9757.3096 | 0 | 0 | 74407.5078 | 0 | 84164.8174 | 0 | 100% | Finished | 9757.3096 | 9757.3096 | 100 | 50 | 100 | 100 | 862.5822 | 100
142 | Dakplaat wapening | 2004-12-06 08:00 | 2004-12-09 17:00 | 4d |  | 0 | 32455.8398 | 0 | 0 | 32455.8398 | 2004-11-02 08:00 | 3d | 32455.8398 | 0 | 0 | 11501.6797 | 0 | 43957.5195 | 0 | 100% | Finished | 32455.8398 | 32455.8398 | 100 | 75 | 100 | 100 | 135.4379 | 100
143 | Dakplaat beton | 2004-12-10 08:00 | 2004-12-10 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-11-05 08:00 | 1d | 975.73 | 0 | 0 | 7432.3198 | 0 | 8408.0498 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 861.7189 | 100
145 | Constructie PK (uitrit) | 2004-05-04 17:00 | 2004-06-23 17:00 | 33d |  |  | 229054.8557 |  |  | 229054.8557 |  | 32d | [5 empty] | 223800.8491 |  | 100% |  | 229054.8557 | 229054.8557
144 | Afgifte plannen | 2004-05-04 17:00 | 2004-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-05-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | Grondwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  |  | 10501.5098 |  |  | 10501.5098 |  | 2d | [5 empty] | 8458.4697 |  | 100% |  | 10501.5098 | 10501.5098
146 | Graafwerk | 2004-06-02 08:00 | 2004-06-02 17:00 | 1d |  | 0 | 10501.5098 | 0 | 0 | 10501.5098 | 2004-06-14 08:00 | 2d | 10501.5098 | 0 | 0 | -2043.04 | 0 | 8458.4697 | 0 | 100% | Finished | 10501.5098 | 10501.5098 | 100 | 200 | 100 | 100 | 80.5453 | 100
149 | Vloerplaat | 2004-06-03 08:00 | 2004-06-09 17:00 | 5d |  |  | 137589.7976 |  |  | 137589.7976 |  | 4d | [5 empty] | 50133.9006 |  | 100% |  | 137589.7976 | 137589.7976
148 | Werkvloer | 2004-06-03 08:00 | 2004-06-03 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-16 08:00 | 1d | 1377.4301 | 0 | 0 | 7178.6201 | 0 | 8556.0502 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 621.1604 | 100
150 | Wapening vloerplaat | 2004-06-04 08:00 | 2004-06-08 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-06-17 08:00 | 2d | 134834.9375 | 0 | 0 | -101715.5469 | 0 | 33119.3906 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 66.6667 | 100 | 100 | 24.5629 | 100
151 | Beton vloerplaat | 2004-06-09 08:00 | 2004-06-09 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-06-21 08:00 | 1d | 1377.4301 | 0 | 0 | 7081.0298 | 0 | 8458.4598 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 614.0755 | 100
153 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  |  | 69922.3984 |  |  | 69922.3984 |  | 5d | [5 empty] | 128776.4287 |  | 100% |  | 69922.3984 | 69922.3984
152 | Wanden | 2004-06-10 08:00 | 2004-06-23 17:00 | 10d |  | 0 | 31973.9297 | 0 | 0 | 31973.9297 | 2004-06-22 08:00 | 5d | 31973.9297 | 0 | 0 | 52643.3203 | 0 | 84617.25 | 0 | 100% | Finished | 31973.9297 | 31973.9297 | 100 | 50 | 100 | 100 | 264.6445 | 100
154 | Wapening wanden | 2004-06-10 08:00 | 2004-06-15 17:00 | 4d |  | 0 | 37948.4688 | 0 | 0 | 37948.4688 | 2004-06-22 08:00 | 4d | 37948.4688 | 0 | 0 | 6210.71 | 0 | 44159.1787 | 0 | 100% | Finished | 37948.4688 | 37948.4688 | 100 | 100 | 100 | 100 | 116.3662 | 100
156 | Dakplaat | 2004-06-17 08:00 | 2004-06-22 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 36432.05 |  | 100% |  | 11041.1499 | 11041.1499
155 | Dakplaat | 2004-06-17 08:00 | 2004-06-18 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-06-29 08:00 | 2d | 1951.46 | 0 | 0 | 14982.3301 | 0 | 16933.79 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 867.7498 | 100
157 | Wapening dakplaat | 2004-06-21 08:00 | 2004-06-21 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-07-01 08:00 | 1d | 8113.96 | 0 | 0 | 2925.8401 | 0 | 11039.8 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 136.0593 | 100
158 | Beton dakplaat | 2004-06-22 08:00 | 2004-06-22 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-07-02 08:00 | 1d | 975.73 | 0 | 0 | 7482.73 | 0 | 8458.46 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 866.8853 | 100
160 | Constructie PK (inrit) | 2004-09-08 17:00 | 2004-10-19 17:00 | 29d |  |  | 294665.2991 |  |  | 294665.2991 |  | 50d | [5 empty] | 366935.3523 |  | 100% |  | 294665.2991 | 294665.2991
159 | Afgifte plannen | 2004-09-08 17:00 | 2004-09-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-08-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
162 | Grondwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  |  | 21003.0098 |  |  | 21003.0098 |  | 2d | [5 empty] | 16816.0898 |  | 100% |  | 21003.0098 | 21003.0098
161 | Graafwerk | 2004-09-09 08:00 | 2004-09-10 17:00 | 2d |  | 0 | 21003.0098 | 0 | 0 | 21003.0098 | 2004-09-16 08:00 | 2d | 21003.0098 | 0 | 0 | -4186.9199 | 0 | 16816.0898 | 0 | 100% | Finished | 21003.0098 | 21003.0098 | 100 | 100 | 100 | 100 | 80.0651 | 100
164 | Vloerplaat | 2004-09-13 08:00 | 2004-10-04 17:00 | 16d |  |  | 152542.948 |  |  | 152542.948 |  | 16d | [5 empty] | 117146.1902 |  | 100% |  | 152542.948 | 152542.948
163 | Werkvloer | 2004-09-13 08:00 | 2004-09-13 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-09-20 08:00 | 1d | 1377.4301 | 0 | 0 | 7128.2002 | 0 | 8505.6302 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 617.5 | 100
165 | Tech. kelder | 2004-09-14 08:00 | 2004-09-23 17:00 | 8d |  | 0 | 14953.1504 | 0 | 0 | 14953.1504 | 2004-09-21 08:00 | 8d | 14953.1504 | 0 | 0 | 52311.2188 | 0 | 67264.3691 | 0 | 100% | Finished | 14953.1504 | 14953.1504 | 100 | 100 | 100 | 100 | 449.8341 | 100
166 | Wapening vloerplaat | 2004-09-29 08:00 | 2004-10-01 17:00 | 3d |  | 0 | 134834.9375 | 0 | 0 | 134834.9375 | 2004-10-06 08:00 | 3d | 134834.9375 | 0 | 0 | -101866.7969 | 0 | 32968.1406 | 0 | 100% | Finished | 134834.9375 | 134834.9375 | 100 | 100 | 100 | 100 | 24.4507 | 100
167 | Beton vloerplaat | 2004-10-04 08:00 | 2004-10-04 17:00 | 1d |  | 0 | 1377.4301 | 0 | 0 | 1377.4301 | 2004-10-11 08:00 | 1d | 1377.4301 | 0 | 0 | 7030.6201 | 0 | 8408.0502 | 0 | 100% | Finished | 1377.4301 | 1377.4301 | 100 | 100 | 100 | 100 | 610.4158 | 100
169 | Wanden | 2004-10-05 08:00 | 2004-10-19 17:00 | 11d |  |  | 110078.1914 |  |  | 110078.1914 |  | 15d | [5 empty] | 196742.6826 |  | 100% |  | 110078.1914 | 110078.1914
168 | Wapening wanden | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 18974.2402 | 0 | 0 | 18974.2402 | 2004-10-12 08:00 | 2d | 18974.2402 | 0 | 0 | 3004.52 | 0 | 21978.7603 | 0 | 100% | Finished | 18974.2402 | 18974.2402 | 100 | 100 | 100 | 100 | 115.8347 | 100
170 | Wapening waterpartij | 2004-10-05 08:00 | 2004-10-06 17:00 | 2d |  | 0 | 21883.9902 | 0 | 0 | 21883.9902 | 2004-10-12 08:00 | 2d | 21883.9902 | 0 | 0 | 94.77 | 0 | 21978.7602 | 0 | 100% | Finished | 21883.9902 | 21883.9902 | 100 | 100 | 100 | 100 | 100.4331 | 100
171 | Wanden | 2004-10-06 08:00 | 2004-10-13 17:00 | 6d |  | 0 | 19184.3594 | 0 | 0 | 19184.3594 | 2004-10-13 08:00 | 6d | 19184.3594 | 0 | 0 | 31283.4902 | 0 | 50467.8496 | 0 | 100% | Finished | 19184.3594 | 19184.3594 | 100 | 100 | 100 | 100 | 263.0677 | 100
172 | Waterpartij | 2004-10-06 08:00 | 2004-10-19 17:00 | 10d |  | 0 | 50035.6016 | 0 | 0 | 50035.6016 | 2004-10-13 08:00 | 14d | 50035.6016 | 0 | 0 | 52281.7109 | 0 | 102317.3125 | 0 | 100% | Finished | 50035.6016 | 50035.6016 | 100 | 140 | 100 | 100 | 204.489 | 100
174 | Dakplaat | 2004-10-14 08:00 | 2004-10-19 17:00 | 4d |  |  | 11041.1499 |  |  | 11041.1499 |  | 4d | [5 empty] | 36230.3896 |  | 100% |  | 11041.1499 | 11041.1499
173 | Dakplaat | 2004-10-14 08:00 | 2004-10-15 17:00 | 2d |  | 0 | 1951.46 | 0 | 0 | 1951.46 | 2004-10-21 08:00 | 2d | 1951.46 | 0 | 0 | 14881.5 | 0 | 16832.96 | 0 | 100% | Finished | 1951.46 | 1951.46 | 100 | 100 | 100 | 100 | 862.5829 | 100
175 | Wapening dakplaat | 2004-10-18 08:00 | 2004-10-18 17:00 | 1d |  | 0 | 8113.96 | 0 | 0 | 8113.96 | 2004-10-25 08:00 | 1d | 8113.96 | 0 | 0 | 2875.4199 | 0 | 10989.3799 | 0 | 100% | Finished | 8113.96 | 8113.96 | 100 | 100 | 100 | 100 | 135.4379 | 100
176 | Beton dakplaat | 2004-10-19 08:00 | 2004-10-19 17:00 | 1d |  | 0 | 975.73 | 0 | 0 | 975.73 | 2004-10-26 08:00 | 1d | 975.73 | 0 | 0 | 7432.3198 | 0 | 8408.0498 | 0 | 100% | Finished | 975.73 | 975.73 | 100 | 100 | 100 | 100 | 861.7189 | 100
282 | Afwerking parking - technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 1191195.1631 |  |  | 1191195.1631 |  | 140d | [5 empty] | 2301278.7598 |  | 100% |  | 1191195.1631 | 1191195.1631
281 | Technieken | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  |  | 423739.9941 |  |  | 423739.9941 |  | 140d | [5 empty] | 1461643.2598 |  | 100% |  | 423739.9941 | 423739.9941
280 | Elektriciteit en parkeerbeheersysteem | 2004-08-02 08:00 | 2005-03-04 17:00 | 140d |  | 0 | 388148.375 | 0 | 0 | 388148.375 | 2004-08-17 08:00 | 140d | 388148.375 | 0 | 0 | 788978.125 | 0 | 1177126.5 | 0 | 100% | Finished | 388148.375 | 388148.375 | 100 | 100 | 100 | 100 | 303.2671 | 100
283 | Sanitair | 2004-10-22 08:00 | 2004-11-23 17:00 | 20d |  | 0 | 10863.2598 | 0 | 0 | 10863.2598 | 2005-01-31 08:00 | 15d | 10863.2598 | 0 | 0 | 171336.2031 | 0 | 182199.4629 | 0 | 100% | Finished | 10863.2598 | 10863.2598 | 100 | 75 | 100 | 100 | 1677.208 | 100
284 | Waterpartij | 2004-08-02 08:00 | 2004-08-13 17:00 | 10d |  | 0 | 24728.3594 | 0 | 0 | 24728.3594 | 2005-02-28 08:00 | 10d | 24728.3594 | 0 | 0 | 77588.9375 | 0 | 102317.2969 | 0 | 100% | Finished | 24728.3594 | 24728.3594 | 100 | 100 | 100 | 100 | 413.765 | 100
286 | Afwerking | 2004-11-08 08:00 | 2005-01-12 17:00 | 35d |  |  | 319190.0439 |  |  | 319190.0439 |  | 43d | [5 empty] | 419233.1855 |  | 100% |  | 319190.0439 | 319190.0439
285 | Bedrijfsvloer | 2004-11-08 08:00 | 2004-11-16 17:00 | 5d |  | 0 | 175400.3438 | 0 | 0 | 175400.3438 | 2005-01-19 08:00 | 13d | 175400.3438 | 0 | 0 | -132872.2188 | 0 | 42528.125 | 0 | 100% | Finished | 175400.3438 | 175400.3438 | 100 | 260 | 100 | 100 | 24.2463 | 100
287 | Harsgietmortelvloer | 2004-11-17 08:00 | 2004-11-22 17:00 | 4d |  | 0 | 19108.3203 | 0 | 0 | 19108.3203 | 2005-02-28 08:00 | 4d | 19108.3203 | 0 | 0 | 14523.8604 | 0 | 33632.1807 | 0 | 100% | Finished | 19108.3203 | 19108.3203 | 100 | 100 | 100 | 100 | 176.008 | 100
288 | Schilderwerken | 2004-11-17 08:00 | 2004-12-14 17:00 | 20d |  | 0 | 88628.0391 | 0 | 0 | 88628.0391 | 2005-02-14 08:00 | 20d | 88628.0391 | 0 | 0 | 79532.8906 | 0 | 168160.9297 | 0 | 100% | Finished | 88628.0391 | 88628.0391 | 100 | 100 | 100 | 100 | 189.7378 | 100
289 | Afwerking sanitair | 2004-11-08 08:00 | 2004-11-23 17:00 | 10d |  | 0 | 3926.79 | 0 | 0 | 3926.79 | 2005-02-07 08:00 | 10d | 3926.79 | 0 | 0 | 80366.6875 | 0 | 84293.4775 | 0 | 100% | Finished | 3926.79 | 3926.79 | 100 | 100 | 100 | 100 | 2146.6255 | 100
290 | Belijning en pictogrammen | 2004-12-15 08:00 | 2005-01-12 17:00 | 10d |  | 0 | 32126.5508 | 0 | 0 | 32126.5508 | 2005-03-07 08:00 | 10d | 32126.5508 | 0 | 0 | 58491.9219 | 0 | 90618.4727 | 0 | 100% | Finished | 32126.5508 | 32126.5508 | 100 | 100 | 100 | 100 | 282.0672 | 100
291 | Talud bekleding | 2004-08-02 08:00 | 2004-10-11 17:00 | 50d |  | 0 | 448265.125 | 0 | 0 | 448265.125 | 2005-01-10 08:00 | 50d | 448265.125 | 0 | 0 | -27862.8105 | 0 | 420402.3145 | 0 | 100% | Finished | 448265.125 | 448265.125 | 100 | 100 | 100 | 100 | 93.7843 | 100
192 | Wegenis- en rioleringswerken | 2004-02-16 08:00 | 2005-03-21 17:00 | 250d |  |  | 5817466.818 |  |  | 5817466.818 |  | 249d | [5 empty] | 6924813.6576 |  | 100% |  | 5817466.818 | 5817466.818
191 | Fase 1 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 228530.0125 |  |  | 228530.0125 |  | 163d | [5 empty] | 361545.9715 |  | 100% |  | 228530.0125 | 228530.0125
190 | Fase 1.1 | 2004-02-16 08:00 | 2004-02-24 17:00 | 7d |  |  | 57005.7715 |  |  | 57005.7715 |  | 7d | [5 empty] | 75672.4111 |  | 100% |  | 57005.7715 | 57005.7715
189 | Openbreken verharding straat A | 2004-02-16 08:00 | 2004-02-20 17:00 | 5d |  | 0 | 29275.6406 | 0 | 0 | 29275.6406 | 2004-02-16 08:00 | 5d | 29275.6406 | 0 | 0 | 12764.5898 | 0 | 42040.2305 | 0 | 100% | Finished | 29275.6406 | 29275.6406 | 100 | 100 | 100 | 100 | 143.6014 | 100
193 | RW bypass | 2004-02-19 08:00 | 2004-02-24 17:00 | 4d |  | 0 | 27730.1309 | 0 | 0 | 27730.1309 | 2004-02-19 08:00 | 4d | 27730.1309 | 0 | 0 | 5902.0498 | 0 | 33632.1807 | 0 | 100% | Finished | 27730.1309 | 27730.1309 | 100 | 100 | 100 | 100 | 121.2839 | 100
195 | Fase 1.2 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 17023.8298 |  |  | 17023.8298 |  | 156d | [5 empty] | 33632.1794 |  | 100% |  | 17023.8298 | 17023.8298
194 | Openbreken riolering bypass (aan O1) | 2004-02-25 08:00 | 2004-02-26 17:00 | 2d |  | 0 | 1377.95 | 0 | 0 | 1377.95 | 2004-02-25 08:00 | 2d | 1377.95 | 0 | 0 | 15438.1396 | 0 | 16816.0896 | 0 | 100% | Finished | 1377.95 | 1377.95 | 100 | 100 | 100 | 100 | 1220.3701 | 100
196 | Demontage standbeeld | 2004-02-27 08:00 | 2004-03-01 17:00 | 2d |  | 0 | 15645.8799 | 0 | 0 | 15645.8799 | 2004-10-28 08:00 | 2d | 15645.8799 | 0 | 0 | 1170.21 | 0 | 16816.0898 | 0 | 100% | Finished | 15645.8799 | 15645.8799 | 100 | 100 | 100 | 100 | 107.4793 | 100
198 | Fase 1.3 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  |  | 12365.5303 |  |  | 12365.5303 |  | 4d | [5 empty] | 33632.1807 |  | 100% |  | 12365.5303 | 12365.5303
197 | Bouwput O1 | 2004-02-25 08:00 | 2004-03-01 17:00 | 4d |  | 0 | 12365.5303 | 0 | 0 | 12365.5303 | 2004-02-25 08:00 | 4d | 12365.5303 | 0 | 0 | 21266.6504 | 0 | 33632.1807 | 0 | 100% | Finished | 12365.5303 | 12365.5303 | 100 | 100 | 100 | 100 | 271.9833 | 100
200 | Fase 1.4 | 2004-02-16 08:00 | 2004-03-16 17:00 | 22d |  |  | 142134.881 |  |  | 142134.881 |  | 22d | [5 empty] | 218609.2003 |  | 100% |  | 142134.881 | 142134.881
199 | Constructie O1 (gedeeltelijke prefab) | 2004-03-02 08:00 | 2004-03-15 17:00 | 10d |  | 0 | 62489.3594 | 0 | 0 | 62489.3594 | 2004-03-02 08:00 | 10d | 62489.3594 | 0 | 0 | 21591.0996 | 0 | 84080.459 | 0 | 100% | Finished | 62489.3594 | 62489.3594 | 100 | 100 | 100 | 100 | 134.5516 | 100
201 | Aanleg riolering D11 - O1 | 2004-03-05 08:00 | 2004-03-08 17:00 | 2d |  | 0 | 24304.8008 | 0 | 0 | 24304.8008 | 2004-03-05 08:00 | 2d | 24304.8008 | 0 | 0 | -7488.71 | 0 | 16816.0908 | 0 | 100% | Finished | 24304.8008 | 24304.8008 | 100 | 100 | 100 | 100 | 69.1884 | 100
202 | Constructie V3 en V4 | 2004-03-09 08:00 | 2004-03-16 17:00 | 6d |  | 0 | 457.92 | 0 | 0 | 457.92 | 2004-03-09 08:00 | 6d | 457.92 | 0 | 0 | 49990.3594 | 0 | 50448.2794 | 0 | 100% | Finished | 457.92 | 457.92 | 100 | 100 | 100 | 100 | 11016.8322 | 100
203 | Openbreken verharding stadsplein (PK) | 2004-02-16 08:00 | 2004-02-25 17:00 | 8d |  | 0 | 54882.8008 | 0 | 0 | 54882.8008 | 2004-02-16 08:00 | 8d | 54882.8008 | 0 | 0 | 12381.5703 | 0 | 67264.3711 | 0 | 100% | Finished | 54882.8008 | 54882.8008 | 100 | 100 | 100 | 100 | 122.56 | 100
206 | Fase 2 | 2004-03-09 08:00 | 2004-05-07 17:00 | 41d |  |  | 487050.7034 |  |  | 487050.7034 |  | 41d | [5 empty] | 465962.4204 |  | 100% |  | 487050.7034 | 487050.7034
205 | Fase 2.1 | 2004-03-09 08:00 | 2004-03-18 17:00 | 8d |  |  | 53827.6813 |  |  | 53827.6813 |  | 8d | [5 empty] | 100896.5615 |  | 100% |  | 53827.6813 | 53827.6813
204 | Aanleg riolering O1 - D8' | 2004-03-09 08:00 | 2004-03-10 17:00 | 2d |  | 0 | 17948.6406 | 0 | 0 | 17948.6406 | 2004-03-09 08:00 | 2d | 17948.6406 | 0 | 0 | -1132.55 | 0 | 16816.0906 | 0 | 100% | Finished | 17948.6406 | 17948.6406 | 100 | 100 | 100 | 100 | 93.6901 | 100
207 | Constructie V1 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-11 08:00 | 3d | 204.15 | 0 | 0 | 25019.9902 | 0 | 25224.1402 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 12355.6899 | 100
208 | Aanleg riolering O1 - D10 | 2004-03-11 08:00 | 2004-03-15 17:00 | 3d |  | 0 | 29623.8809 | 0 | 0 | 29623.8809 | 2004-03-11 08:00 | 3d | 29623.8809 | 0 | 0 | -4399.7402 | 0 | 25224.1406 | 0 | 100% | Finished | 29623.8809 | 29623.8809 | 100 | 100 | 100 | 100 | 85.148 | 100
209 | Constructie V2 | 2004-03-16 08:00 | 2004-03-18 17:00 | 3d |  | 0 | 204.15 | 0 | 0 | 204.15 | 2004-03-16 08:00 | 3d | 204.15 | 0 | 0 | 25019.9902 | 0 | 25224.1402 | 0 | 100% | Finished | 204.15 | 204.15 | 100 | 100 | 100 | 100 | 12355.6899 | 100
210 | Openbreken verharding straat B | 2004-03-17 08:00 | 2004-03-17 17:00 | 1d |  | 0 | 5846.8599 | 0 | 0 | 5846.8599 | 2004-03-17 08:00 | 1d | 5846.8599 | 0 | 0 | 2561.1899 | 0 | 8408.0498 | 0 | 100% | Finished | 5846.8599 | 5846.8599 | 100 | 100 | 100 | 100 | 143.8045 | 100
212 | Fase 2.2 | 2004-03-19 08:00 | 2004-03-22 17:00 | 2d |  |  | 7169.4 |  |  | 7169.4 |  | 2d | [5 empty] | 16816.0802 |  | 100% |  | 7169.4 | 7169.4
211 | Opschuimen/opbreken D10 - D11 | 2004-03-19 08:00 | 2004-03-19 17:00 | 1d |  | 0 | 5366.04 | 0 | 0 | 5366.04 | 2004-03-19 08:00 | 1d | 5366.04 | 0 | 0 | 3042 | 0 | 8408.04 | 0 | 100% | Finished | 5366.04 | 5366.04 | 100 | 100 | 100 | 100 | 156.6898 | 100
213 | Opschuimen/opbreken D1 - D8' | 2004-03-22 08:00 | 2004-03-22 17:00 | 1d |  | 0 | 1803.36 | 0 | 0 | 1803.36 | 2004-03-22 08:00 | 1d | 1803.36 | 0 | 0 | 6604.6802 | 0 | 8408.0402 | 0 | 100% | Finished | 1803.36 | 1803.36 | 100 | 100 | 100 | 100 | 466.243 | 100
215 | Fase 2.3 | 2004-03-23 08:00 | 2004-05-07 17:00 | 31d |  |  | 426053.6221 |  |  | 426053.6221 |  | 31d | [5 empty] | 348249.7787 |  | 100% |  | 426053.6221 | 426053.6221
214 | Aanleg riolering O1 - wacht | 2004-03-23 08:00 | 2004-03-25 17:00 | 3d |  | 0 | 23918.1797 | 0 | 0 | 23918.1797 | 2004-03-23 08:00 | 3d | 23918.1797 | 0 | 0 | 1305.96 | 0 | 25224.1396 | 0 | 100% | Finished | 23918.1797 | 23918.1797 | 100 | 100 | 100 | 100 | 105.4601 | 100
216 | Aanleg riolering D8 - D7 | 2004-03-26 08:00 | 2004-03-29 17:00 | 2d |  | 0 | 16568.5293 | 0 | 0 | 16568.5293 | 2004-03-26 08:00 | 2d | 16568.5293 | 0 | 0 | 247.56 | 0 | 16816.0893 | 0 | 100% | Finished | 16568.5293 | 16568.5293 | 100 | 100 | 100 | 100 | 101.4942 | 100
217 | Aanleg riolering D7 - D6 | 2004-03-30 08:00 | 2004-03-30 17:00 | 1d |  | 0 | 7600.1201 | 0 | 0 | 7600.1201 | 2004-03-30 08:00 | 1d | 7600.1201 | 0 | 0 | 807.93 | 0 | 8408.0501 | 0 | 100% | Finished | 7600.1201 | 7600.1201 | 100 | 100 | 100 | 100 | 110.6305 | 100
218 | Aanleg riolering O1 - R1 | 2004-03-31 08:00 | 2004-04-06 17:00 | 5d |  | 0 | 46425.3594 | 0 | 0 | 46425.3594 | 2004-03-31 08:00 | 5d | 46425.3594 | 0 | 0 | -4385.1299 | 0 | 42040.2295 | 0 | 100% | Finished | 46425.3594 | 46425.3594 | 100 | 100 | 100 | 100 | 90.5545 | 100
219 | Aanleg riolering O1 - D2 | 2004-04-07 08:00 | 2004-04-15 17:00 | 5d |  | 0 | 42138.1211 | 0 | 0 | 42138.1211 | 2004-04-07 08:00 | 5d | 42138.1211 | 0 | 0 | -97.89 | 0 | 42040.2311 | 0 | 100% | Finished | 42138.1211 | 42138.1211 | 100 | 100 | 100 | 100 | 99.7677 | 100
220 | Aanleg def verharding kruispunt | 2004-03-31 08:00 | 2004-05-07 17:00 | 25d |  | 0 | 289403.3125 | 0 | 0 | 289403.3125 | 2004-03-31 08:00 | 25d | 289403.3125 | 0 | 0 | -75682.2734 | 0 | 213721.0391 | 0 | 100% | Finished | 289403.3125 | 289403.3125 | 100 | 100 | 100 | 100 | 73.8489 | 100
223 | Fase 3 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 33632.1793 |  | 100% |  | 35936.4492 | 35936.4492
222 | Fase 3.1 | 2004-04-16 08:00 | 2004-04-21 17:00 | 4d |  |  | 35936.4492 |  |  | 35936.4492 |  | 4d | [5 empty] | 33632.1793 |  | 100% |  | 35936.4492 | 35936.4492
221 | Aanleg riolering R1 - R2 | 2004-04-16 08:00 | 2004-04-19 17:00 | 2d |  | 0 | 19158.5 | 0 | 0 | 19158.5 | 2004-04-16 08:00 | 2d | 19158.5 | 0 | 0 | -2342.4099 | 0 | 16816.0901 | 0 | 100% | Finished | 19158.5 | 19158.5 | 100 | 100 | 100 | 100 | 87.7735 | 100
224 | Aanleg riolering D2 - D3 | 2004-04-20 08:00 | 2004-04-21 17:00 | 2d |  | 0 | 16777.9492 | 0 | 0 | 16777.9492 | 2004-04-20 08:00 | 2d | 16777.9492 | 0 | 0 | 38.14 | 0 | 16816.0892 | 0 | 100% | Finished | 16777.9492 | 16777.9492 | 100 | 100 | 100 | 100 | 100.2273 | 100
227 | Fase 4 | 2004-05-10 08:00 | 2004-08-31 17:00 | 63d |  |  | 868616.3242 |  |  | 868616.3242 |  | 63d | [5 empty] | 905292.7441 |  | 100% |  | 868616.3242 | 868616.3242
226 | Fase 4.1 | 2004-05-10 08:00 | 2004-06-24 17:00 | 31d |  |  | 285414.4492 |  |  | 285414.4492 |  | 29d | [5 empty] | 327913.8003 |  | 100% |  | 285414.4492 | 285414.4492
225 | Opbraak verharding straat C | 2004-05-10 08:00 | 2004-05-13 17:00 | 4d |  | 0 | 21329.0703 | 0 | 0 | 21329.0703 | 2004-05-10 08:00 | 4d | 21329.0703 | 0 | 0 | 12303.1104 | 0 | 33632.1807 | 0 | 100% | Finished | 21329.0703 | 21329.0703 | 100 | 100 | 100 | 100 | 157.6824 | 100
228 | Start werken straat aan uitrit | 2004-06-01 17:00 | 2004-06-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
229 | Aanleg riolering R2 - R3 | 2004-05-14 08:00 | 2004-05-26 17:00 | 7d |  | 0 | 63674.7188 | 0 | 0 | 63674.7188 | 2004-05-14 08:00 | 7d | 63674.7188 | 0 | 0 | -4818.3999 | 0 | 58856.3188 | 0 | 100% | Finished | 63674.7188 | 63674.7188 | 100 | 100 | 100 | 100 | 92.4328 | 100
230 | Aanleg riolering R3 - O2 - wacht | 2004-05-27 08:00 | 2004-06-07 17:00 | 7d |  | 0 | 61943.1289 | 0 | 0 | 61943.1289 | 2004-05-27 08:00 | 7d | 61943.1289 | 0 | 0 | -3086.8 | 0 | 58856.3289 | 0 | 100% | Finished | 61943.1289 | 61943.1289 | 100 | 100 | 100 | 100 | 95.0167 | 100
231 | Aanleg riolering D3 - D4 | 2004-06-08 08:00 | 2004-06-14 17:00 | 5d |  | 0 | 38520.6914 | 0 | 0 | 38520.6914 | 2004-06-08 08:00 | 5d | 38520.6914 | 0 | 0 | 3519.54 | 0 | 42040.2314 | 0 | 100% | Finished | 38520.6914 | 38520.6914 | 100 | 100 | 100 | 100 | 109.1368 | 100
232 | Aanleg riolering D4 - D5 - aansluiting | 2004-06-17 08:00 | 2004-06-24 17:00 | 6d |  | 0 | 47025.7695 | 0 | 0 | 47025.7695 | 2004-06-15 08:00 | 6d | 47025.7695 | 0 | 0 | 3422.51 | 0 | 50448.2795 | 0 | 100% | Finished | 47025.7695 | 47025.7695 | 100 | 100 | 100 | 100 | 107.2779 | 100
233 | Constructie O2 | 2004-06-08 08:00 | 2004-06-21 17:00 | 10d |  | 0 | 52921.0703 | 0 | 0 | 52921.0703 | 2004-06-08 08:00 | 10d | 52921.0703 | 0 | 0 | 31159.3906 | 0 | 84080.4609 | 0 | 100% | Finished | 52921.0703 | 52921.0703 | 100 | 100 | 100 | 100 | 158.879 | 100
235 | Fase 4.2 | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  |  | 39283.5117 |  |  | 39283.5117 |  | 20d | [5 empty] | 168160.918 |  | 100% |  | 39283.5117 | 39283.5117
234 | Opbraak en aansluitingen bestaande riolering | 2004-06-10 08:00 | 2004-07-07 17:00 | 20d |  | 0 | 39283.5117 | 0 | 0 | 39283.5117 | 2004-06-10 08:00 | 20d | 39283.5117 | 0 | 0 | 128877.4062 | 0 | 168160.918 | 0 | 100% | Finished | 39283.5117 | 39283.5117 | 100 | 100 | 100 | 100 | 428.07 | 100
237 | Fase 4.3 | 2004-06-25 08:00 | 2004-07-06 17:00 | 8d |  |  | 82365.2695 |  |  | 82365.2695 |  | 8d | [5 empty] | 67264.3696 |  | 100% |  | 82365.2695 | 82365.2695
236 | Aanleg riolering O2 - R4 | 2004-06-25 08:00 | 2004-06-30 17:00 | 4d |  | 0 | 40901.25 | 0 | 0 | 40901.25 | 2004-06-23 08:00 | 4d | 40901.25 | 0 | 0 | -7269.0601 | 0 | 33632.1899 | 0 | 100% | Finished | 40901.25 | 40901.25 | 100 | 100 | 100 | 100 | 82.2278 | 100
238 | Aanleg riolering R4 - R5 | 2004-07-01 08:00 | 2004-07-06 17:00 | 4d |  | 0 | 41464.0195 | 0 | 0 | 41464.0195 | 2004-06-29 08:00 | 4d | 41464.0195 | 0 | 0 | -7831.8398 | 0 | 33632.1797 | 0 | 100% | Finished | 41464.0195 | 41464.0195 | 100 | 100 | 100 | 100 | 81.1117 | 100
240 | Fase 4.5 | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  |  | 461553.0938 |  |  | 461553.0938 |  | 40d | [5 empty] | 341953.6562 |  | 100% |  | 461553.0938 | 461553.0938
239 | Aanleg verharding straat C | 2004-06-15 08:00 | 2004-08-31 17:00 | 40d |  | 0 | 461553.0938 | 0 | 0 | 461553.0938 | 2004-06-15 08:00 | 40d | 461553.0938 | 0 | 0 | -119599.4375 | 0 | 341953.6562 | 0 | 100% | Finished | 461553.0938 | 461553.0938 | 100 | 100 | 100 | 100 | 74.0876 | 100
241 | Openstelling straat C | 2004-09-01 17:00 | 2004-09-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2004-09-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
244 | Fase 5 + 6 | 2004-09-02 08:00 | 2004-12-03 17:00 | 64d |  |  | 1025826.356 |  |  | 1025826.356 |  | 64d | [5 empty] | 561576.0433 |  | 100% |  | 1025826.356 | 1025826.356
243 | Fase 5.1 | 2004-09-02 08:00 | 2004-09-27 17:00 | 18d |  |  | 83395.19 |  |  | 83395.19 |  | 18d | [5 empty] | 169174.1597 |  | 100% |  | 83395.19 | 83395.19
242 | Sonderen bestaande leidingen | 2004-09-02 08:00 | 2004-09-08 17:00 | 5d |  | 0 | 451.94 | 0 | 0 | 451.94 | 2004-09-02 08:00 | 5d | 451.94 | 0 | 0 | 59417.6406 | 0 | 59869.5806 | 0 | 100% | Finished | 451.94 | 451.94 | 100 | 100 | 100 | 100 | 13247.2409 | 100
245 | Opbraak rest. riolering stadsplein | 2004-09-09 08:00 | 2004-09-09 17:00 | 1d |  | 0 | 450.25 | 0 | 0 | 450.25 | 2004-09-09 08:00 | 1d | 450.25 | 0 | 0 | 7957.79 | 0 | 8408.04 | 0 | 100% | Finished | 450.25 | 450.25 | 100 | 100 | 100 | 100 | 1867.4159 | 100
246 | Opbraak verharding stadsplein (PK) | 2004-09-10 08:00 | 2004-09-17 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-10 08:00 | 6d | 41246.5 | 0 | 0 | 9201.7695 | 0 | 50448.2695 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 122.3092 | 100
247 | Opbraak wegverharding NO stadsplein | 2004-09-20 08:00 | 2004-09-27 17:00 | 6d |  | 0 | 41246.5 | 0 | 0 | 41246.5 | 2004-09-20 08:00 | 6d | 41246.5 | 0 | 0 | 9201.7695 | 0 | 50448.2695 | 0 | 100% | Finished | 41246.5 | 41246.5 | 100 | 100 | 100 | 100 | 122.3092 | 100
249 | Fase 5.2 | 2004-09-28 08:00 | 2004-10-05 17:00 | 6d |  |  | 47465.2285 |  |  | 47465.2285 |  | 6d | [5 empty] | 50448.2585 |  | 100% |  | 47465.2285 | 47465.2285
248 | Aanleg riolering R15 - R17 | 2004-09-28 08:00 | 2004-09-30 17:00 | 3d |  | 0 | 24597.8691 | 0 | 0 | 24597.8691 | 2004-09-03 08:00 | 3d | 24597.8691 | 0 | 0 | 626.26 | 0 | 25224.1292 | 0 | 100% | Finished | 24597.8691 | 24597.8691 | 100 | 100 | 100 | 100 | 102.546 | 100
250 | Aanleg riolering D6 - D7 | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 22867.3594 | 0 | 0 | 22867.3594 | 2004-09-08 08:00 | 3d | 22867.3594 | 0 | 0 | 2356.77 | 0 | 25224.1294 | 0 | 100% | Finished | 22867.3594 | 22867.3594 | 100 | 100 | 100 | 100 | 110.3063 | 100
252 | Fase 5.3 | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  |  | 894965.9375 |  |  | 894965.9375 |  | 40d | [5 empty] | 341953.625 |  | 100% |  | 894965.9375 | 894965.9375
251 | Aanleg wegverharding NO stadsplein | 2004-10-06 08:00 | 2004-12-03 17:00 | 40d |  | 0 | 894965.9375 | 0 | 0 | 894965.9375 | 2004-10-06 08:00 | 40d | 894965.9375 | 0 | 0 | -553012.3125 | 0 | 341953.625 | 0 | 100% | Finished | 894965.9375 | 894965.9375 | 100 | 100 | 100 | 100 | 38.2086 | 100
255 | Fase 7 | 2004-12-06 08:00 | 2005-02-18 17:00 | 44d |  |  | 778542.7812 |  |  | 778542.7812 |  | 45d | [5 empty] | 374177.8577 |  | 100% |  | 778542.7812 | 778542.7812
254 | Fase 7.1 | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  |  | 33920.1484 |  |  | 33920.1484 |  | 5d | [5 empty] | 42040.2285 |  | 100% |  | 33920.1484 | 33920.1484
253 | Opbraak wegverharding N stadsplein | 2004-12-06 08:00 | 2004-12-10 17:00 | 5d |  | 0 | 33920.1484 | 0 | 0 | 33920.1484 | 2004-12-06 08:00 | 5d | 33920.1484 | 0 | 0 | 8120.0801 | 0 | 42040.2285 | 0 | 100% | Finished | 33920.1484 | 33920.1484 | 100 | 100 | 100 | 100 | 123.9388 | 100
257 | Fase 7.2 | 2004-12-13 08:00 | 2004-12-23 17:00 | 9d |  |  | 76109.8203 |  |  | 76109.8203 |  | 9d | [5 empty] | 75672.4104 |  | 100% |  | 76109.8203 | 76109.8203
256 | Aanleg riolering R7 - R6 - R5 | 2004-12-13 08:00 | 2004-12-17 17:00 | 5d |  | 0 | 46090.3906 | 0 | 0 | 46090.3906 | 2004-12-13 08:00 | 5d | 46090.3906 | 0 | 0 | -4050.1599 | 0 | 42040.2307 | 0 | 100% | Finished | 46090.3906 | 46090.3906 | 100 | 100 | 100 | 100 | 91.2126 | 100
258 | Aanleg riolering D12 - D12' | 2004-12-20 08:00 | 2004-12-23 17:00 | 4d |  | 0 | 30019.4297 | 0 | 0 | 30019.4297 | 2004-12-20 08:00 | 4d | 30019.4297 | 0 | 0 | 3612.75 | 0 | 33632.1797 | 0 | 100% | Finished | 30019.4297 | 30019.4297 | 100 | 100 | 100 | 100 | 112.0347 | 100
260 | Fase 7.3 | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  |  | 668512.8125 |  |  | 668512.8125 |  | 31d | [5 empty] | 256465.2188 |  | 100% |  | 668512.8125 | 668512.8125
259 | Aanleg wegverharding N stadsplein | 2005-01-10 08:00 | 2005-02-18 17:00 | 30d |  | 0 | 668512.8125 | 0 | 0 | 668512.8125 | 2005-01-10 08:00 | 31d | 668512.8125 | 0 | 0 | -412047.5938 | 0 | 256465.2188 | 0 | 100% | Finished | 668512.8125 | 668512.8125 | 100 | 103.3333 | 100 | 100 | 38.3635 | 100
262 | Pleinafwerking | 2004-09-01 08:00 | 2005-02-28 17:00 | 115d |  |  | 206424.2637 |  |  | 206424.2637 |  | 121d | [5 empty] | 1091455.9824 |  | 100% |  | 206424.2637 | 206424.2637
261 | Hoofdkant | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 31664.5605 | 0 | 0 | 31664.5605 | 2004-09-13 08:00 | 50d | 31664.5605 | 0 | 0 | 421427.7812 | 0 | 453092.3418 | 0 | 100% | Finished | 31664.5605 | 31664.5605 | 100 | 100 | 100 | 100 | 1430.9131 | 100
263 | Overige | 2004-11-15 08:00 | 2005-02-28 17:00 | 65d |  | 0 | 174759.7031 | 0 | 0 | 174759.7031 | 2004-11-22 08:00 | 74d | 174759.7031 | 0 | 0 | 463603.9375 | 0 | 638363.6406 | 0 | 100% | Finished | 174759.7031 | 174759.7031 | 100 | 113.8462 | 100 | 100 | 365.2808 | 100
264 | Straatmeubilair en aanplanting | 2005-03-01 08:00 | 2005-03-21 17:00 | 15d |  | 0 | 235690.6719 | 0 | 0 | 235690.6719 | 2005-02-28 08:00 | 15d | 235690.6719 | 0 | 0 | -46522.9688 | 0 | 189167.7031 | 0 | 100% | Finished | 235690.6719 | 235690.6719 | 100 | 100 | 100 | 100 | 80.261 | 100
293 | Liften | 2004-09-01 08:00 | 2004-10-20 17:00 | 36d |  |  | 24833.4189 |  |  | 24833.4189 |  | 40d | [5 empty] | 369954.0244 |  | 100% |  | 24833.4189 | 24833.4189
292 | Constructie | 2004-09-01 08:00 | 2004-09-10 17:00 | 8d |  | 0 | 4644.7798 | 0 | 0 | 4644.7798 | 2005-01-17 08:00 | 4d | 4644.7798 | 0 | 0 | 62619.5898 | 0 | 67264.3696 | 0 | 100% | Finished | 4644.7798 | 4644.7798 | 100 | 50 | 100 | 100 | 1448.1713 | 100
294 | Glas | 2004-09-01 08:00 | 2004-09-08 17:00 | 6d |  | 0 | 3364.77 | 0 | 0 | 3364.77 | 2005-01-31 08:00 | 6d | 3364.77 | 0 | 0 | 47083.5 | 0 | 50448.27 | 0 | 100% | Finished | 3364.77 | 3364.77 | 100 | 100 | 100 | 100 | 1499.3081 | 100
295 | Liftkooi | 2004-09-09 08:00 | 2004-10-20 17:00 | 30d |  | 0 | 16823.8691 | 0 | 0 | 16823.8691 | 2005-02-08 08:00 | 24d | 16823.8691 | 0 | 0 | 235417.5156 | 0 | 252241.3848 | 0 | 100% | Finished | 16823.8691 | 16823.8691 | 100 | 80 | 100 | 100 | 1499.3066 | 100
297 | Promenade | 2004-09-01 08:00 | 2005-01-19 17:00 | 87d |  |  | 1048283.1511 |  |  | 1048283.1511 |  | 84d | [5 empty] | 1469597.9602 |  | 100% |  | 1048283.1511 | 1048283.1511
296 | Dakdichting | 2004-09-01 08:00 | 2004-09-23 17:00 | 17d |  | 0 | 12038.2695 | 0 | 0 | 12038.2695 | 2004-11-02 08:00 | 17d | 12038.2695 | 0 | 0 | 130898.5078 | 0 | 142936.7773 | 0 | 100% | Finished | 12038.2695 | 12038.2695 | 100 | 100 | 100 | 100 | 1187.3532 | 100
298 | Beschermbeton | 2004-09-01 08:00 | 2004-09-20 17:00 | 14d |  | 0 | 3083.78 | 0 | 0 | 3083.78 | 2004-11-05 08:00 | 17d | 3083.78 | 0 | 0 | 114628.8672 | 0 | 117712.6472 | 0 | 100% | Finished | 3083.78 | 3083.78 | 100 | 121.4286 | 100 | 100 | 3817.1545 | 100
299 | Zitbanken | 2004-09-01 08:00 | 2004-09-01 17:00 | 1d |  | 0 | 31102.0195 | 0 | 0 | 31102.0195 | 2004-11-15 08:00 | 20d | 31102.0195 | 0 | 0 | -22693.9805 | 0 | 8408.0391 | 0 | 100% | Finished | 31102.0195 | 31102.0195 | 100 | 2000 | 100 | 100 | 27.0337 | 100
300 | Bevestigingsprofielen glazen leuningen | 2004-09-01 08:00 | 2004-09-21 17:00 | 15d |  | 0 | 132006.2031 | 0 | 0 | 132006.2031 | 2004-11-15 08:00 | 25d | 132006.2031 | 0 | 0 | -5565.98 | 0 | 126440.2231 | 0 | 100% | Finished | 132006.2031 | 132006.2031 | 100 | 166.6667 | 100 | 100 | 95.7835 | 100
301 | Houten promenade | 2004-09-24 08:00 | 2005-01-19 17:00 | 70d |  | 0 | 413377.0625 | 0 | 0 | 413377.0625 | 2004-11-08 08:00 | 80d | 413377.0625 | 0 | 0 | 175414.5625 | 0 | 588791.625 | 0 | 100% | Finished | 413377.0625 | 413377.0625 | 100 | 114.2857 | 100 | 100 | 142.4345 | 100
302 | Glazen leuningen | 2004-09-01 08:00 | 2004-11-10 17:00 | 50d |  | 0 | 440020.6562 | 0 | 0 | 440020.6562 | 2005-01-10 08:00 | 45d | 440020.6562 | 0 | 0 | -19618.3398 | 0 | 420402.3164 | 0 | 100% | Finished | 440020.6562 | 440020.6562 | 100 | 90 | 100 | 100 | 95.5415 | 100
303 | Plaatsen prefabtrappen | 2004-09-01 08:00 | 2004-09-09 17:00 | 7d |  | 0 | 16655.1602 | 0 | 0 | 16655.1602 | 2005-02-04 08:00 | 7d | 16655.1602 | 0 | 0 | 48251.1719 | 0 | 64906.332 | 0 | 100% | Finished | 16655.1602 | 16655.1602 | 100 | 100 | 100 | 100 | 389.707 | 100
305 | Bruggen + luifels | 2004-09-01 08:00 | 2004-11-26 17:00 | 60d |  |  | 595707.5625 |  |  | 595707.5625 |  | 49d | [5 empty] | 504482.791 |  | 100% |  | 595707.5625 | 595707.5625
304 | Constructie | 2004-09-01 08:00 | 2004-10-12 17:00 | 30d |  | 0 | 322152.7812 | 0 | 0 | 322152.7812 | 2005-01-11 08:00 | 35d | 322152.7812 | 0 | 0 | -69911.3906 | 0 | 252241.3906 | 0 | 100% | Finished | 322152.7812 | 322152.7812 | 100 | 116.6667 | 100 | 100 | 78.2987 | 100
306 | Glas | 2004-10-13 08:00 | 2004-11-26 17:00 | 30d |  | 0 | 273554.7812 | 0 | 0 | 273554.7812 | 2005-02-10 08:00 | 27d | 273554.7812 | 0 | 0 | -21313.3809 | 0 | 252241.4004 | 0 | 100% | Finished | 273554.7812 | 273554.7812 | 100 | 90 | 100 | 100 | 92.2087 | 100
308 | Straat A | 2004-09-01 08:00 | 2004-10-05 17:00 | 25d |  |  | 104851.2127 |  |  | 104851.2127 |  | 45d | [5 empty] | 253238.0931 |  | 100% |  | 104851.2127 | 104851.2127
307 | Uitbreken wegverharding + maken koffer | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3592.98 | 0 | 0 | 3592.98 | 2005-01-10 08:00 | 5d | 3592.98 | 0 | 0 | 38447.25 | 0 | 42040.23 | 0 | 100% | Finished | 3592.98 | 3592.98 | 100 | 100 | 100 | 100 | 1170.0658 | 100
309 | Riolering + huisaansluitingen | 2004-09-08 08:00 | 2004-09-28 17:00 | 15d |  | 0 | 78335.2422 | 0 | 0 | 78335.2422 | 2005-01-24 08:00 | 15d | 78335.2422 | 0 | 0 | 47785.4492 | 0 | 126120.6914 | 0 | 100% | Finished | 78335.2422 | 78335.2422 | 100 | 100 | 100 | 100 | 161.0012 | 100
310 | Kantstroken | 2004-09-29 08:00 | 2004-09-30 17:00 | 2d |  | 0 | 182.46 | 0 | 0 | 182.46 | 2005-02-14 08:00 | 3d | 182.46 | 0 | 0 | 16633.6309 | 0 | 16816.0909 | 0 | 100% | Finished | 182.46 | 182.46 | 100 | 150 | 100 | 100 | 9216.316 | 100
311 | Wegverharding | 2004-10-01 08:00 | 2004-10-05 17:00 | 3d |  | 0 | 19392.5605 | 0 | 0 | 19392.5605 | 2005-02-17 08:00 | 2d | 19392.5605 | 0 | 0 | 6124.3198 | 0 | 25516.8804 | 0 | 100% | Finished | 19392.5605 | 19392.5605 | 100 | 66.6667 | 100 | 100 | 131.5808 | 100
312 | Herstellen voetpad verharding aan bouwwerven | 2004-09-01 08:00 | 2004-09-07 17:00 | 5d |  | 0 | 3347.97 | 0 | 0 | 3347.97 | 2005-03-07 08:00 | 5d | 3347.97 | 0 | 0 | 39396.2305 | 0 | 42744.2004 | 0 | 100% | Finished | 3347.97 | 3347.97 | 100 | 100 | 100 | 100 | 1276.7199 | 100
314 | Busperrons | 2004-09-01 08:00 | 2004-09-29 17:00 | 21d |  |  | 177173.9105 |  |  | 177173.9105 |  | 27d | [5 empty] | 344729.8871 |  | 100% |  | 177173.9105 | 177173.9105
313 | Vrijgraven fundering kant | 2004-09-01 08:00 | 2004-09-03 17:00 | 3d |  | 0 | 1511.83 | 0 | 0 | 1511.83 | 2005-02-07 08:00 | 3d | 1511.83 | 0 | 0 | 23712.3105 | 0 | 25224.1405 | 0 | 100% | Finished | 1511.83 | 1511.83 | 100 | 100 | 100 | 100 | 1668.4509 | 100
315 | Boren ankers | 2004-09-06 08:00 | 2004-09-08 17:00 | 3d |  | 0 | 655.73 | 0 | 0 | 655.73 | 2005-02-08 08:00 | 4d | 655.73 | 0 | 0 | 24568.4102 | 0 | 25224.1401 | 0 | 100% | Finished | 655.73 | 655.73 | 100 | 133.3333 | 100 | 100 | 3846.7267 | 100
316 | Plaatsen constructie + ondergieten | 2004-09-09 08:00 | 2004-09-29 17:00 | 15d |  | 0 | 14023.8896 | 0 | 0 | 14023.8896 | 2005-02-21 08:00 | 10d | 14023.8896 | 0 | 0 | 112096.7969 | 0 | 126120.6865 | 0 | 100% | Finished | 14023.8896 | 14023.8896 | 100 | 66.6667 | 100 | 100 | 899.3274 | 100
317 | Leggen klinkers | 2004-09-09 08:00 | 2004-09-22 17:00 | 10d |  | 0 | 99261.0312 | 0 | 0 | 99261.0312 | 2005-02-24 08:00 | 12d | 99261.0312 | 0 | 0 | -15180.5703 | 0 | 84080.4609 | 0 | 100% | Finished | 99261.0312 | 99261.0312 | 100 | 120 | 100 | 100 | 84.7064 | 100
318 | Plaatsen glas | 2004-09-01 08:00 | 2004-09-14 17:00 | 10d |  | 0 | 61721.4297 | 0 | 0 | 61721.4297 | 2005-02-28 08:00 | 12d | 61721.4297 | 0 | 0 | 22359.0293 | 0 | 84080.459 | 0 | 100% | Finished | 61721.4297 | 61721.4297 | 100 | 120 | 100 | 100 | 136.2257 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2004-04-09
1:00 - 2:00 | No | Tuesday | Yes | 2004-04-12
2:00 - 3:00 | No | Wednesday | Yes | 2004-05-03
3:00 - 4:00 | No | Thursday | Yes | 2004-05-20
4:00 - 5:00 | No | Friday | Yes | 2004-05-21
5:00 - 6:00 | No | Saturday | No | 2004-05-31
6:00 - 7:00 | No | Sunday | No | 2004-07-12
7:00 - 8:00 | No |  |  | 2004-07-13
8:00 - 9:00 | Yes |  |  | 2004-07-14
9:00 - 10:00 | Yes |  |  | 2004-07-15
10:00 - 11:00 | Yes |  |  | 2004-07-16
11:00 - 12:00 | Yes |  |  | 2004-07-19
12:00 - 13:00 | No |  |  | 2004-07-20
13:00 - 14:00 | Yes |  |  | 2004-07-21
14:00 - 15:00 | Yes |  |  | 2004-07-22
15:00 - 16:00 | Yes |  |  | 2004-07-23
16:00 - 17:00 | Yes |  |  | 2004-07-26
17:00 - 18:00 | No |  |  | 2004-07-27
18:00 - 19:00 | No |  |  | 2004-07-28
19:00 - 20:00 | No |  |  | 2004-07-29
20:00 - 21:00 | No |  |  | 2004-07-30
21:00 - 22:00 | No |  |  | 2004-08-16
22:00 - 23:00 | No |  |  | 2004-11-01
23:00 - 0:00 | No |  |  | 2004-11-11
2004-11-12
2004-12-24
Generated by PMConverter v1.1.3 |  |  |  | 2004-12-27
2004-12-28
2004-12-29
2004-12-30
2004-12-31
2005-01-03
2005-01-04
2005-01-05
2005-01-06
2005-01-07

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
04/04, 2004 | 2002-01-25 08:00 | 2004-04-04 17:00 | 2432704.33 | 1917382.2775 | 784812.4297 | 2004-03-25 17:00 | -515322.0525 | 78.82% | 1132569.8478 | 244.3% | -6d | 98.95% | 86.97% | 2005-05-10 12:00 | 2006-01-11 10:00 | 2003-08-20 10:00 | 2005-09-06 17:00 | 2006-01-11 10:00 | 2005-01-24 12:00 | 2005-03-29 17:00 | 2005-04-01 11:00 | 2004-09-09 11:00 | 10289320.5164 | 4675145.7095 | 12843783.7931 | 10390253.3457 | 5720724.6502 | 4716458.9832 | 5284795.2363 | 5200614.1934 | 0.98949 | 2.4431 | 0.78817 | 0.86975 | -6 | 2.4431 | 1 | 0.98949 | 1
04/05, 2004 | 2004-04-04 17:00 | 2004-05-04 17:00 | 2992104.5572 | 2520738.6305 | 865058.8487 | 2004-04-13 09:00 | -471365.9266 | 84.25% | 1655679.7818 | 291.4% | -14d 7h | 97.48% | 97.57% | 2005-05-05 11:00 | 2005-10-12 17:00 | 2003-04-18 09:00 | 2005-07-28 17:00 | 2005-10-12 17:00 | 2004-11-16 15:00 | 2005-04-11 16:00 | 2005-04-19 11:00 | 2004-09-13 10:00 | 9766210.5825 | 3919727.0233 | 11430682.8861 | 9996429.4602 | 4490935.1911 | 3998732.7857 | 4426013.729 | 4388707.2887 | 0.97479 | 2.914 | 0.84246 | 0.97574 | -14.875 | 2.914 | 1 | 0.97479 | 1
07/05, 2004 | 2004-05-04 17:00 | 2004-05-07 17:00 | 2992104.5572 | 2586335.8599 | 869236.089 | 2004-04-15 17:00 | -405768.6973 | 86.44% | 1717099.7709 | 297.5% | -15d | 97.47% | 96.35% | 2005-04-28 16:00 | 2005-09-09 11:00 | 2003-03-28 14:00 | 2005-07-12 11:00 | 2005-09-09 11:00 | 2004-11-02 10:00 | 2005-04-11 17:00 | 2005-04-19 11:00 | 2004-09-13 15:00 | 9704790.5933 | 3838758.7098 | 11090995.4929 | 9934086.9905 | 4304645.3505 | 3915822.4457 | 4329806.8236 | 4300158.4205 | 0.9747 | 2.9754 | 0.86439 | 0.96354 | -15 | 2.9754 | 1 | 0.9747 | 1
14/05, 2004 | 2004-05-07 17:00 | 2004-05-14 17:00 | 3077108.3462 | 2679752.319 | 875312.0792 | 2004-04-20 17:00 | -397356.0272 | 87.09% | 1804440.2398 | 306.1% | -17d | 97.16% | 96.64% | 2005-04-28 11:00 | 2005-08-31 12:00 | 2003-03-13 15:00 | 2005-07-07 10:00 | 2005-08-31 12:00 | 2004-10-28 12:00 | 2005-04-13 17:00 | 2005-04-21 17:00 | 2004-09-15 16:00 | 9617450.1245 | 3730836.8136 | 10913742.0312 | 9873244.1809 | 4154256.5289 | 3814389.1724 | 4207733.4374 | 4182343.5418 | 0.97157 | 3.0615 | 0.87087 | 0.96643 | -17 | 3.0615 | 1 | 0.97157 | 1
01/06, 2004 | 2004-05-14 17:00 | 2004-06-01 17:00 | 3139051.4751 | 2844190.2984 | 1041153.1014 | 2004-04-23 17:00 | -294861.1768 | 90.61% | 1803037.197 | 273.2% | -23d | 96.21% | 98.18% | 2005-04-19 10:00 | 2005-07-13 12:00 | 2003-04-15 12:00 | 2005-06-08 17:00 | 2005-07-13 12:00 | 2004-11-05 11:00 | 2005-04-21 17:00 | 2005-05-03 17:00 | 2004-10-08 16:00 | 9618853.1673 | 4181132.5295 | 10508115.3017 | 9956673.5466 | 4506658.5781 | 4304796.1029 | 4665591.1465 | 4648506.6693 | 0.96211 | 2.7318 | 0.90607 | 0.9818 | -23 | 2.7318 | 1 | 0.96211 | 1
07/06, 2004 | 2004-06-01 17:00 | 2004-06-07 17:00 | 3358531.6933 | 2877365.1499 | 1074161.953 | 2004-04-23 17:00 | -481166.5433 | 85.67% | 1803203.197 | 267.9% | -27d | 95.58% | 99.42% | 2005-05-06 09:00 | 2005-09-21 12:00 | 2003-05-20 12:00 | 2005-07-21 12:00 | 2005-09-21 12:00 | 2004-12-10 11:00 | 2005-04-27 17:00 | 2005-05-11 11:00 | 2004-10-18 16:00 | 9618687.1673 | 4263956.5787 | 11047542.8904 | 10013725.1481 | 4797369.0495 | 4411429.9603 | 4766198.4666 | 4734855.1757 | 0.95581 | 2.6787 | 0.85673 | 0.99417 | -27 | 2.6787 | 1 | 0.95581 | 1
13/06, 2004 | 2004-06-07 17:00 | 2004-06-13 17:00 | 3975752.7253 | 3009467.8534 | 1109112.4984 | 2004-05-07 17:00 | -966284.8718 | 75.7% | 1900355.3551 | 271.3% | -22d | 96.42% | 89.15% | 2005-06-22 12:00 | 2006-03-09 11:00 | 2003-07-15 14:00 | 2005-10-17 12:00 | 2006-03-09 11:00 | 2005-02-28 17:00 | 2005-04-20 17:00 | 2005-05-02 09:00 | 2004-10-15 15:00 | 9521535.0092 | 4209435.6793 | 12222609.4195 | 9833631.6285 | 5204892.5286 | 4324456.1008 | 4731857.8918 | 4668318.822 | 0.96423 | 2.7134 | 0.75696 | 0.89148 | -22 | 2.7134 | 1 | 0.96423 | 1
21/06, 2004 | 2004-06-13 17:00 | 2004-06-21 17:00 | 4518043.9178 | 4244857.3756 | 1372464.0621 | 2004-06-14 17:00 | -273186.5421 | 93.95% | 2872393.3135 | 309.3% | -5d | 99.19% | 93.98% | 2005-04-15 15:00 | 2005-05-31 14:00 | 2003-02-07 12:00 | 2005-05-12 12:00 | 2005-05-31 14:00 | 2004-10-19 15:00 | 2005-03-28 17:00 | 2005-03-30 11:00 | 2004-09-29 11:00 | 8549497.0507 | 3692970.7312 | 9011389.7956 | 8607752.1886 | 3842311.7188 | 3711806.0126 | 4068361.5398 | 4057787.6811 | 0.99195 | 3.0929 | 0.93953 | 0.93977 | -5 | 3.0929 | 1 | 0.99195 | 1
08/07, 2004 | 2004-06-21 17:00 | 2004-07-08 17:00 | 5136063.8857 | 4516970.172 | 1456930.4426 | 2004-06-18 17:00 | -619093.7136 | 87.95% | 3060039.7294 | 310% | -14d | 97.79% | 95.8% | 2005-05-19 14:00 | 2005-08-18 15:00 | 2003-03-05 10:00 | 2005-07-06 11:00 | 2005-08-18 15:00 | 2004-11-30 15:00 | 2005-04-08 17:00 | 2005-04-14 15:00 | 2004-10-15 15:00 | 8361850.6348 | 3684084.4969 | 9308235.6056 | 8517768.1876 | 3989337.1379 | 3734375.0723 | 4056518.827 | 4037388.7239 | 0.97792 | 3.1003 | 0.87946 | 0.95804 | -14 | 3.1003 | 1 | 0.97792 | 1
05/08, 2004 | 2004-07-08 17:00 | 2004-08-05 17:00 | 6138893.1357 | 4589736.5128 | 1779426.6272 | 2004-06-22 17:00 | -1549156.6228 | 74.76% | 2810309.8856 | 257.9% | -17d | 97.34% | 97.39% | 2005-08-17 14:00 | 2006-03-28 10:00 | 2003-08-19 14:00 | 2005-11-02 10:00 | 2006-03-28 10:00 | 2005-04-07 16:00 | 2005-04-13 17:00 | 2005-04-20 12:00 | 2004-11-09 11:00 | 8611580.4787 | 4428231.5097 | 10917611.8505 | 8798311.3717 | 5322272.7286 | 4500626.4985 | 4866711.7275 | 4804984.5147 | 0.9734 | 2.5793 | 0.74765 | 0.97385 | -17 | 2.5793 | 1 | 0.9734 | 1
19/08, 2004 | 2004-08-05 17:00 | 2004-08-19 17:00 | 6143336.3957 | 5359228.4062 | 2130513.1533 | 2004-07-09 17:00 | -784107.9895 | 87.24% | 3228715.2529 | 251.5% | -13d | 97.99% | 96.02% | 2005-06-03 17:00 | 2005-08-29 17:00 | 2003-06-11 09:00 | 2005-07-14 15:00 | 2005-08-29 17:00 | 2005-01-27 14:00 | 2005-04-07 17:00 | 2005-04-13 09:00 | 2004-11-18 10:00 | 8193175.1114 | 4540670.0018 | 9080202.3696 | 8317292.6003 | 4893299.7271 | 4590011.7955 | 4902847.3753 | 4875838.1268 | 0.97994 | 2.5155 | 0.87236 | 0.96025 | -13 | 2.5155 | 1 | 0.97994 | 1
09/09, 2004 | 2004-08-19 17:00 | 2004-09-09 17:00 | 7489932.3092 | 5676719.7204 | 2406220.726 | 2004-07-09 17:00 | -1813212.5887 | 75.79% | 3270498.9944 | 235.9% | -28d | 95.78% | 99.7% | 2005-09-12 15:00 | 2006-03-07 17:00 | 2003-10-02 14:00 | 2005-11-01 12:00 | 2006-03-07 17:00 | 2005-05-10 12:00 | 2005-04-28 17:00 | 2005-05-09 14:00 | 2004-12-16 16:00 | 8151391.3699 | 4841456.1011 | 9986468.0072 | 8404721.729 | 5619299.584 | 4948836.5586 | 5223957.9062 | 5169781.4979 | 0.95777 | 2.3592 | 0.75791 | 0.99698 | -28 | 2.3592 | 1 | 0.95777 | 1
16/09, 2004 | 2004-09-09 17:00 | 2004-09-16 17:00 | 7549460.8496 | 5796978.5202 | 2612996.8828 | 2004-07-09 17:00 | -1752482.3293 | 76.79% | 3183981.6375 | 221.9% | -33d | 95.06% | 99.7% | 2005-09-06 14:00 | 2006-02-16 14:00 | 2003-11-03 11:00 | 2005-10-25 09:00 | 2006-02-16 14:00 | 2005-05-19 10:00 | 2005-05-05 17:00 | 2005-05-17 16:00 | 2005-01-14 14:00 | 8237908.7268 | 5148434.4496 | 9938373.646 | 8530226.9801 | 5914921.5976 | 5280197.3467 | 5529896.6761 | 5475644.2915 | 0.9506 | 2.2185 | 0.76787 | 0.99698 | -33 | 2.2185 | 1 | 0.9506 | 1
24/09, 2004 | 2004-09-16 17:00 | 2004-09-24 17:00 | 8004084.4121 | 5905190.8224 | 2660787.2593 | 2004-07-09 17:00 | -2098893.5897 | 73.78% | 3244403.5631 | 221.9% | -39d | 94.21% | 99.7% | 2005-10-10 11:00 | 2006-04-17 11:00 | 2003-11-27 17:00 | 2005-11-23 15:00 | 2006-04-17 11:00 | 2005-06-20 11:00 | 2005-05-13 17:00 | 2005-05-27 10:00 | 2005-01-25 10:00 | 8177486.8012 | 5146526.382 | 10138298.1709 | 8516307.7179 | 6030037.528 | 5299193.8242 | 5529546.6818 | 5469841.7745 | 0.94214 | 2.2193 | 0.73777 | 0.99698 | -39 | 2.2193 | 1 | 0.94214 | 1
01/10, 2004 | 2004-09-24 17:00 | 2004-10-01 17:00 | 8205959.5986 | 5905190.8224 | 3304855.851 | 2004-07-09 17:00 | -2300768.7763 | 71.96% | 2600334.9714 | 178.7% | -44d | 93.52% | 99.7% | 2005-10-28 11:00 | 2006-05-24 10:00 | 2004-06-08 10:00 | 2005-12-13 11:00 | 2006-05-24 10:00 | 2005-09-12 10:00 | 2005-05-20 17:00 | 2005-06-06 12:00 | 2005-02-25 11:00 | 8821555.3929 | 6392291.5169 | 10970960.9644 | 9203814.8887 | 7595212.0986 | 6606224.067 | 6811123.2192 | 6717603.8547 | 0.9352 | 1.7868 | 0.71962 | 0.99698 | -44 | 1.7868 | 1 | 0.9352 | 1
07/10, 2004 | 2004-10-01 17:00 | 2004-10-07 17:00 | 9212381.1576 | 6955994.7071 | 3450093.5508 | 2004-08-31 17:00 | -2256386.4505 | 75.51% | 3505901.1564 | 201.6% | -27d | 96.05% | 92.05% | 2005-10-25 10:00 | 2006-03-13 17:00 | 2004-01-19 10:00 | 2005-11-10 10:00 | 2006-03-13 17:00 | 2005-07-04 12:00 | 2005-04-27 17:00 | 2005-05-05 11:00 | 2005-01-31 09:00 | 7915989.2079 | 5665126.548 | 9364637.0109 | 8099798.9377 | 6383639.2342 | 5756294.0647 | 5981845.608 | 5924227.0269 | 0.96047 | 2.0162 | 0.75507 | 0.92046 | -27 | 2.0162 | 1 | 0.96047 | 1
14/10, 2004 | 2004-10-07 17:00 | 2004-10-14 17:00 | 9487887.3988 | 7172500.8387 | 3559133.4419 | 2004-08-31 17:00 | -2315386.5601 | 75.6% | 3613367.3969 | 201.5% | -32d | 95.35% | 92.05% | 2005-10-31 11:00 | 2006-03-10 15:00 | 2004-01-16 16:00 | 2005-11-10 16:00 | 2006-03-10 15:00 | 2005-07-06 12:00 | 2005-05-04 17:00 | 2005-05-13 11:00 | 2005-02-07 14:00 | 7808522.9674 | 5667762.5948 | 9180287.1007 | 8015810.2614 | 6348458.4512 | 5770622.5535 | 5968927.0787 | 5916123.6786 | 0.95349 | 2.0152 | 0.75596 | 0.92046 | -32 | 2.0152 | 1 | 0.95349 | 1
29/10, 2004 | 2004-10-14 17:00 | 2004-10-29 17:00 | 9754945.6946 | 7445569.5943 | 3714857.258 | 2004-09-08 17:00 | -2309376.1003 | 76.33% | 3730712.3363 | 200.4% | -37d | 94.71% | 78.37% | 2005-10-28 16:00 | 2006-02-24 15:00 | 2004-01-14 15:00 | 2005-11-08 12:00 | 2006-02-24 15:00 | 2005-07-07 17:00 | 2005-05-11 17:00 | 2005-05-20 16:00 | 2005-02-18 11:00 | 7691178.028 | 5698783.9255 | 8924504.7784 | 7913419.5212 | 6314134.1378 | 5809668.0443 | 5979190.9328 | 5932761.6389 | 0.94707 | 2.0043 | 0.76326 | 0.78371 | -37 | 2.0043 | 1 | 0.94707 | 1
09/11, 2004 | 2004-10-29 17:00 | 2004-11-09 17:00 | 10046107.7185 | 7907500.2762 | 4734178.3375 | 2004-09-23 17:00 | -2138607.4423 | 78.71% | 3173321.9387 | 167% | -32d | 95.46% | 77.58% | 2005-10-13 09:00 | 2006-01-12 14:00 | 2004-05-14 16:00 | 2005-10-18 09:00 | 2006-01-12 14:00 | 2005-08-01 15:00 | 2005-05-04 17:00 | 2005-05-12 11:00 | 2005-03-07 16:00 | 8248568.4256 | 6838224.9822 | 9199045.8881 | 8415671.669 | 7407270.7813 | 6938268.8049 | 7087042.7303 | 7035433.3881 | 0.95461 | 1.6703 | 0.78712 | 0.77575 | -32 | 1.6703 | 1 | 0.95461 | 1
18/11, 2004 | 2004-11-09 17:00 | 2004-11-18 17:00 | 10332341.481 | 8070608.4989 | 4790413.6383 | 2004-09-28 17:00 | -2261732.9821 | 78.11% | 3280194.8606 | 168.5% | -34d | 95.21% | 80.83% | 2005-10-25 14:00 | 2006-01-24 10:00 | 2004-05-14 10:00 | 2005-10-25 11:00 | 2006-01-24 10:00 | 2005-08-08 16:00 | 2005-05-06 17:00 | 2005-05-16 12:00 | 2005-03-10 14:00 | 8141695.5037 | 6779610.1599 | 9080869.3873 | 8310251.1005 | 7337068.9168 | 6879658.5057 | 7018639.5676 | 6969094.9811 | 0.95211 | 1.6847 | 0.7811 | 0.8083 | -34 | 1.6847 | 1 | 0.95211 | 1
25/11, 2004 | 2004-11-18 17:00 | 2004-11-25 17:00 | 10342098.7905 | 8245368.202 | 5061248.5992 | 2004-10-04 17:00 | -2096730.5885 | 79.73% | 3184119.6028 | 162.9% | -35d | 95.1% | 81.01% | 2005-10-10 10:00 | 2005-12-26 16:00 | 2004-05-28 09:00 | 2005-10-10 17:00 | 2005-12-26 16:00 | 2005-08-02 10:00 | 2005-05-09 17:00 | 2005-05-17 12:00 | 2005-03-17 11:00 | 8237770.7615 | 7011090.9774 | 9045534.7109 | 8401268.2257 | 7506920.1578 | 7111450.5116 | 7232863.6352 | 7188141.3053 | 0.95105 | 1.6291 | 0.79726 | 0.81009 | -35 | 1.6291 | 1 | 0.95105 | 1
09/12, 2004 | 2004-11-25 17:00 | 2004-12-09 17:00 | 10408474.7788 | 8279288.3504 | 5512538.1821 | 2004-10-05 17:00 | -2129186.4284 | 79.54% | 2766750.1683 | 150.2% | -44d | 93.93% | 81.1% | 2005-10-12 12:00 | 2005-12-29 09:00 | 2004-09-02 16:00 | 2005-10-14 10:00 | 2005-12-29 09:00 | 2005-08-29 10:00 | 2005-05-20 17:00 | 2005-05-31 15:00 | 2005-04-08 11:00 | 8655140.1959 | 7604953.9622 | 9463323.8555 | 8858186.4347 | 8143060.9942 | 7740146.7586 | 7822241.5364 | 7774406.7513 | 0.93931 | 1.5019 | 0.79544 | 0.81103 | -44 | 1.5019 | 1 | 0.93931 | 1
21/12, 2004 | 2004-12-09 17:00 | 2004-12-21 17:00 | 10517686.8799 | 8355398.1707 | 5557797.7363 | 2004-10-05 17:00 | -2162288.7092 | 79.44% | 2797600.4344 | 150.3% | -52d | 92.91% | 81.1% | 2005-10-14 15:00 | 2005-12-30 11:00 | 2004-09-03 09:00 | 2005-10-18 15:00 | 2005-12-30 11:00 | 2005-09-01 12:00 | 2005-06-01 17:00 | 2005-06-13 17:00 | 2005-04-21 09:00 | 8624289.9298 | 7597550.1243 | 9417865.689 | 8858442.0503 | 8125416.477 | 7753302.1422 | 7809963.6186 | 7766284.6536 | 0.92906 | 1.5034 | 0.79441 | 0.81103 | -52 | 1.5034 | 1 | 0.92906 | 1
13/01, 2005 | 2004-12-21 17:00 | 2005-01-13 17:00 | 11186199.6924 | 10237942.5257 | 6763672.7997 | 2004-11-16 17:00 | -948257.1667 | 91.52% | 3474269.7261 | 151.4% | -31d | 95.81% | 92.09% | 2005-06-21 10:00 | 2005-06-30 15:00 | 2004-03-30 11:00 | 2005-06-16 14:00 | 2005-06-30 15:00 | 2005-05-05 09:00 | 2005-05-03 17:00 | 2005-05-09 11:00 | 2005-03-30 15:00 | 7947620.6382 | 7545845.1719 | 8057280.0761 | 7999460.1622 | 7618291.4232 | 7580092.8322 | 7613002.6364 | 7607816.3805 | 0.95805 | 1.5137 | 0.91523 | 0.92094 | -31 | 1.5137 | 1 | 0.95805 | 1
20/01, 2005 | 2005-01-13 17:00 | 2005-01-20 17:00 | 11186199.6924 | 10417987.6493 | 7247868.4651 | 2004-12-10 17:00 | -768212.0431 | 93.13% | 3170119.1841 | 143.7% | -18d | 97.58% | 92.93% | 2005-06-02 16:00 | 2005-06-09 17:00 | 2004-04-29 09:00 | 2005-06-01 09:00 | 2005-06-09 17:00 | 2005-04-28 12:00 | 2005-04-14 17:00 | 2005-04-18 12:00 | 2005-03-22 15:00 | 8251771.1801 | 7946290.7589 | 8325797.9674 | 8276661.3301 | 7997791.7239 | 7963607.0141 | 7999194.7254 | 7994225.4588 | 0.97581 | 1.4374 | 0.93133 | 0.92929 | -18 | 1.4374 | 1 | 0.97581 | 1
28/01, 2005 | 2005-01-20 17:00 | 2005-01-28 17:00 | 11186199.6924 | 10496322.8914 | 7316997.847 | 2004-12-17 17:00 | -689876.8009 | 93.83% | 3179325.0445 | 143.5% | -19d | 97.47% | 93.42% | 2005-05-26 12:00 | 2005-06-01 14:00 | 2004-04-23 16:00 | 2005-05-25 10:00 | 2005-06-01 14:00 | 2005-04-26 09:00 | 2005-04-15 17:00 | 2005-04-19 11:00 | 2005-03-25 11:00 | 8242565.3198 | 7962211.9163 | 8303398.7692 | 8266622.4771 | 8004618.9785 | 7978982.1862 | 8010163.8432 | 8006411.4393 | 0.97467 | 1.4345 | 0.93833 | 0.93422 | -19 | 1.4345 | 1 | 0.97467 | 1
03/02, 2005 | 2005-01-28 17:00 | 2005-02-03 17:00 | 11186199.6924 | 10510550.9212 | 7437030.7947 | 2004-12-17 17:00 | -675648.7712 | 93.96% | 3073520.1265 | 141.3% | -23d | 96.95% | 93.56% | 2005-05-25 12:00 | 2005-05-31 12:00 | 2004-05-06 16:00 | 2005-05-24 12:00 | 2005-05-31 12:00 | 2005-04-27 11:00 | 2005-04-21 17:00 | 2005-04-25 15:00 | 2005-04-01 09:00 | 8348370.2377 | 8081874.2052 | 8406953.7867 | 8377044.3926 | 8123326.6144 | 8102163.396 | 8128205.0234 | 8125084.8673 | 0.9695 | 1.4133 | 0.9396 | 0.93558 | -23 | 1.4133 | 1 | 0.9695 | 1
10/02, 2005 | 2005-02-03 17:00 | 2005-02-10 17:00 | 11186199.6924 | 10823679.0818 | 8646408.0067 | 2004-12-23 17:00 | -362520.6106 | 96.76% | 2177271.0751 | 125.2% | -24d | 96.84% | 96.55% | 2005-04-25 17:00 | 2005-04-27 11:00 | 2004-08-20 16:00 | 2005-04-25 14:00 | 2005-04-27 11:00 | 2005-04-12 14:00 | 2005-04-22 17:00 | 2005-04-26 14:00 | 2005-04-12 09:00 | 9244619.2892 | 9124284.2245 | 9264655.3525 | 9264152.7188 | 9140289.8708 | 9139888.3459 | 9147016.5454 | 9146950.5901 | 0.96838 | 1.2518 | 0.96759 | 0.96553 | -24 | 1.2518 | 1 | 0.96838 | 1
18/02, 2005 | 2005-02-10 17:00 | 2005-02-18 17:00 | 11186199.6924 | 10931882.1414 | 10048717.6545 | 2004-12-23 17:00 | -254317.551 | 97.73% | 883164.4869 | 108.8% | -30d | 96.08% | 97.58% | 2005-04-14 12:00 | 2005-04-15 10:00 | 2005-01-14 10:00 | 2005-04-14 11:00 | 2005-04-15 10:00 | 2005-04-12 09:00 | 2005-05-02 17:00 | 2005-05-05 09:00 | 2005-04-28 15:00 | 10538725.8774 | 10499139.1113 | 10550125.35 | 10558726.213 | 10509617.6438 | 10517523.6606 | 10508489.603 | 10509915.9781 | 0.96078 | 1.0879 | 0.97727 | 0.97582 | -30 | 1.0879 | 1 | 0.96078 | 1
31/03, 2005 | 2005-02-18 17:00 | 2005-03-31 17:00 | 11421890.3643 | 11421890.3643 | 15218926.3789 | 2005-03-21 17:00 | 0 | 100% | -3797036.0146 | 75.05% | -8d | 98.99% | 100% | 2005-03-21 17:00 | 2005-03-21 17:00 | 2006-03-22 10:00 | 2005-03-31 17:00 | 2005-03-31 17:00 | 2005-03-31 17:00 | 2005-03-31 17:00 | 2005-03-31 17:00 | 2005-03-31 17:00 | 15218926.3789 | 15218926.3789 | 15218926.3789 | 15218926.3789 | 15218926.3789 | 15218926.3789 | 15218926.3789 | 15218926.3789 | 0.98992 | 0.75051 | 1 | 1 | -8 | 0.75051 | 1 | 0.98992 | 1