## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Building a Dream | 1 |  |  | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 | 200.2917
1 | Soil Research | 1.1 |  | FS2+4d;FS3 | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 0.375
2 | Calculations | 1.2 | 1FS+4d | FS4 | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 4.375
3 | Building site preparation | 1.3 | 1FS | FS4 | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 0.375
4 | Building foundation | 1.4 | 2FS;3FS | SS5+2d;FS6 | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 9.1667
5 | Sewerage & drainage system | 1.5 | 4SS+2d | FS6 | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 1.9583
6 | Building groundfloor | 1.6 | 4FS;5FS | FS7;FS8 | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 8.375
7 | Building first floor | 1.7 | 6FS | SS11;FS12 | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 8.375
8 | Test jointing | 1.8 | 6FS | SS9+1d | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 0.125
9 | Choosing joint type | 1.9 | 8SS+1d | FS10+1w | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 0.083333
10 | Jointing | 1.10 | 13FS;9FS+1w | FS33 | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 8.0833
11 | Scaffolding | 1.11 | 7SS | FS12 | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 4.1667
12 | Building roof framework | 1.12 | 7FS;11FS | FS13 | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 12.9583
13 | Roof covering | 1.13 | 12FS | FS10;FS14;FS15;FS17 | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 17.9583
14 | Electricity | 1.14 | 13FS | FS16;FS28 | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 5.875
15 | Sanitary | 1.15 | 13FS | FS16 | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 5.9583
16 | Placing windows | 1.16 | 14FS;15FS | FS18 | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 5.875
17 | Underfloor heating | 1.17 | 13FS | FS18 | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 5.1667
18 | Laying floor screed | 1.18 | 16FS;17FS | FS19+4w;FS20+4w | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 6.2083
19 | Configurating underfloor heating | 1.19 | 18FS+4w | FS21+2w | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 0.875
20 | Plastering | 1.20 | 18FS+4w | FS21;FS23+3d | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 21
21 | Floor tiling | 1.21 | 20FS;19FS+2w | FS22+1d;FS23+1d | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 9.7917
22 | Carpenting | 1.22 | 21FS+1d | FS23 | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 3.2917
23 | Painting | 1.23 | 20FS+3d;21FS+1d;22FS | FS24;FS28;FS29 | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 13.375
24 | Finishing up | 1.24 | 23FS | FS25;FS26 | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 | 3.375
25 | Installation of kitchen | 1.25 | 24FS | FS27 | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 | 1.375
26 | Installation of bathroom | 1.26 | 24FS | FS27 | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 | 2.375
27 | Cleaning up | 1.27 | 25FS;26FS | FS29;FS32 | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 | 3.2917
28 | Installation solar panels | 1.28 | 14FS;23FS | FS33 | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 | 3.375
29 | Garden site preparation | 1.29 | 23FS;27FS | FS30;FS31 | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 | 2
30 | Garden landscaping | 1.30 | 29FS | FS33 | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 | 8
31 | Terrace construction | 1.31 | 29FS | FS33 | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 | 5
32 | Moving of furniture | 1.32 | 27FS | FS33 | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 | 2
33 | Final inspection | 1.33 | 10FS;28FS;30FS;31FS;32FS |  | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 1

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Concrete Mixer | Renewable | 1 CM | 0 | 15 | 4[0.67 Concrete Mixer];6;7;10[0.80 Concrete Mixer];18[0.67 Concrete Mixer]; | 3240
2 | Cement Mason | Renewable | 2 | 0 | 45 | 3;4[0.67 Cement Mason];5;6[2.00 Cement Mason];7[2.00 Cement Mason];8[1.33 Cement Mason];9[2.00 Cement Mason];10[1.60 Cement Mason];18[0.67 Cement Mason]; | 18000
3 | Carpenter | Renewable | 2 | 0 | 40 | 22[1.60 Carpenter];24[2.00 Carpenter]; | 3200
4 | Labourer | Renewable | 3 | 0 | 30 | 3[3.00 Labourer];4[2.00 Labourer];5[3.00 Labourer];6[3.00 Labourer];7[3.00 Labourer];10[0.80 Labourer];11[1.60 Labourer];12[0.67 Labourer];13;16[2.40 Labourer];17[0.57 Labourer];18[2.00 Labourer];20[2.00 Labourer];21[2.00 Labourer];24[2.00 Labourer];27[1.71 Labourer]; | 40080
5 | Crane | Renewable | 1 CR | 0 | 125 | 5;6;7;13; | 30000
6 | Painter | Renewable | 2 | 0 | 60 | 23[2.00 Painter]; | 9600
7 | Digger | Renewable | 1 DI | 0 | 70 | 3;4[0.67 Digger];5; | 4480
8 | Roofer | Renewable | 2 | 0 | 45 | 12[1.33 Roofer];13[2.00 Roofer]; | 14400
9 | Plumber | Renewable | 2 | 0 | 50 | 15[2.00 Plumber];17[0.57 Plumber];19[0.67 Plumber];24[2.00 Plumber]; | 5800
10 | Electrician | Renewable | 2 | 0 | 50 | 14[1.60 Electrician];24[2.00 Electrician]; | 4000

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Building a Dream | 1158h |  |  |  |  | 99 | 100 | 101
1 | Soil Research | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Calculations | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Building site preparation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Building foundation | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Sewerage & drainage system | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Building groundfloor | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Building first floor | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Test jointing | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Choosing joint type | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Jointing | 50h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Scaffolding | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Building roof framework | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Roof covering | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Electricity | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Sanitary | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Placing windows | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Underfloor heating | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Laying floor screed | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Configurating underfloor heating | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Plastering | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Floor tiling | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Carpenting | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Painting | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Finishing up | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Installation of kitchen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Installation of bathroom | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Cleaning up | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Installation solar panels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Garden site preparation | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Garden landscaping | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Terrace construction | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Moving of furniture | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Final inspection | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-03-08 17:00 |  | TP Name | 8/03/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 5d | [5 empty] | 2490 |  | 1.033% |  | 2490 | 2490
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 |  | 0 | 0 | 1210 | 5d | 0 | 0 | 0 | 1210 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 |  | 0 | 0 | 11800.0002 | 7d 4h | 0 | 0 | 0 | 11800.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 |  | 0 | 0 | 5280 | 2d | 0 | 0 | 0 | 5280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 |  | 0 | 0 | 23920 | 7d | 0 | 0 | 0 | 23920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 |  | 0 | 0 | 24920 | 7d | 0 | 0 | 0 | 24920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 |  | 0 | 0 | 180 | 3h | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 |  | 0 | 0 | 2180 | 2h | 0 | 0 | 0 | 2180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 |  | 0 | 0 | 1210 | 2d 4h | 0 | 0 | 0 | 1210 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-03-15 17:00 |  | TP Name | 15/03/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 10d | [5 empty] | 3700 |  | 1.535% |  | 3700 | 3700
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 4d 6h | 1210 | 0 | 3d 7h | 0 | 0 | 1210 | 0 | 55.07% | Started | 1210 | 1210 | 100 | 95 | 55.0725 | 100 | 100 | 55.0725
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 |  | 0 | 0 | 11800.0002 | 7d 4h | 0 | 0 | 0 | 11800.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 |  | 0 | 0 | 5280 | 2d | 0 | 0 | 0 | 5280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 |  | 0 | 0 | 23920 | 7d | 0 | 0 | 0 | 23920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 |  | 0 | 0 | 24920 | 7d | 0 | 0 | 0 | 24920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 |  | 0 | 0 | 180 | 3h | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 |  | 0 | 0 | 2180 | 2h | 0 | 0 | 0 | 2180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 |  | 0 | 0 | 1210 | 2d 4h | 0 | 0 | 0 | 1210 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-03-22 17:00 |  | TP Name | 22/03/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 15d | [5 empty] | 8020 |  | 3.087% |  | 7440.187 | 12566.6668
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 1d 1h | 4320 | 14373.3336 | 12d 2h | 0 | 0 | 4320 | 14373.3336 | 8.411% | Started | 3740.187 | 8866.6668 | 100 | 15 | 8.4112 | 100 | 36.6102 | 8.4112
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 |  | 0 | 0 | 5280 | 2d | 0 | 0 | 0 | 5280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 |  | 0 | 0 | 23920 | 7d | 0 | 0 | 0 | 23920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 |  | 0 | 0 | 24920 | 7d | 0 | 0 | 0 | 24920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 |  | 0 | 0 | 180 | 3h | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 |  | 0 | 0 | 2180 | 2h | 0 | 0 | 0 | 2180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 |  | 0 | 0 | 1210 | 2d 4h | 0 | 0 | 0 | 1210 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-03-29 17:00 |  | TP Name | 29/03/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 20d | [5 empty] | 22796.6668 |  | 6.643% |  | 16009.9065 | 20780.0002
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 6d 1h | 10186.6668 | 8506.6668 | 7d 2h | 0 | 0 | 10186.6668 | 8506.6668 | 45.79% | Started | 7029.9065 | 11800.0002 | 100 | 81.6667 | 45.7944 | 100 | 86.3277 | 45.7944
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 |  | 0 | 0 | 23920 | 7d | 0 | 0 | 0 | 23920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 |  | 0 | 0 | 24920 | 7d | 0 | 0 | 0 | 24920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 |  | 0 | 0 | 180 | 3h | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 |  | 0 | 0 | 2180 | 2h | 0 | 0 | 0 | 2180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 |  | 0 | 0 | 1210 | 2d 4h | 0 | 0 | 0 | 1210 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-04-05 17:00 |  | TP Name | 5/04/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 25d | [5 empty] | 28663.3336 |  | 8.008% |  | 19299.6265 | 39580.0002
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 11d 1h | 16053.3336 | 2640 | 2d 2h | 0 | 0 | 16053.3336 | 2640 | 83.18% | Started | 10319.6265 | 11800.0002 | 100 | 148.3333 | 83.1776 | 100 | 136.0452 | 83.1776
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 |  | 0 | 0 | 23920 | 7d | 0 | 0 | 0 | 23920 | 0% | Not Started | 0 | 18800 | 100 |  | 0 | 100 |  | 0
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 |  | 0 | 0 | 24920 | 7d | 0 | 0 | 0 | 24920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 |  | 0 | 0 | 180 | 3h | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 |  | 0 | 0 | 2180 | 2h | 0 | 0 | 0 | 2180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 |  | 0 | 0 | 1210 | 2d 4h | 0 | 0 | 0 | 1210 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-04-12 17:00 |  | TP Name | 12/04/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 30d | [5 empty] | 44343.3336 |  | 13.55% |  | 32664.1792 | 59380.0002
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 2d 6h | 13040 | 14400 | 5d 5h | 0 | 0 | 13040 | 14400 | 32.84% | Started | 11884.179 | 23920 | 100 | 39.2857 | 32.8358 | 100 | 54.5151 | 32.8358
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 |  | 0 | 0 | 24920 | 7d | 0 | 0 | 0 | 24920 | 0% | Not Started | 0 | 14680 | 100 |  | 0 | 100 |  | 0
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 |  | 0 | 0 | 180 | 3h | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 |  | 0 | 0 | 2180 | 2h | 0 | 0 | 0 | 2180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 |  | 0 | 0 | 1210 | 2d 4h | 0 | 0 | 0 | 1210 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-04-19 17:00 |  | TP Name | 19/04/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 35d | [5 empty] | 57143.3336 |  | 17.99% |  | 43362.6868 | 70434.0002
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 7d 6h | 25840 | 1600 | 5h | 0 | 0 | 25840 | 1600 | 92.54% | Started | 22582.6866 | 23920 | 100 | 110.7143 | 92.5373 | 100 | 108.0268 | 92.5373
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 |  | 0 | 0 | 24920 | 7d | 0 | 0 | 0 | 24920 | 0% | Not Started | 0 | 24920 | 100 |  | 0 | 100 |  | 0
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 |  | 0 | 0 | 180 | 3h | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 180 | 100 |  | 0 | 100 |  | 0
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 |  | 0 | 0 | 2180 | 2h | 0 | 0 | 0 | 2180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 |  | 0 | 0 | 1210 | 2d 4h | 0 | 0 | 0 | 1210 | 0% | Not Started | 0 | 634 | 100 |  | 0 | 100 |  | 0
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2013-04-26 17:00 |  | TP Name | 26/04/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 40d | [5 empty] | 81347.3336 |  | 25.7% |  | 61942.3403 | 75430.0002
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 4d 3h | 18200 | 18880 | 7d 3h | 0 | 0 | 18200 | 18880 | 37.23% | Started | 13672.3402 | 24920 | 100 | 62.5 | 37.234 | 100 | 73.0337 | 37.234
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 2240.0001 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2013-05-03 17:00 |  | TP Name | 3/05/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 45d | [5 empty] | 94147.3336 |  | 28.86% |  | 69567.8729 | 78630.0003
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 9d 3h | 31000 | 6080 | 2d 3h | 0 | 0 | 31000 | 6080 | 79.79% | Started | 21297.8728 | 24920 | 100 | 133.9286 | 79.7872 | 100 | 124.3981 | 79.7872
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 |  | 0 | 0 | 5760.0002 | 9d | 0 | 0 | 0 | 5760.0002 | 0% | Not Started | 0 | 5440.0002 | 100 |  | 0 | 100 |  | 0
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2013-05-10 17:00 |  | TP Name | 10/05/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 50d | [5 empty] | 101907.3337 |  | 30.85% |  | 74342.0002 | 102770.0003
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 2d 5h | 1680.0001 | 6720.0002 | 10d 4h | 0 | 0 | 1680.0001 | 6720.0002 | 20% | Started | 1152.0001 | 5760.0002 | 100 | 29.1667 | 20 | 100 | 29.1667 | 20
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 23820 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2013-05-17 17:00 |  | TP Name | 17/05/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 55d | [5 empty] | 105107.3338 |  | 31.76% |  | 76536.2861 | 112570.0003
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 7d 5h | 4880.0001 | 3520.0001 | 5d 4h | 0 | 0 | 4880.0001 | 3520.0001 | 58.1% | Started | 3346.286 | 5760.0002 | 100 | 84.7222 | 58.0952 | 100 | 84.7222 | 58.0952
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 33620 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2013-05-24 17:00 |  | TP Name | 24/05/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 60d | [5 empty] | 108307.3339 |  | 32.67% |  | 78730.5718 | 126860.0004
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 12d 5h | 8080.0002 | 320 | 4h | 0 | 0 | 8080.0002 | 320 | 96.19% | Started | 5540.5716 | 5760.0002 | 100 | 140.2778 | 96.1905 | 100 | 140.2778 | 96.1905
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 |  | 0 | 0 | 42440 | 14d | 0 | 0 | 0 | 42440 | 0% | Not Started | 0 | 42440 | 100 |  | 0 | 100 |  | 0
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 570 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 4900 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2013-05-31 17:00 |  | TP Name | 31/05/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 65d | [5 empty] | 132447.3339 |  | 41.21% |  | 99318.6959 | 138652.5719
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 4d 4h | 23820 | 36260 | 18d 4h | 0 | 0 | 23820 | 36260 | 19.57% | Started | 20368.6956 | 42440 | 100 | 32.1429 | 19.5652 | 100 | 56.1263 | 19.5652
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 2650 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 7700 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 3864 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 3048.5715 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2013-06-07 17:00 |  | TP Name | 7/06/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 70d | [5 empty] | 142247.3339 |  | 43.68% |  | 105283.9131 | 145880.0006
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 9d 4h | 33620 | 26460 | 13d 4h | 0 | 0 | 33620 | 26460 | 41.3% | Started | 26333.9128 | 42440 | 100 | 67.8571 | 41.3043 | 100 | 79.2177 | 41.3043
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 2650 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 7700 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 5160.0001 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 3780.0001 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 5200 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2013-06-14 17:00 |  | TP Name | 14/06/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 75d | [5 empty] | 152047.3339 |  | 46.16% |  | 111249.1316 | 150088.0006
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 2808 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 14d 4h | 43420 | 16660 | 8d 4h | 0 | 0 | 43420 | 16660 | 63.04% | Started | 32299.1312 | 42440 | 100 | 103.5714 | 63.0435 | 100 | 102.3091 | 63.0435
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 2650 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 7700 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 5160.0001 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 3780.0001 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 6600 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2013-06-21 17:00 |  | TP Name | 21/06/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 80d | [5 empty] | 161847.3339 |  | 48.63% |  | 117214.3475 | 152680.0006
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 |  | 0 | 0 | 5400.0001 | 6d 2h | 0 | 0 | 0 | 5400.0001 | 0% | Not Started | 0 | 5400.0001 | 100 |  | 0 | 100 |  | 0
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 19d 4h | 53220 | 6860 | 3d 4h | 0 | 0 | 53220 | 6860 | 84.78% | Started | 38264.3472 | 42440 | 100 | 139.2857 | 84.7826 | 100 | 125.4006 | 84.7826
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 |  | 0 | 0 | 2650 | 3d 6h | 0 | 0 | 0 | 2650 | 0% | Not Started | 0 | 2650 | 100 |  | 0 | 100 |  | 0
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 |  | 0 | 0 | 7700 | 4d | 0 | 0 | 0 | 7700 | 0% | Not Started | 0 | 7700 | 100 |  | 0 | 100 |  | 0
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 5160.0001 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 |  | 0 | 0 | 3780.0001 | 3d 4h | 0 | 0 | 0 | 3780.0001 | 0% | Not Started | 0 | 3780.0001 | 100 |  | 0 | 100 |  | 0
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 6600 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2013-06-28 17:00 |  | TP Name | 28/06/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 85d | [5 empty] | 179961.9054 |  | 54.41% |  | 131140.8968 | 152680.0006
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 1d 4h | 1296 | 6480.0001 | 7d 4h | 0 | 0 | 1296 | 6480.0001 | 16.67% | Started | 900 | 5400.0001 | 100 | 24 | 16.6667 | 100 | 24 | 16.6667
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 1d 4h | 1210 | 3120 | 4d 7h | 0 | 0 | 1210 | 3120 | 23.53% | Started | 814.7059 | 2650 | 100 | 40 | 23.5294 | 100 | 45.6604 | 23.5294
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 1d 4h | 5700 | 5100 | 6d 3h | 0 | 0 | 5700 | 5100 | 19.05% | Started | 5109.5238 | 7700 | 100 | 37.5 | 19.0476 | 100 | 74.026 | 19.0476
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 5160.0001 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 1d 4h | 3048.5715 | 1097.1429 | 3d | 0 | 0 | 3048.5715 | 1097.1429 | 33.33% | Started | 2926.6667 | 3780.0001 | 100 | 42.8571 | 33.3333 | 100 | 80.65 | 33.3333
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 6600 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2013-07-05 17:00 |  | TP Name | 5/07/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 90d | [5 empty] | 192499.0484 |  | 57.62% |  | 138861.2703 | 152680.0006
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 6d 4h | 5616.0001 | 2160 | 2d 4h | 0 | 0 | 5616.0001 | 2160 | 72.22% | Started | 3900 | 5400.0001 | 100 | 104 | 72.2222 | 100 | 104 | 72.2222
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 6d 4h | 9700 | 1100 | 1d 3h | 0 | 0 | 9700 | 1100 | 82.54% | Started | 7141.2699 | 7700 | 100 | 162.5 | 82.5397 | 100 | 125.974 | 82.5397
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 |  | 0 | 0 | 5160.0001 | 3d 6h | 0 | 0 | 0 | 5160.0001 | 0% | Not Started | 0 | 5160.0001 | 100 |  | 0 | 100 |  | 0
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 6600 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2013-07-12 17:00 |  | TP Name | 12/07/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 95d | [5 empty] | 200847.0485 |  | 60.2% |  | 145101.8873 | 154540.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 3d 5h | 5088.0001 | 1728.0001 | 3d | 0 | 0 | 5088.0001 | 1728.0001 | 54.72% | Started | 4181.8868 | 5160.0001 | 100 | 96.6667 | 54.717 | 100 | 98.6047 | 54.717
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 4d 4h | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 6600 | 100 |  | 0 | 100 |  | 0
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 1660 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2013-07-19 17:00 |  | TP Name | 19/07/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 100d | [5 empty] | 207175.0486 |  | 62.26% |  | 150056.2718 | 156940.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 2d | 4600 | 4300.0001 | 5d 3h | 0 | 0 | 4600 | 4300.0001 | 27.12% | Started | 3976.2712 | 6600 | 100 | 44.4444 | 27.1186 | 100 | 69.697 | 27.1186
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 4060 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2013-07-26 17:00 |  | TP Name | 26/07/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 105d | [5 empty] | 211175.0486 |  | 63.27% |  | 152496.9498 | 159340.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d | 8600.0001 | 300 | 3h | 0 | 0 | 8600.0001 | 300 | 94.92% | Started | 6416.9491 | 6600 | 100 | 155.5556 | 94.9153 | 100 | 130.303 | 94.9153
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 6460 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2013-08-02 17:00 |  | TP Name | 2/08/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 110d | [5 empty] | 211475.0487 |  | 63.35% |  | 152680.0006 | 162997.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 7300 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 2817 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2013-08-09 17:00 |  | TP Name | 9/08/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 115d | [5 empty] | 211475.0487 |  | 63.35% |  | 152680.0006 | 165037.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 7300 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 4857 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2013-08-16 17:00 |  | TP Name | 16/08/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 120d | [5 empty] | 211475.0487 |  | 63.35% |  | 152680.0006 | 167917.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 7300 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 4857 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 1920 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 960 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2013-08-23 17:00 |  | TP Name | 23/08/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 125d | [5 empty] | 211475.0487 |  | 63.35% |  | 152680.0006 | 172717.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 6h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200 | 100 |  | 0 | 100 |  | 0
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 |  | 0 | 0 | 7300 | 15d | 0 | 0 | 0 | 7300 | 0% | Not Started | 0 | 7300 | 100 |  | 0 | 100 |  | 0
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 4857 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 1920 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 5760 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2013-08-30 17:00 |  | TP Name | 30/08/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 130d | [5 empty] | 214061.7153 |  | 64.25% |  | 154856.0569 | 191277.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 4d 5h | 2320 | 6300 | 13d 1h | 0 | 0 | 2320 | 6300 | 26.06% | Started | 1976.0563 | 7300 | 100 | 30.8333 | 26.0563 | 100 | 31.7808 | 26.0563
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 4857 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 1920 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 9600 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 2720 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2013-09-06 17:00 |  | TP Name | 6/09/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 135d | [5 empty] | 216461.7153 |  | 65.09% |  | 156884.2258 | 221408.4293
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 9d 5h | 4720 | 3900 | 8d 1h | 0 | 0 | 4720 | 3900 | 54.23% | Started | 4004.2252 | 7300 | 100 | 64.1667 | 54.2253 | 100 | 64.6575 | 54.2253
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 4857 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 1920 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 9600 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 411.4286 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2013-09-13 17:00 |  | TP Name | 13/09/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 140d | [5 empty] | 218861.7153 |  | 65.93% |  | 158912.3951 | 240915.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 14d 5h | 7120 | 1500 | 3d 1h | 0 | 0 | 7120 | 1500 | 82.39% | Started | 6032.3945 | 7300 | 100 | 97.5 | 82.3944 | 100 | 97.5342 | 82.3944
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 |  | 0 | 0 | 4857 | 7d 4h | 0 | 0 | 0 | 4857 | 0% | Not Started | 0 | 4857 | 100 |  | 0 | 100 |  | 0
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 1920 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 9600 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP29
| TP Status Date | 2013-09-20 17:00 |  | TP Name | 20/09/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 145d | [5 empty] | 222518.7153 |  | 67.17% |  | 161898.5391 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 1d 7h | 2157 | 6120 | 12d 6h | 0 | 0 | 2157 | 6120 | 12.82% | Started | 1718.5385 | 4857 | 100 | 25 | 12.8205 | 100 | 44.4101 | 12.8205
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 1920 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 9600 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP30
| TP Status Date | 2013-09-27 17:00 |  | TP Name | 27/09/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 150d | [5 empty] | 224918.7153 |  | 67.68% |  | 163129.3084 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 6d 7h | 4557 | 3720 | 7d 6h | 0 | 0 | 4557 | 3720 | 47.01% | Started | 2949.3077 | 4857 | 100 | 91.6667 | 47.0085 | 100 | 93.8233 | 47.0085
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 1920 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 9600 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP31
| TP Status Date | 2013-10-04 17:00 |  | TP Name | 4/10/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 155d | [5 empty] | 227318.7153 |  | 68.19% |  | 164360.0776 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 11d 7h | 6957 | 1320 | 2d 6h | 0 | 0 | 6957 | 1320 | 81.2% | Started | 4180.077 | 4857 | 100 | 158.3333 | 81.1966 | 100 | 143.2366 | 81.1966
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 |  | 0 | 0 | 1920 | 3d 6h | 0 | 0 | 0 | 1920 | 0% | Not Started | 0 | 1920 | 100 |  | 0 | 100 |  | 0
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 9600 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP32
| TP Status Date | 2013-10-11 17:00 |  | TP Name | 11/10/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 160d | [5 empty] | 229278.7153 |  | 68.62% |  | 165373.8428 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 1d 2h | 640 | 3008 | 5d 7h | 0 | 0 | 640 | 3008 | 17.54% | Started | 336.8421 | 1920 | 100 | 33.3333 | 17.5439 | 100 | 33.3333 | 17.5439
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 9600 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP33
| TP Status Date | 2013-10-18 17:00 |  | TP Name | 18/10/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 165d | [5 empty] | 231838.7154 |  | 69.17% |  | 166721.2112 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 6d 2h | 3200 | 448 | 7h | 0 | 0 | 3200 | 448 | 87.72% | Started | 1684.2105 | 1920 | 100 | 166.6667 | 87.7193 | 100 | 166.6667 | 87.7193
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 |  | 0 | 0 | 9600 | 10d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 9600 | 100 |  | 0 | 100 |  | 0
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP34
| TP Status Date | 2013-10-25 17:00 |  | TP Name | 25/10/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 170d | [5 empty] | 236246.7154 |  | 70.22% |  | 169236.1373 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 100% | Finished | 1920 | 1920 | 100 | 190 | 100 | 100 | 190 | 100
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 4d 1h | 3960 | 12720 | 13d 2h | 0 | 0 | 3960 | 12720 | 23.74% | Started | 2279.1367 | 9600 | 100 | 41.25 | 23.741 | 100 | 41.25 | 23.741
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP35
| TP Status Date | 2013-11-01 17:00 |  | TP Name | 1/11/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 175d | [5 empty] | 241046.7154 |  | 71.36% |  | 171998.7274 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 100% | Finished | 1920 | 1920 | 100 | 190 | 100 | 100 | 190 | 100
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 9d 1h | 8760 | 7920 | 8d 2h | 0 | 0 | 8760 | 7920 | 52.52% | Started | 5041.7267 | 9600 | 100 | 91.25 | 52.518 | 100 | 91.25 | 52.518
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP36
| TP Status Date | 2013-11-08 17:00 |  | TP Name | 8/11/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 180d | [5 empty] | 245846.7154 |  | 72.51% |  | 174761.3174 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 100% | Finished | 1920 | 1920 | 100 | 190 | 100 | 100 | 190 | 100
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 14d 1h | 13560 | 3120 | 3d 2h | 0 | 0 | 13560 | 3120 | 81.29% | Started | 7804.3167 | 9600 | 100 | 141.25 | 81.295 | 100 | 141.25 | 81.295
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 |  | 0 | 0 | 5440 | 2d | 0 | 0 | 0 | 5440 | 0% | Not Started | 0 | 5440 | 100 |  | 0 | 100 |  | 0
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 |  | 0 | 0 | 12000 | 2d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000 | 100 |  | 0 | 100 |  | 0
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP37
| TP Status Date | 2013-11-15 17:00 |  | TP Name | 15/11/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 185d | [5 empty] | 265726.7154 |  | 79.9% |  | 192565.4217 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 100% | Finished | 1920 | 1920 | 100 | 190 | 100 | 100 | 190 | 100
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 17d 3h | 16680 | 0 | 0 | 0 | 0 | 16680 | 0 | 100% | Finished | 9600 | 9600 | 100 | 173.75 | 100 | 100 | 173.75 | 100
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 | 2013-11-14 10:00 | 1d 6h | 4760 | 1700 | 5h | 0 | 0 | 4760 | 1700 | 73.68% | Started | 4008.421 | 5440 | 100 | 87.5 | 73.6842 | 100 | 87.5 | 73.6842
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 |  | 0 | 0 | 19000 | 2d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 19000 | 100 |  | 0 | 100 |  | 0
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 |  | 0 | 0 | 8000 | 3d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 8000 | 100 |  | 0 | 100 |  | 0
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 |  | 0 | 0 | 720 | 1d 6h | 0 | 0 | 0 | 720 | 0% | Not Started | 0 | 720 | 100 |  | 0 | 100 |  | 0
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 | 2013-11-14 10:00 | 1d 6h | 12000 | 0 | 1d 6h | 0 | 0 | 12000 | 0 | 50% | Started | 12000 | 12000 | 100 | 87.5 | 50 | 100 | 100 | 50
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP38
| TP Status Date | 2013-11-22 17:00 |  | TP Name | 22/11/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 190d | [5 empty] | 294735.2868 |  | 91.78% |  | 221193.3643 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 100% | Finished | 1920 | 1920 | 100 | 190 | 100 | 100 | 190 | 100
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 17d 3h | 16680 | 0 | 0 | 0 | 0 | 16680 | 0 | 100% | Finished | 9600 | 9600 | 100 | 173.75 | 100 | 100 | 173.75 | 100
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 | 2013-11-14 10:00 | 2d 3h | 6460 | 0 | 0 | 0 | 0 | 6460 | 0 | 100% | Finished | 5440 | 5440 | 100 | 118.75 | 100 | 100 | 118.75 | 100
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 | 2013-11-18 14:00 | 3d 5h | 19000 | 0 | 0 | 0 | 0 | 19000 | 0 | 100% | Finished | 19000 | 19000 | 100 | 181.25 | 100 | 100 | 100 | 100
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 | 2013-11-18 14:00 | 3d 1h | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 100% | Finished | 8000 | 8000 | 100 | 104.1667 | 100 | 100 | 100 | 100
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 | 2013-11-22 10:00 | 6h | 308.5714 | 822.8572 | 2d | 0 | 0 | 308.5714 | 822.8572 | 27.27% | Started | 196.3636 | 720 | 100 | 42.8571 | 27.2727 | 100 | 42.8571 | 27.2727
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 | 2013-11-14 10:00 | 3d 4h | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 100% | Finished | 12000 | 12000 | 100 | 175 | 100 | 100 | 100 | 100
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 |  | 0 | 0 | 2500 | 2d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 |  | 0 | 0 | 198 | 2d | 0 | 0 | 0 | 198 | 0% | Not Started | 0 | 198 | 100 |  | 0 | 100 |  | 0
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP39
| TP Status Date | 2013-11-29 17:00 |  | TP Name | 29/11/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 195d | [5 empty] | 298256.144 |  | 93.11% |  | 224415.0007 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 100% | Finished | 1920 | 1920 | 100 | 190 | 100 | 100 | 190 | 100
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 17d 3h | 16680 | 0 | 0 | 0 | 0 | 16680 | 0 | 100% | Finished | 9600 | 9600 | 100 | 173.75 | 100 | 100 | 173.75 | 100
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 | 2013-11-14 10:00 | 2d 3h | 6460 | 0 | 0 | 0 | 0 | 6460 | 0 | 100% | Finished | 5440 | 5440 | 100 | 118.75 | 100 | 100 | 118.75 | 100
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 | 2013-11-18 14:00 | 3d 5h | 19000 | 0 | 0 | 0 | 0 | 19000 | 0 | 100% | Finished | 19000 | 19000 | 100 | 181.25 | 100 | 100 | 100 | 100
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 | 2013-11-18 14:00 | 3d 1h | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 100% | Finished | 8000 | 8000 | 100 | 104.1667 | 100 | 100 | 100 | 100
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 | 2013-11-22 10:00 | 2d 6h | 1131.4286 | 0 | 0 | 0 | 0 | 1131.4286 | 0 | 100% | Finished | 720 | 720 | 100 | 157.1429 | 100 | 100 | 157.1429 | 100
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 | 2013-11-14 10:00 | 3d 4h | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 100% | Finished | 12000 | 12000 | 100 | 175 | 100 | 100 | 100 | 100
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 | 2013-11-27 08:00 | 3d | 2500 | 0 | 3h | 0 | 0 | 2500 | 0 | 88.89% | Started | 2500 | 2500 | 100 | 150 | 88.8889 | 100 | 100 | 88.8889
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 |  | 0 | 0 | 6500 | 6d | 0 | 0 | 0 | 6500 | 0% | Not Started | 0 | 6500 | 100 |  | 0 | 100 |  | 0
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 3d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 | 2013-11-27 08:00 | 2d | 198 | 0 | 0 | 0 | 0 | 198 | 0 | 100% | Finished | 198 | 198 | 100 | 100 | 100 | 100 | 100 | 100
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP40
| TP Status Date | 2013-12-06 17:00 |  | TP Name | 6/12/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 200d | [5 empty] | 314756.144 |  | 99.96% |  | 240915.0007 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 100% | Finished | 1920 | 1920 | 100 | 190 | 100 | 100 | 190 | 100
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 17d 3h | 16680 | 0 | 0 | 0 | 0 | 16680 | 0 | 100% | Finished | 9600 | 9600 | 100 | 173.75 | 100 | 100 | 173.75 | 100
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 | 2013-11-14 10:00 | 2d 3h | 6460 | 0 | 0 | 0 | 0 | 6460 | 0 | 100% | Finished | 5440 | 5440 | 100 | 118.75 | 100 | 100 | 118.75 | 100
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 | 2013-11-18 14:00 | 3d 5h | 19000 | 0 | 0 | 0 | 0 | 19000 | 0 | 100% | Finished | 19000 | 19000 | 100 | 181.25 | 100 | 100 | 100 | 100
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 | 2013-11-18 14:00 | 3d 1h | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 100% | Finished | 8000 | 8000 | 100 | 104.1667 | 100 | 100 | 100 | 100
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 | 2013-11-22 10:00 | 2d 6h | 1131.4286 | 0 | 0 | 0 | 0 | 1131.4286 | 0 | 100% | Finished | 720 | 720 | 100 | 157.1429 | 100 | 100 | 157.1429 | 100
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 | 2013-11-14 10:00 | 3d 4h | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 100% | Finished | 12000 | 12000 | 100 | 175 | 100 | 100 | 100 | 100
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 | 2013-11-27 08:00 | 3d 3h | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 168.75 | 100 | 100 | 100 | 100
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 | 2013-12-02 11:00 | 4d 5h | 6500 | 0 | 3d 1h | 0 | 0 | 6500 | 0 | 59.68% | Started | 6500 | 6500 | 100 | 77.0833 | 59.6774 | 100 | 100 | 59.6774
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 | 2013-12-02 11:00 | 4d 5h | 10000 | 0 | 5h | 0 | 0 | 10000 | 0 | 88.1% | Started | 10000 | 10000 | 100 | 154.1667 | 88.0952 | 100 | 100 | 88.0952
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 | 2013-11-27 08:00 | 2d | 198 | 0 | 0 | 0 | 0 | 198 | 0 | 100% | Finished | 198 | 198 | 100 | 100 | 100 | 100 | 100 | 100
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 100 | 100 |  | 0 | 100 |  | 0

## TP41
| TP Status Date | 2013-12-13 17:00 |  | TP Name | 13/12/2013 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a Dream | 2013-03-04 08:00 | 2013-09-20 15:00 | 144d 6h |  |  | 108215 |  |  | 241015.0007 |  | 204d 3h | [5 empty] | 314856.144 |  | 100% |  | 241015.0007 | 241015.0007
1 | Soil Research | 2013-03-04 08:00 | 2013-03-04 17:00 | 1d |  | 0 | 850 | 0 | 0 | 850 | 2013-03-04 08:00 | 1d 2h | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 100% | Finished | 850 | 850 | 100 | 125 | 100 | 100 | 100 | 100
2 | Calculations | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 1210 | 0 | 0 | 1210 | 2013-03-11 10:00 | 8d 5h | 1210 | 0 | 0 | 0 | 0 | 1210 | 0 | 100% | Finished | 1210 | 1210 | 100 | 172.5 | 100 | 100 | 100 | 100
3 | Building site preparation | 2013-03-05 08:00 | 2013-03-05 17:00 | 1d | Cement Mason;Labourer[3.00 #3];Digger | 1640 | 0 | 0 | 0 | 1640 | 2013-03-05 10:00 | 1d | 1640 | 0 | 0 | 0 | 0 | 1640 | 0 | 100% | Finished | 1640 | 1640 | 100 | 100 | 100 | 100 | 100 | 100
4 | Building foundation | 2013-03-18 08:00 | 2013-03-27 12:00 | 7d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3];Digger[0.67 #1] | 8800.0002 | 3000 | 0 | 0 | 11800.0002 | 2013-03-21 16:00 | 13d 3h | 18693.3336 | 0 | 0 | 0 | 0 | 18693.3336 | 0 | 100% | Finished | 11800.0002 | 11800.0002 | 100 | 178.3333 | 100 | 100 | 158.4181 | 100
5 | Sewerage & drainage system | 2013-03-27 13:00 | 2013-03-29 12:00 | 2d | Cement Mason;Labourer[3.00 #3];Crane;Digger | 5280 | 0 | 0 | 0 | 5280 | 2013-03-25 16:00 | 3d 3h | 8910 | 0 | 0 | 0 | 0 | 8910 | 0 | 100% | Finished | 5280 | 5280 | 100 | 168.75 | 100 | 100 | 168.75 | 100
6 | Building groundfloor | 2013-04-01 08:00 | 2013-04-09 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 6000 | 0 | 0 | 23920 | 2013-04-10 10:00 | 8d 3h | 27440 | 0 | 0 | 0 | 0 | 27440 | 0 | 100% | Finished | 23920 | 23920 | 100 | 119.6429 | 100 | 100 | 114.7157 | 100
7 | Building first floor | 2013-04-10 08:00 | 2013-04-18 17:00 | 7d | Concrete Mixer;Cement Mason[2.00 #2];Labourer[3.00 #3];Crane | 17920 | 7000 | 0 | 0 | 24920 | 2013-04-22 14:00 | 11d 6h | 37080 | 0 | 0 | 0 | 0 | 37080 | 0 | 100% | Finished | 24920 | 24920 | 100 | 167.8571 | 100 | 100 | 148.7961 | 100
8 | Test jointing | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Cement Mason[1.33 #2] | 180 | 0 | 0 | 0 | 180 | 2013-04-22 14:00 | 5h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 180 | 180 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
9 | Choosing joint type | 2013-04-22 08:00 | 2013-04-22 10:00 | 2h | Cement Mason[2.00 #2] | 180 | 2000 | 0 | 0 | 2180 | 2013-04-23 14:00 | 3h | 2270 | 0 | 0 | 0 | 0 | 2270 | 0 | 100% | Finished | 2180 | 2180 | 100 | 150 | 100 | 100 | 104.1284 | 100
10 | Jointing | 2013-06-11 15:00 | 2013-06-19 17:00 | 6d 2h | Concrete Mixer[0.80 #1];Cement Mason[1.60 #2];Labourer[0.80 #3] | 5400.0001 | 0 | 0 | 0 | 5400.0001 | 2013-06-27 13:00 | 9d | 7776.0001 | 0 | 0 | 0 | 0 | 7776.0001 | 0 | 100% | Finished | 5400.0001 | 5400.0001 | 100 | 144 | 100 | 100 | 144 | 100
11 | Scaffolding | 2013-04-19 08:00 | 2013-04-23 12:00 | 2d 4h | Labourer[1.60 #3] | 960 | 250 | 0 | 0 | 1210 | 2013-04-22 14:00 | 4d 1h | 1834 | 0 | 0 | 0 | 0 | 1834 | 0 | 100% | Finished | 1210 | 1210 | 100 | 165 | 100 | 100 | 151.5702 | 100
12 | Building roof framework | 2013-04-23 13:00 | 2013-05-06 12:00 | 9d | Labourer[0.67 #3];Roofer[1.33 #2] | 5760.0002 | 0 | 0 | 0 | 5760.0002 | 2013-05-08 11:00 | 13d 1h | 8400.0003 | 0 | 0 | 0 | 0 | 8400.0003 | 0 | 100% | Finished | 5760.0002 | 5760.0002 | 100 | 145.8333 | 100 | 100 | 145.8333 | 100
13 | Roof covering | 2013-05-06 13:00 | 2013-05-24 12:00 | 14d | Labourer;Crane;Roofer[2.00 #2] | 27440 | 15000 | 0 | 0 | 42440 | 2013-05-27 13:00 | 23d | 60080 | 0 | 0 | 0 | 0 | 60080 | 0 | 100% | Finished | 42440 | 42440 | 100 | 164.2857 | 100 | 100 | 141.5646 | 100
14 | Electricity | 2013-05-24 13:00 | 2013-05-30 10:00 | 3d 6h | Electrician[1.60 #2] | 2400 | 250 | 0 | 0 | 2650 | 2013-06-27 13:00 | 6d 3h | 4330.0001 | 0 | 0 | 0 | 0 | 4330.0001 | 0 | 100% | Finished | 2650 | 2650 | 100 | 170 | 100 | 100 | 163.3962 | 100
15 | Sanitary | 2013-05-24 13:00 | 2013-05-30 12:00 | 4d | Plumber[2.00 #2] | 3200 | 4500 | 0 | 0 | 7700 | 2013-06-27 13:00 | 7d 7h | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 7700 | 7700 | 100 | 196.875 | 100 | 100 | 140.2597 | 100
16 | Placing windows | 2013-05-30 13:00 | 2013-06-05 10:00 | 3d 6h | Labourer[2.40 #3] | 2160.0001 | 3000 | 0 | 0 | 5160.0001 | 2013-07-09 11:00 | 6d 5h | 6816.0002 | 0 | 0 | 0 | 0 | 6816.0002 | 0 | 100% | Finished | 5160.0001 | 5160.0001 | 100 | 176.6667 | 100 | 100 | 132.093 | 100
17 | Underfloor heating | 2013-05-30 13:00 | 2013-06-04 17:00 | 3d 4h | Labourer[0.57 #3];Plumber[0.57 #2] | 1280.0001 | 2500 | 0 | 0 | 3780.0001 | 2013-06-27 13:00 | 4d 4h | 4145.7144 | 0 | 0 | 0 | 0 | 4145.7144 | 0 | 100% | Finished | 3780.0001 | 3780.0001 | 100 | 128.5714 | 100 | 100 | 109.675 | 100
18 | Laying floor screed | 2013-06-05 10:00 | 2013-06-11 15:00 | 4d 4h | Concrete Mixer[0.67 #1];Cement Mason[0.67 #2];Labourer[2.00 #3] | 3600 | 3000 | 0 | 0 | 6600 | 2013-07-18 08:00 | 7d 3h | 8900.0001 | 0 | 0 | 0 | 0 | 8900.0001 | 0 | 100% | Finished | 6600 | 6600 | 100 | 163.8889 | 100 | 100 | 134.8485 | 100
19 | Configurating underfloor heating | 2013-07-09 15:00 | 2013-07-10 12:00 | 6h | Plumber[0.67 #2] | 200 | 0 | 0 | 0 | 200 | 2013-08-26 11:00 | 1d | 266.6667 | 0 | 0 | 0 | 0 | 266.6667 | 0 | 100% | Finished | 200 | 200 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
20 | Plastering | 2013-07-09 15:00 | 2013-07-30 15:00 | 15d | Labourer[2.00 #3] | 7200 | 100 | 0 | 0 | 7300 | 2013-08-26 11:00 | 17d 6h | 8620 | 0 | 0 | 0 | 0 | 8620 | 0 | 100% | Finished | 7300 | 7300 | 100 | 118.3333 | 100 | 100 | 118.0822 | 100
21 | Floor tiling | 2013-07-30 15:00 | 2013-08-09 10:00 | 7d 4h | Labourer[2.00 #3] | 3600 | 1257 | 0 | 0 | 4857 | 2013-09-19 09:00 | 14d 5h | 8277 | 0 | 0 | 0 | 0 | 8277 | 0 | 100% | Finished | 4857 | 4857 | 100 | 195 | 100 | 100 | 170.4138 | 100
22 | Carpenting | 2013-08-12 10:00 | 2013-08-15 17:00 | 3d 6h | Carpenter[1.60 #2] | 1920 | 0 | 0 | 0 | 1920 | 2013-10-10 15:00 | 7d 1h | 3648.0001 | 0 | 0 | 0 | 0 | 3648.0001 | 0 | 100% | Finished | 1920 | 1920 | 100 | 190 | 100 | 100 | 190 | 100
23 | Painting | 2013-08-16 08:00 | 2013-08-29 17:00 | 10d | Painter[2.00 #2] | 9600 | 0 | 0 | 0 | 9600 | 2013-10-21 16:00 | 17d 3h | 16680 | 0 | 0 | 0 | 0 | 16680 | 0 | 100% | Finished | 9600 | 9600 | 100 | 173.75 | 100 | 100 | 173.75 | 100
24 | Finishing up | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d | Labourer[2.00 #3];Carpenter[2.00 #2];Plumber[2.00 #2];Electrician[2.00 #2] | 5440 | 0 | 0 | 0 | 5440 | 2013-11-14 10:00 | 2d 3h | 6460 | 0 | 0 | 0 | 0 | 6460 | 0 | 100% | Finished | 5440 | 5440 | 100 | 118.75 | 100 | 100 | 118.75 | 100
25 | Installation of kitchen | 2013-09-03 08:00 | 2013-09-04 17:00 | 2d |  | 0 | 19000 | 0 | 0 | 19000 | 2013-11-18 14:00 | 3d 5h | 19000 | 0 | 0 | 0 | 0 | 19000 | 0 | 100% | Finished | 19000 | 19000 | 100 | 181.25 | 100 | 100 | 100 | 100
26 | Installation of bathroom | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 8000 | 0 | 0 | 8000 | 2013-11-18 14:00 | 3d 1h | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 100% | Finished | 8000 | 8000 | 100 | 104.1667 | 100 | 100 | 100 | 100
27 | Cleaning up | 2013-09-06 08:00 | 2013-09-09 15:00 | 1d 6h | Labourer[1.71 #3] | 720 | 0 | 0 | 0 | 720 | 2013-11-22 10:00 | 2d 6h | 1131.4286 | 0 | 0 | 0 | 0 | 1131.4286 | 0 | 100% | Finished | 720 | 720 | 100 | 157.1429 | 100 | 100 | 157.1429 | 100
28 | Installation solar panels | 2013-08-30 08:00 | 2013-09-02 17:00 | 2d |  | 0 | 12000 | 0 | 0 | 12000 | 2013-11-14 10:00 | 3d 4h | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 100% | Finished | 12000 | 12000 | 100 | 175 | 100 | 100 | 100 | 100
29 | Garden site preparation | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 2500 | 0 | 0 | 2500 | 2013-11-27 08:00 | 3d 3h | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 168.75 | 100 | 100 | 100 | 100
30 | Garden landscaping | 2013-09-11 15:00 | 2013-09-19 15:00 | 6d |  | 0 | 6500 | 0 | 0 | 6500 | 2013-12-02 11:00 | 7d 6h | 6500 | 0 | 0 | 0 | 0 | 6500 | 0 | 100% | Finished | 6500 | 6500 | 100 | 129.1667 | 100 | 100 | 100 | 100
31 | Terrace construction | 2013-09-11 15:00 | 2013-09-16 15:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 | 2013-12-02 11:00 | 5d 2h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 175 | 100 | 100 | 100 | 100
32 | Moving of furniture | 2013-09-09 15:00 | 2013-09-11 15:00 | 2d |  | 0 | 198 | 0 | 0 | 198 | 2013-11-27 08:00 | 2d | 198 | 0 | 0 | 0 | 0 | 198 | 0 | 100% | Finished | 198 | 198 | 100 | 100 | 100 | 100 | 100 | 100
33 | Final inspection | 2013-09-19 15:00 | 2013-09-20 15:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2013-12-12 09:00 | 1d 2h | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 125 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
8/03/2013 17:00 | 2013-03-04 08:00 | 2013-03-08 17:00 | 2490 | 2490 | 2490 | 2013-03-08 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
15/03/2013 17:00 | 2013-03-08 17:00 | 2013-03-15 17:00 | 3700 | 3700 | 3700 | 2013-03-15 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-09-20 15:00 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 241015.0007 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
22/03/2013 17:00 | 2013-03-15 17:00 | 2013-03-22 17:00 | 12566.6668 | 7440.187 | 8020 | 2013-03-18 14:00 | -5126.4798 | 59.21% | -579.8131 | 92.77% | -4d 3h | 70.83% | 100% | 2013-09-25 16:00 | 2014-02-07 12:00 | 2014-03-06 12:00 | 2013-09-30 16:00 | 2014-02-07 12:00 | 2014-03-05 11:00 | 2013-09-27 09:00 | 2013-12-13 11:00 | 2014-01-03 09:00 | 241594.8138 | 259797.277 | 402533.8567 | 337772.6782 | 433278.2844 | 363470.2734 | 279437.2295 | 272295.7391 | 0.70833 | 0.9277 | 0.59206 | 1 | -4.375 | 0.9277 | 1 | 0.70833 | 1
29/03/2013 17:00 | 2013-03-22 17:00 | 2013-03-29 17:00 | 20780.0002 | 16009.9065 | 22796.6668 | 2013-03-27 14:00 | -4770.0936 | 77.04% | -6786.7603 | 70.23% | -2d 3h | 88.12% | 69.87% | 2013-09-25 14:00 | 2013-11-20 16:00 | 2014-03-12 12:00 | 2013-09-27 11:00 | 2013-11-20 16:00 | 2014-02-27 17:00 | 2013-09-25 09:00 | 2013-10-18 10:00 | 2014-01-13 11:00 | 247801.7609 | 343183.6814 | 314841.2132 | 278121.5963 | 438641.831 | 386356.3996 | 337083.4724 | 327647.2326 | 0.88125 | 0.70229 | 0.77045 | 0.69867 | -2.375 | 0.70229 | 1 | 0.88125 | 1
5/04/2013 17:00 | 2013-03-29 17:00 | 2013-04-05 17:00 | 39580.0002 | 19299.6265 | 28663.3336 | 2013-03-28 16:00 | -20280.3736 | 48.76% | -9363.7071 | 67.33% | -6d 1h | 75.5% | 92.26% | 2013-10-08 16:00 | 2014-04-22 16:00 | 2014-11-10 16:00 | 2013-10-09 12:00 | 2014-04-22 16:00 | 2014-10-23 15:00 | 2013-09-30 16:00 | 2013-11-26 15:00 | 2014-03-19 14:00 | 250378.7077 | 357949.5881 | 483360.9693 | 322326.0808 | 703969.1484 | 464804.068 | 377174.3402 | 350149.8402 | 0.755 | 0.67332 | 0.48761 | 0.92262 | -6.125 | 0.67332 | 1 | 0.755 | 1
12/04/2013 17:00 | 2013-04-05 17:00 | 2013-04-12 17:00 | 59380.0002 | 32664.1792 | 44343.3336 | 2013-04-03 10:00 | -26715.821 | 55.01% | -11679.1545 | 73.66% | -7d 6h | 74.17% | 100% | 2013-10-14 15:00 | 2014-03-06 09:00 | 2014-07-16 10:00 | 2013-10-10 10:00 | 2014-03-06 09:00 | 2014-07-01 12:00 | 2013-10-02 12:00 | 2013-12-02 09:00 | 2014-02-21 10:00 | 252694.1551 | 327190.4838 | 423102.9454 | 325265.7896 | 558529.3397 | 425710.2777 | 342279.6343 | 326803.438 | 0.74167 | 0.73662 | 0.55009 | 1 | -7.75 | 0.73662 | 1 | 0.74167 | 1
19/04/2013 17:00 | 2013-04-12 17:00 | 2013-04-19 17:00 | 70434.0002 | 43362.6868 | 57143.3336 | 2013-04-09 11:00 | -27071.3134 | 61.56% | -13780.6468 | 75.88% | -8d 5h | 75.36% | 100% | 2013-10-14 17:00 | 2014-01-27 09:00 | 2014-05-09 16:00 | 2013-10-10 10:00 | 2014-01-27 09:00 | 2014-04-24 15:00 | 2013-10-03 11:00 | 2013-11-27 09:00 | 2014-02-04 17:00 | 254795.6475 | 317609.4845 | 378189.9326 | 319430.7644 | 480218.4306 | 402785.6191 | 327824.8278 | 317971.7142 | 0.75357 | 0.75884 | 0.61565 | 1 | -8.625 | 0.75884 | 1 | 0.75357 | 1
26/04/2013 17:00 | 2013-04-19 17:00 | 2013-04-26 17:00 | 75430.0002 | 61942.3403 | 81347.3336 | 2013-04-15 17:00 | -13487.6599 | 82.12% | -19404.9933 | 76.15% | -9d | 77.5% | 94.24% | 2013-10-02 16:00 | 2013-11-05 10:00 | 2014-01-21 12:00 | 2013-10-01 16:00 | 2013-11-05 10:00 | 2014-01-02 17:00 | 2013-10-03 15:00 | 2013-11-19 15:00 | 2014-01-22 15:00 | 260419.994 | 316519.0008 | 299412.2427 | 312408.8309 | 367726.5505 | 384794.6462 | 312886.2474 | 315685.3103 | 0.775 | 0.76146 | 0.82119 | 0.9424 | -9 | 0.76146 | 1 | 0.775 | 1
3/05/2013 17:00 | 2013-04-26 17:00 | 2013-05-03 17:00 | 78630.0003 | 69567.8729 | 94147.3336 | 2013-04-18 16:00 | -9062.1274 | 88.47% | -24579.4607 | 73.89% | -11d 1h | 75.28% | 95.24% | 2013-09-30 10:00 | 2013-10-17 14:00 | 2014-01-07 11:00 | 2013-09-27 16:00 | 2013-10-17 14:00 | 2013-12-16 12:00 | 2013-10-07 16:00 | 2013-11-27 10:00 | 2014-02-07 11:00 | 265594.4614 | 326169.5194 | 287927.6972 | 321899.9757 | 356393.4506 | 402368.6874 | 317359.5038 | 325302.8523 | 0.75278 | 0.73893 | 0.88475 | 0.95235 | -11.125 | 0.73893 | 1 | 0.75278 | 1
10/05/2013 17:00 | 2013-05-03 17:00 | 2013-05-10 17:00 | 102770.0003 | 74342.0002 | 101907.3337 | 2013-04-25 10:00 | -28428.0001 | 72.34% | -27565.3335 | 72.95% | -11d 6h | 76.5% | 100% | 2013-10-15 16:00 | 2013-12-09 09:00 | 2014-03-21 10:00 | 2013-10-10 14:00 | 2013-12-09 09:00 | 2014-02-24 15:00 | 2013-10-08 12:00 | 2013-11-22 10:00 | 2014-02-03 16:00 | 268580.3342 | 330381.1577 | 332315.2359 | 319780.5369 | 417748.3778 | 400565.9272 | 330765.3714 | 328179.3051 | 0.765 | 0.72951 | 0.72338 | 1 | -11.75 | 0.72951 | 1 | 0.765 | 1
17/05/2013 17:00 | 2013-05-10 17:00 | 2013-05-17 17:00 | 112570.0003 | 76536.2861 | 105107.3338 | 2013-04-30 14:00 | -36033.7142 | 67.99% | -28571.0477 | 72.82% | -13d 3h | 75.68% | 100% | 2013-10-22 11:00 | 2013-12-25 16:00 | 2014-04-16 11:00 | 2013-10-16 11:00 | 2013-12-25 16:00 | 2014-03-18 16:00 | 2013-10-10 09:00 | 2013-11-26 10:00 | 2014-02-05 09:00 | 269586.0483 | 330986.0643 | 347023.5528 | 322436.5662 | 437331.0418 | 403565.7165 | 334021.1671 | 329222.7723 | 0.75682 | 0.72817 | 0.6799 | 1 | -13.375 | 0.72817 | 1 | 0.75682 | 1
24/05/2013 17:00 | 2013-05-17 17:00 | 2013-05-24 17:00 | 126860.0004 | 78730.5718 | 108307.3339 | 2013-05-06 09:00 | -48129.4286 | 62.06% | -29576.7621 | 72.69% | -14d 7h | 75.21% | 100% | 2013-10-31 14:00 | 2014-01-23 10:00 | 2014-05-26 16:00 | 2013-10-23 12:00 | 2014-01-23 10:00 | 2014-04-24 11:00 | 2013-10-11 14:00 | 2013-11-27 12:00 | 2014-02-05 10:00 | 270591.7628 | 331557.2536 | 369799.1819 | 324087.184 | 468033.9845 | 405149.3323 | 338283.8459 | 330022.1472 | 0.75208 | 0.72692 | 0.62061 | 1 | -14.875 | 0.72692 | 1 | 0.75208 | 1
31/05/2013 17:00 | 2013-05-24 17:00 | 2013-05-31 17:00 | 138652.5719 | 99318.6959 | 132447.3339 | 2013-05-09 09:00 | -39333.8759 | 71.63% | -33128.6379 | 74.99% | -16d 7h | 74.04% | 100% | 2013-10-24 11:00 | 2013-12-11 09:00 | 2014-03-14 12:00 | 2013-10-17 10:00 | 2013-12-11 09:00 | 2014-02-12 15:00 | 2013-10-15 14:00 | 2013-12-02 12:00 | 2014-01-30 17:00 | 274143.6386 | 321407.7064 | 330260.6146 | 323829.3559 | 396243.0008 | 387666.5384 | 323114.3232 | 321887.1211 | 0.74038 | 0.74987 | 0.71631 | 1 | -16.875 | 0.74987 | 1 | 0.74038 | 1
7/06/2013 17:00 | 2013-05-31 17:00 | 2013-06-07 17:00 | 145880.0006 | 105283.9131 | 142247.3339 | 2013-05-14 10:00 | -40596.0874 | 72.17% | -36963.4208 | 74.01% | -18d 6h | 73.21% | 100% | 2013-10-25 09:00 | 2013-12-09 14:00 | 2014-03-17 17:00 | 2013-10-18 10:00 | 2013-12-09 14:00 | 2014-02-11 11:00 | 2013-10-17 12:00 | 2013-12-04 15:00 | 2014-02-05 12:00 | 277978.4214 | 325631.3358 | 330314.5375 | 327636.1364 | 396341.7867 | 392723.0438 | 326549.2236 | 326028.8196 | 0.73214 | 0.74015 | 0.72172 | 1 | -18.75 | 0.74015 | 1 | 0.73214 | 1
14/06/2013 17:00 | 2013-06-07 17:00 | 2013-06-14 17:00 | 150088.0006 | 111249.1316 | 152047.3339 | 2013-05-17 10:00 | -38838.869 | 74.12% | -40798.2023 | 73.17% | -20d 6h | 72.33% | 100% | 2013-10-24 09:00 | 2013-12-02 10:00 | 2014-03-11 16:00 | 2013-10-18 09:00 | 2013-12-02 10:00 | 2014-01-31 11:00 | 2013-10-21 12:00 | 2013-12-09 09:00 | 2014-02-10 17:00 | 281813.203 | 329402.0166 | 327116.5643 | 331447.153 | 391319.4015 | 397238.1395 | 328940.1649 | 329807.3051 | 0.72333 | 0.73167 | 0.74123 | 1 | -20.75 | 0.73167 | 1 | 0.72333 | 1
21/06/2013 17:00 | 2013-06-14 17:00 | 2013-06-21 17:00 | 152680.0006 | 117214.3475 | 161847.3339 | 2013-05-22 10:00 | -35465.6531 | 76.77% | -44632.9864 | 72.42% | -22d 6h | 71.56% | 100% | 2013-10-21 17:00 | 2013-11-21 12:00 | 2014-03-03 11:00 | 2013-10-17 11:00 | 2013-11-21 12:00 | 2014-01-17 16:00 | 2013-10-23 12:00 | 2013-12-11 10:00 | 2014-02-13 16:00 | 285647.9871 | 332788.9129 | 323106.4647 | 334843.8798 | 384510.8639 | 400717.6626 | 330760.5092 | 333195.9913 | 0.71562 | 0.72423 | 0.76771 | 1 | -22.75 | 0.72423 | 1 | 0.71562 | 1
28/06/2013 17:00 | 2013-06-21 17:00 | 2013-06-28 17:00 | 152680.0006 | 131140.8968 | 179961.9054 | 2013-05-29 16:00 | -21539.1038 | 85.89% | -48821.0086 | 72.87% | -22d 1h | 73.97% | 97.19% | 2013-10-09 14:00 | 2013-10-24 12:00 | 2014-01-21 10:00 | 2013-10-08 15:00 | 2013-10-24 12:00 | 2013-12-06 14:00 | 2013-10-22 16:00 | 2013-12-02 14:00 | 2014-01-28 16:00 | 289836.0093 | 330739.8364 | 307882.1702 | 328499.4613 | 355504.205 | 383796.8817 | 325537.3534 | 330286.371 | 0.73971 | 0.72871 | 0.85893 | 0.97186 | -22.125 | 0.72871 | 1 | 0.73971 | 1
5/07/2013 17:00 | 2013-06-28 17:00 | 2013-07-05 17:00 | 152680.0006 | 138861.2703 | 192499.0484 | 2013-06-03 09:00 | -13818.7303 | 90.95% | -53637.7781 | 72.14% | -24d 7h | 72.36% | 96.76% | 2013-10-02 17:00 | 2013-10-11 09:00 | 2014-01-06 14:00 | 2013-10-02 16:00 | 2013-10-11 09:00 | 2013-11-18 16:00 | 2013-10-25 14:00 | 2013-12-06 17:00 | 2014-02-05 12:00 | 294652.7788 | 334111.579 | 304818.5712 | 333671.1902 | 348204.1 | 388201.5859 | 327091.2324 | 334023.2816 | 0.72361 | 0.72136 | 0.90949 | 0.96761 | -24.875 | 0.72136 | 1 | 0.72361 | 1
12/07/2013 17:00 | 2013-07-05 17:00 | 2013-07-12 17:00 | 154540.0007 | 145101.8873 | 200847.0485 | 2013-06-06 17:00 | -9438.1133 | 93.89% | -55745.1612 | 72.24% | -26d | 72.63% | 96.29% | 2013-09-30 11:00 | 2013-10-04 09:00 | 2013-12-26 11:00 | 2013-09-30 12:00 | 2013-10-04 09:00 | 2013-11-05 16:00 | 2013-10-28 15:00 | 2013-12-06 10:00 | 2014-01-31 11:00 | 296760.1619 | 333608.0076 | 302998.8046 | 332901.335 | 342243.4085 | 383633.8762 | 326101.6399 | 333466.0687 | 0.72632 | 0.72245 | 0.93893 | 0.96293 | -26 | 0.72245 | 1 | 0.72632 | 1
19/07/2013 17:00 | 2013-07-12 17:00 | 2013-07-19 17:00 | 156940.0007 | 150056.2718 | 207175.0486 | 2013-06-14 16:00 | -6883.7288 | 95.61% | -57118.7768 | 72.43% | -25d 1h | 74.88% | 98.25% | 2013-09-26 16:00 | 2013-10-01 11:00 | 2013-12-19 17:00 | 2013-09-27 09:00 | 2013-10-01 11:00 | 2013-10-28 17:00 | 2013-10-25 16:00 | 2013-11-28 11:00 | 2014-01-16 16:00 | 298133.7775 | 332757.1309 | 302306.447 | 328655.8217 | 338518.1231 | 374897.3622 | 325201.3074 | 331914.8634 | 0.74875 | 0.7243 | 0.95614 | 0.98251 | -25.125 | 0.7243 | 1 | 0.74875 | 1
26/07/2013 17:00 | 2013-07-19 17:00 | 2013-07-26 17:00 | 159340.0007 | 152496.9498 | 211175.0486 | 2013-06-19 15:00 | -6843.0509 | 95.71% | -58678.0989 | 72.21% | -27d 2h | 74.05% | 99.88% | 2013-09-26 16:00 | 2013-10-01 10:00 | 2013-12-20 12:00 | 2013-09-27 10:00 | 2013-10-01 10:00 | 2013-10-24 17:00 | 2013-10-29 17:00 | 2013-12-02 12:00 | 2014-01-20 10:00 | 299693.0996 | 333753.2625 | 303665.2022 | 330717.111 | 339253.7591 | 376714.7586 | 326265.2423 | 333133.7565 | 0.74048 | 0.72214 | 0.95705 | 0.9988 | -27.25 | 0.72214 | 1 | 0.74048 | 1
2/08/2013 17:00 | 2013-07-26 17:00 | 2013-08-02 17:00 | 162997.0007 | 152680.0006 | 211475.0487 | 2013-07-09 15:00 | -10317 | 93.67% | -58795.048 | 72.2% | -18d 2h | 83.41% | 100% | 2013-09-30 17:00 | 2013-10-04 12:00 | 2013-12-26 17:00 | 2013-10-01 15:00 | 2013-10-04 12:00 | 2013-10-29 14:00 | 2013-10-16 17:00 | 2013-10-31 12:00 | 2013-12-04 17:00 | 299810.0487 | 333826.6884 | 305779.0832 | 317380.7708 | 342094.3191 | 358163.663 | 326957.4093 | 330141.1959 | 0.83409 | 0.72198 | 0.9367 | 1 | -18.25 | 0.72198 | 1 | 0.83409 | 1
9/08/2013 17:00 | 2013-08-02 17:00 | 2013-08-09 17:00 | 165037.0007 | 152680.0006 | 211475.0487 | 2013-07-09 15:00 | -12357 | 92.51% | -58795.048 | 72.2% | -23d 2h | 79.78% | 100% | 2013-10-02 09:00 | 2013-10-08 12:00 | 2013-12-31 15:00 | 2013-10-03 11:00 | 2013-10-08 12:00 | 2013-10-30 11:00 | 2013-10-23 17:00 | 2013-11-12 11:00 | 2013-12-17 17:00 | 299810.0487 | 333826.6884 | 306959.3518 | 322194.6672 | 343729.0934 | 364831.3273 | 327308.0777 | 331308.7814 | 0.79783 | 0.72198 | 0.92513 | 1 | -23.25 | 0.72198 | 1 | 0.79783 | 1
16/08/2013 17:00 | 2013-08-09 17:00 | 2013-08-16 17:00 | 167917.0007 | 152680.0006 | 211475.0487 | 2013-07-09 15:00 | -15237 | 90.93% | -58795.048 | 72.2% | -28d 2h | 76.46% | 100% | 2013-10-03 16:00 | 2013-10-11 10:00 | 2014-01-06 12:00 | 2013-10-07 14:00 | 2013-10-11 10:00 | 2013-11-01 10:00 | 2013-10-30 17:00 | 2013-11-22 11:00 | 2013-12-30 17:00 | 299810.0487 | 333826.6884 | 308625.6132 | 327008.5637 | 346037.0102 | 371498.9916 | 327792.107 | 332399.4358 | 0.76458 | 0.72198 | 0.90926 | 1 | -28.25 | 0.72198 | 1 | 0.76458 | 1
23/08/2013 17:00 | 2013-08-16 17:00 | 2013-08-23 17:00 | 172717.0007 | 152680.0006 | 211475.0487 | 2013-07-09 15:00 | -20037 | 88.4% | -58795.048 | 72.2% | -33d 2h | 73.4% | 100% | 2013-10-08 15:00 | 2013-10-17 15:00 | 2014-01-14 15:00 | 2013-10-11 10:00 | 2013-10-17 15:00 | 2013-11-07 14:00 | 2013-11-06 17:00 | 2013-12-04 10:00 | 2014-01-10 17:00 | 299810.0487 | 333826.6884 | 311402.7157 | 331822.4602 | 349883.538 | 378166.6559 | 328571.3581 | 333420.52 | 0.734 | 0.72198 | 0.88399 | 1 | -33.25 | 0.72198 | 1 | 0.734 | 1
30/08/2013 17:00 | 2013-08-23 17:00 | 2013-08-30 17:00 | 191277.0007 | 154856.0569 | 214061.7153 | 2013-07-15 14:00 | -36420.9437 | 80.96% | -59205.6584 | 72.34% | -34d 3h | 73.56% | 100% | 2013-10-22 14:00 | 2013-11-07 15:00 | 2014-02-12 09:00 | 2013-10-25 12:00 | 2013-11-07 15:00 | 2013-12-04 12:00 | 2013-11-08 09:00 | 2013-12-03 15:00 | 2014-01-08 11:00 | 300220.6591 | 333161.5533 | 320484.5745 | 331192.8284 | 361172.9116 | 375975.2205 | 330390.1687 | 332762.5316 | 0.73558 | 0.72342 | 0.80959 | 1 | -34.375 | 0.72342 | 1 | 0.73558 | 1
6/09/2013 17:00 | 2013-08-30 17:00 | 2013-09-06 17:00 | 221408.4293 | 156884.2258 | 216461.7153 | 2013-07-19 16:00 | -64524.2034 | 70.86% | -59577.4895 | 72.48% | -35d 1h | 73.98% | 100% | 2013-11-14 12:00 | 2013-12-13 10:00 | 2014-04-01 16:00 | 2013-11-15 09:00 | 2013-12-13 10:00 | 2014-01-20 14:00 | 2013-11-08 16:00 | 2013-12-02 14:00 | 2014-01-02 15:00 | 300592.4902 | 332541.5299 | 335194.256 | 330180.4098 | 380283.4717 | 373365.5948 | 333062.5498 | 332061.4945 | 0.73981 | 0.72477 | 0.70857 | 1 | -35.125 | 0.72477 | 1 | 0.73981 | 1
13/09/2013 17:00 | 2013-09-06 17:00 | 2013-09-13 17:00 | 240915.0007 | 158912.3951 | 218861.7153 | 2013-07-25 17:00 | -82002.6056 | 65.96% | -59949.3202 | 72.61% | -36d | 74.29% | 100% | 2013-11-28 17:00 | 2014-01-03 12:00 | 2014-04-30 10:00 | 2013-11-27 11:00 | 2014-01-03 12:00 | 2014-02-14 11:00 | 2013-11-11 15:00 | 2013-11-29 16:00 | 2013-12-30 12:00 | 300964.3209 | 331937.3321 | 343331.2337 | 329384.4536 | 390287.0612 | 371078.8917 | 334046.1211 | 331417.3651 | 0.74286 | 0.72609 | 0.65962 | 1 | -36 | 0.72609 | 1 | 0.74286 | 1
20/09/2013 17:00 | 2013-09-13 17:00 | 2013-09-20 17:00 | 241015.0007 | 161898.5391 | 222518.7153 | 2013-07-31 14:00 | -79116.4615 | 67.17% | -60620.1762 | 72.76% | -37d 3h | 74.22% | 100% | 2013-11-27 10:00 | 2013-12-30 12:00 | 2014-04-22 09:00 | 2013-11-27 14:00 | 2013-12-30 16:00 | 2014-02-05 11:00 | 2013-11-13 09:00 | 2013-11-29 17:00 | 2013-12-26 15:00 | 301635.1769 | 331259.0009 | 340297.7523 | 329109.9992 | 384398.1254 | 369021.3068 | 332954.035 | 330822.2962 | 0.74224 | 0.72757 | 0.67174 | 1 | -37.375 | 0.72757 | 1 | 0.74224 | 1
27/09/2013 17:00 | 2013-09-20 17:00 | 2013-09-27 17:00 | 241015.0007 | 163129.3084 | 224918.7153 | 2013-08-05 10:00 | -77885.6923 | 67.68% | -61789.407 | 72.53% | -39d 6h | 73.5% | 100% | 2013-11-26 12:00 | 2013-12-26 16:00 | 2014-04-18 16:00 | 2013-12-05 12:00 | 2014-01-07 14:00 | 2014-02-13 15:00 | 2013-11-15 12:00 | 2013-12-03 17:00 | 2013-12-27 15:00 | 302804.4077 | 332305.61 | 339990.7424 | 330885.6437 | 383577.2223 | 371023.334 | 333759.404 | 332018.5805 | 0.735 | 0.72528 | 0.67684 | 1 | -39.75 | 0.72528 | 1 | 0.735 | 1
4/10/2013 17:00 | 2013-09-27 17:00 | 2013-10-04 17:00 | 241015.0007 | 164360.0776 | 227318.7153 | 2013-08-07 15:00 | -76654.9231 | 68.19% | -62958.6377 | 72.3% | -42d 2h | 72.74% | 100% | 2013-11-25 15:00 | 2013-12-25 10:00 | 2014-04-17 14:00 | 2013-12-13 10:00 | 2014-01-15 10:00 | 2014-02-21 17:00 | 2013-11-19 17:00 | 2013-12-05 17:00 | 2013-12-30 16:00 | 303973.6384 | 333336.5445 | 339724.2739 | 332697.9887 | 382781.5719 | 373063.8464 | 334555.3429 | 333208.215 | 0.72742 | 0.72304 | 0.68195 | 1 | -42.25 | 0.72304 | 1 | 0.72742 | 1
11/10/2013 17:00 | 2013-10-04 17:00 | 2013-10-11 17:00 | 241015.0007 | 165373.8428 | 229278.7153 | 2013-08-12 16:00 | -75641.1579 | 68.62% | -63904.8726 | 72.13% | -44d 1h | 72.42% | 100% | 2013-11-25 09:00 | 2013-12-23 17:00 | 2014-04-16 12:00 | 2013-12-23 10:00 | 2014-01-23 09:00 | 2014-03-04 12:00 | 2013-11-21 16:00 | 2013-12-06 16:00 | 2013-12-30 10:00 | 304919.8733 | 334149.6382 | 339517.7557 | 333723.8956 | 382117.0671 | 374084.3047 | 335181.0261 | 334064.2123 | 0.72422 | 0.72128 | 0.68616 | 1 | -44.125 | 0.72128 | 1 | 0.72422 | 1
18/10/2013 17:00 | 2013-10-11 17:00 | 2013-10-18 17:00 | 241015.0007 | 166721.2112 | 231838.7154 | 2013-08-15 12:00 | -74293.7895 | 69.17% | -65117.5042 | 71.91% | -46d 4h | 71.82% | 100% | 2013-11-22 11:00 | 2013-12-20 10:00 | 2014-04-14 17:00 | 2013-12-30 16:00 | 2014-01-30 12:00 | 2014-03-12 10:00 | 2013-11-26 10:00 | 2013-12-10 12:00 | 2013-12-30 16:00 | 306132.5049 | 335149.9653 | 339239.0731 | 335285.764 | 381187.2044 | 375689.8229 | 335942.6859 | 335177.0965 | 0.71818 | 0.71913 | 0.69175 | 1 | -46.5 | 0.71913 | 1 | 0.71818 | 1
25/10/2013 17:00 | 2013-10-18 17:00 | 2013-10-25 17:00 | 241015.0007 | 169236.1373 | 236246.7154 | 2013-08-20 10:00 | -71778.8633 | 70.22% | -67010.578 | 71.64% | -48d 6h | 71.32% | 100% | 2013-11-20 16:00 | 2013-12-17 09:00 | 2014-04-09 15:00 | 2014-01-06 14:00 | 2014-02-05 09:00 | 2014-03-17 14:00 | 2013-11-28 12:00 | 2013-12-11 17:00 | 2013-12-30 17:00 | 308025.5787 | 336447.0684 | 338469.4621 | 336885.1217 | 378945.4825 | 376733.8082 | 336845.1199 | 336534.3737 | 0.71324 | 0.71635 | 0.70218 | 1 | -48.75 | 0.71635 | 1 | 0.71324 | 1
1/11/2013 17:00 | 2013-10-25 17:00 | 2013-11-01 17:00 | 241015.0007 | 171998.7274 | 241046.7154 | 2013-08-23 10:00 | -69016.2733 | 71.36% | -69047.988 | 71.35% | -50d 6h | 71% | 100% | 2013-11-19 10:00 | 2013-12-11 16:00 | 2014-04-04 10:00 | 2014-01-13 09:00 | 2014-02-10 10:00 | 2014-03-20 11:00 | 2013-12-02 12:00 | 2013-12-12 16:00 | 2013-12-30 12:00 | 310062.9887 | 337769.2101 | 337756.4842 | 338252.7341 | 376580.1142 | 377275.5811 | 337766.6646 | 337865.5297 | 0.71 | 0.71355 | 0.71364 | 1 | -50.75 | 0.71355 | 1 | 0.71 | 1
8/11/2013 17:00 | 2013-11-01 17:00 | 2013-11-08 17:00 | 241015.0007 | 174761.3174 | 245846.7154 | 2013-08-28 09:00 | -66253.6833 | 72.51% | -71085.398 | 71.09% | -52d 7h | 70.62% | 100% | 2013-11-15 12:00 | 2013-12-06 14:00 | 2014-03-31 16:00 | 2014-01-17 12:00 | 2014-02-13 10:00 | 2014-03-24 17:00 | 2013-12-04 14:00 | 2013-12-13 17:00 | 2013-12-30 09:00 | 312100.3987 | 339049.5515 | 337217.8023 | 339657.2404 | 374383.6361 | 377815.3329 | 338677.3496 | 339170.4586 | 0.70625 | 0.71085 | 0.72511 | 1 | -52.875 | 0.71085 | 1 | 0.70625 | 1
15/11/2013 17:00 | 2013-11-08 17:00 | 2013-11-15 17:00 | 241015.0007 | 192565.4217 | 265726.7154 | 2013-09-02 11:00 | -48449.579 | 79.9% | -73161.2937 | 72.47% | -54d 5h | 70.47% | 100% | 2013-10-31 16:00 | 2013-11-12 09:00 | 2014-02-14 17:00 | 2014-01-08 10:00 | 2014-01-21 12:00 | 2014-02-14 10:00 | 2013-12-06 11:00 | 2013-12-16 11:00 | 2013-12-26 09:00 | 314176.2944 | 332583.7211 | 326366.2384 | 334475.8783 | 349404.985 | 360595.7167 | 331240.2757 | 332953.774 | 0.70473 | 0.72467 | 0.79898 | 1 | -54.625 | 0.72467 | 1 | 0.70473 | 1
22/11/2013 17:00 | 2013-11-15 17:00 | 2013-11-22 17:00 | 241015.0007 | 221193.3643 | 294735.2868 | 2013-09-06 11:00 | -19821.6364 | 91.78% | -73541.9225 | 75.05% | -55d 5h | 70.72% | 100% | 2013-10-08 14:00 | 2013-10-09 15:00 | 2013-12-23 09:00 | 2013-12-16 14:00 | 2013-12-17 17:00 | 2013-12-25 14:00 | 2013-12-09 11:00 | 2013-12-13 14:00 | 2013-12-20 12:00 | 314556.9232 | 321147.1807 | 316333.1847 | 322762.1587 | 323514.0101 | 332080.4764 | 320020.0281 | 321455.1133 | 0.70724 | 0.75048 | 0.91776 | 1 | -55.625 | 0.75048 | 1 | 0.70724 | 1
29/11/2013 17:00 | 2013-11-22 17:00 | 2013-11-29 17:00 | 241015.0007 | 224415.0007 | 298256.144 | 2013-09-11 15:00 | -16600 | 93.11% | -73841.1433 | 75.24% | -57d 2h | 70.64% | 100% | 2013-10-04 15:00 | 2013-10-07 12:00 | 2013-12-17 14:00 | 2013-12-19 11:00 | 2013-12-20 11:00 | 2013-12-27 09:00 | 2013-12-10 17:00 | 2013-12-13 16:00 | 2013-12-19 09:00 | 314856.144 | 320318.1807 | 316084.0476 | 321755.2365 | 321950.1118 | 329487.3393 | 319317.7529 | 320591.3568 | 0.70641 | 0.75242 | 0.93112 | 1 | -57.25 | 0.75242 | 1 | 0.70641 | 1
6/12/2013 17:00 | 2013-11-29 17:00 | 2013-12-06 17:00 | 241015.0007 | 240915.0007 | 314756.144 | 2013-09-19 15:00 | -100 | 99.96% | -73841.1433 | 76.54% | -56d 2h | 71.88% | 100% | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-11-22 10:00 | 2013-12-09 09:00 | 2013-12-09 09:00 | 2013-12-09 09:00 | 2013-12-09 17:00 | 2013-12-10 11:00 | 2013-12-10 16:00 | 314856.144 | 314886.7943 | 314856.1855 | 314895.2744 | 314886.8485 | 314937.9183 | 314879.2605 | 314888.4066 | 0.71875 | 0.7654 | 0.99959 | 1 | -56.25 | 0.7654 | 1 | 0.71875 | 1
13/12/2013 17:00 | 2013-12-06 17:00 | 2013-12-13 17:00 | 241015.0007 | 241015.0007 | 314856.144 | 2013-09-20 15:00 | 0 | 100% | -73841.1433 | 76.55% | -60d 2h | 70.61% | 100% | 2013-09-20 15:00 | 2013-09-20 15:00 | 2013-11-22 09:00 | 2013-12-13 17:00 | 2013-12-13 17:00 | 2013-12-13 17:00 | 2013-12-13 17:00 | 2013-12-13 17:00 | 2013-12-13 17:00 | 314856.144 | 314856.144 | 314856.144 | 314856.144 | 314856.144 | 314856.144 | 314856.144 | 314856.144 | 0.7061 | 0.76548 | 1 | 1 | -60.25 | 0.76548 | 1 | 0.7061 | 1