## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House (1) | 1 |  |  | 2016-03-08 08:00 | 2017-02-07 17:00 | 241d |  |  | 162472 |  |  | 162472 | 336.375
56 | Voorbereiding | 1.1 |  |  | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  |  | 14539 |  |  | 14539 | 29.375
1 | Werfinrichting, werftoiletten | 1.1.1 |  | FS8 | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 2848 | 0 | 0 | 2848 | 6.375
2 | Voorbereiding oplevering | 1.1.2 |  | FS8 | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 30 | 0 | 0 | 30 | 0.375
3 | Transportkosten | 1.1.3 |  | FS8 | 2016-03-08 08:00 | 2016-03-10 17:00 | 3d |  | 0 | 790 | 0 | 0 | 790 | 2.375
4 | Rijtijden ploegen | 1.1.4 |  | FS8 | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 0.375
5 | Magazijn | 1.1.5 |  | FS8 | 2016-03-08 08:00 | 2016-03-11 17:00 | 4d |  | 0 | 943 | 0 | 0 | 943 | 3.375
6 | Studiekosten projectontwikkelaar | 1.1.6 |  | FS8 | 2016-03-08 08:00 | 2016-03-23 17:00 | 12d |  | 0 | 3318 | 0 | 0 | 3318 | 15.375
7 | Studiekosten aannemer | 1.1.7 |  | FS8 | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  | 0 | 6510 | 0 | 0 | 6510 | 29.375
57 | Funderingen | 1.2 |  |  | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  |  | 11167 |  |  | 11167 | 33.375
8 | Funderingen | 1.2.1 | 1FS;2FS;3FS;4FS;5FS;6FS;7FS | FS9 | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  | 0 | 11167 | 0 | 0 | 11167 | 33.375
58 | Ruwbouw | 1.3 |  |  | 2016-05-11 08:00 | 2016-08-12 17:00 | 68d |  |  | 46742 |  |  | 46742 | 93.375
9 | GEWA/Metselwerk | 1.3.1 | 8FS | FS10;FS11 | 2016-05-11 08:00 | 2016-06-02 17:00 | 17d |  | 0 | 13968 | 0 | 0 | 13968 | 22.375
10 | Gewelven/Structuur | 1.3.2 | 9FS | FS12 | 2016-06-03 08:00 | 2016-06-07 17:00 | 3d |  | 0 | 5417 | 0 | 0 | 5417 | 4.375
11 | Uitbranden GEWA | 1.3.3 | 9FS | FS12 | 2016-06-03 08:00 | 2016-06-03 17:00 | 1d |  | 0 | 341 | 0 | 0 | 341 | 0.375
12 | Isolatie | 1.3.4 | 10FS;11FS | FS13 | 2016-06-08 08:00 | 2016-06-15 17:00 | 6d |  | 0 | 4629 | 0 | 0 | 4629 | 7.375
13 | Parament | 1.3.5 | 12FS | FS14 | 2016-06-16 08:00 | 2016-07-22 17:00 | 27d |  | 0 | 15804 | 0 | 0 | 15804 | 36.375
14 | Ytong/gipswanden | 1.3.6 | 13FS | FS15;FS16 | 2016-07-25 08:00 | 2016-07-28 17:00 | 4d |  | 0 | 2696 | 0 | 0 | 2696 | 3.375
15 | Dorpels | 1.3.7 | 14FS | FS17 | 2016-07-29 08:00 | 2016-07-29 17:00 | 1d |  | 0 | 646 | 0 | 0 | 646 | 0.375
16 | Voegwerk | 1.3.8 | 14FS | FS17 | 2016-07-29 08:00 | 2016-08-08 17:00 | 7d |  | 0 | 1821 | 0 | 0 | 1821 | 10.375
17 | Stelling | 1.3.9 | 15FS;16FS | FS18 | 2016-08-09 08:00 | 2016-08-12 17:00 | 4d |  | 0 | 1420 | 0 | 0 | 1420 | 3.375
59 | Dakwerken | 1.4 |  |  | 2016-08-15 08:00 | 2016-09-26 17:00 | 31d |  |  | 17795 |  |  | 17795 | 42.375
18 | Daktimmer traditioneel / prefabkap | 1.4.1 | 17FS | FS19 | 2016-08-15 08:00 | 2016-09-02 17:00 | 15d |  | 0 | 9252 | 0 | 0 | 9252 | 18.375
19 | Dakdekken | 1.4.2 | 18FS | FS21;FS20;FS22 | 2016-09-05 08:00 | 2016-09-08 17:00 | 4d |  | 0 | 2317 | 0 | 0 | 2317 | 3.375
20 | Goten & afleiders | 1.4.3 | 19FS |  | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 177 | 0 | 0 | 177 | 0.375
21 | Zonnepanelen | 1.4.4 | 19FS |  | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 245 | 0 | 0 | 245 | 0.375
22 | Oversteken / gevelbekleding | 1.4.5 | 19FS | FS23;FS24 | 2016-09-09 08:00 | 2016-09-14 17:00 | 4d |  | 0 | 1509 | 0 | 0 | 1509 | 5.375
23 | Afdichting/Groendaken/Plat dak | 1.4.6 | 22FS | FS25 | 2016-09-15 08:00 | 2016-09-26 17:00 | 8d |  | 0 | 3438 | 0 | 0 | 3438 | 11.375
24 | Dakvlakramen | 1.4.7 | 22FS | FS25 | 2016-09-15 08:00 | 2016-09-19 17:00 | 3d |  | 0 | 857 | 0 | 0 | 857 | 4.375
60 | Buitenschrijnwerk | 1.5 |  |  | 2016-09-27 08:00 | 2016-10-10 17:00 | 10d |  |  | 11316 |  |  | 11316 | 13.375
25 | Kader buitenschrijnwerk Wachtbuizen | 1.5.1 | 23FS;24FS | FS26 | 2016-09-27 08:00 | 2016-09-30 17:00 | 4d |  | 0 | 1783 | 0 | 0 | 1783 | 3.375
26 | Buitenschrijnwerk plaatsen | 1.5.2 | 25FS | FS27;FS28;FS29;FS39;FS40 | 2016-10-03 08:00 | 2016-10-07 17:00 | 5d |  | 0 | 8910 | 0 | 0 | 8910 | 4.375
27 | Elastische voegen | 1.5.3 | 26FS |  | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 0.375
28 | Ballustrades/trapleuningen | 1.5.4 | 26FS |  | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 297 | 0 | 0 | 297 | 0.375
29 | Poort | 1.5.5 | 26FS |  | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 276 | 0 | 0 | 276 | 0.375
61 | Binnenafwerking | 1.6 |  |  | 2016-11-10 08:00 | 2017-01-11 17:00 | 45d |  |  | 28749 |  |  | 28749 | 62.375
30 | Plakwerken | 1.6.1 | 49FS | FS31 | 2016-11-10 08:00 | 2016-11-23 17:00 | 10d |  | 0 | 6891 | 0 | 0 | 6891 | 13.375
31 | Chapes | 1.6.2 | 30FS | FS42 | 2016-11-24 08:00 | 2016-12-12 17:00 | 13d |  | 0 | 4779 | 0 | 0 | 4779 | 18.375
32 | Vloerisolatie | 1.6.3 | 42FS | FS33 | 2016-12-14 08:00 | 2016-12-15 17:00 | 2d |  | 0 | 2697 | 0 | 0 | 2697 | 1.375
33 | Tegelwerken | 1.6.4 | 32FS | FS34;FS35;FS36;FS37;FS38;FS46 | 2016-12-16 08:00 | 2016-12-30 17:00 | 11d |  | 0 | 3027 | 0 | 0 | 3027 | 14.375
34 | Buisbek/zoldluik/platen zold/stijl | 1.6.5 | 33FS |  | 2017-01-02 08:00 | 2017-01-02 17:00 | 1d |  | 0 | 227 | 0 | 0 | 227 | 0.375
35 | Binnendeuren/Uitbekledingen | 1.6.6 | 33FS |  | 2017-01-02 08:00 | 2017-01-05 17:00 | 4d |  | 0 | 987 | 0 | 0 | 987 | 3.375
36 | Trap | 1.6.7 | 33FS |  | 2017-01-02 08:00 | 2017-01-11 17:00 | 8d |  | 0 | 2150 | 0 | 0 | 2150 | 9.375
37 | Luchtdichten | 1.6.8 | 33FS |  | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 491 | 0 | 0 | 491 | 1.375
38 | Keuken (laminaat, kasten) | 1.6.9 | 33FS |  | 2017-01-02 08:00 | 2017-01-10 17:00 | 7d |  | 0 | 7500 | 0 | 0 | 7500 | 8.375
62 | Technieken | 1.7 |  |  | 2016-10-10 08:00 | 2017-01-31 17:00 | 82d |  |  | 30762 |  |  | 30762 | 113.375
39 | UZL | 1.7.1 | 26FS | FS41 | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2.375
40 | Betonplexplaten | 1.7.2 | 26FS | FS41 | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2.375
41 | Slijpen technieken / boringen | 1.7.3 | 39FS;40FS | FS43 | 2016-10-13 08:00 | 2016-10-19 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 | 6.375
42 | Bad en douche | 1.7.4 | 31FS | FS32 | 2016-12-13 08:00 | 2016-12-13 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 | 0.375
43 | Leidingen ventilatie | 1.7.5 | 41FS | FS44 | 2016-10-20 08:00 | 2016-10-24 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 | 4.375
44 | Leidingen san/CV/WP | 1.7.6 | 43FS | FS45 | 2016-10-25 08:00 | 2016-10-28 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 | 3.375
45 | Leidingen vloerverwarming | 1.7.7 | 44FS | FS49 | 2016-10-31 08:00 | 2016-11-03 17:00 | 4d |  | 0 | 2102 | 0 | 0 | 2102 | 3.375
46 | Afwerken ventilatie | 1.7.8 | 33FS | FS47 | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 | 1.375
47 | Afwerken sanitair | 1.7.9 | 46FS | FS48 | 2017-01-04 08:00 | 2017-01-05 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 | 1.375
48 | Afwerken CV/WP | 1.7.10 | 47FS | FS50 | 2017-01-06 08:00 | 2017-01-11 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 | 5.375
49 | Leidingen electro | 1.7.11 | 45FS | FS30 | 2016-11-04 08:00 | 2016-11-09 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 | 5.375
50 | Afwerken electro | 1.7.12 | 48FS | FS51;FS52;FS53;FS54 | 2017-01-12 08:00 | 2017-01-18 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 | 6.375
51 | Verlichting | 1.7.13 | 50FS | FS55 | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 0.375
52 | Programmatie domotica | 1.7.14 | 50FS | FS55 | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 600 | 0 | 0 | 600 | 0.375
53 | Diepsondering, bron en aansluiting | 1.7.15 | 50FS | FS55 | 2017-01-19 08:00 | 2017-01-31 17:00 | 9d |  | 0 | 2460 | 0 | 0 | 2460 | 12.375
54 | Karweien | 1.7.16 | 50FS | FS55 | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 160 | 0 | 0 | 160 | 0.375
63 | Omgevingswerken | 1.8 |  |  | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  |  | 1402 |  |  | 1402 | 6.375
55 | Opkuis werk (afvoer puin en afval) | 1.8.1 | 51FS;52FS;53FS;54FS |  | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  | 0 | 1402 | 0 | 0 | 1402 | 6.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House (1) | 1928h |  |  |  |  | 99 | 100 | 101
56 | Voorbereiding | 176h |  |  |  |  | 99 | 100 | 101
1 | Werfinrichting, werftoiletten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Voorbereiding oplevering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Transportkosten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Rijtijden ploegen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Magazijn | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Studiekosten projectontwikkelaar | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Studiekosten aannemer | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Funderingen | 192h |  |  |  |  | 99 | 100 | 101
8 | Funderingen | 192h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
58 | Ruwbouw | 544h |  |  |  |  | 99 | 100 | 101
9 | GEWA/Metselwerk | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Gewelven/Structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Uitbranden GEWA | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Isolatie | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Parament | 216h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Ytong/gipswanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Dorpels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Voegwerk | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Stelling | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Dakwerken | 248h |  |  |  |  | 99 | 100 | 101
18 | Daktimmer traditioneel / prefabkap | 120h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
19 | Dakdekken | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Goten & afleiders | 8h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
21 | Zonnepanelen | 8h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
22 | Oversteken / gevelbekleding | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
23 | Afdichting/Groendaken/Plat dak | 64h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
24 | Dakvlakramen | 24h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
60 | Buitenschrijnwerk | 80h |  |  |  |  | 99 | 100 | 101
25 | Kader buitenschrijnwerk Wachtbuizen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Buitenschrijnwerk plaatsen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Elastische voegen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Ballustrades/trapleuningen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Poort | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Binnenafwerking | 360h |  |  |  |  | 99 | 100 | 101
30 | Plakwerken | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
31 | Chapes | 104h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
32 | Vloerisolatie | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
33 | Tegelwerken | 88h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
34 | Buisbek/zoldluik/platen zold/stijl | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
35 | Binnendeuren/Uitbekledingen | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
36 | Trap | 64h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
37 | Luchtdichten | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
38 | Keuken (laminaat, kasten) | 56h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
62 | Technieken | 656h |  |  |  |  | 99 | 100 | 101
39 | UZL | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
40 | Betonplexplaten | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
41 | Slijpen technieken / boringen | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
42 | Bad en douche | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
43 | Leidingen ventilatie | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
44 | Leidingen san/CV/WP | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
45 | Leidingen vloerverwarming | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
46 | Afwerken ventilatie | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
47 | Afwerken sanitair | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
48 | Afwerken CV/WP | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
49 | Leidingen electro | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
50 | Afwerken electro | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
51 | Verlichting | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
52 | Programmatie domotica | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
53 | Diepsondering, bron en aansluiting | 72h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
54 | Karweien | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
63 | Omgevingswerken | 40h |  |  |  |  | 99 | 100 | 101
55 | Opkuis werk (afvoer puin en afval) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2016-05-17 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (1) | 2016-03-08 08:00 | 2017-02-07 17:00 | 241d |  |  | 162472 |  |  | 162472 |  | 50d | [5 empty] | 25566 |  | 15.82% |  | 25706 | 39674
56 | Voorbereiding | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  |  | 14539 |  |  | 14539 |  | 22d | [5 empty] | 13303 |  | 100% |  | 14539 | 14539
1 | Werfinrichting, werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 2848 | 0 | 0 | 2848 | 2016-03-08 08:00 | 4d | 2848 | 0 | 0 | -267 | 0 | 2581 | 0 | 100% | Finished | 2848 | 2848 | 100 | 80 | 100 | 100 | 90.625 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 30 | 0 | 0 | 30 | 2016-03-08 08:00 | 1d | 30 | 0 | 0 | -1 | 0 | 29 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 96.6667 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-10 17:00 | 3d |  | 0 | 790 | 0 | 0 | 790 | 2016-03-08 08:00 | 1d | 790 | 0 | 0 | -687 | 0 | 103 | 0 | 100% | Finished | 790 | 790 | 100 | 33.3333 | 100 | 100 | 13.038 | 100
4 | Rijtijden ploegen | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-03-08 08:00 | 1d | 100 | 0 | 0 | 2 | 0 | 102 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 102 | 100
5 | Magazijn | 2016-03-08 08:00 | 2016-03-11 17:00 | 4d |  | 0 | 943 | 0 | 0 | 943 | 2016-03-08 08:00 | 2d | 943 | 0 | 0 | -480 | 0 | 463 | 0 | 100% | Finished | 943 | 943 | 100 | 50 | 100 | 100 | 49.0986 | 100
6 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-23 17:00 | 12d |  | 0 | 3318 | 0 | 0 | 3318 | 2016-03-08 08:00 | 10d | 3318 | 0 | 0 | 207 | 0 | 3525 | 0 | 100% | Finished | 3318 | 3318 | 100 | 83.3333 | 100 | 100 | 106.2387 | 100
7 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  | 0 | 6510 | 0 | 0 | 6510 | 2016-03-08 08:00 | 22d | 6510 | 0 | 0 | -10 | 0 | 6500 | 0 | 100% | Finished | 6510 | 6510 | 100 | 100 | 100 | 100 | 99.8464 | 100
57 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  |  | 11167 |  |  | 11167 |  | 28d | [5 empty] | 12263 |  | 100% |  | 11167 | 11167
8 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  | 0 | 11167 | 0 | 0 | 11167 | 2016-04-07 08:00 | 28d | 11167 | 0 | 0 | 1096 | 0 | 12263 | 0 | 100% | Finished | 11167 | 11167 | 100 | 116.6667 | 100 | 100 | 109.8146 | 100
58 | Ruwbouw | 2016-05-11 08:00 | 2016-08-12 17:00 | 68d |  |  | 46742 |  |  | 46742 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 13968
9 | GEWA/Metselwerk | 2016-05-11 08:00 | 2016-06-02 17:00 | 17d |  | 0 | 13968 | 0 | 0 | 13968 |  | 0 | 0 | 13968 | 17d | 0 | 0 | 0 | 13968 | 0% | Not Started | 0 | 13968 | 100 |  | 0 | 100 |  | 0
10 | Gewelven/Structuur | 2016-06-03 08:00 | 2016-06-07 17:00 | 3d |  | 0 | 5417 | 0 | 0 | 5417 |  | 0 | 0 | 5417 | 3d | 0 | 0 | 0 | 5417 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Uitbranden GEWA | 2016-06-03 08:00 | 2016-06-03 17:00 | 1d |  | 0 | 341 | 0 | 0 | 341 |  | 0 | 0 | 341 | 1d | 0 | 0 | 0 | 341 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Isolatie | 2016-06-08 08:00 | 2016-06-15 17:00 | 6d |  | 0 | 4629 | 0 | 0 | 4629 |  | 0 | 0 | 4629 | 6d | 0 | 0 | 0 | 4629 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Parament | 2016-06-16 08:00 | 2016-07-22 17:00 | 27d |  | 0 | 15804 | 0 | 0 | 15804 |  | 0 | 0 | 15804 | 27d | 0 | 0 | 0 | 15804 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ytong/gipswanden | 2016-07-25 08:00 | 2016-07-28 17:00 | 4d |  | 0 | 2696 | 0 | 0 | 2696 |  | 0 | 0 | 2696 | 4d | 0 | 0 | 0 | 2696 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Dorpels | 2016-07-29 08:00 | 2016-07-29 17:00 | 1d |  | 0 | 646 | 0 | 0 | 646 |  | 0 | 0 | 646 | 1d | 0 | 0 | 0 | 646 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Voegwerk | 2016-07-29 08:00 | 2016-08-08 17:00 | 7d |  | 0 | 1821 | 0 | 0 | 1821 |  | 0 | 0 | 1821 | 7d | 0 | 0 | 0 | 1821 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Stelling | 2016-08-09 08:00 | 2016-08-12 17:00 | 4d |  | 0 | 1420 | 0 | 0 | 1420 |  | 0 | 0 | 1420 | 4d | 0 | 0 | 0 | 1420 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Dakwerken | 2016-08-15 08:00 | 2016-09-26 17:00 | 31d |  |  | 17795 |  |  | 17795 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Daktimmer traditioneel / prefabkap | 2016-08-15 08:00 | 2016-09-02 17:00 | 15d |  | 0 | 9252 | 0 | 0 | 9252 |  | 0 | 0 | 9252 | 15d | 0 | 0 | 0 | 9252 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Dakdekken | 2016-09-05 08:00 | 2016-09-08 17:00 | 4d |  | 0 | 2317 | 0 | 0 | 2317 |  | 0 | 0 | 2317 | 4d | 0 | 0 | 0 | 2317 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Goten & afleiders | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 177 | 0 | 0 | 177 |  | 0 | 0 | 177 | 1d | 0 | 0 | 0 | 177 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Zonnepanelen | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 245 | 0 | 0 | 245 |  | 0 | 0 | 245 | 1d | 0 | 0 | 0 | 245 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Oversteken / gevelbekleding | 2016-09-09 08:00 | 2016-09-14 17:00 | 4d |  | 0 | 1509 | 0 | 0 | 1509 |  | 0 | 0 | 1509 | 4d | 0 | 0 | 0 | 1509 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afdichting/Groendaken/Plat dak | 2016-09-15 08:00 | 2016-09-26 17:00 | 8d |  | 0 | 3438 | 0 | 0 | 3438 |  | 0 | 0 | 3438 | 8d | 0 | 0 | 0 | 3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Dakvlakramen | 2016-09-15 08:00 | 2016-09-19 17:00 | 3d |  | 0 | 857 | 0 | 0 | 857 |  | 0 | 0 | 857 | 3d | 0 | 0 | 0 | 857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Buitenschrijnwerk | 2016-09-27 08:00 | 2016-10-10 17:00 | 10d |  |  | 11316 |  |  | 11316 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-09-27 08:00 | 2016-09-30 17:00 | 4d |  | 0 | 1783 | 0 | 0 | 1783 |  | 0 | 0 | 1783 | 4d | 0 | 0 | 0 | 1783 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Buitenschrijnwerk plaatsen | 2016-10-03 08:00 | 2016-10-07 17:00 | 5d |  | 0 | 8910 | 0 | 0 | 8910 |  | 0 | 0 | 8910 | 5d | 0 | 0 | 0 | 8910 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Elastische voegen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Ballustrades/trapleuningen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 297 | 0 | 0 | 297 |  | 0 | 0 | 297 | 1d | 0 | 0 | 0 | 297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Poort | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 276 | 0 | 0 | 276 |  | 0 | 0 | 276 | 1d | 0 | 0 | 0 | 276 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Binnenafwerking | 2016-11-10 08:00 | 2017-01-11 17:00 | 45d |  |  | 28749 |  |  | 28749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Plakwerken | 2016-11-10 08:00 | 2016-11-23 17:00 | 10d |  | 0 | 6891 | 0 | 0 | 6891 |  | 0 | 0 | 6891 | 10d | 0 | 0 | 0 | 6891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Chapes | 2016-11-24 08:00 | 2016-12-12 17:00 | 13d |  | 0 | 4779 | 0 | 0 | 4779 |  | 0 | 0 | 4779 | 13d | 0 | 0 | 0 | 4779 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Vloerisolatie | 2016-12-14 08:00 | 2016-12-15 17:00 | 2d |  | 0 | 2697 | 0 | 0 | 2697 |  | 0 | 0 | 2697 | 2d | 0 | 0 | 0 | 2697 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Tegelwerken | 2016-12-16 08:00 | 2016-12-30 17:00 | 11d |  | 0 | 3027 | 0 | 0 | 3027 |  | 0 | 0 | 3027 | 11d | 0 | 0 | 0 | 3027 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buisbek/zoldluik/platen zold/stijl | 2017-01-02 08:00 | 2017-01-02 17:00 | 1d |  | 0 | 227 | 0 | 0 | 227 |  | 0 | 0 | 227 | 1d | 0 | 0 | 0 | 227 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Binnendeuren/Uitbekledingen | 2017-01-02 08:00 | 2017-01-05 17:00 | 4d |  | 0 | 987 | 0 | 0 | 987 |  | 0 | 0 | 987 | 4d | 0 | 0 | 0 | 987 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Trap | 2017-01-02 08:00 | 2017-01-11 17:00 | 8d |  | 0 | 2150 | 0 | 0 | 2150 |  | 0 | 0 | 2150 | 8d | 0 | 0 | 0 | 2150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Luchtdichten | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 491 | 0 | 0 | 491 |  | 0 | 0 | 491 | 2d | 0 | 0 | 0 | 491 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Keuken (laminaat, kasten) | 2017-01-02 08:00 | 2017-01-10 17:00 | 7d |  | 0 | 7500 | 0 | 0 | 7500 |  | 0 | 0 | 7500 | 7d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Technieken | 2016-10-10 08:00 | 2017-01-31 17:00 | 82d |  |  | 30762 |  |  | 30762 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | UZL | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Betonplexplaten | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Slijpen technieken / boringen | 2016-10-13 08:00 | 2016-10-19 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 |  | 0 | 0 | 1300 | 5d | 0 | 0 | 0 | 1300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Bad en douche | 2016-12-13 08:00 | 2016-12-13 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 |  | 0 | 0 | 1152 | 1d | 0 | 0 | 0 | 1152 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Leidingen ventilatie | 2016-10-20 08:00 | 2016-10-24 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 |  | 0 | 0 | 1926 | 3d | 0 | 0 | 0 | 1926 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Leidingen san/CV/WP | 2016-10-25 08:00 | 2016-10-28 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 |  | 0 | 0 | 2481 | 4d | 0 | 0 | 0 | 2481 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Leidingen vloerverwarming | 2016-10-31 08:00 | 2016-11-03 17:00 | 4d |  | 0 | 2102 | 0 | 0 | 2102 |  | 0 | 0 | 2102 | 4d | 0 | 0 | 0 | 2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Afwerken ventilatie | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 |  | 0 | 0 | 1899 | 2d | 0 | 0 | 0 | 1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken sanitair | 2017-01-04 08:00 | 2017-01-05 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 |  | 0 | 0 | 2565 | 2d | 0 | 0 | 0 | 2565 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Afwerken CV/WP | 2017-01-06 08:00 | 2017-01-11 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 |  | 0 | 0 | 6352 | 4d | 0 | 0 | 0 | 6352 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Leidingen electro | 2016-11-04 08:00 | 2016-11-09 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 |  | 0 | 0 | 2594 | 4d | 0 | 0 | 0 | 2594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Afwerken electro | 2017-01-12 08:00 | 2017-01-18 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 |  | 0 | 0 | 3608 | 5d | 0 | 0 | 0 | 3608 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Verlichting | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Programmatie domotica | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 600 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Diepsondering, bron en aansluiting | 2017-01-19 08:00 | 2017-01-31 17:00 | 9d |  | 0 | 2460 | 0 | 0 | 2460 |  | 0 | 0 | 2460 | 9d | 0 | 0 | 0 | 2460 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Karweien | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 160 | 0 | 0 | 160 |  | 0 | 0 | 160 | 1d | 0 | 0 | 0 | 160 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Omgevingswerken | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  |  | 1402 |  |  | 1402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opkuis werk (afvoer puin en afval) | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  | 0 | 1402 | 0 | 0 | 1402 |  | 0 | 0 | 1402 | 5d | 0 | 0 | 0 | 1402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-08-19 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (1) | 2016-03-08 08:00 | 2017-02-07 17:00 | 241d |  |  | 162472 |  |  | 162472 |  | 118d | [5 empty] | 71965 |  | 44.59% |  | 72448 | 81700
56 | Voorbereiding | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  |  | 14539 |  |  | 14539 |  | 22d | [5 empty] | 13303 |  | 100% |  | 14539 | 14539
1 | Werfinrichting, werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 2848 | 0 | 0 | 2848 | 2016-03-08 08:00 | 4d | 2848 | 0 | 0 | -267 | 0 | 2581 | 0 | 100% | Finished | 2848 | 2848 | 100 | 80 | 100 | 100 | 90.625 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 30 | 0 | 0 | 30 | 2016-03-08 08:00 | 1d | 30 | 0 | 0 | -1 | 0 | 29 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 96.6667 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-10 17:00 | 3d |  | 0 | 790 | 0 | 0 | 790 | 2016-03-08 08:00 | 1d | 790 | 0 | 0 | -687 | 0 | 103 | 0 | 100% | Finished | 790 | 790 | 100 | 33.3333 | 100 | 100 | 13.038 | 100
4 | Rijtijden ploegen | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-03-08 08:00 | 1d | 100 | 0 | 0 | 2 | 0 | 102 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 102 | 100
5 | Magazijn | 2016-03-08 08:00 | 2016-03-11 17:00 | 4d |  | 0 | 943 | 0 | 0 | 943 | 2016-03-08 08:00 | 2d | 943 | 0 | 0 | -480 | 0 | 463 | 0 | 100% | Finished | 943 | 943 | 100 | 50 | 100 | 100 | 49.0986 | 100
6 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-23 17:00 | 12d |  | 0 | 3318 | 0 | 0 | 3318 | 2016-03-08 08:00 | 10d | 3318 | 0 | 0 | 207 | 0 | 3525 | 0 | 100% | Finished | 3318 | 3318 | 100 | 83.3333 | 100 | 100 | 106.2387 | 100
7 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  | 0 | 6510 | 0 | 0 | 6510 | 2016-03-08 08:00 | 22d | 6510 | 0 | 0 | -10 | 0 | 6500 | 0 | 100% | Finished | 6510 | 6510 | 100 | 100 | 100 | 100 | 99.8464 | 100
57 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  |  | 11167 |  |  | 11167 |  | 28d | [5 empty] | 12263 |  | 100% |  | 11167 | 11167
8 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  | 0 | 11167 | 0 | 0 | 11167 | 2016-04-07 08:00 | 28d | 11167 | 0 | 0 | 1096 | 0 | 12263 | 0 | 100% | Finished | 11167 | 11167 | 100 | 116.6667 | 100 | 100 | 109.8146 | 100
58 | Ruwbouw | 2016-05-11 08:00 | 2016-08-12 17:00 | 68d |  |  | 46742 |  |  | 46742 |  | 68d | [5 empty] | 46399 |  | 100% |  | 46742 | 46742
9 | GEWA/Metselwerk | 2016-05-11 08:00 | 2016-06-02 17:00 | 17d |  | 0 | 13968 | 0 | 0 | 13968 | 2016-05-17 08:00 | 16d | 13968 | 0 | 0 | -536 | 0 | 13432 | 0 | 100% | Finished | 13968 | 13968 | 100 | 94.1176 | 100 | 100 | 96.1627 | 100
10 | Gewelven/Structuur | 2016-06-03 08:00 | 2016-06-07 17:00 | 3d |  | 0 | 5417 | 0 | 0 | 5417 | 2016-06-08 08:00 | 3d | 5417 | 0 | 0 | 0 | 0 | 5417 | 0 | 100% | Finished | 5417 | 5417 | 100 | 100 | 100 | 100 | 100 | 100
11 | Uitbranden GEWA | 2016-06-03 08:00 | 2016-06-03 17:00 | 1d |  | 0 | 341 | 0 | 0 | 341 | 2016-06-08 08:00 | 1d | 341 | 0 | 0 | 0 | 0 | 341 | 0 | 100% | Finished | 341 | 341 | 100 | 100 | 100 | 100 | 100 | 100
12 | Isolatie | 2016-06-08 08:00 | 2016-06-15 17:00 | 6d |  | 0 | 4629 | 0 | 0 | 4629 | 2016-06-13 08:00 | 6d | 4629 | 0 | 0 | 0 | 0 | 4629 | 0 | 100% | Finished | 4629 | 4629 | 100 | 100 | 100 | 100 | 100 | 100
13 | Parament | 2016-06-16 08:00 | 2016-07-22 17:00 | 27d |  | 0 | 15804 | 0 | 0 | 15804 | 2016-06-21 08:00 | 27d | 15804 | 0 | 0 | 92 | 0 | 15896 | 0 | 100% | Finished | 15804 | 15804 | 100 | 100 | 100 | 100 | 100.5821 | 100
14 | Ytong/gipswanden | 2016-07-25 08:00 | 2016-07-28 17:00 | 4d |  | 0 | 2696 | 0 | 0 | 2696 | 2016-07-28 08:00 | 4d | 2696 | 0 | 0 | 0 | 0 | 2696 | 0 | 100% | Finished | 2696 | 2696 | 100 | 100 | 100 | 100 | 100 | 100
15 | Dorpels | 2016-07-29 08:00 | 2016-07-29 17:00 | 1d |  | 0 | 646 | 0 | 0 | 646 | 2016-08-03 08:00 | 1d | 646 | 0 | 0 | 0 | 0 | 646 | 0 | 100% | Finished | 646 | 646 | 100 | 100 | 100 | 100 | 100 | 100
16 | Voegwerk | 2016-07-29 08:00 | 2016-08-08 17:00 | 7d |  | 0 | 1821 | 0 | 0 | 1821 | 2016-08-03 08:00 | 8d | 1821 | 0 | 0 | 312 | 0 | 2133 | 0 | 100% | Finished | 1821 | 1821 | 100 | 114.2857 | 100 | 100 | 117.1334 | 100
17 | Stelling | 2016-08-09 08:00 | 2016-08-12 17:00 | 4d |  | 0 | 1420 | 0 | 0 | 1420 | 2016-08-15 08:00 | 4d | 1420 | 0 | 0 | -211 | 0 | 1209 | 0 | 100% | Finished | 1420 | 1420 | 100 | 100 | 100 | 100 | 85.1408 | 100
59 | Dakwerken | 2016-08-15 08:00 | 2016-09-26 17:00 | 31d |  |  | 17795 |  |  | 17795 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 9252
18 | Daktimmer traditioneel / prefabkap | 2016-08-15 08:00 | 2016-09-02 17:00 | 15d |  | 0 | 9252 | 0 | 0 | 9252 |  | 0 | 0 | 9252 | 15d | 0 | 0 | 0 | 9252 | 0% | Not Started | 0 | 9252 | 100 |  | 0 | 100 |  | 0
19 | Dakdekken | 2016-09-05 08:00 | 2016-09-08 17:00 | 4d |  | 0 | 2317 | 0 | 0 | 2317 |  | 0 | 0 | 2317 | 4d | 0 | 0 | 0 | 2317 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Goten & afleiders | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 177 | 0 | 0 | 177 |  | 0 | 0 | 177 | 1d | 0 | 0 | 0 | 177 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Zonnepanelen | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 245 | 0 | 0 | 245 |  | 0 | 0 | 245 | 1d | 0 | 0 | 0 | 245 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Oversteken / gevelbekleding | 2016-09-09 08:00 | 2016-09-14 17:00 | 4d |  | 0 | 1509 | 0 | 0 | 1509 |  | 0 | 0 | 1509 | 4d | 0 | 0 | 0 | 1509 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afdichting/Groendaken/Plat dak | 2016-09-15 08:00 | 2016-09-26 17:00 | 8d |  | 0 | 3438 | 0 | 0 | 3438 |  | 0 | 0 | 3438 | 8d | 0 | 0 | 0 | 3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Dakvlakramen | 2016-09-15 08:00 | 2016-09-19 17:00 | 3d |  | 0 | 857 | 0 | 0 | 857 |  | 0 | 0 | 857 | 3d | 0 | 0 | 0 | 857 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Buitenschrijnwerk | 2016-09-27 08:00 | 2016-10-10 17:00 | 10d |  |  | 11316 |  |  | 11316 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-09-27 08:00 | 2016-09-30 17:00 | 4d |  | 0 | 1783 | 0 | 0 | 1783 |  | 0 | 0 | 1783 | 4d | 0 | 0 | 0 | 1783 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Buitenschrijnwerk plaatsen | 2016-10-03 08:00 | 2016-10-07 17:00 | 5d |  | 0 | 8910 | 0 | 0 | 8910 |  | 0 | 0 | 8910 | 5d | 0 | 0 | 0 | 8910 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Elastische voegen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Ballustrades/trapleuningen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 297 | 0 | 0 | 297 |  | 0 | 0 | 297 | 1d | 0 | 0 | 0 | 297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Poort | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 276 | 0 | 0 | 276 |  | 0 | 0 | 276 | 1d | 0 | 0 | 0 | 276 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Binnenafwerking | 2016-11-10 08:00 | 2017-01-11 17:00 | 45d |  |  | 28749 |  |  | 28749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Plakwerken | 2016-11-10 08:00 | 2016-11-23 17:00 | 10d |  | 0 | 6891 | 0 | 0 | 6891 |  | 0 | 0 | 6891 | 10d | 0 | 0 | 0 | 6891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Chapes | 2016-11-24 08:00 | 2016-12-12 17:00 | 13d |  | 0 | 4779 | 0 | 0 | 4779 |  | 0 | 0 | 4779 | 13d | 0 | 0 | 0 | 4779 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Vloerisolatie | 2016-12-14 08:00 | 2016-12-15 17:00 | 2d |  | 0 | 2697 | 0 | 0 | 2697 |  | 0 | 0 | 2697 | 2d | 0 | 0 | 0 | 2697 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Tegelwerken | 2016-12-16 08:00 | 2016-12-30 17:00 | 11d |  | 0 | 3027 | 0 | 0 | 3027 |  | 0 | 0 | 3027 | 11d | 0 | 0 | 0 | 3027 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buisbek/zoldluik/platen zold/stijl | 2017-01-02 08:00 | 2017-01-02 17:00 | 1d |  | 0 | 227 | 0 | 0 | 227 |  | 0 | 0 | 227 | 1d | 0 | 0 | 0 | 227 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Binnendeuren/Uitbekledingen | 2017-01-02 08:00 | 2017-01-05 17:00 | 4d |  | 0 | 987 | 0 | 0 | 987 |  | 0 | 0 | 987 | 4d | 0 | 0 | 0 | 987 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Trap | 2017-01-02 08:00 | 2017-01-11 17:00 | 8d |  | 0 | 2150 | 0 | 0 | 2150 |  | 0 | 0 | 2150 | 8d | 0 | 0 | 0 | 2150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Luchtdichten | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 491 | 0 | 0 | 491 |  | 0 | 0 | 491 | 2d | 0 | 0 | 0 | 491 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Keuken (laminaat, kasten) | 2017-01-02 08:00 | 2017-01-10 17:00 | 7d |  | 0 | 7500 | 0 | 0 | 7500 |  | 0 | 0 | 7500 | 7d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Technieken | 2016-10-10 08:00 | 2017-01-31 17:00 | 82d |  |  | 30762 |  |  | 30762 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | UZL | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Betonplexplaten | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Slijpen technieken / boringen | 2016-10-13 08:00 | 2016-10-19 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 |  | 0 | 0 | 1300 | 5d | 0 | 0 | 0 | 1300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Bad en douche | 2016-12-13 08:00 | 2016-12-13 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 |  | 0 | 0 | 1152 | 1d | 0 | 0 | 0 | 1152 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Leidingen ventilatie | 2016-10-20 08:00 | 2016-10-24 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 |  | 0 | 0 | 1926 | 3d | 0 | 0 | 0 | 1926 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Leidingen san/CV/WP | 2016-10-25 08:00 | 2016-10-28 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 |  | 0 | 0 | 2481 | 4d | 0 | 0 | 0 | 2481 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Leidingen vloerverwarming | 2016-10-31 08:00 | 2016-11-03 17:00 | 4d |  | 0 | 2102 | 0 | 0 | 2102 |  | 0 | 0 | 2102 | 4d | 0 | 0 | 0 | 2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Afwerken ventilatie | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 |  | 0 | 0 | 1899 | 2d | 0 | 0 | 0 | 1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken sanitair | 2017-01-04 08:00 | 2017-01-05 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 |  | 0 | 0 | 2565 | 2d | 0 | 0 | 0 | 2565 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Afwerken CV/WP | 2017-01-06 08:00 | 2017-01-11 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 |  | 0 | 0 | 6352 | 4d | 0 | 0 | 0 | 6352 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Leidingen electro | 2016-11-04 08:00 | 2016-11-09 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 |  | 0 | 0 | 2594 | 4d | 0 | 0 | 0 | 2594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Afwerken electro | 2017-01-12 08:00 | 2017-01-18 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 |  | 0 | 0 | 3608 | 5d | 0 | 0 | 0 | 3608 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Verlichting | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Programmatie domotica | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 600 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Diepsondering, bron en aansluiting | 2017-01-19 08:00 | 2017-01-31 17:00 | 9d |  | 0 | 2460 | 0 | 0 | 2460 |  | 0 | 0 | 2460 | 9d | 0 | 0 | 0 | 2460 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Karweien | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 160 | 0 | 0 | 160 |  | 0 | 0 | 160 | 1d | 0 | 0 | 0 | 160 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Omgevingswerken | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  |  | 1402 |  |  | 1402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opkuis werk (afvoer puin en afval) | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  | 0 | 1402 | 0 | 0 | 1402 |  | 0 | 0 | 1402 | 5d | 0 | 0 | 0 | 1402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-10-04 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (1) | 2016-03-08 08:00 | 2017-02-07 17:00 | 241d |  |  | 162472 |  |  | 162472 |  | 150d | [5 empty] | 91166 |  | 55.54% |  | 90243 | 100936
56 | Voorbereiding | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  |  | 14539 |  |  | 14539 |  | 22d | [5 empty] | 13303 |  | 100% |  | 14539 | 14539
1 | Werfinrichting, werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 2848 | 0 | 0 | 2848 | 2016-03-08 08:00 | 4d | 2848 | 0 | 0 | -267 | 0 | 2581 | 0 | 100% | Finished | 2848 | 2848 | 100 | 80 | 100 | 100 | 90.625 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 30 | 0 | 0 | 30 | 2016-03-08 08:00 | 1d | 30 | 0 | 0 | -1 | 0 | 29 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 96.6667 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-10 17:00 | 3d |  | 0 | 790 | 0 | 0 | 790 | 2016-03-08 08:00 | 1d | 790 | 0 | 0 | -687 | 0 | 103 | 0 | 100% | Finished | 790 | 790 | 100 | 33.3333 | 100 | 100 | 13.038 | 100
4 | Rijtijden ploegen | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-03-08 08:00 | 1d | 100 | 0 | 0 | 2 | 0 | 102 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 102 | 100
5 | Magazijn | 2016-03-08 08:00 | 2016-03-11 17:00 | 4d |  | 0 | 943 | 0 | 0 | 943 | 2016-03-08 08:00 | 2d | 943 | 0 | 0 | -480 | 0 | 463 | 0 | 100% | Finished | 943 | 943 | 100 | 50 | 100 | 100 | 49.0986 | 100
6 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-23 17:00 | 12d |  | 0 | 3318 | 0 | 0 | 3318 | 2016-03-08 08:00 | 10d | 3318 | 0 | 0 | 207 | 0 | 3525 | 0 | 100% | Finished | 3318 | 3318 | 100 | 83.3333 | 100 | 100 | 106.2387 | 100
7 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  | 0 | 6510 | 0 | 0 | 6510 | 2016-03-08 08:00 | 22d | 6510 | 0 | 0 | -10 | 0 | 6500 | 0 | 100% | Finished | 6510 | 6510 | 100 | 100 | 100 | 100 | 99.8464 | 100
57 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  |  | 11167 |  |  | 11167 |  | 28d | [5 empty] | 12263 |  | 100% |  | 11167 | 11167
8 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  | 0 | 11167 | 0 | 0 | 11167 | 2016-04-07 08:00 | 28d | 11167 | 0 | 0 | 1096 | 0 | 12263 | 0 | 100% | Finished | 11167 | 11167 | 100 | 116.6667 | 100 | 100 | 109.8146 | 100
58 | Ruwbouw | 2016-05-11 08:00 | 2016-08-12 17:00 | 68d |  |  | 46742 |  |  | 46742 |  | 68d | [5 empty] | 46399 |  | 100% |  | 46742 | 46742
9 | GEWA/Metselwerk | 2016-05-11 08:00 | 2016-06-02 17:00 | 17d |  | 0 | 13968 | 0 | 0 | 13968 | 2016-05-17 08:00 | 16d | 13968 | 0 | 0 | -536 | 0 | 13432 | 0 | 100% | Finished | 13968 | 13968 | 100 | 94.1176 | 100 | 100 | 96.1627 | 100
10 | Gewelven/Structuur | 2016-06-03 08:00 | 2016-06-07 17:00 | 3d |  | 0 | 5417 | 0 | 0 | 5417 | 2016-06-08 08:00 | 3d | 5417 | 0 | 0 | 0 | 0 | 5417 | 0 | 100% | Finished | 5417 | 5417 | 100 | 100 | 100 | 100 | 100 | 100
11 | Uitbranden GEWA | 2016-06-03 08:00 | 2016-06-03 17:00 | 1d |  | 0 | 341 | 0 | 0 | 341 | 2016-06-08 08:00 | 1d | 341 | 0 | 0 | 0 | 0 | 341 | 0 | 100% | Finished | 341 | 341 | 100 | 100 | 100 | 100 | 100 | 100
12 | Isolatie | 2016-06-08 08:00 | 2016-06-15 17:00 | 6d |  | 0 | 4629 | 0 | 0 | 4629 | 2016-06-13 08:00 | 6d | 4629 | 0 | 0 | 0 | 0 | 4629 | 0 | 100% | Finished | 4629 | 4629 | 100 | 100 | 100 | 100 | 100 | 100
13 | Parament | 2016-06-16 08:00 | 2016-07-22 17:00 | 27d |  | 0 | 15804 | 0 | 0 | 15804 | 2016-06-21 08:00 | 27d | 15804 | 0 | 0 | 92 | 0 | 15896 | 0 | 100% | Finished | 15804 | 15804 | 100 | 100 | 100 | 100 | 100.5821 | 100
14 | Ytong/gipswanden | 2016-07-25 08:00 | 2016-07-28 17:00 | 4d |  | 0 | 2696 | 0 | 0 | 2696 | 2016-07-28 08:00 | 4d | 2696 | 0 | 0 | 0 | 0 | 2696 | 0 | 100% | Finished | 2696 | 2696 | 100 | 100 | 100 | 100 | 100 | 100
15 | Dorpels | 2016-07-29 08:00 | 2016-07-29 17:00 | 1d |  | 0 | 646 | 0 | 0 | 646 | 2016-08-03 08:00 | 1d | 646 | 0 | 0 | 0 | 0 | 646 | 0 | 100% | Finished | 646 | 646 | 100 | 100 | 100 | 100 | 100 | 100
16 | Voegwerk | 2016-07-29 08:00 | 2016-08-08 17:00 | 7d |  | 0 | 1821 | 0 | 0 | 1821 | 2016-08-03 08:00 | 8d | 1821 | 0 | 0 | 312 | 0 | 2133 | 0 | 100% | Finished | 1821 | 1821 | 100 | 114.2857 | 100 | 100 | 117.1334 | 100
17 | Stelling | 2016-08-09 08:00 | 2016-08-12 17:00 | 4d |  | 0 | 1420 | 0 | 0 | 1420 | 2016-08-15 08:00 | 4d | 1420 | 0 | 0 | -211 | 0 | 1209 | 0 | 100% | Finished | 1420 | 1420 | 100 | 100 | 100 | 100 | 85.1408 | 100
59 | Dakwerken | 2016-08-15 08:00 | 2016-09-26 17:00 | 31d |  |  | 17795 |  |  | 17795 |  | 32d | [5 empty] | 19201 |  | 100% |  | 17795 | 17795
18 | Daktimmer traditioneel / prefabkap | 2016-08-15 08:00 | 2016-09-02 17:00 | 15d |  | 0 | 9252 | 0 | 0 | 9252 | 2016-08-19 08:00 | 16d | 9252 | 0 | 0 | 691 | 0 | 9943 | 0 | 100% | Finished | 9252 | 9252 | 100 | 106.6667 | 100 | 100 | 107.4687 | 100
19 | Dakdekken | 2016-09-05 08:00 | 2016-09-08 17:00 | 4d |  | 0 | 2317 | 0 | 0 | 2317 | 2016-09-12 08:00 | 4d | 2317 | 0 | 0 | 0 | 0 | 2317 | 0 | 100% | Finished | 2317 | 2317 | 100 | 100 | 100 | 100 | 100 | 100
20 | Goten & afleiders | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 177 | 0 | 0 | 177 | 2016-09-16 08:00 | 2d | 177 | 0 | 0 | 143 | 0 | 320 | 0 | 100% | Finished | 177 | 177 | 100 | 200 | 100 | 100 | 180.791 | 100
21 | Zonnepanelen | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 245 | 0 | 0 | 245 | 2016-09-16 08:00 | 1d | 245 | 0 | 0 | 4 | 0 | 249 | 0 | 100% | Finished | 245 | 245 | 100 | 100 | 100 | 100 | 101.6327 | 100
22 | Oversteken / gevelbekleding | 2016-09-09 08:00 | 2016-09-14 17:00 | 4d |  | 0 | 1509 | 0 | 0 | 1509 | 2016-09-16 08:00 | 4d | 1509 | 0 | 0 | 14 | 0 | 1523 | 0 | 100% | Finished | 1509 | 1509 | 100 | 100 | 100 | 100 | 100.9278 | 100
23 | Afdichting/Groendaken/Plat dak | 2016-09-15 08:00 | 2016-09-26 17:00 | 8d |  | 0 | 3438 | 0 | 0 | 3438 | 2016-09-22 08:00 | 8d | 3438 | 0 | 0 | 21 | 0 | 3459 | 0 | 100% | Finished | 3438 | 3438 | 100 | 100 | 100 | 100 | 100.6108 | 100
24 | Dakvlakramen | 2016-09-15 08:00 | 2016-09-19 17:00 | 3d |  | 0 | 857 | 0 | 0 | 857 | 2016-09-22 08:00 | 5d | 857 | 0 | 0 | 533 | 0 | 1390 | 0 | 100% | Finished | 857 | 857 | 100 | 166.6667 | 100 | 100 | 162.1937 | 100
60 | Buitenschrijnwerk | 2016-09-27 08:00 | 2016-10-10 17:00 | 10d |  |  | 11316 |  |  | 11316 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10693
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-09-27 08:00 | 2016-09-30 17:00 | 4d |  | 0 | 1783 | 0 | 0 | 1783 |  | 0 | 0 | 1783 | 4d | 0 | 0 | 0 | 1783 | 0% | Not Started | 0 | 1783 | 100 |  | 0 | 100 |  | 0
26 | Buitenschrijnwerk plaatsen | 2016-10-03 08:00 | 2016-10-07 17:00 | 5d |  | 0 | 8910 | 0 | 0 | 8910 |  | 0 | 0 | 8910 | 5d | 0 | 0 | 0 | 8910 | 0% | Not Started | 0 | 8910 | 100 |  | 0 | 100 |  | 0
27 | Elastische voegen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Ballustrades/trapleuningen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 297 | 0 | 0 | 297 |  | 0 | 0 | 297 | 1d | 0 | 0 | 0 | 297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Poort | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 276 | 0 | 0 | 276 |  | 0 | 0 | 276 | 1d | 0 | 0 | 0 | 276 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Binnenafwerking | 2016-11-10 08:00 | 2017-01-11 17:00 | 45d |  |  | 28749 |  |  | 28749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Plakwerken | 2016-11-10 08:00 | 2016-11-23 17:00 | 10d |  | 0 | 6891 | 0 | 0 | 6891 |  | 0 | 0 | 6891 | 10d | 0 | 0 | 0 | 6891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Chapes | 2016-11-24 08:00 | 2016-12-12 17:00 | 13d |  | 0 | 4779 | 0 | 0 | 4779 |  | 0 | 0 | 4779 | 13d | 0 | 0 | 0 | 4779 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Vloerisolatie | 2016-12-14 08:00 | 2016-12-15 17:00 | 2d |  | 0 | 2697 | 0 | 0 | 2697 |  | 0 | 0 | 2697 | 2d | 0 | 0 | 0 | 2697 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Tegelwerken | 2016-12-16 08:00 | 2016-12-30 17:00 | 11d |  | 0 | 3027 | 0 | 0 | 3027 |  | 0 | 0 | 3027 | 11d | 0 | 0 | 0 | 3027 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buisbek/zoldluik/platen zold/stijl | 2017-01-02 08:00 | 2017-01-02 17:00 | 1d |  | 0 | 227 | 0 | 0 | 227 |  | 0 | 0 | 227 | 1d | 0 | 0 | 0 | 227 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Binnendeuren/Uitbekledingen | 2017-01-02 08:00 | 2017-01-05 17:00 | 4d |  | 0 | 987 | 0 | 0 | 987 |  | 0 | 0 | 987 | 4d | 0 | 0 | 0 | 987 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Trap | 2017-01-02 08:00 | 2017-01-11 17:00 | 8d |  | 0 | 2150 | 0 | 0 | 2150 |  | 0 | 0 | 2150 | 8d | 0 | 0 | 0 | 2150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Luchtdichten | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 491 | 0 | 0 | 491 |  | 0 | 0 | 491 | 2d | 0 | 0 | 0 | 491 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Keuken (laminaat, kasten) | 2017-01-02 08:00 | 2017-01-10 17:00 | 7d |  | 0 | 7500 | 0 | 0 | 7500 |  | 0 | 0 | 7500 | 7d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Technieken | 2016-10-10 08:00 | 2017-01-31 17:00 | 82d |  |  | 30762 |  |  | 30762 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | UZL | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Betonplexplaten | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Slijpen technieken / boringen | 2016-10-13 08:00 | 2016-10-19 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 |  | 0 | 0 | 1300 | 5d | 0 | 0 | 0 | 1300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Bad en douche | 2016-12-13 08:00 | 2016-12-13 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 |  | 0 | 0 | 1152 | 1d | 0 | 0 | 0 | 1152 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Leidingen ventilatie | 2016-10-20 08:00 | 2016-10-24 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 |  | 0 | 0 | 1926 | 3d | 0 | 0 | 0 | 1926 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Leidingen san/CV/WP | 2016-10-25 08:00 | 2016-10-28 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 |  | 0 | 0 | 2481 | 4d | 0 | 0 | 0 | 2481 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Leidingen vloerverwarming | 2016-10-31 08:00 | 2016-11-03 17:00 | 4d |  | 0 | 2102 | 0 | 0 | 2102 |  | 0 | 0 | 2102 | 4d | 0 | 0 | 0 | 2102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Afwerken ventilatie | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 |  | 0 | 0 | 1899 | 2d | 0 | 0 | 0 | 1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken sanitair | 2017-01-04 08:00 | 2017-01-05 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 |  | 0 | 0 | 2565 | 2d | 0 | 0 | 0 | 2565 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Afwerken CV/WP | 2017-01-06 08:00 | 2017-01-11 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 |  | 0 | 0 | 6352 | 4d | 0 | 0 | 0 | 6352 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Leidingen electro | 2016-11-04 08:00 | 2016-11-09 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 |  | 0 | 0 | 2594 | 4d | 0 | 0 | 0 | 2594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Afwerken electro | 2017-01-12 08:00 | 2017-01-18 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 |  | 0 | 0 | 3608 | 5d | 0 | 0 | 0 | 3608 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Verlichting | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Programmatie domotica | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 600 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Diepsondering, bron en aansluiting | 2017-01-19 08:00 | 2017-01-31 17:00 | 9d |  | 0 | 2460 | 0 | 0 | 2460 |  | 0 | 0 | 2460 | 9d | 0 | 0 | 0 | 2460 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Karweien | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 160 | 0 | 0 | 160 |  | 0 | 0 | 160 | 1d | 0 | 0 | 0 | 160 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Omgevingswerken | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  |  | 1402 |  |  | 1402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opkuis werk (afvoer puin en afval) | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  | 0 | 1402 | 0 | 0 | 1402 |  | 0 | 0 | 1402 | 5d | 0 | 0 | 0 | 1402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-11-18 08:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (1) | 2016-03-08 08:00 | 2017-02-07 17:00 | 241d |  |  | 162472 |  |  | 162472 |  | 183d | [5 empty] | 112485 |  | 69.84% |  | 113475 | 120366
56 | Voorbereiding | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  |  | 14539 |  |  | 14539 |  | 22d | [5 empty] | 13303 |  | 100% |  | 14539 | 14539
1 | Werfinrichting, werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 2848 | 0 | 0 | 2848 | 2016-03-08 08:00 | 4d | 2848 | 0 | 0 | -267 | 0 | 2581 | 0 | 100% | Finished | 2848 | 2848 | 100 | 80 | 100 | 100 | 90.625 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 30 | 0 | 0 | 30 | 2016-03-08 08:00 | 1d | 30 | 0 | 0 | -1 | 0 | 29 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 96.6667 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-10 17:00 | 3d |  | 0 | 790 | 0 | 0 | 790 | 2016-03-08 08:00 | 1d | 790 | 0 | 0 | -687 | 0 | 103 | 0 | 100% | Finished | 790 | 790 | 100 | 33.3333 | 100 | 100 | 13.038 | 100
4 | Rijtijden ploegen | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-03-08 08:00 | 1d | 100 | 0 | 0 | 2 | 0 | 102 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 102 | 100
5 | Magazijn | 2016-03-08 08:00 | 2016-03-11 17:00 | 4d |  | 0 | 943 | 0 | 0 | 943 | 2016-03-08 08:00 | 2d | 943 | 0 | 0 | -480 | 0 | 463 | 0 | 100% | Finished | 943 | 943 | 100 | 50 | 100 | 100 | 49.0986 | 100
6 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-23 17:00 | 12d |  | 0 | 3318 | 0 | 0 | 3318 | 2016-03-08 08:00 | 10d | 3318 | 0 | 0 | 207 | 0 | 3525 | 0 | 100% | Finished | 3318 | 3318 | 100 | 83.3333 | 100 | 100 | 106.2387 | 100
7 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  | 0 | 6510 | 0 | 0 | 6510 | 2016-03-08 08:00 | 22d | 6510 | 0 | 0 | -10 | 0 | 6500 | 0 | 100% | Finished | 6510 | 6510 | 100 | 100 | 100 | 100 | 99.8464 | 100
57 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  |  | 11167 |  |  | 11167 |  | 28d | [5 empty] | 12263 |  | 100% |  | 11167 | 11167
8 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  | 0 | 11167 | 0 | 0 | 11167 | 2016-04-07 08:00 | 28d | 11167 | 0 | 0 | 1096 | 0 | 12263 | 0 | 100% | Finished | 11167 | 11167 | 100 | 116.6667 | 100 | 100 | 109.8146 | 100
58 | Ruwbouw | 2016-05-11 08:00 | 2016-08-12 17:00 | 68d |  |  | 46742 |  |  | 46742 |  | 68d | [5 empty] | 46399 |  | 100% |  | 46742 | 46742
9 | GEWA/Metselwerk | 2016-05-11 08:00 | 2016-06-02 17:00 | 17d |  | 0 | 13968 | 0 | 0 | 13968 | 2016-05-17 08:00 | 16d | 13968 | 0 | 0 | -536 | 0 | 13432 | 0 | 100% | Finished | 13968 | 13968 | 100 | 94.1176 | 100 | 100 | 96.1627 | 100
10 | Gewelven/Structuur | 2016-06-03 08:00 | 2016-06-07 17:00 | 3d |  | 0 | 5417 | 0 | 0 | 5417 | 2016-06-08 08:00 | 3d | 5417 | 0 | 0 | 0 | 0 | 5417 | 0 | 100% | Finished | 5417 | 5417 | 100 | 100 | 100 | 100 | 100 | 100
11 | Uitbranden GEWA | 2016-06-03 08:00 | 2016-06-03 17:00 | 1d |  | 0 | 341 | 0 | 0 | 341 | 2016-06-08 08:00 | 1d | 341 | 0 | 0 | 0 | 0 | 341 | 0 | 100% | Finished | 341 | 341 | 100 | 100 | 100 | 100 | 100 | 100
12 | Isolatie | 2016-06-08 08:00 | 2016-06-15 17:00 | 6d |  | 0 | 4629 | 0 | 0 | 4629 | 2016-06-13 08:00 | 6d | 4629 | 0 | 0 | 0 | 0 | 4629 | 0 | 100% | Finished | 4629 | 4629 | 100 | 100 | 100 | 100 | 100 | 100
13 | Parament | 2016-06-16 08:00 | 2016-07-22 17:00 | 27d |  | 0 | 15804 | 0 | 0 | 15804 | 2016-06-21 08:00 | 27d | 15804 | 0 | 0 | 92 | 0 | 15896 | 0 | 100% | Finished | 15804 | 15804 | 100 | 100 | 100 | 100 | 100.5821 | 100
14 | Ytong/gipswanden | 2016-07-25 08:00 | 2016-07-28 17:00 | 4d |  | 0 | 2696 | 0 | 0 | 2696 | 2016-07-28 08:00 | 4d | 2696 | 0 | 0 | 0 | 0 | 2696 | 0 | 100% | Finished | 2696 | 2696 | 100 | 100 | 100 | 100 | 100 | 100
15 | Dorpels | 2016-07-29 08:00 | 2016-07-29 17:00 | 1d |  | 0 | 646 | 0 | 0 | 646 | 2016-08-03 08:00 | 1d | 646 | 0 | 0 | 0 | 0 | 646 | 0 | 100% | Finished | 646 | 646 | 100 | 100 | 100 | 100 | 100 | 100
16 | Voegwerk | 2016-07-29 08:00 | 2016-08-08 17:00 | 7d |  | 0 | 1821 | 0 | 0 | 1821 | 2016-08-03 08:00 | 8d | 1821 | 0 | 0 | 312 | 0 | 2133 | 0 | 100% | Finished | 1821 | 1821 | 100 | 114.2857 | 100 | 100 | 117.1334 | 100
17 | Stelling | 2016-08-09 08:00 | 2016-08-12 17:00 | 4d |  | 0 | 1420 | 0 | 0 | 1420 | 2016-08-15 08:00 | 4d | 1420 | 0 | 0 | -211 | 0 | 1209 | 0 | 100% | Finished | 1420 | 1420 | 100 | 100 | 100 | 100 | 85.1408 | 100
59 | Dakwerken | 2016-08-15 08:00 | 2016-09-26 17:00 | 31d |  |  | 17795 |  |  | 17795 |  | 32d | [5 empty] | 19201 |  | 100% |  | 17795 | 17795
18 | Daktimmer traditioneel / prefabkap | 2016-08-15 08:00 | 2016-09-02 17:00 | 15d |  | 0 | 9252 | 0 | 0 | 9252 | 2016-08-19 08:00 | 16d | 9252 | 0 | 0 | 691 | 0 | 9943 | 0 | 100% | Finished | 9252 | 9252 | 100 | 106.6667 | 100 | 100 | 107.4687 | 100
19 | Dakdekken | 2016-09-05 08:00 | 2016-09-08 17:00 | 4d |  | 0 | 2317 | 0 | 0 | 2317 | 2016-09-12 08:00 | 4d | 2317 | 0 | 0 | 0 | 0 | 2317 | 0 | 100% | Finished | 2317 | 2317 | 100 | 100 | 100 | 100 | 100 | 100
20 | Goten & afleiders | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 177 | 0 | 0 | 177 | 2016-09-16 08:00 | 2d | 177 | 0 | 0 | 143 | 0 | 320 | 0 | 100% | Finished | 177 | 177 | 100 | 200 | 100 | 100 | 180.791 | 100
21 | Zonnepanelen | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 245 | 0 | 0 | 245 | 2016-09-16 08:00 | 1d | 245 | 0 | 0 | 4 | 0 | 249 | 0 | 100% | Finished | 245 | 245 | 100 | 100 | 100 | 100 | 101.6327 | 100
22 | Oversteken / gevelbekleding | 2016-09-09 08:00 | 2016-09-14 17:00 | 4d |  | 0 | 1509 | 0 | 0 | 1509 | 2016-09-16 08:00 | 4d | 1509 | 0 | 0 | 14 | 0 | 1523 | 0 | 100% | Finished | 1509 | 1509 | 100 | 100 | 100 | 100 | 100.9278 | 100
23 | Afdichting/Groendaken/Plat dak | 2016-09-15 08:00 | 2016-09-26 17:00 | 8d |  | 0 | 3438 | 0 | 0 | 3438 | 2016-09-22 08:00 | 8d | 3438 | 0 | 0 | 21 | 0 | 3459 | 0 | 100% | Finished | 3438 | 3438 | 100 | 100 | 100 | 100 | 100.6108 | 100
24 | Dakvlakramen | 2016-09-15 08:00 | 2016-09-19 17:00 | 3d |  | 0 | 857 | 0 | 0 | 857 | 2016-09-22 08:00 | 5d | 857 | 0 | 0 | 533 | 0 | 1390 | 0 | 100% | Finished | 857 | 857 | 100 | 166.6667 | 100 | 100 | 162.1937 | 100
60 | Buitenschrijnwerk | 2016-09-27 08:00 | 2016-10-10 17:00 | 10d |  |  | 11316 |  |  | 11316 |  | 10d | [5 empty] | 11207 |  | 100% |  | 11316 | 11316
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-09-27 08:00 | 2016-09-30 17:00 | 4d |  | 0 | 1783 | 0 | 0 | 1783 | 2016-10-04 08:00 | 4d | 1783 | 0 | 0 | 16 | 0 | 1799 | 0 | 100% | Finished | 1783 | 1783 | 100 | 100 | 100 | 100 | 100.8974 | 100
26 | Buitenschrijnwerk plaatsen | 2016-10-03 08:00 | 2016-10-07 17:00 | 5d |  | 0 | 8910 | 0 | 0 | 8910 | 2016-10-10 08:00 | 5d | 8910 | 0 | 0 | -136 | 0 | 8774 | 0 | 100% | Finished | 8910 | 8910 | 100 | 100 | 100 | 100 | 98.4736 | 100
27 | Elastische voegen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 2016-10-17 08:00 | 1d | 50 | 0 | 0 | 5 | 0 | 55 | 0 | 100% | Finished | 50 | 50 | 100 | 100 | 100 | 100 | 110 | 100
28 | Ballustrades/trapleuningen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 297 | 0 | 0 | 297 | 2016-10-17 08:00 | 1d | 297 | 0 | 0 | 3 | 0 | 300 | 0 | 100% | Finished | 297 | 297 | 100 | 100 | 100 | 100 | 101.0101 | 100
29 | Poort | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 276 | 0 | 0 | 276 | 2016-10-17 08:00 | 1d | 276 | 0 | 0 | 3 | 0 | 279 | 0 | 100% | Finished | 276 | 276 | 100 | 100 | 100 | 100 | 101.087 | 100
61 | Binnenafwerking | 2016-11-10 08:00 | 2017-01-11 17:00 | 45d |  |  | 28749 |  |  | 28749 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6891
30 | Plakwerken | 2016-11-10 08:00 | 2016-11-23 17:00 | 10d |  | 0 | 6891 | 0 | 0 | 6891 |  | 0 | 0 | 6891 | 10d | 0 | 0 | 0 | 6891 | 0% | Not Started | 0 | 6891 | 100 |  | 0 | 100 |  | 0
31 | Chapes | 2016-11-24 08:00 | 2016-12-12 17:00 | 13d |  | 0 | 4779 | 0 | 0 | 4779 |  | 0 | 0 | 4779 | 13d | 0 | 0 | 0 | 4779 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Vloerisolatie | 2016-12-14 08:00 | 2016-12-15 17:00 | 2d |  | 0 | 2697 | 0 | 0 | 2697 |  | 0 | 0 | 2697 | 2d | 0 | 0 | 0 | 2697 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Tegelwerken | 2016-12-16 08:00 | 2016-12-30 17:00 | 11d |  | 0 | 3027 | 0 | 0 | 3027 |  | 0 | 0 | 3027 | 11d | 0 | 0 | 0 | 3027 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buisbek/zoldluik/platen zold/stijl | 2017-01-02 08:00 | 2017-01-02 17:00 | 1d |  | 0 | 227 | 0 | 0 | 227 |  | 0 | 0 | 227 | 1d | 0 | 0 | 0 | 227 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Binnendeuren/Uitbekledingen | 2017-01-02 08:00 | 2017-01-05 17:00 | 4d |  | 0 | 987 | 0 | 0 | 987 |  | 0 | 0 | 987 | 4d | 0 | 0 | 0 | 987 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Trap | 2017-01-02 08:00 | 2017-01-11 17:00 | 8d |  | 0 | 2150 | 0 | 0 | 2150 |  | 0 | 0 | 2150 | 8d | 0 | 0 | 0 | 2150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Luchtdichten | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 491 | 0 | 0 | 491 |  | 0 | 0 | 491 | 2d | 0 | 0 | 0 | 491 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Keuken (laminaat, kasten) | 2017-01-02 08:00 | 2017-01-10 17:00 | 7d |  | 0 | 7500 | 0 | 0 | 7500 |  | 0 | 0 | 7500 | 7d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Technieken | 2016-10-10 08:00 | 2017-01-31 17:00 | 82d |  |  | 30762 |  |  | 30762 |  | 24d | [5 empty] | 10112 |  | 38.74% |  | 11916 | 11916
39 | UZL | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-10-17 08:00 | 3d | 888 | 0 | 0 | 0 | 0 | 888 | 0 | 100% | Finished | 888 | 888 | 100 | 100 | 100 | 100 | 100 | 100
40 | Betonplexplaten | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2016-10-17 08:00 | 1d | 625 | 0 | 0 | -370 | 0 | 255 | 0 | 100% | Finished | 625 | 625 | 100 | 33.3333 | 100 | 100 | 40.8 | 100
41 | Slijpen technieken / boringen | 2016-10-13 08:00 | 2016-10-19 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 | 2016-10-20 08:00 | 5d | 1300 | 0 | 0 | 25 | 0 | 1325 | 0 | 100% | Finished | 1300 | 1300 | 100 | 100 | 100 | 100 | 101.9231 | 100
42 | Bad en douche | 2016-12-13 08:00 | 2016-12-13 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 |  | 0 | 0 | 1152 | 1d | 0 | 0 | 0 | 1152 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Leidingen ventilatie | 2016-10-20 08:00 | 2016-10-24 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 | 2016-10-27 08:00 | 4d | 1926 | 0 | 0 | -59 | 0 | 1867 | 0 | 100% | Finished | 1926 | 1926 | 100 | 133.3333 | 100 | 100 | 96.9367 | 100
44 | Leidingen san/CV/WP | 2016-10-25 08:00 | 2016-10-28 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 | 2016-11-02 08:00 | 4d | 2481 | 0 | 0 | -265 | 0 | 2216 | 0 | 100% | Finished | 2481 | 2481 | 100 | 100 | 100 | 100 | 89.3188 | 100
45 | Leidingen vloerverwarming | 2016-10-31 08:00 | 2016-11-03 17:00 | 4d |  | 0 | 2102 | 0 | 0 | 2102 | 2016-11-08 08:00 | 4d | 2102 | 0 | 0 | -215 | 0 | 1887 | 0 | 100% | Finished | 2102 | 2102 | 100 | 100 | 100 | 100 | 89.7716 | 100
46 | Afwerken ventilatie | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 |  | 0 | 0 | 1899 | 2d | 0 | 0 | 0 | 1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken sanitair | 2017-01-04 08:00 | 2017-01-05 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 |  | 0 | 0 | 2565 | 2d | 0 | 0 | 0 | 2565 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Afwerken CV/WP | 2017-01-06 08:00 | 2017-01-11 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 |  | 0 | 0 | 6352 | 4d | 0 | 0 | 0 | 6352 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Leidingen electro | 2016-11-04 08:00 | 2016-11-09 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 | 2016-11-14 08:00 | 4d | 2594 | 0 | 0 | -920 | 0 | 1674 | 0 | 100% | Finished | 2594 | 2594 | 100 | 100 | 100 | 100 | 64.5335 | 100
50 | Afwerken electro | 2017-01-12 08:00 | 2017-01-18 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 |  | 0 | 0 | 3608 | 5d | 0 | 0 | 0 | 3608 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Verlichting | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Programmatie domotica | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 600 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Diepsondering, bron en aansluiting | 2017-01-19 08:00 | 2017-01-31 17:00 | 9d |  | 0 | 2460 | 0 | 0 | 2460 |  | 0 | 0 | 2460 | 9d | 0 | 0 | 0 | 2460 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Karweien | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 160 | 0 | 0 | 160 |  | 0 | 0 | 160 | 1d | 0 | 0 | 0 | 160 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Omgevingswerken | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  |  | 1402 |  |  | 1402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opkuis werk (afvoer puin en afval) | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  | 0 | 1402 | 0 | 0 | 1402 |  | 0 | 0 | 1402 | 5d | 0 | 0 | 0 | 1402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2017-02-24 17:00 |  | TP Name | Tracking Period 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (1) | 2016-03-08 08:00 | 2017-02-07 17:00 | 241d |  |  | 162472 |  |  | 162472 |  | 254d | [5 empty] | 163189 |  | 100% |  | 162472 | 162472
56 | Voorbereiding | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  |  | 14539 |  |  | 14539 |  | 22d | [5 empty] | 13303 |  | 100% |  | 14539 | 14539
1 | Werfinrichting, werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 2848 | 0 | 0 | 2848 | 2016-03-08 08:00 | 4d | 2848 | 0 | 0 | -267 | 0 | 2581 | 0 | 100% | Finished | 2848 | 2848 | 100 | 80 | 100 | 100 | 90.625 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 30 | 0 | 0 | 30 | 2016-03-08 08:00 | 1d | 30 | 0 | 0 | -1 | 0 | 29 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 96.6667 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-10 17:00 | 3d |  | 0 | 790 | 0 | 0 | 790 | 2016-03-08 08:00 | 1d | 790 | 0 | 0 | -687 | 0 | 103 | 0 | 100% | Finished | 790 | 790 | 100 | 33.3333 | 100 | 100 | 13.038 | 100
4 | Rijtijden ploegen | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-03-08 08:00 | 1d | 100 | 0 | 0 | 2 | 0 | 102 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 102 | 100
5 | Magazijn | 2016-03-08 08:00 | 2016-03-11 17:00 | 4d |  | 0 | 943 | 0 | 0 | 943 | 2016-03-08 08:00 | 2d | 943 | 0 | 0 | -480 | 0 | 463 | 0 | 100% | Finished | 943 | 943 | 100 | 50 | 100 | 100 | 49.0986 | 100
6 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-23 17:00 | 12d |  | 0 | 3318 | 0 | 0 | 3318 | 2016-03-08 08:00 | 10d | 3318 | 0 | 0 | 207 | 0 | 3525 | 0 | 100% | Finished | 3318 | 3318 | 100 | 83.3333 | 100 | 100 | 106.2387 | 100
7 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-06 17:00 | 22d |  | 0 | 6510 | 0 | 0 | 6510 | 2016-03-08 08:00 | 22d | 6510 | 0 | 0 | -10 | 0 | 6500 | 0 | 100% | Finished | 6510 | 6510 | 100 | 100 | 100 | 100 | 99.8464 | 100
57 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  |  | 11167 |  |  | 11167 |  | 28d | [5 empty] | 12263 |  | 100% |  | 11167 | 11167
8 | Funderingen | 2016-04-07 08:00 | 2016-05-10 17:00 | 24d |  | 0 | 11167 | 0 | 0 | 11167 | 2016-04-07 08:00 | 28d | 11167 | 0 | 0 | 1096 | 0 | 12263 | 0 | 100% | Finished | 11167 | 11167 | 100 | 116.6667 | 100 | 100 | 109.8146 | 100
58 | Ruwbouw | 2016-05-11 08:00 | 2016-08-12 17:00 | 68d |  |  | 46742 |  |  | 46742 |  | 68d | [5 empty] | 46399 |  | 100% |  | 46742 | 46742
9 | GEWA/Metselwerk | 2016-05-11 08:00 | 2016-06-02 17:00 | 17d |  | 0 | 13968 | 0 | 0 | 13968 | 2016-05-17 08:00 | 16d | 13968 | 0 | 0 | -536 | 0 | 13432 | 0 | 100% | Finished | 13968 | 13968 | 100 | 94.1176 | 100 | 100 | 96.1627 | 100
10 | Gewelven/Structuur | 2016-06-03 08:00 | 2016-06-07 17:00 | 3d |  | 0 | 5417 | 0 | 0 | 5417 | 2016-06-08 08:00 | 3d | 5417 | 0 | 0 | 0 | 0 | 5417 | 0 | 100% | Finished | 5417 | 5417 | 100 | 100 | 100 | 100 | 100 | 100
11 | Uitbranden GEWA | 2016-06-03 08:00 | 2016-06-03 17:00 | 1d |  | 0 | 341 | 0 | 0 | 341 | 2016-06-08 08:00 | 1d | 341 | 0 | 0 | 0 | 0 | 341 | 0 | 100% | Finished | 341 | 341 | 100 | 100 | 100 | 100 | 100 | 100
12 | Isolatie | 2016-06-08 08:00 | 2016-06-15 17:00 | 6d |  | 0 | 4629 | 0 | 0 | 4629 | 2016-06-13 08:00 | 6d | 4629 | 0 | 0 | 0 | 0 | 4629 | 0 | 100% | Finished | 4629 | 4629 | 100 | 100 | 100 | 100 | 100 | 100
13 | Parament | 2016-06-16 08:00 | 2016-07-22 17:00 | 27d |  | 0 | 15804 | 0 | 0 | 15804 | 2016-06-21 08:00 | 27d | 15804 | 0 | 0 | 92 | 0 | 15896 | 0 | 100% | Finished | 15804 | 15804 | 100 | 100 | 100 | 100 | 100.5821 | 100
14 | Ytong/gipswanden | 2016-07-25 08:00 | 2016-07-28 17:00 | 4d |  | 0 | 2696 | 0 | 0 | 2696 | 2016-07-28 08:00 | 4d | 2696 | 0 | 0 | 0 | 0 | 2696 | 0 | 100% | Finished | 2696 | 2696 | 100 | 100 | 100 | 100 | 100 | 100
15 | Dorpels | 2016-07-29 08:00 | 2016-07-29 17:00 | 1d |  | 0 | 646 | 0 | 0 | 646 | 2016-08-03 08:00 | 1d | 646 | 0 | 0 | 0 | 0 | 646 | 0 | 100% | Finished | 646 | 646 | 100 | 100 | 100 | 100 | 100 | 100
16 | Voegwerk | 2016-07-29 08:00 | 2016-08-08 17:00 | 7d |  | 0 | 1821 | 0 | 0 | 1821 | 2016-08-03 08:00 | 8d | 1821 | 0 | 0 | 312 | 0 | 2133 | 0 | 100% | Finished | 1821 | 1821 | 100 | 114.2857 | 100 | 100 | 117.1334 | 100
17 | Stelling | 2016-08-09 08:00 | 2016-08-12 17:00 | 4d |  | 0 | 1420 | 0 | 0 | 1420 | 2016-08-15 08:00 | 4d | 1420 | 0 | 0 | -211 | 0 | 1209 | 0 | 100% | Finished | 1420 | 1420 | 100 | 100 | 100 | 100 | 85.1408 | 100
59 | Dakwerken | 2016-08-15 08:00 | 2016-09-26 17:00 | 31d |  |  | 17795 |  |  | 17795 |  | 32d | [5 empty] | 19201 |  | 100% |  | 17795 | 17795
18 | Daktimmer traditioneel / prefabkap | 2016-08-15 08:00 | 2016-09-02 17:00 | 15d |  | 0 | 9252 | 0 | 0 | 9252 | 2016-08-19 08:00 | 16d | 9252 | 0 | 0 | 691 | 0 | 9943 | 0 | 100% | Finished | 9252 | 9252 | 100 | 106.6667 | 100 | 100 | 107.4687 | 100
19 | Dakdekken | 2016-09-05 08:00 | 2016-09-08 17:00 | 4d |  | 0 | 2317 | 0 | 0 | 2317 | 2016-09-12 08:00 | 4d | 2317 | 0 | 0 | 0 | 0 | 2317 | 0 | 100% | Finished | 2317 | 2317 | 100 | 100 | 100 | 100 | 100 | 100
20 | Goten & afleiders | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 177 | 0 | 0 | 177 | 2016-09-16 08:00 | 2d | 177 | 0 | 0 | 143 | 0 | 320 | 0 | 100% | Finished | 177 | 177 | 100 | 200 | 100 | 100 | 180.791 | 100
21 | Zonnepanelen | 2016-09-09 08:00 | 2016-09-09 17:00 | 1d |  | 0 | 245 | 0 | 0 | 245 | 2016-09-16 08:00 | 1d | 245 | 0 | 0 | 4 | 0 | 249 | 0 | 100% | Finished | 245 | 245 | 100 | 100 | 100 | 100 | 101.6327 | 100
22 | Oversteken / gevelbekleding | 2016-09-09 08:00 | 2016-09-14 17:00 | 4d |  | 0 | 1509 | 0 | 0 | 1509 | 2016-09-16 08:00 | 4d | 1509 | 0 | 0 | 14 | 0 | 1523 | 0 | 100% | Finished | 1509 | 1509 | 100 | 100 | 100 | 100 | 100.9278 | 100
23 | Afdichting/Groendaken/Plat dak | 2016-09-15 08:00 | 2016-09-26 17:00 | 8d |  | 0 | 3438 | 0 | 0 | 3438 | 2016-09-22 08:00 | 8d | 3438 | 0 | 0 | 21 | 0 | 3459 | 0 | 100% | Finished | 3438 | 3438 | 100 | 100 | 100 | 100 | 100.6108 | 100
24 | Dakvlakramen | 2016-09-15 08:00 | 2016-09-19 17:00 | 3d |  | 0 | 857 | 0 | 0 | 857 | 2016-09-22 08:00 | 5d | 857 | 0 | 0 | 533 | 0 | 1390 | 0 | 100% | Finished | 857 | 857 | 100 | 166.6667 | 100 | 100 | 162.1937 | 100
60 | Buitenschrijnwerk | 2016-09-27 08:00 | 2016-10-10 17:00 | 10d |  |  | 11316 |  |  | 11316 |  | 10d | [5 empty] | 11207 |  | 100% |  | 11316 | 11316
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-09-27 08:00 | 2016-09-30 17:00 | 4d |  | 0 | 1783 | 0 | 0 | 1783 | 2016-10-04 08:00 | 4d | 1783 | 0 | 0 | 16 | 0 | 1799 | 0 | 100% | Finished | 1783 | 1783 | 100 | 100 | 100 | 100 | 100.8974 | 100
26 | Buitenschrijnwerk plaatsen | 2016-10-03 08:00 | 2016-10-07 17:00 | 5d |  | 0 | 8910 | 0 | 0 | 8910 | 2016-10-10 08:00 | 5d | 8910 | 0 | 0 | -136 | 0 | 8774 | 0 | 100% | Finished | 8910 | 8910 | 100 | 100 | 100 | 100 | 98.4736 | 100
27 | Elastische voegen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 2016-10-17 08:00 | 1d | 50 | 0 | 0 | 5 | 0 | 55 | 0 | 100% | Finished | 50 | 50 | 100 | 100 | 100 | 100 | 110 | 100
28 | Ballustrades/trapleuningen | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 297 | 0 | 0 | 297 | 2016-10-17 08:00 | 1d | 297 | 0 | 0 | 3 | 0 | 300 | 0 | 100% | Finished | 297 | 297 | 100 | 100 | 100 | 100 | 101.0101 | 100
29 | Poort | 2016-10-10 08:00 | 2016-10-10 17:00 | 1d |  | 0 | 276 | 0 | 0 | 276 | 2016-10-17 08:00 | 1d | 276 | 0 | 0 | 3 | 0 | 279 | 0 | 100% | Finished | 276 | 276 | 100 | 100 | 100 | 100 | 101.087 | 100
61 | Binnenafwerking | 2016-11-10 08:00 | 2017-01-11 17:00 | 45d |  |  | 28749 |  |  | 28749 |  | 53d | [5 empty] | 30821 |  | 100% |  | 28749 | 28749
30 | Plakwerken | 2016-11-10 08:00 | 2016-11-23 17:00 | 10d |  | 0 | 6891 | 0 | 0 | 6891 | 2016-11-18 08:00 | 9d | 6891 | 0 | 0 | -347 | 0 | 6544 | 0 | 100% | Finished | 6891 | 6891 | 100 | 90 | 100 | 100 | 94.9644 | 100
31 | Chapes | 2016-11-24 08:00 | 2016-12-12 17:00 | 13d |  | 0 | 4779 | 0 | 0 | 4779 | 2016-12-01 08:00 | 16d | 4779 | 0 | 0 | 782 | 0 | 5561 | 0 | 100% | Finished | 4779 | 4779 | 100 | 123.0769 | 100 | 100 | 116.3633 | 100
32 | Vloerisolatie | 2016-12-14 08:00 | 2016-12-15 17:00 | 2d |  | 0 | 2697 | 0 | 0 | 2697 | 2016-12-28 08:00 | 3d | 2697 | 0 | 0 | 65 | 0 | 2762 | 0 | 100% | Finished | 2697 | 2697 | 100 | 150 | 100 | 100 | 102.4101 | 100
33 | Tegelwerken | 2016-12-16 08:00 | 2016-12-30 17:00 | 11d |  | 0 | 3027 | 0 | 0 | 3027 | 2017-01-02 08:00 | 14d | 3027 | 0 | 0 | 662 | 0 | 3689 | 0 | 100% | Finished | 3027 | 3027 | 100 | 127.2727 | 100 | 100 | 121.8698 | 100
34 | Buisbek/zoldluik/platen zold/stijl | 2017-01-02 08:00 | 2017-01-02 17:00 | 1d |  | 0 | 227 | 0 | 0 | 227 | 2017-01-20 08:00 | 3d | 227 | 0 | 0 | 553 | 0 | 780 | 0 | 100% | Finished | 227 | 227 | 100 | 300 | 100 | 100 | 343.6123 | 100
35 | Binnendeuren/Uitbekledingen | 2017-01-02 08:00 | 2017-01-05 17:00 | 4d |  | 0 | 987 | 0 | 0 | 987 | 2017-01-20 08:00 | 4d | 987 | 0 | 0 | 7 | 0 | 994 | 0 | 100% | Finished | 987 | 987 | 100 | 100 | 100 | 100 | 100.7092 | 100
36 | Trap | 2017-01-02 08:00 | 2017-01-11 17:00 | 8d |  | 0 | 2150 | 0 | 0 | 2150 | 2017-01-20 08:00 | 8d | 2150 | 0 | 0 | -58 | 0 | 2092 | 0 | 100% | Finished | 2150 | 2150 | 100 | 100 | 100 | 100 | 97.3023 | 100
37 | Luchtdichten | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 491 | 0 | 0 | 491 | 2017-01-20 08:00 | 3d | 491 | 0 | 0 | 408 | 0 | 899 | 0 | 100% | Finished | 491 | 491 | 100 | 150 | 100 | 100 | 183.0957 | 100
38 | Keuken (laminaat, kasten) | 2017-01-02 08:00 | 2017-01-10 17:00 | 7d |  | 0 | 7500 | 0 | 0 | 7500 | 2017-01-20 08:00 | 7d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Technieken | 2016-10-10 08:00 | 2017-01-31 17:00 | 82d |  |  | 30762 |  |  | 30762 |  | 89d | [5 empty] | 28290 |  | 100% |  | 30762 | 30762
39 | UZL | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-10-17 08:00 | 3d | 888 | 0 | 0 | 0 | 0 | 888 | 0 | 100% | Finished | 888 | 888 | 100 | 100 | 100 | 100 | 100 | 100
40 | Betonplexplaten | 2016-10-10 08:00 | 2016-10-12 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2016-10-17 08:00 | 1d | 625 | 0 | 0 | -370 | 0 | 255 | 0 | 100% | Finished | 625 | 625 | 100 | 33.3333 | 100 | 100 | 40.8 | 100
41 | Slijpen technieken / boringen | 2016-10-13 08:00 | 2016-10-19 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 | 2016-10-20 08:00 | 5d | 1300 | 0 | 0 | 25 | 0 | 1325 | 0 | 100% | Finished | 1300 | 1300 | 100 | 100 | 100 | 100 | 101.9231 | 100
42 | Bad en douche | 2016-12-13 08:00 | 2016-12-13 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 | 2016-12-23 08:00 | 3d | 1152 | 0 | 0 | -69 | 0 | 1083 | 0 | 100% | Finished | 1152 | 1152 | 100 | 300 | 100 | 100 | 94.0104 | 100
43 | Leidingen ventilatie | 2016-10-20 08:00 | 2016-10-24 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 | 2016-10-27 08:00 | 4d | 1926 | 0 | 0 | -59 | 0 | 1867 | 0 | 100% | Finished | 1926 | 1926 | 100 | 133.3333 | 100 | 100 | 96.9367 | 100
44 | Leidingen san/CV/WP | 2016-10-25 08:00 | 2016-10-28 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 | 2016-11-02 08:00 | 4d | 2481 | 0 | 0 | -265 | 0 | 2216 | 0 | 100% | Finished | 2481 | 2481 | 100 | 100 | 100 | 100 | 89.3188 | 100
45 | Leidingen vloerverwarming | 2016-10-31 08:00 | 2016-11-03 17:00 | 4d |  | 0 | 2102 | 0 | 0 | 2102 | 2016-11-08 08:00 | 4d | 2102 | 0 | 0 | -215 | 0 | 1887 | 0 | 100% | Finished | 2102 | 2102 | 100 | 100 | 100 | 100 | 89.7716 | 100
46 | Afwerken ventilatie | 2017-01-02 08:00 | 2017-01-03 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 | 2017-01-20 08:00 | 1d | 1899 | 0 | 0 | -372 | 0 | 1527 | 0 | 100% | Finished | 1899 | 1899 | 100 | 50 | 100 | 100 | 80.4107 | 100
47 | Afwerken sanitair | 2017-01-04 08:00 | 2017-01-05 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 | 2017-01-23 08:00 | 4d | 2565 | 0 | 0 | 148 | 0 | 2713 | 0 | 100% | Finished | 2565 | 2565 | 100 | 200 | 100 | 100 | 105.77 | 100
48 | Afwerken CV/WP | 2017-01-06 08:00 | 2017-01-11 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 | 2017-01-27 08:00 | 3d | 6352 | 0 | 0 | 0 | 0 | 6352 | 0 | 100% | Finished | 6352 | 6352 | 100 | 75 | 100 | 100 | 100 | 100
49 | Leidingen electro | 2016-11-04 08:00 | 2016-11-09 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 | 2016-11-14 08:00 | 4d | 2594 | 0 | 0 | -920 | 0 | 1674 | 0 | 100% | Finished | 2594 | 2594 | 100 | 100 | 100 | 100 | 64.5335 | 100
50 | Afwerken electro | 2017-01-12 08:00 | 2017-01-18 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 | 2017-02-01 08:00 | 3d | 3608 | 0 | 0 | -274 | 0 | 3334 | 0 | 100% | Finished | 3608 | 3608 | 100 | 60 | 100 | 100 | 92.4058 | 100
51 | Verlichting | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 2017-02-06 08:00 | 1d | 50 | 0 | 0 | -20 | 0 | 30 | 0 | 100% | Finished | 50 | 50 | 100 | 100 | 100 | 100 | 60 | 100
52 | Programmatie domotica | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 600 | 0 | 0 | 600 | 2017-02-06 08:00 | 1d | 600 | 0 | 0 | 6 | 0 | 606 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 101 | 100
53 | Diepsondering, bron en aansluiting | 2017-01-19 08:00 | 2017-01-31 17:00 | 9d |  | 0 | 2460 | 0 | 0 | 2460 | 2017-02-06 08:00 | 9d | 2460 | 0 | 0 | -89 | 0 | 2371 | 0 | 100% | Finished | 2460 | 2460 | 100 | 100 | 100 | 100 | 96.3821 | 100
54 | Karweien | 2017-01-19 08:00 | 2017-01-19 17:00 | 1d |  | 0 | 160 | 0 | 0 | 160 | 2017-02-06 08:00 | 1d | 160 | 0 | 0 | 2 | 0 | 162 | 0 | 100% | Finished | 160 | 160 | 100 | 100 | 100 | 100 | 101.25 | 100
63 | Omgevingswerken | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  |  | 1402 |  |  | 1402 |  | 6d | [5 empty] | 1705 |  | 100% |  | 1402 | 1402
55 | Opkuis werk (afvoer puin en afval) | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d |  | 0 | 1402 | 0 | 0 | 1402 | 2017-02-17 08:00 | 6d | 1402 | 0 | 0 | 303 | 0 | 1705 | 0 | 100% | Finished | 1402 | 1402 | 100 | 120 | 100 | 100 | 121.612 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-08 08:00 | 2016-05-17 08:00 | 39674 | 25706 | 25566 | 2016-05-10 17:00 | -13968 | 64.79% | 140 | 100.5% | -4d | 92% | 100% | 2017-03-08 15:00 | 2017-08-09 17:00 | 2017-08-07 16:00 | 2017-03-03 14:00 | 2017-08-09 17:00 | 2017-08-08 10:00 | 2017-02-13 17:00 | 2017-03-08 17:00 | 2017-03-07 15:00 | 162332 | 161587.1451 | 236647.2372 | 174224.6957 | 235497.6467 | 173415.0708 | 172001.5893 | 163939.7902 | 0.92 | 1.0055 | 0.64793 | 1 | -4 | 1.0055 | 1 | 0.92 | 1
Tracking Period 2 | 2016-05-17 08:00 | 2016-08-19 08:00 | 81700 | 72448 | 71965 | 2016-08-12 17:00 | -9252 | 88.68% | 483 | 100.7% | -4d | 96.61% | 100% | 2017-02-27 15:00 | 2017-03-22 15:00 | 2017-03-20 17:00 | 2017-02-27 11:00 | 2017-03-22 15:00 | 2017-03-21 15:00 | 2017-02-13 17:00 | 2017-02-20 12:00 | 2017-02-17 14:00 | 161989 | 161388.8234 | 173485.5499 | 165147.7368 | 172808.7276 | 164526.5014 | 163571.916 | 162116.1478 | 0.9661 | 1.0067 | 0.88676 | 1 | -4 | 1.0067 | 1 | 0.9661 | 1
Tracking Period 3 | 2016-08-19 08:00 | 2016-10-04 08:00 | 100936 | 90243 | 91166 | 2016-09-26 17:00 | -10693 | 89.41% | -923 | 98.99% | -5d | 96.67% | 100% | 2017-03-01 16:00 | 2017-03-20 12:00 | 2017-03-23 11:00 | 2017-03-01 16:00 | 2017-03-20 12:00 | 2017-03-21 15:00 | 2017-02-14 17:00 | 2017-02-20 10:00 | 2017-02-21 11:00 | 163395 | 164133.7539 | 171953.4998 | 165885.6552 | 172779.7895 | 166649.8833 | 165574.2076 | 164477.5311 | 0.96667 | 0.98988 | 0.89406 | 1 | -5 | 0.98988 | 1 | 0.96667 | 1
Tracking Period 4 | 2016-10-04 08:00 | 2016-11-18 08:00 | 120366 | 113475 | 112485 | 2016-11-09 17:00 | -6891 | 94.27% | 990 | 100.9% | -6d | 96.72% | 100% | 2017-02-22 10:00 | 2017-02-28 14:00 | 2017-02-24 11:00 | 2017-02-22 12:00 | 2017-02-28 14:00 | 2017-02-27 17:00 | 2017-02-15 17:00 | 2017-02-20 09:00 | 2017-02-17 14:00 | 161482 | 161054.5311 | 164457.4424 | 163142.9153 | 164004.0146 | 162700.9559 | 161698.9913 | 161458.3184 | 0.96721 | 1.0088 | 0.94275 | 1 | -6 | 1.0088 | 1 | 0.96721 | 1
Tracking Period 5 | 2016-11-18 08:00 | 2017-02-24 17:00 | 162472 | 162472 | 163189 | 2017-02-07 17:00 | 0 | 100% | -717 | 99.56% | -13d | 94.88% | 100% | 2017-02-07 17:00 | 2017-02-07 17:00 | 2017-02-09 09:00 | 2017-02-24 17:00 | 2017-02-24 17:00 | 2017-02-24 17:00 | 2017-02-24 17:00 | 2017-02-24 17:00 | 2017-02-24 17:00 | 163189 | 163189 | 163189 | 163189 | 163189 | 163189 | 163189 | 163189 | 0.94882 | 0.99561 | 1 | 1 | -13 | 0.99561 | 1 | 0.94882 | 1