## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Sluiskil Tunnel | 1 |  |  | 2010-07-01 08:00 | 2015-06-23 16:00 | 1298d 7h |  |  | 508700000 |  |  | 528569220 | 1818.3333
50 | Preparation - relocation of cables | 1.1 |  |  | 2010-07-01 08:00 | 2010-08-25 17:00 | 40d |  |  | 8400000 |  |  | 8519200 | 55.375
1 | Drawing a relocation plan | 1.1.1 |  | FS3;FS4 | 2010-07-01 08:00 | 2010-07-20 17:00 | 14d |  | 0 | 800000 | 0 | 0 | 800000 | 19.375
2 | switching off all electricity and adapting the cables to other temporary networks | 1.1.2 |  | FS13 | 2010-07-21 08:00 | 2010-08-05 17:00 | 12d | Electrician[6.00 #10] | 40320 | 2400000 | 0 | 0 | 2440320 | 15.375
3 | allocating cables type A | 1.1.3 | 1FS | FS5 | 2010-07-21 08:00 | 2010-08-17 17:00 | 20d | Manpower[10.00 #100] | 64000 | 3400000 | 0 | 0 | 3464000 | 27.375
4 | allocating cables type B | 1.1.4 | 1FS | FS5 | 2010-07-21 08:00 | 2010-07-23 10:00 | 2d 2h | Manpower[10.00 #100] | 7200 | 1800000 | 0 | 0 | 1807200 | 2.0833
5 | Checking if all cables are properly located | 1.1.5 | 3FS;4FS | FS6 | 2010-08-18 08:00 | 2010-08-25 17:00 | 6d | Electric engineer designer[2.00 #2] | 7680 | 0 | 0 | 0 | 7680 | 7.375
51 | Design Tunnel | 1.2 |  |  | 2010-08-26 08:00 | 2010-12-29 17:00 | 90d |  |  | 16000000 |  |  | 16115200 | 125.375
6 | Drawing two concepts | 1.2.1 | 5FS | FS7;FS9;FS10 | 2010-08-26 08:00 | 2010-10-13 17:00 | 35d |  | 0 | 8000000 | 0 | 0 | 8000000 | 48.375
7 | approval of either one of the concepts | 1.2.2 | 6FS | FS8 | 2010-10-14 08:00 | 2010-11-03 17:00 | 15d |  | 0 | 500000 | 0 | 0 | 500000 | 20.375
8 | drawing the final design | 1.2.3 | 7FS | FS13 | 2010-11-04 08:00 | 2010-12-29 17:00 | 40d | Construction Engineer[2.00 #4];Electric engineer designer[2.00 #2] | 115200 | 7500000 | 0 | 0 | 7615200 | 55.375
52 | Design Tunnel related electric installations | 1.3 |  |  | 2010-10-14 08:00 | 2011-05-11 17:00 | 150d |  |  | 32000000 |  |  | 32048000 | 209.375
9 | testing different materials due to the clay type of the Westerschelde | 1.3.1 | 6FS | FS11 | 2010-10-14 08:00 | 2010-11-24 17:00 | 30d | Construction Engineer[2.00 #4] | 48000 | 12000000 | 0 | 0 | 12048000 | 41.375
10 | Drawing a test design | 1.3.2 | 6FS | FS11 | 2010-10-14 08:00 | 2011-02-02 17:00 | 80d |  | 0 | 8000000 | 0 | 0 | 8000000 | 111.375
11 | approve the design | 1.3.3 | 9FS;10FS | FS12 | 2011-02-03 08:00 | 2011-02-23 17:00 | 15d |  | 0 | 500000 | 0 | 0 | 500000 | 20.375
12 | Drawing and finishing the final design | 1.3.4 | 11FS | FS13 | 2011-02-24 08:00 | 2011-05-11 17:00 | 55d |  | 0 | 11500000 | 0 | 0 | 11500000 | 76.375
53 | Construction Tunnel Entrance Driveways | 1.4 |  |  | 2011-05-12 08:00 | 2012-03-13 16:00 | 218d 7h |  |  | 64000000 |  |  | 70506340 | 306.3333
13 | Setting up all equipment | 1.4.1 | 12FS;2FS;8FS | FS14;FS15 | 2011-05-12 08:00 | 2011-06-10 17:00 | 22d | Manpower[20.00 #100];Truck driver[4.00 #4] | 183040 | 1000000 | 0 | 0 | 1183040 | 29.375
14 | Constructing driveway A | 1.4.2 | 13FS | FS16;FS21 | 2011-10-25 08:00 | 2011-12-26 17:00 | 45d | Manpower[60.00 #100];Road workers[20.00 #20];Construction Engineer[4.00 #4];Crane[2.00 #4] | 1483200 | 14000000 | 0 | 0 | 15483200 | 62.375
15 | Constructing driveway B | 1.4.3 | 13FS | FS17 | 2011-06-13 08:00 | 2011-08-03 17:00 | 38d | Manpower[50.00 #100];Road workers[20.00 #20];Construction Engineer[4.00 #4];Crane[2.00 #4] | 1130880 | 13500000 | 0 | 0 | 14630880 | 51.375
16 | constructing the administrative office | 1.4.4 | 14FS | FS18 | 2011-12-27 08:00 | 2012-02-14 17:00 | 36d | Manpower[100.00 #100];Construction Engineer[2.00 #4];Crane[4.00 #4] | 1278720 | 12700000 | 0 | 0 | 13978720 | 49.375
17 | constructing the entrances | 1.4.5 | 15FS | FS19 | 2011-08-04 08:00 | 2011-10-24 17:00 | 58d | Manpower[100.00 #100];Construction Engineer[2.00 #4];Crane[4.00 #4] | 2060160 | 9000000 | 0 | 0 | 11060160 | 81.375
18 | installing all electrics | 1.4.6 | 16FS | FS20 | 2012-02-15 08:00 | 2012-02-17 16:00 | 2d 7h | Electrician[10.00 #10] | 16100 | 6500000 | 0 | 0 | 6516100 | 2.3333
19 | installing safety devices | 1.4.7 | 17FS | FS20 | 2011-10-25 08:00 | 2011-12-15 17:00 | 38d | Electrician[10.00 #10] | 212800 | 6500000 | 0 | 0 | 6712800 | 51.375
20 | Clearing all equipment from the site | 1.4.8 | 18FS;19FS | FS21 | 2012-02-17 16:00 | 2012-03-13 16:00 | 17d | Manpower[20.00 #100];Truck driver[4.00 #4] | 141440 | 800000 | 0 | 0 | 941440 | 25
54 | Construction Tunnel roads | 1.5 |  |  | 2012-03-13 16:00 | 2013-10-07 16:00 | 409d |  |  | 116000000 |  |  | 117532800 | 573
21 | setting up all equipment | 1.5.1 | 14FS;20FS | FS22;FS23 | 2012-03-13 16:00 | 2012-04-03 16:00 | 15d | Manpower[20.00 #100];Truck driver[4.00 #4] | 124800 | 2000000 | 0 | 0 | 2124800 | 21
22 | Constructing tunnel road a | 1.5.2 | 21FS | FS27;FS24 | 2012-04-03 16:00 | 2012-07-16 16:00 | 74d | Construction Engineer[4.00 #4] | 236800 | 33500000 | 0 | 0 | 33736800 | 104
23 | constructing tunnel road b | 1.5.3 | 21FS | FS24;FS27 | 2012-07-16 16:00 | 2012-10-26 16:00 | 74d | Construction Engineer[4.00 #4] | 236800 | 33500000 | 0 | 0 | 33736800 | 102
24 | installing all safety tunnels | 1.5.4 | 22FS;23FS | FS25 | 2013-06-07 16:00 | 2013-08-22 16:00 | 54d | Manpower[50.00 #100] | 864000 | 34400000 | 0 | 0 | 35264000 | 76
25 | final check | 1.5.5 | 24FS | FS26 | 2013-08-22 16:00 | 2013-09-20 16:00 | 21d |  | 0 | 11000000 | 0 | 0 | 11000000 | 29
26 | clearing all equipment from the site | 1.5.6 | 25FS | FS49 | 2013-09-20 16:00 | 2013-10-07 16:00 | 11d | Manpower[20.00 #100] | 70400 | 1600000 | 0 | 0 | 1670400 | 17
55 | Drilling and constructing the tunnel pipes | 1.6 |  |  | 2012-10-26 16:00 | 2014-06-13 16:00 | 425d |  |  | 222200000 |  |  | 230902400 | 595
27 | Mounting and constructing the tunnel drull machine on site | 1.6.1 | 22FS;23FS | FS28;FS29;FS34 | 2012-10-26 16:00 | 2012-12-21 16:00 | 40d | Manpower[20.00 #100] | 256000 | 2000000 | 0 | 0 | 2256000 | 56
28 | Drilling the first tunnel pipe | 1.6.2 | 27FS | FS30 | 2012-12-21 16:00 | 2013-06-07 16:00 | 120d | Manpower[80.00 #100];Tunnel drill | 3072000 | 93000000 | 0 | 0 | 96072000 | 168
29 | Constructing the first tunnel pipe | 1.6.3 | 27FS | FS30 | 2013-06-07 16:00 | 2013-11-15 16:00 | 115d | Manpower[50.00 #100];Electrician[10.00 #10] | 2484000 | 62000000 | 0 | 0 | 64484000 | 161
30 | De-mounting tunnel drill and installing it fot the construction of the second tunnel pipe | 1.6.4 | 28FS;29FS | FS31;FS32 | 2013-11-15 16:00 | 2013-12-13 16:00 | 20d | Manpower[20.00 #100] | 128000 | 1000000 | 0 | 0 | 1128000 | 28
31 | Drilling the second tunnel pipe | 1.6.5 | 30FS | FS33 | 2013-12-13 16:00 | 2014-02-28 16:00 | 55d | Manpower[80.00 #100];Tunnel drill | 1408000 | 31600000 | 0 | 0 | 33008000 | 77
32 | constructing the second tunnel pipe | 1.6.6 | 30FS | FS33 | 2014-02-28 16:00 | 2014-05-16 16:00 | 55d | Manpower[50.00 #100];Electrician[10.00 #10] | 1188000 | 31600000 | 0 | 0 | 32788000 | 77
33 | clearing all equipment from the site | 1.6.7 | 31FS;32FS | FS34 | 2014-05-16 16:00 | 2014-06-13 16:00 | 20d | Manpower[20.00 #100];Truck driver[4.00 #4] | 166400 | 1000000 | 0 | 0 | 1166400 | 28
56 | Construction of roads | 1.7 |  |  | 2014-06-13 16:00 | 2015-06-19 16:00 | 265d |  |  | 42100000 |  |  | 44858400 | 371
34 | Setting up all equipment | 1.7.1 | 27FS;33FS | FS35;FS36 | 2014-06-13 16:00 | 2014-06-24 16:00 | 7d | Truck driver[4.00 #4] | 13440 | 500000 | 0 | 0 | 513440 | 11
35 | constructing road A | 1.7.2 | 34FS | FS37 | 2014-06-24 16:00 | 2014-10-20 16:00 | 84d | Road workers[20.00 #20];Construction Engineer[4.00 #4];Crane[2.00 #4] | 1155840 | 13000000 | 0 | 0 | 14155840 | 118
36 | Constructing road B | 1.7.3 | 34FS | FS38 | 2014-10-20 16:00 | 2015-02-11 16:00 | 82d | Road workers[10.00 #20];Construction Engineer[4.00 #4];Crane[2.00 #4] | 734720 | 13000000 | 0 | 0 | 13734720 | 114
37 | Constructing emergency strips side A | 1.7.4 | 35FS | FS39 | 2014-10-20 16:00 | 2015-01-21 16:00 | 67d | Road workers[10.00 #20] | 321600 | 6825000 | 0 | 0 | 7146600 | 93
38 | Constructing an emergency side strip side B | 1.7.5 | 36FS | FS40 | 2015-02-11 16:00 | 2015-05-14 16:00 | 66d | Road workers[10.00 #20] | 316800 | 6825000 | 0 | 0 | 7141800 | 92
39 | painting road lines road A | 1.7.6 | 37FS | FS42;FS41 | 2015-01-21 16:00 | 2015-02-20 16:00 | 22d | Road workers[10.00 #20] | 105600 | 800000 | 0 | 0 | 905600 | 30
40 | painting road lines road B | 1.7.7 | 38FS | FS41;FS47 | 2015-05-14 16:00 | 2015-06-12 16:00 | 21d | Road workers[10.00 #20] | 100800 | 800000 | 0 | 0 | 900800 | 29
41 | clearing all equipment from the site | 1.7.8 | 39FS;40FS | FS49 | 2015-06-12 16:00 | 2015-06-19 16:00 | 5d | Truck driver[4.00 #4] | 9600 | 350000 | 0 | 0 | 359600 | 7
57 | Testing the tunnel and electric installations | 1.8 |  |  | 2015-02-20 16:00 | 2015-06-23 16:00 | 87d |  |  | 8000000 |  |  | 8086880 | 123
42 | Setting up all equipment | 1.8.1 | 39FS | FS43;FS44 | 2015-02-20 16:00 | 2015-02-24 16:00 | 2d | Manpower[10.00 #100];Truck driver[2.00 #4] | 8320 | 200000 | 0 | 0 | 208320 | 4
43 | checking all electronics tunnel A | 1.8.2 | 42FS | FS45 | 2015-02-24 16:00 | 2015-03-05 16:00 | 7d | Electrician[2.00 #10];Electric engineer designer[2.00 #2] | 16800 | 1900000 | 0 | 0 | 1916800 | 9
44 | Checking electronics tunnel B | 1.8.3 | 42FS | FS46 | 2015-03-05 16:00 | 2015-03-13 16:00 | 6d | Electrician[2.00 #10];Electric engineer designer[2.00 #2] | 14400 | 1700000 | 0 | 0 | 1714400 | 8
45 | Checking all sprinkle systems tunnel A | 1.8.4 | 43FS | FS47 | 2015-03-05 16:00 | 2015-03-18 16:00 | 9d | Electrician[2.00 #10] | 10080 | 1100000 | 0 | 0 | 1110080 | 13
46 | checking all sprinkle systems tunnel B | 1.8.5 | 44FS | FS47 | 2015-03-13 16:00 | 2015-03-25 16:00 | 8d | Electrician[2.00 #10] | 8960 | 900000 | 0 | 0 | 908960 | 12
47 | checking all safety tunnels | 1.8.6 | 45FS;46FS;40FS | FS48 | 2015-06-12 16:00 | 2015-06-19 16:00 | 5d | Electrician[2.00 #10];Construction Engineer[2.00 #4];Electric engineer designer[2.00 #2] | 20000 | 2000000 | 0 | 0 | 2020000 | 7
48 | clearing all equipment from the site | 1.8.7 | 47FS | FS49 | 2015-06-19 16:00 | 2015-06-23 16:00 | 2d | Manpower[10.00 #100];Truck driver[2.00 #4] | 8320 | 200000 | 0 | 0 | 208320 | 4
49 | END | 1.9 | 48FS;41FS;26FS |  | 2015-06-23 16:00 | 2015-06-23 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Manpower | Renewable | 100 MP | 0 | 40 | 3[10.00 Manpower];4[10.00 Manpower];13[20.00 Manpower];14[60.00 Manpower];15[50.00 Manpower];16[100.00 Manpower];17[100.00 Manpower];20[20.00 Manpower];21[20.00 Manpower];24[50.00 Manpower];26[20.00 Manpower];27[20.00 Manpower];28[80.00 Manpower];29[50.00 Manpower];30[20.00 Manpower];31[80.00 Manpower];32[50.00 Manpower];33[20.00 Manpower];42[10.00 Manpower];48[10.00 Manpower]; | 13556000
2 | Electric engineer designer | Renewable | 2 EED | 0 | 80 | 5[2.00 Electric engineer designer];8[2.00 Electric engineer designer];43[2.00 Electric engineer designer];44[2.00 Electric engineer designer];47[2.00 Electric engineer designer]; | 81920
3 | Crane | Renewable | 4 C | 0 | 60 | 14[2.00 Crane];15[2.00 Crane];16[4.00 Crane];17[4.00 Crane];35[2.00 Crane];36[2.00 Crane]; | 419520
4 | Truck driver | Renewable | 4 TD | 0 | 60 | 13[4.00 Truck driver];20[4.00 Truck driver];21[4.00 Truck driver];33[4.00 Truck driver];34[4.00 Truck driver];41[4.00 Truck driver];42[2.00 Truck driver];48[2.00 Truck driver]; | 168960
5 | Electrician | Renewable | 10 E | 0 | 70 | 2[6.00 Electrician];18[10.00 Electrician];19[10.00 Electrician];29[10.00 Electrician];32[10.00 Electrician];43[2.00 Electrician];44[2.00 Electrician];45[2.00 Electrician];46[2.00 Electrician];47[2.00 Electrician]; | 1260420
6 | Road workers | Renewable | 20 RW | 0 | 60 | 14[20.00 Road workers];15[20.00 Road workers];35[20.00 Road workers];36[10.00 Road workers];37[10.00 Road workers];38[10.00 Road workers];39[10.00 Road workers];40[10.00 Road workers]; | 2841600
7 | Construction Engineer | Renewable | 4 CE | 0 | 100 | 8[2.00 Construction Engineer];9[2.00 Construction Engineer];14[4.00 Construction Engineer];15[4.00 Construction Engineer];16[2.00 Construction Engineer];17[2.00 Construction Engineer];22[4.00 Construction Engineer];23[4.00 Construction Engineer];35[4.00 Construction Engineer];36[4.00 Construction Engineer];47[2.00 Construction Engineer]; | 1540800
8 | Tunnel drill | Renewable | 1 T | 0 | 0 | 28;31; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Sluiskil Tunnel | 10391h |  |  |  |  | 99 | 100 | 101
50 | Preparation - relocation of cables | 320h |  |  |  |  | 99 | 100 | 101
1 | Drawing a relocation plan | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | switching off all electricity and adapting the cables to other temporary networks | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | allocating cables type A | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | allocating cables type B | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Checking if all cables are properly located | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Design Tunnel | 720h |  |  |  |  | 99 | 100 | 101
6 | Drawing two concepts | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | approval of either one of the concepts | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | drawing the final design | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Design Tunnel related electric installations | 1200h |  |  |  |  | 99 | 100 | 101
9 | testing different materials due to the clay type of the Westerschelde | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Drawing a test design | 640h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | approve the design | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Drawing and finishing the final design | 440h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Construction Tunnel Entrance Driveways | 1751h |  |  |  |  | 99 | 100 | 101
13 | Setting up all equipment | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Constructing driveway A | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Constructing driveway B | 304h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | constructing the administrative office | 288h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | constructing the entrances | 464h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | installing all electrics | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | installing safety devices | 304h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Clearing all equipment from the site | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Construction Tunnel roads | 3272h |  |  |  |  | 99 | 100 | 101
21 | setting up all equipment | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Constructing tunnel road a | 592h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | constructing tunnel road b | 592h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | installing all safety tunnels | 432h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | final check | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | clearing all equipment from the site | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Drilling and constructing the tunnel pipes | 3400h |  |  |  |  | 99 | 100 | 101
27 | Mounting and constructing the tunnel drull machine on site | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Drilling the first tunnel pipe | 960h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Constructing the first tunnel pipe | 920h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | De-mounting tunnel drill and installing it fot the construction of the second tunnel pipe | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Drilling the second tunnel pipe | 440h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | constructing the second tunnel pipe | 440h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | clearing all equipment from the site | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Construction of roads | 2120h |  |  |  |  | 99 | 100 | 101
34 | Setting up all equipment | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | constructing road A | 672h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Constructing road B | 656h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Constructing emergency strips side A | 536h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Constructing an emergency side strip side B | 528h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | painting road lines road A | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | painting road lines road B | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | clearing all equipment from the site | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Testing the tunnel and electric installations | 696h |  |  |  |  | 99 | 100 | 101
42 | Setting up all equipment | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | checking all electronics tunnel A | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Checking electronics tunnel B | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Checking all sprinkle systems tunnel A | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | checking all sprinkle systems tunnel B | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | checking all safety tunnels | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | clearing all equipment from the site | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | END | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold