## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Project Artes | 1 |  |  | 2016-11-07 08:00 | 2018-02-15 17:00 | 334d |  |  | 0 |  |  | 0 | 465.375
1 | Funderingen TK | 1.1 |  | FS2 | 2017-01-20 08:00 | 2017-01-25 17:00 | 4d | work hours/day[13.50 #32] | 0 | 0 | 0 | 0 | 0 | 5.375
2 | Montage TK | 1.2 | 1FS |  | 2017-04-21 08:00 | 2017-04-24 17:00 | 2d | work hours/day[18.50 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
3 | Voorbereidende werken afbraak bestaand gebouw | 1.3 |  |  | 2017-07-03 08:00 | 2017-07-26 17:00 | 18d | work hours/day[30.00 #32] | 0 | 0 | 0 | 0 | 0 | 23.375
4 | Afbraak bestaand gebouw | 1.4 |  | FS6;FS15 | 2016-11-07 08:00 | 2016-11-24 17:00 | 14d | work hours/day[27.00 #32] | 0 | 0 | 0 | 0 | 0 | 17.375
5 | Grondwerk beton | 1.5 | 6SS+2d | SS7+2d;FS9;FS18 | 2016-11-29 08:00 | 2016-12-12 17:00 | 10d | work hours/day[6.00 #32] | 0 | 0 | 0 | 0 | 0 | 13.375
6 | Riolering | 1.6 | 4FS | SS5+2d | 2016-11-25 08:00 | 2016-12-05 17:00 | 7d | work hours/day[7.50 #32] | 0 | 0 | 0 | 0 | 0 | 10.375
7 | Wapening | 1.7 | 5SS+2d |  | 2017-04-07 08:00 | 2017-04-17 17:00 | 7d | work hours/day[7.00 #32] | 0 | 0 | 0 | 0 | 0 | 10.375
8 | Grondwerk beton | 1.8 | 9SS+2d | SS10+1d;FS11 | 2016-12-28 08:00 | 2017-01-05 17:00 | 7d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 8.375
9 | Riolering | 1.9 | 5FS | SS8+2d;FS12 | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d | work hours/day[5.50 #32] | 0 | 0 | 0 | 0 | 0 | 2.375
10 | Wapening | 1.10 | 8SS+1d |  | 2017-01-02 08:00 | 2017-01-06 17:00 | 5d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
11 | Grondwerk beton | 1.11 | 12FS;8FS | SS14+1d;FS27 | 2017-01-06 08:00 | 2017-01-20 17:00 | 11d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 14.375
12 | Riolering | 1.12 | 9FS | FS11 | 2016-12-28 08:00 | 2016-12-28 17:00 | 1d | work hours/day[4.00 #32] | 0 | 0 | 0 | 0 | 0 | 0.375
13 | Waterbehandeling | 1.13 | 14SS+3d |  | 2017-01-12 08:00 | 2017-01-17 17:00 | 4d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 5.375
14 | Wapening | 1.14 | 11SS+1d | SS13+3d | 2017-01-09 08:00 | 2017-01-19 17:00 | 9d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 10.375
15 | Grondwerk beton | 1.15 | 4FS | SS16;SS17+2d;FS35;FS37 | 2016-11-25 08:00 | 2016-12-08 17:00 | 10d | work hours/day[8.00 #32] | 0 | 0 | 0 | 0 | 0 | 13.375
16 | Riolering in opbouw | 1.16 | 15SS |  | 2016-12-06 08:00 | 2016-12-06 17:00 | 1d | work hours/day[8.00 #32] | 0 | 0 | 0 | 0 | 0 | 0.375
17 | Wapening | 1.17 | 15SS+2d |  | 2017-04-11 08:00 | 2017-04-20 17:00 | 8d | work hours/day[7.50 #32] | 0 | 0 | 0 | 0 | 0 | 9.375
18 | Kolommen | 1.18 | 5FS | FS19;SS20+1d;FS21 | 2016-12-13 08:00 | 2016-12-22 17:00 | 8d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 9.375
19 | Balken GLV | 1.19 | 18FS | FS21;FS22 | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d | work hours/day[6.00 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
20 | Metselwerk GLV | 1.20 | 18SS+1d | FS21;SS98 | 2016-12-21 08:00 | 2017-01-11 17:00 | 16d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 21.375
21 | Gewelven GLV + Vloeren ter plaatse | 1.21 | 18FS;19FS;20FS | FS40 | 2017-01-12 08:00 | 2017-01-24 17:00 | 9d | work hours/day[5.50 #32] | 0 | 0 | 0 | 0 | 0 | 12.375
22 | Kolommen | 1.22 | 19FS | FS23;SS25+3d;FS26 | 2016-12-28 08:00 | 2017-01-06 17:00 | 8d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 9.375
23 | Balken GLV | 1.23 | 22FS | FS24;FS26 | 2017-01-09 08:00 | 2017-01-13 17:00 | 5d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
24 | Wanden | 1.24 | 23FS | FS26 | 2017-01-16 08:00 | 2017-01-23 17:00 | 6d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 7.375
25 | Metselwerk GLV | 1.25 | 22SS+3d | FS26 | 2017-01-02 08:00 | 2017-01-10 17:00 | 7d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 8.375
26 | Gewelven GLV + Vloeren ter plaatse | 1.26 | 22FS;23FS;24FS;25FS | FS46 | 2017-01-24 08:00 | 2017-02-03 17:00 | 9d | work hours/day[5.50 #32] | 0 | 0 | 0 | 0 | 0 | 10.375
27 | Kolommen | 1.27 | 11FS | FS28;SS33+1w;FS34 | 2017-01-23 08:00 | 2017-02-01 17:00 | 8d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 9.375
28 | Balken GLV | 1.28 | 27FS | FS34 | 2017-02-02 08:00 | 2017-02-03 17:00 | 2d | work hours/day[4.00 #32] | 0 | 0 | 0 | 0 | 0 | 1.375
29 | Buffer | 1.29 | 30SS | FS31;FS34 | 2016-11-25 08:00 | 2016-12-06 17:00 | 8d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 11.375
30 | wanden groot bad | 1.30 |  | SS29;FS34 | 2016-11-07 08:00 | 2016-12-02 17:00 | 20d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 25.375
31 | afdek klein bad | 1.31 | 29FS | FS32;FS34 | 2016-12-07 08:00 | 2016-12-15 17:00 | 7d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 8.375
32 | wanden klein bad | 1.32 | 31FS | FS34 | 2016-12-16 08:00 | 2016-12-27 17:00 | 8d | work hours/day[8.50 #32] | 0 | 0 | 0 | 0 | 0 | 11.375
33 | Metselwerk GLV | 1.33 | 27SS+1w | FS34;FS34 | 2017-01-30 08:00 | 2017-02-13 17:00 | 11d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 14.375
34 | Afdek GLV (filters edm binnen!) | 1.34 | 27FS;28FS;33FS;29FS;30FS;31FS;32FS;33FS | FS52 | 2017-02-14 08:00 | 2017-03-13 17:00 | 20d | work hours/day[9.00 #32] | 0 | 0 | 0 | 0 | 0 | 27.375
35 | Kolommen | 1.35 | 15FS | FS36;SS38;FS39 | 2016-12-09 08:00 | 2016-12-20 17:00 | 8d | work hours/day[5.50 #32] | 0 | 0 | 0 | 0 | 0 | 11.375
36 | Balken GLV | 1.36 | 35FS | FS39 | 2016-12-29 08:00 | 2016-12-30 17:00 | 2d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 1.375
37 | Wanden | 1.37 | 15FS | FS39 | 2016-12-09 08:00 | 2016-12-30 17:00 | 16d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 21.375
38 | Metselwerk GLV | 1.38 | 35SS | FS39 | 2016-12-09 08:00 | 2017-01-03 17:00 | 18d | work hours/day[5.50 #32] | 0 | 0 | 0 | 0 | 0 | 25.375
39 | Gewelven GLV + vloer ter plaatse | 1.39 | 35FS;36FS;37FS;38FS | FS57 | 2017-01-04 08:00 | 2017-01-11 17:00 | 6d | work hours/day[5.50 #32] | 0 | 0 | 0 | 0 | 0 | 7.375
40 | kolommen | 1.40 | 21FS | FS41 | 2017-01-25 08:00 | 2017-01-31 17:00 | 5d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 6.375
41 | Balken +1 | 1.41 | 40FS | SS42;FS43 | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d | work hours/day[4.00 #32] | 0 | 0 | 0 | 0 | 0 | 6.375
42 | Metselwerk +1 (niet dragend) | 1.42 | 41SS |  | 2017-02-01 08:00 | 2017-02-07 17:00 | 5d | work hours/day[4.00 #32] | 0 | 0 | 0 | 0 | 0 | 6.375
43 | Gelammeleerde liggers +1 | 1.43 | 41FS | FS44;SF59 | 2017-02-08 08:00 | 2017-02-09 17:00 | 2d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 1.375
44 | Houten kanaalplaten | 1.44 | 43FS | SS45+1d | 2017-02-10 08:00 | 2017-02-13 17:00 | 2d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
45 | Dampscherm | 1.45 | 44SS+1d | FS62;FS75;FS84 | 2017-02-13 08:00 | 2017-02-16 17:00 | 4d | work hours/day[7.00 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
46 | kolommen | 1.46 | 26FS | FS47 | 2017-02-06 08:00 | 2017-02-10 17:00 | 5d | work hours/day[10.00 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
47 | Balken +1 | 1.47 | 46FS | FS48;FS49 | 2017-02-13 08:00 | 2017-02-16 17:00 | 4d | work hours/day[7.00 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
48 | Metselwerk +1 (niet dragend) | 1.48 | 47FS |  | 2017-02-17 08:00 | 2017-02-24 17:00 | 6d | work hours/day[6.50 #32] | 0 | 0 | 0 | 0 | 0 | 7.375
49 | Gelammeleerde liggers +1 | 1.49 | 47FS | FS50 | 2017-02-17 08:00 | 2017-02-20 17:00 | 2d | work hours/day[6.50 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
50 | Houten Kanaalplaten | 1.50 | 49FS | SS51+1d | 2017-03-03 08:00 | 2017-03-07 17:00 | 3d | work hours/day[18.00 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
51 | Dampscherm | 1.51 | 50SS+1d | FS68;FS75;FS85 | 2017-03-08 08:00 | 2017-03-10 17:00 | 3d | work hours/day[6.50 #32] | 0 | 0 | 0 | 0 | 0 | 2.375
52 | Balken +1 | 1.52 | 34FS | SS53;SS54 | 2017-03-14 08:00 | 2017-03-20 17:00 | 5d | work hours/day[6.40 #32] | 0 | 0 | 0 | 0 | 0 | 6.375
53 | Metselwerk +1 (niet dragend) | 1.53 | 52SS |  | 2017-03-15 08:00 | 2017-03-17 17:00 | 3d | work hours/day[6.40 #32] | 0 | 0 | 0 | 0 | 0 | 2.375
54 | tribune | 1.54 | 52SS | FS55 | 2017-03-14 08:00 | 2017-03-17 17:00 | 4d | work hours/day[6.40 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
55 | Gelammeleerde liggers +1 | 1.55 | 54FS | SS56+1d | 2017-03-20 08:00 | 2017-03-23 17:00 | 4d | work hours/day[6.00 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
56 | Dampscherm | 1.56 | 55SS+1d | FS70;SS71;FS75;FS86 | 2017-03-21 08:00 | 2017-03-23 17:00 | 3d | work hours/day[6.00 #32] | 0 | 0 | 0 | 0 | 0 | 2.375
57 | Balken +1 | 1.57 | 39FS | SS58 | 2017-01-12 08:00 | 2017-01-13 17:00 | 2d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 1.375
58 | Metselwerk +1 (niet dragend) | 1.58 | 57SS |  | 2017-01-26 08:00 | 2017-02-08 17:00 | 10d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 13.375
59 | Gelammeleerde liggers +1 | 1.59 | 43SF | FS60 | 2017-02-03 08:00 | 2017-02-07 17:00 | 3d | work hours/day[4.00 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
60 | Houten kanaalplaten | 1.60 | 59FS | SS61+1d | 2017-02-08 08:00 | 2017-02-09 17:00 | 2d | work hours/day[4.50 #32] | 0 | 0 | 0 | 0 | 0 | 1.375
61 | Dampscherm | 1.61 | 60SS+1d | FS75;FS87 | 2017-02-09 08:00 | 2017-02-13 17:00 | 3d | work hours/day[5.00 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
62 | kolommen | 1.62 | 45FS | FS63 | 2017-02-17 08:00 | 2017-02-21 17:00 | 3d | work hours/day[10.00 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
63 | Balken +2 | 1.63 | 62FS | FS64;FS65 | 2017-02-22 08:00 | 2017-02-23 17:00 | 2d | work hours/day[10.50 #32] | 0 | 0 | 0 | 0 | 0 | 1.375
64 | Metselwerk +2 (niet dragend) | 1.64 | 63FS |  | 2017-02-24 08:00 | 2017-03-01 17:00 | 4d | work hours/day[7.00 #32] | 0 | 0 | 0 | 0 | 0 | 5.375
65 | Gelammeleerde liggers +2 | 1.65 | 63FS | FS66 | 2017-02-24 08:00 | 2017-02-27 17:00 | 2d | work hours/day[8.00 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
66 | Houten kanaalplaten | 1.66 | 65FS | SS67+1d | 2017-02-28 08:00 | 2017-02-28 17:00 | 1d | work hours/day[6.40 #32] | 0 | 0 | 0 | 0 | 0 | 0.375
67 | Dampscherm | 1.67 | 66SS+1d | FS76;FS81 | 2017-03-01 08:00 | 2017-03-02 17:00 | 2d | work hours/day[6.40 #32] | 0 | 0 | 0 | 0 | 0 | 1.375
68 | Betonwanden | 1.68 | 51FS | FS69 | 2017-03-13 08:00 | 2017-03-21 17:00 | 7d | work hours/day[12.00 #32] | 0 | 0 | 0 | 0 | 0 | 8.375
69 | Gewelven +2 | 1.69 | 68FS | FS76;FS82 | 2017-03-22 08:00 | 2017-03-24 17:00 | 3d | work hours/day[9.00 #32] | 0 | 0 | 0 | 0 | 0 | 2.375
70 | Balken +2 | 1.70 | 56FS | FS72 | 2017-03-24 08:00 | 2017-03-27 17:00 | 2d | work hours/day[16.00 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
71 | Metselwerk +2 (niet dragend) | 1.71 | 56SS |  | 2017-03-21 08:00 | 2017-03-23 17:00 | 3d | work hours/day[6.00 #32] | 0 | 0 | 0 | 0 | 0 | 2.375
72 | Gelammeleerde liggers +2 | 1.72 | 70FS | FS73;SS74 | 2017-03-28 08:00 | 2017-03-29 17:00 | 2d | work hours/day[10.50 #32] | 0 | 0 | 0 | 0 | 0 | 1.375
73 | Houten kanaalplaten | 1.73 | 72FS |  | 2017-03-31 08:00 | 2017-04-03 17:00 | 2d | work hours/day[10.50 #32] | 0 | 0 | 0 | 0 | 0 | 3.375
74 | Dampscherm | 1.74 | 72SS | FS76;FS83 | 2017-03-28 08:00 | 2017-03-30 17:00 | 3d | work hours/day[10.50 #32] | 0 | 0 | 0 | 0 | 0 | 2.375
75 | Dakdichting Afdek +1 | 1.75 | 51FS;56FS;61FS;45FS |  | 2017-05-15 08:00 | 2017-06-16 17:00 | 25d |  | 0 | 0 | 0 | 0 | 0 | 32.375
76 | Dakdichting Afdek +2 | 1.76 | 67FS;69FS;74FS |  | 2017-05-22 08:00 | 2017-06-02 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
77 | Fase 1 | 1.77 | 84FS | FS88 | 2017-04-13 08:00 | 2017-05-03 17:00 | 15d | work hours/day[8.50 #32] | 0 | 0 | 0 | 0 | 0 | 20.375
78 | Fase 2 | 1.78 | 85FS | FS89 | 2017-05-05 08:00 | 2017-05-22 17:00 | 12d | work hours/day[10.00 #32] | 0 | 0 | 0 | 0 | 0 | 17.375
79 | Fase 3 | 1.79 | 86FS | FS90;FS92+2w | 2017-05-29 08:00 | 2017-06-30 17:00 | 25d | work hours/day[32.00 #32] | 0 | 0 | 0 | 0 | 0 | 32.375
80 | Fase 4 | 1.80 | 87FS | FS91 | 2017-03-30 08:00 | 2017-04-06 17:00 | 6d | work hours/day[6.00 #32] | 0 | 0 | 0 | 0 | 0 | 7.375
81 | Fase 1 | 1.81 | 67FS |  | 2017-03-08 08:00 | 2017-03-14 17:00 | 5d | work hours/day[6.50 #32] | 0 | 0 | 0 | 0 | 0 | 6.375
82 | Fase 2 | 1.82 | 69FS |  | 2017-03-27 08:00 | 2017-03-31 17:00 | 5d | work hours/day[6.00 #32] | 0 | 0 | 0 | 0 | 0 | 4.375
83 | Fase 3 | 1.83 | 74FS |  | 2017-04-04 08:00 | 2017-04-10 17:00 | 5d | work hours/day[24.50 #32] | 0 | 0 | 0 | 0 | 0 | 6.375
84 | BA Fase 1 | 1.84 | 45FS;87FS | FS77;FS85 | 2017-03-30 08:00 | 2017-04-12 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
85 | BA Fase 2 | 1.85 | 51FS;84FS | FS78;FS86 | 2017-04-21 08:00 | 2017-05-04 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
86 | BA fase 3 | 1.86 | 56FS;85FS | FS79 | 2017-05-15 08:00 | 2017-05-26 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
87 | BA fase 4 | 1.87 | 61FS | FS80;FS84 | 2017-03-16 08:00 | 2017-03-29 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
88 | O&s Fase 1 | 1.88 | 77FS |  | 2017-05-15 08:00 | 2017-05-26 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
89 | O&s Fase 2 | 1.89 | 78FS |  | 2017-05-24 08:00 | 2017-06-06 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
90 | O&s Fase 3 | 1.90 | 79FS |  | 2017-07-06 08:00 | 2017-07-19 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
91 | O&s Fase 4 | 1.91 | 80FS |  | 2017-04-07 08:00 | 2017-04-20 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
92 | PUR | 1.92 | 79FS+2w | FS93 | 2017-08-11 08:00 | 2017-08-17 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 6.375
93 | Chapewerken | 1.93 | 92FS | SS94+1w;SS95+2w | 2017-08-21 08:00 | 2017-09-01 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
94 | Plakwerken | 1.94 | 93SS+1w |  | 2017-08-28 08:00 | 2017-09-22 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 25.375
95 | Waterdichtingswerken | 1.95 | 93SS+2w | SS96+1w | 2017-09-04 08:00 | 2017-09-29 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 25.375
96 | Tegelwerken | 1.96 | 95SS+1w | SS97+4w | 2017-09-11 08:00 | 2017-12-15 17:00 | 70d |  | 0 | 0 | 0 | 0 | 0 | 95.375
97 | Afwerking droog | 1.97 | 96SS+4w | FS100 | 2017-10-09 08:00 | 2018-01-12 17:00 | 70d |  | 0 | 0 | 0 | 0 | 0 | 95.375
98 | Technieken | 1.98 | 20SS | FF99;FS100 | 2017-01-26 08:00 | 2017-12-06 17:00 | 225d |  | 0 | 0 | 0 | 0 | 0 | 314.375
99 | Buitenaanleg | 1.99 | 98FF | FS100 | 2017-12-07 08:00 | 2018-01-17 17:00 | 30d |  | 0 | 0 | 0 | 0 | 0 | 41.375
100 | Oplevering | 1.100 | 97FS;98FS;99FS |  | 2018-02-01 08:00 | 2018-02-15 17:00 | 11d | work hours/day[32.00 #32] | 0 | 0 | 0 | 0 | 0 | 14.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | work hours/day | Renewable | 32 h | 0 | 0 | 1[13.50 work hours/day];2[18.50 work hours/day];3[30.00 work hours/day];4[27.00 work hours/day];5[6.00 work hours/day];6[7.50 work hours/day];7[7.00 work hours/day];8[4.50 work hours/day];9[5.50 work hours/day];10[4.50 work hours/day];11[5.00 work hours/day];12[4.00 work hours/day];13[4.50 work hours/day];14[5.00 work hours/day];15[8.00 work hours/day];16[8.00 work hours/day];17[7.50 work hours/day];18[5.00 work hours/day];19[6.00 work hours/day];20[5.00 work hours/day];21[5.50 work hours/day];22[5.00 work hours/day];23[5.00 work hours/day];24[4.50 work hours/day];25[5.00 work hours/day];26[5.50 work hours/day];27[4.50 work hours/day];28[4.00 work hours/day];29[4.50 work hours/day];30[5.00 work hours/day];31[4.50 work hours/day];32[8.50 work hours/day];33[4.50 work hours/day];34[9.00 work hours/day];35[5.50 work hours/day];36[4.50 work hours/day];37[5.00 work hours/day];38[5.50 work hours/day];39[5.50 work hours/day];40[4.50 work hours/day];41[4.00 work hours/day];42[4.00 work hours/day];43[4.50 work hours/day];44[5.00 work hours/day];45[7.00 work hours/day];46[10.00 work hours/day];47[7.00 work hours/day];48[6.50 work hours/day];49[6.50 work hours/day];50[18.00 work hours/day];51[6.50 work hours/day];52[6.40 work hours/day];53[6.40 work hours/day];54[6.40 work hours/day];55[6.00 work hours/day];56[6.00 work hours/day];57[4.50 work hours/day];58[4.50 work hours/day];59[4.00 work hours/day];60[4.50 work hours/day];61[5.00 work hours/day];62[10.00 work hours/day];63[10.50 work hours/day];64[7.00 work hours/day];65[8.00 work hours/day];66[6.40 work hours/day];67[6.40 work hours/day];68[12.00 work hours/day];69[9.00 work hours/day];70[16.00 work hours/day];71[6.00 work hours/day];72[10.50 work hours/day];73[10.50 work hours/day];74[10.50 work hours/day];77[8.50 work hours/day];78[10.00 work hours/day];79[32.00 work hours/day];80[6.00 work hours/day];81[6.50 work hours/day];82[6.00 work hours/day];83[24.50 work hours/day];100[32.00 work hours/day]; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Project Artes | 2672h |  |  |  |  | 99 | 100 | 101
1 | Funderingen TK | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Montage TK | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Voorbereidende werken afbraak bestaand gebouw | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Afbraak bestaand gebouw | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Grondwerk beton | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Riolering | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Wapening | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Grondwerk beton | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Riolering | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Wapening | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Grondwerk beton | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Riolering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Waterbehandeling | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Wapening | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Grondwerk beton | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Riolering in opbouw | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Wapening | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Kolommen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Balken GLV | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Metselwerk GLV | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Gewelven GLV + Vloeren ter plaatse | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Kolommen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Balken GLV | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Wanden | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Metselwerk GLV | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Gewelven GLV + Vloeren ter plaatse | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Kolommen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Balken GLV | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Buffer | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | wanden groot bad | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | afdek klein bad | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | wanden klein bad | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Metselwerk GLV | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Afdek GLV (filters edm binnen!) | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Kolommen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Balken GLV | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Wanden | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Metselwerk GLV | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Gewelven GLV + vloer ter plaatse | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | kolommen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Balken +1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Metselwerk +1 (niet dragend) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Gelammeleerde liggers +1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Houten kanaalplaten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Dampscherm | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | kolommen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Balken +1 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Metselwerk +1 (niet dragend) | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Gelammeleerde liggers +1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Houten Kanaalplaten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Dampscherm | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Balken +1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Metselwerk +1 (niet dragend) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | tribune | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Gelammeleerde liggers +1 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Dampscherm | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Balken +1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Metselwerk +1 (niet dragend) | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Gelammeleerde liggers +1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Houten kanaalplaten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Dampscherm | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | kolommen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Balken +2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Metselwerk +2 (niet dragend) | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Gelammeleerde liggers +2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Houten kanaalplaten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Dampscherm | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Betonwanden | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Gewelven +2 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | Balken +2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Metselwerk +2 (niet dragend) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | Gelammeleerde liggers +2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | Houten kanaalplaten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Dampscherm | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | Dakdichting Afdek +1 | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | Dakdichting Afdek +2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | Fase 1 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | Fase 2 | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | Fase 3 | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | Fase 4 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | Fase 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | Fase 2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Fase 3 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | BA Fase 1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | BA Fase 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | BA fase 3 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | BA fase 4 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | O&s Fase 1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | O&s Fase 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | O&s Fase 3 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | O&s Fase 4 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | PUR | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Chapewerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | Plakwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | Waterdichtingswerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | Tegelwerken | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | Afwerking droog | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | Technieken | 1800h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | Buitenaanleg | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | Oplevering | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))