## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building (4) | 1 |  |  | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 | 326.375
40 | Algemeen | 1.1 |  |  | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 | 188.375
1 | Werfinrichting | 1.1.1 |  | FS2 | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 3.375
2 | Ontmanteling | 1.1.2 | 1FS | FS3 | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 34.375
3 | Ruwbouw Aanpassingen | 1.1.3 | 2FS | FS4;FS7 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 27.375
4 | Valleidingen in schachten | 1.1.4 | 3FS | FS5 | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 13.375
5 | Dakisolatie 6de verdieping | 1.1.5 | 4FS |  | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 6.375
6 | Herstelling Liften | 1.1.6 | 11FS;30FS |  | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 6.375
41 | Verdiepingen (6) | 1.2 |  |  | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 | 221.375
7 | Uitzetten wanden | 1.2.1 | 3FS | FS8;FS26 | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 13.375
8 | Leidingen Technieken | 1.2.2 | 7FS | FS9;FS27 | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 13.375
9 | Dekvloer (Chapewerken) | 1.2.3 | 8FS | FS10;FS13 | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 6.375
10 | Gyproc fase 1 | 1.2.4 | 9FS | FS11;FS12 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 27.375
11 | Elektriciteit in wanden | 1.2.5 | 10FS | FS6;FS13 | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 13.375
12 | Sanitair in wanden | 1.2.6 | 10FS | FS13 | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 13.375
13 | Gyproc fase 2 (dichten wanden) | 1.2.7 | 9FS;11FS;12FS | FS14 | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 13.375
14 | Pleisterwerken | 1.2.8 | 13FS | FS15 | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 6.375
15 | Plaatsen Sanitaire Installaties | 1.2.9 | 14FS | FS16 | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 | 6.375
16 | Stenen vloeren en Faiences | 1.2.10 | 15FS | FS17;FS18 | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 | 20.375
17 | Technieken Ventilatie | 1.2.11 | 16FS | FS19;FS20 | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 | 13.375
18 | Buitenschrijnwerk | 1.2.12 | 16FS | FS19;FS20 | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 | 13.375
19 | Terrassen | 1.2.13 | 17FS;18FS | FS21 | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 | 20.375
20 | Gyproc: Vals plafond | 1.2.14 | 17FS;18FS | FS21 | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 | 20.375
21 | Parket | 1.2.15 | 19FS;20FS | FS22;FS23 | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 | 13.375
22 | Binnenschrijnwerk | 1.2.16 | 21FS | FS24 | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 | 13.375
23 | Keukens | 1.2.17 | 21FS | FS24 | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 | 27.375
24 | Afwerken Elektriciteit en Sanitair | 1.2.18 | 22FS;23FS | FS25 | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 | 13.375
25 | Opkuis | 1.2.19 | 24FS |  | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 | 4.375
42 | Gelijkvloers | 1.3 |  |  | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 | 108.375
26 | Uitzetten wanden | 1.3.1 | 7FS | FS27 | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 6.375
27 | Leidingen Technieken | 1.3.2 | 8FS;26FS | FS28 | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 6.375
28 | Dekvloer (Chapewerken) | 1.3.3 | 27FS | FS29;FS31 | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 6.375
29 | Gyproc fase 1 | 1.3.4 | 28FS | FS30 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 13.375
30 | Elektriciteit in wanden | 1.3.5 | 29FS | FS6;FS31 | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 6.375
31 | Gyproc fase 2 (dichten wanden) | 1.3.6 | 28FS;30FS | FS32 | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 6.375
32 | Pleisterwerken | 1.3.7 | 31FS | FS33 | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 | 6.375
33 | Stenen vloeren en Faiences | 1.3.8 | 32FS | FS34 | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 | 6.375
34 | Buitenschrijnwerk | 1.3.9 | 33FS | FS35 | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 | 6.375
35 | Gyproc: Vals plafond | 1.3.10 | 34FS | FS36;FS37 | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 | 13.375
36 | Binnenschrijnwerk | 1.3.11 | 35FS |  | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 | 6.375
37 | Brievenbussen | 1.3.12 | 35FS | FS38 | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 | 6.375
38 | Afwerken Elektriciteit | 1.3.13 | 37FS | FS39 | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 | 6.375
39 | Opkuis | 1.3.14 | 38FS |  | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 | 3.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building (4) | 1864h |  |  |  |  | 99 | 100 | 101
40 | Algemeen | 1080h |  |  |  |  | 99 | 100 | 101
1 | Werfinrichting | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Ontmanteling | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Ruwbouw Aanpassingen | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Valleidingen in schachten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Dakisolatie 6de verdieping | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Herstelling Liften | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Verdiepingen (6) | 1264h |  |  |  |  | 99 | 100 | 101
7 | Uitzetten wanden | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Leidingen Technieken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Dekvloer (Chapewerken) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Gyproc fase 1 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Elektriciteit in wanden | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Sanitair in wanden | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Gyproc fase 2 (dichten wanden) | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Plaatsen Sanitaire Installaties | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Stenen vloeren en Faiences | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Technieken Ventilatie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Buitenschrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Terrassen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Gyproc: Vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Parket | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Binnenschrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Keukens | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Afwerken Elektriciteit en Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Opkuis | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Gelijkvloers | 616h |  |  |  |  | 99 | 100 | 101
26 | Uitzetten wanden | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Leidingen Technieken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Dekvloer (Chapewerken) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Gyproc fase 1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Elektriciteit in wanden | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Gyproc fase 2 (dichten wanden) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Stenen vloeren en Faiences | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Buitenschrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Gyproc: Vals plafond | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Binnenschrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Brievenbussen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Afwerken Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Opkuis | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-07-25 17:00 |  | TP Name | 25/07, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 27d | [5 empty] | 38402.339 |  | 1.488% |  | 29635.36 | 40146.9591
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 27d | [5 empty] | 38402.339 |  | 9.929% |  | 29635.36 | 40146.9591
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 24d | 32108.1592 | 14716.2396 | 11d | -2752.1201 | -1261.39 | 29356.0391 | 13454.8496 | 68.57% | Started | 22934.4 | 33445.9991 | 100 | 96 | 68.5714 | 100 | 87.7715 | 68.5714
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 |  | 0 | 0 | 142487.998 | 20d | 0 | 0 | 0 | 142487.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 |  | 0 | 0 | 67495.2002 | 10d | 0 | 0 | 0 | 67495.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 |  | 0 | 0 | 16734.0002 | 5d | 0 | 0 | 0 | 16734.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 |  | 0 | 0 | 31596.001 | 5d | 0 | 0 | 0 | 31596.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 |  | 0 | 0 | 15478.3997 | 10d | 0 | 0 | 0 | 15478.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 |  | 0 | 0 | 130024.8047 | 10d | 0 | 0 | 0 | 130024.8047 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 |  | 0 | 0 | 57308.3984 | 5d | 0 | 0 | 0 | 57308.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 |  | 0 | 0 | 105278.3984 | 20d | 0 | 0 | 0 | 105278.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 |  | 0 | 0 | 77003.1982 | 10d | 0 | 0 | 0 | 77003.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 |  | 0 | 0 | 86682.4023 | 10d | 0 | 0 | 0 | 86682.4023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 |  | 0 | 0 | 52639.1992 | 10d | 0 | 0 | 0 | 52639.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 |  | 0 | 0 | 15000 | 5d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 |  | 0 | 0 | 122045.1953 | 5d | 0 | 0 | 0 | 122045.1953 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 |  | 0 | 0 | 60261.5991 | 15d | 0 | 0 | 0 | 60261.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 |  | 0 | 0 | 65012.002 | 10d | 0 | 0 | 0 | 65012.002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 |  | 0 | 0 | 116564.0039 | 10d | 0 | 0 | 0 | 116564.0039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 |  | 0 | 0 | 6453.2001 | 5d | 0 | 0 | 0 | 6453.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 |  | 0 | 0 | 43341.6016 | 5d | 0 | 0 | 0 | 43341.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 |  | 0 | 0 | 29471.9995 | 5d | 0 | 0 | 0 | 29471.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 |  | 0 | 0 | 35092.8003 | 10d | 0 | 0 | 0 | 35092.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 |  | 0 | 0 | 12834.0002 | 5d | 0 | 0 | 0 | 12834.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 |  | 0 | 0 | 17546.4001 | 5d | 0 | 0 | 0 | 17546.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 |  | 0 | 0 | 9232.0001 | 5d | 0 | 0 | 0 | 9232.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 |  | 0 | 0 | 10043.5999 | 5d | 0 | 0 | 0 | 10043.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 |  | 0 | 0 | 19426.4001 | 5d | 0 | 0 | 0 | 19426.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 |  | 0 | 0 | 26320 | 10d | 0 | 0 | 0 | 26320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 |  | 0 | 0 | 14181.9995 | 5d | 0 | 0 | 0 | 14181.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 |  | 0 | 0 | 2956.4001 | 5d | 0 | 0 | 0 | 2956.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 |  | 0 | 0 | 6416.7999 | 5d | 0 | 0 | 0 | 6416.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 |  | 0 | 0 | 2676.6399 | 2d | 0 | 0 | 0 | 2676.6399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-08-09 17:00 |  | TP Name | 09/08, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 38d | [5 empty] | 51857.1787 |  | 2.015% |  | 40146.9591 | 40146.9591
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 38d | [5 empty] | 51857.1787 |  | 13.45% |  | 40146.9591 | 40146.9591
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 |  | 0 | 0 | 142487.998 | 20d | 0 | 0 | 0 | 142487.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 |  | 0 | 0 | 67495.2002 | 10d | 0 | 0 | 0 | 67495.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 |  | 0 | 0 | 16734.0002 | 5d | 0 | 0 | 0 | 16734.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 |  | 0 | 0 | 31596.001 | 5d | 0 | 0 | 0 | 31596.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 |  | 0 | 0 | 15478.3997 | 10d | 0 | 0 | 0 | 15478.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 |  | 0 | 0 | 130024.8047 | 10d | 0 | 0 | 0 | 130024.8047 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 |  | 0 | 0 | 57308.3984 | 5d | 0 | 0 | 0 | 57308.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 |  | 0 | 0 | 105278.3984 | 20d | 0 | 0 | 0 | 105278.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 |  | 0 | 0 | 77003.1982 | 10d | 0 | 0 | 0 | 77003.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 |  | 0 | 0 | 86682.4023 | 10d | 0 | 0 | 0 | 86682.4023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 |  | 0 | 0 | 52639.1992 | 10d | 0 | 0 | 0 | 52639.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 |  | 0 | 0 | 15000 | 5d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 |  | 0 | 0 | 122045.1953 | 5d | 0 | 0 | 0 | 122045.1953 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 |  | 0 | 0 | 60261.5991 | 15d | 0 | 0 | 0 | 60261.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 |  | 0 | 0 | 65012.002 | 10d | 0 | 0 | 0 | 65012.002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 |  | 0 | 0 | 116564.0039 | 10d | 0 | 0 | 0 | 116564.0039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 |  | 0 | 0 | 6453.2001 | 5d | 0 | 0 | 0 | 6453.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 |  | 0 | 0 | 43341.6016 | 5d | 0 | 0 | 0 | 43341.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 |  | 0 | 0 | 29471.9995 | 5d | 0 | 0 | 0 | 29471.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 |  | 0 | 0 | 35092.8003 | 10d | 0 | 0 | 0 | 35092.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 |  | 0 | 0 | 12834.0002 | 5d | 0 | 0 | 0 | 12834.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 |  | 0 | 0 | 17546.4001 | 5d | 0 | 0 | 0 | 17546.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 |  | 0 | 0 | 9232.0001 | 5d | 0 | 0 | 0 | 9232.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 |  | 0 | 0 | 10043.5999 | 5d | 0 | 0 | 0 | 10043.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 |  | 0 | 0 | 19426.4001 | 5d | 0 | 0 | 0 | 19426.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 |  | 0 | 0 | 26320 | 10d | 0 | 0 | 0 | 26320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 |  | 0 | 0 | 14181.9995 | 5d | 0 | 0 | 0 | 14181.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 |  | 0 | 0 | 2956.4001 | 5d | 0 | 0 | 0 | 2956.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 |  | 0 | 0 | 6416.7999 | 5d | 0 | 0 | 0 | 6416.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 |  | 0 | 0 | 2676.6399 | 2d | 0 | 0 | 0 | 2676.6399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-09-09 17:00 |  | TP Name | 09/09, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 61d | [5 empty] | 92038.7981 |  | 3.732% |  | 74344.0779 | 82893.3585
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 61d | [5 empty] | 92038.7981 |  | 24.91% |  | 74344.0779 | 82893.3585
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 6d | 42746.3994 | 135363.5981 | 19d | -2564.78 | -8121.79 | 40181.6194 | 127241.8081 | 24% | Started | 34197.1188 | 42746.3994 | 100 | 30 | 24 | 100 | 28.2 | 24
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 |  | 0 | 0 | 67495.2002 | 10d | 0 | 0 | 0 | 67495.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 |  | 0 | 0 | 16734.0002 | 5d | 0 | 0 | 0 | 16734.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 |  | 0 | 0 | 31596.001 | 5d | 0 | 0 | 0 | 31596.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 |  | 0 | 0 | 15478.3997 | 10d | 0 | 0 | 0 | 15478.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 |  | 0 | 0 | 130024.8047 | 10d | 0 | 0 | 0 | 130024.8047 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 |  | 0 | 0 | 57308.3984 | 5d | 0 | 0 | 0 | 57308.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 |  | 0 | 0 | 105278.3984 | 20d | 0 | 0 | 0 | 105278.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 |  | 0 | 0 | 77003.1982 | 10d | 0 | 0 | 0 | 77003.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 |  | 0 | 0 | 86682.4023 | 10d | 0 | 0 | 0 | 86682.4023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 |  | 0 | 0 | 52639.1992 | 10d | 0 | 0 | 0 | 52639.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 |  | 0 | 0 | 15000 | 5d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 |  | 0 | 0 | 122045.1953 | 5d | 0 | 0 | 0 | 122045.1953 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 |  | 0 | 0 | 60261.5991 | 15d | 0 | 0 | 0 | 60261.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 |  | 0 | 0 | 65012.002 | 10d | 0 | 0 | 0 | 65012.002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 |  | 0 | 0 | 116564.0039 | 10d | 0 | 0 | 0 | 116564.0039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 |  | 0 | 0 | 6453.2001 | 5d | 0 | 0 | 0 | 6453.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 |  | 0 | 0 | 43341.6016 | 5d | 0 | 0 | 0 | 43341.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 |  | 0 | 0 | 29471.9995 | 5d | 0 | 0 | 0 | 29471.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 |  | 0 | 0 | 35092.8003 | 10d | 0 | 0 | 0 | 35092.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 |  | 0 | 0 | 12834.0002 | 5d | 0 | 0 | 0 | 12834.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 |  | 0 | 0 | 17546.4001 | 5d | 0 | 0 | 0 | 17546.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 |  | 0 | 0 | 9232.0001 | 5d | 0 | 0 | 0 | 9232.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 |  | 0 | 0 | 10043.5999 | 5d | 0 | 0 | 0 | 10043.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 |  | 0 | 0 | 19426.4001 | 5d | 0 | 0 | 0 | 19426.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 |  | 0 | 0 | 26320 | 10d | 0 | 0 | 0 | 26320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 |  | 0 | 0 | 14181.9995 | 5d | 0 | 0 | 0 | 14181.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 |  | 0 | 0 | 2956.4001 | 5d | 0 | 0 | 0 | 2956.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 |  | 0 | 0 | 6416.7999 | 5d | 0 | 0 | 0 | 6416.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 |  | 0 | 0 | 2676.6399 | 2d | 0 | 0 | 0 | 2676.6399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-10-13 17:00 |  | TP Name | 13/10, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 85d | [5 empty] | 259993.4859 |  | 11.12% |  | 221542.024 | 265608.557
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 85d | [5 empty] | 253028.2061 |  | 72.5% |  | 216382.5573 | 250130.1573
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 5d | 33747.6001 | 33747.6001 | 5d | 0 | 0 | 33747.6001 | 33747.6001 | 50% | Started | 33747.6001 | 67495.2002 | 100 | 50 | 50 | 100 | 50 | 50
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 |  | 0 | 0 | 16734.0002 | 5d | 0 | 0 | 0 | 16734.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 |  | 0 | 0 | 31596.001 | 5d | 0 | 0 | 0 | 31596.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 5d | [5 empty] | 6965.2798 |  | 0.3539% |  | 5159.4667 | 15478.3997
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 5d | 7739.1998 | 15478.3997 | 10d | -773.92 | -1547.84 | 6965.2798 | 13930.5597 | 33.33% | Started | 5159.4667 | 15478.3997 | 100 | 50 | 33.3333 | 100 | 45 | 33.3333
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 |  | 0 | 0 | 130024.8047 | 10d | 0 | 0 | 0 | 130024.8047 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 |  | 0 | 0 | 57308.3984 | 5d | 0 | 0 | 0 | 57308.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 |  | 0 | 0 | 105278.3984 | 20d | 0 | 0 | 0 | 105278.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 |  | 0 | 0 | 77003.1982 | 10d | 0 | 0 | 0 | 77003.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 |  | 0 | 0 | 86682.4023 | 10d | 0 | 0 | 0 | 86682.4023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 |  | 0 | 0 | 52639.1992 | 10d | 0 | 0 | 0 | 52639.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 |  | 0 | 0 | 15000 | 5d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 |  | 0 | 0 | 122045.1953 | 5d | 0 | 0 | 0 | 122045.1953 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 |  | 0 | 0 | 60261.5991 | 15d | 0 | 0 | 0 | 60261.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 |  | 0 | 0 | 65012.002 | 10d | 0 | 0 | 0 | 65012.002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 |  | 0 | 0 | 116564.0039 | 10d | 0 | 0 | 0 | 116564.0039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 |  | 0 | 0 | 6453.2001 | 5d | 0 | 0 | 0 | 6453.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 |  | 0 | 0 | 43341.6016 | 5d | 0 | 0 | 0 | 43341.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 |  | 0 | 0 | 29471.9995 | 5d | 0 | 0 | 0 | 29471.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 |  | 0 | 0 | 35092.8003 | 10d | 0 | 0 | 0 | 35092.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 |  | 0 | 0 | 12834.0002 | 5d | 0 | 0 | 0 | 12834.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 |  | 0 | 0 | 17546.4001 | 5d | 0 | 0 | 0 | 17546.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 |  | 0 | 0 | 9232.0001 | 5d | 0 | 0 | 0 | 9232.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 |  | 0 | 0 | 10043.5999 | 5d | 0 | 0 | 0 | 10043.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 |  | 0 | 0 | 19426.4001 | 5d | 0 | 0 | 0 | 19426.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 |  | 0 | 0 | 26320 | 10d | 0 | 0 | 0 | 26320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 |  | 0 | 0 | 14181.9995 | 5d | 0 | 0 | 0 | 14181.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 |  | 0 | 0 | 2956.4001 | 5d | 0 | 0 | 0 | 2956.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 |  | 0 | 0 | 6416.7999 | 5d | 0 | 0 | 0 | 6416.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 |  | 0 | 0 | 2676.6399 | 2d | 0 | 0 | 0 | 2676.6399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-11-10 17:00 |  | TP Name | 10/11, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 105d | [5 empty] | 488914.3168 |  | 23.9% |  | 476128.9604 | 575262.1611
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 105d | [5 empty] | 315223.5566 |  | 89.41% |  | 266864.1576 | 266864.1576
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 |  | 0 | 0 | 31596.001 | 5d | 0 | 0 | 0 | 31596.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 25d | [5 empty] | 162720.3199 |  | 13.91% |  | 202811.6028 | 229131.2024
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 |  | 0 | 0 | 105278.3984 | 20d | 0 | 0 | 0 | 105278.3984 | 0% | Not Started | 0 | 26319.5996 | 100 |  | 0 | 100 |  | 0
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 |  | 0 | 0 | 77003.1982 | 10d | 0 | 0 | 0 | 77003.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 |  | 0 | 0 | 86682.4023 | 10d | 0 | 0 | 0 | 86682.4023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 |  | 0 | 0 | 52639.1992 | 10d | 0 | 0 | 0 | 52639.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 |  | 0 | 0 | 15000 | 5d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 |  | 0 | 0 | 122045.1953 | 5d | 0 | 0 | 0 | 122045.1953 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 |  | 0 | 0 | 60261.5991 | 15d | 0 | 0 | 0 | 60261.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 |  | 0 | 0 | 65012.002 | 10d | 0 | 0 | 0 | 65012.002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 |  | 0 | 0 | 116564.0039 | 10d | 0 | 0 | 0 | 116564.0039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 10d | [5 empty] | 10970.4402 |  | 2.734% |  | 6453.2001 | 79266.8011
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 |  | 0 | 0 | 43341.6016 | 5d | 0 | 0 | 0 | 43341.6016 | 0% | Not Started | 0 | 43341.6016 | 100 |  | 0 | 100 |  | 0
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 |  | 0 | 0 | 29471.9995 | 5d | 0 | 0 | 0 | 29471.9995 | 0% | Not Started | 0 | 29471.9995 | 100 |  | 0 | 100 |  | 0
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 |  | 0 | 0 | 35092.8003 | 10d | 0 | 0 | 0 | 35092.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 |  | 0 | 0 | 12834.0002 | 5d | 0 | 0 | 0 | 12834.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 |  | 0 | 0 | 17546.4001 | 5d | 0 | 0 | 0 | 17546.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 |  | 0 | 0 | 9232.0001 | 5d | 0 | 0 | 0 | 9232.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 |  | 0 | 0 | 10043.5999 | 5d | 0 | 0 | 0 | 10043.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 |  | 0 | 0 | 19426.4001 | 5d | 0 | 0 | 0 | 19426.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 |  | 0 | 0 | 26320 | 10d | 0 | 0 | 0 | 26320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 |  | 0 | 0 | 14181.9995 | 5d | 0 | 0 | 0 | 14181.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 |  | 0 | 0 | 2956.4001 | 5d | 0 | 0 | 0 | 2956.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 |  | 0 | 0 | 6416.7999 | 5d | 0 | 0 | 0 | 6416.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 |  | 0 | 0 | 2676.6399 | 2d | 0 | 0 | 0 | 2676.6399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2011-12-15 17:00 |  | TP Name | 15/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 130d | [5 empty] | 747352.6476 |  | 34.01% |  | 677616.1609 | 892611.7614
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 130d | [5 empty] | 315223.5566 |  | 89.41% |  | 266864.1576 | 266864.1576
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 |  | 0 | 0 | 31596.001 | 5d | 0 | 0 | 0 | 31596.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 50d | [5 empty] | 286422.3981 |  | 21.13% |  | 308090.0012 | 471775.6018
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 100% | Finished | 105278.3984 | 105278.3984 | 100 | 125 | 100 | 100 | 117.5 | 100
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 |  | 0 | 0 | 77003.1982 | 10d | 0 | 0 | 0 | 77003.1982 | 0% | Not Started | 0 | 77003.1982 | 100 |  | 0 | 100 |  | 0
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 |  | 0 | 0 | 86682.4023 | 10d | 0 | 0 | 0 | 86682.4023 | 0% | Not Started | 0 | 86682.4023 | 100 |  | 0 | 100 |  | 0
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 |  | 0 | 0 | 52639.1992 | 10d | 0 | 0 | 0 | 52639.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 |  | 0 | 0 | 15000 | 5d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 |  | 0 | 0 | 122045.1953 | 5d | 0 | 0 | 0 | 122045.1953 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 |  | 0 | 0 | 60261.5991 | 15d | 0 | 0 | 0 | 60261.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 |  | 0 | 0 | 65012.002 | 10d | 0 | 0 | 0 | 65012.002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 |  | 0 | 0 | 116564.0039 | 10d | 0 | 0 | 0 | 116564.0039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 35d | [5 empty] | 145706.6929 |  | 43.5% |  | 102662.002 | 153972.002
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 100% | Finished | 43341.6016 | 43341.6016 | 100 | 200 | 100 | 100 | 170.0001 | 100
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 100% | Finished | 29471.9995 | 29471.9995 | 100 | 100 | 100 | 100 | 100 | 100
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 10d | 35092.8003 | 17546.4001 | 5d | -3509.3 | -1754.65 | 31583.5002 | 15791.7501 | 66.67% | Started | 23395.2009 | 35092.8003 | 100 | 100 | 66.6667 | 100 | 89.9999 | 66.6667
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 |  | 0 | 0 | 12834.0002 | 5d | 0 | 0 | 0 | 12834.0002 | 0% | Not Started | 0 | 12834.0002 | 100 |  | 0 | 100 |  | 0
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 |  | 0 | 0 | 17546.4001 | 5d | 0 | 0 | 0 | 17546.4001 | 0% | Not Started | 0 | 17546.4001 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 |  | 0 | 0 | 9232.0001 | 5d | 0 | 0 | 0 | 9232.0001 | 0% | Not Started | 0 | 9232.0001 | 100 |  | 0 | 100 |  | 0
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 |  | 0 | 0 | 10043.5999 | 5d | 0 | 0 | 0 | 10043.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 |  | 0 | 0 | 19426.4001 | 5d | 0 | 0 | 0 | 19426.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 |  | 0 | 0 | 26320 | 10d | 0 | 0 | 0 | 26320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 |  | 0 | 0 | 14181.9995 | 5d | 0 | 0 | 0 | 14181.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 |  | 0 | 0 | 2956.4001 | 5d | 0 | 0 | 0 | 2956.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 |  | 0 | 0 | 6416.7999 | 5d | 0 | 0 | 0 | 6416.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 |  | 0 | 0 | 2676.6399 | 2d | 0 | 0 | 0 | 2676.6399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2012-01-12 17:00 |  | TP Name | 12/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 150d | [5 empty] | 1084698.4603 |  | 47.25% |  | 941295.3618 | 1169682.1569
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 150d | [5 empty] | 346819.5576 |  | 100% |  | 298460.1586 | 298460.1586
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 2012-01-06 08:00 | 5d | 31596.001 | 0 | 0 | 0 | 0 | 31596.001 | 0 | 100% | Finished | 31596.001 | 31596.001 | 100 | 100 | 100 | 100 | 100 | 100
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 70d | [5 empty] | 533717.589 |  | 34.17% |  | 498095.2014 | 661459.9963
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 100% | Finished | 105278.3984 | 105278.3984 | 100 | 125 | 100 | 100 | 117.5 | 100
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 2011-12-16 08:00 | 15d | 115504.7974 | 0 | 0 | -11550.5098 | 0 | 103954.2876 | 0 | 100% | Finished | 77003.1982 | 77003.1982 | 100 | 150 | 100 | 100 | 135 | 100
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 2011-12-16 08:00 | 15d | 130023.6035 | 0 | 0 | -13002.2998 | 0 | 117021.3037 | 0 | 100% | Finished | 86682.4023 | 86682.4023 | 100 | 150 | 100 | 100 | 135.0001 | 100
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 2012-01-06 08:00 | 5d | 26319.5996 | 26319.5996 | 5d | 0 | 0 | 26319.5996 | 26319.5996 | 50% | Started | 26319.5996 | 52639.1992 | 100 | 50 | 50 | 100 | 50 | 50
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 |  | 0 | 0 | 15000 | 5d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 15000 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 |  | 0 | 0 | 122045.1953 | 5d | 0 | 0 | 0 | 122045.1953 | 0% | Not Started | 0 | 122045.1953 | 100 |  | 0 | 100 |  | 0
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 |  | 0 | 0 | 60261.5991 | 15d | 0 | 0 | 0 | 60261.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 |  | 0 | 0 | 65012.002 | 10d | 0 | 0 | 0 | 65012.002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 |  | 0 | 0 | 116564.0039 | 10d | 0 | 0 | 0 | 116564.0039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 55d | [5 empty] | 204161.3137 |  | 61.33% |  | 144740.0018 | 209762.002
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 100% | Finished | 43341.6016 | 43341.6016 | 100 | 200 | 100 | 100 | 170.0001 | 100
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 100% | Finished | 29471.9995 | 29471.9995 | 100 | 100 | 100 | 100 | 100 | 100
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 15d | 52639.2004 | 0 | 0 | -5263.9399 | 0 | 47375.2605 | 0 | 100% | Finished | 35092.8003 | 35092.8003 | 100 | 150 | 100 | 100 | 134.9999 | 100
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 2011-12-23 08:00 | 5d | 12834.0002 | 0 | 0 | 0 | 0 | 12834.0002 | 0 | 100% | Finished | 12834.0002 | 12834.0002 | 100 | 100 | 100 | 100 | 100 | 100
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 2011-12-30 08:00 | 10d | 35092.8003 | 0 | 0 | -5263.9399 | 0 | 29828.8604 | 0 | 100% | Finished | 17546.4001 | 17546.4001 | 100 | 200 | 100 | 100 | 169.9999 | 100
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 |  | 0 | 0 | 9232.0001 | 5d | 0 | 0 | 0 | 9232.0001 | 0% | Not Started | 0 | 9232.0001 | 100 |  | 0 | 100 |  | 0
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 |  | 0 | 0 | 10043.5999 | 5d | 0 | 0 | 0 | 10043.5999 | 0% | Not Started | 0 | 10043.5999 | 100 |  | 0 | 100 |  | 0
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 |  | 0 | 0 | 19426.4001 | 5d | 0 | 0 | 0 | 19426.4001 | 0% | Not Started | 0 | 19426.4001 | 100 |  | 0 | 100 |  | 0
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 |  | 0 | 0 | 26320 | 10d | 0 | 0 | 0 | 26320 | 0% | Not Started | 0 | 26320 | 100 |  | 0 | 100 |  | 0
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 |  | 0 | 0 | 14181.9995 | 5d | 0 | 0 | 0 | 14181.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 |  | 0 | 0 | 2956.4001 | 5d | 0 | 0 | 0 | 2956.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 |  | 0 | 0 | 6416.7999 | 5d | 0 | 0 | 0 | 6416.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 |  | 0 | 0 | 2676.6399 | 2d | 0 | 0 | 0 | 2676.6399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2012-02-16 17:00 |  | TP Name | 16/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 175d | [5 empty] | 1412474.6221 |  | 59.06% |  | 1176609.3572 | 1437751.6013
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 150d | [5 empty] | 346819.5576 |  | 100% |  | 298460.1586 | 298460.1586
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 2012-01-06 08:00 | 5d | 31596.001 | 0 | 0 | 0 | 0 | 31596.001 | 0 | 100% | Finished | 31596.001 | 31596.001 | 100 | 100 | 100 | 100 | 100 | 100
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 95d | [5 empty] | 802601.2008 |  | 46.75% |  | 681547.1966 | 903297.6013
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 100% | Finished | 105278.3984 | 105278.3984 | 100 | 125 | 100 | 100 | 117.5 | 100
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 2011-12-16 08:00 | 15d | 115504.7974 | 0 | 0 | -11550.5098 | 0 | 103954.2876 | 0 | 100% | Finished | 77003.1982 | 77003.1982 | 100 | 150 | 100 | 100 | 135 | 100
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 2011-12-16 08:00 | 15d | 130023.6035 | 0 | 0 | -13002.2998 | 0 | 117021.3037 | 0 | 100% | Finished | 86682.4023 | 86682.4023 | 100 | 150 | 100 | 100 | 135.0001 | 100
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 2012-01-06 08:00 | 10d | 52639.1992 | 0 | 0 | 0 | 0 | 52639.1992 | 0 | 100% | Finished | 52639.1992 | 52639.1992 | 100 | 100 | 100 | 100 | 100 | 100
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 2012-01-20 08:00 | 5d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 | 2012-01-27 08:00 | 10d | 244090.3906 | 0 | 0 | -36613.5781 | 0 | 207476.8125 | 0 | 100% | Finished | 122045.1953 | 122045.1953 | 100 | 200 | 100 | 100 | 170 | 100
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 | 2012-02-10 08:00 | 5d | 20087.1997 | 40174.3994 | 10d | 0 | 0 | 20087.1997 | 40174.3994 | 33.33% | Started | 20087.2003 | 60261.5991 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 |  | 0 | 0 | 65012.002 | 10d | 0 | 0 | 0 | 65012.002 | 0% | Not Started | 0 | 65012.002 | 100 |  | 0 | 100 |  | 0
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 |  | 0 | 0 | 116564.0039 | 10d | 0 | 0 | 0 | 116564.0039 | 0% | Not Started | 0 | 116564.0039 | 100 |  | 0 | 100 |  | 0
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 80d | [5 empty] | 263053.8636 |  | 83.31% |  | 196602.002 | 235993.8414
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 100% | Finished | 43341.6016 | 43341.6016 | 100 | 200 | 100 | 100 | 170.0001 | 100
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 100% | Finished | 29471.9995 | 29471.9995 | 100 | 100 | 100 | 100 | 100 | 100
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 15d | 52639.2004 | 0 | 0 | -5263.9399 | 0 | 47375.2605 | 0 | 100% | Finished | 35092.8003 | 35092.8003 | 100 | 150 | 100 | 100 | 134.9999 | 100
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 2011-12-23 08:00 | 5d | 12834.0002 | 0 | 0 | 0 | 0 | 12834.0002 | 0 | 100% | Finished | 12834.0002 | 12834.0002 | 100 | 100 | 100 | 100 | 100 | 100
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 2011-12-30 08:00 | 10d | 35092.8003 | 0 | 0 | -5263.9399 | 0 | 29828.8604 | 0 | 100% | Finished | 17546.4001 | 17546.4001 | 100 | 200 | 100 | 100 | 169.9999 | 100
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 | 2012-01-13 08:00 | 5d | 9232.0001 | 0 | 0 | 0 | 0 | 9232.0001 | 0 | 100% | Finished | 9232.0001 | 9232.0001 | 100 | 100 | 100 | 100 | 100 | 100
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 | 2012-01-20 08:00 | 10d | 20087.1997 | 0 | 0 | -3013.05 | 0 | 17074.1497 | 0 | 100% | Finished | 10043.5999 | 10043.5999 | 100 | 200 | 100 | 100 | 170.0003 | 100
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 | 2012-02-03 08:00 | 5d | 19426.4001 | 0 | 0 | 0 | 0 | 19426.4001 | 0 | 100% | Finished | 19426.4001 | 19426.4001 | 100 | 100 | 100 | 100 | 100 | 100
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 | 2012-02-10 08:00 | 5d | 13160 | 13160 | 5d | 0 | 0 | 13160 | 13160 | 50% | Started | 13160 | 26320 | 100 | 50 | 50 | 100 | 50 | 50
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 |  | 0 | 0 | 14181.9995 | 5d | 0 | 0 | 0 | 14181.9995 | 0% | Not Started | 0 | 14181.9995 | 100 |  | 0 | 100 |  | 0
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 |  | 0 | 0 | 2956.4001 | 5d | 0 | 0 | 0 | 2956.4001 | 0% | Not Started | 0 | 2956.4001 | 100 |  | 0 | 100 |  | 0
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 |  | 0 | 0 | 6416.7999 | 5d | 0 | 0 | 0 | 6416.7999 | 0% | Not Started | 0 | 6416.7999 | 100 |  | 0 | 100 |  | 0
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 |  | 0 | 0 | 2676.6399 | 2d | 0 | 0 | 0 | 2676.6399 | 0% | Not Started | 0 | 2676.6399 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2012-03-15 17:00 |  | TP Name | 15/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 195d | [5 empty] | 1671887.9161 |  | 70.22% |  | 1398896.9357 | 1583265.1987
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 150d | [5 empty] | 346819.5576 |  | 100% |  | 298460.1586 | 298460.1586
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 2012-01-06 08:00 | 5d | 31596.001 | 0 | 0 | 0 | 0 | 31596.001 | 0 | 100% | Finished | 31596.001 | 31596.001 | 100 | 100 | 100 | 100 | 100 | 100
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 115d | [5 empty] | 1012695.2057 |  | 59.3% |  | 864442.9357 | 1048811.1987
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 100% | Finished | 105278.3984 | 105278.3984 | 100 | 125 | 100 | 100 | 117.5 | 100
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 2011-12-16 08:00 | 15d | 115504.7974 | 0 | 0 | -11550.5098 | 0 | 103954.2876 | 0 | 100% | Finished | 77003.1982 | 77003.1982 | 100 | 150 | 100 | 100 | 135 | 100
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 2011-12-16 08:00 | 15d | 130023.6035 | 0 | 0 | -13002.2998 | 0 | 117021.3037 | 0 | 100% | Finished | 86682.4023 | 86682.4023 | 100 | 150 | 100 | 100 | 135.0001 | 100
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 2012-01-06 08:00 | 10d | 52639.1992 | 0 | 0 | 0 | 0 | 52639.1992 | 0 | 100% | Finished | 52639.1992 | 52639.1992 | 100 | 100 | 100 | 100 | 100 | 100
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 2012-01-20 08:00 | 5d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 | 2012-01-27 08:00 | 10d | 244090.3906 | 0 | 0 | -36613.5781 | 0 | 207476.8125 | 0 | 100% | Finished | 122045.1953 | 122045.1953 | 100 | 200 | 100 | 100 | 170 | 100
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 | 2012-02-10 08:00 | 15d | 60261.5991 | 0 | 0 | 0 | 0 | 60261.5991 | 0 | 100% | Finished | 60261.5991 | 60261.5991 | 100 | 100 | 100 | 100 | 100 | 100
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 | 2012-03-02 08:00 | 10d | 65012.002 | 0 | 0 | 0 | 0 | 65012.002 | 0 | 100% | Finished | 65012.002 | 65012.002 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 | 2012-03-02 08:00 | 10d | 116564.0039 | 58282.002 | 5d | -11656.4004 | -5828.2002 | 104907.6035 | 52453.8018 | 66.67% | Started | 77709.3383 | 116564.0039 | 100 | 100 | 66.6667 | 100 | 90 | 66.6667
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 |  | 0 | 0 | 41319.5984 | 15d | 0 | 0 | 0 | 41319.5984 | 0% | Not Started | 0 | 41319.5984 | 100 |  | 0 | 100 |  | 0
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 |  | 0 | 0 | 78958.7988 | 15d | 0 | 0 | 0 | 78958.7988 | 0% | Not Started | 0 | 78958.7988 | 100 |  | 0 | 100 |  | 0
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 25235.2002 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 97d | [5 empty] | 312373.1528 |  | 100% |  | 235993.8414 | 235993.8414
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 100% | Finished | 43341.6016 | 43341.6016 | 100 | 200 | 100 | 100 | 170.0001 | 100
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 100% | Finished | 29471.9995 | 29471.9995 | 100 | 100 | 100 | 100 | 100 | 100
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 15d | 52639.2004 | 0 | 0 | -5263.9399 | 0 | 47375.2605 | 0 | 100% | Finished | 35092.8003 | 35092.8003 | 100 | 150 | 100 | 100 | 134.9999 | 100
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 2011-12-23 08:00 | 5d | 12834.0002 | 0 | 0 | 0 | 0 | 12834.0002 | 0 | 100% | Finished | 12834.0002 | 12834.0002 | 100 | 100 | 100 | 100 | 100 | 100
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 2011-12-30 08:00 | 10d | 35092.8003 | 0 | 0 | -5263.9399 | 0 | 29828.8604 | 0 | 100% | Finished | 17546.4001 | 17546.4001 | 100 | 200 | 100 | 100 | 169.9999 | 100
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 | 2012-01-13 08:00 | 5d | 9232.0001 | 0 | 0 | 0 | 0 | 9232.0001 | 0 | 100% | Finished | 9232.0001 | 9232.0001 | 100 | 100 | 100 | 100 | 100 | 100
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 | 2012-01-20 08:00 | 10d | 20087.1997 | 0 | 0 | -3013.05 | 0 | 17074.1497 | 0 | 100% | Finished | 10043.5999 | 10043.5999 | 100 | 200 | 100 | 100 | 170.0003 | 100
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 | 2012-02-03 08:00 | 5d | 19426.4001 | 0 | 0 | 0 | 0 | 19426.4001 | 0 | 100% | Finished | 19426.4001 | 19426.4001 | 100 | 100 | 100 | 100 | 100 | 100
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 | 2012-02-10 08:00 | 10d | 26320 | 0 | 0 | 0 | 0 | 26320 | 0 | 100% | Finished | 26320 | 26320 | 100 | 100 | 100 | 100 | 100 | 100
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 | 2012-02-24 08:00 | 10d | 28363.999 | 0 | 0 | -4254.5498 | 0 | 24109.4492 | 0 | 100% | Finished | 14181.9995 | 14181.9995 | 100 | 200 | 100 | 100 | 170.0004 | 100
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 | 2012-02-24 08:00 | 5d | 2956.4001 | 0 | 0 | 0 | 0 | 2956.4001 | 0 | 100% | Finished | 2956.4001 | 2956.4001 | 100 | 100 | 100 | 100 | 100 | 100
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 | 2012-03-02 08:00 | 5d | 6416.7999 | 0 | 0 | 0 | 0 | 6416.7999 | 0 | 100% | Finished | 6416.7999 | 6416.7999 | 100 | 100 | 100 | 100 | 100 | 100
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 | 2012-03-09 08:00 | 2d | 2676.6399 | 0 | 0 | 0 | 0 | 2676.6399 | 0 | 100% | Finished | 2676.6399 | 2676.6399 | 100 | 100 | 100 | 100 | 100 | 100

## TP10
| TP Status Date | 2012-04-12 17:00 |  | TP Name | 12/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 215d | [5 empty] | 1834978.837 |  | 78.21% |  | 1558029.9985 | 1876643.2065
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 150d | [5 empty] | 346819.5576 |  | 100% |  | 298460.1586 | 298460.1586
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 2012-01-06 08:00 | 5d | 31596.001 | 0 | 0 | 0 | 0 | 31596.001 | 0 | 100% | Finished | 31596.001 | 31596.001 | 100 | 100 | 100 | 100 | 100 | 100
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 135d | [5 empty] | 1175786.1266 |  | 70.22% |  | 1023575.9985 | 1342189.2065
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 100% | Finished | 105278.3984 | 105278.3984 | 100 | 125 | 100 | 100 | 117.5 | 100
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 2011-12-16 08:00 | 15d | 115504.7974 | 0 | 0 | -11550.5098 | 0 | 103954.2876 | 0 | 100% | Finished | 77003.1982 | 77003.1982 | 100 | 150 | 100 | 100 | 135 | 100
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 2011-12-16 08:00 | 15d | 130023.6035 | 0 | 0 | -13002.2998 | 0 | 117021.3037 | 0 | 100% | Finished | 86682.4023 | 86682.4023 | 100 | 150 | 100 | 100 | 135.0001 | 100
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 2012-01-06 08:00 | 10d | 52639.1992 | 0 | 0 | 0 | 0 | 52639.1992 | 0 | 100% | Finished | 52639.1992 | 52639.1992 | 100 | 100 | 100 | 100 | 100 | 100
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 2012-01-20 08:00 | 5d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 | 2012-01-27 08:00 | 10d | 244090.3906 | 0 | 0 | -36613.5781 | 0 | 207476.8125 | 0 | 100% | Finished | 122045.1953 | 122045.1953 | 100 | 200 | 100 | 100 | 170 | 100
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 | 2012-02-10 08:00 | 15d | 60261.5991 | 0 | 0 | 0 | 0 | 60261.5991 | 0 | 100% | Finished | 60261.5991 | 60261.5991 | 100 | 100 | 100 | 100 | 100 | 100
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 | 2012-03-02 08:00 | 10d | 65012.002 | 0 | 0 | 0 | 0 | 65012.002 | 0 | 100% | Finished | 65012.002 | 65012.002 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 | 2012-03-02 08:00 | 15d | 174846.0059 | 0 | 0 | -17484.6094 | 0 | 157361.3965 | 0 | 100% | Finished | 116564.0039 | 116564.0039 | 100 | 150 | 100 | 100 | 135 | 100
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 | 2012-03-23 08:00 | 10d | 27546.3989 | 0 | 0 | 4131.9302 | 0 | 31678.3291 | 0 | 100% | Finished | 41319.5984 | 41319.5984 | 100 | 66.6667 | 100 | 100 | 76.6666 | 100
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 | 2012-03-23 08:00 | 15d | 78958.7988 | 0 | 0 | 0 | 0 | 78958.7988 | 0 | 100% | Finished | 78958.7988 | 78958.7988 | 100 | 100 | 100 | 100 | 100 | 100
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 |  | 0 | 0 | 50470.4004 | 10d | 0 | 0 | 0 | 50470.4004 | 0% | Not Started | 0 | 50470.4004 | 100 |  | 0 | 100 |  | 0
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 |  | 0 | 0 | 85091.2012 | 10d | 0 | 0 | 0 | 85091.2012 | 0% | Not Started | 0 | 85091.2012 | 100 |  | 0 | 100 |  | 0
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 |  | 0 | 0 | 244068.8086 | 20d | 0 | 0 | 0 | 244068.8086 | 0% | Not Started | 0 | 183051.6064 | 100 |  | 0 | 100 |  | 0
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 97d | [5 empty] | 312373.1528 |  | 100% |  | 235993.8414 | 235993.8414
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 100% | Finished | 43341.6016 | 43341.6016 | 100 | 200 | 100 | 100 | 170.0001 | 100
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 100% | Finished | 29471.9995 | 29471.9995 | 100 | 100 | 100 | 100 | 100 | 100
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 15d | 52639.2004 | 0 | 0 | -5263.9399 | 0 | 47375.2605 | 0 | 100% | Finished | 35092.8003 | 35092.8003 | 100 | 150 | 100 | 100 | 134.9999 | 100
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 2011-12-23 08:00 | 5d | 12834.0002 | 0 | 0 | 0 | 0 | 12834.0002 | 0 | 100% | Finished | 12834.0002 | 12834.0002 | 100 | 100 | 100 | 100 | 100 | 100
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 2011-12-30 08:00 | 10d | 35092.8003 | 0 | 0 | -5263.9399 | 0 | 29828.8604 | 0 | 100% | Finished | 17546.4001 | 17546.4001 | 100 | 200 | 100 | 100 | 169.9999 | 100
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 | 2012-01-13 08:00 | 5d | 9232.0001 | 0 | 0 | 0 | 0 | 9232.0001 | 0 | 100% | Finished | 9232.0001 | 9232.0001 | 100 | 100 | 100 | 100 | 100 | 100
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 | 2012-01-20 08:00 | 10d | 20087.1997 | 0 | 0 | -3013.05 | 0 | 17074.1497 | 0 | 100% | Finished | 10043.5999 | 10043.5999 | 100 | 200 | 100 | 100 | 170.0003 | 100
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 | 2012-02-03 08:00 | 5d | 19426.4001 | 0 | 0 | 0 | 0 | 19426.4001 | 0 | 100% | Finished | 19426.4001 | 19426.4001 | 100 | 100 | 100 | 100 | 100 | 100
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 | 2012-02-10 08:00 | 10d | 26320 | 0 | 0 | 0 | 0 | 26320 | 0 | 100% | Finished | 26320 | 26320 | 100 | 100 | 100 | 100 | 100 | 100
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 | 2012-02-24 08:00 | 10d | 28363.999 | 0 | 0 | -4254.5498 | 0 | 24109.4492 | 0 | 100% | Finished | 14181.9995 | 14181.9995 | 100 | 200 | 100 | 100 | 170.0004 | 100
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 | 2012-02-24 08:00 | 5d | 2956.4001 | 0 | 0 | 0 | 0 | 2956.4001 | 0 | 100% | Finished | 2956.4001 | 2956.4001 | 100 | 100 | 100 | 100 | 100 | 100
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 | 2012-03-02 08:00 | 5d | 6416.7999 | 0 | 0 | 0 | 0 | 6416.7999 | 0 | 100% | Finished | 6416.7999 | 6416.7999 | 100 | 100 | 100 | 100 | 100 | 100
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 | 2012-03-09 08:00 | 2d | 2676.6399 | 0 | 0 | 0 | 0 | 2676.6399 | 0 | 100% | Finished | 2676.6399 | 2676.6399 | 100 | 100 | 100 | 100 | 100 | 100

## TP11
| TP Status Date | 2012-05-10 17:00 |  | TP Name | 10/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 235d | [5 empty] | 1998761.1505 |  | 84.61% |  | 1685677.8959 | 1992222.0874
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 150d | [5 empty] | 346819.5576 |  | 100% |  | 298460.1586 | 298460.1586
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 2012-01-06 08:00 | 5d | 31596.001 | 0 | 0 | 0 | 0 | 31596.001 | 0 | 100% | Finished | 31596.001 | 31596.001 | 100 | 100 | 100 | 100 | 100 | 100
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 155d | [5 empty] | 1339568.4401 |  | 78.97% |  | 1151223.8959 | 1457768.0874
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 100% | Finished | 105278.3984 | 105278.3984 | 100 | 125 | 100 | 100 | 117.5 | 100
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 2011-12-16 08:00 | 15d | 115504.7974 | 0 | 0 | -11550.5098 | 0 | 103954.2876 | 0 | 100% | Finished | 77003.1982 | 77003.1982 | 100 | 150 | 100 | 100 | 135 | 100
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 2011-12-16 08:00 | 15d | 130023.6035 | 0 | 0 | -13002.2998 | 0 | 117021.3037 | 0 | 100% | Finished | 86682.4023 | 86682.4023 | 100 | 150 | 100 | 100 | 135.0001 | 100
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 2012-01-06 08:00 | 10d | 52639.1992 | 0 | 0 | 0 | 0 | 52639.1992 | 0 | 100% | Finished | 52639.1992 | 52639.1992 | 100 | 100 | 100 | 100 | 100 | 100
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 2012-01-20 08:00 | 5d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 | 2012-01-27 08:00 | 10d | 244090.3906 | 0 | 0 | -36613.5781 | 0 | 207476.8125 | 0 | 100% | Finished | 122045.1953 | 122045.1953 | 100 | 200 | 100 | 100 | 170 | 100
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 | 2012-02-10 08:00 | 15d | 60261.5991 | 0 | 0 | 0 | 0 | 60261.5991 | 0 | 100% | Finished | 60261.5991 | 60261.5991 | 100 | 100 | 100 | 100 | 100 | 100
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 | 2012-03-02 08:00 | 10d | 65012.002 | 0 | 0 | 0 | 0 | 65012.002 | 0 | 100% | Finished | 65012.002 | 65012.002 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 | 2012-03-02 08:00 | 15d | 174846.0059 | 0 | 0 | -17484.6094 | 0 | 157361.3965 | 0 | 100% | Finished | 116564.0039 | 116564.0039 | 100 | 150 | 100 | 100 | 135 | 100
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 | 2012-03-23 08:00 | 10d | 27546.3989 | 0 | 0 | 4131.9302 | 0 | 31678.3291 | 0 | 100% | Finished | 41319.5984 | 41319.5984 | 100 | 66.6667 | 100 | 100 | 76.6666 | 100
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 | 2012-03-23 08:00 | 15d | 78958.7988 | 0 | 0 | 0 | 0 | 78958.7988 | 0 | 100% | Finished | 78958.7988 | 78958.7988 | 100 | 100 | 100 | 100 | 100 | 100
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 | 2012-04-13 08:00 | 15d | 75705.6006 | 0 | 0 | -7570.5 | 0 | 68135.1006 | 0 | 100% | Finished | 50470.4004 | 50470.4004 | 100 | 150 | 100 | 100 | 135.0001 | 100
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 | 2012-05-04 08:00 | 5d | 42545.6006 | 85091.2012 | 10d | -4254.5498 | -8509.0996 | 38291.0508 | 76582.1016 | 33.33% | Started | 28363.7346 | 85091.2012 | 100 | 50 | 33.3333 | 100 | 45 | 33.3333
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 | 2012-05-04 08:00 | 5d | 61017.2021 | 244068.8086 | 20d | -3661.04 | -14644.1504 | 57356.1621 | 229424.6582 | 20% | Started | 48813.7624 | 244068.8086 | 100 | 25 | 20 | 100 | 23.5 | 20
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 38501.5991 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 16060.0796 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 97d | [5 empty] | 312373.1528 |  | 100% |  | 235993.8414 | 235993.8414
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 100% | Finished | 43341.6016 | 43341.6016 | 100 | 200 | 100 | 100 | 170.0001 | 100
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 100% | Finished | 29471.9995 | 29471.9995 | 100 | 100 | 100 | 100 | 100 | 100
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 15d | 52639.2004 | 0 | 0 | -5263.9399 | 0 | 47375.2605 | 0 | 100% | Finished | 35092.8003 | 35092.8003 | 100 | 150 | 100 | 100 | 134.9999 | 100
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 2011-12-23 08:00 | 5d | 12834.0002 | 0 | 0 | 0 | 0 | 12834.0002 | 0 | 100% | Finished | 12834.0002 | 12834.0002 | 100 | 100 | 100 | 100 | 100 | 100
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 2011-12-30 08:00 | 10d | 35092.8003 | 0 | 0 | -5263.9399 | 0 | 29828.8604 | 0 | 100% | Finished | 17546.4001 | 17546.4001 | 100 | 200 | 100 | 100 | 169.9999 | 100
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 | 2012-01-13 08:00 | 5d | 9232.0001 | 0 | 0 | 0 | 0 | 9232.0001 | 0 | 100% | Finished | 9232.0001 | 9232.0001 | 100 | 100 | 100 | 100 | 100 | 100
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 | 2012-01-20 08:00 | 10d | 20087.1997 | 0 | 0 | -3013.05 | 0 | 17074.1497 | 0 | 100% | Finished | 10043.5999 | 10043.5999 | 100 | 200 | 100 | 100 | 170.0003 | 100
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 | 2012-02-03 08:00 | 5d | 19426.4001 | 0 | 0 | 0 | 0 | 19426.4001 | 0 | 100% | Finished | 19426.4001 | 19426.4001 | 100 | 100 | 100 | 100 | 100 | 100
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 | 2012-02-10 08:00 | 10d | 26320 | 0 | 0 | 0 | 0 | 26320 | 0 | 100% | Finished | 26320 | 26320 | 100 | 100 | 100 | 100 | 100 | 100
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 | 2012-02-24 08:00 | 10d | 28363.999 | 0 | 0 | -4254.5498 | 0 | 24109.4492 | 0 | 100% | Finished | 14181.9995 | 14181.9995 | 100 | 200 | 100 | 100 | 170.0004 | 100
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 | 2012-02-24 08:00 | 5d | 2956.4001 | 0 | 0 | 0 | 0 | 2956.4001 | 0 | 100% | Finished | 2956.4001 | 2956.4001 | 100 | 100 | 100 | 100 | 100 | 100
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 | 2012-03-02 08:00 | 5d | 6416.7999 | 0 | 0 | 0 | 0 | 6416.7999 | 0 | 100% | Finished | 6416.7999 | 6416.7999 | 100 | 100 | 100 | 100 | 100 | 100
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 | 2012-03-09 08:00 | 2d | 2676.6399 | 0 | 0 | 0 | 0 | 2676.6399 | 0 | 100% | Finished | 2676.6399 | 2676.6399 | 100 | 100 | 100 | 100 | 100 | 100

## TP12
| TP Status Date | 2012-06-07 17:00 |  | TP Name | 07/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 255d | [5 empty] | 2304767.921 |  | 97.26% |  | 1937660.4087 | 1992222.0874
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 150d | [5 empty] | 346819.5576 |  | 100% |  | 298460.1586 | 298460.1586
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 2012-01-06 08:00 | 5d | 31596.001 | 0 | 0 | 0 | 0 | 31596.001 | 0 | 100% | Finished | 31596.001 | 31596.001 | 100 | 100 | 100 | 100 | 100 | 100
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 175d | [5 empty] | 1645575.2106 |  | 96.26% |  | 1403206.4087 | 1457768.0874
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 100% | Finished | 105278.3984 | 105278.3984 | 100 | 125 | 100 | 100 | 117.5 | 100
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 2011-12-16 08:00 | 15d | 115504.7974 | 0 | 0 | -11550.5098 | 0 | 103954.2876 | 0 | 100% | Finished | 77003.1982 | 77003.1982 | 100 | 150 | 100 | 100 | 135 | 100
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 2011-12-16 08:00 | 15d | 130023.6035 | 0 | 0 | -13002.2998 | 0 | 117021.3037 | 0 | 100% | Finished | 86682.4023 | 86682.4023 | 100 | 150 | 100 | 100 | 135.0001 | 100
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 2012-01-06 08:00 | 10d | 52639.1992 | 0 | 0 | 0 | 0 | 52639.1992 | 0 | 100% | Finished | 52639.1992 | 52639.1992 | 100 | 100 | 100 | 100 | 100 | 100
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 2012-01-20 08:00 | 5d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 | 2012-01-27 08:00 | 10d | 244090.3906 | 0 | 0 | -36613.5781 | 0 | 207476.8125 | 0 | 100% | Finished | 122045.1953 | 122045.1953 | 100 | 200 | 100 | 100 | 170 | 100
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 | 2012-02-10 08:00 | 15d | 60261.5991 | 0 | 0 | 0 | 0 | 60261.5991 | 0 | 100% | Finished | 60261.5991 | 60261.5991 | 100 | 100 | 100 | 100 | 100 | 100
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 | 2012-03-02 08:00 | 10d | 65012.002 | 0 | 0 | 0 | 0 | 65012.002 | 0 | 100% | Finished | 65012.002 | 65012.002 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 | 2012-03-02 08:00 | 15d | 174846.0059 | 0 | 0 | -17484.6094 | 0 | 157361.3965 | 0 | 100% | Finished | 116564.0039 | 116564.0039 | 100 | 150 | 100 | 100 | 135 | 100
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 | 2012-03-23 08:00 | 10d | 27546.3989 | 0 | 0 | 4131.9302 | 0 | 31678.3291 | 0 | 100% | Finished | 41319.5984 | 41319.5984 | 100 | 66.6667 | 100 | 100 | 76.6666 | 100
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 | 2012-03-23 08:00 | 15d | 78958.7988 | 0 | 0 | 0 | 0 | 78958.7988 | 0 | 100% | Finished | 78958.7988 | 78958.7988 | 100 | 100 | 100 | 100 | 100 | 100
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 | 2012-04-13 08:00 | 15d | 75705.6006 | 0 | 0 | -7570.5 | 0 | 68135.1006 | 0 | 100% | Finished | 50470.4004 | 50470.4004 | 100 | 150 | 100 | 100 | 135.0001 | 100
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 | 2012-05-04 08:00 | 15d | 127636.8018 | 0 | 0 | -12763.6396 | 0 | 114873.1621 | 0 | 100% | Finished | 85091.2012 | 85091.2012 | 100 | 150 | 100 | 100 | 135 | 100
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 | 2012-05-04 08:00 | 25d | 305086.0107 | 0 | 0 | -18305.1895 | 0 | 286780.8213 | 0 | 100% | Finished | 244068.8086 | 244068.8086 | 100 | 125 | 100 | 100 | 117.5 | 100
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 |  | 0 | 0 | 38501.5991 | 10d | 0 | 0 | 0 | 38501.5991 | 0% | Not Started | 0 | 38501.5991 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 |  | 0 | 0 | 16060.0796 | 3d | 0 | 0 | 0 | 16060.0796 | 0% | Not Started | 0 | 16060.0796 | 100 |  | 0 | 100 |  | 0
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 97d | [5 empty] | 312373.1528 |  | 100% |  | 235993.8414 | 235993.8414
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 100% | Finished | 43341.6016 | 43341.6016 | 100 | 200 | 100 | 100 | 170.0001 | 100
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 100% | Finished | 29471.9995 | 29471.9995 | 100 | 100 | 100 | 100 | 100 | 100
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 15d | 52639.2004 | 0 | 0 | -5263.9399 | 0 | 47375.2605 | 0 | 100% | Finished | 35092.8003 | 35092.8003 | 100 | 150 | 100 | 100 | 134.9999 | 100
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 2011-12-23 08:00 | 5d | 12834.0002 | 0 | 0 | 0 | 0 | 12834.0002 | 0 | 100% | Finished | 12834.0002 | 12834.0002 | 100 | 100 | 100 | 100 | 100 | 100
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 2011-12-30 08:00 | 10d | 35092.8003 | 0 | 0 | -5263.9399 | 0 | 29828.8604 | 0 | 100% | Finished | 17546.4001 | 17546.4001 | 100 | 200 | 100 | 100 | 169.9999 | 100
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 | 2012-01-13 08:00 | 5d | 9232.0001 | 0 | 0 | 0 | 0 | 9232.0001 | 0 | 100% | Finished | 9232.0001 | 9232.0001 | 100 | 100 | 100 | 100 | 100 | 100
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 | 2012-01-20 08:00 | 10d | 20087.1997 | 0 | 0 | -3013.05 | 0 | 17074.1497 | 0 | 100% | Finished | 10043.5999 | 10043.5999 | 100 | 200 | 100 | 100 | 170.0003 | 100
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 | 2012-02-03 08:00 | 5d | 19426.4001 | 0 | 0 | 0 | 0 | 19426.4001 | 0 | 100% | Finished | 19426.4001 | 19426.4001 | 100 | 100 | 100 | 100 | 100 | 100
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 | 2012-02-10 08:00 | 10d | 26320 | 0 | 0 | 0 | 0 | 26320 | 0 | 100% | Finished | 26320 | 26320 | 100 | 100 | 100 | 100 | 100 | 100
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 | 2012-02-24 08:00 | 10d | 28363.999 | 0 | 0 | -4254.5498 | 0 | 24109.4492 | 0 | 100% | Finished | 14181.9995 | 14181.9995 | 100 | 200 | 100 | 100 | 170.0004 | 100
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 | 2012-02-24 08:00 | 5d | 2956.4001 | 0 | 0 | 0 | 0 | 2956.4001 | 0 | 100% | Finished | 2956.4001 | 2956.4001 | 100 | 100 | 100 | 100 | 100 | 100
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 | 2012-03-02 08:00 | 5d | 6416.7999 | 0 | 0 | 0 | 0 | 6416.7999 | 0 | 100% | Finished | 6416.7999 | 6416.7999 | 100 | 100 | 100 | 100 | 100 | 100
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 | 2012-03-09 08:00 | 2d | 2676.6399 | 0 | 0 | 0 | 0 | 2676.6399 | 0 | 100% | Finished | 2676.6399 | 2676.6399 | 100 | 100 | 100 | 100 | 100 | 100

## TP13
| TP Status Date | 2012-07-05 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (4) | 2011-06-17 08:00 | 2012-05-08 17:00 | 233d |  |  | 0 |  |  | 1992222.0874 |  | 275d | [5 empty] | 2380299.8593 |  | 100% |  | 1992222.0874 | 1992222.0874
40 | Algemeen | 2011-06-17 08:00 | 2011-12-22 17:00 | 135d |  |  | 0 |  |  | 298460.1586 |  | 150d | [5 empty] | 346819.5576 |  | 100% |  | 298460.1586 | 298460.1586
1 | Werfinrichting | 2011-06-17 08:00 | 2011-06-20 17:00 | 2d |  | 0 | 0 | 418.81 | 6700.96 | 6700.96 | 2011-06-17 08:00 | 3d | 10051.4399 | 0 | 0 | -1005.14 | 0 | 9046.2999 | 0 | 100% | Finished | 6700.96 | 6700.96 | 100 | 150 | 100 | 100 | 135.0001 | 100
2 | Ontmanteling | 2011-06-21 08:00 | 2011-07-25 17:00 | 25d |  | 0 | 0 | 167.23 | 33445.9991 | 33445.9991 | 2011-06-22 08:00 | 35d | 46824.3988 | 0 | 0 | -4013.52 | 0 | 42810.8788 | 0 | 100% | Finished | 33445.9991 | 33445.9991 | 100 | 140 | 100 | 100 | 128 | 100
3 | Ruwbouw Aanpassingen | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 890.55 | 142487.998 | 142487.998 | 2011-09-02 08:00 | 25d | 178109.9976 | 0 | 0 | -10686.5703 | 0 | 167423.4272 | 0 | 100% | Finished | 142487.998 | 142487.998 | 100 | 125 | 100 | 100 | 117.5 | 100
4 | Valleidingen in schachten | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 843.69 | 67495.2002 | 67495.2002 | 2011-10-07 08:00 | 10d | 67495.2002 | 0 | 0 | 0 | 0 | 67495.2002 | 0 | 100% | Finished | 67495.2002 | 67495.2002 | 100 | 100 | 100 | 100 | 100 | 100
5 | Dakisolatie 6de verdieping | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 418.35 | 16734.0002 | 16734.0002 | 2011-10-21 08:00 | 10d | 33468.0005 | 0 | 0 | -5020.25 | 0 | 28447.7505 | 0 | 100% | Finished | 16734.0002 | 16734.0002 | 100 | 200 | 100 | 100 | 169.9997 | 100
6 | Herstelling Liften | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 789.9 | 31596.001 | 31596.001 | 2012-01-06 08:00 | 5d | 31596.001 | 0 | 0 | 0 | 0 | 31596.001 | 0 | 100% | Finished | 31596.001 | 31596.001 | 100 | 100 | 100 | 100 | 100 | 100
41 | Verdiepingen (6) | 2011-09-30 08:00 | 2012-05-08 17:00 | 158d |  |  | 0 |  |  | 1457768.0874 |  | 195d | [5 empty] | 1721107.1488 |  | 100% |  | 1457768.0874 | 1457768.0874
7 | Uitzetten wanden | 2011-09-30 08:00 | 2011-10-13 17:00 | 10d |  | 0 | 0 | 193.48 | 15478.3997 | 15478.3997 | 2011-10-07 08:00 | 15d | 23217.5995 | 0 | 0 | -2321.76 | 0 | 20895.8395 | 0 | 100% | Finished | 15478.3997 | 15478.3997 | 100 | 150 | 100 | 100 | 135 | 100
8 | Leidingen Technieken | 2011-10-14 08:00 | 2011-10-27 17:00 | 10d |  | 0 | 0 | 1625.3101 | 130024.8047 | 130024.8047 | 2011-10-28 08:00 | 5d | 65012.4023 | 0 | 0 | 19503.6797 | 0 | 84516.082 | 0 | 100% | Finished | 130024.8047 | 130024.8047 | 100 | 50 | 100 | 100 | 65 | 100
9 | Dekvloer (Chapewerken) | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1432.71 | 57308.3984 | 57308.3984 | 2011-11-04 08:00 | 5d | 57308.3984 | 0 | 0 | 0 | 0 | 57308.3984 | 0 | 100% | Finished | 57308.3984 | 57308.3984 | 100 | 100 | 100 | 100 | 100 | 100
10 | Gyproc fase 1 | 2011-11-04 08:00 | 2011-12-01 17:00 | 20d |  | 0 | 0 | 657.99 | 105278.3984 | 105278.3984 | 2011-11-11 08:00 | 25d | 131597.998 | 0 | 0 | -7895.9199 | 0 | 123702.0781 | 0 | 100% | Finished | 105278.3984 | 105278.3984 | 100 | 125 | 100 | 100 | 117.5 | 100
11 | Elektriciteit in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 962.54 | 77003.1982 | 77003.1982 | 2011-12-16 08:00 | 15d | 115504.7974 | 0 | 0 | -11550.5098 | 0 | 103954.2876 | 0 | 100% | Finished | 77003.1982 | 77003.1982 | 100 | 150 | 100 | 100 | 135 | 100
12 | Sanitair in wanden | 2011-12-02 08:00 | 2011-12-15 17:00 | 10d |  | 0 | 0 | 1083.53 | 86682.4023 | 86682.4023 | 2011-12-16 08:00 | 15d | 130023.6035 | 0 | 0 | -13002.2998 | 0 | 117021.3037 | 0 | 100% | Finished | 86682.4023 | 86682.4023 | 100 | 150 | 100 | 100 | 135.0001 | 100
13 | Gyproc fase 2 (dichten wanden) | 2011-12-16 08:00 | 2011-12-29 17:00 | 10d |  | 0 | 0 | 657.99 | 52639.1992 | 52639.1992 | 2012-01-06 08:00 | 10d | 52639.1992 | 0 | 0 | 0 | 0 | 52639.1992 | 0 | 100% | Finished | 52639.1992 | 52639.1992 | 100 | 100 | 100 | 100 | 100 | 100
14 | Pleisterwerken | 2011-12-30 08:00 | 2012-01-05 17:00 | 5d |  | 0 | 0 | 375 | 15000 | 15000 | 2012-01-20 08:00 | 5d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen Sanitaire Installaties | 2012-01-06 08:00 | 2012-01-12 17:00 | 5d |  | 0 | 0 | 3051.1299 | 122045.1953 | 122045.1953 | 2012-01-27 08:00 | 10d | 244090.3906 | 0 | 0 | -36613.5781 | 0 | 207476.8125 | 0 | 100% | Finished | 122045.1953 | 122045.1953 | 100 | 200 | 100 | 100 | 170 | 100
16 | Stenen vloeren en Faiences | 2012-01-13 08:00 | 2012-02-02 17:00 | 15d |  | 0 | 0 | 502.18 | 60261.5991 | 60261.5991 | 2012-02-10 08:00 | 15d | 60261.5991 | 0 | 0 | 0 | 0 | 60261.5991 | 0 | 100% | Finished | 60261.5991 | 60261.5991 | 100 | 100 | 100 | 100 | 100 | 100
17 | Technieken Ventilatie | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 812.65 | 65012.002 | 65012.002 | 2012-03-02 08:00 | 10d | 65012.002 | 0 | 0 | 0 | 0 | 65012.002 | 0 | 100% | Finished | 65012.002 | 65012.002 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenschrijnwerk | 2012-02-03 08:00 | 2012-02-16 17:00 | 10d |  | 0 | 0 | 1457.05 | 116564.0039 | 116564.0039 | 2012-03-02 08:00 | 15d | 174846.0059 | 0 | 0 | -17484.6094 | 0 | 157361.3965 | 0 | 100% | Finished | 116564.0039 | 116564.0039 | 100 | 150 | 100 | 100 | 135 | 100
19 | Terrassen | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 344.33 | 41319.5984 | 41319.5984 | 2012-03-23 08:00 | 10d | 27546.3989 | 0 | 0 | 4131.9302 | 0 | 31678.3291 | 0 | 100% | Finished | 41319.5984 | 41319.5984 | 100 | 66.6667 | 100 | 100 | 76.6666 | 100
20 | Gyproc: Vals plafond | 2012-02-17 08:00 | 2012-03-08 17:00 | 15d |  | 0 | 0 | 657.99 | 78958.7988 | 78958.7988 | 2012-03-23 08:00 | 15d | 78958.7988 | 0 | 0 | 0 | 0 | 78958.7988 | 0 | 100% | Finished | 78958.7988 | 78958.7988 | 100 | 100 | 100 | 100 | 100 | 100
21 | Parket | 2012-03-09 08:00 | 2012-03-22 17:00 | 10d |  | 0 | 0 | 630.88 | 50470.4004 | 50470.4004 | 2012-04-13 08:00 | 15d | 75705.6006 | 0 | 0 | -7570.5 | 0 | 68135.1006 | 0 | 100% | Finished | 50470.4004 | 50470.4004 | 100 | 150 | 100 | 100 | 135.0001 | 100
22 | Binnenschrijnwerk | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 0 | 1063.64 | 85091.2012 | 85091.2012 | 2012-05-04 08:00 | 15d | 127636.8018 | 0 | 0 | -12763.6396 | 0 | 114873.1621 | 0 | 100% | Finished | 85091.2012 | 85091.2012 | 100 | 150 | 100 | 100 | 135 | 100
23 | Keukens | 2012-03-23 08:00 | 2012-04-19 17:00 | 20d |  | 0 | 0 | 1525.4301 | 244068.8086 | 244068.8086 | 2012-05-04 08:00 | 25d | 305086.0107 | 0 | 0 | -18305.1895 | 0 | 286780.8213 | 0 | 100% | Finished | 244068.8086 | 244068.8086 | 100 | 125 | 100 | 100 | 117.5 | 100
24 | Afwerken Elektriciteit en Sanitair | 2012-04-20 08:00 | 2012-05-03 17:00 | 10d |  | 0 | 0 | 481.27 | 38501.5991 | 38501.5991 | 2012-06-08 08:00 | 15d | 57752.3987 | 0 | 0 | -5775.2598 | 0 | 51977.1389 | 0 | 100% | Finished | 38501.5991 | 38501.5991 | 100 | 150 | 100 | 100 | 134.9999 | 100
25 | Opkuis | 2012-05-04 08:00 | 2012-05-08 17:00 | 3d |  | 0 | 0 | 669.17 | 16060.0796 | 16060.0796 | 2012-06-29 08:00 | 5d | 26766.7993 | 0 | 0 | -3212 | 0 | 23554.7993 | 0 | 100% | Finished | 16060.0796 | 16060.0796 | 100 | 166.6667 | 100 | 100 | 146.6668 | 100
42 | Gelijkvloers | 2011-10-14 08:00 | 2012-01-30 17:00 | 77d |  |  | 0 |  |  | 235993.8414 |  | 97d | [5 empty] | 312373.1528 |  | 100% |  | 235993.8414 | 235993.8414
26 | Uitzetten wanden | 2011-10-14 08:00 | 2011-10-20 17:00 | 5d |  | 0 | 0 | 161.33 | 6453.2001 | 6453.2001 | 2011-10-28 08:00 | 10d | 12906.4001 | 0 | 0 | -1935.96 | 0 | 10970.4402 | 0 | 100% | Finished | 6453.2001 | 6453.2001 | 100 | 200 | 100 | 100 | 170 | 100
27 | Leidingen Technieken | 2011-10-28 08:00 | 2011-11-03 17:00 | 5d |  | 0 | 0 | 1083.54 | 43341.6016 | 43341.6016 | 2011-11-11 08:00 | 10d | 86683.2031 | 0 | 0 | -13002.4502 | 0 | 73680.7529 | 0 | 100% | Finished | 43341.6016 | 43341.6016 | 100 | 200 | 100 | 100 | 170.0001 | 100
28 | Dekvloer (Chapewerken) | 2011-11-04 08:00 | 2011-11-10 17:00 | 5d |  | 0 | 0 | 736.8 | 29471.9995 | 29471.9995 | 2011-11-25 08:00 | 5d | 29471.9995 | 0 | 0 | 0 | 0 | 29471.9995 | 0 | 100% | Finished | 29471.9995 | 29471.9995 | 100 | 100 | 100 | 100 | 100 | 100
29 | Gyproc fase 1 | 2011-11-11 08:00 | 2011-11-24 17:00 | 10d |  | 0 | 0 | 438.66 | 35092.8003 | 35092.8003 | 2011-12-02 08:00 | 15d | 52639.2004 | 0 | 0 | -5263.9399 | 0 | 47375.2605 | 0 | 100% | Finished | 35092.8003 | 35092.8003 | 100 | 150 | 100 | 100 | 134.9999 | 100
30 | Elektriciteit in wanden | 2011-11-25 08:00 | 2011-12-01 17:00 | 5d |  | 0 | 0 | 320.85 | 12834.0002 | 12834.0002 | 2011-12-23 08:00 | 5d | 12834.0002 | 0 | 0 | 0 | 0 | 12834.0002 | 0 | 100% | Finished | 12834.0002 | 12834.0002 | 100 | 100 | 100 | 100 | 100 | 100
31 | Gyproc fase 2 (dichten wanden) | 2011-12-02 08:00 | 2011-12-08 17:00 | 5d |  | 0 | 0 | 438.66 | 17546.4001 | 17546.4001 | 2011-12-30 08:00 | 10d | 35092.8003 | 0 | 0 | -5263.9399 | 0 | 29828.8604 | 0 | 100% | Finished | 17546.4001 | 17546.4001 | 100 | 200 | 100 | 100 | 169.9999 | 100
32 | Pleisterwerken | 2011-12-09 08:00 | 2011-12-15 17:00 | 5d |  | 0 | 0 | 230.8 | 9232.0001 | 9232.0001 | 2012-01-13 08:00 | 5d | 9232.0001 | 0 | 0 | 0 | 0 | 9232.0001 | 0 | 100% | Finished | 9232.0001 | 9232.0001 | 100 | 100 | 100 | 100 | 100 | 100
33 | Stenen vloeren en Faiences | 2011-12-16 08:00 | 2011-12-22 17:00 | 5d |  | 0 | 0 | 251.09 | 10043.5999 | 10043.5999 | 2012-01-20 08:00 | 10d | 20087.1997 | 0 | 0 | -3013.05 | 0 | 17074.1497 | 0 | 100% | Finished | 10043.5999 | 10043.5999 | 100 | 200 | 100 | 100 | 170.0003 | 100
34 | Buitenschrijnwerk | 2011-12-23 08:00 | 2011-12-29 17:00 | 5d |  | 0 | 0 | 485.66 | 19426.4001 | 19426.4001 | 2012-02-03 08:00 | 5d | 19426.4001 | 0 | 0 | 0 | 0 | 19426.4001 | 0 | 100% | Finished | 19426.4001 | 19426.4001 | 100 | 100 | 100 | 100 | 100 | 100
35 | Gyproc: Vals plafond | 2011-12-30 08:00 | 2012-01-12 17:00 | 10d |  | 0 | 0 | 329 | 26320 | 26320 | 2012-02-10 08:00 | 10d | 26320 | 0 | 0 | 0 | 0 | 26320 | 0 | 100% | Finished | 26320 | 26320 | 100 | 100 | 100 | 100 | 100 | 100
36 | Binnenschrijnwerk | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 354.55 | 14181.9995 | 14181.9995 | 2012-02-24 08:00 | 10d | 28363.999 | 0 | 0 | -4254.5498 | 0 | 24109.4492 | 0 | 100% | Finished | 14181.9995 | 14181.9995 | 100 | 200 | 100 | 100 | 170.0004 | 100
37 | Brievenbussen | 2012-01-13 08:00 | 2012-01-19 17:00 | 5d |  | 0 | 0 | 73.91 | 2956.4001 | 2956.4001 | 2012-02-24 08:00 | 5d | 2956.4001 | 0 | 0 | 0 | 0 | 2956.4001 | 0 | 100% | Finished | 2956.4001 | 2956.4001 | 100 | 100 | 100 | 100 | 100 | 100
38 | Afwerken Elektriciteit | 2012-01-20 08:00 | 2012-01-26 17:00 | 5d |  | 0 | 0 | 160.42 | 6416.7999 | 6416.7999 | 2012-03-02 08:00 | 5d | 6416.7999 | 0 | 0 | 0 | 0 | 6416.7999 | 0 | 100% | Finished | 6416.7999 | 6416.7999 | 100 | 100 | 100 | 100 | 100 | 100
39 | Opkuis | 2012-01-27 08:00 | 2012-01-30 17:00 | 2d |  | 0 | 0 | 167.29 | 2676.6399 | 2676.6399 | 2012-03-09 08:00 | 2d | 2676.6399 | 0 | 0 | 0 | 0 | 2676.6399 | 0 | 100% | Finished | 2676.6399 | 2676.6399 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
25/07, 2011 | 2011-06-17 08:00 | 2011-07-25 17:00 | 40146.9591 | 29635.36 | 38402.339 | 2011-07-14 09:00 | -10511.5991 | 73.82% | -8766.979 | 77.17% | -7d 7h | 70.83% | 100% | 2012-05-10 10:00 | 2012-08-31 14:00 | 2013-01-09 17:00 | 2012-05-18 09:00 | 2012-08-31 14:00 | 2012-12-28 17:00 | 2012-05-18 16:00 | 2012-09-19 17:00 | 2013-01-23 10:00 | 2000989.0664 | 2581577.8158 | 2697114.4007 | 2809113.013 | 3483636.7435 | 3628767.718 | 2603874.7713 | 2624045.2429 | 0.70833 | 0.77171 | 0.73817 | 1 | -7.875 | 0.77171 | 1 | 0.70833 | 1
09/08, 2011 | 2011-07-25 17:00 | 2011-08-09 17:00 | 40146.9591 | 40146.9591 | 51857.1787 | 2011-08-09 17:00 | 0 | 100% | -11710.2196 | 77.42% | 0 | 100% | 100% | 2012-05-08 17:00 | 2012-05-08 17:00 | 2012-08-10 17:00 | 2012-05-08 17:00 | 2012-05-08 17:00 | 2012-07-26 16:00 | 2012-05-08 17:00 | 2012-05-08 17:00 | 2012-07-26 16:00 | 2003932.307 | 2573321.0962 | 2003932.307 | 2003932.307 | 2573321.0962 | 2573321.0962 | 2434335.0335 | 2434335.0335 | 1 | 0.77418 | 1 | 1 | 0 | 0.77418 | 1 | 1 | 1
09/09, 2011 | 2011-08-09 17:00 | 2011-09-09 17:00 | 82893.3585 | 74344.0779 | 92038.7981 | 2011-09-08 15:00 | -8549.2806 | 89.69% | -17694.7202 | 80.77% | -1d 2h | 97.95% | 100% | 2012-05-09 17:00 | 2012-06-14 15:00 | 2012-09-10 14:00 | 2012-05-17 10:00 | 2012-06-14 15:00 | 2012-08-21 09:00 | 2012-05-10 10:00 | 2012-05-15 16:00 | 2012-07-12 17:00 | 2009916.8076 | 2466393.1776 | 2230465.3411 | 2050039.7785 | 2739434.7235 | 2516065.8634 | 2415132.82 | 2369534.8774 | 0.97951 | 0.80775 | 0.89686 | 1 | -1.25 | 0.80775 | 1 | 0.97951 | 1
13/10, 2011 | 2011-09-09 17:00 | 2011-10-13 17:00 | 265608.557 | 221542.024 | 259993.4859 | 2011-10-06 14:00 | -44066.533 | 83.41% | -38451.4619 | 85.21% | -5d 3h | 93.68% | 99.1% | 2012-05-16 09:00 | 2012-07-12 11:00 | 2012-09-18 16:00 | 2012-05-29 09:00 | 2012-07-12 11:00 | 2012-08-29 09:00 | 2012-05-16 11:00 | 2012-05-30 15:00 | 2012-07-10 09:00 | 2030673.5493 | 2337997.8026 | 2382876.3962 | 2150201.4029 | 2751329.9743 | 2478271.2494 | 2346821.0765 | 2297511.4067 | 0.93676 | 0.85211 | 0.83409 | 0.99095 | -5.375 | 0.85211 | 1 | 0.93676 | 1
10/11, 2011 | 2011-10-13 17:00 | 2011-11-10 17:00 | 575262.1611 | 476128.9604 | 488914.3168 | 2011-11-01 15:00 | -99133.2007 | 82.77% | -12785.3563 | 97.38% | -7d 2h | 93.1% | 94.97% | 2012-05-24 14:00 | 2012-07-16 12:00 | 2012-07-26 09:00 | 2012-06-04 09:00 | 2012-07-16 12:00 | 2012-07-23 10:00 | 2012-05-18 10:00 | 2012-06-01 10:00 | 2012-06-07 09:00 | 2005007.4437 | 2045718.6637 | 2320668.0666 | 2117454.2485 | 2369855.632 | 2161184.9708 | 2093900.9161 | 2059555.7059 | 0.93095 | 0.97385 | 0.82767 | 0.94973 | -7.25 | 0.97385 | 1 | 0.93095 | 1
15/12, 2011 | 2011-11-10 17:00 | 2011-12-15 17:00 | 892611.7614 | 677616.1609 | 747352.6476 | 2011-11-28 15:00 | -214995.6005 | 75.91% | -69736.4867 | 90.67% | -13d 2h | 89.81% | 97.61% | 2012-06-13 09:00 | 2012-08-20 16:00 | 2012-10-03 12:00 | 2012-06-21 10:00 | 2012-08-20 16:00 | 2012-09-14 09:00 | 2012-05-28 10:00 | 2012-06-14 12:00 | 2012-07-03 15:00 | 2061958.5741 | 2197250.5049 | 2479059.7398 | 2211153.6793 | 2657277.4029 | 2361799.9406 | 2246027.8667 | 2200009.9712 | 0.89808 | 0.90669 | 0.75914 | 0.97608 | -13.25 | 0.90669 | 1 | 0.89808 | 1
12/01, 2012 | 2011-12-15 17:00 | 2012-01-12 17:00 | 1169682.1569 | 941295.3618 | 1084698.4603 | 2011-12-21 12:00 | -228386.795 | 80.47% | -143403.0985 | 86.78% | -16d 4h | 89% | 98.27% | 2012-06-14 15:00 | 2012-07-26 12:00 | 2012-09-26 14:00 | 2012-06-19 10:00 | 2012-07-26 12:00 | 2012-08-24 15:00 | 2012-05-31 12:00 | 2012-06-18 15:00 | 2012-07-11 16:00 | 2135625.1859 | 2295730.2442 | 2390611.8739 | 2265515.0059 | 2589563.2737 | 2445408.3298 | 2313587.3205 | 2289564.1207 | 0.89 | 0.86779 | 0.80474 | 0.9827 | -16.5 | 0.86779 | 1 | 0.89 | 1
16/02, 2012 | 2012-01-12 17:00 | 2012-02-16 17:00 | 1437751.6013 | 1176609.3572 | 1412474.6221 | 2012-01-13 16:00 | -261142.2442 | 81.84% | -235865.2649 | 83.3% | -24d 1h | 86.21% | 98.63% | 2012-06-20 12:00 | 2012-07-19 15:00 | 2012-10-08 15:00 | 2012-06-21 15:00 | 2012-07-19 15:00 | 2012-08-20 15:00 | 2012-06-12 09:00 | 2012-06-29 10:00 | 2012-07-26 11:00 | 2228087.3523 | 2391586.5728 | 2409108.2982 | 2358504.3009 | 2608895.3087 | 2548147.1415 | 2395041.4563 | 2384786.3042 | 0.86214 | 0.83301 | 0.81837 | 0.98626 | -24.125 | 0.83301 | 1 | 0.86214 | 1
15/03, 2012 | 2012-02-16 17:00 | 2012-03-15 17:00 | 1583265.1987 | 1398896.9357 | 1671887.9161 | 2012-02-14 15:00 | -184368.2631 | 88.36% | -272990.9805 | 83.67% | -22d 2h | 88.59% | 99.1% | 2012-06-07 14:00 | 2012-06-20 15:00 | 2012-08-31 09:00 | 2012-06-08 15:00 | 2012-06-20 15:00 | 2012-07-10 09:00 | 2012-06-08 10:00 | 2012-06-19 17:00 | 2012-07-09 10:00 | 2265213.0679 | 2380998.878 | 2343410.6283 | 2341632.6605 | 2474456.4823 | 2472331.5489 | 2373148.3167 | 2372759.7176 | 0.8859 | 0.83672 | 0.88355 | 0.99096 | -22.25 | 0.83672 | 1 | 0.8859 | 1
12/04, 2012 | 2012-03-15 17:00 | 2012-04-12 17:00 | 1876643.2065 | 1558029.9985 | 1834978.837 | 2012-03-08 17:00 | -318613.208 | 83.02% | -276948.8385 | 84.91% | -25d | 88.37% | 100% | 2012-06-29 10:00 | 2012-07-13 14:00 | 2012-09-21 12:00 | 2012-06-28 12:00 | 2012-07-13 14:00 | 2012-07-31 11:00 | 2012-06-12 17:00 | 2012-06-20 14:00 | 2012-07-03 10:00 | 2269170.9259 | 2346351.0796 | 2357962.1138 | 2326301.4639 | 2450925.4144 | 2413636.901 | 2348631.8572 | 2342211.3084 | 0.88372 | 0.84907 | 0.83022 | 1 | -25 | 0.84907 | 1 | 0.88372 | 1
10/05, 2012 | 2012-04-12 17:00 | 2012-05-10 17:00 | 1992222.0874 | 1685677.8959 | 1998761.1505 | 2012-03-28 14:00 | -306544.1915 | 84.61% | -313083.2546 | 84.34% | -31d 3h | 86.65% | 99.85% | 2012-06-27 16:00 | 2012-07-06 11:00 | 2012-09-17 12:00 | 2012-07-02 09:00 | 2012-07-10 15:00 | 2012-07-20 14:00 | 2012-06-21 11:00 | 2012-06-27 16:00 | 2012-07-06 10:00 | 2305305.342 | 2362240.2127 | 2361051.0699 | 2352538.3635 | 2428339.6707 | 2418245.8877 | 2362001.7601 | 2360257.5055 | 0.86649 | 0.84336 | 0.84613 | 0.99853 | -31.375 | 0.84336 | 1 | 0.86649 | 1
07/06, 2012 | 2012-05-10 17:00 | 2012-06-07 17:00 | 1992222.0874 | 1937660.4087 | 2304767.921 | 2012-04-19 17:00 | -54561.6787 | 97.26% | -367107.5123 | 84.07% | -35d | 86.27% | 100% | 2012-05-17 11:00 | 2012-05-17 12:00 | 2012-07-19 17:00 | 2012-06-18 17:00 | 2012-06-19 09:00 | 2012-06-20 12:00 | 2012-06-26 17:00 | 2012-06-29 09:00 | 2012-07-03 16:00 | 2359329.5997 | 2369666.8095 | 2360865.9767 | 2368009.8668 | 2371494.2672 | 2379991.6327 | 2367692.4513 | 2369328.5113 | 0.86275 | 0.84072 | 0.97261 | 1 | -35 | 0.84072 | 1 | 0.86275 | 1
Actual Schedule | 2012-06-07 17:00 | 2012-07-05 17:00 | 1992222.0874 | 1992222.0874 | 2380299.8593 | 2012-05-08 17:00 | 0 | 100% | -388077.7719 | 83.7% | -42d | 84.73% | 100% | 2012-05-08 17:00 | 2012-05-08 17:00 | 2012-07-11 11:00 | 2012-07-05 17:00 | 2012-07-05 17:00 | 2012-07-05 17:00 | 2012-07-05 17:00 | 2012-07-05 17:00 | 2012-07-05 17:00 | 2380299.8593 | 2380299.8593 | 2380299.8593 | 2380299.8593 | 2380299.8593 | 2380299.8593 | 2380299.8593 | 2380299.8593 | 0.84727 | 0.83696 | 1 | 1 | -42 | 0.83696 | 1 | 0.84727 | 1