## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Compressor Station Zelzate | 1 |  |  | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 | 729.375
24 | JUNE 06 | 1.1 |  | FS1 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 29.375
1 | July | 1.2 | 24FS | FS2 | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 28.375
2 | August | 1.3 | 1FS | FS3 | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 30.375
3 | September | 1.4 | 2FS | FS4 | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 28.375
4 | October | 1.5 | 3FS | FS5 | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 29.375
5 | November | 1.6 | 4FS | FS6 | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 29.375
6 | December | 1.7 | 5FS | FS7 | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 28.375
7 | January 07 | 1.8 | 6FS | FS8 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 30.375
8 | February | 1.9 | 7FS | FS9 | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 27.375
9 | March | 1.10 | 8FS | FS10 | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 29.375
10 | April | 1.11 | 9FS | FS11 | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 28.375
11 | May | 1.12 | 10FS | FS12 | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 30.375
12 | June | 1.13 | 11FS | FS13 | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 28.375
13 | July | 1.14 | 12FS | FS14 | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 29.375
14 | August | 1.15 | 13FS | FS15 | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 30.375
15 | September | 1.16 | 14FS | FS16 | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 25.375
16 | October | 1.17 | 15FS | FS17 | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 30.375
17 | November | 1.18 | 16FS | FS18 | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 29.375
18 | December | 1.19 | 17FS | FS19 | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 28.375
19 | January 08 | 1.20 | 18FS | FS20 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 30.375
20 | February | 1.21 | 19FS | FS21 | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 27.375
21 | March | 1.22 | 20FS | FS22 | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 28.375
22 | April | 1.23 | 21FS | FS23 | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 29.375
23 | May | 1.24 | 22FS |  | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 | 29.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Compressor Station Zelzate | 4176h |  |  |  |  | 99 | 100 | 101
24 | JUNE 06 | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | July | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | August | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | September | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | October | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | November | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | December | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | January 07 | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | February | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | March | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | April | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | May | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | June | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | July | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | August | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | September | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | October | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | November | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | December | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | January 08 | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | February | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | March | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | April | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | May | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-06-30 17:00 |  | TP Name | 30/06, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 22d | [5 empty] | 6238559.9375 |  | 10% |  | 6238559.9375 | 6238559.9375
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 |  | 0 | 0 | 2052486.0234 | 21d | 0 | 0 | 0 | 2052486.0234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 |  | 0 | 0 | 879636.9766 | 23d | 0 | 0 | 0 | 879636.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 |  | 0 | 0 | 2564047.9922 | 21d | 0 | 0 | 0 | 2564047.9922 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 |  | 0 | 0 | 2620195.0156 | 22d | 0 | 0 | 0 | 2620195.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2006-07-31 17:00 |  | TP Name | 31/07, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 43d | [5 empty] | 6424700.9609 |  | 10.3% |  | 6423283.6869 | 8291045.9609
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 21d | 2052486.0234 | 20756986.6299 | 212d 3h | -1866345 | 0 | 186141.0234 | 20756986.6299 | 9% | Started | 184723.7494 | 2052486.0234 | 100 | 100 | 9 | 100 | 9.0691 | 9
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 |  | 0 | 0 | 879636.9766 | 23d | 0 | 0 | 0 | 879636.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 |  | 0 | 0 | 2564047.9922 | 21d | 0 | 0 | 0 | 2564047.9922 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 |  | 0 | 0 | 2620195.0156 | 22d | 0 | 0 | 0 | 2620195.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2006-08-31 17:00 |  | TP Name | 31/08, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 66d | [5 empty] | 8149090.3438 |  | 13.06% |  | 8147371.954 | 9170682.9375
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 44d | 4300446.9062 | 317646.6465 | 3d 2h | -2389916.5 | 0 | 1910530.4062 | 317646.6465 | 93% | Started | 1908812.0165 | 2052486.0234 | 100 | 209.5238 | 93 | 100 | 93.0837 | 93
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 |  | 0 | 0 | 879636.9766 | 23d | 0 | 0 | 0 | 879636.9766 | 0% | Not Started | 0 | 879636.9766 | 100 |  | 0 | 100 |  | 0
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 |  | 0 | 0 | 2564047.9922 | 21d | 0 | 0 | 0 | 2564047.9922 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 |  | 0 | 0 | 2620195.0156 | 22d | 0 | 0 | 0 | 2620195.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2006-09-30 17:00 |  | TP Name | 30/09, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 87d | [5 empty] | 8335230.9219 |  | 13.36% |  | 8335027.8104 | 11734730.9297
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 6d | 229470.5156 | 4359939.7969 | 114d | -185285.3125 | 0 | 44185.2031 | 4359939.7969 | 5% | Started | 43981.8495 | 879636.9766 | 100 | 26.087 | 5 | 100 | 5.0231 | 5
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 |  | 0 | 0 | 2564047.9922 | 21d | 0 | 0 | 0 | 2564047.9922 | 0% | Not Started | 0 | 2564047.9922 | 100 |  | 0 | 100 |  | 0
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 |  | 0 | 0 | 2620195.0156 | 22d | 0 | 0 | 0 | 2620195.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2006-10-31 17:00 |  | TP Name | 31/10, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 109d | [5 empty] | 9077284.7109 |  | 14.54% |  | 9073922.8575 | 14354925.9453
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 29d | 1109107.4922 | 138638.4365 | 3d 5h | -322868.5 | 0 | 786238.9922 | 138638.4365 | 89% | Started | 782876.8966 | 879636.9766 | 100 | 126.087 | 89 | 100 | 89.3822 | 89
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 |  | 0 | 0 | 2564047.9922 | 21d | 0 | 0 | 0 | 2564047.9922 | 0% | Not Started | 0 | 2564047.9922 | 100 |  | 0 | 100 |  | 0
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 |  | 0 | 0 | 2620195.0156 | 22d | 0 | 0 | 0 | 2620195.0156 | 0% | Not Started | 0 | 2620195.0156 | 100 |  | 0 | 100 |  | 0
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2006-11-30 17:00 |  | TP Name | 30/11, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 131d | [5 empty] | 10827394.4531 |  | 17.37% |  | 10837314.0713 | 15471627.8984
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 19d | 2319852.9453 | 1251499.6152 | 10d 2h | -663533.375 | 0 | 1656319.5703 | 1251499.6152 | 65% | Started | 1666631.1338 | 2564047.9922 | 100 | 90.4762 | 65 | 100 | 64.5978 | 65
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 |  | 0 | 0 | 2620195.0156 | 22d | 0 | 0 | 0 | 2620195.0156 | 0% | Not Started | 0 | 2620195.0156 | 100 |  | 0 | 100 |  | 0
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 1116701.9531 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2006-12-31 17:00 |  | TP Name | 31/12, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 152d | [5 empty] | 11127791.2969 |  | 17.82% |  | 11119359.3871 | 16856587.9062
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 39d | 4761803.4141 | 1510956.8525 | 12d 3h | -2805087 | 0 | 1956716.4141 | 1510956.8525 | 76% | Started | 1948676.4496 | 2564047.9922 | 100 | 185.7143 | 76 | 100 | 76.3136 | 76
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 |  | 0 | 0 | 2620195.0156 | 22d | 0 | 0 | 0 | 2620195.0156 | 0% | Not Started | 0 | 2620195.0156 | 100 |  | 0 | 100 |  | 0
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 1116701.9531 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 1384960.0078 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2007-01-31 17:00 |  | TP Name | 31/01, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 175d | [5 empty] | 12013010.4141 |  | 19.27% |  | 12022952.3798 | 18247786.9297
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 22d | 2620195.0156 | 21199759.6719 | 178d | -2342306.75 | 0 | 277888.2656 | 21199759.6719 | 11% | Started | 288221.4502 | 2620195.0156 | 100 | 100 | 11 | 100 | 10.6056 | 11
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 1116701.9531 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 1384960.0078 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 1391199.0234 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2007-02-28 17:00 |  | TP Name | 28/02, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 195d | [5 empty] | 13410441.6328 |  | 21.5% |  | 13411655.7022 | 22683402.8672
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 42d | 5002190.4844 | 2813732.1475 | 23d 5h | -3326871 | 0 | 1675319.4844 | 2813732.1475 | 64% | Started | 1676924.7725 | 2620195.0156 | 100 | 190.9091 | 64 | 100 | 63.9387 | 64
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 |  | 0 | 0 | 1116701.9531 | 22d | 0 | 0 | 0 | 1116701.9531 | 0% | Not Started | 0 | 1116701.9531 | 100 |  | 0 | 100 |  | 0
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 1384960.0078 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 1391199.0234 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 4435615.9375 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2007-03-31 17:00 |  | TP Name | 31/03, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 217d | [5 empty] | 15251763.3047 |  | 24.44% |  | 15248287.5211 | 26351675.9922
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 17d | 862906.0547 | 215726.5137 | 4d 2h | 33540.25 | 0 | 896446.3047 | 215726.5137 | 80% | Started | 893361.5758 | 1116701.9531 | 100 | 77.2727 | 80 | 100 | 80.2762 | 80
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 |  | 0 | 0 | 1384960.0078 | 21d | 0 | 0 | 0 | 1384960.0078 | 0% | Not Started | 0 | 1384960.0078 | 100 |  | 0 | 100 |  | 0
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 1391199.0234 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 4435615.9375 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 3668273.125 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2007-04-30 17:00 |  | TP Name | 30/04, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 238d | [5 empty] | 16725411.6719 |  | 26.8% |  | 16718091.8724 | 28971870.9297
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 18d | 1187108.5781 | 131900.9531 | 2d | 66284.1328 | 0 | 1253392.7109 | 131900.9531 | 90% | Started | 1246463.974 | 1384960.0078 | 100 | 85.7143 | 90 | 100 | 90.5003 | 90
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 |  | 0 | 0 | 1391199.0234 | 23d | 0 | 0 | 0 | 1391199.0234 | 0% | Not Started | 0 | 1391199.0234 | 100 |  | 0 | 100 |  | 0
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 |  | 0 | 0 | 4435615.9375 | 20d | 0 | 0 | 0 | 4435615.9375 | 0% | Not Started | 0 | 4435615.9375 | 100 |  | 0 | 100 |  | 0
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 3668273.125 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 2620194.9375 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2007-05-31 17:00 |  | TP Name | 31/05, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 261d | [5 empty] | 18964006.7344 |  | 30.39% |  | 18957485.4638 | 31598304.8984
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 2d | 443561.5938 | 2328698.3672 | 10d 4h | 272267.0938 | 0 | 715828.6875 | 2328698.3672 | 16% | Started | 709698.5341 | 4435615.9375 | 100 | 10 | 16 | 100 | 16.1382 | 16
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 3668273.125 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 2620194.9375 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 2626433.9688 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2007-06-30 17:00 |  | TP Name | 30/06, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 282d | [5 empty] | 20807434.9219 |  | 33.37% |  | 20820444.0994 | 38785125.7109
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 24d | 5322739.125 | 3853441.3457 | 17d 3h | -2763482.25 | 0 | 2559256.875 | 3853441.3457 | 58% | Started | 2572657.1697 | 4435615.9375 | 100 | 120 | 58 | 100 | 57.6979 | 58
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 |  | 0 | 0 | 3668273.125 | 22d | 0 | 0 | 0 | 3668273.125 | 0% | Not Started | 0 | 3668273.125 | 100 |  | 0 | 100 |  | 0
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 2620194.9375 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 2626433.9688 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 7186820.8125 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2007-07-31 17:00 |  | TP Name | 31/07, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 304d | [5 empty] | 24922950.75 |  | 39.83% |  | 24847683.9147 | 41448990.7266
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 11d | 1834136.5625 | 1271390.1172 | 7d 5h | 405020.25 | 0 | 2239156.8125 | 1271390.1172 | 59% | Started | 2164281.0475 | 3668273.125 | 100 | 50 | 59 | 100 | 61.0412 | 59
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 |  | 0 | 0 | 2620194.9375 | 21d | 0 | 0 | 0 | 2620194.9375 | 0% | Not Started | 0 | 2620194.9375 | 100 |  | 0 | 100 |  | 0
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 2626433.9688 | 100 |  | 0 | 100 |  | 0
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 |  | 0 | 0 | 7186820.8125 | 21d | 0 | 0 | 0 | 7186820.8125 | 0% | Not Started | 0 | 7186820.8125 | 100 |  | 0 | 100 |  | 0
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 2663865.0156 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2007-08-31 17:00 |  | TP Name | 31/08, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 327d | [5 empty] | 32887206.125 |  | 52.61% |  | 32820064.4494 | 43470283.7344
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 2d | 684459.125 | 3336738.2344 | 9d 6h | 514450.9688 | 0 | 1198910.0938 | 3336738.2344 | 17% | Started | 1221759.551 | 7186820.8125 | 100 | 9.5238 | 17 | 100 | 16.6821 | 17
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 |  | 0 | 0 | 2663865.0156 | 22d | 0 | 0 | 0 | 2663865.0156 | 0% | Not Started | 0 | 2663865.0156 | 100 |  | 0 | 100 |  | 0
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 2021293.0078 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2007-09-30 17:00 |  | TP Name | 30/09, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 347d | [5 empty] | 40014764.4766 |  | 62.43% |  | 38944957.6083 | 46209011.8594
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 3d | 363254.3203 | 5690984.3516 | 47d | 776393.3125 | 0 | 1139647.6328 | 5690984.3516 | 6% | Started | 159831.8974 | 2663865.0156 | 100 | 13.6364 | 6 | 100 | 42.7817 | 6
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 |  | 0 | 0 | 2021293.0078 | 23d | 0 | 0 | 0 | 2021293.0078 | 0% | Not Started | 0 | 2021293.0078 | 100 |  | 0 | 100 |  | 0
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 2738728.125 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2007-10-31 17:00 |  | TP Name | 31/10, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 370d | [5 empty] | 43004373.2188 |  | 67.09% |  | 41853249.3341 | 48835445.8281
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 8d | 703058.4375 | 2812233.75 | 32d | -213741.9844 | 0 | 489316.4531 | 2812233.75 | 20% | Started | 404258.6076 | 2021293.0078 | 100 | 34.7826 | 20 | 100 | 24.2081 | 20
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 |  | 0 | 0 | 2738728.125 | 20d | 0 | 0 | 0 | 2738728.125 | 0% | Not Started | 0 | 2738728.125 | 100 |  | 0 | 100 |  | 0
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 |  | 0 | 0 | 2626433.9688 | 23d | 0 | 0 | 0 | 2626433.9688 | 0% | Not Started | 0 | 2626433.9688 | 100 |  | 0 | 100 |  | 0
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2007-11-30 17:00 |  | TP Name | 30/11, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 392d | [5 empty] | 47926924.2773 |  | 74.28% |  | 46340333.5598 | 51430686.8281
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 1d | 114192.7812 | 2169662.8438 | 19d | 22745.6602 | 0 | 136938.4414 | 2169662.8438 | 5% | Started | 131321.7004 | 2626433.9688 | 100 | 4.3478 | 5 | 100 | 5.2139 | 5
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 2595241 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2007-12-31 17:00 |  | TP Name | 31/12, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 413d | [5 empty] | 49388059.6172 |  | 77% |  | 48039556.723 | 52921702.7422
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 23d | 2626433.9688 | 1141927.8125 | 10d | -1028360.1875 | 0 | 1598073.7812 | 1141927.8125 | 69.7% | Started | 1830544.8636 | 2626433.9688 | 100 | 100 | 69.697 | 100 | 60.8458 | 69.697
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 |  | 0 | 0 | 2595241 | 22d | 0 | 0 | 0 | 2595241 | 0% | Not Started | 0 | 2595241 | 100 |  | 0 | 100 |  | 0
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 1491015.9141 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2008-01-31 17:00 |  | TP Name | 31/01, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 436d | [5 empty] | 50843984.9297 |  | 79.57% |  | 49638734.7385 | 54219322.7617
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 13d | 1533551.5 | 3420999.5 | 29d | -1219554 | 0 | 313997.5 | 3420999.5 | 30.95% | Started | 803288.9104 | 2595241 | 100 | 59.0909 | 30.9524 | 100 | 12.099 | 30.9524
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 |  | 0 | 0 | 1491015.9141 | 21d | 0 | 0 | 0 | 1491015.9141 | 0% | Not Started | 0 | 1491015.9141 | 100 |  | 0 | 100 |  | 0
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 1297620.0195 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2008-02-29 17:00 |  | TP Name | 29/02, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 457d | [5 empty] | 52514677.1016 |  | 83.12% |  | 51856691.394 | 55011619.7148
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 6d | 426004.5469 | 1065011.3672 | 15d | 0 | 0 | 426004.5469 | 1065011.3672 | 28.57% | Started | 426004.5659 | 1491015.9141 | 100 | 28.5714 | 28.5714 | 100 | 28.5714 | 28.5714
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 |  | 0 | 0 | 1297620.0195 | 23d | 0 | 0 | 0 | 1297620.0195 | 0% | Not Started | 0 | 1297620.0195 | 100 |  | 0 | 100 |  | 0
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 |  | 0 | 0 | 792296.9531 | 20d | 0 | 0 | 0 | 792296.9531 | 0% | Not Started | 0 | 792296.9531 | 100 |  | 0 | 100 |  | 0
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2008-03-31 17:00 |  | TP Name | 31/03, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 478d | [5 empty] | 55156536.2227 |  | 87.12% |  | 54351372.2578 | 59066683.6211
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 2d | 79229.6953 | 396148.4766 | 10d | 0 | 0 | 79229.6953 | 396148.4766 | 16.67% | Started | 132049.4961 | 792296.9531 | 100 | 10 | 16.6667 | 100 | 10 | 16.6667
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 |  | 0 | 0 | 4055063.9062 | 21d | 0 | 0 | 0 | 4055063.9062 | 0% | Not Started | 0 | 4055063.9062 | 100 |  | 0 | 100 |  | 0
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2008-04-30 17:00 |  | TP Name | 30/04, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 500d | [5 empty] | 56605187.9492 |  | 89.8% |  | 56025385.6914 | 59266317.6152
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 12d | 2317179.375 | 6951538.125 | 36d | -1264676.125 | 0 | 1052503.25 | 6951538.125 | 25% | Started | 1013765.9766 | 4055063.9062 | 100 | 57.1429 | 25 | 100 | 25.9553 | 25
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 199633.9941 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2008-05-31 17:00 |  | TP Name | 31/05, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 522d | [5 empty] | 57829313.543 |  | 90.04% |  | 56174957.6633 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 35d | 6758439.8438 | 16799550.4688 | 87d | -4481811 | 0 | 2276628.8438 | 16799550.4688 | 28.69% | Started | 1163337.9484 | 4055063.9062 | 100 | 166.6667 | 28.6885 | 100 | 56.1429 | 28.6885
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 199633.9941 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2008-06-30 17:00 |  | TP Name | 30/06, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 543d | [5 empty] | 58991373.668 |  | 91.11% |  | 56839722.2916 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 55d | 10620405.4688 | 12937584.8438 | 67d | -7181716.5 | 0 | 3438688.9688 | 12937584.8438 | 45.08% | Started | 1828102.5767 | 4055063.9062 | 100 | 261.9048 | 45.082 | 100 | 84.7999 | 45.082
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 199633.9941 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2008-07-31 17:00 |  | TP Name | 31/07, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 566d | [5 empty] | 59405161.3555 |  | 92.28% |  | 57570963.4189 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 77d | 14868567.6562 | 8689422.6562 | 45d | -11016091 | 0 | 3852476.6562 | 8689422.6562 | 63.11% | Started | 2559343.7041 | 4055063.9062 | 100 | 366.6667 | 63.1148 | 100 | 95.0041 | 63.1148
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 199633.9941 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2008-08-31 17:00 |  | TP Name | 31/08, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 587d | [5 empty] | 59681681.9805 |  | 93.35% |  | 58235727.9264 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 97d | 18730533.2812 | 4827457.0312 | 25d | -14601536 | 0 | 4128997.2812 | 4827457.0312 | 79.51% | Started | 3224108.2115 | 4055063.9062 | 100 | 461.9048 | 79.5082 | 100 | 101.8232 | 79.5082
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 199633.9941 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2008-09-30 17:00 |  | TP Name | 30/09, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 609d | [5 empty] | 60620647.6055 |  | 94.41% |  | 58900492.4338 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 117d | 22592498.9062 | 965491.4062 | 5d | -17524536 | 0 | 5067962.9062 | 965491.4062 | 95.9% | Started | 3888872.719 | 4055063.9062 | 100 | 557.1429 | 95.9016 | 100 | 124.9786 | 95.9016
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 |  | 0 | 0 | 199633.9941 | 22d | 0 | 0 | 0 | 199633.9941 | 0% | Not Started | 0 | 199633.9941 | 100 |  | 0 | 100 |  | 0
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP29
| TP Status Date | 2008-10-31 17:00 |  | TP Name | 31/10, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 632d | [5 empty] | 61034809.916 |  | 94.81% |  | 59150251.3378 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 100% | Finished | 4055063.9062 | 4055063.9062 | 100 | 580.9524 | 100 | 100 | 131.1641 | 100
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 18d | 163336.9043 | 226856.8115 | 25d | 0 | 0 | 163336.9043 | 226856.8115 | 41.86% | Started | 83567.7167 | 199633.9941 | 100 | 81.8182 | 41.8605 | 100 | 81.8182 | 41.8605
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP30
| TP Status Date | 2008-11-30 17:00 |  | TP Name | 30/11, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 652d | [5 empty] | 61446403.6777 |  | 94.96% |  | 59243104.3609 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 100% | Finished | 4055063.9062 | 4055063.9062 | 100 | 580.9524 | 100 | 100 | 131.1641 | 100
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 38d | 344822.3535 | 45371.3623 | 5d | 230108.3125 | 0 | 574930.666 | 45371.3623 | 88.37% | Started | 176420.7398 | 199633.9941 | 100 | 172.7273 | 88.3721 | 100 | 287.9924 | 88.3721
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP31
| TP Status Date | 2008-12-31 17:00 |  | TP Name | 31/12, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 675d | [5 empty] | 61841559.1025 |  | 94.96% |  | 59243104.3609 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 100% | Finished | 4055063.9062 | 4055063.9062 | 100 | 580.9524 | 100 | 100 | 131.1641 | 100
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 43d | 390193.7158 | 51042.7826 | 5d 5h | 579892.375 | 0 | 970086.0908 | 51042.7826 | 88.37% | Started | 176420.7398 | 199633.9941 | 100 | 195.4545 | 88.3721 | 100 | 485.9323 | 88.3721
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP32
| TP Status Date | 2009-01-31 17:00 |  | TP Name | 31/01, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 697d | [5 empty] | 62076304.1143 |  | 94.96% |  | 59243104.3609 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 100% | Finished | 4055063.9062 | 4055063.9062 | 100 | 580.9524 | 100 | 100 | 131.1641 | 100
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 63d | 571679.165 | 74862.7478 | 8d 2h | 633151.9375 | 0 | 1204831.1025 | 74862.7478 | 88.37% | Started | 176420.7398 | 199633.9941 | 100 | 286.3636 | 88.3721 | 100 | 603.52 | 88.3721
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP33
| TP Status Date | 2009-02-28 17:00 |  | TP Name | 28/02, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 717d | [5 empty] | 62409998.3389 |  | 95% |  | 59266317.6152 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 100% | Finished | 4055063.9062 | 4055063.9062 | 100 | 580.9524 | 100 | 100 | 131.1641 | 100
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 73d | 662421.8896 | 0 | 0 | 876103.4375 | 0 | 1538525.3271 | 0 | 100% | Finished | 199633.9941 | 199633.9941 | 100 | 331.8182 | 100 | 100 | 770.673 | 100
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 |  | 0 | 0 | 3119279.9688 | 22d | 0 | 0 | 0 | 3119279.9688 | 0% | Not Started | 0 | 3119279.9688 | 100 |  | 0 | 100 |  | 0

## TP34
| TP Status Date | 2009-06-30 17:00 |  | TP Name | 30/06, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 804d | [5 empty] | 62424248.917 |  | 95.92% |  | 59839246.5948 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 100% | Finished | 4055063.9062 | 4055063.9062 | 100 | 580.9524 | 100 | 100 | 131.1641 | 100
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 73d | 662421.8896 | 0 | 0 | 876103.4375 | 0 | 1538525.3271 | 0 | 100% | Finished | 199633.9941 | 199633.9941 | 100 | 331.8182 | 100 | 100 | 770.673 | 100
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 | 2009-06-18 08:00 | 9d | 1276069.0781 | 5671418.125 | 40d | -1261818.5 | 0 | 14250.5781 | 5671418.125 | 18.37% | Started | 572928.9795 | 3119279.9688 | 100 | 40.9091 | 18.3673 | 100 | 0.45685 | 18.3673

## TP35
| TP Status Date | 2009-07-31 17:00 |  | TP Name | 31/07, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 827d | [5 empty] | 62487847.4795 |  | 96.5% |  | 60202101.643 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 100% | Finished | 4055063.9062 | 4055063.9062 | 100 | 580.9524 | 100 | 100 | 131.1641 | 100
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 73d | 662421.8896 | 0 | 0 | 876103.4375 | 0 | 1538525.3271 | 0 | 100% | Finished | 199633.9941 | 199633.9941 | 100 | 331.8182 | 100 | 100 | 770.673 | 100
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 | 2009-06-18 08:00 | 29d | 4111778.1406 | 9588241.2676 | 67d 5h | -4033929 | 0 | 77849.1406 | 9588241.2676 | 30% | Started | 935784.0278 | 3119279.9688 | 100 | 131.8182 | 30 | 100 | 2.4957 | 30

## TP36
| TP Status Date | 2009-08-31 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Compressor Station Zelzate | 2006-06-01 08:00 | 2008-05-30 17:00 | 522d |  |  | 0 |  |  | 62385597.584 |  | 844d | [5 empty] | 65526930.042 |  | 100% |  | 62385597.584 | 62385597.584
24 | JUNE 06 | 2006-06-01 08:00 | 2006-06-30 17:00 | 22d |  | 0 | 0 | 35446.3633 | 6238559.9375 | 6238559.9375 | 2006-06-01 08:00 | 22d | 6238559.9375 | 0 | 0 | 0 | 0 | 6238559.9375 | 0 | 100% | Finished | 6238559.9375 | 6238559.9375 | 100 | 100 | 100 | 100 | 100 | 100
1 | July | 2006-07-03 08:00 | 2006-07-31 17:00 | 21d |  | 0 | 0 | 12217.1787 | 2052486.0234 | 2052486.0234 | 2006-07-03 08:00 | 60d | 5864245.7812 | 0 | 0 | -3811760 | 0 | 2052485.7812 | 0 | 100% | Finished | 2052486.0234 | 2052486.0234 | 100 | 285.7143 | 100 | 100 | 100 | 100
2 | August | 2006-08-01 08:00 | 2006-08-31 17:00 | 23d |  | 0 | 0 | 4780.6357 | 879636.9766 | 879636.9766 | 2006-09-22 08:00 | 31d | 1185597.6641 | 0 | 0 | -305568.5 | 0 | 880029.1641 | 0 | 100% | Finished | 879636.9766 | 879636.9766 | 100 | 134.7826 | 100 | 100 | 100.0446 | 100
3 | September | 2006-09-01 08:00 | 2006-09-29 17:00 | 21d |  | 0 | 0 | 15262.1904 | 2564047.9922 | 2564047.9922 | 2006-11-06 08:00 | 54d | 6593266.2656 | 0 | 0 | -4029219 | 0 | 2564047.2656 | 0 | 100% | Finished | 2564047.9922 | 2564047.9922 | 100 | 257.1429 | 100 | 100 | 100 | 100
4 | October | 2006-10-02 08:00 | 2006-10-31 17:00 | 22d |  | 0 | 0 | 14887.4717 | 2620195.0156 | 2620195.0156 | 2007-01-22 08:00 | 47d | 5597689.3516 | 0 | 0 | -2977494.5 | 0 | 2620194.8516 | 0 | 100% | Finished | 2620195.0156 | 2620195.0156 | 100 | 213.6364 | 100 | 100 | 100 | 100
5 | November | 2006-11-01 08:00 | 2006-11-30 17:00 | 22d |  | 0 | 0 | 6344.8975 | 1116701.9531 | 1116701.9531 | 2007-03-08 08:00 | 20d | 1015183.5938 | 0 | 0 | 101518.3672 | 0 | 1116701.9609 | 0 | 100% | Finished | 1116701.9531 | 1116701.9531 | 100 | 90.9091 | 100 | 100 | 100 | 100
6 | December | 2006-12-01 08:00 | 2006-12-29 17:00 | 21d |  | 0 | 0 | 8243.8096 | 1384960.0078 | 1384960.0078 | 2007-04-05 08:00 | 19d | 1253059.0547 | 0 | 0 | 131901 | 0 | 1384960.0547 | 0 | 100% | Finished | 1384960.0078 | 1384960.0078 | 100 | 90.4762 | 100 | 100 | 100 | 100
7 | January 07 | 2007-01-01 08:00 | 2007-01-31 17:00 | 23d |  | 0 | 0 | 7560.8643 | 1391199.0234 | 1391199.0234 | 2007-05-02 08:00 | 20d | 1209738.2812 | 0 | 0 | 181460.75 | 0 | 1391199.0312 | 0 | 100% | Finished | 1391199.0234 | 1391199.0234 | 100 | 86.9565 | 100 | 100 | 100 | 100
8 | February | 2007-02-01 08:00 | 2007-02-28 17:00 | 20d |  | 0 | 0 | 27722.5996 | 4435615.9375 | 4435615.9375 | 2007-05-30 08:00 | 35d | 7762327.8906 | 0 | 0 | -3326712 | 0 | 4435615.8906 | 0 | 100% | Finished | 4435615.9375 | 4435615.9375 | 100 | 175 | 100 | 100 | 100 | 100
9 | March | 2007-03-01 08:00 | 2007-03-30 17:00 | 22d |  | 0 | 0 | 20842.4609 | 3668273.125 | 3668273.125 | 2007-07-17 08:00 | 22d | 3668273.125 | 0 | 0 | 89600 | 0 | 3757873.125 | 0 | 100% | Finished | 3668273.125 | 3668273.125 | 100 | 100 | 100 | 100 | 102.4426 | 100
10 | April | 2007-04-02 08:00 | 2007-04-30 17:00 | 21d |  | 0 | 0 | 15596.3984 | 2620194.9375 | 2620194.9375 | 2007-08-16 08:00 | 5d | 623855.9375 | 0 | 0 | 1996339 | 0 | 2620194.9375 | 0 | 100% | Finished | 2620194.9375 | 2620194.9375 | 100 | 23.8095 | 100 | 100 | 100 | 100
11 | May | 2007-05-01 08:00 | 2007-05-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-08-23 08:00 | 5d | 570963.9062 | 0 | 0 | 2055470.125 | 0 | 2626434.0312 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 21.7391 | 100 | 100 | 100 | 100
12 | June | 2007-06-01 08:00 | 2007-06-29 17:00 | 21d |  | 0 | 0 | 42778.6953 | 7186820.8125 | 7186820.8125 | 2007-08-30 08:00 | 21d | 7186820.8125 | 0 | 0 | 0 | 0 | 7186820.8125 | 0 | 100% | Finished | 7186820.8125 | 7186820.8125 | 100 | 100 | 100 | 100 | 100 | 100
13 | July | 2007-07-02 08:00 | 2007-07-31 17:00 | 22d |  | 0 | 0 | 15135.5967 | 2663865.0156 | 2663865.0156 | 2007-09-28 08:00 | 18d | 2179525.9219 | 0 | 0 | 1460414 | 0 | 3639939.9219 | 0 | 100% | Finished | 2663865.0156 | 2663865.0156 | 100 | 81.8182 | 100 | 100 | 136.6413 | 100
14 | August | 2007-08-01 08:00 | 2007-08-31 17:00 | 23d |  | 0 | 0 | 10985.2881 | 2021293.0078 | 2021293.0078 | 2007-10-22 08:00 | 23d | 2021293.0078 | 0 | 0 | 913900 | 0 | 2935193.0078 | 0 | 100% | Finished | 2021293.0078 | 2021293.0078 | 100 | 100 | 100 | 100 | 145.2136 | 100
15 | September | 2007-09-03 08:00 | 2007-09-28 17:00 | 20d |  | 0 | 0 | 17117.0508 | 2738728.125 | 2738728.125 | 2007-11-22 08:00 | 6d | 821618.4375 | 0 | 0 | 1518117.625 | 0 | 2339736.0625 | 0 | 100% | Finished | 2738728.125 | 2738728.125 | 100 | 30 | 100 | 100 | 85.4315 | 100
16 | October | 2007-10-01 08:00 | 2007-10-31 17:00 | 23d |  | 0 | 0 | 14274.0977 | 2626433.9688 | 2626433.9688 | 2007-11-30 08:00 | 33d | 3768361.7812 | 0 | 0 | -1028360.1875 | 0 | 2740001.5938 | 0 | 100% | Finished | 2626433.9688 | 2626433.9688 | 100 | 143.4783 | 100 | 100 | 104.324 | 100
17 | November | 2007-11-01 08:00 | 2007-11-30 17:00 | 22d |  | 0 | 0 | 14745.6875 | 2595241 | 2595241 | 2008-01-15 08:00 | 30d | 3538965 | 0 | 0 | -1980279.875 | 0 | 1558685.125 | 0 | 100% | Finished | 2595241 | 2595241 | 100 | 136.3636 | 100 | 100 | 60.0594 | 100
18 | December | 2007-12-03 08:00 | 2007-12-31 17:00 | 21d |  | 0 | 0 | 8875.0947 | 1491015.9141 | 1491015.9141 | 2008-02-22 08:00 | 21d | 1491015.9141 | 0 | 0 | 120000 | 0 | 1611015.9141 | 0 | 100% | Finished | 1491015.9141 | 1491015.9141 | 100 | 100 | 100 | 100 | 108.0482 | 100
19 | January 08 | 2008-01-01 08:00 | 2008-01-31 17:00 | 23d |  | 0 | 0 | 7052.2827 | 1297620.0195 | 1297620.0195 | 2008-03-24 08:00 | 5d | 282091.3086 | 0 | 0 | 1095526.75 | 0 | 1377618.0586 | 0 | 100% | Finished | 1297620.0195 | 1297620.0195 | 100 | 21.7391 | 100 | 100 | 106.165 | 100
20 | February | 2008-02-01 08:00 | 2008-02-28 17:00 | 20d |  | 0 | 0 | 4951.856 | 792296.9531 | 792296.9531 | 2008-03-28 08:00 | 12d | 475378.1719 | 0 | 0 | 0 | 0 | 475378.1719 | 0 | 100% | Finished | 792296.9531 | 792296.9531 | 100 | 60 | 100 | 100 | 60 | 100
21 | March | 2008-03-03 08:00 | 2008-03-31 17:00 | 21d |  | 0 | 0 | 24137.2852 | 4055063.9062 | 4055063.9062 | 2008-04-15 08:00 | 122d | 23557990.3125 | 0 | 0 | -18239202 | 0 | 5318788.3125 | 0 | 100% | Finished | 4055063.9062 | 4055063.9062 | 100 | 580.9524 | 100 | 100 | 131.1641 | 100
22 | April | 2008-04-01 08:00 | 2008-04-30 17:00 | 22d |  | 0 | 0 | 1134.2841 | 199633.9941 | 199633.9941 | 2008-10-08 08:00 | 73d | 662421.8896 | 0 | 0 | 876103.4375 | 0 | 1538525.3271 | 0 | 100% | Finished | 199633.9941 | 199633.9941 | 100 | 331.8182 | 100 | 100 | 770.673 | 100
23 | May | 2008-05-01 08:00 | 2008-05-30 17:00 | 22d |  | 0 | 0 | 17723.1816 | 3119279.9688 | 3119279.9688 | 2009-06-18 08:00 | 49d | 6947487.2031 | 0 | 0 | -3830555.5 | 0 | 3116931.7031 | 0 | 100% | Finished | 3119279.9688 | 3119279.9688 | 100 | 222.7273 | 100 | 100 | 99.9247 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/06, 2006 | 2006-06-01 08:00 | 2006-06-30 17:00 | 6238559.9375 | 6238559.9375 | 6238559.9375 | 2006-06-30 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-05-30 17:00 | 62385597.584 | 62385597.584 | 62385597.584 | 62385597.584 | 62385597.584 | 62385597.584 | 62385597.584 | 62385597.584 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
31/07, 2006 | 2006-06-30 17:00 | 2006-07-31 17:00 | 8291045.9609 | 6423283.6869 | 6424700.9609 | 2006-07-04 16:00 | -1867762.274 | 77.47% | -1417.274 | 99.98% | -19d 1h | 55.52% | 100% | 2008-06-23 14:00 | 2008-12-30 15:00 | 2008-12-30 16:00 | 2008-06-13 14:00 | 2008-12-30 15:00 | 2008-12-30 16:00 | 2008-06-27 09:00 | 2010-01-07 09:00 | 2010-01-07 11:00 | 62387014.858 | 62399362.7373 | 78659735.1294 | 107215465.2572 | 78675673.5248 | 107237704.3697 | 65038184.9887 | 67863009.2143 | 0.55523 | 0.99978 | 0.77473 | 1 | -19.125 | 0.99978 | 1 | 0.55523 | 1
31/08, 2006 | 2006-07-31 17:00 | 2006-08-31 17:00 | 9170682.9375 | 8147371.954 | 8149090.3438 | 2006-07-28 12:00 | -1023310.9835 | 88.84% | -1718.3898 | 99.98% | -24d 4h | 62.88% | 100% | 2008-06-12 12:00 | 2008-09-01 14:00 | 2008-09-01 14:00 | 2008-06-11 11:00 | 2008-09-01 14:00 | 2008-09-01 14:00 | 2008-07-04 12:00 | 2009-08-06 09:00 | 2009-08-06 11:00 | 62387315.9738 | 62398755.5414 | 69199644.2101 | 94407473.2734 | 69212520.5889 | 94425666.3207 | 63634954.598 | 66747704.4422 | 0.62879 | 0.99979 | 0.88841 | 1 | -24.5 | 0.99979 | 1 | 0.62879 | 1
30/09, 2006 | 2006-08-31 17:00 | 2006-09-30 17:00 | 11734730.9297 | 8335027.8104 | 8335230.9219 | 2006-08-02 09:00 | -3399703.1193 | 71.03% | -203.1115 | 100% | -42d 7h | 50.72% | 100% | 2008-07-10 12:00 | 2009-03-25 16:00 | 2009-03-25 16:00 | 2008-07-07 10:00 | 2009-03-25 16:00 | 2009-03-25 16:00 | 2008-07-30 16:00 | 2010-05-12 10:00 | 2010-05-12 10:00 | 62385800.6954 | 62387117.8224 | 84432024.7557 | 114905192.855 | 84433879.1143 | 114907789.7966 | 65711445.2795 | 68296993.9501 | 0.50718 | 0.99998 | 0.71029 | 1 | -42.875 | 0.99998 | 1 | 0.50718 | 1
31/10, 2006 | 2006-09-30 17:00 | 2006-10-31 17:00 | 14354925.9453 | 9073922.8575 | 9077284.7109 | 2006-08-29 11:00 | -5281003.0878 | 63.21% | -3361.8534 | 99.96% | -45d 5h | 58.14% | 100% | 2008-08-01 10:00 | 2009-07-30 15:00 | 2009-07-31 09:00 | 2008-07-28 09:00 | 2009-07-30 15:00 | 2009-07-31 09:00 | 2008-08-04 14:00 | 2009-11-09 15:00 | 2009-11-10 09:00 | 62388959.4374 | 62408711.2074 | 93416236.5334 | 100769159.1912 | 93447483.79 | 100803130.6773 | 66641446.2823 | 67278558.0295 | 0.58142 | 0.99963 | 0.63211 | 1 | -45.625 | 0.99963 | 1 | 0.58142 | 1
30/11, 2006 | 2006-10-31 17:00 | 2006-11-30 17:00 | 15471627.8984 | 10837314.0713 | 10827394.4531 | 2006-09-20 14:00 | -4634313.8271 | 70.05% | 9919.6182 | 100.1% | -51d 3h | 60.78% | 100% | 2008-07-24 15:00 | 2009-04-09 10:00 | 2009-04-08 12:00 | 2008-07-25 10:00 | 2009-04-09 10:00 | 2009-04-08 14:00 | 2008-08-12 11:00 | 2009-09-15 15:00 | 2009-09-15 09:00 | 62375677.9658 | 62328494.7536 | 84419047.8891 | 95635245.507 | 84351687.9236 | 95557619.1233 | 65617867.3852 | 66718542.3985 | 0.60782 | 1.0009 | 0.70046 | 1 | -51.375 | 1.0009 | 1 | 0.60782 | 1
31/12, 2006 | 2006-11-30 17:00 | 2006-12-31 17:00 | 16856587.9062 | 11119359.3871 | 11127791.2969 | 2006-09-22 16:00 | -5737228.5191 | 65.96% | -8431.9098 | 99.92% | -70d 1h | 53.87% | 100% | 2008-08-06 17:00 | 2009-06-12 11:00 | 2009-06-12 16:00 | 2008-08-12 15:00 | 2009-06-12 11:00 | 2009-06-12 16:00 | 2008-09-08 09:00 | 2010-02-17 09:00 | 2010-02-17 15:00 | 62394029.4937 | 62432905.1411 | 88845744.3464 | 106302975.4914 | 88904678.566 | 106375147.6856 | 66174484.5321 | 67642924.7518 | 0.53865 | 0.99924 | 0.65964 | 1 | -70.125 | 0.99924 | 1 | 0.53865 | 1
31/01, 2007 | 2006-12-31 17:00 | 2007-01-31 17:00 | 18247786.9297 | 12022952.3798 | 12013010.4141 | 2006-10-04 11:00 | -6224834.5498 | 65.89% | 9941.9658 | 100.1% | -85d 5h | 51.07% | 100% | 2008-08-13 09:00 | 2009-06-15 10:00 | 2009-06-12 14:00 | 2008-08-22 15:00 | 2009-06-15 10:00 | 2009-06-12 15:00 | 2008-09-29 14:00 | 2010-05-03 09:00 | 2010-04-30 11:00 | 62375655.6182 | 62334009.9658 | 88450709.73 | 110625182.8417 | 88387502.211 | 110543638.907 | 66024890.4256 | 67797646.8712 | 0.51071 | 1.0008 | 0.65887 | 1 | -85.625 | 1.0008 | 1 | 0.51071 | 1
28/02, 2007 | 2007-01-31 17:00 | 2007-02-28 17:00 | 22683402.8672 | 13411655.7022 | 13410441.6328 | 2006-10-19 17:00 | -9271747.165 | 59.13% | 1214.0694 | 100% | -94d | 51.79% | 100% | 2008-09-17 14:00 | 2009-10-19 16:00 | 2009-10-19 15:00 | 2008-09-19 15:00 | 2009-10-19 16:00 | 2009-10-19 15:00 | 2008-10-09 17:00 | 2010-04-12 16:00 | 2010-04-12 15:00 | 62384383.5146 | 62379950.2242 | 96241053.9275 | 107964091.8006 | 96233555.8144 | 107955532.4776 | 66740183.3946 | 67605409.1403 | 0.51795 | 1.0001 | 0.59125 | 1 | -94 | 1.0001 | 1 | 0.51795 | 1
31/03, 2007 | 2007-02-28 17:00 | 2007-03-31 17:00 | 26351675.9922 | 15248287.5211 | 15251763.3047 | 2006-11-24 12:00 | -11103388.4711 | 57.86% | -3475.7836 | 99.98% | -90d 4h | 58.29% | 100% | 2008-10-08 16:00 | 2009-11-16 09:00 | 2009-11-16 10:00 | 2008-10-07 11:00 | 2009-11-16 09:00 | 2009-11-16 10:00 | 2008-10-06 12:00 | 2009-11-05 12:00 | 2009-11-05 14:00 | 62389073.3675 | 62399818.1208 | 96713181.1983 | 96111812.9777 | 96731749.9888 | 96130244.6889 | 66737178.8024 | 66688823.4156 | 0.58295 | 0.99977 | 0.57865 | 1 | -90.5 | 0.99977 | 1 | 0.58295 | 1
30/04, 2007 | 2007-03-31 17:00 | 2007-04-30 17:00 | 28971870.9297 | 16718091.8724 | 16725411.6719 | 2006-12-27 16:00 | -12253779.0572 | 57.7% | -7319.7994 | 99.96% | -88d 1h | 62.97% | 100% | 2008-10-22 12:00 | 2009-11-18 14:00 | 2009-11-18 17:00 | 2008-10-20 14:00 | 2009-11-18 14:00 | 2009-11-18 16:00 | 2008-10-02 09:00 | 2009-08-04 16:00 | 2009-08-05 10:00 | 62392917.3834 | 62412912.3078 | 95865608.4868 | 89244953.6859 | 95900258.9943 | 89276705.4256 | 66632035.2933 | 66063937.4775 | 0.62973 | 0.99956 | 0.57705 | 1 | -88.125 | 0.99956 | 1 | 0.62973 | 1
31/05, 2007 | 2007-04-30 17:00 | 2007-05-31 17:00 | 31598304.8984 | 18957485.4638 | 18964006.7344 | 2007-02-06 09:00 | -12640819.4346 | 60% | -6521.2706 | 99.97% | -82d 7h | 68.25% | 100% | 2008-10-27 15:00 | 2009-10-01 09:00 | 2009-10-01 11:00 | 2008-10-24 11:00 | 2009-10-01 09:00 | 2009-10-01 10:00 | 2008-09-24 16:00 | 2009-05-06 16:00 | 2009-05-06 17:00 | 62392118.8545 | 62407057.8858 | 91349911.0018 | 82597619.441 | 91374811.3541 | 82619509.0531 | 66183082.479 | 65350701.5925 | 0.68247 | 0.99966 | 0.59995 | 1 | -82.875 | 0.99966 | 1 | 0.68247 | 1
30/06, 2007 | 2007-05-31 17:00 | 2007-06-30 17:00 | 38785125.7109 | 20820444.0994 | 20807434.9219 | 2007-02-16 12:00 | -17964681.6115 | 53.68% | 13009.1775 | 100.1% | -95d 4h | 66.13% | 100% | 2008-12-29 11:00 | 2010-02-22 11:00 | 2010-02-19 15:00 | 2008-12-01 14:00 | 2010-02-22 11:00 | 2010-02-19 17:00 | 2008-10-13 12:00 | 2009-06-10 10:00 | 2009-06-09 17:00 | 62372588.4064 | 62346617.3725 | 98236604.7992 | 83656621.424 | 98188224.9561 | 83617351.5496 | 66590932.9764 | 65368439.0759 | 0.66135 | 1.0006 | 0.53682 | 1 | -95.5 | 1.0006 | 1 | 0.66135 | 1
31/07, 2007 | 2007-06-30 17:00 | 2007-07-31 17:00 | 41448990.7266 | 24847683.9147 | 24922950.75 | 2007-03-19 16:00 | -16601306.8118 | 59.95% | -75266.8353 | 99.7% | -96d 1h | 68.38% | 100% | 2008-12-11 16:00 | 2009-10-01 15:00 | 2009-10-06 11:00 | 2008-11-18 15:00 | 2009-10-01 15:00 | 2009-10-05 12:00 | 2008-10-14 09:00 | 2009-05-05 11:00 | 2009-05-06 15:00 | 62460864.4193 | 62574571.5951 | 87540804.4264 | 79819045.7852 | 87730481.9712 | 79985333.1284 | 65837133.1279 | 65098644.4364 | 0.6838 | 0.99698 | 0.59948 | 1 | -96.125 | 0.99698 | 1 | 0.6838 | 1
31/08, 2007 | 2007-07-31 17:00 | 2007-08-31 17:00 | 43470283.7344 | 32820064.4494 | 32887206.125 | 2007-06-06 12:00 | -10650219.285 | 75.5% | -67141.6756 | 99.8% | -62d 4h | 80.89% | 100% | 2008-10-03 09:00 | 2009-01-23 11:00 | 2009-01-26 15:00 | 2008-09-22 09:00 | 2009-01-23 11:00 | 2009-01-26 09:00 | 2008-08-27 12:00 | 2008-11-20 11:00 | 2008-11-20 17:00 | 62452739.2596 | 62513222.9749 | 72046852.3865 | 69438923.8377 | 72126963.2671 | 69513699.5462 | 64029579.0764 | 63680131.6979 | 0.80887 | 0.99796 | 0.755 | 1 | -62.5 | 0.99796 | 1 | 0.80887 | 1
30/09, 2007 | 2007-08-31 17:00 | 2007-09-30 17:00 | 46209011.8594 | 38944957.6083 | 40014764.4766 | 2007-07-03 10:00 | -7264054.2511 | 84.28% | -1069806.8683 | 97.33% | -63d 6h | 81.63% | 100% | 2008-08-25 15:00 | 2008-10-15 11:00 | 2008-11-07 11:00 | 2008-08-15 12:00 | 2008-10-15 11:00 | 2008-10-24 16:00 | 2008-08-28 15:00 | 2008-11-12 12:00 | 2008-11-24 12:00 | 63455404.4522 | 64099312.141 | 67827577.1524 | 68731100.122 | 68591587.1771 | 69519929.6648 | 64762799.3887 | 64902152.0583 | 0.81628 | 0.97326 | 0.8428 | 1 | -63.75 | 0.97326 | 1 | 0.81628 | 1
31/10, 2007 | 2007-09-30 17:00 | 2007-10-31 17:00 | 48835445.8281 | 41853249.3341 | 43004373.2188 | 2007-08-07 12:00 | -6982196.494 | 85.7% | -1151123.8846 | 97.32% | -61d 4h | 83.38% | 100% | 2008-08-21 11:00 | 2008-10-01 09:00 | 2008-10-23 16:00 | 2008-08-13 16:00 | 2008-10-01 09:00 | 2008-10-09 14:00 | 2008-08-26 12:00 | 2008-10-23 17:00 | 2008-11-04 09:00 | 63536721.4686 | 64101439.3066 | 66962044.2869 | 67629880.0338 | 67620971.5583 | 68307175.3338 | 64617573.1767 | 64723849.938 | 0.83378 | 0.97323 | 0.85703 | 1 | -61.5 | 0.97323 | 1 | 0.83378 | 1
30/11, 2007 | 2007-10-31 17:00 | 2007-11-30 17:00 | 51430686.8281 | 46340333.5598 | 47926924.2773 | 2007-10-02 09:00 | -5090353.2684 | 90.1% | -1586590.7176 | 96.69% | -43d 7h | 88.81% | 100% | 2008-07-30 14:00 | 2008-08-20 11:00 | 2008-09-17 09:00 | 2008-07-24 15:00 | 2008-08-20 11:00 | 2008-08-28 15:00 | 2008-07-31 16:00 | 2008-09-01 15:00 | 2008-09-10 12:00 | 63972188.3016 | 64521542.7193 | 65734714.7206 | 65994410.087 | 66344414.1519 | 66613000.9143 | 64750770.7025 | 64796586.8035 | 0.88807 | 0.9669 | 0.90102 | 1 | -43.875 | 0.9669 | 1 | 0.88807 | 1
31/12, 2007 | 2007-11-30 17:00 | 2007-12-31 17:00 | 52921702.7422 | 48039556.723 | 49388059.6172 | 2007-10-22 17:00 | -4882146.0192 | 90.77% | -1348502.8942 | 97.27% | -50d | 87.89% | 100% | 2008-07-28 16:00 | 2008-08-13 17:00 | 2008-09-05 10:00 | 2008-07-24 09:00 | 2008-08-13 17:00 | 2008-08-20 14:00 | 2008-08-08 17:00 | 2008-09-09 16:00 | 2008-09-16 17:00 | 63734100.4782 | 64136803.5617 | 65192054.5281 | 65710139.1643 | 65635683.3693 | 66168310.9921 | 64336427.5145 | 64426728.2956 | 0.87893 | 0.9727 | 0.90775 | 1 | -50 | 0.9727 | 1 | 0.87893 | 1
31/01, 2008 | 2007-12-31 17:00 | 2008-01-31 17:00 | 54219322.7617 | 49638734.7385 | 50843984.9297 | 2007-11-09 15:00 | -4580588.0232 | 91.55% | -1205250.1911 | 97.63% | -59d 2h | 86.41% | 100% | 2008-07-24 11:00 | 2008-08-07 09:00 | 2008-08-26 17:00 | 2008-07-22 16:00 | 2008-08-07 09:00 | 2008-08-12 11:00 | 2008-08-22 10:00 | 2008-09-24 09:00 | 2008-09-30 09:00 | 63590847.7751 | 63900347.1804 | 64767109.1684 | 65595497.0746 | 65105168.7148 | 65953670.2418 | 64064957.3082 | 64207476.6649 | 0.86411 | 0.9763 | 0.91552 | 1 | -59.25 | 0.9763 | 1 | 0.86411 | 1
29/02, 2008 | 2008-01-31 17:00 | 2008-02-29 17:00 | 55011619.7148 | 51856691.394 | 52514677.1016 | 2007-12-10 17:00 | -3154928.3208 | 94.26% | -657985.7075 | 98.75% | -59d | 87.09% | 100% | 2008-07-08 11:00 | 2008-07-15 15:00 | 2008-07-24 15:00 | 2008-07-08 10:00 | 2008-07-15 15:00 | 2008-07-16 17:00 | 2008-08-21 17:00 | 2008-09-17 11:00 | 2008-09-19 10:00 | 63043583.2915 | 63177179.7398 | 63684155.2878 | 64604401.0433 | 63825879.6595 | 64757801.9902 | 63274859.3123 | 63435014.2087 | 0.8709 | 0.98747 | 0.94265 | 1 | -59 | 0.98747 | 1 | 0.8709 | 1
31/03, 2008 | 2008-02-29 17:00 | 2008-03-31 17:00 | 59066683.6211 | 54351372.2578 | 55156536.2227 | 2008-02-06 10:00 | -4715311.3633 | 92.02% | -805163.9648 | 98.54% | -38d 6h | 91.89% | 100% | 2008-07-25 12:00 | 2008-08-04 10:00 | 2008-08-14 15:00 | 2008-07-24 09:00 | 2008-08-04 10:00 | 2008-08-05 14:00 | 2008-07-24 15:00 | 2008-08-04 17:00 | 2008-08-06 11:00 | 63190761.5488 | 63309780.9672 | 63887779.3499 | 63899529.2924 | 64017124.4251 | 64029048.4319 | 63419176.4477 | 63421278.6655 | 0.91893 | 0.9854 | 0.92017 | 1 | -38.75 | 0.9854 | 1 | 0.91893 | 1
30/04, 2008 | 2008-03-31 17:00 | 2008-04-30 17:00 | 59266317.6152 | 56025385.6914 | 56605187.9492 | 2008-03-10 10:00 | -3240931.9238 | 94.53% | -579802.2578 | 98.98% | -37d 6h | 92.45% | 100% | 2008-07-09 09:00 | 2008-07-14 10:00 | 2008-07-21 16:00 | 2008-07-09 11:00 | 2008-07-14 10:00 | 2008-07-14 15:00 | 2008-07-23 15:00 | 2008-07-30 14:00 | 2008-07-31 10:00 | 62965399.8418 | 63031221.1685 | 63333322.5881 | 63484811.4133 | 63402951.518 | 63556008.0891 | 63089451.4302 | 63117090.2682 | 0.9245 | 0.98976 | 0.94532 | 1 | -37.75 | 0.98976 | 1 | 0.9245 | 1
31/05, 2008 | 2008-04-30 17:00 | 2008-05-31 17:00 | 62385597.584 | 56174957.6633 | 57829313.543 | 2008-03-10 17:00 | -6210639.9207 | 90.04% | -1654355.8797 | 97.14% | -59d | 88.7% | 100% | 2008-08-12 17:00 | 2008-08-20 15:00 | 2008-09-12 15:00 | 2008-08-12 17:00 | 2008-08-20 15:00 | 2008-08-22 11:00 | 2008-08-21 17:00 | 2008-09-02 12:00 | 2008-09-04 12:00 | 64039953.4637 | 64222857.1826 | 64726594.804 | 64831374.1015 | 64929720.1517 | 65037585.2058 | 64317631.0362 | 64335949.552 | 0.88697 | 0.97139 | 0.90045 | 1 | -59 | 0.97139 | 1 | 0.88697 | 1
30/06, 2008 | 2008-05-31 17:00 | 2008-06-30 17:00 | 62385597.584 | 56839722.2916 | 58991373.668 | 2008-03-14 11:00 | -5545875.2924 | 91.11% | -2151651.3764 | 96.35% | -76d 5h | 85.89% | 100% | 2008-08-05 11:00 | 2008-08-11 16:00 | 2008-09-10 14:00 | 2008-09-05 10:00 | 2008-09-11 17:00 | 2008-09-15 17:00 | 2008-09-16 14:00 | 2008-09-29 15:00 | 2008-10-02 10:00 | 64537248.9604 | 64747186.4781 | 65078362.3142 | 65448431.3657 | 65308783.5227 | 65692861.4319 | 64810506.9953 | 64874979.9411 | 0.85889 | 0.96353 | 0.9111 | 1 | -76.625 | 0.96353 | 1 | 0.85889 | 1
31/07, 2008 | 2008-06-30 17:00 | 2008-07-31 17:00 | 62385597.584 | 57570963.4189 | 59405161.3555 | 2008-03-20 10:00 | -4814634.165 | 92.28% | -1834197.9365 | 96.91% | -95d 6h | 83.08% | 100% | 2008-07-28 10:00 | 2008-07-31 14:00 | 2008-08-26 14:00 | 2008-10-01 14:00 | 2008-10-07 11:00 | 2008-10-08 16:00 | 2008-10-13 15:00 | 2008-10-28 10:00 | 2008-10-30 10:00 | 64219795.5205 | 64373188.6813 | 64622441.2427 | 65200127.7296 | 64788662.6056 | 65384754.0539 | 64421115.5497 | 64519141.1977 | 0.83083 | 0.96912 | 0.92282 | 1 | -95.75 | 0.96912 | 1 | 0.83083 | 1
31/08, 2008 | 2008-07-31 17:00 | 2008-08-31 17:00 | 62385597.584 | 58235727.9264 | 59681681.9805 | 2008-03-25 14:00 | -4149869.6576 | 93.35% | -1445954.0541 | 97.58% | -113d 3h | 80.69% | 100% | 2008-07-18 15:00 | 2008-07-23 10:00 | 2008-08-12 09:00 | 2008-10-23 17:00 | 2008-10-28 16:00 | 2008-10-29 16:00 | 2008-11-06 11:00 | 2008-11-21 17:00 | 2008-11-25 12:00 | 63831551.6381 | 63934590.1175 | 64127270.7574 | 64824935.5862 | 64237651.7442 | 64952639.1226 | 63971778.3758 | 64087114.4589 | 0.80686 | 0.97577 | 0.93348 | 1 | -113.375 | 0.97577 | 1 | 0.80686 | 1
30/09, 2008 | 2008-08-31 17:00 | 2008-09-30 17:00 | 62385597.584 | 58900492.4338 | 60620647.6055 | 2008-03-31 09:00 | -3485105.1502 | 94.41% | -1720155.1717 | 97.16% | -131d 7h | 78.35% | 100% | 2008-07-11 09:00 | 2008-07-14 16:00 | 2008-08-05 17:00 | 2008-11-17 17:00 | 2008-11-19 17:00 | 2008-11-21 09:00 | 2008-12-02 16:00 | 2008-12-19 10:00 | 2008-12-22 17:00 | 64105752.7556 | 64207533.257 | 64311964.2389 | 65069018.6538 | 64419767.0285 | 65198930.7844 | 64227944.0506 | 64352060.6731 | 0.78346 | 0.97162 | 0.94414 | 1 | -131.875 | 0.97162 | 1 | 0.78346 | 1
31/10, 2008 | 2008-09-30 17:00 | 2008-10-31 17:00 | 62385597.584 | 59150251.3378 | 61034809.916 | 2008-04-14 09:00 | -3235346.2462 | 94.81% | -1884558.5782 | 96.91% | -144d 7h | 77.08% | 100% | 2008-07-09 09:00 | 2008-07-10 12:00 | 2008-08-05 09:00 | 2008-12-17 15:00 | 2008-12-19 14:00 | 2008-12-22 14:00 | 2008-12-19 16:00 | 2009-01-05 10:00 | 2009-01-06 15:00 | 64270156.1622 | 64373236.0205 | 64447120.1665 | 65232374.8688 | 64555838.1924 | 65366111.5285 | 64387755.7753 | 64515727.7644 | 0.77077 | 0.96912 | 0.94814 | 1 | -144.875 | 0.96912 | 1 | 0.77077 | 1
30/11, 2008 | 2008-10-31 17:00 | 2008-11-30 17:00 | 62385597.584 | 59243104.3609 | 61446403.6777 | 2008-04-28 11:00 | -3142493.2231 | 94.96% | -2203299.3168 | 96.41% | -154d 5h | 76.28% | 100% | 2008-07-08 10:00 | 2008-07-09 15:00 | 2008-08-07 09:00 | 2009-01-14 16:00 | 2009-01-16 14:00 | 2009-01-19 16:00 | 2009-01-02 14:00 | 2009-01-14 10:00 | 2009-01-15 12:00 | 64588896.9008 | 64705768.784 | 64755587.4172 | 65565841.8912 | 64878658.6564 | 65719047.1545 | 64715612.1478 | 64847800.2741 | 0.76285 | 0.96414 | 0.94963 | 1 | -154.625 | 0.96414 | 1 | 0.76285 | 1
31/12, 2008 | 2008-11-30 17:00 | 2008-12-31 17:00 | 62385597.584 | 59243104.3609 | 61841559.1025 | 2008-04-28 11:00 | -3142493.2231 | 94.96% | -2598454.7416 | 95.8% | -177d 5h | 73.69% | 100% | 2008-07-08 10:00 | 2008-07-09 15:00 | 2008-08-12 15:00 | 2009-02-17 17:00 | 2009-02-19 15:00 | 2009-02-23 11:00 | 2009-02-04 14:00 | 2009-02-17 11:00 | 2009-02-18 16:00 | 64984052.3256 | 65121884.8464 | 65150742.842 | 66106314.9217 | 65295886.5557 | 66293370.8686 | 65127616.1098 | 65280653.5128 | 0.73685 | 0.95798 | 0.94963 | 1 | -177.625 | 0.95798 | 1 | 0.73685 | 1
31/01, 2009 | 2008-12-31 17:00 | 2009-01-31 17:00 | 62385597.584 | 59243104.3609 | 62076304.1143 | 2008-04-28 11:00 | -3142493.2231 | 94.96% | -2833199.7533 | 95.44% | -199d 5h | 71.36% | 100% | 2008-07-08 10:00 | 2008-07-09 15:00 | 2008-08-14 17:00 | 2009-03-23 09:00 | 2009-03-24 17:00 | 2009-03-26 15:00 | 2009-03-06 14:00 | 2009-03-20 12:00 | 2009-03-24 09:00 | 65218797.3373 | 65369081.6804 | 65385487.8537 | 66480059.3824 | 65543743.8846 | 66690661.4174 | 65372349.8881 | 65544050.0029 | 0.71359 | 0.95436 | 0.94963 | 1 | -199.625 | 0.95436 | 1 | 0.71359 | 1
28/02, 2009 | 2009-01-31 17:00 | 2009-02-28 17:00 | 62385597.584 | 59266317.6152 | 62409998.3389 | 2008-04-30 17:00 | -3119279.9688 | 95% | -3143680.7236 | 94.96% | -217d | 69.74% | 100% | 2008-07-08 09:00 | 2008-07-09 12:00 | 2008-08-19 14:00 | 2009-04-20 16:00 | 2009-04-22 15:00 | 2009-04-24 15:00 | 2009-03-31 17:00 | 2009-04-14 12:00 | 2009-04-16 10:00 | 65529278.3076 | 65694735.1928 | 65693450.9425 | 66883045.8141 | 65867616.0851 | 67120310.9874 | 65694478.2624 | 65879053.1411 | 0.69735 | 0.94963 | 0.95 | 1 | -217 | 0.94963 | 1 | 0.69735 | 1
30/06, 2009 | 2009-02-28 17:00 | 2009-06-30 17:00 | 62385597.584 | 59839246.5948 | 62424248.917 | 2008-05-06 17:00 | -2546350.9892 | 95.92% | -2585002.3222 | 95.86% | -300d | 62.69% | 100% | 2008-07-01 10:00 | 2008-07-02 10:00 | 2008-08-04 15:00 | 2009-08-14 16:00 | 2009-08-18 10:00 | 2009-08-19 15:00 | 2009-07-24 17:00 | 2009-08-10 15:00 | 2009-08-11 17:00 | 64970599.9062 | 65080600.0081 | 65078955.2704 | 66486285.0188 | 65193636.2278 | 66661761.3718 | 65080270.8975 | 65278118.7894 | 0.62687 | 0.95859 | 0.95918 | 1 | -300 | 0.95859 | 1 | 0.62687 | 1
31/07, 2009 | 2009-06-30 17:00 | 2009-07-31 17:00 | 62385597.584 | 60202101.643 | 62487847.4795 | 2008-05-09 12:00 | -2183495.9409 | 96.5% | -2285745.8364 | 96.34% | -320d 4h | 61.25% | 100% | 2008-06-26 10:00 | 2008-06-26 16:00 | 2008-07-25 12:00 | 2009-09-10 17:00 | 2009-09-11 17:00 | 2009-09-15 09:00 | 2009-08-24 12:00 | 2009-09-07 10:00 | 2009-09-08 10:00 | 64671343.4204 | 64754246.1202 | 64750537.5747 | 66053002.7473 | 64836447.1081 | 66188364.1149 | 64753503.4389 | 64932348.4221 | 0.61245 | 0.96342 | 0.965 | 1 | -320.5 | 0.96342 | 1 | 0.61245 | 1
Actual Schedule | 2009-07-31 17:00 | 2009-08-31 17:00 | 62385597.584 | 62385597.584 | 65526930.042 | 2008-05-30 17:00 | 0 | 100% | -3141332.458 | 95.21% | -326d | 61.56% | 100% | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-07-08 10:00 | 2009-08-31 17:00 | 2009-08-31 17:00 | 2009-08-31 17:00 | 2009-08-31 17:00 | 2009-08-31 17:00 | 2009-08-31 17:00 | 65526930.042 | 65526930.042 | 65526930.042 | 65526930.042 | 65526930.042 | 65526930.042 | 65526930.042 | 65526930.042 | 0.61557 | 0.95206 | 1 | 1 | -326 | 0.95206 | 1 | 0.61557 | 1