## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Gas Pipeline Project |  |  |  | Mon 22/08/16 | Fri 4/11/16 | 58 days
1 | Excavation |  |  |  | Mon 22/08/16 | Fri 23/09/16 | 23,88 days
2 | Asphalt digging |  |  |  | Mon 22/08/16 | Thu 1/09/16 | 9 days | worker[5] | 288 | 0 | 0 | 0
3 | digging canals |  | 2 |  | Wed 31/08/16 | Fri 23/09/16 | 18 days | worker[3];professional worker[3] | 8640 | 360 | 0 | 0
4 | Piping |  |  |  | Fri 23/09/16 | Thu 13/10/16 | 17,01 days |  |  |  | 0 | 0
5 | Laying piplines |  |  |  | Fri 23/09/16 | Tue 4/10/16 | 10,38 days |  |  |  | 0 | 0
6 | Sanding |  | 3FS+1d |  | Fri 23/09/16 | Wed 28/09/16 | 4 days | worker[3] | 768 | 1536 | 0 | 0
7 | Floor level |  | 6 |  | Fri 23/09/16 | Tue 4/10/16 | 5,75 days | worker[3];engineer | 264 | 400 | 0 | 0
8 | Laying the pipes |  | 7 |  | Sun 25/09/16 | Tue 4/10/16 | 5 days | worker[3] | 888 | 0 | 0 | 0
9 | Welding |  |  |  | Wed 28/09/16 | Thu 13/10/16 | 12,01 days |  |  |  | 0 | 0
10 | Cleaning connections |  | 8 |  | Wed 28/09/16 | Fri 7/10/16 | 5 days | professional worker[5] | 2400 | 150 | 0 | 0
11 | Welding connections |  | 8 |  | Wed 28/09/16 | Thu 13/10/16 | 10 days | professional worker[4] | 1920 | 80 | 0 | 0
12 | Tube testing |  |  |  | Thu 29/09/16 | Sat 8/10/16 | 7 days |  |  |  | 0 | 0
13 | Connect the device |  | 11SS+1d |  | Thu 29/09/16 | Mon 3/10/16 | 3 days |  |  | 1000 | 0 | 0
14 | Test |  | 13 |  | Mon 3/10/16 | Sat 8/10/16 | 4 days | engineer | 640 | 160 | 0 | 0
15 | Leveling |  |  |  | Mon 3/10/16 | Fri 4/11/16 | 26 days |  |  |  | 0 | 0
16 | Excavation |  | 14 |  | Sun 9/10/16 | Mon 10/10/16 | 2 days | worker[3] | 120 | 1800 | 0 | 0
17 | Asphalt Work |  |  |  | Mon 3/10/16 | Fri 4/11/16 | 26 days |  |  |  | 0 | 0
18 | Infrastructure |  | 13 |  | Mon 3/10/16 | Mon 17/10/16 | 10 days | engineer[2] | 3200 | 0 | 0 | 0
19 | Asphalt |  | 18 |  | Mon 17/10/16 | Fri 4/11/16 | 14 days | engineer; professional worker[4] | 7616 | 2194 | 0 | 0
20 | Roller |  | 19SS+1d |  | Tue 18/10/16 | Sat 22/10/16 | 3 days |  |  | 400 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availibility | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | worker | Renewable | 700% | 8
2 | professional worker | Renewable | 500% | 12
3 | engineer | Renewable | 30% | 20
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Gas Pipeline Project
1 | Excavation
2 | Asphalt digging |  |  | 1w 2d | 1w 4d | 2w 6h
3 | digging canals |  |  | 2w 4d | 3w 3d | 4w 2d
4 | Piping
5 | Laying piplines
6 | Sanding |  |  | 3d 2h | 4d | 4d 6h
7 | Floor level |  |  | 5h | 6h | 7h
8 | Laying the pipes |  |  | 3d 6h | 4d 5h | 1w 4h
9 | Welding
10 | Cleaning connections |  |  | 4d | 1w | 1w 1d
11 | Welding connections |  |  | 4d | 1w | 1w 1d
12 | Tube testing
13 | Connect the device |  |  | 2d 3h | 3d | 3d 5h
14 | Test |  |  | 3d 2h | 4d | 4d 6h
15 | Leveling
16 | Excavation |  |  | 4h | 5h | 6h
17 | Asphalt Work
18 | Infrastructure |  |  | 1w 3d | 2w | 2w 2d
19 | Asphalt |  |  | 2w 1d | 2w 4d | 3w 2d
20 | Roller |  |  | 2d 3h | 3d | 3d 5h

## Project Control - TP1 (hidden)
| TP Status Date |  |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Gas Pipeline Project | [9 empty] | Mon 22/08/16 | 30,93d | [5 empty] | $18.613,67 |  | 53%
1 | Excavation | [9 empty] | Mon 22/08/16 | 23,88d | [5 empty] | $13.250,00 |  | 100%
2 | Asphalt digging | [9 empty] | Mon 22/08/16 | 9d | [5 empty] | $3.100,00 |  | 100%
3 | digging canals | [9 empty] | Wed 31/08/16 | 18d | [5 empty] | $10.150,00 |  | 100%
4 | Piping | [9 empty] | Fri 23/09/16 | 7,37d | [5 empty] | $5.363,67 |  | 61%
5 | Laying piplines | [9 empty] | Fri 23/09/16 | 5,87d | [5 empty] | $3.288,00 |  | 90%
6 | Sanding | [9 empty] | Fri 23/09/16 | 4d | [5 empty] | $3.000,00 |  | 100%
7 | Floor level | [9 empty] | Fri 23/09/16 | 0d | [5 empty] | $0,00 |  | 0%
8 | Laying the pipes | [9 empty] | Sun 25/09/16 | 4,5d | [5 empty] | $288,00 |  | 96%
9 | Welding | [9 empty] | Wed 28/09/16 | 3,24d | [5 empty] | $1.284,00 |  | 54%
10 | Cleaning connections | [9 empty] | Wed 28/09/16 | 2d | [5 empty] | $960,00 |  | 40%
11 | Welding connections | [9 empty] | Wed 28/09/16 | 3,38d | [5 empty] | $324,00 |  | 67%
12 | Tube testing | [9 empty] | Thu 29/09/16 | 2,04d | [5 empty] | $791,67 |  | 34%
13 | Connect the device | [9 empty] | Thu 29/09/16 | 2,38d | [5 empty] | $791,67 |  | 79%
14 | Test | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%
15 | Leveling | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%
16 | Excavation | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%
17 | Asphalt Work | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%
18 | Infrastructure | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%
19 | Asphalt | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%
20 | Roller | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%

## TP2 (hidden)
| TP Status Date | 2006-07-07 17:00 |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Gas Pipeline Project | [9 empty] | Mon 22/08/16 | 34,88d | [5 empty] | $4.462,00 |  | 59%
1 | Excavation | [9 empty] | Mon 22/08/16 | 25d | [5 empty] | $1.730,00 |  | 100%
2 | Asphalt digging | [9 empty] | Mon 22/08/16 | 9d | [5 empty] | $220,00 |  | 100%
3 | digging canals | [9 empty] | Wed 31/08/16 | 18d | [5 empty] | $1.510,00 |  | 100%
4 | Piping | [9 empty] | Fri 23/09/16 | 18,36d | [5 empty] | $2.232,00 |  | 51%
5 | Laying piplines | [9 empty] | Fri 23/09/16 | 10,38d | [5 empty] | $2.232,00 |  | 100%
6 | Sanding | [9 empty] | Fri 23/09/16 | 4d | [5 empty] | $2.232,00 |  | 100%
7 | Floor level | [9 empty] | Fri 23/09/16 | 5,75d | [5 empty] | $0,00 |  | 100%
8 | Laying the pipes | [9 empty] | Sun 25/09/16 | 5d | [5 empty] | $0,00 |  | 100%
9 | Welding | [9 empty] | Wed 28/09/16 | 5,06d | [5 empty] | $0,00 |  | 16%
10 | Cleaning connections | [9 empty] | Wed 28/09/16 | 5d | [5 empty] | $0,00 |  | 100%
11 | Welding connections | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%
12 | Tube testing | [9 empty] | Thu 29/09/16 | 12d | [5 empty] | $0,00 |  | 100%
13 | Connect the device | [9 empty] | Thu 29/09/16 | 3d | [5 empty] | $0,00 |  | 100%
14 | Test | [9 empty] | Sat 8/10/16 | 4d | [5 empty] | $0,00 |  | 100%
15 | Leveling | [9 empty] | Mon 3/10/16 | 9,2d | [5 empty] | $500,00 |  | 34%
16 | Excavation | [9 empty] | Tue 11/10/16 | 2d | [5 empty] | $500,00 |  | 100%
17 | Asphalt Work | [9 empty] | Mon 3/10/16 | 7,82d | [5 empty] | $0,00 |  | 29%
18 | Infrastructure | [9 empty] | Mon 3/10/16 | 7,5d | [5 empty] | $0,00 |  | 83%
19 | Asphalt | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%
20 | Roller | [9 empty] | NA | 0d | [5 empty] | $0,00 |  | 0%