## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Project | 1 |  |  | 2018-09-03 09:00 | 2019-02-04 09:00 | 110d |  |  | 0 |  |  | 0 | 154
1 | App development | 1.1 |  |  | 2018-09-03 09:00 | 2019-02-04 09:00 | 110d |  |  | 0 |  |  | 0 | 154
2 | Analysis | 1.1.1 |  |  | 2018-09-03 09:00 | 2018-10-16 09:00 | 31d |  |  | 0 |  |  | 0 | 43
3 | Documentation prior the software development | 1.1.1.1 |  | FS4;FS5 | 2018-09-03 09:00 | 2018-09-10 09:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 7
4 | Development of a low fidelity prototype | 1.1.1.2 | 3FS | FS6 | 2018-09-10 09:00 | 2018-09-20 09:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 10
5 | Writing user stories | 1.1.1.3 | 3FS | FS6;FS7 | 2018-09-10 09:00 | 2018-09-17 09:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 7
6 | User stories prototype | 1.1.1.4 | 4FS;5FS | FS9 | 2018-09-24 09:00 | 2018-10-04 09:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 10
7 | Requirement modelling | 1.1.1.5 | 5FS | FS8 | 2018-09-17 09:00 | 2018-09-24 09:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 7
8 | Use case modelling | 1.1.1.6 | 7FS | FS9 | 2018-10-04 09:00 | 2018-10-11 09:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 7
9 | Submit results | 1.1.1.7 | 8FS;6FS | FS11;FS12 | 2018-10-11 09:00 | 2018-10-16 09:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 5
10 | Design | 1.1.2 |  |  | 2018-10-16 09:00 | 2018-11-12 09:00 | 19d |  |  | 0 |  |  | 0 | 27
11 | Software architecture | 1.1.2.1 | 9FS | FS14 | 2018-10-16 09:00 | 2018-10-26 09:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 10
12 | Class diagram | 1.1.2.2 | 9FS | FS13 | 2018-10-16 09:00 | 2018-10-23 09:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 7
13 | Database modelling | 1.1.2.3 | 12FS | FS14 | 2018-10-26 09:00 | 2018-11-07 09:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 12
14 | Submit results | 1.1.2.4 | 13FS;11FS | FS16 | 2018-11-07 09:00 | 2018-11-12 09:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 5
15 | Execution | 1.1.3 |  |  | 2018-11-12 09:00 | 2018-12-28 09:00 | 34d |  |  | 0 |  |  | 0 | 46
16 | GPS verification and activation | 1.1.3.1 | 14FS | FS17 | 2018-11-12 09:00 | 2018-11-15 09:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 3
17 | Locate the mobile in the map | 1.1.3.2 | 16FS | FS18 | 2018-11-15 09:00 | 2018-11-16 09:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 1
18 | Start app | 1.1.3.3 | 17FS | FS19 | 2018-11-16 09:00 | 2018-11-19 09:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 3
19 | Measure | 1.1.3.4 | 18FS | FS20 | 2018-11-19 09:00 | 2018-11-26 09:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 7
20 | Information storing | 1.1.3.5 | 19FS | FS21 | 2018-11-26 09:00 | 2018-12-06 09:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 10
21 | Daily report generating | 1.1.3.6 | 20FS | FS22 | 2018-12-06 09:00 | 2018-12-18 09:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 12
22 | Share the progress in Twitter | 1.1.3.7 | 21FS | FS23 | 2018-12-18 09:00 | 2018-12-25 09:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 7
23 | Submit results | 1.1.3.8 | 22FS | FS25;FS26 | 2018-12-25 09:00 | 2018-12-28 09:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 3
24 | Test | 1.1.4 |  |  | 2018-12-28 09:00 | 2019-02-04 09:00 | 26d |  |  | 0 |  |  | 0 | 38
25 | Application test | 1.1.4.1 | 23FS | FS27 | 2018-12-28 09:00 | 2019-01-16 09:00 | 13d |  | 0 | 0 | 0 | 0 | 0 | 19
26 | App user guide | 1.1.4.2 | 23FS | FS27 | 2019-01-16 09:00 | 2019-01-23 09:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 7
27 | Submit client feedback | 1.1.4.3 | 26FS;25FS |  | 2019-01-23 09:00 | 2019-02-04 09:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 12

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Project | 880h |  |  |  |  | 99 | 100 | 101
1 | App development | 880h |  |  |  |  | 99 | 100 | 101
2 | Analysis | 248h |  |  |  |  | 99 | 100 | 101
3 | Documentation prior the software development | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Development of a low fidelity prototype | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Writing user stories | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | User stories prototype | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Requirement modelling | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Use case modelling | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Submit results | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Design | 152h |  |  |  |  | 99 | 100 | 101
11 | Software architecture | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Class diagram | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Database modelling | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Submit results | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Execution | 272h |  |  |  |  | 99 | 100 | 101
16 | GPS verification and activation | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Locate the mobile in the map | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Start app | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Measure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Information storing | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Daily report generating | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Share the progress in Twitter | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Submit results | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Test | 208h |  |  |  |  | 99 | 100 | 101
25 | Application test | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | App user guide | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Submit client feedback | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))

## SV(t)
S