## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Electric and ecological step sharing project | 1 |  |  | 2019-11-25 08:00 | 2021-06-04 17:00 | 400d |  |  | 0 |  |  | 0
1 | Survey development | 1.1 |  | FS2 | 2019-11-25 08:00 | 2019-11-27 12:00 | 2d 4h | Marketing resource[2.00 #2] | 0 | 0 | 0 | 0 | 0
2 | Survey distribution | 1.2 | 1FS | FS3 | 2019-11-27 13:00 | 2019-12-25 12:00 | 20d | Marketing resource[2.00 #2] | 0 | 0 | 0 | 0 | 0
3 | Surve analysis | 1.3 | 2FS | FS4;FS5;FS6;FS7 | 2019-12-25 13:00 | 2020-01-01 12:00 | 5d | Marketing resource[2.00 #2] | 0 | 0 | 0 | 0 | 0
4 | Financial scheduling | 1.4 | 3FS | FS9;FS25 | 2020-01-01 13:00 | 2020-01-08 12:00 | 5d | Marketing resource;Technical resource | 0 | 0 | 0 | 0 | 0
5 | Business plan | 1.5 | 3FS | FS9 | 2020-01-08 13:00 | 2020-01-29 12:00 | 15d | Marketing resource[2.00 #2];Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
6 | Search for ecological partners | 1.6 | 3FS | FS8;FS15;FS9 | 2020-01-29 13:00 | 2020-02-12 12:00 | 10d | Marketing resource[2.00 #2] | 0 | 0 | 0 | 0 | 0
7 | Market strategy | 1.7 | 3FS | FS8;FS24 | 2020-06-24 13:00 | 2020-07-01 12:00 | 5d | Marketing resource[2.00 #2] | 0 | 0 | 0 | 0 | 0
8 | Approval government | 1.8 | 7FS;6FS | FS22 | 2020-07-01 13:00 | 2020-09-16 12:00 | 55d |  | 0 | 0 | 0 | 0 | 0
9 | Sponsoring | 1.9 | 5FS;4FS;6FS | FS10;FS13 | 2020-02-12 13:00 | 2020-03-18 12:00 | 25d | Marketing resource[2.00 #2] | 0 | 0 | 0 | 0 | 0
10 | Software research | 1.10 | 9FS | FS11 | 2020-03-18 13:00 | 2020-04-08 12:00 | 15d | Marketing resource;Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
11 | Development software | 1.11 | 10FS | FS12 | 2020-04-08 13:00 | 2020-05-13 12:00 | 25d | Technical resource[3.00 #4] | 0 | 0 | 0 | 0 | 0
12 | Software testing | 1.12 | 11FS | FS17 | 2020-05-13 13:00 | 2020-05-27 12:00 | 10d | Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
13 | Tendering | 1.13 | 9FS | FS14 | 2020-04-08 13:00 | 2020-06-10 12:00 | 45d | Marketing resource[2.00 #2];Technical resource | 0 | 0 | 0 | 0 | 0
14 | Comparing offers | 1.14 | 13FS | FS17;FS18 | 2020-06-10 13:00 | 2020-06-24 12:00 | 10d | Marketing resource[2.00 #2];Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
15 | Collect aluminium from partner | 1.15 | 6FS | FS16 | 2020-02-12 13:00 | 2020-02-19 12:00 | 5d | Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
16 | Recycle aluminium | 1.16 | 15FS | FS17 | 2020-02-19 13:00 | 2020-03-04 12:00 | 10d | Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
17 | Manufacturing steps | 1.17 | 12FS;14FS;16FS | FS21 | 2020-06-24 13:00 | 2020-09-02 12:00 | 50d |  | 0 | 0 | 0 | 0 | 0
18 | Manufacturing charging stations | 1.18 | 14FS | FS19 | 2020-06-24 13:00 | 2020-09-16 12:00 | 60d |  | 0 | 0 | 0 | 0 | 0
19 | Installation charging stations | 1.19 | 18FS | FS20 | 2020-09-16 13:00 | 2020-10-07 12:00 | 15d |  | 0 | 0 | 0 | 0 | 0
20 | Placing solar panels | 1.20 | 19FS | FS21 | 2020-10-07 13:00 | 2020-10-21 12:00 | 10d | Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
21 | Calculate total emission of project | 1.21 | 20FS;17FS | FS22 | 2020-10-21 13:00 | 2020-10-23 17:00 | 2d 4h | Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
22 | Compensate total emission | 1.22 | 21FS;8FS | FS23 | 2020-10-28 13:00 | 2020-11-18 12:00 | 15d | Marketing resource[2.00 #2];Technical resource | 0 | 0 | 0 | 0 | 0
23 | Request CO2 neutral label | 1.23 | 22FS | FS24;FS28 | 2020-11-18 13:00 | 2020-12-16 12:00 | 20d | Marketing resource | 0 | 0 | 0 | 0 | 0
24 | Development marketing campaign | 1.24 | 23FS;7FS | FS27 | 2020-12-16 13:00 | 2021-01-20 12:00 | 25d | Marketing resource[2.00 #2] | 0 | 0 | 0 | 0 | 0
25 | Search office | 1.25 | 4FS | FS26 | 2020-07-01 13:00 | 2020-09-23 12:00 | 60d | Marketing resource;Technical resource | 0 | 0 | 0 | 0 | 0
26 | Customer helpdesk | 1.26 | 25FS | FS28 | 2020-09-23 13:00 | 2020-10-28 12:00 | 25d | Marketing resource[2.00 #2];Technical resource | 0 | 0 | 0 | 0 | 0
27 | Marketing campaign | 1.27 | 24FS | FS28 | 2021-01-20 13:00 | 2021-02-24 12:00 | 25d | Marketing resource[2.00 #2] | 0 | 0 | 0 | 0 | 0
28 | Initial launch | 1.28 | 27FS;26FS;23FS | FS29 | 2021-02-24 13:00 | 2021-05-05 12:00 | 50d | Marketing resource;Technical resource[2.00 #4] | 0 | 0 | 0 | 0 | 0
29 | Adjustments | 1.29 | 28FS | FS30 | 2021-05-05 13:00 | 2021-06-02 12:00 | 20d | Technical resource[3.00 #4] | 0 | 0 | 0 | 0 | 0
30 | Official launch | 1.30 | 29FS |  | 2021-06-02 13:00 | 2021-06-04 17:00 | 2d 4h | Marketing resource[2.00 #2];Technical resource[4.00 #4] | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Marketing resource | Renewable | 2 | 0 | 0 | 1[2.00 Marketing resource];2[2.00 Marketing resource];3[2.00 Marketing resource];4;5[2.00 Marketing resource];6[2.00 Marketing resource];7[2.00 Marketing resource];9[2.00 Marketing resource];10;13[2.00 Marketing resource];14[2.00 Marketing resource];22[2.00 Marketing resource];23;24[2.00 Marketing resource];25;26[2.00 Marketing resource];27[2.00 Marketing resource];28;30[2.00 Marketing resource]; | 0
2 | Technical resource | Renewable | 4 | 0 | 0 | 4;5[2.00 Technical resource];10[2.00 Technical resource];11[3.00 Technical resource];12[2.00 Technical resource];13;14[2.00 Technical resource];15[2.00 Technical resource];16[2.00 Technical resource];20[2.00 Technical resource];21[2.00 Technical resource];22;25;26;28[2.00 Technical resource];29[3.00 Technical resource];30[4.00 Technical resource]; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Electric and ecological step sharing project | 3200h
1 | Survey development | 20h | standard - symmetric | 80 | 100 | 120
2 | Survey distribution | 160h | standard - symmetric | 80 | 100 | 120
3 | Surve analysis | 40h | standard - symmetric | 80 | 100 | 120
4 | Financial scheduling | 40h | standard - symmetric | 80 | 100 | 120
5 | Business plan | 120h | standard - symmetric | 80 | 100 | 120
6 | Search for ecological partners | 80h | standard - symmetric | 80 | 100 | 120
7 | Market strategy | 40h | standard - symmetric | 80 | 100 | 120
8 | Approval government | 440h | standard - symmetric | 80 | 100 | 120
9 | Sponsoring | 200h | standard - symmetric | 80 | 100 | 120
10 | Software research | 120h | standard - symmetric | 80 | 100 | 120
11 | Development software | 200h | standard - symmetric | 80 | 100 | 120
12 | Software testing | 80h | standard - symmetric | 80 | 100 | 120
13 | Tendering | 360h | standard - symmetric | 80 | 100 | 120
14 | Comparing offers | 80h | standard - symmetric | 80 | 100 | 120
15 | Collect aluminium from partner | 40h | standard - symmetric | 80 | 100 | 120
16 | Recycle aluminium | 80h | standard - symmetric | 80 | 100 | 120
17 | Manufacturing steps | 400h | standard - symmetric | 80 | 100 | 120
18 | Manufacturing charging stations | 480h | standard - symmetric | 80 | 100 | 120
19 | Installation charging stations | 120h | standard - symmetric | 80 | 100 | 120
20 | Placing solar panels | 80h | standard - symmetric | 80 | 100 | 120
21 | Calculate total emission of project | 20h | standard - symmetric | 80 | 100 | 120
22 | Compensate total emission | 120h | standard - symmetric | 80 | 100 | 120
23 | Request CO2 neutral label | 160h | standard - symmetric | 80 | 100 | 120
24 | Development marketing campaign | 200h | standard - symmetric | 80 | 100 | 120
25 | Search office | 480h | standard - symmetric | 80 | 100 | 120
26 | Customer helpdesk | 200h | standard - symmetric | 80 | 100 | 120
27 | Marketing campaign | 200h | standard - symmetric | 80 | 100 | 120
28 | Initial launch | 400h | standard - symmetric | 80 | 100 | 120
29 | Adjustments | 160h | standard - symmetric | 80 | 100 | 120
30 | Official launch | 20h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))