## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | MIVB SeSaMe | 1 |  |  | 2013-01-02 08:00 | 2013-01-21 11:00 | 13d 3h |  |  | 1531809.5103 |  |  | 1538853.5103 | 19.125
1 | Start | 1.1 |  | FS2;FS3;FS4;FS5;FS6;FS7;FS8 | 2013-01-02 08:00 | 2013-01-01 18:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.58333
22 | Installation and wiring | 1.2 |  |  | 2013-01-02 08:00 | 2013-01-15 12:00 | 9d 4h |  |  | 1529875.7404 |  |  | 1536175.7403 | 13.1667
9 | Gate Installation | 1.2.1 |  |  | 2013-01-02 08:00 | 2013-01-04 17:00 | 2d 8h |  |  | 176810.3091 |  |  | 179470.3091 | 2.375
2 | Left Entry gates | 1.2.1.1 | 1FS | FS10;FS11 | 2013-01-02 08:00 | 2013-01-02 15:00 | 6h | Labourer[2.00 #7] | 240 | 8034.0801 | 0 | 0 | 8274.0801 | 0.29167
3 | Left Exit Gates | 1.2.1.2 | 1FS | FS10;FS11 | 2013-01-02 15:00 | 2013-01-03 14:00 | 8h | Labourer[0.88 #7] | 140 | 26156.4102 | 0 | 0 | 26296.4102 | 0.95833
4 | Middle Entry Gates | 1.2.1.3 | 1FS | FS10;FS11 | 2013-01-03 14:00 | 2013-01-04 17:00 | 1d 3h | Labourer[3.00 #7] | 720 | 18680.4297 | 0 | 0 | 19400.4297 | 1.125
5 | Middle Exit gates | 1.2.1.4 | 1FS | FS10;FS11 | 2013-01-03 17:00 | 2013-01-04 12:00 | 5h | Labourer[1.60 #7] | 160 | 4206.3301 | 0 | 0 | 4366.3301 | 0.79167
6 | Higher capacity middle entry gates | 1.2.1.5 | 1FS | FS10;FS11 | 2013-01-02 08:00 | 2013-01-03 10:00 | 1d 2h | Labourer[4.09 #7] | 900 | 73545.9688 | 0 | 0 | 74445.9687 | 1.0833
7 | Right Entry gates | 1.2.1.6 | 1FS | FS10;FS11 | 2013-01-03 13:00 | 2013-01-04 11:00 | 8h | Labourer[0.88 #7] | 140 | 42516.0703 | 0 | 0 | 42656.0703 | 0.91667
8 | Right Exit Gates | 1.2.1.7 | 1FS | FS10;FS11 | 2013-01-03 10:00 | 2013-01-03 17:00 | 6h | Labourer[3.00 #7] | 360 | 3671.02 | 0 | 0 | 4031.02 | 0.29167
12 | Door Installation | 1.2.2 |  |  | 2013-01-07 17:00 | 2013-01-09 18:00 | 2d 1h |  |  | 1294009.7305 |  |  | 1296249.7305 | 2.0417
10 | STD-G install | 1.2.2.1 | 2FS;3FS;4FS;5FS;6FS;7FS;8FS | FS13;FS14 | 2013-01-08 15:00 | 2013-01-09 18:00 | 1d 3h | Labourer[7.00 #7] | 1680 | 1234567 | 0 | 0 | 1236247 | 1.125
11 | SAS-G install | 1.2.2.2 | 2FS;3FS;4FS;5FS;6FS;7FS;8FS | FS13;FS14 | 2013-01-07 17:00 | 2013-01-08 15:00 | 7h | Labourer[4.00 #7] | 560 | 59442.7305 | 0 | 0 | 60002.7305 | 0.91667
15 | ICT installation | 1.2.3 |  |  | 2013-01-10 08:00 | 2013-01-11 16:00 | 1d 7h |  |  | 13293.5701 |  |  | 13653.5701 | 1.3333
13 | Annulation System | 1.2.3.1 | 10FS;11FS | FS16;FS17;FS18;FS19;FS20 | 2013-01-11 09:00 | 2013-01-11 16:00 | 6h | informatician[0.83 #1] | 120 | 9439.4102 | 0 | 0 | 9559.4102 | 0.29167
14 | Validation System | 1.2.3.2 | 10FS;11FS | FS16;FS17;FS18;FS19;FS20 | 2013-01-10 08:00 | 2013-01-11 09:00 | 1d 1h | informatician | 240 | 3854.1599 | 0 | 0 | 4094.1599 | 1.0417
21 | Other installations | 1.2.4 |  |  | 2013-01-11 16:00 | 2013-01-15 12:00 | 1d 6h |  |  | 45762.1307 |  |  | 46802.1307 | 3.8333
16 | Service Entry | 1.2.4.1 | 13FS;14FS | FS19 | 2013-01-14 11:00 | 2013-01-14 16:00 | 4h | Labourer[1.50 #7] | 120 | 5730.2402 | 0 | 0 | 5850.2402 | 0.20833
17 | Special Switches | 1.2.4.2 | 13FS;14FS | FS19 | 2013-01-14 11:00 | 2013-01-14 14:00 | 2h | Labourer | 40 | 894.1 | 0 | 0 | 934.1 | 0.125
18 | Partitions | 1.2.4.3 | 13FS;14FS | FS19 | 2013-01-11 16:00 | 2013-01-14 14:00 | 7h | Labourer[3.00 #7] | 420 | 30173.9004 | 0 | 0 | 30593.9004 | 2.9167
19 | Positioning Cables | 1.2.4.4 | 13FS;14FS;16FS;17FS;18FS | FS23;FS24;FS25 | 2013-01-14 16:00 | 2013-01-15 12:00 | 6h | Labourer[0.50 #7] | 60 | 5236.8901 | 0 | 0 | 5296.8901 | 0.83333
20 | Alarm buttons | 1.2.4.5 | 13FS;14FS | FS23;FS24;FS25 | 2013-01-11 16:00 | 2013-01-14 11:00 | 5h | Labourer[4.00 #7] | 400 | 3727 | 0 | 0 | 4127 | 2.7917
26 | Configuration, setup and testing | 1.3 |  |  | 2013-01-15 13:00 | 2013-01-17 16:00 | 2d 3h |  |  | 877.85 |  |  | 1381.85 | 2.125
23 | gate configuration | 1.3.1 | 19FS;20FS | FS27;FS28;FS29 | 2013-01-15 13:00 | 2013-01-15 18:00 | 5h | informatician | 120 | 306.91 | 0 | 0 | 426.91 | 0.20833
24 | door configuration | 1.3.2 | 19FS;20FS | FS27;FS28;FS29 | 2013-01-17 11:00 | 2013-01-17 16:00 | 4h | informatician | 96 | 406.59 | 0 | 0 | 502.59 | 0.20833
25 | setup and testing | 1.3.3 | 19FS;20FS | FS27;FS28;FS29 | 2013-01-16 08:00 | 2013-01-17 11:00 | 1d 3h | informatician | 288 | 164.35 | 0 | 0 | 452.35 | 1.125
30 | Security control and commissioning | 1.4 |  |  | 2013-01-17 16:00 | 2013-01-21 11:00 | 1d 5h |  |  | 1055.92 |  |  | 1295.92 | 3.7917
27 | gate security control | 1.4.1 | 23FS;24FS;25FS | FS31 | 2013-01-18 11:00 | 2013-01-21 10:00 | 8h | informatician[0.62 #1] | 120 | 306.91 | 0 | 0 | 426.91 | 2.9583
28 | door security control | 1.4.2 | 23FS;24FS;25FS | FS31 | 2013-01-17 16:00 | 2013-01-18 11:00 | 5h | informatician[0.80 #1] | 96 | 363.36 | 0 | 0 | 459.36 | 0.79167
29 | commissioning | 1.4.3 | 23FS;24FS;25FS | FS31 | 2013-01-21 10:00 | 2013-01-21 11:00 | 1h | informatician | 24 | 385.65 | 0 | 0 | 409.65 | 0.041667
31 | The end | 1.5 | 27FS;28FS;29FS |  | 2013-01-21 11:00 | 2013-01-21 11:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Labourer | Renewable | 7 h | 0 | 20 | 2[2.00 Labourer];3[0.88 Labourer];4[3.00 Labourer];5[1.60 Labourer];6[4.09 Labourer];7[0.88 Labourer];8[3.00 Labourer];10[7.00 Labourer];11[4.00 Labourer];16[1.50 Labourer];17;18[3.00 Labourer];19[0.50 Labourer];20[4.00 Labourer]; | 5940
2 | informatician | Renewable | 1 h | 0 | 24 | 13[0.83 informatician];14;23;24;25;27[0.62 informatician];28[0.80 informatician];29; | 1104

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | MIVB SeSaMe | 120h |  |  |  |  | 99 | 100 | 101
1 | Start | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Installation and wiring | 85h |  |  |  |  | 99 | 100 | 101
9 | Gate Installation | 26h |  |  |  |  | 99 | 100 | 101
2 | Left Entry gates | 6h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
3 | Left Exit Gates | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
4 | Middle Entry Gates | 12h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
5 | Middle Exit gates | 5h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
6 | Higher capacity middle entry gates | 11h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
7 | Right Entry gates | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
8 | Right Exit Gates | 6h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | Door Installation | 19h |  |  |  |  | 99 | 100 | 101
10 | STD-G install | 12h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
11 | SAS-G install | 7h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
15 | ICT installation | 16h |  |  |  |  | 99 | 100 | 101
13 | Annulation System | 6h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
14 | Validation System | 10h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | Other installations | 15h |  |  |  |  | 99 | 100 | 101
16 | Service Entry | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
17 | Special Switches | 2h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
18 | Partitions | 7h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
19 | Positioning Cables | 6h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
20 | Alarm buttons | 5h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
26 | Configuration, setup and testing | 21h |  |  |  |  | 99 | 100 | 101
23 | gate configuration | 5h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
24 | door configuration | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | setup and testing | 12h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
30 | Security control and commissioning | 14h |  |  |  |  | 99 | 100 | 101
27 | gate security control | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
28 | door security control | 5h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
29 | commissioning | 1h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
31 | The end | 0 | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | Yes
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold