## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Office Finishing Works (4) | 1 |  |  | 2011-05-02 08:00 | 2012-01-30 17:00 | 196d |  |  | 2 |  |  | 248203.9245 | 273.375
9 | Verplaatsbare wanden (1) | 1.1 |  | SS1;SS2;SS4 | 2011-05-02 08:00 | 2011-08-31 17:00 | 88d |  | 0 | 0 | 7.71 | 5427.84 | 5427.84 | 121.375
1 | Akoestische dammen | 1.2 | 9SS | FS3 | 2011-06-17 08:00 | 2011-07-08 17:00 | 16d |  | 0 | 0 | 128.34 | 16427.5195 | 16427.5195 | 21.375
2 | Verplaatsbare wanden (2) | 1.3 | 9SS | FS3 | 2011-06-17 08:00 | 2011-09-08 17:00 | 60d |  | 0 | 0 | 424.54 | 203779.2041 | 203779.2041 | 83.375
4 | Zuivere OA | 1.4 | 9SS |  | 2011-06-28 08:00 | 2011-09-28 17:00 | 67d |  | 0 | 0 | 40.65 | 21788.4008 | 21788.4008 | 92.375
3 | Verplaatsbare wanden (3) | 1.5 | 1FS;2FS |  | 2011-09-26 08:00 | 2012-01-30 17:00 | 91d |  | 0 | 0 | 1.07 | 778.96 | 778.96 | 126.375
10 | Meerwerken 1 | 1.6 |  |  | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 0.041667
11 | meerwerken 2 | 1.7 |  |  | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 0.041667

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Office Finishing Works (4) | 1568h |  |  |  |  | 99 | 100 | 101
9 | Verplaatsbare wanden (1) | 704h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Akoestische dammen | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Verplaatsbare wanden (2) | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Zuivere OA | 536h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Verplaatsbare wanden (3) | 728h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Meerwerken 1 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | meerwerken 2 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-06-30 18:00 |  | TP Name | periode 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (4) | 2011-05-02 08:00 | 2012-01-30 17:00 | 196d |  |  | 2 |  |  | 248203.9245 |  | 22d | [5 empty] | 62311.0009 |  | 18.84% |  | 46751.2815 | 47921.9204
9 | Verplaatsbare wanden (1) | 2011-05-02 08:00 | 2011-08-31 17:00 | 88d |  | 0 | 0 | 7.71 | 5427.84 | 5427.84 | 2011-06-01 08:00 | 22d | 1356.96 | 4070.88 | 66d | 156.04 | 0 | 1513 | 4070.88 | 25% | Started | 1356.96 | 2713.92 | 100 | 25 | 25 | 100 | 27.8748 | 25
1 | Akoestische dammen | 2011-06-17 08:00 | 2011-07-08 17:00 | 16d |  | 0 | 0 | 128.34 | 16427.5195 | 16427.5195 | 2011-06-17 08:00 | 10d | 10267.1997 | 6160.3198 | 6d | -6112.2002 | 0 | 4154.9995 | 6160.3198 | 62.5% | Started | 10267.1997 | 10267.1997 | 100 | 62.5 | 62.5 | 100 | 25.2929 | 62.5
2 | Verplaatsbare wanden (2) | 2011-06-17 08:00 | 2011-09-08 17:00 | 60d |  | 0 | 0 | 424.54 | 203779.2041 | 203779.2041 | 2011-06-17 08:00 | 10d | 33963.2007 | 169816.0034 | 50d | 17578.8008 | 0 | 51542.0015 | 169816.0034 | 16.67% | Started | 33963.2017 | 33963.2007 | 100 | 16.6667 | 16.6667 | 100 | 25.2931 | 16.6667
4 | Zuivere OA | 2011-06-28 08:00 | 2011-09-28 17:00 | 67d |  | 0 | 0 | 40.65 | 21788.4008 | 21788.4008 | 2011-06-28 08:00 | 3d | 975.6 | 20812.8008 | 64d | 3927.3999 | 0 | 4902.9999 | 20812.8008 | 4.478% | Started | 975.6 | 975.6 | 100 | 4.4776 | 4.4776 | 100 | 22.5028 | 4.4776
3 | Verplaatsbare wanden (3) | 2011-09-26 08:00 | 2012-01-30 17:00 | 91d |  | 0 | 0 | 1.07 | 778.96 | 778.96 | 2011-06-01 08:00 | 22d | 188.32 | 590.64 | 69d | 9.68 | 0 | 198 | 590.64 | 24.18% | Started | 188.32 | 0 | 100 | 24.1758 | 24.1758 | 100 | 25.4185 | 24.1758
10 | Meerwerken 1 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
11 | meerwerken 2 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-07-31 18:00 |  | TP Name | periode 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (4) | 2011-05-02 08:00 | 2012-01-30 17:00 | 196d |  |  | 2 |  |  | 248203.9245 |  | 43d | [5 empty] | 112260.0023 |  | 49.39% |  | 122586.4823 | 133529.442
9 | Verplaatsbare wanden (1) | 2011-05-02 08:00 | 2011-08-31 17:00 | 88d |  | 0 | 0 | 7.71 | 5427.84 | 5427.84 | 2011-06-01 08:00 | 42d | 2590.56 | 2837.28 | 46d | 134.44 | 0 | 2725 | 2837.28 | 47.73% | Started | 2590.56 | 4009.2 | 100 | 47.7273 | 47.7273 | 100 | 50.2041 | 47.7273
1 | Akoestische dammen | 2011-06-17 08:00 | 2011-07-08 17:00 | 16d |  | 0 | 0 | 128.34 | 16427.5195 | 16427.5195 | 2011-06-17 08:00 | 30d | 30801.5991 | 41068.7988 | 40d | -23316.5996 | 0 | 7484.9995 | 41068.7988 | 62.5% | Started | 10267.1997 | 16427.5195 | 100 | 187.5 | 62.5 | 100 | 45.5638 | 62.5
2 | Verplaatsbare wanden (2) | 2011-06-17 08:00 | 2011-09-08 17:00 | 60d |  | 0 | 0 | 424.54 | 203779.2041 | 203779.2041 | 2011-06-17 08:00 | 30d | 101889.6021 | 101889.6021 | 30d | -9029.5996 | 0 | 92860.0024 | 101889.6021 | 50% | Started | 101889.6021 | 105285.9221 | 100 | 50 | 50 | 100 | 45.5689 | 50
4 | Zuivere OA | 2011-06-28 08:00 | 2011-09-28 17:00 | 67d |  | 0 | 0 | 40.65 | 21788.4008 | 21788.4008 | 2011-06-28 08:00 | 23d | 7479.6003 | 14308.8005 | 44d | 1354.4 | 0 | 8834.0003 | 14308.8005 | 34.33% | Started | 7479.6005 | 7804.8003 | 100 | 34.3284 | 34.3284 | 100 | 40.5445 | 34.3284
3 | Verplaatsbare wanden (3) | 2011-09-26 08:00 | 2012-01-30 17:00 | 91d |  | 0 | 0 | 1.07 | 778.96 | 778.96 | 2011-06-01 08:00 | 42d | 359.52 | 419.44 | 49d | -3.52 | 0 | 356 | 419.44 | 46.15% | Started | 359.52 | 0 | 100 | 46.1538 | 46.1538 | 100 | 45.702 | 46.1538
10 | Meerwerken 1 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
11 | meerwerken 2 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-08-31 18:00 |  | TP Name | periode 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (4) | 2011-05-02 08:00 | 2012-01-30 17:00 | 196d |  |  | 2 |  |  | 248203.9245 |  | 66d | [5 empty] | 159035.0025 |  | 80.53% |  | 199888.4227 | 220543.0438
9 | Verplaatsbare wanden (1) | 2011-05-02 08:00 | 2011-08-31 17:00 | 88d |  | 0 | 0 | 7.71 | 5427.84 | 5427.84 | 2011-06-01 08:00 | 62d | 3824.16 | 1603.68 | 26d | 35.84 | 0 | 3860 | 1603.68 | 70.45% | Started | 3824.1599 | 5427.84 | 100 | 70.4545 | 70.4545 | 100 | 71.1148 | 70.4545
1 | Akoestische dammen | 2011-06-17 08:00 | 2011-07-08 17:00 | 16d |  | 0 | 0 | 128.34 | 16427.5195 | 16427.5195 | 2011-06-17 08:00 | 50d | 51335.9985 | 20534.3994 | 20d | -40732 | 0 | 10603.9985 | 20534.3994 | 71.43% | Started | 11733.9428 | 16427.5195 | 100 | 312.5 | 71.4286 | 100 | 64.5502 | 71.4286
2 | Verplaatsbare wanden (2) | 2011-06-17 08:00 | 2011-09-08 17:00 | 60d |  | 0 | 0 | 424.54 | 203779.2041 | 203779.2041 | 2011-06-17 08:00 | 50d | 169816.0034 | 33963.2007 | 10d | -38265 | 0 | 131551.0034 | 33963.2007 | 83.33% | Started | 169815.9994 | 183401.2837 | 100 | 83.3333 | 83.3333 | 100 | 64.5557 | 83.3333
4 | Zuivere OA | 2011-06-28 08:00 | 2011-09-28 17:00 | 67d |  | 0 | 0 | 40.65 | 21788.4008 | 21788.4008 | 2011-06-28 08:00 | 43d | 13983.6005 | 7804.8003 | 24d | -1468.6 | 0 | 12515.0005 | 7804.8003 | 64.18% | Started | 13983.6005 | 15284.4006 | 100 | 64.1791 | 64.1791 | 100 | 57.4388 | 64.1791
3 | Verplaatsbare wanden (3) | 2011-09-26 08:00 | 2012-01-30 17:00 | 91d |  | 0 | 0 | 1.07 | 778.96 | 778.96 | 2011-06-01 08:00 | 62d | 530.72 | 248.24 | 29d | -25.72 | 0 | 505 | 248.24 | 68.13% | Started | 530.72 | 0 | 100 | 68.1319 | 68.1319 | 100 | 64.83 | 68.1319
10 | Meerwerken 1 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
11 | meerwerken 2 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-09-30 18:00 |  | TP Name | periode 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (4) | 2011-05-02 08:00 | 2012-01-30 17:00 | 196d |  |  | 2 |  |  | 248203.9245 |  | 88d | [5 empty] | 197309.0037 |  | 100% |  | 248202.9245 | 247467.7645
9 | Verplaatsbare wanden (1) | 2011-05-02 08:00 | 2011-08-31 17:00 | 88d |  | 0 | 0 | 7.71 | 5427.84 | 5427.84 | 2011-06-01 08:00 | 87d | 5366.16 | 0 | 0 | -824.16 | 0 | 4542.0001 | 0 | 100% | Finished | 5427.84 | 5427.84 | 100 | 98.8636 | 100 | 100 | 83.6797 | 100
1 | Akoestische dammen | 2011-06-17 08:00 | 2011-07-08 17:00 | 16d |  | 0 | 0 | 128.34 | 16427.5195 | 16427.5195 | 2011-06-17 08:00 | 75d | 77003.9978 | 0 | 0 | -64529 | 0 | 12474.9978 | 0 | 100% | Finished | 16427.5195 | 16427.5195 | 100 | 468.75 | 100 | 100 | 75.9396 | 100
2 | Verplaatsbare wanden (2) | 2011-06-17 08:00 | 2011-09-08 17:00 | 60d |  | 0 | 0 | 424.54 | 203779.2041 | 203779.2041 | 2011-06-17 08:00 | 60d | 203779.2041 | 0 | 0 | -49013.1992 | 0 | 154766.0049 | 0 | 100% | Finished | 203779.2041 | 203779.2041 | 100 | 100 | 100 | 100 | 75.9479 | 100
4 | Zuivere OA | 2011-06-28 08:00 | 2011-09-28 17:00 | 67d |  | 0 | 0 | 40.65 | 21788.4008 | 21788.4008 | 2011-06-28 08:00 | 67d | 21788.4008 | 0 | 0 | -7064.3999 | 0 | 14724.0009 | 0 | 100% | Finished | 21788.4008 | 21788.4008 | 100 | 100 | 100 | 100 | 67.5772 | 100
3 | Verplaatsbare wanden (3) | 2011-09-26 08:00 | 2012-01-30 17:00 | 91d |  | 0 | 0 | 1.07 | 778.96 | 778.96 | 2011-06-01 08:00 | 87d | 744.72 | 0 | 0 | -150.72 | 0 | 594 | 0 | 100% | Finished | 778.96 | 42.8 | 100 | 95.6044 | 100 | 100 | 76.2555 | 100
10 | Meerwerken 1 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-09-01 08:00 | 20d | 1 | 0 | 0 | 10207 | 0 | 10208 | 0 | 100% | Finished | 1 | 1 | 100 | 16000 | 100 | 100 | 1020800 | 100
11 | meerwerken 2 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-10-31 18:00 |  | TP Name | periode 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (4) | 2011-05-02 08:00 | 2012-01-30 17:00 | 196d |  |  | 2 |  |  | 248203.9245 |  | 108d | [5 empty] | 198567.0037 |  | 100% |  | 248203.9245 | 247647.5245
9 | Verplaatsbare wanden (1) | 2011-05-02 08:00 | 2011-08-31 17:00 | 88d |  | 0 | 0 | 7.71 | 5427.84 | 5427.84 | 2011-06-01 08:00 | 87d | 5366.16 | 0 | 0 | -824.16 | 0 | 4542.0001 | 0 | 100% | Finished | 5427.84 | 5427.84 | 100 | 98.8636 | 100 | 100 | 83.6797 | 100
1 | Akoestische dammen | 2011-06-17 08:00 | 2011-07-08 17:00 | 16d |  | 0 | 0 | 128.34 | 16427.5195 | 16427.5195 | 2011-06-17 08:00 | 75d | 77003.9978 | 0 | 0 | -64529 | 0 | 12474.9978 | 0 | 100% | Finished | 16427.5195 | 16427.5195 | 100 | 468.75 | 100 | 100 | 75.9396 | 100
2 | Verplaatsbare wanden (2) | 2011-06-17 08:00 | 2011-09-08 17:00 | 60d |  | 0 | 0 | 424.54 | 203779.2041 | 203779.2041 | 2011-06-17 08:00 | 60d | 203779.2041 | 0 | 0 | -49013.1992 | 0 | 154766.0049 | 0 | 100% | Finished | 203779.2041 | 203779.2041 | 100 | 100 | 100 | 100 | 75.9479 | 100
4 | Zuivere OA | 2011-06-28 08:00 | 2011-09-28 17:00 | 67d |  | 0 | 0 | 40.65 | 21788.4008 | 21788.4008 | 2011-06-28 08:00 | 67d | 21788.4008 | 0 | 0 | -7064.3999 | 0 | 14724.0009 | 0 | 100% | Finished | 21788.4008 | 21788.4008 | 100 | 100 | 100 | 100 | 67.5772 | 100
3 | Verplaatsbare wanden (3) | 2011-09-26 08:00 | 2012-01-30 17:00 | 91d |  | 0 | 0 | 1.07 | 778.96 | 778.96 | 2011-06-01 08:00 | 87d | 744.72 | 0 | 0 | -150.72 | 0 | 594 | 0 | 100% | Finished | 778.96 | 222.56 | 100 | 95.6044 | 100 | 100 | 76.2555 | 100
10 | Meerwerken 1 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-09-01 08:00 | 20d | 1 | 0 | 0 | 10207 | 0 | 10208 | 0 | 100% | Finished | 1 | 1 | 100 | 16000 | 100 | 100 | 1020800 | 100
11 | meerwerken 2 | 2011-05-02 08:00 | 2011-05-02 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-10-03 08:00 | 20d | 1 | 0 | 0 | 1257 | 0 | 1258 | 0 | 100% | Finished | 1 | 1 | 100 | 16000 | 100 | 100 | 125800 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
periode 1 | 2011-05-02 08:00 | 2011-06-30 18:00 | 47921.9204 | 46751.2815 | 62311.0009 | 2011-06-30 15:00 | -1170.639 | 97.56% | -15559.7195 | 75.03% | -2h | 99.43% | 97.12% | 2012-01-31 16:00 | 2012-02-06 16:00 | 2012-05-09 15:00 | 2012-02-01 09:00 | 2012-02-06 16:00 | 2012-04-19 09:00 | 2012-01-31 10:00 | 2012-02-01 09:00 | 2012-04-12 09:00 | 263763.644 | 330810.9316 | 268807.9617 | 264914.8019 | 337534.0946 | 332345.2169 | 315600.3523 | 314411.953 | 0.99432 | 0.75029 | 0.97557 | 0.97124 | -0.25 | 0.75029 | 1 | 0.99432 | 1
periode 2 | 2011-06-30 18:00 | 2011-07-31 18:00 | 133529.442 | 122586.4823 | 112260.0023 | 2011-07-26 17:00 | -10942.9597 | 91.8% | 10326.48 | 109.2% | -3d | 95.38% | 93.95% | 2012-02-10 14:00 | 2012-02-23 12:00 | 2012-01-30 12:00 | 2012-02-07 11:00 | 2012-02-23 12:00 | 2012-02-06 17:00 | 2012-02-02 17:00 | 2012-02-13 12:00 | 2012-01-26 14:00 | 237877.4445 | 227295.6415 | 249090.9697 | 243955.7079 | 237564.5581 | 232861.8822 | 231080.9567 | 230281.6906 | 0.95385 | 1.092 | 0.91805 | 0.93947 | -3 | 1.092 | 1 | 0.95385 | 1
periode 3 | 2011-07-31 18:00 | 2011-08-31 18:00 | 220543.0438 | 199888.4227 | 159035.0025 | 2011-08-24 12:00 | -20654.6211 | 90.63% | 40853.4201 | 125.7% | -5d 4h | 93.75% | 97.02% | 2012-02-22 10:00 | 2012-02-28 10:00 | 2011-12-27 17:00 | 2012-02-10 10:00 | 2012-02-28 10:00 | 2012-01-20 17:00 | 2012-02-07 12:00 | 2012-02-17 09:00 | 2012-01-13 11:00 | 207350.5044 | 197475.7279 | 212342.9815 | 210571.5378 | 201447.837 | 200038.4429 | 199746.5668 | 199533.9432 | 0.9375 | 1.2569 | 0.90635 | 0.97016 | -5.5 | 1.2569 | 1 | 0.9375 | 1
periode 4 | 2011-08-31 18:00 | 2011-09-30 18:00 | 247467.7645 | 248202.9245 | 197309.0037 | 2012-01-30 17:00 | 735.16 | 100.3% | 50893.9208 | 125.8% | 86d | 178.2% | 100% | 2012-01-30 11:00 | 2012-01-30 11:00 | 2011-12-05 11:00 | 2012-01-30 14:00 | 2012-01-30 11:00 | 2012-01-04 16:00 | 2011-09-30 17:00 | 2011-09-30 17:00 | 2011-09-30 17:00 | 197310.0037 | 197309.7986 | 197310.0007 | 197309.5649 | 197309.7963 | 197309.4498 | 197309.8322 | 197309.7375 | 1.7818 | 1.2579 | 1.003 | 1 | 86 | 1.2579 | 1 | 1.7818 | 1
periode 5 | 2011-09-30 18:00 | 2011-10-31 18:00 | 247647.5245 | 248203.9245 | 198567.0037 | 2012-01-30 17:00 | 556.4 | 100.2% | 49636.9208 | 125% | 65d | 149.6% | 100% | 2012-01-30 12:00 | 2012-01-30 12:00 | 2011-12-06 12:00 | 2012-01-30 15:00 | 2012-01-30 12:00 | 2012-01-11 14:00 | 2011-10-31 17:00 | 2011-10-31 17:00 | 2011-10-31 17:00 | 198567.0037 | 198567.0037 | 198567.0037 | 198567.0037 | 198567.0037 | 198567.0037 | 198567.0037 | 198567.0037 | 1.4962 | 1.25 | 1.0022 | 1 | 65 | 1.25 | 1 | 1.4962 | 1