## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Project | 1 |  |  | 2015-06-08 08:00 | 2016-01-27 14:00 | 167d 5h |  |  | 0 |  |  | 0
1 | 010 | 1.1 |  | SS2+2d | 2015-06-08 08:00 | 2015-07-10 17:00 | 25d |  | 0 | 0 | 0 | 0 | 0
2 | 020 | 1.2 | 1SS+2d | SS3+3w 2h;FF4+3d 1h;FF5+2w 2d;SS6+1w | 2015-06-10 08:00 | 2015-08-20 17:00 | 52d |  | 0 | 0 | 0 | 0 | 0
3 | 030 | 1.3 | 2SS+3w 2h | FF6+2d 3h | 2015-07-01 10:00 | 2015-08-05 10:00 | 25d |  | 0 | 0 | 0 | 0 | 0
4 | 040 | 1.4 | 2FF+3d 1h | FF7+2d 1h | 2015-07-21 09:00 | 2015-08-26 09:00 | 26d |  | 0 | 0 | 0 | 0 | 0
5 | 050 | 1.5 | 2FF+2w 2d | FF8+2w 3d 7h | 2015-08-10 08:00 | 2015-09-07 17:00 | 21d |  | 0 | 0 | 0 | 0 | 0
6 | 060 | 1.6 | 2SS+1w;3FF+2d 3h | FS7;SS9+1w | 2015-07-02 14:00 | 2015-08-07 14:00 | 26d |  | 0 | 0 | 0 | 0 | 0
7 | 070 | 1.7 | 6FS;4FF+2d 1h | FS8 | 2015-08-07 14:00 | 2015-09-07 14:00 | 21d |  | 0 | 0 | 0 | 0 | 0
8 | 080 | 1.8 | 7FS;5FF+2w 3d 7h | FF11+1w | 2015-09-07 14:00 | 2015-10-21 14:00 | 32d |  | 0 | 0 | 0 | 0 | 0
9 | 090 | 1.9 | 6SS+1w | FS10;SS12+1w;SS13+1w | 2015-07-09 14:00 | 2015-08-27 14:00 | 35d |  | 0 | 0 | 0 | 0 | 0
10 | 100 | 1.10 | 9FS | FS11 | 2015-08-27 14:00 | 2015-09-24 14:00 | 20d |  | 0 | 0 | 0 | 0 | 0
11 | 110 | 1.11 | 10FS;8FF+1w | FF12+1w;FF13+1w | 2015-09-24 14:00 | 2015-12-17 14:00 | 60d |  | 0 | 0 | 0 | 0 | 0
12 | 120 a | 1.12 | 9SS+1w;11FF+1w | SS14+1w;SS15+1w | 2015-08-31 10:00 | 2015-12-24 14:00 | 83d 3h |  | 0 | 0 | 0 | 0 | 0
13 | 120 b | 1.13 | 9SS+1w;11FF+1w | FF14+1w;FF15+1w | 2015-08-31 10:00 | 2015-12-24 14:00 | 83d 3h |  | 0 | 0 | 0 | 0 | 0
14 | 130 a | 1.14 | 13FF+1w;12SS+1w | SS17+1w;SS18+1w | 2015-11-04 08:00 | 2015-12-31 14:00 | 41d 5h |  | 0 | 0 | 0 | 0 | 0
15 | 130 b | 1.15 | 13FF+1w;12SS+1w | FF17+1w;FF18+1w | 2015-11-04 08:00 | 2015-12-31 14:00 | 41d 5h |  | 0 | 0 | 0 | 0 | 0
16 | 140 | 1.16 | 19FS |  | 2016-01-14 14:00 | 2016-01-27 14:00 | 9d |  | 0 | 0 | 0 | 0 | 0
17 | 150 a | 1.17 | 14SS+1w;15FF+1w | SS19+1w | 2015-11-23 14:00 | 2016-01-07 14:00 | 33d |  | 0 | 0 | 0 | 0 | 0
18 | 150 b | 1.18 | 14SS+1w;15FF+1w | FF19+1w | 2015-11-23 14:00 | 2016-01-07 14:00 | 33d |  | 0 | 0 | 0 | 0 | 0
19 | 160 | 1.19 | 17SS+1w;18FF+1w | FS16 | 2015-12-14 14:00 | 2016-01-14 14:00 | 23d |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Project | 1341h
1 | 010 | 200h | standard - symmetric | 80 | 100 | 120
2 | 020 | 416h | standard - symmetric | 80 | 100 | 120
3 | 030 | 200h | standard - symmetric | 80 | 100 | 120
4 | 040 | 208h | standard - symmetric | 80 | 100 | 120
5 | 050 | 168h | standard - symmetric | 80 | 100 | 120
6 | 060 | 208h | standard - symmetric | 80 | 100 | 120
7 | 070 | 168h | standard - symmetric | 80 | 100 | 120
8 | 080 | 256h | standard - symmetric | 80 | 100 | 120
9 | 090 | 280h | standard - symmetric | 80 | 100 | 120
10 | 100 | 160h | standard - symmetric | 80 | 100 | 120
11 | 110 | 480h | standard - symmetric | 80 | 100 | 120
12 | 120 a | 667h | standard - symmetric | 80 | 100 | 120
13 | 120 b | 667h | standard - symmetric | 80 | 100 | 120
14 | 130 a | 333h | standard - symmetric | 80 | 100 | 120
15 | 130 b | 333h | standard - symmetric | 80 | 100 | 120
16 | 140 | 72h | standard - symmetric | 80 | 100 | 120
17 | 150 a | 264h | standard - symmetric | 80 | 100 | 120
18 | 150 b | 264h | standard - symmetric | 80 | 100 | 120
19 | 160 | 184h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))