## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building Finishing Works (3) | 1 |  |  | 2016-03-21 08:00 | 2016-08-29 17:00 | 116d |  |  | 377282 |  |  | 377282 | 161.375
25 | gelijkvloers blok B | 1.1 |  |  | 2016-03-21 08:00 | 2016-07-20 17:00 | 88d |  |  | 199743 |  |  | 199743 | 121.375
1 | pleisterwerken wanden 0 B | 1.1.1 |  | SS2 | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 15239 | 0 | 0 | 15239 | 18.375
2 | pleisterwerken plafonds 0 B | 1.1.2 | 1SS | FS3-1w | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 19593 | 0 | 0 | 19593 | 4.375
3 | lichte scheidingswanden 0 B | 1.1.3 | 2FS-1w | FS4 | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 5007 | 0 | 0 | 5007 | 11.375
4 | gespoten PU isolaie en uitvullingen 0 B | 1.1.4 | 3FS | FS5 | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 7619 | 0 | 0 | 7619 | 2.375
5 | chape 0 B | 1.1.5 | 4FS | FS6+4w;FS8+3w;FS9+8w;FS13+3w | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 3265 | 0 | 0 | 3265 | 6.375
6 | plaatsen keramsiche tegels 0 B | 1.1.6 | 5FS+4w | FS7-1w | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 28302 | 0 | 0 | 28302 | 13.375
7 | plaatsen faience 0 B | 1.1.7 | 6FS-1w |  | 2016-05-19 08:00 | 2016-06-01 17:00 | 10d |  | 0 | 11865 | 0 | 0 | 11865 | 13.375
8 | verlaagde plafonds 0 B | 1.1.8 | 5FS+3w |  | 2016-05-05 08:00 | 2016-06-01 17:00 | 20d |  | 0 | 10885 | 0 | 0 | 10885 | 27.375
9 | zachte vloerbekleding 0 B | 1.1.9 | 5FS+8w | FS10;FS11;FS12 | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 8708 | 0 | 0 | 8708 | 13.375
10 | binnenschrijnwerk 0 B | 1.1.10 | 9FS |  | 2016-06-23 08:00 | 2016-07-04 17:00 | 8d |  | 0 | 30479 | 0 | 0 | 30479 | 11.375
11 | schilderwerken wanden en plafonds 0 B | 1.1.11 | 9FS |  | 2016-06-23 08:00 | 2016-07-20 17:00 | 20d |  | 0 | 26125 | 0 | 0 | 26125 | 27.375
12 | binnenmeubilair 0 B | 1.1.12 | 9FS |  | 2016-06-23 08:00 | 2016-07-06 17:00 | 10d |  | 0 | 32656 | 0 | 0 | 32656 | 13.375
26 | nivo +1 blok B | 1.2 |  |  | 2016-05-05 08:00 | 2016-08-29 17:00 | 83d |  |  | 177539 |  |  | 177539 | 116.375
13 | pleisterwerken wanden 1 B | 1.2.1 | 5FS+3w | SS14 | 2016-05-05 08:00 | 2016-05-25 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 20.375
14 | pleisterwerken plafonds 1 B | 1.2.2 | 13SS | FS15-1w | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 13.375
15 | lichte scheidingswanden 1 B | 1.2.3 | 14FS-1w | FS16 | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 13.375
16 | vloer uitvullingen 1 B | 1.2.4 | 15FS | FS17 | 2016-05-26 08:00 | 2016-05-30 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 4.375
17 | chape 1 B | 1.2.5 | 16FS | FS18+2w;FS20+6w | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 6.375
18 | plaatsen keramsiche tegels 1 B | 1.2.6 | 17FS+2w | FS19-1w | 2016-06-21 08:00 | 2016-07-04 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 | 13.375
19 | plaatsen faience 1 B | 1.2.7 | 18FS-1w |  | 2016-06-28 08:00 | 2016-07-11 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 | 13.375
20 | zachte vloerbekleding 1 B | 1.2.8 | 17FS+6w | FS21;FS22;FS24 | 2016-07-19 08:00 | 2016-08-01 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 | 13.375
21 | binnenschrijnwerk 1B | 1.2.9 | 20FS |  | 2016-08-02 08:00 | 2016-08-11 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 | 9.375
22 | schilderwerken wanden en plafonds 1B | 1.2.10 | 20FS |  | 2016-08-02 08:00 | 2016-08-29 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 | 27.375
24 | binnenmeubilair 1B | 1.2.11 | 20FS |  | 2016-08-02 08:00 | 2016-08-15 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 | 13.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building Finishing Works (3) | 928h |  |  |  |  | 99 | 100 | 101
25 | gelijkvloers blok B | 704h |  |  |  |  | 99 | 100 | 101
1 | pleisterwerken wanden 0 B | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | pleisterwerken plafonds 0 B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | lichte scheidingswanden 0 B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | gespoten PU isolaie en uitvullingen 0 B | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
5 | chape 0 B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | plaatsen keramsiche tegels 0 B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | plaatsen faience 0 B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | verlaagde plafonds 0 B | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
9 | zachte vloerbekleding 0 B | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
10 | binnenschrijnwerk 0 B | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | schilderwerken wanden en plafonds 0 B | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | binnenmeubilair 0 B | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
26 | nivo +1 blok B | 664h |  |  |  |  | 99 | 100 | 101
13 | pleisterwerken wanden 1 B | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | pleisterwerken plafonds 1 B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | lichte scheidingswanden 1 B | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
16 | vloer uitvullingen 1 B | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
17 | chape 1 B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | plaatsen keramsiche tegels 1 B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | plaatsen faience 1 B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | zachte vloerbekleding 1 B | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | binnenschrijnwerk 1B | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | schilderwerken wanden en plafonds 1B | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
24 | binnenmeubilair 1B | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120

## Project Control - TP1
| TP Status Date | 2016-05-11 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (3) | 2016-03-21 08:00 | 2016-08-29 17:00 | 116d |  |  | 377282 |  |  | 377282 |  | 37d | [5 empty] | 56288 |  | 13.44% |  | 50723 | 93796
25 | gelijkvloers blok B | 2016-03-21 08:00 | 2016-07-20 17:00 | 88d |  |  | 199743 |  |  | 199743 |  | 37d | [5 empty] | 56288 |  | 25.39% |  | 50723 | 61608
1 | pleisterwerken wanden 0 B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 15239 | 0 | 0 | 15239 | 2016-03-21 08:00 | 18d | 15239 | 0 | 0 | -87 | 0 | 15152 | 0 | 100% | Finished | 15239 | 15239 | 100 | 120 | 100 | 100 | 99.4291 | 100
2 | pleisterwerken plafonds 0 B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 19593 | 0 | 0 | 19593 | 2016-03-21 08:00 | 7d | 19593 | 0 | 0 | 3828 | 0 | 23421 | 0 | 100% | Finished | 19593 | 19593 | 100 | 140 | 100 | 100 | 119.5376 | 100
3 | lichte scheidingswanden 0 B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 5007 | 0 | 0 | 5007 | 2016-03-23 08:00 | 10d | 5007 | 0 | 0 | 148 | 0 | 5155 | 0 | 100% | Finished | 5007 | 5007 | 100 | 100 | 100 | 100 | 102.9559 | 100
4 | gespoten PU isolaie en uitvullingen 0 B | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 7619 | 0 | 0 | 7619 | 2016-04-06 08:00 | 5d | 7619 | 0 | 0 | 1470 | 0 | 9089 | 0 | 100% | Finished | 7619 | 7619 | 100 | 166.6667 | 100 | 100 | 119.2939 | 100
5 | chape 0 B | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 3265 | 0 | 0 | 3265 | 2016-04-13 08:00 | 5d | 3265 | 0 | 0 | 206 | 0 | 3471 | 0 | 100% | Finished | 3265 | 3265 | 100 | 100 | 100 | 100 | 106.3093 | 100
6 | plaatsen keramsiche tegels 0 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 28302 | 0 | 0 | 28302 |  | 0 | 0 | 28302 | 10d | 0 | 0 | 0 | 28302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | plaatsen faience 0 B | 2016-05-19 08:00 | 2016-06-01 17:00 | 10d |  | 0 | 11865 | 0 | 0 | 11865 |  | 0 | 0 | 11865 | 10d | 0 | 0 | 0 | 11865 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | verlaagde plafonds 0 B | 2016-05-05 08:00 | 2016-06-01 17:00 | 20d |  | 0 | 10885 | 0 | 0 | 10885 |  | 0 | 0 | 10885 | 20d | 0 | 0 | 0 | 10885 | 0% | Not Started | 0 | 10885 | 100 |  | 0 | 100 |  | 0
9 | zachte vloerbekleding 0 B | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 8708 | 0 | 0 | 8708 |  | 0 | 0 | 8708 | 10d | 0 | 0 | 0 | 8708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | binnenschrijnwerk 0 B | 2016-06-23 08:00 | 2016-07-04 17:00 | 8d |  | 0 | 30479 | 0 | 0 | 30479 |  | 0 | 0 | 30479 | 8d | 0 | 0 | 0 | 30479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | schilderwerken wanden en plafonds 0 B | 2016-06-23 08:00 | 2016-07-20 17:00 | 20d |  | 0 | 26125 | 0 | 0 | 26125 |  | 0 | 0 | 26125 | 20d | 0 | 0 | 0 | 26125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | binnenmeubilair 0 B | 2016-06-23 08:00 | 2016-07-06 17:00 | 10d |  | 0 | 32656 | 0 | 0 | 32656 |  | 0 | 0 | 32656 | 10d | 0 | 0 | 0 | 32656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | nivo +1 blok B | 2016-05-05 08:00 | 2016-08-29 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 32188
13 | pleisterwerken wanden 1 B | 2016-05-05 08:00 | 2016-05-25 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 |  | 0 | 0 | 14082 | 15d | 0 | 0 | 0 | 14082 | 0% | Not Started | 0 | 14082 | 100 |  | 0 | 100 |  | 0
14 | pleisterwerken plafonds 1 B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 |  | 0 | 0 | 18106 | 10d | 0 | 0 | 0 | 18106 | 0% | Not Started | 0 | 18106 | 100 |  | 0 | 100 |  | 0
15 | lichte scheidingswanden 1 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 |  | 0 | 0 | 4627 | 10d | 0 | 0 | 0 | 4627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | vloer uitvullingen 1 B | 2016-05-26 08:00 | 2016-05-30 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 |  | 0 | 0 | 3017 | 3d | 0 | 0 | 0 | 3017 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | chape 1 B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 |  | 0 | 0 | 26153 | 5d | 0 | 0 | 0 | 26153 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | plaatsen keramsiche tegels 1 B | 2016-06-21 08:00 | 2016-07-04 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 |  | 0 | 0 | 10964 | 10d | 0 | 0 | 0 | 10964 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | plaatsen faience 1 B | 2016-06-28 08:00 | 2016-07-11 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 |  | 0 | 0 | 10059 | 10d | 0 | 0 | 0 | 10059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | zachte vloerbekleding 1 B | 2016-07-19 08:00 | 2016-08-01 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 |  | 0 | 0 | 8047 | 10d | 0 | 0 | 0 | 8047 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnenschrijnwerk 1B | 2016-08-02 08:00 | 2016-08-11 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 |  | 0 | 0 | 28165 | 8d | 0 | 0 | 0 | 28165 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | schilderwerken wanden en plafonds 1B | 2016-08-02 08:00 | 2016-08-29 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 |  | 0 | 0 | 24142 | 20d | 0 | 0 | 0 | 24142 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenmeubilair 1B | 2016-08-02 08:00 | 2016-08-15 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 |  | 0 | 0 | 30177 | 10d | 0 | 0 | 0 | 30177 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-06-29 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (3) | 2016-03-21 08:00 | 2016-08-29 17:00 | 116d |  |  | 377282 |  |  | 377282 |  | 72d | [5 empty] | 183621 |  | 46.77% |  | 176468 | 286751
25 | gelijkvloers blok B | 2016-03-21 08:00 | 2016-07-20 17:00 | 88d |  |  | 199743 |  |  | 199743 |  | 72d | [5 empty] | 114173 |  | 55.31% |  | 110483 | 199743
1 | pleisterwerken wanden 0 B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 15239 | 0 | 0 | 15239 | 2016-03-21 08:00 | 18d | 15239 | 0 | 0 | -87 | 0 | 15152 | 0 | 100% | Finished | 15239 | 15239 | 100 | 120 | 100 | 100 | 99.4291 | 100
2 | pleisterwerken plafonds 0 B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 19593 | 0 | 0 | 19593 | 2016-03-21 08:00 | 7d | 19593 | 0 | 0 | 3828 | 0 | 23421 | 0 | 100% | Finished | 19593 | 19593 | 100 | 140 | 100 | 100 | 119.5376 | 100
3 | lichte scheidingswanden 0 B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 5007 | 0 | 0 | 5007 | 2016-03-23 08:00 | 10d | 5007 | 0 | 0 | 148 | 0 | 5155 | 0 | 100% | Finished | 5007 | 5007 | 100 | 100 | 100 | 100 | 102.9559 | 100
4 | gespoten PU isolaie en uitvullingen 0 B | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 7619 | 0 | 0 | 7619 | 2016-04-06 08:00 | 5d | 7619 | 0 | 0 | 1470 | 0 | 9089 | 0 | 100% | Finished | 7619 | 7619 | 100 | 166.6667 | 100 | 100 | 119.2939 | 100
5 | chape 0 B | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 3265 | 0 | 0 | 3265 | 2016-04-13 08:00 | 5d | 3265 | 0 | 0 | 206 | 0 | 3471 | 0 | 100% | Finished | 3265 | 3265 | 100 | 100 | 100 | 100 | 106.3093 | 100
6 | plaatsen keramsiche tegels 0 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 28302 | 0 | 0 | 28302 | 2016-05-18 08:00 | 10d | 28302 | 0 | 0 | -1014 | 0 | 27288 | 0 | 100% | Finished | 28302 | 28302 | 100 | 100 | 100 | 100 | 96.4172 | 100
7 | plaatsen faience 0 B | 2016-05-19 08:00 | 2016-06-01 17:00 | 10d |  | 0 | 11865 | 0 | 0 | 11865 | 2016-05-25 08:00 | 10d | 11865 | 0 | 0 | -713 | 0 | 11152 | 0 | 100% | Finished | 11865 | 11865 | 100 | 100 | 100 | 100 | 93.9907 | 100
8 | verlaagde plafonds 0 B | 2016-05-05 08:00 | 2016-06-01 17:00 | 20d |  | 0 | 10885 | 0 | 0 | 10885 | 2016-05-11 08:00 | 20d | 10885 | 0 | 0 | 352 | 0 | 11237 | 0 | 100% | Finished | 10885 | 10885 | 100 | 100 | 100 | 100 | 103.2338 | 100
9 | zachte vloerbekleding 0 B | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 8708 | 0 | 0 | 8708 | 2016-06-15 08:00 | 10d | 8708 | 0 | 0 | -500 | 0 | 8208 | 0 | 100% | Finished | 8708 | 8708 | 100 | 100 | 100 | 100 | 94.2582 | 100
10 | binnenschrijnwerk 0 B | 2016-06-23 08:00 | 2016-07-04 17:00 | 8d |  | 0 | 30479 | 0 | 0 | 30479 |  | 0 | 0 | 30479 | 8d | 0 | 0 | 0 | 30479 | 0% | Not Started | 0 | 30479 | 100 |  | 0 | 100 |  | 0
11 | schilderwerken wanden en plafonds 0 B | 2016-06-23 08:00 | 2016-07-20 17:00 | 20d |  | 0 | 26125 | 0 | 0 | 26125 |  | 0 | 0 | 26125 | 20d | 0 | 0 | 0 | 26125 | 0% | Not Started | 0 | 26125 | 100 |  | 0 | 100 |  | 0
12 | binnenmeubilair 0 B | 2016-06-23 08:00 | 2016-07-06 17:00 | 10d |  | 0 | 32656 | 0 | 0 | 32656 |  | 0 | 0 | 32656 | 10d | 0 | 0 | 0 | 32656 | 0% | Not Started | 0 | 32656 | 100 |  | 0 | 100 |  | 0
26 | nivo +1 blok B | 2016-05-05 08:00 | 2016-08-29 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 35d | [5 empty] | 69448 |  | 37.17% |  | 65985 | 87008
13 | pleisterwerken wanden 1 B | 2016-05-05 08:00 | 2016-05-25 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 2016-05-11 08:00 | 18d | 14082 | 0 | 0 | 2028 | 0 | 16110 | 0 | 100% | Finished | 14082 | 14082 | 100 | 120 | 100 | 100 | 114.4014 | 100
14 | pleisterwerken plafonds 1 B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 2016-05-11 08:00 | 12d | 18106 | 0 | 0 | 871 | 0 | 18977 | 0 | 100% | Finished | 18106 | 18106 | 100 | 120 | 100 | 100 | 104.8106 | 100
15 | lichte scheidingswanden 1 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 2016-05-20 08:00 | 10d | 4627 | 0 | 0 | -427 | 0 | 4200 | 0 | 100% | Finished | 4627 | 4627 | 100 | 100 | 100 | 100 | 90.7716 | 100
16 | vloer uitvullingen 1 B | 2016-05-26 08:00 | 2016-05-30 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2016-06-03 08:00 | 5d | 3017 | 0 | 0 | 616 | 0 | 3633 | 0 | 100% | Finished | 3017 | 3017 | 100 | 166.6667 | 100 | 100 | 120.4176 | 100
17 | chape 1 B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 2016-06-10 08:00 | 5d | 26153 | 0 | 0 | 375 | 0 | 26528 | 0 | 100% | Finished | 26153 | 26153 | 100 | 100 | 100 | 100 | 101.4339 | 100
18 | plaatsen keramsiche tegels 1 B | 2016-06-21 08:00 | 2016-07-04 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 |  | 0 | 0 | 10964 | 10d | 0 | 0 | 0 | 10964 | 0% | Not Started | 0 | 10964 | 100 |  | 0 | 100 |  | 0
19 | plaatsen faience 1 B | 2016-06-28 08:00 | 2016-07-11 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 |  | 0 | 0 | 10059 | 10d | 0 | 0 | 0 | 10059 | 0% | Not Started | 0 | 10059 | 100 |  | 0 | 100 |  | 0
20 | zachte vloerbekleding 1 B | 2016-07-19 08:00 | 2016-08-01 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 |  | 0 | 0 | 8047 | 10d | 0 | 0 | 0 | 8047 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnenschrijnwerk 1B | 2016-08-02 08:00 | 2016-08-11 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 |  | 0 | 0 | 28165 | 8d | 0 | 0 | 0 | 28165 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | schilderwerken wanden en plafonds 1B | 2016-08-02 08:00 | 2016-08-29 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 |  | 0 | 0 | 24142 | 20d | 0 | 0 | 0 | 24142 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenmeubilair 1B | 2016-08-02 08:00 | 2016-08-15 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 |  | 0 | 0 | 30177 | 10d | 0 | 0 | 0 | 30177 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-08-12 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (3) | 2016-03-21 08:00 | 2016-08-29 17:00 | 116d |  |  | 377282 |  |  | 377282 |  | 104d | [5 empty] | 304393 |  | 78.14% |  | 294798 | 377282
25 | gelijkvloers blok B | 2016-03-21 08:00 | 2016-07-20 17:00 | 88d |  |  | 199743 |  |  | 199743 |  | 97d | [5 empty] | 204250 |  | 100% |  | 199743 | 199743
1 | pleisterwerken wanden 0 B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 15239 | 0 | 0 | 15239 | 2016-03-21 08:00 | 18d | 15239 | 0 | 0 | -87 | 0 | 15152 | 0 | 100% | Finished | 15239 | 15239 | 100 | 120 | 100 | 100 | 99.4291 | 100
2 | pleisterwerken plafonds 0 B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 19593 | 0 | 0 | 19593 | 2016-03-21 08:00 | 7d | 19593 | 0 | 0 | 3828 | 0 | 23421 | 0 | 100% | Finished | 19593 | 19593 | 100 | 140 | 100 | 100 | 119.5376 | 100
3 | lichte scheidingswanden 0 B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 5007 | 0 | 0 | 5007 | 2016-03-23 08:00 | 10d | 5007 | 0 | 0 | 148 | 0 | 5155 | 0 | 100% | Finished | 5007 | 5007 | 100 | 100 | 100 | 100 | 102.9559 | 100
4 | gespoten PU isolaie en uitvullingen 0 B | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 7619 | 0 | 0 | 7619 | 2016-04-06 08:00 | 5d | 7619 | 0 | 0 | 1470 | 0 | 9089 | 0 | 100% | Finished | 7619 | 7619 | 100 | 166.6667 | 100 | 100 | 119.2939 | 100
5 | chape 0 B | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 3265 | 0 | 0 | 3265 | 2016-04-13 08:00 | 5d | 3265 | 0 | 0 | 206 | 0 | 3471 | 0 | 100% | Finished | 3265 | 3265 | 100 | 100 | 100 | 100 | 106.3093 | 100
6 | plaatsen keramsiche tegels 0 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 28302 | 0 | 0 | 28302 | 2016-05-18 08:00 | 10d | 28302 | 0 | 0 | -1014 | 0 | 27288 | 0 | 100% | Finished | 28302 | 28302 | 100 | 100 | 100 | 100 | 96.4172 | 100
7 | plaatsen faience 0 B | 2016-05-19 08:00 | 2016-06-01 17:00 | 10d |  | 0 | 11865 | 0 | 0 | 11865 | 2016-05-25 08:00 | 10d | 11865 | 0 | 0 | -713 | 0 | 11152 | 0 | 100% | Finished | 11865 | 11865 | 100 | 100 | 100 | 100 | 93.9907 | 100
8 | verlaagde plafonds 0 B | 2016-05-05 08:00 | 2016-06-01 17:00 | 20d |  | 0 | 10885 | 0 | 0 | 10885 | 2016-05-11 08:00 | 20d | 10885 | 0 | 0 | 352 | 0 | 11237 | 0 | 100% | Finished | 10885 | 10885 | 100 | 100 | 100 | 100 | 103.2338 | 100
9 | zachte vloerbekleding 0 B | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 8708 | 0 | 0 | 8708 | 2016-06-15 08:00 | 10d | 8708 | 0 | 0 | -500 | 0 | 8208 | 0 | 100% | Finished | 8708 | 8708 | 100 | 100 | 100 | 100 | 94.2582 | 100
10 | binnenschrijnwerk 0 B | 2016-06-23 08:00 | 2016-07-04 17:00 | 8d |  | 0 | 30479 | 0 | 0 | 30479 | 2016-06-29 08:00 | 10d | 30479 | 0 | 0 | -370 | 0 | 30109 | 0 | 100% | Finished | 30479 | 30479 | 100 | 125 | 100 | 100 | 98.786 | 100
11 | schilderwerken wanden en plafonds 0 B | 2016-06-23 08:00 | 2016-07-20 17:00 | 20d |  | 0 | 26125 | 0 | 0 | 26125 | 2016-06-29 08:00 | 25d | 26125 | 0 | 0 | 1412 | 0 | 27537 | 0 | 100% | Finished | 26125 | 26125 | 100 | 125 | 100 | 100 | 105.4048 | 100
12 | binnenmeubilair 0 B | 2016-06-23 08:00 | 2016-07-06 17:00 | 10d |  | 0 | 32656 | 0 | 0 | 32656 | 2016-06-29 08:00 | 10d | 32656 | 0 | 0 | -225 | 0 | 32431 | 0 | 100% | Finished | 32656 | 32656 | 100 | 100 | 100 | 100 | 99.311 | 100
26 | nivo +1 blok B | 2016-05-05 08:00 | 2016-08-29 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 67d | [5 empty] | 100143 |  | 53.54% |  | 95055 | 177539
13 | pleisterwerken wanden 1 B | 2016-05-05 08:00 | 2016-05-25 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 2016-05-11 08:00 | 18d | 14082 | 0 | 0 | 2028 | 0 | 16110 | 0 | 100% | Finished | 14082 | 14082 | 100 | 120 | 100 | 100 | 114.4014 | 100
14 | pleisterwerken plafonds 1 B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 2016-05-11 08:00 | 12d | 18106 | 0 | 0 | 871 | 0 | 18977 | 0 | 100% | Finished | 18106 | 18106 | 100 | 120 | 100 | 100 | 104.8106 | 100
15 | lichte scheidingswanden 1 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 2016-05-20 08:00 | 10d | 4627 | 0 | 0 | -427 | 0 | 4200 | 0 | 100% | Finished | 4627 | 4627 | 100 | 100 | 100 | 100 | 90.7716 | 100
16 | vloer uitvullingen 1 B | 2016-05-26 08:00 | 2016-05-30 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2016-06-03 08:00 | 5d | 3017 | 0 | 0 | 616 | 0 | 3633 | 0 | 100% | Finished | 3017 | 3017 | 100 | 166.6667 | 100 | 100 | 120.4176 | 100
17 | chape 1 B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 2016-06-10 08:00 | 5d | 26153 | 0 | 0 | 375 | 0 | 26528 | 0 | 100% | Finished | 26153 | 26153 | 100 | 100 | 100 | 100 | 101.4339 | 100
18 | plaatsen keramsiche tegels 1 B | 2016-06-21 08:00 | 2016-07-04 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 | 2016-07-01 08:00 | 10d | 10964 | 0 | 0 | 1096 | 0 | 12060 | 0 | 100% | Finished | 10964 | 10964 | 100 | 100 | 100 | 100 | 109.9964 | 100
19 | plaatsen faience 1 B | 2016-06-28 08:00 | 2016-07-11 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 | 2016-07-08 08:00 | 10d | 10059 | 0 | 0 | 558 | 0 | 10617 | 0 | 100% | Finished | 10059 | 10059 | 100 | 100 | 100 | 100 | 105.5473 | 100
20 | zachte vloerbekleding 1 B | 2016-07-19 08:00 | 2016-08-01 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 | 2016-07-29 08:00 | 10d | 8047 | 0 | 0 | -29 | 0 | 8018 | 0 | 100% | Finished | 8047 | 8047 | 100 | 100 | 100 | 100 | 99.6396 | 100
21 | binnenschrijnwerk 1B | 2016-08-02 08:00 | 2016-08-11 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 |  | 0 | 0 | 28165 | 8d | 0 | 0 | 0 | 28165 | 0% | Not Started | 0 | 28165 | 100 |  | 0 | 100 |  | 0
22 | schilderwerken wanden en plafonds 1B | 2016-08-02 08:00 | 2016-08-29 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 |  | 0 | 0 | 24142 | 20d | 0 | 0 | 0 | 24142 | 0% | Not Started | 0 | 24142 | 100 |  | 0 | 100 |  | 0
24 | binnenmeubilair 1B | 2016-08-02 08:00 | 2016-08-15 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 |  | 0 | 0 | 30177 | 10d | 0 | 0 | 0 | 30177 | 0% | Not Started | 0 | 30177 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-09-15 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (3) | 2016-03-21 08:00 | 2016-08-29 17:00 | 116d |  |  | 377282 |  |  | 377282 |  | 129d | [5 empty] | 394829 |  | 100% |  | 377282 | 377282
25 | gelijkvloers blok B | 2016-03-21 08:00 | 2016-07-20 17:00 | 88d |  |  | 199743 |  |  | 199743 |  | 97d | [5 empty] | 204250 |  | 100% |  | 199743 | 199743
1 | pleisterwerken wanden 0 B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 15239 | 0 | 0 | 15239 | 2016-03-21 08:00 | 18d | 15239 | 0 | 0 | -87 | 0 | 15152 | 0 | 100% | Finished | 15239 | 15239 | 100 | 120 | 100 | 100 | 99.4291 | 100
2 | pleisterwerken plafonds 0 B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 19593 | 0 | 0 | 19593 | 2016-03-21 08:00 | 7d | 19593 | 0 | 0 | 3828 | 0 | 23421 | 0 | 100% | Finished | 19593 | 19593 | 100 | 140 | 100 | 100 | 119.5376 | 100
3 | lichte scheidingswanden 0 B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 5007 | 0 | 0 | 5007 | 2016-03-23 08:00 | 10d | 5007 | 0 | 0 | 148 | 0 | 5155 | 0 | 100% | Finished | 5007 | 5007 | 100 | 100 | 100 | 100 | 102.9559 | 100
4 | gespoten PU isolaie en uitvullingen 0 B | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 7619 | 0 | 0 | 7619 | 2016-04-06 08:00 | 5d | 7619 | 0 | 0 | 1470 | 0 | 9089 | 0 | 100% | Finished | 7619 | 7619 | 100 | 166.6667 | 100 | 100 | 119.2939 | 100
5 | chape 0 B | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 3265 | 0 | 0 | 3265 | 2016-04-13 08:00 | 5d | 3265 | 0 | 0 | 206 | 0 | 3471 | 0 | 100% | Finished | 3265 | 3265 | 100 | 100 | 100 | 100 | 106.3093 | 100
6 | plaatsen keramsiche tegels 0 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 28302 | 0 | 0 | 28302 | 2016-05-18 08:00 | 10d | 28302 | 0 | 0 | -1014 | 0 | 27288 | 0 | 100% | Finished | 28302 | 28302 | 100 | 100 | 100 | 100 | 96.4172 | 100
7 | plaatsen faience 0 B | 2016-05-19 08:00 | 2016-06-01 17:00 | 10d |  | 0 | 11865 | 0 | 0 | 11865 | 2016-05-25 08:00 | 10d | 11865 | 0 | 0 | -713 | 0 | 11152 | 0 | 100% | Finished | 11865 | 11865 | 100 | 100 | 100 | 100 | 93.9907 | 100
8 | verlaagde plafonds 0 B | 2016-05-05 08:00 | 2016-06-01 17:00 | 20d |  | 0 | 10885 | 0 | 0 | 10885 | 2016-05-11 08:00 | 20d | 10885 | 0 | 0 | 352 | 0 | 11237 | 0 | 100% | Finished | 10885 | 10885 | 100 | 100 | 100 | 100 | 103.2338 | 100
9 | zachte vloerbekleding 0 B | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 8708 | 0 | 0 | 8708 | 2016-06-15 08:00 | 10d | 8708 | 0 | 0 | -500 | 0 | 8208 | 0 | 100% | Finished | 8708 | 8708 | 100 | 100 | 100 | 100 | 94.2582 | 100
10 | binnenschrijnwerk 0 B | 2016-06-23 08:00 | 2016-07-04 17:00 | 8d |  | 0 | 30479 | 0 | 0 | 30479 | 2016-06-29 08:00 | 10d | 30479 | 0 | 0 | -370 | 0 | 30109 | 0 | 100% | Finished | 30479 | 30479 | 100 | 125 | 100 | 100 | 98.786 | 100
11 | schilderwerken wanden en plafonds 0 B | 2016-06-23 08:00 | 2016-07-20 17:00 | 20d |  | 0 | 26125 | 0 | 0 | 26125 | 2016-06-29 08:00 | 25d | 26125 | 0 | 0 | 1412 | 0 | 27537 | 0 | 100% | Finished | 26125 | 26125 | 100 | 125 | 100 | 100 | 105.4048 | 100
12 | binnenmeubilair 0 B | 2016-06-23 08:00 | 2016-07-06 17:00 | 10d |  | 0 | 32656 | 0 | 0 | 32656 | 2016-06-29 08:00 | 10d | 32656 | 0 | 0 | -225 | 0 | 32431 | 0 | 100% | Finished | 32656 | 32656 | 100 | 100 | 100 | 100 | 99.311 | 100
26 | nivo +1 blok B | 2016-05-05 08:00 | 2016-08-29 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 92d | [5 empty] | 190579 |  | 100% |  | 177539 | 177539
13 | pleisterwerken wanden 1 B | 2016-05-05 08:00 | 2016-05-25 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 2016-05-11 08:00 | 18d | 14082 | 0 | 0 | 2028 | 0 | 16110 | 0 | 100% | Finished | 14082 | 14082 | 100 | 120 | 100 | 100 | 114.4014 | 100
14 | pleisterwerken plafonds 1 B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 2016-05-11 08:00 | 12d | 18106 | 0 | 0 | 871 | 0 | 18977 | 0 | 100% | Finished | 18106 | 18106 | 100 | 120 | 100 | 100 | 104.8106 | 100
15 | lichte scheidingswanden 1 B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 2016-05-20 08:00 | 10d | 4627 | 0 | 0 | -427 | 0 | 4200 | 0 | 100% | Finished | 4627 | 4627 | 100 | 100 | 100 | 100 | 90.7716 | 100
16 | vloer uitvullingen 1 B | 2016-05-26 08:00 | 2016-05-30 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2016-06-03 08:00 | 5d | 3017 | 0 | 0 | 616 | 0 | 3633 | 0 | 100% | Finished | 3017 | 3017 | 100 | 166.6667 | 100 | 100 | 120.4176 | 100
17 | chape 1 B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 2016-06-10 08:00 | 5d | 26153 | 0 | 0 | 375 | 0 | 26528 | 0 | 100% | Finished | 26153 | 26153 | 100 | 100 | 100 | 100 | 101.4339 | 100
18 | plaatsen keramsiche tegels 1 B | 2016-06-21 08:00 | 2016-07-04 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 | 2016-07-01 08:00 | 10d | 10964 | 0 | 0 | 1096 | 0 | 12060 | 0 | 100% | Finished | 10964 | 10964 | 100 | 100 | 100 | 100 | 109.9964 | 100
19 | plaatsen faience 1 B | 2016-06-28 08:00 | 2016-07-11 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 | 2016-07-08 08:00 | 10d | 10059 | 0 | 0 | 558 | 0 | 10617 | 0 | 100% | Finished | 10059 | 10059 | 100 | 100 | 100 | 100 | 105.5473 | 100
20 | zachte vloerbekleding 1 B | 2016-07-19 08:00 | 2016-08-01 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 | 2016-07-29 08:00 | 10d | 8047 | 0 | 0 | -29 | 0 | 8018 | 0 | 100% | Finished | 8047 | 8047 | 100 | 100 | 100 | 100 | 99.6396 | 100
21 | binnenschrijnwerk 1B | 2016-08-02 08:00 | 2016-08-11 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 | 2016-08-12 08:00 | 10d | 28165 | 0 | 0 | 5130 | 0 | 33295 | 0 | 100% | Finished | 28165 | 28165 | 100 | 125 | 100 | 100 | 118.2141 | 100
22 | schilderwerken wanden en plafonds 1B | 2016-08-02 08:00 | 2016-08-29 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 | 2016-08-12 08:00 | 25d | 24142 | 0 | 0 | 4109 | 0 | 28251 | 0 | 100% | Finished | 24142 | 24142 | 100 | 125 | 100 | 100 | 117.0201 | 100
24 | binnenmeubilair 1B | 2016-08-02 08:00 | 2016-08-15 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 | 2016-08-12 08:00 | 10d | 30177 | 0 | 0 | -1287 | 0 | 28890 | 0 | 100% | Finished | 30177 | 30177 | 100 | 100 | 100 | 100 | 95.7352 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-21 08:00 | 2016-05-11 08:00 | 93796 | 50723 | 56288 | 2016-05-04 17:00 | -43073 | 54.08% | -5565 | 90.11% | -4d | 89.19% | 100% | 2016-09-16 10:00 | 2017-01-13 12:00 | 2017-02-15 17:00 | 2016-09-21 17:00 | 2017-01-13 12:00 | 2017-02-09 17:00 | 2016-09-02 17:00 | 2016-09-16 17:00 | 2016-10-03 10:00 | 382847 | 418674.9446 | 660154.6476 | 422429.9091 | 726406.9965 | 462600.6349 | 450177.3585 | 419419.7634 | 0.89189 | 0.90113 | 0.54078 | 1 | -4 | 0.90113 | 1 | 0.89189 | 1
Tracking Period 2 | 2016-05-11 08:00 | 2016-06-29 08:00 | 286751 | 176468 | 183621 | 2016-06-20 17:00 | -110283 | 61.54% | -7153 | 96.1% | -6d | 91.67% | 100% | 2016-10-14 16:00 | 2016-12-08 12:00 | 2016-12-20 09:00 | 2016-10-06 15:00 | 2016-12-08 12:00 | 2016-12-15 10:00 | 2016-09-06 17:00 | 2016-09-13 12:00 | 2016-09-15 15:00 | 384435 | 392574.8471 | 509932.9394 | 402690.8182 | 523159.7527 | 411570.6514 | 408769.8008 | 394522.6047 | 0.91667 | 0.96104 | 0.61541 | 1 | -6 | 0.96104 | 1 | 0.91667 | 1
Tracking Period 3 | 2016-06-29 08:00 | 2016-08-12 08:00 | 377282 | 294798 | 304393 | 2016-08-01 17:00 | -82484 | 78.14% | -9595 | 96.85% | -8d | 92.31% | 100% | 2016-10-04 11:00 | 2016-10-13 12:00 | 2016-10-20 10:00 | 2016-09-29 15:00 | 2016-10-13 12:00 | 2016-10-14 16:00 | 2016-09-08 17:00 | 2016-09-12 14:00 | 2016-09-13 11:00 | 386877 | 389561.6654 | 409955.8888 | 393750.6667 | 413391.7191 | 396659.0541 | 392984.7627 | 390367.748 | 0.92308 | 0.96848 | 0.78137 | 1 | -8 | 0.96848 | 1 | 0.92308 | 1
Tracking Period 4 | 2016-08-12 08:00 | 2016-09-15 17:00 | 377282 | 377282 | 394829 | 2016-08-29 17:00 | 0 | 100% | -17547 | 95.56% | -13d | 89.92% | 100% | 2016-08-29 17:00 | 2016-08-29 17:00 | 2016-09-06 11:00 | 2016-09-15 17:00 | 2016-09-15 17:00 | 2016-09-15 17:00 | 2016-09-15 17:00 | 2016-09-15 17:00 | 2016-09-15 17:00 | 394829 | 394829 | 394829 | 394829 | 394829 | 394829 | 394829 | 394829 | 0.89922 | 0.95556 | 1 | 1 | -13 | 0.95556 | 1 | 0.89922 | 1