## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | start | [8 empty] | 7612805.1487
2 | DO1 Diksmuidelaan TS111 | [12 empty] | Legend
4 | Engineering |  |  | FS5 | 2020-02-03 08:00 |  | 10d |  |  | 52408.6267 |  | 0 |  |  | Necessary input
5 | Place orders |  | 4FS | FS6;FS7 | 2020-02-17 08:00 |  | 5d |  |  | 26204.3133 |  | 0 |  |  | Additional input
6 | Lead time LS |  | 5FS | FS8 | 2020-02-24 08:00 |  | 30d |  |  | 157225.88 |  | 0 |  |  | Output
7 | Lead time MS |  | 5FS | FS8 | 2020-02-24 08:00 |  | 80d |  |  | 419269.0133 |  | 0
8 | Montage |  | 6FS;7FS | FS9 | 2020-06-15 08:00 |  | 15d |  |  | 78612.94 |  | 0 |  | For further explanation, see Guideline for project data input
9 | Pre-SAT |  | 8FS | FS10 | 2020-07-06 08:00 |  | 8d |  |  | 41926.9013 |  | 0
10 | SAT |  | 9FS | FS11 | 2020-07-16 08:00 |  | 2d |  |  | 10481.7253 |  | 0
11 | Packing, Transport and Delivery |  | 10FS |  | 2020-07-20 08:00 |  | 5d |  |  | 26204.3133 |  | 0
12 | DO1: REC
13 | Technical clarification & Engineering |  |  | FS14 | 2020-02-03 08:00 |  | 10d |  |  | 52408.6267 |  | 0
14 | Production |  | 13FS | FS15 | 2020-02-17 08:00 |  | 100d |  |  | 524086.2667 |  | 0
15 | Transport & Delivery |  | 14FS |  | 2020-07-06 08:00 |  | 5d |  |  | 26204.3133 |  | 0
16 | DO1: Pole Disconnector
17 | Technical Clarification |  |  | FS18 | 2020-02-03 08:00 |  | 20d |  |  | 104817.2533 |  | 0
18 | Prototype: Engineering, Production & Testing |  | 17FS | SS21 | 2020-03-02 08:00 |  | 40d |  |  | 209634.5067 |  | 0
19 | DO2 Populierenlaan TS107 - ombouw MOB TS198
21 | MS |  | 18SS | SS22 | 2020-03-02 08:00 |  | 125d |  |  | 228088.8711 |  | 0
22 | Engineering |  | 21SS | FS23 | 2020-03-02 08:00 |  | 10d |  |  | 18247.1097 |  | 0
23 | Place orders |  | 22FS | FS24;FS25 | 2020-03-16 08:00 |  | 5d |  |  | 9123.5548 |  | 0
24 | Lead time LS |  | 23FS | FS26 | 2020-03-23 08:00 |  | 30d |  |  | 54741.3291 |  | 0
25 | Lead time MS |  | 23FS | FS26 | 2020-03-23 08:00 |  | 80d |  |  | 145976.8775 |  | 0
26 | Montage |  | 24FS;25FS | FS27 | 2020-07-13 08:00 |  | 15d |  |  | 27370.6645 |  | 0
27 | Pre-SAT |  | 26FS | FS28 | 2020-08-03 08:00 |  | 8d |  |  | 14597.6877 |  | 0
28 | SAT |  | 27FS | FS29 | 2020-08-13 08:00 |  | 2d |  |  | 3649.4219 |  | 0
29 | Packing, Transport and Delivery |  | 28FS |  | 2020-08-17 08:00 |  | 5d |  |  | 9123.5548 |  | 0
30 | REC |  |  |  | 2020-03-02 08:00 |  | 115d |  |  | 209841.7614 |  | 0
31 | Technical clarification & Engineering |  |  | FS32 | 2020-03-02 08:00 |  | 10d |  |  | 18247.1097 |  | 0
32 | Production |  | 31FS | FS33 | 2020-03-16 08:00 |  | 30d |  |  | 54741.3291 |  | 0
33 | Transport & Delivery |  | 32FS |  | 2020-08-03 08:00 |  | 5d |  |  | 9123.5548 |  | 0
34 | DO2: Populierenlaan TS107
35 | MS |  |  |  | 2020-05-04 08:00 |  | 125d |  |  | 228088.8711 |  | 0
36 | Engineering |  |  | FS37 | 2020-05-04 08:00 |  | 10d |  |  | 18247.1097 |  | 0
37 | Place orders |  | 36FS | FS38;FS39 | 2020-05-18 08:00 |  | 5d |  |  | 9123.5548 |  | 0
38 | Lead time LS |  | 37FS | FS40 | 2020-05-25 08:00 |  | 30d |  |  | 54741.3291 |  | 0
39 | Lead time MS |  | 37FS | FS40 | 2020-05-25 08:00 |  | 80d |  |  | 145976.8775 |  | 0
40 | Montage |  | 38FS;39FS | FS41 | 2020-09-14 08:00 |  | 15d |  |  | 27370.6645 |  | 0
41 | Pre-SAT |  | 40FS | FS42 | 2020-10-05 08:00 |  | 8d |  |  | 14597.6877 |  | 0
42 | SAT |  | 41FS | FS43 | 2020-10-15 08:00 |  | 2d |  |  | 3649.4219 |  | 0
43 | Packing, Transport and Delivery |  | 42FS |  | 2020-10-19 08:00 |  | 5d |  |  | 9123.5548 |  | 0
44 | REC |  |  |  | 2020-05-04 08:00 |  | 115d |  |  | 209841.7614 |  | 0
45 | Technical clarification & Engineering |  |  | FS46 | 2020-05-04 08:00 |  | 10d |  |  | 18247.1097 |  | 0
46 | Production |  | 45FS | FS47 | 2020-05-18 08:00 |  | 100d |  |  | 182471.0968 |  | 0
47 | Transport & Delivery |  | 46FS |  | 2020-10-05 08:00 |  | 5d |  |  | 9123.5548 |  | 0
48 | DO3 Heidestraat TS148
50 | Engineering |  |  | FS51 | 2020-08-03 08:00 |  | 10d |  |  | 47994.6715 |  | 0
51 | Place orders |  | 50FS | FS52;FS53 | 2020-08-17 08:00 |  | 5d |  |  | 23997.3357 |  | 0
52 | Lead time LS |  | 51FS | FS54 | 2020-08-24 08:00 |  | 30d |  |  | 143984.0144 |  | 0
53 | Lead time MS |  | 51FS | FS54 | 2020-08-24 08:00 |  | 80d |  |  | 383957.3719 |  | 0
54 | Montage |  | 52FS;53FS | FS55 | 2020-12-14 08:00 |  | 15d |  |  | 71992.0072 |  | 0
55 | Pre-SAT |  | 54FS | FS56 | 2021-01-04 08:00 |  | 8d |  |  | 38395.7372 |  | 0
56 | SAT |  | 55FS | FS57 | 2021-01-14 08:00 |  | 2d |  |  | 9598.9343 |  | 0
57 | Packing, Transport and Delivery |  | 56FS |  | 2021-01-18 08:00 |  | 5d |  |  | 23997.3357 |  | 0
58 | DO3: REC
59 | Technical clarification & Engineering |  |  | FS60 | 2020-08-03 08:00 |  | 10d |  |  | 47994.6715 |  | 0
60 | Production |  | 59FS | FS61 | 2020-08-17 08:00 |  | 100d |  |  | 479946.7148 |  | 0
61 | Transport & Delivery |  | 60FS |  | 2021-01-04 08:00 |  | 5d |  |  | 23997.3357 |  | 0
62 | DO4 Steynstraat TS149
64 | Engineering |  |  | FS65 | 2020-11-02 08:00 |  | 10d |  |  | 54558.0707 |  | 0
65 | Place orders |  | 64FS | FS66;FS67 | 2020-11-16 08:00 |  | 5d |  |  | 27279.0354 |  | 0
66 | Lead time LS |  | 65FS | FS68 | 2020-11-23 08:00 |  | 30d |  |  | 163674.2122 |  | 0
67 | Lead time MS |  | 65FS | FS68 | 2020-11-23 08:00 |  | 80d |  |  | 436464.5659 |  | 0
68 | Montage |  | 66FS;67FS | FS69 | 2021-03-15 08:00 |  | 15d |  |  | 81837.1061 |  | 0
69 | Pre-SAT |  | 68FS | FS70 | 2021-04-05 08:00 |  | 8d |  |  | 43646.4566 |  | 0
70 | SAT |  | 69FS | FS71 | 2021-04-15 08:00 |  | 2d |  |  | 10911.6141 |  | 0
71 | Packing, Transport and Delivery |  | 70FS |  | 2021-04-19 08:00 |  | 5d |  |  | 27279.0354 |  | 0
72 | DO4: REC
73 | Technical clarification & Engineering |  |  | FS74 | 2020-11-02 08:00 |  | 10d |  |  | 54558.0707 |  | 0
74 | Production |  | 73FS | FS75 | 2020-11-16 08:00 |  | 100d |  |  | 545580.7074 |  | 0
75 | Transport & Delivery |  | 74FS |  | 2021-04-05 08:00 |  | 5d |  |  | 27279.0354 |  | 0
76 | DO5 Schotensesteenweg TS108
78 | Engineering |  |  | FS79 | 2021-02-01 08:00 |  | 10d |  |  | 51145.2225 |  | 0
79 | Place orders |  | 78FS | FS80;FS81 | 2021-02-15 08:00 |  | 5d |  |  | 25572.6113 |  | 0
80 | Lead time LS |  | 79FS | FS82 | 2021-02-22 08:00 |  | 30d |  |  | 153435.6676 |  | 0
81 | Lead time MS |  | 79FS | FS82 | 2021-02-22 08:00 |  | 80d |  |  | 409161.7804 |  | 0
82 | Montage |  | 80FS;81FS | FS83 | 2021-06-14 08:00 |  | 15d |  |  | 76717.8338 |  | 0
83 | Pre-SAT |  | 82FS | FS84 | 2021-07-05 08:00 |  | 8d |  |  | 40916.178 |  | 0
84 | SAT |  | 83FS | FS85 | 2021-07-15 08:00 |  | 2d |  |  | 10229.0445 |  | 0
85 | Packing, Transport and Delivery |  | 84FS |  | 2021-07-19 08:00 |  | 5d |  |  | 25572.6113 |  | 0
86 | DO5: REC
87 | Technical clarification & Engineering |  |  | FS88 | 2021-02-01 08:00 |  | 10d |  |  | 51145.2225 |  | 0
88 | Production |  | 87FS | FS89 | 2021-02-15 08:00 |  | 100d |  |  | 511452.2255 |  | 0
89 | Transport & Delivery |  | 88FS |  | 2021-07-05 08:00 |  | 5d |  |  | 25572.6113 |  | 0
89 | Transport & Delivery |  | 88FS |  | 2021-07-05 08:00 |  | 5d |  |  | 25572.6113 |  | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availibility | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | start
2 | DO1 Diksmuidelaan TS111
4 | Engineering |  | standard - symmetric | 80 | 100 | 120
5 | Place orders |  | standard - symmetric | 80 | 100 | 120
6 | Lead time LS |  | standard - symmetric | 80 | 100 | 120
7 | Lead time MS |  | standard - symmetric | 80 | 100 | 120
8 | Montage |  | standard - symmetric | 80 | 100 | 120
9 | Pre-SAT |  | standard - symmetric | 80 | 100 | 120
10 | SAT |  | standard - symmetric | 80 | 100 | 120
11 | Packing, Transport and Delivery |  | standard - symmetric | 80 | 100 | 120
12 | DO1: REC
13 | Technical clarification & Engineering |  | standard - symmetric | 80 | 100 | 120
14 | Production |  | standard - symmetric | 80 | 100 | 120
15 | Transport & Delivery |  | standard - symmetric | 80 | 100 | 120
16 | DO1: Pole Disconnector
17 | Technical Clarification |  | standard - symmetric | 80 | 100 | 120
18 | Prototype: Engineering, Production & Testing |  | standard - symmetric | 80 | 100 | 120
19 | DO2 Populierenlaan TS107 - ombouw MOB TS198
21 | MS |  | standard - symmetric | 80 | 100 | 120
22 | Engineering |  | standard - symmetric | 80 | 100 | 120
23 | Place orders |  | standard - symmetric | 80 | 100 | 120
24 | Lead time LS |  | standard - symmetric | 80 | 100 | 120
25 | Lead time MS |  | standard - symmetric | 80 | 100 | 120
26 | Montage |  | standard - symmetric | 80 | 100 | 120
27 | Pre-SAT |  | standard - symmetric | 80 | 100 | 120
28 | SAT |  | standard - symmetric | 80 | 100 | 120
29 | Packing, Transport and Delivery |  | standard - symmetric | 80 | 100 | 120
30 | REC |  | standard - symmetric | 80 | 100 | 120
31 | Technical clarification & Engineering |  | standard - symmetric | 80 | 100 | 120
32 | Production |  | standard - symmetric | 80 | 100 | 120
33 | Transport & Delivery |  | standard - symmetric | 80 | 100 | 120
34 | DO2: Populierenlaan TS107
35 | MS |  | standard - symmetric | 80 | 100 | 120
36 | Engineering |  | standard - symmetric | 80 | 100 | 120
37 | Place orders |  | standard - symmetric | 80 | 100 | 120
38 | Lead time LS |  | standard - symmetric | 80 | 100 | 120
39 | Lead time MS |  | standard - symmetric | 80 | 100 | 120
40 | Montage |  | standard - symmetric | 80 | 100 | 120
41 | Pre-SAT |  | standard - symmetric | 80 | 100 | 120
42 | SAT |  | standard - symmetric | 80 | 100 | 120
43 | Packing, Transport and Delivery |  | standard - symmetric | 80 | 100 | 120
44 | REC |  | standard - symmetric | 80 | 100 | 120
45 | Technical clarification & Engineering |  | standard - symmetric | 80 | 100 | 120
46 | Production |  | standard - symmetric | 80 | 100 | 120
47 | Transport & Delivery |  | standard - symmetric | 80 | 100 | 120
48 | DO3 Heidestraat TS148
50 | Engineering |  | standard - symmetric | 80 | 100 | 120
51 | Place orders |  | standard - symmetric | 80 | 100 | 120
52 | Lead time LS |  | standard - symmetric | 80 | 100 | 120
53 | Lead time MS |  | standard - symmetric | 80 | 100 | 120
54 | Montage |  | standard - symmetric | 80 | 100 | 120
55 | Pre-SAT |  | standard - symmetric | 80 | 100 | 120
56 | SAT |  | standard - symmetric | 80 | 100 | 120
57 | Packing, Transport and Delivery |  | standard - symmetric | 80 | 100 | 120
58 | DO3: REC
59 | Technical clarification & Engineering |  | standard - symmetric | 80 | 100 | 120
60 | Production |  | standard - symmetric | 80 | 100 | 120
61 | Transport & Delivery |  | standard - symmetric | 80 | 100 | 120
62 | DO4 Steynstraat TS149
64 | Engineering |  | standard - symmetric | 80 | 100 | 120
65 | Place orders |  | standard - symmetric | 80 | 100 | 120
66 | Lead time LS |  | standard - symmetric | 80 | 100 | 120
67 | Lead time MS |  | standard - symmetric | 80 | 100 | 120
68 | Montage |  | standard - symmetric | 80 | 100 | 120
69 | Pre-SAT |  | standard - symmetric | 80 | 100 | 120
70 | SAT |  | standard - symmetric | 80 | 100 | 120
71 | Packing, Transport and Delivery |  | standard - symmetric | 80 | 100 | 120
72 | DO4: REC
73 | Technical clarification & Engineering |  | standard - symmetric | 80 | 100 | 120
74 | Production |  | standard - symmetric | 80 | 100 | 120
75 | Transport & Delivery |  | standard - symmetric | 80 | 100 | 120
76 | DO5 Schotensesteenweg TS108
78 | Engineering |  | standard - symmetric | 80 | 100 | 120
79 | Place orders |  | standard - symmetric | 80 | 100 | 120
80 | Lead time LS |  | standard - symmetric | 80 | 100 | 120
81 | Lead time MS |  | standard - symmetric | 80 | 100 | 120
82 | Montage |  | standard - symmetric | 80 | 100 | 120
83 | Pre-SAT |  | standard - symmetric | 80 | 100 | 120
84 | SAT |  | standard - symmetric | 80 | 100 | 120
85 | Packing, Transport and Delivery |  | standard - symmetric | 80 | 100 | 120
86 | DO5: REC
87 | Technical clarification & Engineering |  | standard - symmetric | 80 | 100 | 120
88 | Production |  | standard - symmetric | 80 | 100 | 120
89 | Transport & Delivery |  | standard - symmetric | 80 | 100 | 120
89 | Transport & Delivery |  | standard - symmetric | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2020-03-01 17:00 |  | TP Name | start project
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | start
2 | DO1 Diksmuidelaan TS111
4 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
5 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
6 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
7 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
8 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
9 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
10 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
11 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
12 | DO1: REC
13 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
14 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
15 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
16 | DO1: Pole Disconnector
17 | Technical Clarification | [10 empty] | 0 | [5 empty] | 0 |  | 0%
18 | Prototype: Engineering, Production & Testing | [10 empty] | 0 | [5 empty] | 0 |  | 0%
19 | DO2 Populierenlaan TS107 - ombouw MOB TS198
21 | MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
22 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
23 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
24 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
25 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
26 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
27 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
28 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
29 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
30 | REC | [10 empty] | 0 | [5 empty] | 0 |  | 0%
31 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
32 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
33 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
34 | DO2: Populierenlaan TS107
35 | MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
36 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
37 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
38 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
39 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
40 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
41 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
42 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
43 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
44 | REC | [10 empty] | 0 | [5 empty] | 0 |  | 0%
45 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
46 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
47 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
48 | DO3 Heidestraat TS148
50 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
51 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
52 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
53 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
54 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
55 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
56 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
57 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
58 | DO3: REC
59 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
60 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
61 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
62 | DO4 Steynstraat TS149
64 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
65 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
66 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
67 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
68 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
69 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
70 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
71 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
72 | DO4: REC
73 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
74 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
75 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
76 | DO5 Schotensesteenweg TS108
78 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
79 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
80 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
81 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
82 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
83 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
84 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
85 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
86 | DO5: REC
87 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
88 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
89 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
89 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%

## TP2
| TP Status Date | 2020-09-30 |  | TP Name | opvolging 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | start
2 | DO1 Diksmuidelaan TS111
4 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
5 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
6 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
7 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
8 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
9 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
10 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
11 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
12 | DO1: REC
13 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
14 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
15 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
16 | DO1: Pole Disconnector
17 | Technical Clarification | [9 empty] | 2020-05-01 08:00 | 20d | [5 empty] | 104817.2533 |  | 100%
18 | Prototype: Engineering, Production & Testing | [9 empty] | 2020-05-29 08:00 | 60d | [5 empty] | 209634.5067 |  | 100%
19 | DO2 Populierenlaan TS107 - ombouw MOB TS198
21 | MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
22 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
23 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
24 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
25 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
26 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
27 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
28 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
29 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
30 | REC | [9 empty] | 2020-03-02 08:00 | 115d | [5 empty] | 209841.7614 |  | 100%
31 | Technical clarification & Engineering | [9 empty] | 2020-03-02 08:00 | 10d | [5 empty] | 18247.1097 |  | 100%
32 | Production | [9 empty] | 2020-03-16 08:00 | 30d | [5 empty] | 54741.3291 |  | 100%
33 | Transport & Delivery | [9 empty] | 2020-08-03 08:00 | 5d | [5 empty] | 9123.5548 |  | 100%
34 | DO2: Populierenlaan TS107
35 | MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
36 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
37 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
38 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
39 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
40 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
41 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
42 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
43 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
44 | REC | [10 empty] | 0 | [5 empty] | 0 |  | 0%
45 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
46 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
47 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
48 | DO3 Heidestraat TS148
50 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
51 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
52 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
53 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
54 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
55 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
56 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
57 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
58 | DO3: REC
59 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
60 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
61 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
62 | DO4 Steynstraat TS149
64 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
65 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
66 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
67 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
68 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
69 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
70 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
71 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
72 | DO4: REC
73 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
74 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
75 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
76 | DO5 Schotensesteenweg TS108
78 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
79 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
80 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
81 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
82 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
83 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
84 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
85 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
86 | DO5: REC
87 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
88 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
89 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
89 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%

## TP3
| TP Status Date | 2020-12-31 |  | TP Name | opvolging 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | start
2 | DO1 Diksmuidelaan TS111
4 | Engineering | [9 empty] | 2020-11-11 | 36d | [5 empty] | 23583.882 |  | 45%
5 | Place orders | [9 empty] | 2020-12-23 | 6d | [5 empty] | 26204.3133 |  | 100%
6 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
7 | Lead time MS | [9 empty] | 2020-12-30 | 1d | [5 empty] | 4192.6901 |  | 1%
8 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
9 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
10 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
11 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
12 | DO1: REC
13 | Technical clarification & Engineering | [9 empty] | 2020-10-01 | 65d | [5 empty] | 20963.4507 |  | 40%
14 | Production | [9 empty] | 2020-10-15 | 55d | [5 empty] | 288247.4467 |  | 55%
15 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
16 | DO1: Pole Disconnector
17 | Technical Clarification | [9 empty] | 2020-05-01 08:00 | 20d | [5 empty] | 104817.2533 |  | 100%
18 | Prototype: Engineering, Production & Testing | [9 empty] | 2020-05-29 08:00 | 60d | [5 empty] | 209634.5067 |  | 100%
19 | DO2 Populierenlaan TS107 - ombouw MOB TS198
21 | MS | [9 empty] | 2020-11-02 | 42d | [5 empty] | 72988.4387 |  | 32%
22 | Engineering | [9 empty] | 2020-11-02 | 42d | [5 empty] | 9488.497 |  | 52%
23 | Place orders | [9 empty] | 2020-12-14 | 5d | [5 empty] | 9123.5548 |  | 100%
24 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
25 | Lead time MS | [9 empty] | 2020-12-21 | 7d | [5 empty] | 11678.1502 |  | 8%
26 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
27 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
28 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
29 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
30 | REC | [9 empty] | 2020-03-02 08:00 | 115d | [5 empty] | 209841.7614 |  | 100%
31 | Technical clarification & Engineering | [9 empty] | 2020-03-02 08:00 | 10d | [5 empty] | 18247.1097 |  | 100%
32 | Production | [9 empty] | 2020-03-16 08:00 | 30d | [5 empty] | 54741.3291 |  | 100%
33 | Transport & Delivery | [9 empty] | 2020-08-03 08:00 | 5d | [5 empty] | 9123.5548 |  | 100%
34 | DO2: Populierenlaan TS107
35 | MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
36 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
37 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
38 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
39 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
40 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
41 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
42 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
43 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
44 | REC | [9 empty] | 2020-10-01 | 65d | [5 empty] | 62952.5284 |  | 30%
45 | Technical clarification & Engineering | [9 empty] | 2020-10-01 | 10d | [5 empty] | 18247.1097 |  | 100%
46 | Production | [9 empty] | 2020-10-15 | 55d | [5 empty] | 100359.1033 |  | 55%
47 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
48 | DO3 Heidestraat TS148
50 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
51 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
52 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
53 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
54 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
55 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
56 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
57 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
58 | DO3: REC
59 | Technical clarification & Engineering | [9 empty] | 2020-10-01 | 65d | [5 empty] | 19197.8686 |  | 40%
60 | Production | [9 empty] | 2020-10-15 | 55d | [5 empty] | 263970.6931 |  | 55%
61 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
62 | DO4 Steynstraat TS149
64 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
65 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
66 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
67 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
68 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
69 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
70 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
71 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
72 | DO4: REC
73 | Technical clarification & Engineering | [9 empty] | 2020-10-01 | 65d | [5 empty] | 21823.2283 |  | 40%
74 | Production | [9 empty] | 2020-10-15 | 55d | [5 empty] | 300069.3891 |  | 55%
75 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
76 | DO5 Schotensesteenweg TS108
78 | Engineering | [9 empty] | 2020-11-11 | 36d | [5 empty] | 23015.3501 |  | 45%
79 | Place orders | [9 empty] | 2020-12-23 | 6d | [5 empty] | 2045.8089 |  | 8%
80 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
81 | Lead time MS | [9 empty] | 2020-12-30 | 1d | [5 empty] | 4091.6178 |  | 1%
82 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
83 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
84 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
85 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
86 | DO5: REC
87 | Technical clarification & Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
88 | Production | [10 empty] | 0 | [5 empty] | 0 |  | 0%
89 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
89 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%

## TP4
| TP Status Date | 2021-03-12 |  | TP Name | opvolging 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | start
2 | DO1 Diksmuidelaan TS111
4 | Engineering | [9 empty] | 2020-11-11 | 80d | [5 empty] | 52408.6267 |  | 100%
5 | Place orders | [9 empty] | 2020-12-23 | 5d | [5 empty] | 26204.3133 |  | 100%
6 | Lead time LS | [9 empty] | 2021-02-24 | 30d | [5 empty] | 157225.88 |  | 100%
7 | Lead time MS | [9 empty] | 2020-12-30 | 96d | [5 empty] | 419269.0133 |  | 100%
8 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
9 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
10 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
11 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
12 | DO1: REC
13 | Technical clarification & Engineering | [9 empty] | 2020-10-01 | 162d | [5 empty] | 44547.3327 |  | 85%
14 | Production | [9 empty] | 2020-10-15 | 100d | [5 empty] | 524086.2667 |  | 100%
15 | Transport & Delivery | [9 empty] | 2021-03-04 | 5d | [5 empty] | 26204.3133 |  | 100%
16 | DO1: Pole Disconnector
17 | Technical Clarification | [9 empty] | 2020-05-01 08:00 | 20d | [5 empty] | 104817.2533 |  | 100%
18 | Prototype: Engineering, Production & Testing | [9 empty] | 2020-05-29 08:00 | 60d | [5 empty] | 209634.5067 |  | 100%
19 | DO2 Populierenlaan TS107 - ombouw MOB TS198
21 | MS | [9 empty] | 2020-11-02 | 130d | [5 empty] | 159662.2097 |  | 70%
22 | Engineering | [9 empty] | 2020-11-02 | 80d | [5 empty] | 18247.1097 |  | 100%
23 | Place orders | [9 empty] | 2020-12-14 | 5d | [5 empty] | 9123.5548 |  | 100%
24 | Lead time LS | [9 empty] | 2021-02-15 | 30d | [5 empty] | 54741.3291 |  | 100%
25 | Lead time MS | [9 empty] | 2020-12-21 | 96d | [5 empty] | 145976.8775 |  | 100%
26 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
27 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
28 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
29 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
30 | REC | [9 empty] | 2020-03-02 08:00 | 115d | [5 empty] | 209841.7614 |  | 100%
31 | Technical clarification & Engineering | [9 empty] | 2020-03-02 08:00 | 10d | [5 empty] | 18247.1097 |  | 100%
32 | Production | [9 empty] | 2020-03-16 08:00 | 30d | [5 empty] | 54741.3291 |  | 100%
33 | Transport & Delivery | [9 empty] | 2020-08-03 08:00 | 5d | [5 empty] | 9123.5548 |  | 100%
34 | DO2: Populierenlaan TS107
35 | MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
36 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
37 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
38 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
39 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
40 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
41 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
42 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
43 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
44 | REC | [9 empty] | 2020-10-01 | 160d | [5 empty] | 62952.5284 |  | 30%
45 | Technical clarification & Engineering | [9 empty] | 2020-10-01 | 10d | [5 empty] | 18247.1097 |  | 100%
46 | Production | [9 empty] | 2020-10-15 | 100d | [5 empty] | 182471.0968 |  | 100%
47 | Transport & Delivery | [9 empty] | 2021-03-04 | 5d | [5 empty] | 9123.5548 |  | 100%
48 | DO3 Heidestraat TS148
50 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
51 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
52 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
53 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
54 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
55 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
56 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
57 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
58 | DO3: REC
59 | Technical clarification & Engineering | [9 empty] | 2020-10-01 | 162d | [5 empty] | 47994.6715 |  | 100%
60 | Production | [9 empty] | 2020-10-15 | 100d | [5 empty] | 479946.7148 |  | 100%
61 | Transport & Delivery | [9 empty] | 2021-03-04 | 8d | [5 empty] | 23997.3357 |  | 100%
62 | DO4 Steynstraat TS149
64 | Engineering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
65 | Place orders | [10 empty] | 0 | [5 empty] | 0 |  | 0%
66 | Lead time LS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
67 | Lead time MS | [10 empty] | 0 | [5 empty] | 0 |  | 0%
68 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
69 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
70 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
71 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
72 | DO4: REC
73 | Technical clarification & Engineering | [9 empty] | 2020-10-01 | 162d | [5 empty] | 54558.0707 |  | 100%
74 | Production | [9 empty] | 2020-10-15 | 100d | [5 empty] | 545580.7074 |  | 100%
75 | Transport & Delivery | [9 empty] | 2021-03-04 | 5d | [5 empty] | 27279.0354 |  | 100%
76 | DO5 Schotensesteenweg TS108
78 | Engineering | [9 empty] | 2020-11-11 | 80d | [5 empty] | 51145.2225 |  | 100%
79 | Place orders | [9 empty] | 2020-12-23 | 79d | [5 empty] | 25572.6113 |  | 100%
80 | Lead time LS | [9 empty] | 2021-02-24 | 16d | [5 empty] | 153435.6676 |  | 100%
81 | Lead time MS | [9 empty] | 2020-12-30 | 72d | [5 empty] | 302779.7175 |  | 74%
82 | Montage | [10 empty] | 0 | [5 empty] | 0 |  | 0%
83 | Pre-SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
84 | SAT | [10 empty] | 0 | [5 empty] | 0 |  | 0%
85 | Packing, Transport and Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
86 | DO5: REC
87 | Technical clarification & Engineering | [9 empty] | 2021-02-01 08:00 | 10d | [5 empty] | 51145.2225 |  | 100%
88 | Production | [9 empty] | 2021-02-15 08:00 | 100d | [5 empty] | 511452.2255 |  | 100%
89 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%
89 | Transport & Delivery | [10 empty] | 0 | [5 empty] | 0 |  | 0%

## Agenda
Working Hours |  | Working Days |  | Holidays
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No