## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Pumping Station Jabbeke | 1 |  |  | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 | 172.375
1 | start plaatsing looplatform ALSB | 1.1 |  | FS2 | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 0.375
2 | start plaatsing RVS looplatform krooshekreiniger | 1.2 | 1FS | FS3 | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 0.375
3 | start plaatsing trap krooshekreiniger | 1.3 | 2FS | FS4 | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 0.375
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 1.4 | 3FS | FS5 | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 0.375
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 1.5 | 4FS | FS6;FS15 | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 0.375
6 | constructie ALSB in atelier | 1.6 | 5FS | FS13;SS7 | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 32.375
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 1.7 | 6SS | FS12;FS8 | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 0.375
8 | bespreken lay-out ALSB met Glenn | 1.8 | 7FS | FS9;FS10 | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 0.375
9 | bestellen lay-out ALSB | 1.9 | 8FS | FS13 | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 0.375
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 1.10 | 8FS | FS20;FS21;FS11 | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 1.375
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 1.11 | 10FS | FS17 | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 0.375
12 | programmatie en testen PLC en visualisatie atelier Decat | 1.12 | 7FS | FS13 | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2.375
13 | oplevering ALSB bij Decat door glenn Degros | 1.13 | 6FS;9FS;12FS | SS14 | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 4.375
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 1.14 | 13SS | FS16 | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 4.375
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 1.15 | 5FS | SS16 | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 4.375
16 | nazicht en uit testen door Glenn Degros | 1.16 | 14FS;15SS | SS19 | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 4.375
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 1.17 | 11FS | FS18 | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 1.375
18 | maken sleuf voor peilmeting stroomopwaarts | 1.18 | 17FS | FS19 | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 0.375
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 1.19 | 16SS;18FS | FS22 | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 5.375
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 1.20 | 10FS | FS25 | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 4.375
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 1.21 | 10FS | FS25 | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 0.375
22 | plaatsen platform peilmeting af en opwaarts | 1.22 | 19FS | FS23 | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 0.375
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 1.23 | 22FS | FS24 | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 0.375
24 | opstellen peilmetingen na de roosters | 1.24 | 23FS | FS26 | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 4.375
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 1.25 | 20FS;21FS | FS28;FS27 | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 4.375
26 | aansluitingen peilmetingen | 1.26 | 24FS | FS27 | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 1.375
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 1.27 | 25FS;26FS | FS29 | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 1.375
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 1.28 | 25FS | FS33 | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 4.375
29 | uitvoeren van de nodige aardingen | 1.29 | 27FS | FS30 | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 0.375
30 | ALSB onder spanning brengen | 1.30 | 29FS | FS31;FS42 | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 0.375
31 | omschakelen pomp 1 op nieuw ALSB | 1.31 | 30FS | SS32 | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 0.16667
32 | leveren en plaatsen werkschakelaar pomp 1 | 1.32 | 31SS | FS34 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 0.16667
33 | tussenwand tussen bureau en keuken | 1.33 | 28FS | FS35;FS37 | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 0.375
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 1.34 | 32FS | FS36 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 0.375
35 | leveren en plaatsen keukenblok | 1.35 | 33FS | FS37 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 0.375
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 1.36 | 34FS | FS38 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 0.375
37 | Verplaatsen boiler en aanpassen leidingen | 1.37 | 33FS;35FS | FS39 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 0.375
38 | aanpassen smeersysteem pomp 1 | 1.38 | 36FS | FS40 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 0.375
39 | geluidsdichte omkasting rond boiler | 1.39 | 37FS | FS60 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 0.375
40 | proefdraaien pomp 1 op nieuw ALSB | 1.40 | 38FS | SS41 | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 0.375
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 1.41 | 40SS | FS53;FS43 | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 4.375
42 | aansluiten installatie op Abba | 1.42 | 30FS | FS43 | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 0.375
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 1.43 | 41FS;42FS | FS44 | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 0.375
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 1.44 | 43FS | FS45 | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 0.375
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 1.45 | 44FS | FS46 | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 0.375
46 | aansluiten transportband op nieuw ALSB | 1.46 | 45FS | FS47 | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 0.375
47 | aansluiten noodstoppen op nieuw ALSB | 1.47 | 46FS | FS48 | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 0.375
48 | omschakelen pomp 2 op nieuw ALSB | 1.48 | 47FS | SS49 | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 0.16667
49 | leveren en plaatsen werkschakelaar pomp 2 | 1.49 | 48SS | FS50 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 0.16667
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 1.50 | 49FS | FS51 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 0.375
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 1.51 | 50FS | FS52 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 0.375
52 | aanpassen smeersysteem pomp 2 | 1.52 | 51FS | FS54 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 0.375
53 | leveren en plaatsen bekabeling noodschuiven | 1.53 | 41FS | SS55+1d | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 3.375
54 | proefdraaien pomp 2 op nieuw ALSB | 1.54 | 52FS | FS55 | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 0.375
55 | aansluiten noodschuif 1 + in dienst stellen | 1.55 | 53SS+1d;54FS | FS56 | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 0.375
56 | aansluiten noodschuif 2 + in dienst stellen | 1.56 | 55FS | FS57 | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 0.375
57 | aansluiten noodschuif 3 + in dienst stellen | 1.57 | 56FS | FS58;FS61 | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 0.375
58 | leveren en plaatsen seinborden | 1.58 | 57FS | SS59 | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 | 2.375
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 1.59 | 58SS |  | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 | 0.375
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 1.60 | 39FS | FS62 | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 3.375
61 | omschakelen pomp 3 op nieuw ALSB | 1.61 | 57FS | SS70;SS63 | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 | 0.16667
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 1.62 | 60FS | FS68 | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 4.375
63 | leveren en plaatsen werkschakelaar pomp 3 | 1.63 | 61SS | FS64 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 | 0.16667
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 1.64 | 63FS | FS65 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 | 0.375
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 1.65 | 64FS | FS66 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 | 0.375
66 | aanpassen smeersysteem pomp 3 | 1.66 | 65FS | FS67 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 | 0.375
67 | proefdraaien pomp 3 | 1.67 | 66FS | FS73 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 0.375
68 | leveren en installeren branddetectie | 1.68 | 62FS | FS69 | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 | 4.375
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 1.69 | 68FS | FS74;FS73 | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 | 9.375
70 | afbraak bestaand ALSB | 1.70 | 61SS | FS71 | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 | 0.375
71 | opmaken as built dossier elekriciteit en mechanica | 1.71 | 70FS | FS72 | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 | 1.375
72 | kabelnummering bord | 1.72 | 71FS | FS73 | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 | 1.375
73 | identificatie kabels en toestellen | 1.73 | 67FS;69FS;72FS |  | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 | 10.375
74 | schilderwerken | 1.74 | 69FS |  | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 | 10.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | ploeg 1&2 | Renewable | 2 | 0 | 93.75 | 1;2;3;4;5;6;7;8;9;12;13;14;16;17;18;19;20;22;23;24;25;26;27;28;29;30;31;32;33;34;35;36;37;38;39;40;41;42;43;44;45;46;47;48;49;50;51;52;53;54;55;56;57;58;59;60;61;62;63;64;65;66;67;68;69;70;71;72;73;74; | 127500
2 | vandezande | Renewable | 1 | 0 | 93.75 | 10;11;15;21; | 6750

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Pumping Station Jabbeke | 1000h |  |  |  |  | 99 | 100 | 101
1 | start plaatsing looplatform ALSB | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | start plaatsing RVS looplatform krooshekreiniger | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | start plaatsing trap krooshekreiniger | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | constructie ALSB in atelier | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | bespreken lay-out ALSB met Glenn | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | bestellen lay-out ALSB | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | programmatie en testen PLC en visualisatie atelier Decat | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | oplevering ALSB bij Decat door glenn Degros | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | nazicht en uit testen door Glenn Degros | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | maken sleuf voor peilmeting stroomopwaarts | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | plaatsen platform peilmeting af en opwaarts | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | opstellen peilmetingen na de roosters | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | aansluitingen peilmetingen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | uitvoeren van de nodige aardingen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | ALSB onder spanning brengen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | omschakelen pomp 1 op nieuw ALSB | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | leveren en plaatsen werkschakelaar pomp 1 | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | tussenwand tussen bureau en keuken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | leveren en plaatsen keukenblok | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Verplaatsen boiler en aanpassen leidingen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | aanpassen smeersysteem pomp 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | geluidsdichte omkasting rond boiler | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | proefdraaien pomp 1 op nieuw ALSB | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | aansluiten installatie op Abba | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | aansluiten transportband op nieuw ALSB | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | aansluiten noodstoppen op nieuw ALSB | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | omschakelen pomp 2 op nieuw ALSB | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | leveren en plaatsen werkschakelaar pomp 2 | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | aanpassen smeersysteem pomp 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | leveren en plaatsen bekabeling noodschuiven | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | proefdraaien pomp 2 op nieuw ALSB | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | aansluiten noodschuif 1 + in dienst stellen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | aansluiten noodschuif 2 + in dienst stellen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | aansluiten noodschuif 3 + in dienst stellen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | leveren en plaatsen seinborden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | omschakelen pomp 3 op nieuw ALSB | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | leveren en plaatsen werkschakelaar pomp 3 | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | aanpassen smeersysteem pomp 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | proefdraaien pomp 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | leveren en installeren branddetectie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | afbraak bestaand ALSB | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | opmaken as built dossier elekriciteit en mechanica | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | kabelnummering bord | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | identificatie kabels en toestellen | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | schilderwerken | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-01-09 08:00 |  | TP Name | 09/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 5d | [5 empty] | 54635 |  | 15.97% |  | 53725 | 53725
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 |  | 0 | 0 | 22250 | 25d | 0 | 0 | 0 | 22250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 |  | 0 | 0 | 1032 | 1d | 0 | 0 | 0 | 1032 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 |  | 0 | 0 | 790 | 1d | 0 | 0 | 0 | 790 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 |  | 0 | 0 | 1860 | 2d | 0 | 0 | 0 | 1860 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 |  | 0 | 0 | 4809 | 1d | 0 | 0 | 0 | 4809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 |  | 0 | 0 | 8943.52 | 3d | 0 | 0 | 0 | 8943.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 |  | 0 | 0 | 5341 | 5d | 0 | 0 | 0 | 5341 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 |  | 0 | 0 | 4865 | 5d | 0 | 0 | 0 | 4865 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 |  | 0 | 0 | 14536 | 5d | 0 | 0 | 0 | 14536 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 |  | 0 | 0 | 5634 | 5d | 0 | 0 | 0 | 5634 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 |  | 0 | 0 | 9216 | 2d | 0 | 0 | 0 | 9216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 |  | 0 | 0 | 1042 | 1d | 0 | 0 | 0 | 1042 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 |  | 0 | 0 | 4567 | 4d | 0 | 0 | 0 | 4567 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 |  | 0 | 0 | 6589 | 5d | 0 | 0 | 0 | 6589 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 |  | 0 | 0 | 2265 | 1d | 0 | 0 | 0 | 2265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 |  | 0 | 0 | 4247.29 | 1d | 0 | 0 | 0 | 4247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 1d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 3d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-01-16 08:00 |  | TP Name | 16/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 10d | [5 empty] | 62635 |  | 18.4% |  | 61912.5 | 60975
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 5d | 7250 | 11250 | 15d | 750 | 0 | 8000 | 11250 | 25% | Started | 8187.5 | 7250 | 100 | 20 | 25 | 100 | 35.9551 | 25
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 |  | 0 | 0 | 1032 | 1d | 0 | 0 | 0 | 1032 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 |  | 0 | 0 | 790 | 1d | 0 | 0 | 0 | 790 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 |  | 0 | 0 | 1860 | 2d | 0 | 0 | 0 | 1860 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 |  | 0 | 0 | 4809 | 1d | 0 | 0 | 0 | 4809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 |  | 0 | 0 | 8943.52 | 3d | 0 | 0 | 0 | 8943.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 |  | 0 | 0 | 5341 | 5d | 0 | 0 | 0 | 5341 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 |  | 0 | 0 | 4865 | 5d | 0 | 0 | 0 | 4865 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 |  | 0 | 0 | 14536 | 5d | 0 | 0 | 0 | 14536 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 |  | 0 | 0 | 5634 | 5d | 0 | 0 | 0 | 5634 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 |  | 0 | 0 | 9216 | 2d | 0 | 0 | 0 | 9216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 |  | 0 | 0 | 1042 | 1d | 0 | 0 | 0 | 1042 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 |  | 0 | 0 | 4567 | 4d | 0 | 0 | 0 | 4567 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 |  | 0 | 0 | 6589 | 5d | 0 | 0 | 0 | 6589 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 |  | 0 | 0 | 2265 | 1d | 0 | 0 | 0 | 2265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 |  | 0 | 0 | 4247.29 | 1d | 0 | 0 | 0 | 4247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 1d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 3d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2012-01-23 08:00 |  | TP Name | 23/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 15d | [5 empty] | 71356.5 |  | 21.11% |  | 71032 | 69157
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 10d | 11000 | 7500 | 10d | 750 | 0 | 11750 | 7500 | 50% | Started | 12875 | 11000 | 100 | 40 | 50 | 100 | 52.809 | 50
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 |  | 0 | 0 | 4809 | 1d | 0 | 0 | 0 | 4809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 |  | 0 | 0 | 8943.52 | 3d | 0 | 0 | 0 | 8943.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 |  | 0 | 0 | 5341 | 5d | 0 | 0 | 0 | 5341 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 |  | 0 | 0 | 4865 | 5d | 0 | 0 | 0 | 4865 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 |  | 0 | 0 | 14536 | 5d | 0 | 0 | 0 | 14536 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 |  | 0 | 0 | 5634 | 5d | 0 | 0 | 0 | 5634 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 |  | 0 | 0 | 9216 | 2d | 0 | 0 | 0 | 9216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 |  | 0 | 0 | 1042 | 1d | 0 | 0 | 0 | 1042 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 |  | 0 | 0 | 4567 | 4d | 0 | 0 | 0 | 4567 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 |  | 0 | 0 | 6589 | 5d | 0 | 0 | 0 | 6589 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 |  | 0 | 0 | 2265 | 1d | 0 | 0 | 0 | 2265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 |  | 0 | 0 | 4247.29 | 1d | 0 | 0 | 0 | 4247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 1d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 3d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2012-01-30 08:00 |  | TP Name | 30/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 20d | [5 empty] | 75106.5 |  | 22.51% |  | 75719.5 | 72907
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 15d | 14750 | 3750 | 5d | 750 | 0 | 15500 | 3750 | 75% | Started | 17562.5 | 14750 | 100 | 60 | 75 | 100 | 69.6629 | 75
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 |  | 0 | 0 | 4809 | 1d | 0 | 0 | 0 | 4809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 |  | 0 | 0 | 8943.52 | 3d | 0 | 0 | 0 | 8943.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 |  | 0 | 0 | 5341 | 5d | 0 | 0 | 0 | 5341 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 |  | 0 | 0 | 4865 | 5d | 0 | 0 | 0 | 4865 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 |  | 0 | 0 | 14536 | 5d | 0 | 0 | 0 | 14536 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 |  | 0 | 0 | 5634 | 5d | 0 | 0 | 0 | 5634 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 |  | 0 | 0 | 9216 | 2d | 0 | 0 | 0 | 9216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 |  | 0 | 0 | 1042 | 1d | 0 | 0 | 0 | 1042 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 |  | 0 | 0 | 4567 | 4d | 0 | 0 | 0 | 4567 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 |  | 0 | 0 | 6589 | 5d | 0 | 0 | 0 | 6589 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 |  | 0 | 0 | 2265 | 1d | 0 | 0 | 0 | 2265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 |  | 0 | 0 | 4247.29 | 1d | 0 | 0 | 0 | 4247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 1d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 3d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2012-02-06 08:00 |  | TP Name | 06/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 25d | [5 empty] | 87800.02 |  | 26.56% |  | 89350.52 | 76657
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 18500 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 |  | 0 | 0 | 4809 | 1d | 0 | 0 | 0 | 4809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 0 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 |  | 0 | 0 | 5341 | 5d | 0 | 0 | 0 | 5341 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 |  | 0 | 0 | 4865 | 5d | 0 | 0 | 0 | 4865 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 |  | 0 | 0 | 14536 | 5d | 0 | 0 | 0 | 14536 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 |  | 0 | 0 | 5634 | 5d | 0 | 0 | 0 | 5634 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 |  | 0 | 0 | 9216 | 2d | 0 | 0 | 0 | 9216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 |  | 0 | 0 | 1042 | 1d | 0 | 0 | 0 | 1042 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 |  | 0 | 0 | 4567 | 4d | 0 | 0 | 0 | 4567 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 |  | 0 | 0 | 6589 | 5d | 0 | 0 | 0 | 6589 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 |  | 0 | 0 | 2265 | 1d | 0 | 0 | 0 | 2265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 |  | 0 | 0 | 4247.29 | 1d | 0 | 0 | 0 | 4247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 1d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 3d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2012-02-13 08:00 |  | TP Name | 13/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 30d | [5 empty] | 103200.02 |  | 31.02% |  | 104365.52 | 94159.52
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 0 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 0 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 |  | 0 | 0 | 14536 | 5d | 0 | 0 | 0 | 14536 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 |  | 0 | 0 | 5634 | 5d | 0 | 0 | 0 | 5634 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 |  | 0 | 0 | 9216 | 2d | 0 | 0 | 0 | 9216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 |  | 0 | 0 | 1042 | 1d | 0 | 0 | 0 | 1042 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 |  | 0 | 0 | 4567 | 4d | 0 | 0 | 0 | 4567 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 |  | 0 | 0 | 6589 | 5d | 0 | 0 | 0 | 6589 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 |  | 0 | 0 | 2265 | 1d | 0 | 0 | 0 | 2265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 |  | 0 | 0 | 4247.29 | 1d | 0 | 0 | 0 | 4247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 1d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 3d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2012-02-20 08:00 |  | TP Name | 20/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 35d | [5 empty] | 123370.02 |  | 37.02% |  | 124535.52 | 99500.52
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 0 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 0 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 0 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 |  | 0 | 0 | 9216 | 2d | 0 | 0 | 0 | 9216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 |  | 0 | 0 | 1042 | 1d | 0 | 0 | 0 | 1042 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 |  | 0 | 0 | 4567 | 4d | 0 | 0 | 0 | 4567 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 |  | 0 | 0 | 6589 | 5d | 0 | 0 | 0 | 6589 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 |  | 0 | 0 | 2265 | 1d | 0 | 0 | 0 | 2265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 |  | 0 | 0 | 4247.29 | 1d | 0 | 0 | 0 | 4247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 1d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 3d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2012-02-27 08:00 |  | TP Name | 27/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 40d | [5 empty] | 143342.02 |  | 42.94% |  | 144449.52 | 118901.52
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 0 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 0 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 0 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 2d | 3067 | 1500 | 2d | 0 | 0 | 3067 | 1500 | 50% | Started | 3067 | 0 | 100 | 50 | 50 | 100 | 67.1557 | 50
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 0 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 |  | 0 | 0 | 2265 | 1d | 0 | 0 | 0 | 2265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 |  | 0 | 0 | 4247.29 | 1d | 0 | 0 | 0 | 4247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 1d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 3d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2012-03-05 08:00 |  | TP Name | 05/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 45d | [5 empty] | 160454.3101 |  | 47.99% |  | 161456.3902 | 137860.52
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 3067 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 0 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 0 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 0 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 0 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 1d | 3747.29 | 1500 | 2d | 152.71 | 0 | 3900 | 1500 | 33.33% | Started | 3747.2901 | 0 | 100 | 33.3333 | 33.3333 | 100 | 74.3241 | 33.3333
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 |  | 0 | 0 | 5247.29 | 2d | 0 | 0 | 0 | 5247.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2012-03-12 08:00 |  | TP Name | 12/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 50d | [5 empty] | 168154.3102 |  | 50% |  | 168203.6802 | 161456.3901
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 3747.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 |  | 0 | 0 | 45454.7891 | 5d | 0 | 0 | 0 | 45454.7891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 0 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2012-03-19 08:00 |  | TP Name | 19/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 55d | [5 empty] | 216154.3092 |  | 63.51% |  | 213658.4692 | 213658.4692
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 |  | 0 | 0 | 3358 | 2d | 0 | 0 | 0 | 3358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 |  | 0 | 0 | 1186.3 | 1d | 0 | 0 | 0 | 1186.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 |  | 0 | 0 | 1059 | 1d | 0 | 0 | 0 | 1059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 |  | 0 | 0 | 1564 | 1d | 0 | 0 | 0 | 1564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2012-03-26 08:00 |  | TP Name | 26/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 60d | [5 empty] | 224444.6092 |  | 65.64% |  | 220825.7692 | 224450.7692
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 |  | 0 | 0 | 5189 | 5d | 0 | 0 | 0 | 5189 | 0% | Not Started | 0 | 5189 | 100 |  | 0 | 100 |  | 0
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 |  | 0 | 0 | 1562.7 | 4h | 0 | 0 | 0 | 1562.7 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 |  | 0 | 0 | 1358 | 1d | 0 | 0 | 0 | 1358 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 |  | 0 | 0 | 1069 | 1d | 0 | 0 | 0 | 1069 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 |  | 0 | 0 | 1163.8 | 1d | 0 | 0 | 0 | 1163.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 0 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2012-04-02 08:00 |  | TP Name | 02/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 65d | [5 empty] | 237952.3091 |  | 69.1% |  | 232461.2692 | 236714.2692
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 |  | 0 | 0 | 2045 | 1d | 0 | 0 | 0 | 2045 | 0% | Not Started | 0 | 2045 | 100 |  | 0 | 100 |  | 0
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 |  | 0 | 0 | 1482 | 1d | 0 | 0 | 0 | 1482 | 0% | Not Started | 0 | 1482 | 100 |  | 0 | 100 |  | 0
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 |  | 0 | 0 | 1540 | 1d | 0 | 0 | 0 | 1540 | 0% | Not Started | 0 | 1540 | 100 |  | 0 | 100 |  | 0
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 750 | 100 |  | 0 | 100 |  | 0
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 0 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2012-04-09 08:00 |  | TP Name | 09/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 70d | [5 empty] | 245850.3091 |  | 71.16% |  | 239401.2692 | 247056.8693
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 7655.6001 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2012-04-16 08:00 |  | TP Name | 16/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 75d | [5 empty] | 245850.3091 |  | 71.16% |  | 239401.2692 | 252725.9193
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 |  | 0 | 0 | 7655.6001 | 5d | 0 | 0 | 0 | 7655.6001 | 0% | Not Started | 0 | 7655.6001 | 100 |  | 0 | 100 |  | 0
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 1160.35 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 1160.35 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 1160.35 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 1098 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 1090 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2012-04-23 08:00 |  | TP Name | 23/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 80d | [5 empty] | 253850.3092 |  | 73.44% |  | 247056.8693 | 252725.9193
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 1160.35 | 100 |  | 0 | 100 |  | 0
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 1160.35 | 100 |  | 0 | 100 |  | 0
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 |  | 0 | 0 | 1160.35 | 1d | 0 | 0 | 0 | 1160.35 | 0% | Not Started | 0 | 1160.35 | 100 |  | 0 | 100 |  | 0
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 |  | 0 | 0 | 1098 | 1d | 0 | 0 | 0 | 1098 | 0% | Not Started | 0 | 1098 | 100 |  | 0 | 100 |  | 0
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 |  | 0 | 0 | 1090 | 1d | 0 | 0 | 0 | 1090 | 0% | Not Started | 0 | 1090 | 100 |  | 0 | 100 |  | 0
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 |  | 0 | 0 | 4523 | 4d | 0 | 0 | 0 | 4523 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2012-04-30 08:00 |  | TP Name | 30/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 85d | [5 empty] | 265056.0092 |  | 76.47% |  | 257248.9193 | 258506.9193
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 |  | 0 | 0 | 1293 | 4h | 0 | 0 | 0 | 1293 | 0% | Not Started | 0 | 1293 | 100 |  | 0 | 100 |  | 0
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 1125 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 1043 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 1085 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 0 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2012-05-07 08:00 |  | TP Name | 07/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 90d | [5 empty] | 267256.0092 |  | 76.85% |  | 258541.9193 | 267857.9193
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 1125 | 100 |  | 0 | 100 |  | 0
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 |  | 0 | 0 | 1043 | 1d | 0 | 0 | 0 | 1043 | 0% | Not Started | 0 | 1043 | 100 |  | 0 | 100 |  | 0
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 |  | 0 | 0 | 1085 | 1d | 0 | 0 | 0 | 1085 | 0% | Not Started | 0 | 1085 | 100 |  | 0 | 100 |  | 0
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 1123 | 100 |  | 0 | 100 |  | 0
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2012-05-14 08:00 |  | TP Name | 14/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 95d | [5 empty] | 274066.0092 |  | 78.52% |  | 264152.9193 | 277502.6292
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 3564 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 1839.71 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 |  | 0 | 0 | 4241 | 4d | 0 | 0 | 0 | 4241 | 0% | Not Started | 0 | 4241 | 100 |  | 0 | 100 |  | 0
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2012-05-21 08:00 |  | TP Name | 21/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 100d | [5 empty] | 277557.0092 |  | 79.56% |  | 267643.9193 | 288955.6292
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 3564 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 1839.71 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 3d | 3491 | 750 | 1d | 0 | 0 | 3491 | 750 | 75% | Started | 3491 | 4241 | 100 | 75 | 75 | 100 | 82.3155 | 75
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 1292 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 |  | 0 | 0 | 5228 | 5d | 0 | 0 | 0 | 5228 | 0% | Not Started | 0 | 5228 | 100 |  | 0 | 100 |  | 0
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 1452 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 1230 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 1156 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 1095 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2012-05-28 08:00 |  | TP Name | 28/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 105d | [5 empty] | 283007.0092 |  | 81.11% |  | 272871.9193 | 295558.2592
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 |  | 0 | 0 | 1235 | 1d | 0 | 0 | 0 | 1235 | 0% | Not Started | 0 | 1235 | 100 |  | 0 | 100 |  | 0
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 3564 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 1839.71 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 100% | Finished | 4241 | 4241 | 100 | 100 | 100 | 100 | 100 | 100
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 1292 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 750 | 1d | 222 | 0 | 4700 | 750 | 80% | Started | 4478 | 5228 | 100 | 80 | 80 | 100 | 89.9005 | 80
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 1452 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 1230 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 1156 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 1095 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 1123 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 5479.63 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2012-06-04 08:00 |  | TP Name | 04/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 110d | [5 empty] | 287407.0092 |  | 82.21% |  | 276576.9193 | 301706.2592
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-29 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-30 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-31 08:00 | 2d | 1985 | 0 | 0 | -385 | 0 | 1600 | 0 | 100% | Finished | 1235 | 1235 | 100 | 200 | 100 | 100 | 129.5547 | 100
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 3564 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 1839.71 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 100% | Finished | 4241 | 4241 | 100 | 100 | 100 | 100 | 100 | 100
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 1292 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 750 | 1d | 222 | 0 | 4700 | 750 | 80% | Started | 4478 | 5228 | 100 | 80 | 80 | 100 | 89.9005 | 80
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 1452 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 1230 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 1156 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 1095 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 1123 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 |  | 0 | 0 | 5479.63 | 5d | 0 | 0 | 0 | 5479.63 | 0% | Not Started | 0 | 5479.63 | 100 |  | 0 | 100 |  | 0
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 6148 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2012-06-11 08:00 |  | TP Name | 11/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 115d | [5 empty] | 292886.6392 |  | 83.84% |  | 282056.5493 | 313982.7592
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-29 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-30 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-31 08:00 | 2d | 1985 | 0 | 0 | -385 | 0 | 1600 | 0 | 100% | Finished | 1235 | 1235 | 100 | 200 | 100 | 100 | 129.5547 | 100
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 3564 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 1839.71 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 100% | Finished | 4241 | 4241 | 100 | 100 | 100 | 100 | 100 | 100
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 1292 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 750 | 1d | 222 | 0 | 4700 | 750 | 80% | Started | 4478 | 5228 | 100 | 80 | 80 | 100 | 89.9005 | 80
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 1452 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 1230 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 1156 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 1095 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 1123 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 | 2012-06-04 08:00 | 5d | 5479.63 | 0 | 0 | 0 | 0 | 5479.63 | 0 | 100% | Finished | 5479.63 | 5479.63 | 100 | 100 | 100 | 100 | 100 | 100
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 |  | 0 | 0 | 8398 | 8d | 0 | 0 | 0 | 8398 | 0% | Not Started | 0 | 8398 | 100 |  | 0 | 100 |  | 0
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 1170 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 5578 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 3278.5 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2012-06-18 08:00 |  | TP Name | 18/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 120d | [5 empty] | 299886.6392 |  | 85.67% |  | 288204.5493 | 328910.1494
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-29 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-30 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-31 08:00 | 2d | 1985 | 0 | 0 | -385 | 0 | 1600 | 0 | 100% | Finished | 1235 | 1235 | 100 | 200 | 100 | 100 | 129.5547 | 100
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 3564 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 1839.71 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 100% | Finished | 4241 | 4241 | 100 | 100 | 100 | 100 | 100 | 100
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 |  | 0 | 0 | 1292 | 4h | 0 | 0 | 0 | 1292 | 0% | Not Started | 0 | 1292 | 100 |  | 0 | 100 |  | 0
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 750 | 1d | 222 | 0 | 4700 | 750 | 80% | Started | 4478 | 5228 | 100 | 80 | 80 | 100 | 89.9005 | 80
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 |  | 0 | 0 | 1452 | 4h | 0 | 0 | 0 | 1452 | 0% | Not Started | 0 | 1452 | 100 |  | 0 | 100 |  | 0
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 |  | 0 | 0 | 1230 | 1d | 0 | 0 | 0 | 1230 | 0% | Not Started | 0 | 1230 | 100 |  | 0 | 100 |  | 0
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 |  | 0 | 0 | 1156 | 1d | 0 | 0 | 0 | 1156 | 0% | Not Started | 0 | 1156 | 100 |  | 0 | 100 |  | 0
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 |  | 0 | 0 | 1095 | 1d | 0 | 0 | 0 | 1095 | 0% | Not Started | 0 | 1095 | 100 |  | 0 | 100 |  | 0
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 1123 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 | 2012-06-04 08:00 | 5d | 5479.63 | 0 | 0 | 0 | 0 | 5479.63 | 0 | 100% | Finished | 5479.63 | 5479.63 | 100 | 100 | 100 | 100 | 100 | 100
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 | 2012-06-11 08:00 | 5d | 6148 | 2250 | 3d | 852 | 0 | 7000 | 2250 | 62.5% | Started | 6148 | 8398 | 100 | 62.5 | 62.5 | 100 | 83.3532 | 62.5
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 1170 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 5578 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 3278.5 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 6690.46 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 8236.9302 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2012-06-25 08:00 |  | TP Name | 25/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 125d | [5 empty] | 307031.6392 |  | 87.74% |  | 295179.5493 | 336410.1494
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-29 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-30 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-31 08:00 | 2d | 1985 | 0 | 0 | -385 | 0 | 1600 | 0 | 100% | Finished | 1235 | 1235 | 100 | 200 | 100 | 100 | 129.5547 | 100
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 3564 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 1839.71 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 100% | Finished | 4241 | 4241 | 100 | 100 | 100 | 100 | 100 | 100
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 | 2012-06-18 08:00 | 1d | 1667 | 0 | 0 | 0 | 0 | 1667 | 0 | 100% | Finished | 1292 | 1292 | 100 | 200 | 100 | 100 | 129.0248 | 100
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 0 | 0 | 222 | 0 | 4700 | 0 | 100% | Finished | 5228 | 5228 | 100 | 80 | 100 | 100 | 89.9005 | 100
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 | 2012-06-19 08:00 | 1d | 1827 | 0 | 0 | 0 | 0 | 1827 | 0 | 100% | Finished | 1452 | 1452 | 100 | 200 | 100 | 100 | 125.8264 | 100
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 | 2012-06-20 08:00 | 1d | 1230 | 0 | 0 | 170 | 0 | 1400 | 0 | 100% | Finished | 1230 | 1230 | 100 | 100 | 100 | 100 | 113.8211 | 100
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 | 2012-06-21 08:00 | 1d | 1156 | 0 | 0 | 0 | 0 | 1156 | 0 | 100% | Finished | 1156 | 1156 | 100 | 100 | 100 | 100 | 100 | 100
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 | 2012-06-22 08:00 | 1d | 1095 | 0 | 0 | 0 | 0 | 1095 | 0 | 100% | Finished | 1095 | 1095 | 100 | 100 | 100 | 100 | 100 | 100
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 1123 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 | 2012-06-04 08:00 | 5d | 5479.63 | 0 | 0 | 0 | 0 | 5479.63 | 0 | 100% | Finished | 5479.63 | 5479.63 | 100 | 100 | 100 | 100 | 100 | 100
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 | 2012-06-11 08:00 | 5d | 6148 | 2250 | 3d | 852 | 0 | 7000 | 2250 | 62.5% | Started | 6148 | 8398 | 100 | 62.5 | 62.5 | 100 | 83.3532 | 62.5
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 |  | 0 | 0 | 1170 | 1d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 1170 | 100 |  | 0 | 100 |  | 0
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 |  | 0 | 0 | 5578 | 2d | 0 | 0 | 0 | 5578 | 0% | Not Started | 0 | 5578 | 100 |  | 0 | 100 |  | 0
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 |  | 0 | 0 | 3278.5 | 2d | 0 | 0 | 0 | 3278.5 | 0% | Not Started | 0 | 3278.5 | 100 |  | 0 | 100 |  | 0
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 10440.46 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 11986.9302 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2012-07-02 08:00 |  | TP Name | 02/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 130d | [5 empty] | 317058.1392 |  | 90.72% |  | 305206.0493 | 336410.1494
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-29 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-30 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-31 08:00 | 2d | 1985 | 0 | 0 | -385 | 0 | 1600 | 0 | 100% | Finished | 1235 | 1235 | 100 | 200 | 100 | 100 | 129.5547 | 100
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 |  | 0 | 0 | 3564 | 3d | 0 | 0 | 0 | 3564 | 0% | Not Started | 0 | 3564 | 100 |  | 0 | 100 |  | 0
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 |  | 0 | 0 | 1839.71 | 1d | 0 | 0 | 0 | 1839.71 | 0% | Not Started | 0 | 1839.71 | 100 |  | 0 | 100 |  | 0
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 100% | Finished | 4241 | 4241 | 100 | 100 | 100 | 100 | 100 | 100
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 | 2012-06-18 08:00 | 1d | 1667 | 0 | 0 | 0 | 0 | 1667 | 0 | 100% | Finished | 1292 | 1292 | 100 | 200 | 100 | 100 | 129.0248 | 100
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 0 | 0 | 222 | 0 | 4700 | 0 | 100% | Finished | 5228 | 5228 | 100 | 80 | 100 | 100 | 89.9005 | 100
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 | 2012-06-19 08:00 | 1d | 1827 | 0 | 0 | 0 | 0 | 1827 | 0 | 100% | Finished | 1452 | 1452 | 100 | 200 | 100 | 100 | 125.8264 | 100
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 | 2012-06-20 08:00 | 1d | 1230 | 0 | 0 | 170 | 0 | 1400 | 0 | 100% | Finished | 1230 | 1230 | 100 | 100 | 100 | 100 | 113.8211 | 100
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 | 2012-06-21 08:00 | 1d | 1156 | 0 | 0 | 0 | 0 | 1156 | 0 | 100% | Finished | 1156 | 1156 | 100 | 100 | 100 | 100 | 100 | 100
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 | 2012-06-22 08:00 | 1d | 1095 | 0 | 0 | 0 | 0 | 1095 | 0 | 100% | Finished | 1095 | 1095 | 100 | 100 | 100 | 100 | 100 | 100
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 |  | 0 | 0 | 1123 | 1d | 0 | 0 | 0 | 1123 | 0% | Not Started | 0 | 1123 | 100 |  | 0 | 100 |  | 0
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 | 2012-06-04 08:00 | 5d | 5479.63 | 0 | 0 | 0 | 0 | 5479.63 | 0 | 100% | Finished | 5479.63 | 5479.63 | 100 | 100 | 100 | 100 | 100 | 100
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 | 2012-06-11 08:00 | 5d | 6148 | 2250 | 3d | 852 | 0 | 7000 | 2250 | 62.5% | Started | 6148 | 8398 | 100 | 62.5 | 62.5 | 100 | 83.3532 | 62.5
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 | 2012-06-25 08:00 | 1d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1170 | 1170 | 100 | 100 | 100 | 100 | 100 | 100
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 | 2012-06-26 08:00 | 2d | 5578 | 0 | 0 | 0 | 0 | 5578 | 0 | 100% | Finished | 5578 | 5578 | 100 | 100 | 100 | 100 | 100 | 100
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 | 2012-06-28 08:00 | 2d | 3278.5 | 0 | 0 | 0 | 0 | 3278.5 | 0 | 100% | Finished | 3278.5 | 3278.5 | 100 | 100 | 100 | 100 | 100 | 100
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 |  | 0 | 0 | 10440.46 | 9d | 0 | 0 | 0 | 10440.46 | 0% | Not Started | 0 | 10440.46 | 100 |  | 0 | 100 |  | 0
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 11986.9302 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2012-07-09 08:00 |  | TP Name | 09/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 135d | [5 empty] | 334261.3092 |  | 94.65% |  | 318423.2192 | 336410.1494
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-29 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-30 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-31 08:00 | 2d | 1985 | 0 | 0 | -385 | 0 | 1600 | 0 | 100% | Finished | 1235 | 1235 | 100 | 200 | 100 | 100 | 129.5547 | 100
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 | 2012-07-02 08:00 | 4d | 4314 | 0 | 0 | 1986 | 0 | 6300 | 0 | 100% | Finished | 3564 | 3564 | 100 | 133.3333 | 100 | 100 | 176.7677 | 100
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 | 2012-07-06 08:00 | 1d | 1839.71 | 0 | 0 | 1250 | 0 | 3089.71 | 0 | 100% | Finished | 1839.71 | 1839.71 | 100 | 100 | 100 | 100 | 167.9455 | 100
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 100% | Finished | 4241 | 4241 | 100 | 100 | 100 | 100 | 100 | 100
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 | 2012-06-18 08:00 | 1d | 1667 | 0 | 0 | 0 | 0 | 1667 | 0 | 100% | Finished | 1292 | 1292 | 100 | 200 | 100 | 100 | 129.0248 | 100
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 0 | 0 | 222 | 0 | 4700 | 0 | 100% | Finished | 5228 | 5228 | 100 | 80 | 100 | 100 | 89.9005 | 100
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 | 2012-06-19 08:00 | 1d | 1827 | 0 | 0 | 0 | 0 | 1827 | 0 | 100% | Finished | 1452 | 1452 | 100 | 200 | 100 | 100 | 125.8264 | 100
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 | 2012-06-20 08:00 | 1d | 1230 | 0 | 0 | 170 | 0 | 1400 | 0 | 100% | Finished | 1230 | 1230 | 100 | 100 | 100 | 100 | 113.8211 | 100
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 | 2012-06-21 08:00 | 1d | 1156 | 0 | 0 | 0 | 0 | 1156 | 0 | 100% | Finished | 1156 | 1156 | 100 | 100 | 100 | 100 | 100 | 100
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 | 2012-06-22 08:00 | 1d | 1095 | 0 | 0 | 0 | 0 | 1095 | 0 | 100% | Finished | 1095 | 1095 | 100 | 100 | 100 | 100 | 100 | 100
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-07-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 | 2012-06-04 08:00 | 5d | 5479.63 | 0 | 0 | 0 | 0 | 5479.63 | 0 | 100% | Finished | 5479.63 | 5479.63 | 100 | 100 | 100 | 100 | 100 | 100
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 | 2012-06-11 08:00 | 5d | 6148 | 2250 | 3d | 852 | 0 | 7000 | 2250 | 62.5% | Started | 6148 | 8398 | 100 | 62.5 | 62.5 | 100 | 83.3532 | 62.5
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 | 2012-06-25 08:00 | 1d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1170 | 1170 | 100 | 100 | 100 | 100 | 100 | 100
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 | 2012-06-26 08:00 | 2d | 5578 | 0 | 0 | 0 | 0 | 5578 | 0 | 100% | Finished | 5578 | 5578 | 100 | 100 | 100 | 100 | 100 | 100
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 | 2012-06-28 08:00 | 2d | 3278.5 | 0 | 0 | 0 | 0 | 3278.5 | 0 | 100% | Finished | 3278.5 | 3278.5 | 100 | 100 | 100 | 100 | 100 | 100
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 | 2012-07-03 08:00 | 4d | 6690.46 | 3750 | 5d | 0 | 0 | 6690.46 | 3750 | 44.44% | Started | 6690.46 | 10440.46 | 100 | 44.4444 | 44.4444 | 100 | 64.082 | 44.4444
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 |  | 0 | 0 | 11986.9302 | 9d | 0 | 0 | 0 | 11986.9302 | 0% | Not Started | 0 | 11986.9302 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2012-07-16 08:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Pumping Station Jabbeke | 2012-01-02 08:00 | 2012-06-22 17:00 | 125d |  |  | 202160.1494 |  |  | 336410.1494 |  | 140d | [5 empty] | 350511.3094 |  | 100% |  | 336410.1494 | 336410.1494
1 | start plaatsing looplatform ALSB | 2012-01-02 08:00 | 2012-01-02 17:00 | 1d | ploeg 1&2 | 750 | 2850 | 0 | 0 | 3600 | 2012-01-02 08:00 | 1d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 3600 | 3600 | 100 | 100 | 100 | 100 | 100 | 100
2 | start plaatsing RVS looplatform krooshekreiniger | 2012-01-03 08:00 | 2012-01-03 17:00 | 1d | ploeg 1&2 | 750 | 10050 | 0 | 0 | 10800 | 2012-01-03 08:00 | 1d | 10800 | 0 | 0 | 0 | 0 | 10800 | 0 | 100% | Finished | 10800 | 10800 | 100 | 100 | 100 | 100 | 100 | 100
3 | start plaatsing trap krooshekreiniger | 2012-01-04 08:00 | 2012-01-04 17:00 | 1d | ploeg 1&2 | 750 | 17450 | 0 | 0 | 18200 | 2012-01-04 08:00 | 1d | 18200 | 0 | 0 | 0 | 0 | 18200 | 0 | 100% | Finished | 18200 | 18200 | 100 | 100 | 100 | 100 | 100 | 100
4 | startplaatsing RVS roosters uitstroom + veilgheidsleuning | 2012-01-05 08:00 | 2012-01-05 17:00 | 1d | ploeg 1&2 | 750 | 15200 | 0 | 0 | 15950 | 2012-01-05 08:00 | 1d | 15950 | 0 | 0 | 910 | 0 | 16860 | 0 | 100% | Finished | 15950 | 15950 | 100 | 100 | 100 | 100 | 105.7053 | 100
5 | leveren en plaatsen opbergsysteem noodafsluitschotten | 2012-01-06 08:00 | 2012-01-06 17:00 | 1d | ploeg 1&2 | 750 | 4425 | 0 | 0 | 5175 | 2012-01-06 08:00 | 1d | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
6 | constructie ALSB in atelier | 2012-01-09 08:00 | 2012-02-10 17:00 | 25d | ploeg 1&2 | 18750 | 3500 | 0 | 0 | 22250 | 2012-01-09 08:00 | 20d | 18500 | 0 | 0 | 750 | 0 | 19250 | 0 | 100% | Finished | 22250 | 22250 | 100 | 80 | 100 | 100 | 86.5169 | 100
7 | verplaatsen bord PLC , wegnemen stopcontacten en verwarming muur loopplatform ALSB | 2012-01-17 08:00 | 2012-01-17 17:00 | 1d | ploeg 1&2 | 750 | 282 | 0 | 0 | 1032 | 2012-01-17 08:00 | 1d | 1032 | 0 | 0 | 0 | 0 | 1032 | 0 | 100% | Finished | 1032 | 1032 | 100 | 100 | 100 | 100 | 100 | 100
8 | bespreken lay-out ALSB met Glenn | 2012-01-18 08:00 | 2012-01-18 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-01-18 08:00 | 1d | 750 | 0 | 0 | 199.5 | 0 | 949.5 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 126.6 | 100
9 | bestellen lay-out ALSB | 2012-01-19 08:00 | 2012-01-19 17:00 | 1d | ploeg 1&2 | 750 | 40 | 0 | 0 | 790 | 2012-01-19 08:00 | 1d | 790 | 0 | 0 | 40 | 0 | 830 | 0 | 100% | Finished | 790 | 790 | 100 | 100 | 100 | 100 | 105.0633 | 100
10 | afwerking looplatform ALSBkroooshekreiniger,trap krooshekreiniger,leuning uitstroom | 2012-01-19 08:00 | 2012-01-20 17:00 | 2d | vandezande | 1500 | 360 | 0 | 0 | 1860 | 2012-01-19 08:00 | 2d | 1860 | 0 | 0 | 300 | 0 | 2160 | 0 | 100% | Finished | 1860 | 1860 | 100 | 100 | 100 | 100 | 116.129 | 100
11 | verhogen rolbrug mits voorafgaandelijke goedkeuring offerte door bestuur + omwisselen manuele bediening takel | 2012-02-06 08:00 | 2012-02-06 17:00 | 1d | vandezande | 750 | 4059 | 0 | 0 | 4809 | 2012-02-06 08:00 | 1d | 4809 | 0 | 0 | 91 | 0 | 4900 | 0 | 100% | Finished | 4809 | 4809 | 100 | 100 | 100 | 100 | 101.8923 | 100
12 | programmatie en testen PLC en visualisatie atelier Decat | 2012-02-08 08:00 | 2012-02-10 17:00 | 3d | ploeg 1&2 | 2250 | 6693.52 | 0 | 0 | 8943.52 | 2012-02-01 08:00 | 3d | 8943.52 | 0 | 0 | 0 | 0 | 8943.52 | 0 | 100% | Finished | 8943.52 | 8943.52 | 100 | 100 | 100 | 100 | 100 | 100
13 | oplevering ALSB bij Decat door glenn Degros | 2012-02-13 08:00 | 2012-02-17 17:00 | 5d | ploeg 1&2 | 3750 | 1591 | 0 | 0 | 5341 | 2012-02-06 08:00 | 2d | 3091 | 0 | 0 | 2409 | 0 | 5500 | 0 | 100% | Finished | 5341 | 5341 | 100 | 40 | 100 | 100 | 102.977 | 100
14 | uitvoeren nodige aanpassingen aan bord + software + schema's volgens opmerkingen glenn Degros | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | ploeg 1&2 | 3750 | 1115 | 0 | 0 | 4865 | 2012-02-08 08:00 | 3d | 3365 | 0 | 0 | 1635 | 0 | 5000 | 0 | 100% | Finished | 4865 | 4865 | 100 | 60 | 100 | 100 | 102.7749 | 100
15 | leveren en plaatsen van elektrische spindelaandrijving op de noodschuiven | 2012-02-20 08:00 | 2012-02-24 17:00 | 5d | vandezande | 3750 | 10786 | 0 | 0 | 14536 | 2012-02-13 08:00 | 5d | 14536 | 0 | 0 | 0 | 0 | 14536 | 0 | 100% | Finished | 14536 | 14536 | 100 | 100 | 100 | 100 | 100 | 100
16 | nazicht en uit testen door Glenn Degros | 2012-02-27 08:00 | 2012-03-02 17:00 | 5d | ploeg 1&2 | 3750 | 1884 | 0 | 0 | 5634 | 2012-02-13 08:00 | 5d | 5634 | 0 | 0 | 0 | 0 | 5634 | 0 | 100% | Finished | 5634 | 5634 | 100 | 100 | 100 | 100 | 100 | 100
17 | graafwerken+ opstellen betonijzer + gieten fundering voor peilmeting stroom af en opwaarts + seinborden | 2012-02-27 08:00 | 2012-02-28 17:00 | 2d | ploeg 1&2 | 1500 | 7716 | 0 | 0 | 9216 | 2012-02-20 08:00 | 2d | 9216 | 0 | 0 | 0 | 0 | 9216 | 0 | 100% | Finished | 9216 | 9216 | 100 | 100 | 100 | 100 | 100 | 100
18 | maken sleuf voor peilmeting stroomopwaarts | 2012-02-29 08:00 | 2012-02-29 17:00 | 1d | ploeg 1&2 | 750 | 292 | 0 | 0 | 1042 | 2012-02-22 08:00 | 1d | 1042 | 0 | 0 | 58 | 0 | 1100 | 0 | 100% | Finished | 1042 | 1042 | 100 | 100 | 100 | 100 | 105.5662 | 100
19 | leveren en plaatsen bekabeling tussen ALSB en peilmeting + vlotters stroomopwaarts+ seinborden | 2012-03-01 08:00 | 2012-03-06 17:00 | 4d | ploeg 1&2 | 3000 | 1567 | 0 | 0 | 4567 | 2012-02-23 08:00 | 4d | 4567 | 0 | 0 | 0 | 0 | 4567 | 0 | 100% | Finished | 4567 | 4567 | 100 | 100 | 100 | 100 | 100 | 100
20 | opstellen en aansluiten ALSB op loopplatform + kast no break | 2012-03-05 08:00 | 2012-03-09 17:00 | 5d | ploeg 1&2 | 3750 | 2839 | 0 | 0 | 6589 | 2012-02-20 08:00 | 5d | 6589 | 0 | 0 | 0 | 0 | 6589 | 0 | 100% | Finished | 6589 | 6589 | 100 | 100 | 100 | 100 | 100 | 100
21 | venster pomplokaal wegnemen + bijkomende doorgang maken naar loopplatform roosterreinigers | 2012-03-05 08:00 | 2012-03-05 17:00 | 1d | vandezande | 750 | 1515 | 0 | 0 | 2265 | 2012-02-27 08:00 | 1d | 2265 | 0 | 0 | 0 | 0 | 2265 | 0 | 100% | Finished | 2265 | 2265 | 100 | 100 | 100 | 100 | 100 | 100
22 | plaatsen platform peilmeting af en opwaarts | 2012-03-07 08:00 | 2012-03-07 17:00 | 1d | ploeg 1&2 | 750 | 3497.29 | 0 | 0 | 4247.29 | 2012-02-29 08:00 | 1d | 4247.29 | 0 | 0 | 0 | 0 | 4247.29 | 0 | 100% | Finished | 4247.29 | 4247.29 | 100 | 100 | 100 | 100 | 100 | 100
23 | opstelling radarpeilmeting op en afwaarts + vlotters | 2012-03-08 08:00 | 2012-03-08 17:00 | 1d | ploeg 1&2 | 750 | 4497.29 | 0 | 0 | 5247.29 | 2012-03-01 08:00 | 1d | 5247.29 | 0 | 0 | -47.29 | 0 | 5200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 99.0988 | 100
24 | opstellen peilmetingen na de roosters | 2012-03-09 08:00 | 2012-03-13 17:00 | 3d | ploeg 1&2 | 2250 | 2997.29 | 0 | 0 | 5247.29 | 2012-03-02 08:00 | 3d | 5247.29 | 0 | 0 | 152.71 | 0 | 5400 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 100 | 100 | 100 | 102.9103 | 100
25 | leveren en plaatsen ventilatiekanalen voor koeling frequentieregelaars ALSB+geluidswerende wand | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d | ploeg 1&2 | 3750 | 41704.7891 | 0 | 0 | 45454.7891 | 2012-03-12 08:00 | 5d | 45454.7891 | 0 | 0 | 2545.21 | 0 | 47999.999 | 0 | 100% | Finished | 45454.7891 | 45454.7891 | 100 | 100 | 100 | 100 | 105.5994 | 100
26 | aansluitingen peilmetingen | 2012-03-14 08:00 | 2012-03-15 17:00 | 2d | ploeg 1&2 | 1500 | 3747.29 | 0 | 0 | 5247.29 | 2012-03-07 08:00 | 3d | 5997.29 | 0 | 0 | 202.71 | 0 | 6200 | 0 | 100% | Finished | 5247.29 | 5247.29 | 100 | 150 | 100 | 100 | 118.1562 | 100
27 | leveren en plaatsen nieuwe voedingskabels tussen ALSB en transfo HS lokaal voor voeding nieuw ALSB incl aansluiting op transformator | 2012-03-19 08:00 | 2012-03-20 17:00 | 2d | ploeg 1&2 | 1500 | 1858 | 0 | 0 | 3358 | 2012-03-19 08:00 | 2d | 3358 | 0 | 0 | 442 | 0 | 3800 | 0 | 100% | Finished | 3358 | 3358 | 100 | 100 | 100 | 100 | 113.1626 | 100
28 | plaatsen geluidswerende wand + dubbel geluidswerende deur | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d | ploeg 1&2 | 3750 | 1439 | 0 | 0 | 5189 | 2012-03-26 08:00 | 5d | 5189 | 0 | 0 | 1111 | 0 | 6300 | 0 | 100% | Finished | 5189 | 5189 | 100 | 100 | 100 | 100 | 121.4107 | 100
29 | uitvoeren van de nodige aardingen | 2012-03-21 08:00 | 2012-03-21 17:00 | 1d | ploeg 1&2 | 750 | 436.3 | 0 | 0 | 1186.3 | 2012-03-21 08:00 | 1d | 1186.3 | 0 | 0 | 225 | 0 | 1411.3 | 0 | 100% | Finished | 1186.3 | 1186.3 | 100 | 100 | 100 | 100 | 118.9665 | 100
30 | ALSB onder spanning brengen | 2012-03-22 08:00 | 2012-03-22 17:00 | 1d | ploeg 1&2 | 750 | 309 | 0 | 0 | 1059 | 2012-03-22 08:00 | 1d | 1059 | 0 | 0 | 231 | 0 | 1290 | 0 | 100% | Finished | 1059 | 1059 | 100 | 100 | 100 | 100 | 121.813 | 100
31 | omschakelen pomp 1 op nieuw ALSB | 2012-03-26 08:00 | 2012-03-26 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-03-26 08:00 | 1d | 1668 | 0 | 0 | 0 | 0 | 1668 | 0 | 100% | Finished | 1293 | 1293 | 100 | 200 | 100 | 100 | 129.0023 | 100
32 | leveren en plaatsen werkschakelaar pomp 1 | 2012-03-26 13:00 | 2012-03-26 17:00 | 4h | ploeg 1&2 | 375 | 1187.7 | 0 | 0 | 1562.7 | 2012-03-27 08:00 | 1d | 1937.7 | 0 | 0 | 0 | 0 | 1937.7 | 0 | 100% | Finished | 1562.7 | 1562.7 | 100 | 200 | 100 | 100 | 123.9969 | 100
33 | tussenwand tussen bureau en keuken | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d | ploeg 1&2 | 750 | 1295 | 0 | 0 | 2045 | 2012-04-02 08:00 | 2d | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 100% | Finished | 2045 | 2045 | 100 | 200 | 100 | 100 | 136.6748 | 100
34 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 1 | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 608 | 0 | 0 | 1358 | 2012-03-28 08:00 | 1d | 1358 | 0 | 0 | 0 | 0 | 1358 | 0 | 100% | Finished | 1358 | 1358 | 100 | 100 | 100 | 100 | 100 | 100
35 | leveren en plaatsen keukenblok | 2012-03-27 08:00 | 2012-03-27 17:00 | 1d | ploeg 1&2 | 750 | 732 | 0 | 0 | 1482 | 2012-04-04 08:00 | 1d | 1482 | 0 | 0 | 0 | 0 | 1482 | 0 | 100% | Finished | 1482 | 1482 | 100 | 100 | 100 | 100 | 100 | 100
36 | leveren en plaatsen voedingskabel smeerpomp 1 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 319 | 0 | 0 | 1069 | 2012-03-29 08:00 | 1d | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 100% | Finished | 1069 | 1069 | 100 | 100 | 100 | 100 | 100 | 100
37 | Verplaatsen boiler en aanpassen leidingen | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d | ploeg 1&2 | 750 | 790 | 0 | 0 | 1540 | 2012-04-05 08:00 | 1d | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 100% | Finished | 1540 | 1540 | 100 | 100 | 100 | 100 | 100 | 100
38 | aanpassen smeersysteem pomp 1 | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 413.8 | 0 | 0 | 1163.8 | 2012-03-30 08:00 | 1d | 1163.8 | 0 | 0 | 11.2 | 0 | 1175 | 0 | 100% | Finished | 1163.8 | 1163.8 | 100 | 100 | 100 | 100 | 100.9624 | 100
39 | geluidsdichte omkasting rond boiler | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d | ploeg 1&2 | 750 | 0 | 0 | 0 | 750 | 2012-04-06 08:00 | 1d | 750 | 0 | 0 | 208 | 0 | 958 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 127.7333 | 100
40 | proefdraaien pomp 1 op nieuw ALSB | 2012-04-02 08:00 | 2012-04-02 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-04-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
41 | leveren en plaatsen bekabeling roosterreinigers + transportband + noodstoppen + console + buitenverlichting | 2012-04-02 08:00 | 2012-04-06 17:00 | 5d | ploeg 1&2 | 3750 | 3905.6001 | 0 | 0 | 7655.6001 | 2012-04-16 08:00 | 5d | 7655.6001 | 0 | 0 | 344.4 | 0 | 8000.0001 | 0 | 100% | Finished | 7655.6001 | 7655.6001 | 100 | 100 | 100 | 100 | 104.4987 | 100
42 | aansluiten installatie op Abba | 2012-04-03 08:00 | 2012-04-03 17:00 | 1d | ploeg 1&2 | 750 | 814 | 0 | 0 | 1564 | 2012-03-23 08:00 | 1d | 1564 | 0 | 0 | 225 | 0 | 1789 | 0 | 100% | Finished | 1564 | 1564 | 100 | 100 | 100 | 100 | 114.3862 | 100
43 | aansluiten roosterreiniger 1 op nieuw ALSB , testen en in dienst stellen | 2012-04-09 08:00 | 2012-04-09 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-23 08:00 | 1d | 1160.35 | 0 | 0 | 239.65 | 0 | 1400 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 120.6533 | 100
44 | aansluiten roosterreiniger 2 op nieuw ALSB , testen en in dienst stellen | 2012-04-10 08:00 | 2012-04-10 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-24 08:00 | 1d | 1160.35 | 0 | 0 | 375 | 0 | 1535.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 132.3178 | 100
45 | aansluiten roosterreiniger 3 op nieuw ALSB , testen en in dienst stellen | 2012-04-11 08:00 | 2012-04-11 17:00 | 1d | ploeg 1&2 | 750 | 410.35 | 0 | 0 | 1160.35 | 2012-04-25 08:00 | 1d | 1160.35 | 0 | 0 | 0 | 0 | 1160.35 | 0 | 100% | Finished | 1160.35 | 1160.35 | 100 | 100 | 100 | 100 | 100 | 100
46 | aansluiten transportband op nieuw ALSB | 2012-04-12 08:00 | 2012-04-12 17:00 | 1d | ploeg 1&2 | 750 | 348 | 0 | 0 | 1098 | 2012-04-25 08:00 | 1d | 1098 | 0 | 0 | 12 | 0 | 1110 | 0 | 100% | Finished | 1098 | 1098 | 100 | 100 | 100 | 100 | 101.0929 | 100
47 | aansluiten noodstoppen op nieuw ALSB | 2012-04-13 08:00 | 2012-04-13 17:00 | 1d | ploeg 1&2 | 750 | 340 | 0 | 0 | 1090 | 2012-04-27 08:00 | 1d | 1090 | 0 | 0 | 10 | 0 | 1100 | 0 | 100% | Finished | 1090 | 1090 | 100 | 100 | 100 | 100 | 100.9174 | 100
48 | omschakelen pomp 2 op nieuw ALSB | 2012-04-24 08:00 | 2012-04-24 12:00 | 4h | ploeg 1&2 | 375 | 918 | 0 | 0 | 1293 | 2012-05-03 08:00 | 2d | 2418 | 0 | 0 | -218 | 0 | 2200 | 0 | 100% | Finished | 1293 | 1293 | 100 | 400 | 100 | 100 | 170.1469 | 100
49 | leveren en plaatsen werkschakelaar pomp 2 | 2012-04-24 13:00 | 2012-04-24 17:00 | 4h | ploeg 1&2 | 375 | 750 | 0 | 0 | 1125 | 2012-05-07 08:00 | 1d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1125 | 1125 | 100 | 200 | 100 | 100 | 133.3333 | 100
50 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 2 | 2012-04-25 08:00 | 2012-04-25 17:00 | 1d | ploeg 1&2 | 750 | 293 | 0 | 0 | 1043 | 2012-05-08 08:00 | 1d | 1043 | 0 | 0 | 157 | 0 | 1200 | 0 | 100% | Finished | 1043 | 1043 | 100 | 100 | 100 | 100 | 115.0527 | 100
51 | leveren en plaatsen voedingskabel smeerpomp 2 | 2012-04-26 08:00 | 2012-04-26 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-09 08:00 | 1d | 1235 | 0 | 0 | 375 | 0 | 1610 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 130.3644 | 100
52 | aanpassen smeersysteem pomp 2 | 2012-04-27 08:00 | 2012-04-27 17:00 | 1d | ploeg 1&2 | 750 | 335 | 0 | 0 | 1085 | 2012-05-10 08:00 | 1d | 1085 | 0 | 0 | 415 | 0 | 1500 | 0 | 100% | Finished | 1085 | 1085 | 100 | 100 | 100 | 100 | 138.2488 | 100
53 | leveren en plaatsen bekabeling noodschuiven | 2012-04-30 08:00 | 2012-05-03 17:00 | 4d | ploeg 1&2 | 3000 | 1523 | 0 | 0 | 4523 | 2012-04-23 08:00 | 5d | 5273 | 0 | 0 | -373 | 0 | 4900 | 0 | 100% | Finished | 4523 | 4523 | 100 | 125 | 100 | 100 | 108.3352 | 100
54 | proefdraaien pomp 2 op nieuw ALSB | 2012-04-30 08:00 | 2012-04-30 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-05-11 08:00 | 1d | 1123 | 0 | 0 | -123 | 0 | 1000 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 89.0472 | 100
55 | aansluiten noodschuif 1 + in dienst stellen | 2012-05-02 08:00 | 2012-05-02 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-29 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
56 | aansluiten noodschuif 2 + in dienst stellen | 2012-05-03 08:00 | 2012-05-03 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-30 08:00 | 1d | 1235 | 0 | 0 | 165 | 0 | 1400 | 0 | 100% | Finished | 1235 | 1235 | 100 | 100 | 100 | 100 | 113.3603 | 100
57 | aansluiten noodschuif 3 + in dienst stellen | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d | ploeg 1&2 | 750 | 485 | 0 | 0 | 1235 | 2012-05-31 08:00 | 2d | 1985 | 0 | 0 | -385 | 0 | 1600 | 0 | 100% | Finished | 1235 | 1235 | 100 | 200 | 100 | 100 | 129.5547 | 100
58 | leveren en plaatsen seinborden | 2012-05-07 08:00 | 2012-05-09 17:00 | 3d | ploeg 1&2 | 2250 | 1314 | 0 | 0 | 3564 | 2012-07-02 08:00 | 4d | 4314 | 0 | 0 | 1986 | 0 | 6300 | 0 | 100% | Finished | 3564 | 3564 | 100 | 133.3333 | 100 | 100 | 176.7677 | 100
59 | leveren, plaatsen en aansluiten buitenverlichtingspaal | 2012-05-07 08:00 | 2012-05-07 17:00 | 1d | ploeg 1&2 | 750 | 1089.71 | 0 | 0 | 1839.71 | 2012-07-06 08:00 | 1d | 1839.71 | 0 | 0 | 1250 | 0 | 3089.71 | 0 | 100% | Finished | 1839.71 | 1839.71 | 100 | 100 | 100 | 100 | 167.9455 | 100
60 | leveren en plaatsen bekabeling binnenverlichting , stopcontacten en klimatisatie | 2012-05-08 08:00 | 2012-05-11 17:00 | 4d | ploeg 1&2 | 3000 | 1241 | 0 | 0 | 4241 | 2012-05-14 08:00 | 4d | 4241 | 0 | 0 | 0 | 0 | 4241 | 0 | 100% | Finished | 4241 | 4241 | 100 | 100 | 100 | 100 | 100 | 100
61 | omschakelen pomp 3 op nieuw ALSB | 2012-05-14 08:00 | 2012-05-14 12:00 | 4h | ploeg 1&2 | 375 | 917 | 0 | 0 | 1292 | 2012-06-18 08:00 | 1d | 1667 | 0 | 0 | 0 | 0 | 1667 | 0 | 100% | Finished | 1292 | 1292 | 100 | 200 | 100 | 100 | 129.0248 | 100
62 | plaatsen en aansluiten verlichting en stopcontacten pomplokaal | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d | ploeg 1&2 | 3750 | 1478 | 0 | 0 | 5228 | 2012-05-22 08:00 | 4d | 4478 | 0 | 0 | 222 | 0 | 4700 | 0 | 100% | Finished | 5228 | 5228 | 100 | 80 | 100 | 100 | 89.9005 | 100
63 | leveren en plaatsen werkschakelaar pomp 3 | 2012-05-14 13:00 | 2012-05-14 17:00 | 4h | ploeg 1&2 | 375 | 1077 | 0 | 0 | 1452 | 2012-06-19 08:00 | 1d | 1827 | 0 | 0 | 0 | 0 | 1827 | 0 | 100% | Finished | 1452 | 1452 | 100 | 200 | 100 | 100 | 125.8264 | 100
64 | leveren en plaatsen voedingskabel tussen pomp en werkschakelaar + tussen werkschakelaar en nieuw bord 3 | 2012-05-15 08:00 | 2012-05-15 17:00 | 1d | ploeg 1&2 | 750 | 480 | 0 | 0 | 1230 | 2012-06-20 08:00 | 1d | 1230 | 0 | 0 | 170 | 0 | 1400 | 0 | 100% | Finished | 1230 | 1230 | 100 | 100 | 100 | 100 | 113.8211 | 100
65 | leveren en plaatsen voedingskabel smeerpomp 3 | 2012-05-16 08:00 | 2012-05-16 17:00 | 1d | ploeg 1&2 | 750 | 406 | 0 | 0 | 1156 | 2012-06-21 08:00 | 1d | 1156 | 0 | 0 | 0 | 0 | 1156 | 0 | 100% | Finished | 1156 | 1156 | 100 | 100 | 100 | 100 | 100 | 100
66 | aanpassen smeersysteem pomp 3 | 2012-05-17 08:00 | 2012-05-17 17:00 | 1d | ploeg 1&2 | 750 | 345 | 0 | 0 | 1095 | 2012-06-22 08:00 | 1d | 1095 | 0 | 0 | 0 | 0 | 1095 | 0 | 100% | Finished | 1095 | 1095 | 100 | 100 | 100 | 100 | 100 | 100
67 | proefdraaien pomp 3 | 2012-05-21 08:00 | 2012-05-21 17:00 | 1d | ploeg 1&2 | 750 | 373 | 0 | 0 | 1123 | 2012-07-02 08:00 | 1d | 1123 | 0 | 0 | 0 | 0 | 1123 | 0 | 100% | Finished | 1123 | 1123 | 100 | 100 | 100 | 100 | 100 | 100
68 | leveren en installeren branddetectie | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d | ploeg 1&2 | 3750 | 1729.63 | 0 | 0 | 5479.63 | 2012-06-04 08:00 | 5d | 5479.63 | 0 | 0 | 0 | 0 | 5479.63 | 0 | 100% | Finished | 5479.63 | 5479.63 | 100 | 100 | 100 | 100 | 100 | 100
69 | leveren en installeren klimatisatie in pomplokaal , bureau en HS | 2012-05-28 08:00 | 2012-06-06 17:00 | 8d | ploeg 1&2 | 6000 | 2398 | 0 | 0 | 8398 | 2012-06-11 08:00 | 5d | 6148 | 0 | 0 | 852 | 0 | 7000 | 0 | 100% | Finished | 8398 | 8398 | 100 | 62.5 | 100 | 100 | 83.3532 | 100
70 | afbraak bestaand ALSB | 2012-06-04 08:00 | 2012-06-04 17:00 | 1d | ploeg 1&2 | 750 | 420 | 0 | 0 | 1170 | 2012-06-25 08:00 | 1d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1170 | 1170 | 100 | 100 | 100 | 100 | 100 | 100
71 | opmaken as built dossier elekriciteit en mechanica | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d | ploeg 1&2 | 1500 | 4078 | 0 | 0 | 5578 | 2012-06-26 08:00 | 2d | 5578 | 0 | 0 | 0 | 0 | 5578 | 0 | 100% | Finished | 5578 | 5578 | 100 | 100 | 100 | 100 | 100 | 100
72 | kabelnummering bord | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d | ploeg 1&2 | 1500 | 1778.5 | 0 | 0 | 3278.5 | 2012-06-28 08:00 | 2d | 3278.5 | 0 | 0 | 0 | 0 | 3278.5 | 0 | 100% | Finished | 3278.5 | 3278.5 | 100 | 100 | 100 | 100 | 100 | 100
73 | identificatie kabels en toestellen | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 3690.46 | 0 | 0 | 10440.46 | 2012-07-03 08:00 | 9d | 10440.46 | 0 | 0 | 0 | 0 | 10440.46 | 0 | 100% | Finished | 10440.46 | 10440.46 | 100 | 100 | 100 | 100 | 100 | 100
74 | schilderwerken | 2012-06-12 08:00 | 2012-06-22 17:00 | 9d | ploeg 1&2 | 6750 | 5236.9302 | 0 | 0 | 11986.9302 | 2012-07-09 08:00 | 5d | 8986.9302 | 0 | 0 | 3513.0701 | 0 | 12500.0002 | 0 | 100% | Finished | 11986.9302 | 11986.9302 | 100 | 55.5556 | 100 | 100 | 104.2802 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
09/01, 2012 | 2012-01-02 08:00 | 2012-01-09 08:00 | 53725 | 53725 | 54635 | 2012-01-06 17:00 | 0 | 100% | -910 | 98.33% | 0 | 100% | 100% | 2012-06-22 17:00 | 2012-06-22 17:00 | 2012-06-27 09:00 | 2012-06-22 17:00 | 2012-06-22 17:00 | 2012-06-26 17:00 | 2012-06-22 17:00 | 2012-06-22 17:00 | 2012-06-26 17:00 | 337320.1494 | 342108.3018 | 337320.1494 | 337320.1494 | 342108.3018 | 342108.3018 | 341137.7387 | 341137.7387 | 1 | 0.98334 | 1 | 1 | 0 | 0.98334 | 1 | 1 | 1
16/01, 2012 | 2012-01-09 08:00 | 2012-01-16 08:00 | 60975 | 61912.5 | 62635 | 2012-01-17 09:00 | 937.5 | 101.5% | -722.5 | 98.85% | 1d 1h | 111.2% | 99.4% | 2012-06-22 14:00 | 2012-06-21 09:00 | 2012-06-22 12:00 | 2012-06-22 16:00 | 2012-06-21 09:00 | 2012-06-22 11:00 | 2012-06-21 16:00 | 2012-06-06 11:00 | 2012-06-07 12:00 | 337132.6494 | 340335.9533 | 332976.1132 | 309374.4601 | 336130.9116 | 312253.8344 | 338832.1003 | 333537.2529 | 1.1125 | 0.98846 | 1.0154 | 0.99396 | 1.125 | 0.98846 | 1 | 1.1125 | 1
23/01, 2012 | 2012-01-16 08:00 | 2012-01-23 08:00 | 69157 | 71032 | 71356.5 | 2012-01-25 12:00 | 1875 | 102.7% | -324.5 | 99.55% | 2d 4h | 116.7% | 100% | 2012-06-22 10:00 | 2012-06-19 15:00 | 2012-06-20 10:00 | 2012-06-22 14:00 | 2012-06-19 15:00 | 2012-06-20 10:00 | 2012-06-20 12:00 | 2012-05-30 09:00 | 2012-05-30 14:00 | 336734.6494 | 337946.9932 | 329729.5808 | 298823.4852 | 330909.923 | 299862.6371 | 336261.959 | 329081.4396 | 1.1667 | 0.99545 | 1.0271 | 1 | 2.5 | 0.99545 | 1 | 1.1667 | 1
30/01, 2012 | 2012-01-23 08:00 | 2012-01-30 08:00 | 72907 | 75719.5 | 75106.5 | 2012-02-02 15:00 | 2812.5 | 103.9% | 613 | 100.8% | 3d 6h | 118.8% | 100% | 2012-06-21 17:00 | 2012-06-18 11:00 | 2012-06-15 11:00 | 2012-06-22 10:00 | 2012-06-18 11:00 | 2012-06-15 12:00 | 2012-06-19 10:00 | 2012-05-28 10:00 | 2012-05-25 14:00 | 335797.1494 | 333686.6842 | 326114.1423 | 294635.4679 | 324082.0676 | 292858.2341 | 332135.8426 | 324803.1567 | 1.1875 | 1.0082 | 1.0386 | 1 | 3.75 | 1.0082 | 1 | 1.1875 | 1
06/02, 2012 | 2012-01-30 08:00 | 2012-02-06 08:00 | 76657 | 89350.52 | 87800.02 | 2012-02-08 09:00 | 12693.52 | 116.6% | 1550.5 | 101.8% | 2d 1h | 108.5% | 94.65% | 2012-06-18 10:00 | 2012-05-30 10:00 | 2012-05-28 11:00 | 2012-06-18 16:00 | 2012-05-30 10:00 | 2012-05-28 16:00 | 2012-06-20 16:00 | 2012-06-11 10:00 | 2012-06-07 14:00 | 334859.6494 | 330572.4225 | 299761.2935 | 315504.7475 | 296083.1285 | 311553.3863 | 323713.8384 | 327401.4419 | 1.085 | 1.0177 | 1.1656 | 0.94648 | 2.125 | 1.0177 | 1 | 1.085 | 1
13/02, 2012 | 2012-02-06 08:00 | 2012-02-13 08:00 | 94159.52 | 104365.52 | 103200.02 | 2012-02-20 09:00 | 10206 | 110.8% | 1165.5 | 101.1% | 5d 1h | 117.1% | 90.25% | 2012-06-19 10:00 | 2012-06-06 15:00 | 2012-06-05 12:00 | 2012-06-19 15:00 | 2012-06-06 15:00 | 2012-06-05 16:00 | 2012-06-15 16:00 | 2012-05-29 15:00 | 2012-05-28 16:00 | 335244.6494 | 332653.2953 | 312552.7921 | 301387.6038 | 310214.8489 | 299174.3477 | 328330.2281 | 325635.1091 | 1.1708 | 1.0113 | 1.1084 | 0.9025 | 5.125 | 1.0113 | 1 | 1.1708 | 1
20/02, 2012 | 2012-02-13 08:00 | 2012-02-20 08:00 | 99500.52 | 124535.52 | 123370.02 | 2012-02-27 09:00 | 25035 | 125.2% | 1165.5 | 100.9% | 5d 1h | 114.6% | 93.93% | 2012-06-11 15:00 | 2012-05-18 16:00 | 2012-05-17 16:00 | 2012-06-12 10:00 | 2012-05-18 16:00 | 2012-05-18 10:00 | 2012-06-15 16:00 | 2012-05-31 17:00 | 2012-05-31 11:00 | 335244.6494 | 333261.7622 | 292652.1316 | 308182.7808 | 291067.8583 | 306453.1597 | 323652.4814 | 327715.841 | 1.1464 | 1.0094 | 1.2516 | 0.93931 | 5.125 | 1.0094 | 1 | 1.1464 | 1
27/02, 2012 | 2012-02-20 08:00 | 2012-02-27 08:00 | 118901.52 | 144449.52 | 143342.02 | 2012-03-05 17:00 | 25548 | 121.5% | 1107.5 | 100.8% | 6d | 115% | 97.91% | 2012-06-11 12:00 | 2012-05-23 16:00 | 2012-05-23 09:00 | 2012-06-12 11:00 | 2012-05-23 16:00 | 2012-05-23 11:00 | 2012-06-14 17:00 | 2012-05-31 15:00 | 2012-05-31 09:00 | 335302.6494 | 333830.8799 | 301351.6182 | 310264.3064 | 300140.1526 | 308984.5069 | 326309.0166 | 328599.8326 | 1.15 | 1.0077 | 1.2149 | 0.97913 | 6 | 1.0077 | 1 | 1.15 | 1
05/03, 2012 | 2012-02-27 08:00 | 2012-03-05 08:00 | 137860.52 | 161456.3902 | 160454.3101 | 2012-03-09 17:00 | 23595.8701 | 117.1% | 1002.08 | 100.6% | 5d | 111.1% | 100% | 2012-06-12 10:00 | 2012-05-29 15:00 | 2012-05-29 09:00 | 2012-06-13 10:00 | 2012-05-29 15:00 | 2012-05-29 11:00 | 2012-06-15 17:00 | 2012-06-06 12:00 | 2012-06-06 09:00 | 335408.0694 | 334322.2179 | 309839.6408 | 317912.6934 | 308912.4799 | 316935.4271 | 328804.0904 | 330772.2806 | 1.1111 | 1.0062 | 1.1712 | 1 | 5 | 1.0062 | 1 | 1.1111 | 1
12/03, 2012 | 2012-03-05 08:00 | 2012-03-12 08:00 | 161456.3901 | 168203.6802 | 168154.3102 | 2012-03-12 09:00 | 6747.29 | 104.2% | 49.37 | 100% | 1h | 100.2% | 79.44% | 2012-06-20 12:00 | 2012-06-15 17:00 | 2012-06-15 17:00 | 2012-06-20 16:00 | 2012-06-15 17:00 | 2012-06-15 17:00 | 2012-06-22 16:00 | 2012-06-22 15:00 | 2012-06-22 14:00 | 336360.7794 | 336311.4086 | 329613.3775 | 335941.3119 | 329565.9871 | 335892.0642 | 334927.71 | 336237.2587 | 1.0025 | 1.0003 | 1.0418 | 0.79445 | 0.125 | 1.0003 | 1 | 1.0025 | 1
19/03, 2012 | 2012-03-12 08:00 | 2012-03-19 08:00 | 213658.4692 | 213658.4692 | 216154.3092 | 2012-03-16 17:00 | 0 | 100% | -2495.84 | 98.85% | 0 | 100% | 100% | 2012-06-22 17:00 | 2012-06-22 17:00 | 2012-06-26 12:00 | 2012-06-22 17:00 | 2012-06-22 17:00 | 2012-06-25 16:00 | 2012-06-22 17:00 | 2012-06-22 17:00 | 2012-06-25 16:00 | 338905.9894 | 340339.9065 | 338905.9894 | 338905.9894 | 340339.9065 | 340339.9065 | 340050.4493 | 340050.4493 | 1 | 0.98845 | 1 | 1 | 0 | 0.98845 | 1 | 1 | 1
26/03, 2012 | 2012-03-19 08:00 | 2012-03-26 08:00 | 224450.7692 | 220825.7692 | 224444.6092 | 2012-03-21 10:00 | -3625 | 98.38% | -3618.84 | 98.39% | -2d 6h | 95.42% | 98.58% | 2012-06-26 11:00 | 2012-06-26 17:00 | 2012-06-29 09:00 | 2012-06-25 17:00 | 2012-06-26 17:00 | 2012-06-28 09:00 | 2012-06-27 15:00 | 2012-07-02 17:00 | 2012-07-04 09:00 | 340028.9894 | 341923.1586 | 341926.3829 | 345581.0775 | 343851.6461 | 347566.233 | 341923.8034 | 342636.9619 | 0.95417 | 0.98388 | 0.98385 | 0.98584 | -2.75 | 0.98388 | 1 | 0.95417 | 1
02/04, 2012 | 2012-03-26 08:00 | 2012-04-02 08:00 | 236714.2692 | 232461.2692 | 237952.3091 | 2012-03-27 17:00 | -4253 | 98.2% | -5491.04 | 97.69% | -3d | 95.38% | 98.48% | 2012-06-26 14:00 | 2012-06-27 10:00 | 2012-07-02 10:00 | 2012-06-26 09:00 | 2012-06-27 10:00 | 2012-06-28 15:00 | 2012-06-27 17:00 | 2012-07-02 17:00 | 2012-07-04 14:00 | 341901.1894 | 344356.5982 | 343802.9883 | 346930.9739 | 346303.3201 | 349505.1928 | 344245.4134 | 344861.6969 | 0.95385 | 0.97692 | 0.98203 | 0.98481 | -3 | 0.97692 | 1 | 0.95385 | 1
09/04, 2012 | 2012-04-02 08:00 | 2012-04-09 08:00 | 247056.8693 | 239401.2692 | 245850.3091 | 2012-03-30 17:00 | -7655.6001 | 96.9% | -6449.04 | 97.38% | -5d | 92.86% | 100% | 2012-06-27 16:00 | 2012-06-28 17:00 | 2012-07-04 12:00 | 2012-06-27 09:00 | 2012-06-28 17:00 | 2012-07-02 14:00 | 2012-06-29 17:00 | 2012-07-06 14:00 | 2012-07-10 11:00 | 342859.1894 | 345472.4343 | 345961.35 | 350321.4109 | 348658.1615 | 353135.6747 | 345569.835 | 346405.8821 | 0.92857 | 0.97377 | 0.96901 | 1 | -5 | 0.97377 | 1 | 0.92857 | 1
16/04, 2012 | 2012-04-09 08:00 | 2012-04-16 08:00 | 252725.9193 | 239401.2692 | 245850.3091 | 2012-03-30 17:00 | -13324.6501 | 94.73% | -6449.04 | 97.38% | -10d | 86.67% | 100% | 2012-06-29 17:00 | 2012-07-03 17:00 | 2012-07-09 12:00 | 2012-06-28 17:00 | 2012-07-03 17:00 | 2012-07-05 12:00 | 2012-07-06 17:00 | 2012-07-20 10:00 | 2012-07-24 09:00 | 342859.1894 | 345472.4343 | 348258.5316 | 357783.6325 | 351017.2251 | 360798.915 | 346017.4597 | 347713.1497 | 0.86667 | 0.97377 | 0.94728 | 1 | -10 | 0.97377 | 1 | 0.86667 | 1
23/04, 2012 | 2012-04-16 08:00 | 2012-04-23 08:00 | 252725.9193 | 247056.8693 | 253850.3092 | 2012-04-06 17:00 | -5669.05 | 97.76% | -6793.44 | 97.32% | -10d | 87.5% | 100% | 2012-06-27 09:00 | 2012-06-27 16:00 | 2012-07-03 11:00 | 2012-06-26 15:00 | 2012-06-27 16:00 | 2012-06-29 09:00 | 2012-07-06 17:00 | 2012-07-18 16:00 | 2012-07-20 14:00 | 343203.5894 | 345660.5789 | 345253.9198 | 355968.3437 | 347767.2882 | 358776.3317 | 345578.9578 | 347552.2278 | 0.875 | 0.97324 | 0.97757 | 1 | -10 | 0.97324 | 1 | 0.875 | 1
30/04, 2012 | 2012-04-23 08:00 | 2012-04-30 08:00 | 258506.9193 | 257248.9193 | 265056.0092 | 2012-04-26 15:00 | -1258 | 99.51% | -7807.09 | 97.05% | -1d 2h | 98.53% | 98.25% | 2012-06-25 12:00 | 2012-06-25 14:00 | 2012-06-29 11:00 | 2012-06-25 11:00 | 2012-06-25 14:00 | 2012-06-26 16:00 | 2012-06-26 10:00 | 2012-06-26 16:00 | 2012-06-28 09:00 | 344217.2393 | 346619.6551 | 344604.354 | 345398.7502 | 347018.518 | 347837.0229 | 346208.467 | 346372.5146 | 0.98529 | 0.97055 | 0.99513 | 0.98247 | -1.25 | 0.97055 | 1 | 0.98529 | 1
07/05, 2012 | 2012-04-30 08:00 | 2012-05-07 08:00 | 267857.9193 | 258541.9193 | 267256.0092 | 2012-04-27 17:00 | -9316 | 96.52% | -8714.09 | 96.74% | -5d | 94.44% | 98.26% | 2012-06-28 12:00 | 2012-06-29 12:00 | 2012-07-05 16:00 | 2012-06-28 09:00 | 2012-06-29 12:00 | 2012-07-02 16:00 | 2012-06-29 17:00 | 2012-07-04 11:00 | 2012-07-05 15:00 | 345124.2393 | 347748.7683 | 347930.0529 | 349704.7235 | 350649.1512 | 352483.6365 | 347784.96 | 348132.4997 | 0.94444 | 0.96739 | 0.96522 | 0.98264 | -5 | 0.96739 | 1 | 0.94444 | 1
14/05, 2012 | 2012-05-07 08:00 | 2012-05-14 08:00 | 277502.6292 | 264152.9193 | 274066.0092 | 2012-05-02 14:00 | -13349.71 | 95.19% | -9913.09 | 96.38% | -7d 3h | 92.24% | 99.64% | 2012-06-29 17:00 | 2012-07-03 11:00 | 2012-07-10 10:00 | 2012-06-29 14:00 | 2012-07-03 11:00 | 2012-07-04 14:00 | 2012-07-04 11:00 | 2012-07-09 12:00 | 2012-07-10 17:00 | 346323.2393 | 349034.8975 | 349974.9615 | 352404.8036 | 352823.6609 | 355344.6898 | 349221.043 | 349685.4833 | 0.92237 | 0.96383 | 0.95189 | 0.99639 | -7.375 | 0.96383 | 1 | 0.92237 | 1
21/05, 2012 | 2012-05-14 08:00 | 2012-05-21 08:00 | 288955.6292 | 267643.9193 | 277557.0092 | 2012-05-04 14:00 | -21311.71 | 92.62% | -9913.09 | 96.43% | -10d 3h | 89.62% | 98.72% | 2012-07-04 16:00 | 2012-07-06 17:00 | 2012-07-13 17:00 | 2012-07-04 11:00 | 2012-07-06 17:00 | 2012-07-10 10:00 | 2012-07-09 11:00 | 2012-07-13 12:00 | 2012-07-16 16:00 | 346323.2393 | 348870.2272 | 351798.895 | 354283.6258 | 354548.6922 | 357125.4533 | 349437.3292 | 349890.9221 | 0.89625 | 0.96428 | 0.92625 | 0.9872 | -10.375 | 0.96428 | 1 | 0.89625 | 1
28/05, 2012 | 2012-05-21 08:00 | 2012-05-28 08:00 | 295558.2592 | 272871.9193 | 283007.0092 | 2012-05-07 17:00 | -22686.3399 | 92.32% | -10135.0899 | 96.42% | -14d | 86.67% | 97.2% | 2012-07-05 11:00 | 2012-07-09 11:00 | 2012-07-16 11:00 | 2012-07-04 17:00 | 2012-07-09 11:00 | 2012-07-10 12:00 | 2012-07-12 17:00 | 2012-07-20 10:00 | 2012-07-23 15:00 | 346545.2393 | 348905.1951 | 351827.7539 | 356320.3516 | 354383.9144 | 359043.3776 | 349469.6792 | 350265.7499 | 0.86667 | 0.96419 | 0.92324 | 0.972 | -14 | 0.96419 | 1 | 0.86667 | 1
04/06, 2012 | 2012-05-28 08:00 | 2012-06-04 08:00 | 301706.2592 | 276576.9193 | 287407.0092 | 2012-05-10 15:00 | -25129.3399 | 91.67% | -10830.0899 | 96.23% | -16d 2h | 85.23% | 98.05% | 2012-07-06 11:00 | 2012-07-10 11:00 | 2012-07-17 15:00 | 2012-07-06 09:00 | 2012-07-10 11:00 | 2012-07-11 11:00 | 2012-07-17 10:00 | 2012-07-24 14:00 | 2012-07-26 09:00 | 347240.2393 | 349583.1653 | 352676.5916 | 357611.3325 | 355232.3922 | 360360.3657 | 350178.1682 | 351038.4718 | 0.85227 | 0.96232 | 0.91671 | 0.98046 | -16.25 | 0.96232 | 1 | 0.85227 | 1
11/06, 2012 | 2012-06-04 08:00 | 2012-06-11 08:00 | 313982.7592 | 282056.5493 | 292886.6392 | 2012-05-14 14:00 | -31926.2099 | 89.83% | -10830.0899 | 96.3% | -19d 3h | 83.15% | 97.21% | 2012-07-10 16:00 | 2012-07-13 09:00 | 2012-07-20 12:00 | 2012-07-10 15:00 | 2012-07-13 09:00 | 2012-07-16 09:00 | 2012-07-20 11:00 | 2012-07-30 11:00 | 2012-07-31 14:00 | 347240.2393 | 349327.2477 | 353392.5674 | 358253.0602 | 355715.806 | 360762.9265 | 350096.0133 | 350911.9231 | 0.83152 | 0.96302 | 0.89832 | 0.9721 | -19.375 | 0.96302 | 1 | 0.83152 | 1
18/06, 2012 | 2012-06-11 08:00 | 2012-06-18 08:00 | 328910.1494 | 288204.5493 | 299886.6392 | 2012-05-17 16:00 | -40705.6001 | 87.62% | -11682.0899 | 96.1% | -21d 1h | 82.4% | 96% | 2012-07-16 09:00 | 2012-07-18 14:00 | 2012-07-26 11:00 | 2012-07-13 16:00 | 2012-07-18 14:00 | 2012-07-19 14:00 | 2012-07-24 09:00 | 2012-07-31 15:00 | 2012-08-01 17:00 | 348092.2393 | 350046.2062 | 354900.7296 | 358391.5394 | 357130.672 | 360762.9784 | 350947.3403 | 351519.2146 | 0.82396 | 0.96104 | 0.87624 | 0.95995 | -21.125 | 0.96104 | 1 | 0.82396 | 1
25/06, 2012 | 2012-06-18 08:00 | 2012-06-25 08:00 | 336410.1494 | 295179.5493 | 307031.6392 | 2012-05-25 11:00 | -41230.6001 | 87.74% | -11852.09 | 96.14% | -20d 5h | 83.5% | 97.79% | 2012-07-16 11:00 | 2012-07-18 12:00 | 2012-07-26 09:00 | 2012-07-16 11:00 | 2012-07-18 12:00 | 2012-07-19 09:00 | 2012-07-23 14:00 | 2012-07-27 15:00 | 2012-07-30 15:00 | 348262.2393 | 349917.7361 | 354021.3185 | 356409.6034 | 355908.0546 | 358392.2343 | 350680.0951 | 351075.861 | 0.835 | 0.9614 | 0.87744 | 0.97788 | -20.625 | 0.9614 | 1 | 0.835 | 1
02/07, 2012 | 2012-06-25 08:00 | 2012-07-02 08:00 | 336410.1494 | 305206.0493 | 317058.1392 | 2012-06-04 17:00 | -31204.1001 | 90.72% | -11852.09 | 96.26% | -19d | 85.38% | 97.6% | 2012-07-10 14:00 | 2012-07-11 15:00 | 2012-07-19 09:00 | 2012-07-17 17:00 | 2012-07-19 10:00 | 2012-07-19 15:00 | 2012-07-19 17:00 | 2012-07-24 11:00 | 2012-07-24 17:00 | 348262.2393 | 349473.9906 | 351452.5295 | 353603.4817 | 352788.1695 | 355022.6498 | 349851.2759 | 350223.5037 | 0.85385 | 0.96262 | 0.90724 | 0.97603 | -19 | 0.96262 | 1 | 0.85385 | 1
09/07, 2012 | 2012-07-02 08:00 | 2012-07-09 08:00 | 336410.1494 | 318423.2192 | 334261.3092 | 2012-06-11 17:00 | -17986.9302 | 94.65% | -15838.0899 | 95.26% | -19d | 85.93% | 99.28% | 2012-07-03 14:00 | 2012-07-03 17:00 | 2012-07-12 14:00 | 2012-07-18 10:00 | 2012-07-18 14:00 | 2012-07-18 17:00 | 2012-07-19 17:00 | 2012-07-23 12:00 | 2012-07-23 17:00 | 352248.2393 | 353142.8934 | 353264.276 | 355194.3744 | 354209.4668 | 356235.5666 | 353167.0457 | 353520.3786 | 0.85926 | 0.95262 | 0.94653 | 0.99283 | -19 | 0.95262 | 1 | 0.85926 | 1
Actual Schedule | 2012-07-09 08:00 | 2012-07-16 08:00 | 336410.1494 | 336410.1494 | 350511.3094 | 2012-06-22 17:00 | 0 | 100% | -14101.16 | 95.98% | -15d | 89.29% | 100% | 2012-06-22 17:00 | 2012-06-22 17:00 | 2012-07-02 10:00 | 2012-07-13 17:00 | 2012-07-13 17:00 | 2012-07-13 17:00 | 2012-07-13 17:00 | 2012-07-13 17:00 | 2012-07-13 17:00 | 350511.3094 | 350511.3094 | 350511.3094 | 350511.3094 | 350511.3094 | 350511.3094 | 350511.3094 | 350511.3094 | 0.89286 | 0.95977 | 1 | 1 | -15 | 0.95977 | 1 | 0.89286 | 1