## Baseline Schedule1
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Project |  |  |  | Tue 20/09/16 | Sun 29/01/17 | 84d
1 | New Product Development |  |  |  | Tue 20/09/16 | Sun 29/01/17 | 84d
2 | Phase 1 - High-Level Planning |  |  |  | Tue 20/09/16 | Mon 10/10/16 | 13d
3 | Determine sales objectives |  |  | 4 | Tue 20/09/16 | Wed 21/09/16 | 1d |  |  | $0,00 | 12 | 96
4 | Define launch goals (launch timing and publicity objectives) |  | 3 |  | Wed 21/09/16 | Sat 24/09/16 | 1d |  |  | $0,00 | 12 | 96
5 | Establish Launch Budget |  |  |  | Sat 24/09/16 | Mon 10/10/16 | 11d
6 | Identify budget requirements |  | 4 |  | Sat 24/09/16 | Sun 25/09/16 | 1d |  |  | $0,00 | 12 | 96
7 | Obtain launch budget approval |  | 6FS+5 days |  | Mon 3/10/16 | Mon 10/10/16 | 5d |  |  | $0,00 | 12 | 480
8 | High-Level Planning Complete |  | 7 |  | Mon 10/10/16 | Mon 10/10/16 | 0d |  |  | $0,00 | 0 | 0
9 | Phase 2 - Detailed Planning |  |  |  | Mon 10/10/16 | Sat 5/11/16 | 19,68d
10 | Kickoff product launch |  | 8 |  | Mon 10/10/16 | Tue 11/10/16 | 2d |  |  | $463,00 | 8 | 128
11 | Marketing |  |  |  | Wed 12/10/16 | Tue 18/10/16 | 5d
12 | Define press release requirements |  | 10 |  | Wed 12/10/16 | Sat 15/10/16 | 1d |  |  | $312,00 | 10 | 80
13 | Define sales presentations |  | 10 |  | Sun 16/10/16 | Tue 18/10/16 | 2d |  |  | $320,00 | 10 | 160
14 | Define product specification literature |  | 10 |  | Wed 12/10/16 | Sun 16/10/16 | 5d |  |  | $160,00 | 20 | 800
15 | Define internal communication needs |  | 10 |  | Wed 12/10/16 | Sat 15/10/16 | 1d |  |  | $200,00 | 10 | 80
16 | Engineering |  |  |  | Tue 18/10/16 | Sun 23/10/16 | 4d
17 | Align product release timing with marketing plan |  | 15,12,13,14 |  | Tue 18/10/16 | Sun 23/10/16 | 4d |  |  | $680,00 | 12 | 384
18 | Manufacturing |  |  |  | Sun 23/10/16 | Wed 26/10/16 | 3,88d
19 | Prepare for volume manufacturing according to sales goals |  | 17 |  | Sun 23/10/16 | Wed 26/10/16 | 2d |  |  | $512,00 | 10 | 160
20 | Sales |  |  |  | Wed 26/10/16 | Sat 29/10/16 | 2d
21 | Plan sales force staffing and training to support sales goals |  | 19 |  | Wed 26/10/16 | Sat 29/10/16 | 2d |  |  | $448,00 | 10 | 160
22 | Product Support |  |  |  | Sat 29/10/16 | Sat 5/11/16 | 4,8d
23 | Plan team staffing to support sales goals |  | 21 |  | Sat 29/10/16 | Sat 5/11/16 | 4,8d |  |  | 1536 | 10 | 380
24 | Phase 3 - Execution |  |  |  | Sat 5/11/16 | Wed 1/02/17 | 55d
25 | Marketing |  |  |  | Sat 5/11/16 | Sun 11/12/16 | 22d
26 | Evaluate market and refine messaging |  | 23 |  | Sat 5/11/16 | Mon 7/11/16 | 1d |  |  | 250 | 15 | 120
27 | Create press releases |  | 26 |  | Mon 7/11/16 | Wed 9/11/16 | 2d |  |  | 100 | 15 | 240
28 | Create product specification literature |  | 27 |  | Wed 9/11/16 | Sat 19/11/16 | 5d |  |  | 100 | 15 | 600
29 | Create sales presentations |  | 28 |  | Sat 19/11/16 | Sun 27/11/16 | 5d |  |  | 100 | 15 | 600
30 | Create sales, field, and product support training |  | 29 |  | Sun 27/11/16 | Sun 4/12/16 | 5d |  |  | 100 | 15 | 600
31 | Update product forecasts based on market feedback and analysis |  | 30 |  | Sun 4/12/16 | Wed 7/12/16 | 2d |  |  | 100 | 15 | 240
32 | Update launch plan based on forecast |  | 31 |  | Wed 7/12/16 | Sun 11/12/16 | 2d |  |  | 100 | 15 | 240
33 | Engineering |  |  |  | Sat 5/11/16 | Sat 24/12/16 | 30d
34 | Complete and test product |  | 26SS |  | Sat 5/11/16 | Sat 24/12/16 | 30d |  |  | 2500 | 20 | 4800
35 | Manufacturing |  |  |  | Sat 24/12/16 | Wed 1/02/17 | 25d
36 | Create prototype products |  | 34 |  | Sat 24/12/16 | Tue 24/01/17 | 20d |  |  | 1000 | 28 | 4480
37 | Prepare pipeline |  | 36 |  | Tue 24/01/17 | Wed 1/02/17 | 5d |  |  | 0 | 15 | 600
38 | Sales |  |  |  | Wed 7/12/16 | Sun 11/12/16 | 2d
39 | Establish sales channels |  | 31 |  | Wed 7/12/16 | Sun 11/12/16 | 2d |  |  | 500 | 10 | 160
40 | Product Support |  |  |  | Sun 11/12/16 | Tue 13/12/16 | 2d
41 | Establish product support mechanisms |  | 39 |  | Sun 11/12/16 | Tue 13/12/16 | 2d |  |  | 400 | 10 | 160
42 | Execution Phase Complete |  | 41 |  | Tue 13/12/16 | Tue 13/12/16 | 0d |  |  | 0 | 0 | 0
43 | Phase 4 - Release To Manufacture |  |  |  | Tue 13/12/16 | Tue 7/02/17 | 35d
44 | Manufacturing |  |  |  | Tue 13/12/16 | Tue 7/02/17 | 35d
45 | Certify product |  | 42 |  | Tue 13/12/16 | Wed 21/12/16 | 5d |  |  | 200 | 12 | 480
46 | Manufacture the volume of product planned to meet sales objectives. |  | 45 |  | Wed 21/12/16 | Tue 7/02/17 | 30d |  |  | 1000 | 8 | 1920
47 | Sales |  |  |  | Sat 24/12/16 | Mon 9/01/17 | 10d
48 | Hire and train sales staff |  | 36SS |  | Sat 24/12/16 | Mon 9/01/17 | 10d |  |  | 500 | 12 | 960
49 | Product Support |  |  |  | Mon 9/01/17 | Tue 24/01/17 | 10d
50 | Hire and train product support personnel |  | 48 |  | Mon 9/01/17 | Tue 24/01/17 | 10d |  |  | 400 | 12 | 960
51 | Final Quality Review |  |  |  | Tue 24/01/17 | Sun 29/01/17 | 3d
52 | Conduct final quality review |  | 50 |  | Tue 24/01/17 | Sun 29/01/17 | 3d |  |  | 0 | 10 | 240
53 | Product Release Information Complete |  | 52 |  | Sun 29/01/17 | Sun 29/01/17 | 0d |  |  | 0 | 0 | 0
54 | Needed materials are on order or in stock. |  | 53 |  | Sun 29/01/17 | Sun 29/01/17 | 0d |  |  | 0 | 0 | 0
55 | Literature Complete |  | 54 |  | Sun 29/01/17 | Sun 29/01/17 | 0d |  |  | 0 | 0 | 0
56 | Training Complete |  | 48,50 |  | Tue 24/01/17 | Tue 24/01/17 | 0d |  |  | 0 | 0 | 0
57 | Launch Product |  | 55,56 |  | Sun 29/01/17 | Sun 29/01/17 | 0d |  |  | 0 | 0 | 0

## Risk Analysis1
General | Baseline | Activity Duration Distribution Profiles
ID | Duration | Description | Optimistic | Most Probable | Pessimistic
1 | New Product Development
2 | Phase 1 - High-Level Planning
3 | Determine sales objectives |  | 6h | 1d | 1d 2h
4 | Define launch goals (launch timing and publicity objectives) |  | 6h | 1d | 1d 2h
5 | Establish Launch Budget
6 | Identify budget requirements |  | 6h | 1d | 1d 2h
7 | Obtain launch budget approval |  | 4d | 1w | 1w 1d
8 | High-Level Planning Complete
9 | Phase 2 - Detailed Planning
10 | Kickoff product launch |  | 1d 5h | 2d | 2d 3h
11 | Marketing
12 | Define press release requirements |  | 6h | 1d | 1d 2h
13 | Define sales presentations |  | 1d 5h | 2d | 2d 3h
14 | Define product specification literature |  | 4d | 1w | 1w 1d
15 | Define internal communication needs |  | 6h | 1d | 1d 2h
16 | Engineering
17 | Align product release timing with marketing plan |  | 3d 2h | 4d | 4d 6h
18 | Manufacturing
19 | Prepare for volume manufacturing according to sales goals |  | 1d 5h | 2d | 2d 3h
20 | Sales
21 | Plan sales force staffing and training to support sales goals |  | 1d 5h | 2d | 2d 3h
22 | Product Support
23 | Plan team staffing to support sales goals |  | 3d 6h | 4d 6h | 1w 6h
24 | Phase 3 - Execution
25 | Marketing
26 | Evaluate market and refine messaging |  | 6h | 1d | 1d 2h
27 | Create press releases |  | 1d 5h | 2d | 2d 3h
28 | Create product specification literature |  | 4d | 1w | 1w 1d
29 | Create sales presentations |  | 4d | 1w | 1w 1d
30 | Create sales, field, and product support training |  | 4d | 1w | 1w 1d
31 | Update product forecasts based on market feedback and analysis |  | 1d 5h | 2d | 2d 3h
32 | Update launch plan based on forecast |  | 1d 5h | 2d | 2d 3h
33 | Engineering
34 | Complete and test product |  | 4w 4d | 6w | 7w 1d
35 | Manufacturing
36 | Create prototype products |  | 3w 1d | 4w | 4w 4d
37 | Prepare pipeline |  | 4d | 1w | 1w 1d
38 | Sales
39 | Establish sales channels |  | 1d 5h | 2d | 2d 3h
40 | Product Support |  | 1d 5h | 2d | 2d 3h
41 | Establish product support mechanisms |  | 1d 5h | 2d | 2d 3h
42 | Execution Phase Complete |  | 0 | 0 | 0
43 | Phase 4 - Release To Manufacture
44 | Manufacturing
45 | Certify product |  | 4d | 1w | 1w 1d
46 | Manufacture the volume of product planned to meet sales objectives. |  | 4w 4d | 6w | 7w 1d
47 | Sales
48 | Hire and train sales staff |  | 1w 3d | 2w | 2w 2d
49 | Product Support
50 | Hire and train product support personnel |  | 1w 3d | 2w | 2w 2d
51 | Final Quality Review
52 | Conduct final quality review |  | 2d 3h | 3d | 3d 5h
53 | Product Release Information Complete |  | 0 | 0 | 0
54 | Needed materials are on order or in stock. |  | 0 | 0 | 0
55 | Literature Complete |  | 0 | 0 | 0
56 | Training Complete |  | 0 | 0 | 0
57 | Launch Product |  | 0 | 0 | 0

## Project Control - TP1
| TP Status Date | Wed 26/10/16 |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | [9 empty] | Tue 20/09/16 | [8 empty] | 12%
1 | New Product Development | [9 empty] | Tue 20/09/16 | 11,43d | [7 empty] | 12%
2 | Phase 1 - High-Level Planning | [9 empty] | Tue 20/09/16 | 13d | [7 empty] | 100%
3 | Determine sales objectives | [9 empty] | Tue 20/09/16 | 1d | [5 empty] | 108 |  | 100%
4 | Define launch goals (launch timing and publicity objectives) | [9 empty] | Wed 21/09/16 | 1d | [5 empty] | 100 |  | 100%
5 | Establish Launch Budget | [9 empty] | Sat 24/09/16 | 11d | [7 empty] | 100%
6 | Identify budget requirements | [9 empty] | Sat 24/09/16 | 1d | [5 empty] | 100 |  | 100%
7 | Obtain launch budget approval | [9 empty] | Mon 3/10/16 | 5d | [5 empty] | 400 |  | 100%
8 | High-Level Planning Complete | [9 empty] | Mon 10/10/16 | 0d | [5 empty] | 0 |  | 100%
9 | Phase 2 - Detailed Planning | [9 empty] | Mon 10/10/16 | 10,99d | [5 empty] | 4321.08 |  | 56%
10 | Kickoff product launch | [9 empty] | Mon 10/10/16 | 2d | [5 empty] | 1000 |  | 100%
11 | Marketing | [9 empty] | Fri 14/10/16 | 4,06d | [7 empty] | 81%
12 | Define press release requirements | [9 empty] | Fri 14/10/16 | 0,5d | [5 empty] | 156 |  | 50%
13 | Define sales presentations | [9 empty] | Sun 16/10/16 | 1,8d | [5 empty] | 288 |  | 90%
14 | Define product specification literature | [9 empty] | Fri 14/10/16 | 5d | [5 empty] | 1150 |  | 100%
15 | Define internal communication needs | [9 empty] | NA | 0d | [7 empty] | 0%
16 | Engineering | [9 empty] | Tue 18/10/16 | 4d | [7 empty] | 100%
17 | Align product release timing with marketing plan | [9 empty] | Tue 18/10/16 | 4d | [5 empty] | 1200 |  | 100%
18 | Manufacturing | [9 empty] | Wed 26/10/16 | 0d | [5 empty] | 0 |  | 0%
19 | Prepare for volume manufacturing according to sales goals | [9 empty] | Wed 26/10/16 | 0d | [5 empty] | 0 |  | 0%
20 | Sales | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
21 | Plan sales force staffing and training to support sales goals | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
22 | Product Support | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
23 | Plan team staffing to support sales goals | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
24 | Phase 3 - Execution | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
25 | Marketing | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
26 | Evaluate market and refine messaging | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
27 | Create press releases | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
28 | Create product specification literature | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
29 | Create sales presentations | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
30 | Create sales, field, and product support training | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
31 | Update product forecasts based on market feedback and analysis | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
32 | Update launch plan based on forecast | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
33 | Engineering | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
34 | Complete and test product | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
35 | Manufacturing | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
36 | Create prototype products | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
37 | Prepare pipeline | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
38 | Sales | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
39 | Establish sales channels | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
40 | Product Support | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
41 | Establish product support mechanisms | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
42 | Execution Phase Complete | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
43 | Phase 4 - Release To Manufacture | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
44 | Manufacturing | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
45 | Certify product | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
46 | Manufacture the volume of product planned to meet sales objectives. | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
47 | Sales | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
48 | Hire and train sales staff | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
49 | Product Support | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
50 | Hire and train product support personnel | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
51 | Final Quality Review | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
52 | Conduct final quality review | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
53 | Product Release Information Complete | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
54 | Needed materials are on order or in stock. | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
55 | Literature Complete | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
56 | Training Complete | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%
57 | Launch Product | [9 empty] | NA | 0d | [5 empty] | 0 |  | 0%

## Project Control - TP2
| TP Status Date | 26/077/2017 |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | [9 empty] | Tue 20/09/16 | 239d | [7 empty] | 100%
1 | New Product Development | [9 empty] | Tue 20/09/16 | 239d | [5 empty] | 35606 |  | 100%
2 | Phase 1 - High-Level Planning | [9 empty] | Tue 20/09/16 | 13d | [5 empty] | 708 |  | 100%
3 | Determine sales objectives | [9 empty] | Tue 20/09/16 | 1d | [5 empty] | 108 |  | 100%
4 | Define launch goals (launch timing and publicity objectives) | [9 empty] | Wed 21/09/16 | 1d | [5 empty] | 100 |  | 100%
5 | Establish Launch Budget | [9 empty] | Sat 24/09/16 | 11d | [5 empty] | 500 |  | 100%
6 | Identify budget requirements | [9 empty] | Sat 24/09/16 | 1d | [5 empty] | 100 |  | 100%
7 | Obtain launch budget approval | [9 empty] | Mon 3/10/16 | 5d | [5 empty] | 400 |  | 100%
8 | High-Level Planning Complete | [9 empty] | Mon 10/10/16 | 0d | [5 empty] | 0 |  | 100%
9 | Phase 2 - Detailed Planning | [9 empty] | Mon 10/10/16 | 26d | [5 empty] | 8387 |  | 100%
10 | Kickoff product launch | [9 empty] | Mon 10/10/16 | 2d | [5 empty] | 1000 |  | 100%
11 | Marketing | [9 empty] | Fri 14/10/16 | 6d | [5 empty] | 2429 |  | 100%
12 | Define press release requirements | [9 empty] | Fri 14/10/16 | 2d | [5 empty] | 425 |  | 100%
13 | Define sales presentations | [9 empty] | Sun 16/10/16 | 2d | [5 empty] | 534 |  | 100%
14 | Define product specification literature | [9 empty] | Fri 14/10/16 | 5d | [5 empty] | 1150 |  | 100%
15 | Define internal communication needs | [9 empty] | Fri 14/10/16 | 2d | [5 empty] | 320 |  | 100%
16 | Engineering | [9 empty] | Tue 18/10/16 | 4d | [5 empty] | 1200 |  | 100%
17 | Align product release timing with marketing plan | [9 empty] | Tue 18/10/16 | 4d | [5 empty] | 1200 |  | 100%
18 | Manufacturing | [9 empty] | Wed 26/10/16 | 5d | [5 empty] | 695 |  | 100%
19 | Prepare for volume manufacturing according to sales goals | [9 empty] | Wed 26/10/16 | 5d | [5 empty] | 695 |  | 100%
20 | Sales | [9 empty] | Tue 02/11/2016 | 3d | [5 empty] | 668 |  | 100%
21 | Plan sales force staffing and training to support sales goals | [9 empty] | Tue 02/11/2016 | 3d | [5 empty] | 668 |  | 100%
22 | Product Support | [9 empty] | Fri 04/11/2016 | 6d | [5 empty] | 1970 |  | 100%
23 | Plan team staffing to support sales goals | [9 empty] | Fri 04/11/2016 | 6d | [5 empty] | 1970 |  | 100%
24 | Phase 3 - Execution | [9 empty] | Mon 14/11/2016 | 128d | [5 empty] | 19451 |  | 100%
25 | Marketing | [9 empty] | Mon 14/11/2016 | 31d | [5 empty] | 3686 |  | 100%
26 | Evaluate market and refine messaging | [9 empty] | Mon 10/01/2017 | 4d | [5 empty] | 388 |  | 100%
27 | Create press releases | [9 empty] | Fri 13/01/2017 | 3d | [5 empty] | 395 |  | 100%
28 | Create product specification literature | [9 empty] | Sat 18/01/17 | 6d | [5 empty] | 720 |  | 100%
29 | Create sales presentations | [9 empty] | Wed 25/01/2017 | 6d | [5 empty] | 715 |  | 100%
30 | Create sales, field, and product support training | [9 empty] | Tue 02/02/2017 | 6d | [5 empty] | 745 |  | 100%
31 | Update product forecasts based on market feedback and analysis | [9 empty] | Fri 10/02/2017 | 2d | [5 empty] | 367 |  | 100%
32 | Update launch plan based on forecast | [9 empty] | Tue 14/02/2017 | 4d | [5 empty] | 356 |  | 100%
33 | Engineering | [9 empty] | Tue 21/02/2017 | 53d | [5 empty] | 7460 |  | 100%
34 | Complete and test product | [9 empty] | Tue 21/02/2017 | 53d | [5 empty] | 7460 |  | 100%
35 | Manufacturing | [9 empty] | Fri 05/05/2017 | 38d | [5 empty] | 6323 |  | 100%
36 | Create prototype products | [9 empty] | Fri 05/05/2017 | 32d | [5 empty] | 5678 |  | 100%
37 | Prepare pipeline | [9 empty] | Web 21/06/2017 | 6d | [5 empty] | 645 |  | 100%
38 | Sales | [9 empty] | Wed 28/06/2017 | 16d | [5 empty] | 1982 |  | 100%
39 | Establish sales channels | [9 empty] | Wed 28/06/2017 | 7d | [5 empty] | 734 |  | 100%
40 | Product Support | [9 empty] | Fri 07/07/2017 | 4d | [5 empty] | 578 |  | 100%
41 | Establish product support mechanisms | [9 empty] | Thu 13/07/2017 | 5d | [5 empty] | 670 |  | 100%
42 | Execution Phase Complete | [9 empty] | Wed 19/07/2017 | 0d | [5 empty] | 0 |  | 100%
43 | Phase 4 - Release To Manufacture | [9 empty] | Wed 19/07/2017 | 72d | [5 empty] | 7060 |  | 100%
44 | Manufacturing | [9 empty] | Wed 19/07/2017 | 41d | [5 empty] | 3898 |  | 100%
45 | Certify product | [9 empty] | Wed 19/07/2017 | 4d | [5 empty] | 758 |  | 100%
46 | Manufacture the volume of product planned to meet sales objectives. | [9 empty] | Tue 25/07/2017 | 37d | [5 empty] | 3140 |  | 100%
47 | Sales | [9 empty] | Fri 15/07/2017 | 12d | [5 empty] | 1537 |  | 100%
48 | Hire and train sales staff | [9 empty] | Fri 15/07/2017 | 12d | [5 empty] | 1537 |  | 100%
49 | Product Support | [9 empty] | Mon 02/07/2017 | 15d | [5 empty] | 1380 |  | 100%
50 | Hire and train product support personnel | [9 empty] | Mon 02/07/2017 | 15d | [5 empty] | 1380 |  | 100%
51 | Final Quality Review | [9 empty] | Mon 23/07/2017 | 4d | [5 empty] | 245 |  | 100%
52 | Conduct final quality review | [9 empty] | Mon 23/07/2017 | 4d | [5 empty] | 245 |  | 100%
53 | Product Release Information Complete | [9 empty] | Tue 26/07/2017 | 0d | [5 empty] | 0 |  | 100%
54 | Needed materials are on order or in stock. | [9 empty] | Tue 26/07/2017 | 0d | [5 empty] | 0 |  | 100%
55 | Literature Complete | [9 empty] | Tue 26/07/2017 | 0d | [5 empty] | 0 |  | 100%
56 | Training Complete | [9 empty] | Tue 26/07/2017 | 0d | [5 empty] | 0 |  | 100%
57 | Launch Product | [9 empty] | Tue 26/07/2017 | 0d | [5 empty] | 0 |  | 100%