## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Project | 1 |  |  | 2017-11-27 08:00 | 2019-05-15 17:00 | 383d |  |  | 75881203.6113 |  |  | 75881203.6113 | 534.375
1 | Stadium | 1.1 |  |  | 2017-11-27 08:00 | 2019-05-15 17:00 | 383d |  |  | 75881203.6113 |  |  | 75881203.6113 | 534.375
2 | Preparatory infrastructure construction | 1.1.1 |  |  | 2017-11-27 08:00 | 2018-01-08 17:00 | 31d |  |  | 312807 |  |  | 312807 | 42.375
3 | Detailed site analysis | 1.1.1.1 |  | FS4;FS5;FS6;FS7;FS8 | 2017-11-27 08:00 | 2017-12-14 17:00 | 14d |  | 0 | 31280.6992 | 0 | 0 | 31280.6992 | 17.375
4 | Road access | 1.1.1.2 | 3FS | FS8 | 2017-12-15 08:00 | 2017-12-28 17:00 | 10d |  | 0 | 46921.0508 | 0 | 0 | 46921.0508 | 13.375
5 | Water supply | 1.1.1.3 | 3FS |  | 2017-12-15 08:00 | 2017-12-28 17:00 | 10d |  | 0 | 78201.75 | 0 | 0 | 78201.75 | 13.375
6 | Electricity | 1.1.1.4 | 3FS |  | 2017-12-15 08:00 | 2017-12-28 17:00 | 10d |  | 0 | 46921.0508 | 0 | 0 | 46921.0508 | 13.375
7 | Storm and sewer water systems | 1.1.1.5 | 3FS |  | 2017-12-15 08:00 | 2018-01-08 17:00 | 17d |  | 0 | 78201.75 | 0 | 0 | 78201.75 | 24.375
8 | Transportation preparation | 1.1.1.6 | 3FS;4FS | FS12 | 2017-12-29 08:00 | 2018-01-04 17:00 | 5d |  | 0 | 31280.6992 | 0 | 0 | 31280.6992 | 6.375
9 | Foundation Work | 1.1.2 |  |  | 2018-01-09 08:00 | 2018-04-09 17:00 | 65d |  |  | 8689113.125 |  |  | 8689113.125 | 90.375
10 | Subsurface drainage | 1.1.2.1 |  | FS11;FS12 | 2018-01-09 08:00 | 2018-01-17 17:00 | 7d |  | 0 | 1303367 | 0 | 0 | 1303367 | 8.375
11 | Groundbreaking ceremony | 1.1.2.2 | 10FS |  | 2018-01-17 17:00 | 2018-01-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
12 | Excavations | 1.1.2.3 | 10FS;8FS | FS13 | 2018-01-18 08:00 | 2018-01-31 17:00 | 10d |  | 0 | 868911.3125 | 0 | 0 | 868911.3125 | 13.375
13 | Placing pipes into the ground | 1.1.2.4 | 12FS | FS14 | 2018-02-01 08:00 | 2018-02-12 17:00 | 8d |  | 0 | 2172278.25 | 0 | 0 | 2172278.25 | 11.375
14 | Lay foundation concrete | 1.1.2.5 | 13FS | FS15 | 2018-02-13 08:00 | 2018-02-26 17:00 | 10d |  | 0 | 2172278.25 | 0 | 0 | 2172278.25 | 13.375
15 | Pour base concrete | 1.1.2.6 | 14FS | FS16 | 2018-02-27 08:00 | 2018-03-19 17:00 | 15d |  | 0 | 1303367 | 0 | 0 | 1303367 | 20.375
16 | Pour concrete for stands | 1.1.2.7 | 15FS | FS18;FS20 | 2018-03-20 08:00 | 2018-04-09 17:00 | 15d |  | 0 | 868911.3125 | 0 | 0 | 868911.3125 | 20.375
17 | Other concrete | 1.1.3 |  |  | 2018-04-10 08:00 | 2018-08-10 17:00 | 89d |  |  | 14461855.5 |  |  | 14461855.5 | 122.375
18 | Building colums | 1.1.3.1 | 16FS | FS19 | 2018-04-10 08:00 | 2018-05-17 17:00 | 28d |  | 0 | 3610464 | 0 | 0 | 3610464 | 37.375
19 | Building raker beams | 1.1.3.2 | 18FS;20FS | FS21;FS22;FS23 | 2018-05-18 08:00 | 2018-07-10 17:00 | 38d |  | 0 | 3610464 | 0 | 0 | 3610464 | 53.375
20 | Building floor slabs | 1.1.3.3 | 16FS | FS19 | 2018-04-10 08:00 | 2018-05-10 17:00 | 23d |  | 0 | 2172278.25 | 0 | 0 | 2172278.25 | 30.375
21 | Building elevator shafts | 1.1.3.4 | 19FS | FS27;FS29 | 2018-07-11 08:00 | 2018-08-08 17:00 | 21d |  | 0 | 1448185.5 | 0 | 0 | 1448185.5 | 28.375
22 | Building stairs | 1.1.3.5 | 19FS | FS25;FS27 | 2018-07-11 08:00 | 2018-08-10 17:00 | 23d |  | 0 | 2172278.25 | 0 | 0 | 2172278.25 | 30.375
23 | Building emergency exits | 1.1.3.6 | 19FS | FS27 | 2018-07-11 08:00 | 2018-07-19 17:00 | 7d |  | 0 | 1448185.5 | 0 | 0 | 1448185.5 | 8.375
24 | Prefabricated elements | 1.1.4 |  |  | 2018-08-13 08:00 | 2018-11-16 17:00 | 70d |  |  | 17378226.25 |  |  | 17378226.25 | 95.375
25 | Building lower tier of the stands | 1.1.4.1 | 22FS | FS26 | 2018-08-13 08:00 | 2018-09-28 17:00 | 35d |  | 0 | 6951290.5 | 0 | 0 | 6951290.5 | 46.375
26 | Building upper tier of the stands | 1.1.4.2 | 25FS;29FS |  | 2018-10-01 08:00 | 2018-11-16 17:00 | 35d |  | 0 | 6951290.5 | 0 | 0 | 6951290.5 | 46.375
27 | Mechanical, electrical& plumbing installations (MEP) | 1.1.4.3 | 21FS;22FS;23FS |  | 2018-08-13 08:00 | 2018-08-31 17:00 | 15d |  | 0 | 3475645.25 | 0 | 0 | 3475645.25 | 18.375
28 | Roof construction & facade | 1.1.5 |  |  | 2018-08-09 08:00 | 2018-12-28 17:00 | 102d |  |  | 17378226.75 |  |  | 17378226.75 | 141.375
29 | Building steel columns (vertical support) | 1.1.5.1 | 21FS | FS26;FS30 | 2018-08-09 08:00 | 2018-08-30 17:00 | 16d |  | 0 | 5213468 | 0 | 0 | 5213468 | 21.375
30 | Building radial roof elements, whether they be cables or steel truss elements | 1.1.5.2 | 29FS | FS31 | 2018-08-31 08:00 | 2018-10-04 17:00 | 25d |  | 0 | 2606734 | 0 | 0 | 2606734 | 34.375
31 | Building roof | 1.1.5.3 | 30FS | FS32;FS34;FS36 | 2018-10-05 08:00 | 2018-11-23 17:00 | 36d |  | 0 | 6082379.5 | 0 | 0 | 6082379.5 | 49.375
32 | Building cladding elements for both the façade and roof can be applied | 1.1.5.4 | 31FS | FS39 | 2018-11-26 08:00 | 2018-12-28 17:00 | 25d |  | 0 | 3475645.25 | 0 | 0 | 3475645.25 | 32.375
33 | Exterior Design Work | 1.1.6 |  |  | 2018-11-26 08:00 | 2019-01-25 17:00 | 45d |  |  | 4500000 |  |  | 4500000 | 60.375
34 | Preparation exterior design work | 1.1.6.1 | 31FS | FS35 | 2018-11-26 08:00 | 2019-01-11 17:00 | 35d |  | 0 | 2500000 | 0 | 0 | 2500000 | 46.375
35 | Add exterior design | 1.1.6.2 | 34FS | FS44 | 2019-01-14 08:00 | 2019-01-25 17:00 | 10d |  | 0 | 1000000 | 0 | 0 | 1000000 | 11.375
36 | Light installation | 1.1.6.3 | 31FS | FS38 | 2018-11-26 08:00 | 2018-12-21 17:00 | 20d |  | 0 | 1000000 | 0 | 0 | 1000000 | 25.375
37 | Trafic and Parking | 1.1.7 |  |  | 2018-12-31 08:00 | 2019-02-15 17:00 | 35d |  |  | 2500000 |  |  | 2500000 | 46.375
38 | Building parking | 1.1.7.1 | 36FS;39FS | FS44 | 2019-01-21 08:00 | 2019-02-15 17:00 | 20d |  | 0 | 2000000 | 0 | 0 | 2000000 | 25.375
39 | Access to Public Transportation | 1.1.7.2 | 32FS | FS38 | 2018-12-31 08:00 | 2019-01-18 17:00 | 15d |  | 0 | 500000 | 0 | 0 | 500000 | 18.375
40 | Hard Construction cmpleted | 1.1.8 |  |  | 2019-02-15 17:00 | 2019-02-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
41 | Furniture, Fixture and Equipment operation | 1.1.9 |  |  | 2018-11-19 08:00 | 2019-03-15 17:00 | 85d |  |  | 361731.9863 |  |  | 361731.9863 | 116.375
42 | Interior design applications | 1.1.9.1 | 43FS | FS44 | 2018-12-24 08:00 | 2019-01-18 17:00 | 20d |  | 0 | 180866 | 0 | 0 | 180866 | 25.375
43 | Installation seats | 1.1.9.2 |  | FS42 | 2018-11-19 08:00 | 2018-12-21 17:00 | 25d |  | 0 | 72346.3984 | 0 | 0 | 72346.3984 | 32.375
44 | VIP lounge | 1.1.9.3 | 42FS;35FS;38FS | FS45;FS46;FS47 | 2019-02-18 08:00 | 2019-03-01 17:00 | 10d |  | 0 | 54259.7891 | 0 | 0 | 54259.7891 | 11.375
45 | Commentators lounge | 1.1.9.4 | 44FS |  | 2019-03-04 08:00 | 2019-03-15 17:00 | 10d |  | 0 | 36173.1992 | 0 | 0 | 36173.1992 | 11.375
46 | Dressing rooms | 1.1.9.5 | 44FS |  | 2019-03-04 08:00 | 2019-03-12 17:00 | 7d |  | 0 | 18086.5996 | 0 | 0 | 18086.5996 | 8.375
47 | Scorebord, volume and video system | 1.1.10 | 44FS | FS54;FS55 | 2019-03-04 08:00 | 2019-03-22 17:00 | 15d |  | 0 | 3906715 | 0 | 0 | 3906715 | 18.375
48 | The lawn | 1.1.11 |  |  | 2019-03-18 08:00 | 2019-04-24 17:00 | 28d |  |  | 1500000 |  |  | 1500000 | 37.375
49 | Ground preparation | 1.1.11.1 |  | FS50 | 2019-03-18 08:00 | 2019-03-22 17:00 | 5d |  | 0 | 200000 | 0 | 0 | 200000 | 4.375
50 | Installation klimate system | 1.1.11.2 | 49FS | FS51 | 2019-03-25 08:00 | 2019-04-05 17:00 | 10d |  | 0 | 1000000 | 0 | 0 | 1000000 | 11.375
51 | Laying out the lawn | 1.1.11.3 | 50FS | FS52 | 2019-04-08 08:00 | 2019-04-10 17:00 | 3d |  | 0 | 250000 | 0 | 0 | 250000 | 2.375
52 | Breeding | 1.1.11.4 | 51FS |  | 2019-04-11 08:00 | 2019-04-24 17:00 | 10d |  | 0 | 50000 | 0 | 0 | 50000 | 13.375
53 | IT | 1.1.12 |  |  | 2019-03-25 08:00 | 2019-04-23 17:00 | 22d |  |  | 4702528 |  |  | 4702528 | 29.375
54 | Hardware installation | 1.1.12.1 | 47FS | FS56;FS57 | 2019-03-25 08:00 | 2019-04-05 17:00 | 10d |  | 0 | 1881011.25 | 0 | 0 | 1881011.25 | 11.375
55 | Software installation | 1.1.12.2 | 47FS | FS56;FS57 | 2019-03-25 08:00 | 2019-04-12 17:00 | 15d |  | 0 | 1410758.375 | 0 | 0 | 1410758.375 | 18.375
56 | Installation internal communication systems | 1.1.12.3 | 55FS;54FS | FS59 | 2019-04-15 08:00 | 2019-04-23 17:00 | 7d |  | 0 | 705379.1875 | 0 | 0 | 705379.1875 | 8.375
57 | Installation external communication systems | 1.1.12.4 | 55FS;54FS | FS59 | 2019-04-15 08:00 | 2019-04-23 17:00 | 7d |  | 0 | 705379.1875 | 0 | 0 | 705379.1875 | 8.375
58 | Tests and accreditations | 1.1.13 |  |  | 2019-04-24 08:00 | 2019-05-15 17:00 | 16d |  |  | 190000 |  |  | 190000 | 21.375
59 | Accreditation Light | 1.1.13.1 | 56FS;57FS | FS61 | 2019-04-24 08:00 | 2019-04-26 17:00 | 3d |  | 0 | 50000 | 0 | 0 | 50000 | 2.375
60 | Accreditaton Lawn | 1.1.13.2 |  | FS63 | 2019-04-25 08:00 | 2019-04-29 17:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 | 4.375
61 | Accreditation security issues | 1.1.13.3 | 59FS | FS63 | 2019-04-29 08:00 | 2019-05-01 17:00 | 3d |  | 0 | 10000 | 0 | 0 | 10000 | 2.375
62 | Accreditaton communication systems | 1.1.13.4 |  | FS63 | 2019-04-24 08:00 | 2019-04-26 17:00 | 3d |  | 0 | 40000 | 0 | 0 | 40000 | 2.375
63 | Test run | 1.1.13.5 | 60FS;61FS;62FS |  | 2019-05-02 08:00 | 2019-05-15 17:00 | 10d |  | 0 | 80000 | 0 | 0 | 80000 | 13.375
64 | Building comleted | 1.2 |  |  | 2019-05-15 17:00 | 2019-05-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Project | 3064h |  |  |  |  | 99 | 100 | 101
1 | Stadium | 3064h |  |  |  |  | 99 | 100 | 101
2 | Preparatory infrastructure construction | 248h |  |  |  |  | 99 | 100 | 101
3 | Detailed site analysis | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Road access | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Water supply | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Electricity | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Storm and sewer water systems | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Transportation preparation | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Foundation Work | 520h |  |  |  |  | 99 | 100 | 101
10 | Subsurface drainage | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Groundbreaking ceremony | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Excavations | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Placing pipes into the ground | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Lay foundation concrete | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Pour base concrete | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Pour concrete for stands | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Other concrete | 712h |  |  |  |  | 99 | 100 | 101
18 | Building colums | 224h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Building raker beams | 304h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Building floor slabs | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Building elevator shafts | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Building stairs | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Building emergency exits | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Prefabricated elements | 560h |  |  |  |  | 99 | 100 | 101
25 | Building lower tier of the stands | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Building upper tier of the stands | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Mechanical, electrical& plumbing installations (MEP) | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Roof construction & facade | 816h |  |  |  |  | 99 | 100 | 101
29 | Building steel columns (vertical support) | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Building radial roof elements, whether they be cables or steel truss elements | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Building roof | 288h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Building cladding elements for both the façade and roof can be applied | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Exterior Design Work | 360h |  |  |  |  | 99 | 100 | 101
34 | Preparation exterior design work | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Add exterior design | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Light installation | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Trafic and Parking | 280h |  |  |  |  | 99 | 100 | 101
38 | Building parking | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Access to Public Transportation | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Hard Construction cmpleted | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Furniture, Fixture and Equipment operation | 680h |  |  |  |  | 99 | 100 | 101
42 | Interior design applications | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Installation seats | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | VIP lounge | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Commentators lounge | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Dressing rooms | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Scorebord, volume and video system | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | The lawn | 224h |  |  |  |  | 99 | 100 | 101
49 | Ground preparation | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Installation klimate system | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Laying out the lawn | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Breeding | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | IT | 176h |  |  |  |  | 99 | 100 | 101
54 | Hardware installation | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Software installation | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Installation internal communication systems | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Installation external communication systems | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Tests and accreditations | 128h |  |  |  |  | 99 | 100 | 101
59 | Accreditation Light | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Accreditaton Lawn | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Accreditation security issues | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Accreditaton communication systems | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Test run | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Building comleted | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))

## CPI, SPI(t)
C