## Overview
Dynamic Scheduling Library (DSLIB): An overview of the empirical project database for baseline scheduling, risk analysis and project control
Written by: | Mario Vanhoucke and Tom Servranckx
Website: | https://www.projectmanagement.ugent.be/research/data
Reference: | ﻿Batselier, J., & Vanhoucke, M. (2015). Construction and evaluation framework for a real-life project database. International Journal of Project Management, 33(3), 697–710. https://doi.org/10.1016/j.ijproman.2014.09.004
The original paper describes 52 projects. The database currently consists of 203 projects for which an update is given in my book "The illusion of control".
Last update | December 2024
Overview
This sheet gives an overview of the parameters used to classify the empirical projects
Project database
| Code | Each project has a unique ID, starting with the year when the data was collected
| Submitted by | Name of the person(s) who collected the project data
| Sector | Sector of the project
| Keywords | Additional keywords
Completeness
= This part uses the colour-coded approach of Batselier and Vanhoucke (2015) to indicate the completeness of the project data
| Baseline schedule | Indication of the completeness of the baseline schedule information, including the project network, activity duration and cost estimates, etc.
| Risk Analysis | Indication of the completeness of the schedule risk analysis information, including the probability distributions, the sensitivity metrics, etc.
| Project control | Indication of the completeness of the project control information, including the project performance indicators and other the progress data
| Recommended reading: | Batselier, J., & Vanhoucke, M. (2015). Construction and evaluation framework for a real-life project database. International Journal of Project Management, 33(3), 697–710. https://doi.org/10.1016/j.ijproman.2014.09.004
Authenticity
= This part uses the colour-coded approach of Batselier and Vanhoucke (2015) to indicate the authenticity of the project data
| Project | The authenticity of all static project data
| Tracking (color or NA | The authenticity of all project progress data for each tracking period (N.A. is used when not available)
| Recommended reading: | Batselier, J., & Vanhoucke, M. (2015). Construction and evaluation framework for a real-life project database. International Journal of Project Management, 33(3), 697–710. https://doi.org/10.1016/j.ijproman.2014.09.004
General
| # activities | The number of activities in the project
| PD (days) | The planned duration of the project schedule
| BAC (euro) | The planned costs (budget at completion) of the project schedule
Resources
| Y or N | Project has resource information (Y) or not (N)
| Renewable | Renewable resource data (available on a period per period basis)
| Consumable | Consumable resource data (limited consumtion over the whole time horizon)
| Recommended reading: | Vanhoucke, M. (2013). Project management with dynamic scheduling: Baseline scheduling, risk analysis and project control (2nd ed.). Springer. https://doi.org/https://doi.org/10.1007/978-3-642-40438-2
Tracking
| Early/late | Percentage deviation of real duration relative to the planned duration (positive values: late projects / negative values: early projects)
| Under/over budget | Percentage deviation of real cost relative to the planned cost (positive values: under-budget projects / negative values: over-budget projects)
Network topology
| SP | The serial/parallel indicator of Vanhoucke et al. (2008)
| AD | The activity distribution indicator of Vanhoucke et al. (2008)
| LA | The length of arcs indicator of Vanhoucke et al. (2008)
| TF | The topological float indicator of Vanhoucke et al. (2008)
| RI | The regularity index indicator of Batselier and Vanhoucke (2017)
| Regularity | Classification of the RI index into three clases as discussed in Batselier and Vanhoucke (2017)
| Recommended readings: | Vanhoucke, M., Coelho, J., Debels, D., Maenhout, B., & Tavares, L. V. (2008). An evaluation of the adequacy of project network generators with systematically sampled networks. European Journal of Operational Research, 187(2), 511–524. https://doi.org/10.1016/j.ejor.2007.03.032
Batselier, J., & Vanhoucke, M. (2017). Project regularity: Development and evaluation of a new project characteristic. Journal of Systems Science and Systems Engineering, 26(1), 100–120. https://doi.org/10.1007/s11518-016-5312-6
Time sensitivity
= This part measures the time sensitivity of activities (relation between activity duration and the total project duration). Since each activity gets a value, the average, standard deviations and skewness for all activities are reported
| CI: Avg, stDev and Skew | Criticality index
| SI | Significance index
| SSI | Schedule sensitivity index
| CRI-r | The cruciality index based on the Pearson product-moment correlation coefficient
| CRI-rho | The cruciality index based on Spearman’s rank correlation
| CRI-tau | The cruciality index based on Kendall’s tau rank correlation index
| Recommended reading: | Vanhoucke, M. (2010). Measuring time: Improving project performance using earned value management (1st ed.). Springer. http://www.springer.com/engineering/production+engineering/book/978-1-4419-1013-4
Cost sensitivity
= This part measures the cost sensitivity of activities (relation between activity cost and the total project cost). Since each activity gets a value, the average, standard deviations and skewness for all activities are reported
| CRI-r | The cruciality index based on the Pearson product-moment correlation coefficient
| CRI-rho | The cruciality index based on Spearman’s rank correlation
| CRI-tau | The cruciality index based on Kendall’s tau rank correlation index
| Recommended reading: | Vanhoucke, M. (2010). Dynamic scheduling on your desktop (1st ed.). OR-AS. http://www.or-as.be/books/protrack2
Resource sensitivity
= This part measures the resource sensitivity of activities (relation between the resource cost and the total project cost). Since each resource gets a value, the average, standard deviations and skewness for all resources are reported
| CRI-r | The cruciality index based on the Pearson product-moment correlation coefficient
| CRI-rho | The cruciality index based on Spearman’s rank correlation
| CRI-tau | The cruciality index based on Kendall’s tau rank correlation index
| Recommended reading: | Vanhoucke, M. (2010). Dynamic scheduling on your desktop (1st ed.). OR-AS. http://www.or-as.be/books/protrack2
Performance metrics
= This part contains values for different performance metrics measuring over the project progress as average values (avg) and standard deviations (stdev) of all tracking periods. Final values are also reported which gives the performance at the end of the project.
| CV | Cost variance (CV = EV - AC)
| SV | Schedule variance (SV = EV - PV)
| SV(t) | Schedule variance based on Earned Schedule (SV(t) = ES - AT) with AT = current period (actual time)
| CPI | Cost performance index (CPI = EV / AC)
| SPI | Schedule performance index (SPI = EV / PV)
| SPI(t) | Schedule performance index based on Earned Schedule (SPI(t) = ES / AT)
| p-factor | Schedule adherence index
| Real duration | The real total project duration (known after the project's finish)
| Real cost | The real total project cost (known after the project's finish)
| Recommended reading: | Vanhoucke, M. (2010). Measuring time: Improving project performance using earned value management (1st ed.). Springer. http://www.springer.com/engineering/production+engineering/book/978-1-4419-1013-4
Reference used in this document
| Batselier and Vanhoucke (2015) | Batselier, J., & Vanhoucke, M. (2015). Construction and evaluation framework for a real-life project database. International Journal of Project Management, 33(3), 697–710. https://doi.org/10.1016/j.ijproman.2014.09.004
| Batselier and Vanhoucke (2017) | Batselier, J., & Vanhoucke, M. (2017). Project regularity: Development and evaluation of a new project characteristic. Journal of Systems Science and Systems Engineering, 26(1), 100–120. https://doi.org/10.1007/s11518-016-5312-6
| Vanhoucke et al. (2008) | Vanhoucke, M., Coelho, J., Debels, D., Maenhout, B., & Tavares, L. V. (2008). An evaluation of the adequacy of project network generators with systematically sampled networks. European Journal of Operational Research, 187(2), 511–524. https://doi.org/10.1016/j.ejor.2007.03.032
| Vanhoucke (2010a) | Vanhoucke, M. (2010). Measuring time: Improving project performance using earned value management (1st ed.). Springer. http://www.springer.com/engineering/production+engineering/book/978-1-4419-1013-4
| Vanhoucke (2013) | Vanhoucke, M. (2013). Project management with dynamic scheduling: Baseline scheduling, risk analysis and project control (2nd ed.). Springer. https://doi.org/https://doi.org/10.1007/978-3-642-40438-2
| Vanhoucke (2010b) | Vanhoucke, M. (2010). Using activity sensitivity and network topology information to monitor project time performance. Omega - The International Journal of Management Science, 38(5), 359–370. https://doi.org/10.1016/j.omega.2009.10.001
| Vanhoucke (2010c) | Vanhoucke, M. (2010). Dynamic scheduling on your desktop (1st ed.). OR-AS. http://www.or-as.be/books/protrack2
| More references: | https://www.projectmanagement.ugent.be/staff/publications
Books with summary of the empirical data
| Vanhoucke (2023) | Vanhoucke, M., 2023, "The illusion of control: Project data, computer algorithms and human intuition for project management and control", Book published by Springer.
| Vanhoucke (2024) | Vanhoucke, M., 2024, "A quest for projects with scarce resources: Seeking schedule intelligence through project data discovery", Book published by Springer.
More information
| Mario Vanhoucke | mario.vanhoucke@ugent.be
| Tom Servranckx | tom.servranckx@ugent.be

## DSLIB
Project database |  |  |  |  | Completeness |  |  | Authenticity |  | General |  |  | Resources |  |  | Tracking |  | Network topology | [5 empty] | Time sensitivity | [17 empty] | Cost sensitivity | [8 empty] | Resource sensitivity | [8 empty] | Performance metrics
[24 empty] | CI |  |  | SI |  |  | SSI |  |  | CRI-r |  |  | CRI-rho |  |  | CRI-tau |  |  | CRI-r |  |  | CRI-rho |  |  | CRI-tau |  |  | CRI-r |  |  | CRI-rho |  |  | CRI-tau |  |  | CV |  |  | SV |  |  | SV(t) |  |  | CPI |  |  | SPI |  |  | SPI(t) |  |  | p-factor |  |  | Real | Real
Code | Project name | Submitted by | Sector | Keywords | Baseline Schedule | Risk Analysis | Project Control | Project | Tracking | # activities | PD (days) | BAC | Resources | Renewable | Consumable | Early/late | Under/over budget | SP | AD | LA | TF | RI | Regularity | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | skew | avg | std. dev. | final | avg | std. dev. | final | avg | std. dev. | final | avg | std. dev. | final | avg | std. dev. | final | avg | std. dev. | final | avg | std. dev. | final | Duration | Cost
C2011-01 | Nursing Home Noordhinder | Nathan Goddefroy | Construction (commercial building) | Nursing Home; Residential Center |  |  |  | G | N/A | 153 | 766 | 4679795 | Y | 12 | - | - | - | 61% | 65% | 26% | 6% | 81% | regular | 58 | 45.4 | -0.3 | 70.4 | 37.9 | -0.8 | 4.7 | 8.2 | 2.2 | 8 | 7.8 | 1.4 | 16.8 | 16.3 | 1.2 | 28.3 | 33.4 | 1.5 | 6.8 | 9.9 | 4.1 | 25.5 | 21 | 0.4 | 48.1 | 42 | 0.3 | 21.2 | 22.6 | 2.4 | 18.9 | 22.7 | 2.8 | 13.2 | 18.5 | 3 | [21 empty] | 1 | 1
C2011-02 | Social Housing Kortrijk | Arne De Jongh | Construction (residential building) | Residential Center |  |  |  | Y | N/A | 113 | 276 | 366457 | Y | 2 | - | - | - | 42% | 29% | 12% | 14% | 89% | regular | 43.8 | 47.4 | 0.2 | 12.8 | 27 | 2.5 | 2.5 | 9.6 | 8.8 | 9.8 | 10.3 | 4.9 | 10 | 10.5 | 4.4 | 21.1 | 15.2 | 0.6 | 9.3 | 8.6 | 2 | 13.3 | 12.2 | 1.8 | 23.7 | 22.4 | 2 | 56 | 44 |  | 53.5 | 46.5 |  | 50 | 45 | [22 empty] | 1 | 1
C2011-03 | Family Day | Raphael Seffers | Event Management | Party Planning |  |  |  | O | N/A | 22 | 97 | 31675 | Y | 2 | - | - | - | 33% | 48% | 7% | 19% | 77% | irregular | 36.4 | 48.1 | 0.6 | 56 | 37 | 0.1 | 12 | 20.1 | 1.5 | 16 | 15.5 | 1.6 | 15.9 | 15 | 1.5 | 14.2 | 11 | 0.9 | 18.1 | 15.1 | 0.8 | 17.8 | 14.2 | 0.8 | 12 | 9.9 | 1 | 61 | 38 |  | 60 | 39 |  | 54 | 36 | [22 empty] | 1 | 1
C2011-04 | Railway Station Sint-Joost | Frederiek Vanhessche | Construction (civil) | Renovation; Outdoors Structure |  |  |  | Y | N/A | 18 | 125 | 59831 | Y | 2 | - | - | - | 47% | 62% | 45% | 19% | 79% | irregular | 33.3 | 47.1 | 0.8 | 15.8 | 20.1 | 1.3 | 7.1 | 20.9 | 4.1 | 11.3 | 20.3 | 3.7 | 11 | 20.3 | 3.7 | 13.2 | 16.3 | 2.9 | 13.4 | 18.9 | 2.5 | 13.3 | 18.7 | 2.4 | 13.4 | 13.4 | 1.8 | 96.5 | 2.5 |  | 96.5 | 2.5 |  | 85 | 7 | [22 empty] | 1 | 1
C2011-05 | Telecom System Agnes | Pieter Van Schoors | IT | Medical; Nurse Center |  |  |  | G | O | 21 | 43 | 180485 | Y | 6 | - | - | - | 60% | 58% | 38% | 9% | 85% | regular | 58.7 | 44.4 | -0.4 | 28.7 | 37.4 | 1 | 12.5 | 17.3 | 1.6 | 17.1 | 13.9 | 0.6 | 21.4 | 16 | 0.3 | 29.5 | 25.8 | 1.9 | 17.7 | 13.8 | 0.9 | 22.8 | 14.9 | 0.7 | 30.5 | 26.4 | 1.6 | 28.5 | 27.9 | 1 | 35 | 26.3 | 0 | 43.5 | 30.3 | 0.9 | 0 | 0 | 0 | -4695.32 | 5929.99 | 0 | -3.53 | 3.66 | -10 | 1 | 0 | 1 | 0.97 | 0.04 | 1 | 0.92 | 0.07 | 0.81 | 0.98 | 0.03 | 1 | 1 | 1
C2011-06 | Veterinary Exposition | Joyca Vervinckt | Event Management | Veterinary Exposition |  |  |  | G | N/A | 75 | 314 | 54350 | Y | 15 | - | - | - | 28% | 40% | 4% | 12% | 48% | irregular | 9.9 | 28.3 | 2.7 | 11.6 | 20.5 | 2.7 | 2 | 9.9 | 4.8 | 6.8 | 10.8 | 3 | 29 | 21.1 | -0.1 | 56.1 | 41.7 | 0 | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [22 empty] | 1 | 1
C2011-07 | Patient Transport System | Els Van Impe | IT | Medical; Patient Transport |  |  |  | G | Y | 49 | 389 | 180759 | Y | 5 | - | 14.4% | - | 70% | 70% | 7% | 8% | 74% | irregular | 71.4 | 45.2 | -1 | 74.6 | 40.6 | -1 | 3.7 | 13.8 | 6.8 | 9.6 | 13.9 | 5.4 | 11 | 14.2 | 4.8 | 17.9 | 16.7 | 2 | 12.8 | 12.3 | 1.5 | 15.5 | 13.5 | 1.4 | 16.9 | 17.7 | 2.5 | 44.2 | 23.8 | 1.5 | 42 | 25.2 | 1.7 | 29.6 | 21.8 | 1.7 | -3897.18 | 3566.9 | -10305.66 | -15439.72 | 18478.79 | 0 | -41.17 | 40.17 | -56 | 0.96 | 0.02 | 0.95 | 0.79 | 0.23 | 1 | 0.84 | 0.17 | 0.87 | 0.97 | 0.04 | 1 | 445 | 1
C2011-08 | Sports Center Tielt | Lise Braeckman | Construction (civil) | Sports Center; Public Construction |  |  |  | Y | N/A | 26 | 72 | 254564 | Y | 1 | - | - | - | 56% | 71% | 10% | 60% | 81% | regular | 58.9 | 47.3 | -0.4 | 13.4 | 28.9 | 2.3 | 11 | 14.9 | 1.6 | 16.8 | 15.7 | 1.7 | 19 | 14 | 1.6 | 21.3 | 11.4 | -0.4 | 16.5 | 15.6 | 1.8 | 18.4 | 13.7 | 1.7 | 21 | 11.2 | -0.2 | 0 | 0 |  | 100 | 0 |  | 99 | 0 | [22 empty] | 1 | 1
C2011-09 | Commercial IT Project | Simon Buysse | IT | Program Developement; Software |  |  |  | O | N/A | 41 | 57 | 33623 | Y | 8 | - | - | - | 52% | 42% | 8% | 24% | 83% | regular | 57.2 | 47.2 | -0.3 | 77.8 | 30.9 | -1.2 | 6.7 | 13.9 | 3.5 | 11.6 | 15.1 | 2.4 | 26.9 | 19.6 | 0.5 | 44.2 | 37.6 | 0.7 | 9.7 | 14.3 | 2.2 | 30.8 | 20.1 | -0.1 | 53.4 | 40.1 | 0.2 | 28.6 | 21.9 | 0.9 | 28 | 23.5 | 0.9 | 20.4 | 14.5 | 0.8 | [21 empty] | 1 | 1
C2011-10 | Building a House | Charline Borsus | Construction (residential building) | Residential Construction |  |  |  | G | N/A | 32 | 195 | 484398 | Y | 1 | - | - | - | 51% | 47% | 27% | 10% | 87% | regular | 49.9 | 49.9 | 0 | 59.2 | 40.1 | -0.2 | 6.1 | 14.2 | 3.5 | 11.6 | 17.2 | 2.8 | 24.4 | 21.9 | 0.8 | 34.1 | 41.2 | 0.9 | 11.9 | 16.4 | 2.4 | 24.4 | 20.9 | 0.6 | 33.9 | 41 | 0.9 | 100 | 0 |  | 100 | 0 |  | 100 | 0 |  | -8776.79 | 4519.7 | -10549.28 | -28744.99 | 29570.42 | 0 | -12.29 | 6.9 | -8.12 | 0.97 | 0.02 | 0.98 | 0.89 | 0.12 | 1 | 0.86 | 0.09 | 0.95 | 1 | 0.01 | 1 | 1 | 1
C2011-11 | Eating Belgium | Wouter Van Damme | Event Management | Party Planning |  |  |  | O | N/A | 24 | 299 | 37760 | Y | 2 | - | - | - | 30% | 42% | 18% | 14% | 50% | irregular | 33.3 | 47.1 | 0.8 | 38.1 | 44.8 | 0.6 | 7.8 | 18.4 | 3 | 15.4 | 17.2 | 2.7 | 17.1 | 18.1 | 2.3 | 27 | 21.4 | 1.7 | 13.3 | 17.6 | 3.6 | 15 | 19.1 | 3 | 25.6 | 23.3 | 1.6 | 50 | 50 |  | 75 | 25 |  | 100 | 0 | [22 empty] | 1 | 1
C2011-12 | Claeys-Verhelst Premises | Laura Demeyere | Construction (commercial building) | Showroom; Warehouse; Offices |  |  |  | G | Y | 49 | 442 | 3027133 | Y | 12 | - | 2.715% | - | 41% | 50% | 5% | 43% | 75% | irregular | 17 | 28 | 1.8 | 42.9 | 29.2 | 0.4 | 3.5 | 8.8 | 3.2 | 6.6 | 10.4 | 2.6 | 20.3 | 19.5 | 0.7 | 33 | 41.4 | 1 | 7.7 | 13.2 | 2.5 | 35.2 | 18.8 | -0.6 | 61.6 | 43.3 | -0.3 | 17.9 | 22.4 | 1.3 | 34 | 20.8 | -0.3 | 44.6 | 41.2 | 0.5 | -51704.94 | 30253.4 | -75262.5 | -214050.8 | 240842.1 | 0 | -22.2 | 14.86 | -12 | 0.96 | 0.03 | 0.98 | 0.82 | 0.23 | 1 | 0.92 | 0.07 | 0.97 | 1 | 0 | 1 | 454 | 1
C2011-13 | Wind Farm | Philip Pensaert | Construction (industrial) | Wind Power |  |  |  | G | G | 134 | 525 | 21369836 | N | - | - | 14.29% | 22.03% | 27% | 36% | 0% | 48% | 36% | irregular | 2.2 | 14.6 | 6.6 | 5.9 | 16.4 | 4.9 | 1.1 | 8.6 | 9 | 7.9 | 10.2 | 4.1 | 18.1 | 18.7 | 1.2 | 31 | 36.6 | 1.2 | 7.2 | 9.5 | 2.6 | 24.4 | 19.8 | 0.4 | 41.9 | 41.8 | 0.6 | [9 empty] | -1212377.3 | 1662288.51 | -4707924 | -1362871.47 | 2079883.95 | 0 | -60.74 | 58.21 | -75 | 0.88 | 0.14 | 0.82 | 0.73 | 0.22 | 1 | 0.79 | 0.22 | 0.88 | 0.96 | 0.07 | 1 | 600 | 26077765
C2011-14 | Hotel Reylof | Ruben Van Caelenberg | Construction (commercial building) | Hotel |  |  |  | G | N/A | 373 | 252 | - | N | - | - | - | - | 3% | 44% | 0% | 61% | - | N/A | 1.4 | 6.6 | 5.7 | 14.6 | 15.2 | 2.2 | 0.3 | 4.6 | 18.6 | 8.6 | 7.7 | 4.1 | 9.4 | 9.3 | 3.5 | 13.3 | 14.9 | 3.6 | [39 empty] | 1 | 1
C2012-01 | Manufacturing Tool Cost Module | Jolien Commeene | IT | Electromechanic Components |  |  |  | G | N/A | 29 | 45 | 61699 | Y | 5 | - | - | - | 79% | 78% | 10% | 11% | 74% | irregular | 80.3 | 37.6 | -1.6 | 64.9 | 44.8 | -0.7 | 13.6 | 15.6 | 0.7 | 11.7 | 12.6 | 0.7 | 31.9 | 17.2 | -0.3 | 48.1 | 43.3 | 0.3 | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [22 empty] | 1 | 1
C2012-02 | Nut Mixing Station | Mathijs Bostyn | Construction (industrial) | New Machine Installation |  |  |  | G | N/A | 47 | 22 | 1056501 | Y | 24 | - | - | - | 17% | 17% | 0% | 48% | 55% | irregular | 19.1 | 38.9 | 1.6 | 37.8 | 35.3 | 0.9 | 6 | 14.1 | 2.5 | 11.7 | 11.5 | 2 | 11.9 | 12.1 | 1.8 | 28.9 | 12.6 | -0.1 | 14.5 | 11.1 | 1 | 16.4 | 13.3 | 1 | 24.6 | 20.8 | 1.9 | 25.9 | 20 | 1.3 | 28 | 19.7 | 1 | 22.6 | 27.6 | 1.9 | [21 empty] | 1 | 1
C2012-03 | Day Care | Emily Bral | Construction (institutional building) | Day Care; Renovation |  |  |  | G | N/A | 24 | 128 | - | N | - | - | - | - | 73% | 76% | 22% | 36% | N/A | N/A | 75 | 43.3 | -1.2 | 83.9 | 30.3 | -1.8 | 15.6 | 18.5 | 1.5 | 14.7 | 14.5 | 1.5 | 18 | 16.6 | 1.1 | 22.9 | 25.7 | 2.3 | [39 empty] | 1 | 1
C2012-04 | Asti-Cuneo Highway | Anna Bierma | Construction (civil) | Highway |  |  |  | G | N/A | 67 | 272 | 6230961 | Y | 16 | 2 | - | - | 63% | 54% | 0% | 10% | 79% | irregular | 62.5 | 47.3 | -0.5 | 67.2 | 42.7 | -0.6 | 5.7 | 11 | 3.2 | 9.9 | 11.6 | 2.6 | 11.3 | 11.4 | 2.4 | 21.7 | 14.2 | 0.2 | 9.4 | 12.7 | 3.2 | 15.9 | 17.6 | 1.6 | 33 | 28.4 | 1.3 | 41.8 | 38.2 | 0.4 | 41.1 | 38.4 | 0.4 | 35.9 | 32.3 | 0.7 | [21 empty] | 1 | 1
C2012-05 | Tappan Zee Bridge | Wolfgang Prestl | Construction (civil) | Bridge Construction |  |  |  | Y | N/A | 19 | 1289 | 4999958016 | Y | 20 | - | - | - | 50% | 44% | 23% | 4% | 88% | regular | 52.7 | 49.7 | -0.1 | 35.8 | 35.4 | 0.4 | 15.7 | 17.3 | 0.8 | 16.6 | 17.1 | 1.2 | 16.3 | 16.5 | 1.2 | 10.7 | 11.1 | 1.4 | 18.2 | 13.8 | 1.6 | 11.6 | 12.1 | 1.9 | 11.2 | 21.6 | 4 | 51.7 | 25.7 | -0.6 | 53.1 | 21.1 | -0.5 | 44.8 | 24.8 | 0.8 | [21 empty] | 1 | 1
C2012-06 | Youth Hostel Merkenveld | Jonathan Dauchot | Construction (commercial building) | Renovation |  |  |  | G | N/A | 46 | 197 | - | Y | 5 | - | - | - | 62% | 64% | 17% | 15% | N/A | N/A | 64.7 | 44.7 | -0.6 | 21.8 | 34.6 | 1.4 | 7.6 | 12 | 2.5 | 10.3 | 13.4 | 2.8 | 17.7 | 17.1 | 1.4 | 30 | 29.6 | 1.4 | [39 empty] | 1 | 1
C2012-07 | Solar Park | Rémi Krick | Construction (industrial) | Solar Power |  |  |  | G | N/A | 175 | 711 | - | N | - | - | - | - | 4% | 65% | 0% | 85% | N/A | N/A | 2.3 | 14.9 | 6.4 | 9.8 | 14.1 | 2.4 | 0.7 | 7.6 | 13 | 7.8 | 9.2 | 5.7 | 12 | 14.7 | 2.6 | 26.3 | 27 | 1.7 | [39 empty] | 1 | 1
C2012-08 | Sea Electricity | Tom Valcke | Construction (industrial) | Offshore Wind Park |  |  |  | O | N/A | 437 | 468 | 139062144 | Y | 27 | - | - | - | 8% | 40% | 0% | 41% | 55% | irregular | 9 | 27.3 | 3 | 25.1 | 36.3 | 1.1 | 1.2 | 5.7 | 8.5 | 8 | 7.4 | 2.2 | 12.3 | 13.5 | 2 | 23.8 | 25.9 | 2.1 | 6.4 | 7.1 | 1.8 | 18.8 | 18.5 | 0.9 | 36.7 | 36.5 | 1 | 23.7 | 24.4 | 1.3 | 26.7 | 24 | 1 | 23.2 | 28.1 | 1.7 | [21 empty] | 1 | 1
C2012-09 | Digipolis Talent Management Suite | Annelies Troch | IT | HR |  |  |  | Y | N/A | 279 | 162 | 4899912 | Y | 1 | - | - | - | 1% | 22% | 0% | 28% | 45% | irregular | 1.5 | 9.4 | 6.9 | 11.8 | 17.4 | 3 | 0.7 | 5.2 | 8 | 7.2 | 7.6 | 1.9 | 18.1 | 18 | 1 | 35.9 | 35.1 | 1.1 | 5.7 | 8 | 6.4 | 17.3 | 18.9 | 1.3 | 34.6 | 36.3 | 1.1 | 21 | 0 |  | 22 | 0 |  | 17 | 0 | [22 empty] | 1 | 1
C2012-10 | Gabala Resort Outdoor Pool | Aleksandra Kostadinova | Construction (commercial building) | Pool |  |  |  | O | N/A | 18 | 54 | 47413 | Y | 9 | - | - | - | 82% | 85% | 0% | 21% | 92% | regular | 83.3 | 37.3 | -2 | 1.7 | 3.8 | 2.1 | 20.4 | 15.4 | 0.2 | 18.2 | 16 | 0.5 | 20.4 | 13.1 | 0.7 | 19.1 | 11.7 | 0.2 | 17.4 | 16.8 | 1.4 | 21.2 | 16.4 | 1.2 | 22.9 | 22.7 | 2.2 | 34.1 | 24.6 | 0.1 | 32.8 | 23.4 | 0.1 | 22.9 | 12.8 | 0.1 | [21 empty] | 1 | 1
C2012-11 | MIVB SeSaMe | Livine Maerschalck | Construction (civil) | Subway; Access Doors; Public Transport |  |  |  | G | N/A | 22 | 13 | 1535854 | Y | 2 | - | - | - | 34% | 47% | 96% | 1% | 54% | irregular | 38.5 | 47.2 | 0.5 | 60.5 | 32.3 | -0.2 | 10.7 | 19.4 | 1.5 | 9.3 | 17.2 | 1.7 | 45.6 | 14.1 | -2.1 | 77.6 | 32.6 | -0.9 | 8.6 | 19 | 2.7 | 43.7 | 15.8 | -1 | 74.6 | 36.4 | -0.8 | 57 | 41 |  | 56.5 | 41.5 |  | 44 | 43 | [22 empty] | 1 | 1
C2012-12 | Railway Station Ghent | Karel Verlinde | Construction (civil) | Railway Station; Renovation |  |  |  | G | N/A | 19 | 440 | - | N | - | - | - | - | 38% | 36% | 20% | 23% | N/A | N/A | 34.5 | 31 | 0.5 | 83.5 | 20.2 | -2.7 | 12.8 | 14.8 | 1.3 | 13.3 | 15.5 | 1.6 | 12.4 | 14.8 | 1.7 | 7.9 | 10.4 | 1.7 | [39 empty] | 1 | 1
C2012-13 | Pumping Station Jabbeke | Niels Crommen | Construction (civil) | Pumping Station; Construction |  |  |  | G | G | 74 | 125 | 336410 | Y | 2 | - | 12% | 4.192% | 64% | 59% | 3% | 27% | 83% | regular | 58.5 | 48.6 | -0.3 | 64.1 | 42.6 | -0.5 | 4.5 | 10.7 | 6 | 10.1 | 12.4 | 3.8 | 14.1 | 16.1 | 2.2 | 34.7 | 24.2 | 1.3 | 10.2 | 10.6 | 2.8 | 15.2 | 14.9 | 1.6 | 32.4 | 24.8 | 1.3 | 54 | 44 |  | 55 | 43 |  | 43 | 43 |  | -5716.75 | 5381.02 | -14101.16 | -6470.76 | 17755.11 | 0 | -6.01 | 8.89 | -15 | 0.98 | 0.02 | 0.96 | 1 | 0.1 | 1 | 0.97 | 0.12 | 0.89 | 0.98 | 0.04 | 1 | 140 | 350511
C2012-14 | Sluiskil Tunnel | Josée De Backere | Construction (civil) | Tunnel |  |  |  | O | N/A | 48 | 1299 | 528569216 | Y | 8 | - | - | - | 58% | 39% | 25% | 10% | 86% | regular | 58.9 | 44.8 | -0.4 | 64.4 | 41 | -0.6 | 8.7 | 10.6 | 1.4 | 12.4 | 10.7 | 1 | 13.2 | 11.5 | 1.2 | 11.6 | 14.9 | 4.4 | 10.3 | 12 | 2.1 | 18.2 | 17.8 | 1 | 25 | 34.2 | 1.6 | 37.1 | 30.8 | 0.5 | 43 | 27.1 | 0.2 | 39.4 | 32.3 | 0.8 | [21 empty] | 1 | 1
C2012-15 | The Master Project | Eline Van Lombeek | Education | Education |  |  |  | O | N/A | 134 | 32 | 185472 | Y | 3 | - | - | - | 17% | 66% | 0% | 84% | 84% | regular | 49.3 | 50 | 0 | 40.8 | 47.9 | 0.4 | 0 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 329.04 | 74.25 | 359.34 | 255.11 | 421.78 | 0 | 0.2 | 1.1 | -2 | 1 | 0 | 1 | 1.01 | 0.01 | 1 | 1.06 | 0.14 | 0.91 | 0.93 | 0.09 | 1 | 1 | 1
C2012-16 | Metal Extraction | N/A | Construction (industrial) | Metals; Electromagnetic Installation |  |  |  | G | N/A | 86 | 88 | - | Y | 10 | - | - | - | 16% | 51% | 0% | 32% | N/A | N/A | 18.4 | 36.5 | 1.7 | 16.5 | 22.2 | 2.8 | 4 | 9 | 2.4 | 11.5 | 9.9 | 1.3 | 11.6 | 9.5 | 1.2 | 22.7 | 11.7 | 0.4 | [39 empty] | 1 | 1
C2012-17 | Building a Dream | Giel-Jan Triest | Construction (residential building) | Residential Construction |  |  |  | O | N/A | 33 | 145 | 241015 | Y | 10 | - | - | - | 65% | 61% | 35% | 0% | 88% | regular | 60.7 | 46.8 | -0.5 | 17.8 | 29.6 | 1.7 | 10.7 | 12.6 | 1.3 | 15.2 | 14.1 | 1.7 | 15.3 | 13.8 | 1.7 | 12.1 | 12.3 | 1.6 | 11.4 | 16.4 | 2 | 26.6 | 20.8 | 0.3 | 39.9 | 41.3 | 0.7 | 50.8 | 24.8 | 0.3 | 49.5 | 24.8 | 0.3 | 35.7 | 20.4 | 0.6 | -46465.52 | 23296.54 | -73841.19 | -32887.07 | 26558.87 | 0 | -29.44 | 16.84 | -59.63 | 0.75 | 0.07 | 0.77 | 0.79 | 0.14 | 1 | 0.75 | 0.06 | 0.71 | 0.99 | 0.05 | 1 | 1 | 1
C2013-01 | Wiedauwkaai Fenders | Pieter Buyse | Construction (civil) | Railway Bridge; Waterway |  |  |  | G | G | 42 | 152 | 1069533 | N | - | - | 0% | 22.91% | 48% | 45% | 0% | 68% | 94% | regular | 2.4 | 15.2 | 6.5 | 12.2 | 17.5 | 3.8 | 2.4 | 15.2 | 6.5 | 9 | 15.2 | 5.3 | 13.7 | 18 | 3.3 | 21 | 27.4 | 2.3 | 11.3 | 13.1 | 0.9 | 32.8 | 17 | -0.3 | 48.6 | 45 | 0.2 | [9 empty] | -106440.36 | 102535.11 | -245052.13 | -9147.2 | 13995.65 | 0 | -2.04 | 3.18 | 0 | 0.92 | 0.15 | 0.81 | 0.94 | 0.11 | 1 | 0.93 | 0.15 | 1 | 0.9 | 0.12 | 1 | 152 | 1314585
C2013-02 | Sewage Plant Hove | Tim Vandenbussche | Construction (civil) | Sewage |  |  |  | G | G | 181 | 403 | 1236604 | N | - | - | 0% | -7.291% | 12% | 38% | 0% | 62% | 16% | irregular | 0.6 | 7.4 | 13.5 | 3 | 7.6 | 11.8 | 0.6 | 7.4 | 13.5 | 8.7 | 8.9 | 6.1 | 8.8 | 9.1 | 5.9 | 10.8 | 11.8 | 3.1 | 6.2 | 8.8 | 4.4 | 22.2 | 20.7 | 0.6 | 39.7 | 42.4 | 0.7 | [9 empty] | 60788.66 | 23225.21 | 90159.88 | -58842.54 | 88480.55 | 0 | -11.6 | 24.47 | 0 | 1.09 | 0.02 | 1.08 | 0.88 | 0.17 | 1 | 0.88 | 0.17 | 1 | 0.92 | 0.05 | 1 | 403 | 1146444
C2013-03 | Brussels Finance Tower | Tim Vandenbussche | Construction (institutional building) | Renovation, Government Building |  |  |  | G | G | 55 | 425 | 15440865 | N | - | - | 0.2353% | 5.81% | 3% | 82% | 0% | 87% | 84% | regular | 1.8 | 13.4 | 7.4 | 18.7 | 23.4 | 1.5 | 1.8 | 13.4 | 7.4 | 7.3 | 5.1 | 0.5 | 9.4 | 13.4 | 5.7 | 6.6 | 13.3 | 6.5 | 9.1 | 10.6 | 3.2 | 11 | 12.7 | 2.5 | 9.6 | 18.9 | 4.2 | [9 empty] | -143840.76 | 306369.43 | -897162 | -632908.56 | 718186.58 | 0 | -13.51 | 19.62 | -1 | 0.99 | 0.02 | 0.95 | 1 | 0.18 | 1 | 0.99 | 0.11 | 1 | 0.85 | 0.1 | 1 | 426 | 16338027
C2013-04 | Kitchen Tower Anderlecht | Tim Vandenbussche | Construction (institutional building) | Cooking School |  |  |  | G | G | 252 | 333 | 2113684 | N | - | - | 36.04% | 18.87% | 47% | 59% | 0% | 63% | 88% | regular | 1.7 | 9.9 | 6.6 | 3.3 | 12.4 | 5.7 | 0.2 | 3.5 | 15.8 | 9.2 | 7.9 | 2.3 | 10.2 | 8.3 | 1.9 | 29.1 | 12.4 | -0.4 | 8.5 | 8.1 | 3.7 | 12.2 | 12.2 | 2.5 | 32.7 | 20.4 | 1.7 | [9 empty] | -229714.09 | 145691.7 | -398840 | -334405.27 | 246606.31 | 0 | -94.14 | 19.74 | -120 | 0.88 | 0.04 | 0.84 | 0.77 | 0.18 | 1 | 0.66 | 0.08 | 0.74 | 0.99 | 0.01 | 1 | 453 | 2512524
C2013-05 | PET Packaging | Annelies Troch | Engineering | Packaging, PET, R&D |  |  |  | G | Y | 28 | 521 | 874554 | N | - | - | 29.17% | - | 14% | 69% | 0% | 80% | 72% | irregular | 3.6 | 12.9 | 3.5 | 27.5 | 22.2 | 2.1 | 4.3 | 15.5 | 3.5 | 1.6 | 15.8 | 3.2 | 11 | 15.7 | 3.1 | 8.1 | 12.8 | 3.3 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [10 empty] | 0 | 0 | 0 | -139615.0013 | 97379.1775 | 0 | -112.1613 | 58.7762 | -152 | 0.93548 | 0.24567 | 1 | 0.69742 | 0.26554 | 1 | 0.55452 | 0.21597 | 0.77 | 0.95516 | 0.080797 | 1 | 673 | 1
C2013-06 | Government Office Building | Evy Dierickx | Construction (institutional building) | Office Building; Government Building |  |  |  | G | G | 276 | 352 | 19429808 | N | - | - | 0% | 10.9% | 10% | 36% | 0% | 34% | 85% | regular | 8.4 | 26.9 | 3.1 | 15.8 | 27.4 | 2.5 | 1.2 | 5.3 | 8.6 | 9 | 8 | 3.5 | 9 | 8.2 | 3.4 | 10.6 | 9.6 | 3.7 | 14.1 | 34.8 | 2.1 | 100 | 0 |  | 100 | 0 | [10 empty] | -753658.54 | 739394.31 | -2117042 | -182373.3 | 447968.47 | 22484 | -0.74 | 6.01 | 8 | 0.94 | 0.02 | 0.9 | 0.97 | 0.09 | 1 | 0.97 | 0.09 | 1.02 | 0.95 | 0.06 | 1 | 352 | 21546846
C2013-07 | Family Residence | Evy Dierickx | Construction (residential building) | Residential Construction |  |  |  | G | G | 46 | 170 | 180476 | N | - | - | 17.65% | -3.017% | 40% | 44% | 3% | 25% | 77% | irregular | 41.3 | 48.6 | 0.4 | 55.7 | 41.5 | -0.1 | 5.9 | 15.4 | 4.4 | 10.3 | 12.9 | 4.2 | 11 | 13.1 | 4.3 | 29.5 | 14.1 | -0.3 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [10 empty] | 5019.8 | 1328.8 | 5445.81 | -10641.17 | 15503.64 | 0 | -8.81 | 5.72 | -13 | 1.05 | 0.02 | 1.03 | 0.88 | 0.22 | 1 | 0.89 | 0.1 | 0.93 | 0.99 | 0.03 | 1 | 200 | 175031
C2013-08 | Timber House | Evy Dierickx | Construction (residential building) | Residential Construction |  |  |  | G | G | 42 | 216 | 501030 | N | - | - | 8.796% | 15.09% | 29% | 42% | 0% | 47% | 57% | irregular | 24.3 | 34 | 1.2 | 43 | 39.7 | 0.3 | 5.7 | 13.8 | 3.9 | 12.3 | 12.5 | 3.1 | 14.7 | 13.8 | 2.3 | 27.4 | 17.3 | 1.5 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [10 empty] | -21913.2 | 20435.94 | -75594.56 | -26727.14 | 36791.73 | 0 | -12.08 | 11.19 | -19 | 0.95 | 0.03 | 0.87 | 0.94 | 0.08 | 1 | 0.94 | 0.05 | 0.92 | 0.99 | 0.02 | 1 | 235 | 576624
C2013-09 | Urban Development Project | Evy Dierickx | Construction (commercial building) | Integrated Building Complex |  |  |  | G | G | 71 | 291 | 1537398 | N | - | - | 23.71% | 10.38% | 34% | 51% | 6% | 16% | 92% | regular | 36.6 | 48.2 | 0.6 | 49.8 | 40.8 | 0.3 | 6.7 | 11.8 | 2 | 11.2 | 8.8 | 1.1 | 11.4 | 8.7 | 1.1 | 14.8 | 12.7 | 1.2 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [10 empty] | -77584.76 | 57723.77 | -159573.63 | -42556.84 | 72557.69 | 0 | -21.89 | 27.06 | -69 | 0.94 | 0.03 | 0.91 | 1.01 | 0.18 | 1 | 0.95 | 0.12 | 0.81 | 1 | 0.02 | 1 | 360 | 1696972
C2013-10 | Town Square | Evy Dierickx | Construction (civil) | Subterranean Parking; Public Square |  |  |  | G | G | 197 | 786 | 11421890 | N | - | - | 1.018% | 33.24% | 18% | 36% | 0% | 62% | 41% | irregular | 11.7 | 32.1 | 2.4 | 5.6 | 10.6 | 4.3 | 1.5 | 7.7 | 7.3 | 8.1 | 8.2 | 2.5 | 11.5 | 12.5 | 2.1 | 20.2 | 22.7 | 2.4 | 4.6 | 20.9 | 4.4 | 100 | 0 |  | 100 | 0 | [10 empty] | 2476655.18 | 1387020.75 | -3797033 | -1203052.42 | 813850.51 | 0 | -27.16 | 12 | 1 | 1.93 | 0.6 | 0.75 | 0.84 | 0.09 | 1 | 0.96 | 0.02 | 1 | 0.92 | 0.07 | 1 | 794 | 15218926
C2013-11 | Recreation Complex | Evy Dierickx | Construction (civil) | Sports Center; Public Construction |  |  |  | G | G | 167 | 359 | 5480520 | N | - | - | -7.799% | -0.5381% | 27% | 44% | 0% | 32% | 80% | regular | 22.2 | 40.1 | 1.4 | 33.5 | 39.1 | 0.9 | 2.4 | 5.9 | 2.9 | 8.3 | 7.7 | 1.7 | 10.8 | 10.8 | 2.3 | 16 | 20.5 | 2.9 | 1.8 | 13.3 | 7.3 | 100 | 0 |  | 100 | 0 | [10 empty] | 2439.77 | 39795.53 | 29490.5 | 172182.28 | 210593.4 | 88408 | 9.38 | 15.16 | 41 | 1.01 | 0.02 | 1.01 | 1.1 | 0.22 | 1.02 | 1.04 | 0.07 | 1.13 | 0.94 | 0.04 | 1 | 331 | 5451028
C2013-12 | Young Cattle Barn | Evy Dierickx | Construction (institutional building) | Experimental Farm; University |  |  |  | G | G | 27 | 115 | 818440 | N | - | - | 72.17% | 7.504% | 64% | 77% | 6% | 54% | 89% | regular | 64.3 | 47.1 | -0.6 | 65.5 | 42.1 | -0.5 | 12.2 | 14.1 | 1.2 | 16.4 | 13.9 | 1 | 19.8 | 15.1 | 0.9 | 18.9 | 24.1 | 2.7 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [10 empty] | -30390.36 | 19389.06 | -61413.25 | -117018.82 | 104761.31 | 0 | -46.6 | 25.71 | -73 | 0.94 | 0.04 | 0.93 | 0.73 | 0.17 | 1 | 0.44 | 0.22 | 0.61 | 0.94 | 0.09 | 1 | 198 | 879853
C2013-13 | Office Finishing Works (1) | Pieter Van Schoors | Construction (commercial building) | Finishing Works |  |  |  | G | G | 11 | 236 | 1118497 | N | - | - | -8.051% | -14.53% | 20% | 49% | 33% | 6% | 63% | irregular | 63.6 | 43.3 | -0.6 | 22.1 | 36.8 | 1.5 | 44 | 38 | 0.2 | 15 | 24.6 | 2.8 | 14.7 | 24.3 | 2.8 | 14.2 | 20.4 | 2.2 | 17.4 | 26.9 | 3 | 17.5 | 27.1 | 2.9 | 17.3 | 26.1 | 2.7 | [9 empty] | 98009 | 77091 | 162567 | 104631 | 91944 | 1093 | 15.76 | 19.22 | 19 | 1.15 | 0.16 | 1.17 | 3.13 | 5.42 | 1 | 1.28 | 0.33 | 1.09 | 0.97 | 0.03 | 1 | 217 | 955929
C2013-14 | Office Finishing Works (2) | Pieter Van Schoors | Construction (commercial building) | Finishing Works |  |  |  | G | G | 9 | 80 | 85848 | N | - | - | 23.75% | -12.09% | 62% | 80% | 66% | 47% | 68% | irregular | 22.2 | 41.6 | 1.6 | 17.8 | 30.4 | 2.6 | 13.9 | 30.7 | 2.6 | 20.6 | 27.6 | 2.6 | 19.2 | 28.1 | 2.6 | 29.4 | 23.7 | 1 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [10 empty] | 5600 | 4779 | 10380 | -12334 | 12334 | 0 | -26.5 | 7.5 | -19 | 1.14 | 0.01 | 1.14 | 0.62 | 0.39 | 1 | 0.41 | 0.41 | 0.81 | 1 | 0 | 1 | 99 | 75468
C2013-15 | Office Finishing Works (3) | Pieter Van Schoors | Construction (commercial building) | Finishing Works |  |  |  | G | G | 17 | 171 | 341468 | N | - | - | -29.82% | -9.7% | 25% | 43% | 21% | 35% | 79% | irregular | 11.8 | 32.2 | 2.6 | 26.8 | 29.3 | 1.8 | 7.8 | 22 | 2.9 | 13.9 | 22.4 | 2.5 | 16.1 | 23.5 | 2 | 17.6 | 25.9 | 2.4 | 17.8 | 14.9 | 0.6 | 20.1 | 15.7 | 0.6 | 16.4 | 22.7 | 3.1 | [9 empty] | 19684 | 23866 | 33124 | 103589 | 73156 | 46108 | 51.92 | 25.9 | 51 | 0.98 | 0.24 | 1.11 | 14.81 | 26.91 | 1.16 | 2.03 | 0.54 | 1.42 | 0.81 | 0.22 | 1 | 120 | 308344
C2013-16 | Office Finishing Works (4) | Pieter Van Schoors | Construction (commercial building) | Finishing Works |  |  |  | G | G | 7 | 196 | 248204 | N | - | - | -33.16% | -20% | 33% | 62% | 0% | 75% | 57% | irregular | 42.9 | 49.5 | 0.4 | 38.6 | 41.7 | 0.7 | 29.7 | 35.2 | 0.6 | 26.3 | 31.9 | 1.2 | 40.7 | 27.4 | 0.3 | 47.6 | 39.1 | 0.3 | 20.4 | 32.6 | 2.5 | 34.9 | 31.3 | 1.3 | 45.4 | 44.8 | 0.4 | [9 empty] | 27230 | 25940 | 49637 | -6295 | 8372 | 556 | 28.45 | 39.02 | 65 | 1.12 | 0.2 | 1.25 | 0.96 | 0.04 | 1 | 1.23 | 0.35 | 1.5 | 0.98 | 0.02 | 1 | 131 | 198567
C2013-17 | Office Finishing Works (5) | Pieter Van Schoors | Construction (commercial building) | Finishing Works |  |  |  | G | G | 23 | 161 | 244205 | N | - | - | -18.01% | -16.62% | 36% | 38% | 20% | 32% | 88% | regular | 12.7 | 30.5 | 2.3 | 35 | 34.4 | 0.8 | 9.2 | 24 | 2.7 | 11 | 19.1 | 4.3 | 13.9 | 20.8 | 3.4 | 18.1 | 25.5 | 2.7 | 17.6 | 15 | 1.2 | 19.6 | 15.6 | 0.9 | 20.1 | 20.5 | 2.7 | [9 empty] | 24973 | 21418 | 40599 | 31330 | 39336 | 18046 | 20.25 | 25.49 | 29 | 1.08 | 0.22 | 1.2 | 1.19 | 0.51 | 1.08 | 1.14 | 0.38 | 1.22 | 0.8 | 0.21 | 1 | 132 | 203606
C2014-01 | Mixed-use Building | Annelies Troch | Construction (residential building) | Residential Construction; Government |  |  |  | G | G | 52 | 474 | 38697824 | N | - | - | 0% | 2.79% | 50% | 38% | 3% | 49% | 76% | irregular | 44.4 | 40.4 | 0.3 | 35.3 | 39.4 | 0.4 | 6.7 | 9.9 | 2.3 | 10.7 | 10.9 | 1.2 | 21.7 | 18 | 0.6 | 29.5 | 38.7 | 1.2 | 52.8 | 49.9 | -0.1 | 100 | 0 |  | 100 | 0 | [10 empty] | -2006173.7708 | 1753596.598 | -1079820 | 715085.6667 | 2748809.6166 | 0 | 3.0104 | 18.9056 | 26 | 0.93042 | 0.036569 | 0.97 | 1.0504 | 0.18195 | 1 | 1.0045 | 0.072681 | 1.058 | 0.97917 | 0.066641 | 1 | 474 | 39777643
C2014-02 | Playing Cards | Annelies Troch | Engineering | New Machine Installation; Playing Cards |  |  |  | G | G | 23 | 124 | 191493 | N | - | - | 17.74% | -0.6405% | 81% | 94% | 0% | 14% | 89% | regular | 78.8 | 32 | -1.5 | 83.7 | 30.5 | -2.1 | 13 | 12.4 | 1.3 | 17.1 | 14.8 | 1 | 21.2 | 16.4 | 0.8 | 23.5 | 26.5 | 2.1 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [10 empty] | 539.6142 | 690.1651 | 1226.1875 | -13362.4965 | 13392.872 | 0 | -9.6207 | 8.2479 | -22 | 1.0031 | 0.0059326 | 1.01 | 0.91103 | 0.088253 | 1 | 0.90655 | 0.078357 | 0.85 | 1 | 0 | 1 | 146 | 190266.5
C2014-03 | Organizational Development | Annelies Troch | Education | Organizational Development |  |  |  | G | G | 112 | 229 | 43170 | Y | 1 | - | 13.54% | 93.91% | 9% | 31% | 0% | 36% | 87% | regular | 7.2 | 4.2 | -0.2 | 37 | 32.6 | 0.4 | 3.3 | 5.2 | 1.8 | 5.2 | 7.4 | 1.4 | 29.7 | 20.5 | -0.1 | 53.2 | 46.1 | 0 | 6.4 | 9 | 1.4 | 31.5 | 19 | -0.2 | 58.8 | 42.5 | -0.2 | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | -21612.1772 | 14983.5713 | -40542 | -6002.8076 | 4214.3917 | 0 | -33.6346 | 21.8213 | -31.25 | 0.52231 | 0.073605 | 0.52 | 0.77769 | 0.11423 | 1 | 0.77692 | 0.085249 | 0.88 | 0.83923 | 0.078 | 1 | 260 | 83712.1484
C2014-04 | Compressor Station Zelzate | Tim Vandenbussche | Construction (industrial) | Compressor Station; Gas Storage |  |  |  | Y | G | 24 | 522 | 62385600 | N | - | - | 62.45% | 5.035% | 95% | 100% | 0% | 100% | 92% | regular | [36 empty] | -1056294 | 1055960 | -3141328 | -5646742 | 4143552 | 0 | -102.21 | 80.09 | -326 | 0.98 | 0.02 | 0.95 | 0.83 | 0.15 | 1 | 0.73 | 0.13 | 0.62 | 1 | 0 | 1 | 848 | 65526930
C2014-05 | Apartment Building (1) | Nicolas Van Den Noortgate | Construction (residential building) | Demolition; Apartment Building |  |  |  | G | G | 25 | 228 | 532410 | N | - | - | 20.18% | 11.08% | 58% | 71% | 35% | 18% | 94% | regular | 60.24 | 44.6724 | -0.44653 | 76.68 | 33.8109 | -1.0908 | 10.64 | 16.9726 | 3.3112 | 11.4 | 16.5457 | 3.193 | 11.76 | 16.1549 | 3.3596 | 12.16 | 14.3685 | 1.9833 | 12.6 | 15.6231 | 2.4945 | 14.84 | 16.6173 | 2.1214 | 14.8 | 21.4177 | 2.8735 | [9 empty] | -41736.4362 | 14667.3556 | -59000.19 | -61471.8523 | 47586.7921 | 0 | -32.7308 | 10.5632 | -46 | 0.83769 | 0.055906 | 0.9 | 0.77154 | 0.16009 | 1 | 0.75692 | 0.064853 | 0.83 | 0.99846 | 0.003608 | 1 | 274 | 591411
C2014-06 | Apartment Building (2) | Nicolas Van Den Noortgate | Construction (residential building) | Demolition; Apartment Building |  |  |  | G | G | 29 | 547 | 3486376 | N | - | - | 11.7% | 3.234% | 57% | 75% | 46% | 15% | 90% | regular | 59 | 43.7 | -0.4 | 29.2 | 38.2 | 0.9 | 9.3 | 15.8 | 3.6 | 11 | 15.2 | 3.7 | 11.2 | 14.8 | 3.9 | 11.6 | 13.3 | 2.4 | 11.9 | 14.6 | 1.3 | 22 | 19.3 | 0.4 | 30 | 36.8 | 1.3 | [9 empty] | -85823.1537 | 29537.6577 | -112738.75 | -272911.65 | 227420.9169 | 0 | -49.6513 | 18.3739 | -64 | 0.95474 | 0.02233 | 0.97 | 0.88 | 0.11868 | 1 | 0.85579 | 0.065157 | 0.9 | 1 | 0 | 1 | 611 | 3599114
C2014-07 | Apartment Building (3) | Nicolas Van Den Noortgate | Construction (residential building) | Demolition; Apartment Building |  |  |  | G | G | 25 | 353 | 1102537 | N | - | - | 14.45% | 16.98% | 58% | 71% | 35% | 18% | 95% | regular | 60.2 | 43.9 | -0.4 | 47.2 | 44.4 | 0.1 | 11.4 | 15.4 | 2.7 | 13 | 15.8 | 2.6 | 13 | 15.5 | 2.7 | 12.7 | 13.3 | 1.9 | 12.9 | 15.9 | 3.6 | 13.1 | 15.4 | 3.7 | 11.9 | 14.5 | 2.2 | [9 empty] | -111722.8407 | 62040.8761 | -187160 | -76474.0514 | 60683.1087 | 0 | -33.1875 | 10.0699 | -51 | 0.81643 | 0.045294 | 0.85 | 0.81571 | 0.16504 | 1 | 0.80214 | 0.11546 | 0.87 | 0.99857 | 0.0034993 | 1 | 404 | 1289697
C2014-08 | Apartment Building (4) | Nicolas Van Den Noortgate | Construction (residential building) | Renovation; Apartment Building |  |  |  | G | G | 39 | 233 | 1992222 | N | - | - | 18.03% | 19.48% | 44% | 29% | 11% | 14% | 79% | irregular | 46.4 | 45.9 | 0.1 | 18.7 | 33.7 | 1.8 | 9.8 | 12.6 | 1.4 | 10.7 | 11.9 | 1.5 | 10.5 | 11.6 | 1.6 | 9.5 | 6.8 | 1.2 | 11.6 | 11.4 | 2.2 | 11.4 | 11.3 | 2.2 | 8 | 7.5 | 2.4 | [9 empty] | -165894.1338 | 141442.3425 | -388078.25 | -133144.0508 | 117842.3734 | 0 | -17.7885 | 12.8743 | -42 | 0.84538 | 0.050629 | 0.84 | 0.86231 | 0.08116 | 1 | 0.88923 | 0.068327 | 0.85 | 0.99077 | 0.013846 | 1 | 275 | 2380300.25
C2015-01 | Young Cattle Barn (2) | Tom Servranckx | Construction (institutional building) | Experimental Farm; University |  |  |  | G | G | 27 | 131 | 612769 | N | - | - | 60.31% | 5.5% | 57% | 73% | 0% | 46% | 94% | regular | [57 empty] | 210 | 646474
C2015-02 | Railway Station (1) | Tom Servranckx | Construction (civil) | Railway Station; Renovation |  |  |  | G | G | 216 | 417 | 1121317 | N | - | - | 20.14% | -13.67% | 8% | 66% | 1% | 80% | 84% | regular | [57 empty] | 501 | 967989
C2015-03 | Industrial Complex (1) | Tom Servranckx | Construction (industrial) | Automotive; Showroom; Offices |  |  |  | G | G | 135 | 257 | 2244091 | N | - | - | 9.728% | -16.72% | 16% | 43% | 0% | 58% | 91% | regular | [57 empty] | 282 | 1868796
C2015-04 | Apartment Building (5) | Tom Servranckx | Construction (residential building) | Apartment Building |  |  |  | G | G | 56 | 160 | 2750938 | N | - | - | 34.38% | -5.821% | 27% | 37% | 0% | 57% | 74% | irregular | [57 empty] | 215 | 2590797
C2015-05 | Apartment Building (6) | Tom Servranckx | Construction (residential building) | Apartment Building |  |  |  | G | G | 64 | 120 | 2524765 | N | - | - | 9.167% | 1.541% | 22% | 41% | 0% | 51% | 76% | irregular | [57 empty] | 131 | 2563676
C2015-06 | Family Residence (2) | Tom Servranckx | Construction (residential building) | Residential Construction |  |  |  | G | G | 184 | 260 | 143673 | N | - | - | 13.46% | 29.54% | 18% | 30% | 0% | 38% | 72% | irregular | [57 empty] | 295 | 186107
C2015-07 | Industrial Complex (2) | Tom Servranckx | Construction (industrial) | Production Hall; Offices |  |  |  | G | G | 138 | 297 | 5999600 | N | - | - | 21.21% | -9.752% | 27% | 38% | 0% | 49% | 86% | regular | [57 empty] | 360 | 5414544
C2015-08 | Garden Center | Tom Servranckx | Construction (commercial building) | Garden Center; Pet Shop |  |  |  | G | G | 186 | 191 | 467297 | N | - | - | 4.712% | -1.155% | 14% | 52% | 0% | 79% | 67% | irregular | [57 empty] | 200 | 461900
C2015-09 | Railway Station (2) | Tom Servranckx | Construction (civil) | Railway Station; Renovation |  |  |  | G | G | 348 | 354 | 1457424 | N | - | - | 61.02% | 47.22% | 4% | 48% | 0% | 75% | 76% | irregular | [57 empty] | 570 | 2145682
C2015-10 | Tax Return System (1) | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 20 | 85 | 18990 | Y | 10 | - | 0% | -57.82% | 10% | 82% | 23% | 21% | 77% | irregular | [57 empty] | 85 | 8010
C2015-11 | Staff Authorization System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 13 | 55 | 14400 | Y | 5 | - | 0% | -36.77% | 25% | 66% | 0% | 52% | 39% | irregular | [57 empty] | 55 | 9105
C2015-12 | Premium Payment System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 42 | 184 | 132570 | Y | 17 | - | 0% | -55.94% | 19% | 63% | 9% | 61% | 37% | irregular | [57 empty] | 184 | 58410
C2015-13 | Broker Account Conversion System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 22 | 117 | 12735 | Y | 7 | - | 0% | -21.55% | 19% | 60% | 7% | 51% | 79% | irregular | [57 empty] | 117 | 9990
C2015-14 | Supplementary Pensions Database | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 24 | 124 | 34260 | Y | 13 | - | 0% | -46.63% | 17% | 55% | 3% | 50% | 74% | irregular | [57 empty] | 124 | 18285
C2015-15 | FACTA System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 19 | 57 | 11700 | Y | 12 | - | -1.754% | -39.87% | 22% | 57% | 8% | 18% | 61% | irregular | [57 empty] | 56 | 7035
C2015-16 | Generic Document Output System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 30 | 270 | 64620 | Y | 13 | - | 0% | -0.766% | 10% | 61% | 12% | 26% | 62% | irregular | [57 empty] | 270 | 64125
C2015-17 | Insurance Bundling System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 91 | 209 | 281430 | Y | 24 | - | 13.4% | -0.1279% | 6% | 77% | 8% | 41% | 74% | irregular | [57 empty] | 237 | 281070
C2015-18 | Tax Return System (2) | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 20 | 128 | 39450 | Y | 6 | - | 0% | -35.67% | 10% | 66% | 16% | 11% | 68% | irregular | [57 empty] | 128 | 25380
C2015-19 | Receipt Numbering System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 24 | 182 | 43800 | Y | 12 | - | 0.5495% | -14.32% | 21% | 46% | 8% | 31% | 67% | irregular | [57 empty] | 183 | 37530
C2015-20 | Policy Numbering System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 11 | 171 | 12645 | Y | 6 | - | 0% | -12.22% | 20% | 62% | 20% | 13% | 5% | irregular | [57 empty] | 171 | 11100
C2015-21 | Investment Product (1) | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 17 | 37 | 4020 | Y | 8 | - | 0% | -19.4% | 18% | 35% | 2% | 36% | 23% | irregular | [57 empty] | 37 | 3240
C2015-22 | Risk Profile Questionnaire | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 31 | 151 | 29880 | Y | 9 | - | 0% | -41.77% | 16% | 70% | 9% | 40% | 81% | regular | [57 empty] | 151 | 17400
C2015-23 | Investment Product (2) | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 40 | 122 | 46920 | Y | 16 | - | -1.639% | -30.08% | 17% | 53% | 5% | 39% | 67% | irregular | [57 empty] | 120 | 32805
C2015-24 | CRM System | Jelle Van Ingelgem | IT | Insurance |  |  |  | G | G | 29 | 233 | 44130 | Y | 12 | - | -0.4292% | -16.45% | 7% | 59% | 7% | 29% | 83% | regular | [57 empty] | 232 | 36870
C2015-25 | Beer Tasting | Jelle Van Ingelgem | Event Management | Experiental Marketing |  |  |  | G | G | 26 | 14 | 1210 | Y | 4 | - | 7.143% | 47.11% | 16% | 40% | 21% | 19% | 85% | regular | [57 empty] | 15 | 1780
C2015-26 | Debt Collection System | Jelle Van Ingelgem | IT | Energy |  |  |  | G | G | 219 | 149 | 458112 | Y | 19 | - | 5.369% | 11.88% | 9% | 43% | 0% | 61% | 89% | regular | [57 empty] | 157 | 512546
C2015-27 | Railway Station Antwerp | Jelle Van Ingelgem | Construction (civil) | Maintenance; Renovation |  |  |  | G | G | 18 | 68 | 22704 | Y | 11 | - | 20.59% | 11.49% | 23% | 40% | -2% | 54% | 89% | regular | [57 empty] | 82 | 25313
C2015-28 | Website Tennis Vlaanderen | Jelle Van Ingelgem | IT | Website; Sports |  |  |  | G | G | 26 | 201 | 219275 | Y | 5 | - | 10.45% | 74.43% | 15% | 54% | 0% | 67% | 86% | regular | [57 empty] | 222 | 382475
C2015-29 | Fire Station | Shana Raes | Construction (institutional building) | Offices; Maintenance Space; Depot |  |  |  | G | G | 204 | 284 | 1874497 | N | - | - | 5.282% | 0.6716% | 48% | 34% | 0% | 41% | 91% | regular | [57 empty] | 299 | 1887087
C2015-30 | Social Apartments Ypres (1) | Torrino Debal | Construction (residential building) | Social Housing |  |  |  | G | G | 40 | 244 | 440941 | N | - | - | 4.098% | 0% | 25% | 51% | -1% | 76% | 81% | regular | [57 empty] | 254 | 440941
C2015-31 | Social Apartments Ypres (2) | Torrino Debal | Construction (residential building) | Social Housing |  |  |  | G | G | 29 | 271 | 1310723 | N | - | - | 36.16% | -2.177% | 32% | 49% | 23% | 43% | 87% | regular | [57 empty] | 369 | 1282186
C2015-32 | Social Apartments Ypres (3) | Torrino Debal | Construction (residential building) | Social Housing |  |  |  | G | G | 53 | 358 | 2509031 | N | - | - | -25.7% | 0% | 38% | 63% | 3% | 59% | 78% | irregular | [57 empty] | 266 | 2509031
C2015-33 | IJzertoren Memorial Square | Torrino Debal | Construction (civil) | Renovation; WWI |  |  |  | G | G | 12 | 50 | 214418 | N | - | - | 100% | 4.837% | 63% | 57% | 0% | 14% | 84% | regular | [57 empty] | 100 | 224790
C2015-34 | Roadworks Poperinge | Torrino Debal | Construction (civil) | Road; Sewerage; Renovation |  |  |  | G | G | 13 | 120 | 511326 | N | - | - | 98.33% | -13.87% | 91% | 99% | 0% | 18% | 65% | irregular | [57 empty] | 238 | 440394
C2015-35 | Retirement Apartments | Torrino Debal | Construction (residential building) | Demolition; Service Flats; Building |  |  |  | G | G | 10 | 850 | 14956314 | N | - | - | 10% | 7.439% | 44% | 75% | 20% | 30% | 75% | irregular | [57 empty] | 935 | 16068878
C2016-01 | Railway Bridge (1) | Mieke De Saedeleer | Construction (civil) | Railway Bridge; Renovation |  |  |  | G | G | 28 | 225 | 671384 | N | - | - | 27.56% | 4.814% | 51% | 71% | 0% | 86% | 93% | regular | [57 empty] | 287 | 703704
C2016-02 | Railway Bridge (2) | Mieke De Saedeleer | Construction (civil) | Railway Bridge; Renovation |  |  |  | G | G | 23 | 229 | 962182 | N | - | - | 10.48% | 1.056% | 63% | 71% | 0% | 82% | 81% | regular | [57 empty] | 253 | 972342
C2016-03 | Railway Bridge (3) | Mieke De Saedeleer | Construction (civil) | Railway Bridge; Renovation |  |  |  | G | G | 25 | 203 | 926888 | N | - | - | 13.3% | -1.743% | 16% | 37% | 0% | 56% | 56% | irregular | [57 empty] | 230 | 910728
C2016-04 | Railway Bridge (4) | Mieke De Saedeleer | Construction (civil) | Railway Bridge; Renovation |  |  |  | G | G | 26 | 248 | 906254 | N | - | - | 1.613% | 0% | 64% | 62% | 0% | 71% | 84% | regular | [57 empty] | 252 | 906254
C2016-05 | Railway Bridge (5) | Mieke De Saedeleer | Construction (civil) | Railway Bridge; Renovation |  |  |  | G | G | 32 | 195 | 832497 | N | - | - | 8.718% | 0% | 77% | 74% | 0% | 51% | 73% | irregular | [57 empty] | 212 | 832497
C2016-06 | Defense Building | Mieke De Saedeleer | Construction (institutional building) | Government; Defense; Renovation; IT |  |  |  | G | G | 98 | 252 | 4331260 | N | - | - | 7.937% | 0% | 14% | 55% | 0% | 76% | 79% | irregular | [57 empty] | 272 | 4331260
C2016-07 | Shopping Village Walkways | Mieke De Saedeleer | Construction (commercial building) | Shopping Village; Walkways; Renovation |  |  |  | G | G | 110 | 224 | 930179 | N | - | - | 48.21% | 0.2772% | 95% | 98% | 0% | 99% | 79% | irregular | [57 empty] | 332 | 932757
C2016-08 | SCM System | Mieke De Saedeleer | IT | Software; Production |  |  |  | G | G | 124 | 725 | 375253 | N | - | - | 2.069% | 16.92% | 49% | 59% | 8% | 52% | 78% | irregular | [57 empty] | 740 | 438742
C2016-09 | Data Loss Prevention System | Mieke De Saedeleer | IT | Software; Government |  |  |  | G | G | 118 | 195 | 584952 | N | - | - | -1.026% | 143.6% | 10% | 36% | 1% | 51% | 80% | regular | [57 empty] | 193 | 1425156
C2016-10 | Biofuel Refinery | Stijn Van Auwenis | Engineering | Biofuel; New Machine Installation |  |  |  | G | N/A | 23 | 360 | 14362625 | N | - | - | - | - | 18% | 22% | 6% | 21% | 42% | irregular | [57 empty] | 1 | 1
C2016-11 | Residential House (1) | William & Jef | Construction (residential building) | Residential Construction |  |  |  | G | G | 55 | 241 | 162472 | N | - | - | 5.394% | 0.4413% | 57% | 77% | 52% | 16% | 94% | regular | [44 empty] | -13 | [12 empty] | 254 | 163189
C2016-12 | Residential House (2) | William & Jef | Construction (residential building) | Residential Construction |  |  |  | G | G | 59 | 291 | 222858 | N | - | - | 0% | 1.538% | 56% | 72% | 50% | 19% | 86% | regular | [44 empty] | 0 | [12 empty] | 291 | 226285
C2016-13 | Residential House (3) | William & Jef | Construction (residential building) | Residential Construction |  |  |  | G | G | 51 | 306 | 367952 | N | - | - | 7.843% | 3.084% | 64% | 81% | 54% | 14% | 87% | regular | [44 empty] | -24 | [12 empty] | 330 | 379300
C2016-14 | Residential House (4) | William & Jef | Construction (residential building) | Residential Construction |  |  |  | G | G | 48 | 321 | 218366 | N | - | - | 0% | 1.674% | 68% | 78% | 42% | 10% | 93% | regular | [44 empty] | 0 | [12 empty] | 321 | 222022
C2016-15 | Residential House Structural Work | William & Jef | Construction (residential building) | Residential Construction; Carcass |  |  |  | G | G | 13 | 126 | 95694 | N | - | - | 3.175% | 5.297% | 66% | 75% | 100% | 0% | 87% | regular | [44 empty] | -4 | [12 empty] | 130 | 100763
C2016-16 | Residential House Finishing Works (1) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 24 | 90 | 54578 | N | - | - | 0% | 18.23% | 69% | 68% | 50% | 28% | 74% | irregular | [44 empty] | 0 | [12 empty] | 90 | 64527
C2016-17 | Residential House Finishing Works (2) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 24 | 86 | 54703 | N | - | - | 0% | 18.06% | 69% | 68% | 50% | 28% | 74% | irregular | [44 empty] | 0 | [12 empty] | 86 | 64580
C2016-18 | Residential House Finishing Works (3) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 25 | 91 | 51116 | N | - | - | 0% | 19% | 66% | 62% | 27% | 31% | 74% | irregular | [44 empty] | 0 | [12 empty] | 91 | 60830
C2016-19 | Residential House Finishing Works (4) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 25 | 91 | 51303 | N | - | - | 0% | 3.992% | 66% | 62% | 27% | 31% | 74% | irregular | [44 empty] | 0 | [12 empty] | 91 | 53351
C2016-20 | Residential House Finishing Works (5) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 25 | 91 | 52021 | N | - | - | 0% | 3.387% | 66% | 62% | 27% | 31% | 75% | irregular | [44 empty] | 0 | [12 empty] | 91 | 53783
C2016-21 | Residential House Finishing Works (6) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 24 | 101 | 54324 | N | - | - | 0% | 1.237% | 69% | 68% | 50% | 28% | 80% | regular | [44 empty] | 0 | [12 empty] | 101 | 54996
C2016-22 | Residential House Finishing Works (7) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 24 | 101 | 56969 | N | - | - | 0% | 1.497% | 69% | 68% | 50% | 28% | 80% | regular | [44 empty] | 0 | [12 empty] | 101 | 57822
C2016-23 | Residential House Finishing Works (8) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 24 | 101 | 56183 | N | - | - | 0% | 0.8241% | 69% | 68% | 50% | 28% | 80% | regular | [44 empty] | 0 | [12 empty] | 101 | 56646
C2016-24 | Residential House Finishing Works (9) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 24 | 101 | 52263 | N | - | - | 0% | 1.749% | 69% | 68% | 50% | 28% | 80% | regular | [44 empty] | 0 | [12 empty] | 101 | 53177
C2016-25 | Residential House Finishing Works (10) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 24 | 91 | 54580 | N | - | - | 0% | 3.972% | 69% | 68% | 50% | 28% | 71% | irregular | [44 empty] | 0 | [12 empty] | 91 | 56748
C2016-26 | Residential House Finishing Works (11) | William & Jef | Construction (residential building) | Housing Estate |  |  |  | G | G | 24 | 91 | 51286 | N | - | - | 0% | 3.964% | 69% | 68% | 50% | 28% | 71% | irregular | [44 empty] | 0 | [12 empty] | 91 | 53319
C2016-27 | Apartment Building Foundations | William & Jef | Construction (residential building) | Care Center |  |  |  | G | G | 16 | 78 | 813663 | N | - | - | 12.82% | 8.116% | 66% | 59% | 0% | 48% | 91% | regular | [44 empty] | -10 | [12 empty] | 88 | 879701
C2016-28 | Apartment Building Structural Work (1) | William & Jef | Construction (residential building) | Care Center |  |  |  | G | G | 19 | 71 | 569178 | N | - | - | 11.27% | 2.971% | 55% | 29% | 0% | 30% | 73% | irregular | [44 empty] | -8 | [12 empty] | 79 | 586087
C2016-29 | Apartment Building Structural Work (2) | William & Jef | Construction (residential building) | Care Center |  |  |  | G | G | 19 | 129 | 1797874 | N | - | - | 14.73% | 3.474% | 72% | 69% | 0% | 35% | 90% | regular | [44 empty] | -19 | [12 empty] | 148 | 1860331
C2016-30 | Apartment Building Structural Work (3) | William & Jef | Construction (residential building) | Care Center |  |  |  | G | G | 23 | 85 | 1319736 | N | - | - | 12.94% | 2.548% | 81% | 83% | 0% | 31% | 88% | regular | [44 empty] | -11 | [12 empty] | 96 | 1353361
C2016-31 | Apartment Building Finishing Works (1) | William & Jef | Construction (residential building) | Care Center |  |  |  | G | G | 23 | 105 | 488936 | N | - | - | 11.43% | 1.951% | 31% | 40% | 0% | 11% | 88% | regular | [44 empty] | -12 | [12 empty] | 117 | 498473
C2016-32 | Apartment Building Finishing Works (2) | William & Jef | Construction (residential building) | Care Center |  |  |  | G | G | 22 | 89 | 477381 | N | - | - | 8.989% | 4.108% | 52% | 72% | 0% | 27% | 87% | regular | [44 empty] | -8 | [12 empty] | 97 | 496991
C2016-33 | Apartment Building Finishing Works (3) | William & Jef | Construction (residential building) | Care Center |  |  |  | G | G | 23 | 116 | 377282 | N | - | - | 11.21% | 4.651% | 50% | 72% | 0% | 30% | 88% | regular | [44 empty] | -13 | [12 empty] | 129 | 394829
C2016-34 | Apartment Building Finishing Works (4) | William & Jef | Construction (residential building) | Care Center |  |  |  | G | G | 23 | 83 | 362476 | N | - | - | 10.84% | 5.902% | 40% | 43% | 0% | 26% | 86% | regular | [44 empty] | -9 | [12 empty] | 92 | 383871
C2016-35 | Sweetpack | Mayté & Thymo | Construction (Industrial) | - |  |  | O |  | N/A | 15 | 137 | - | N | - | - | - | - | 24% | 29% | 1% | 40% | - | N/A | 28 | 43.4 | 1 | 35.8 | 43.6 | 0.7 | 5.9 | 13 | 2.7 | 10.7 | 12.7 | 2.1 | 21.3 | 19 | 0.8 | 39.2 | 34.7 | 1 | [39 empty] | 1 | 1
C2016-36 | Residential reconstruction | Mayté & Thymo | Construction (residential building) | - |  |  | O |  | N/A | 18 | 103 | - | N | - | - | - | - | 35% | 30% | 29% | 3% | - | N/A | 44.6 | 43.2 | 0.3 | 49 | 37.9 | -0.3 | 16.4 | 18.8 | 0.8 | 15.8 | 15.4 | 1.3 | 19.6 | 16.3 | 1.1 | 15.1 | 22.5 | 3.2 | [39 empty] | 1 | 1
C2016-37 | Event planning | Mayté & Thymo | Event management | - |  |  | O |  | N/A | 30 | 145 | 426354 | N | - | - | - | - | 44% | 29% | 0% | 46% | 68.5% | Irregular | 23.3 | 42.3 | 1.3 | 41.1 | 36.3 | 0.8 | 0.9 | 2.5 | 3.9 | 10.3 | 17.6 | 4.5 | 10 | 17.3 | 4.7 | 14.6 | 18.2 | 2.7 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [31 empty] | 1 | 1
C2016-38 | Passive house construction | Mayté & Thymo | Construction (residential building) | - |  |  | O |  | N/A | 30 | 115 | 201405.59 | Y | 9 | - | - | - | 67% | 78% | 6% | 17% | 94.5% | Regular | 72.7 | 44.5 | -1.1 | 80 | 34.2 | -1.4 | 12.3 | 20.4 | 3 | 13 | 15.9 | 3.3 | 14 | 15.7 | 3.1 | 20.6 | 14.5 | 0.8 | 12.39 | 16.97 | 4 | 13.56 | 16.79 | 4 | 19.41 | 16.53 | 1.1 | [30 empty] | 1 | 1
C2016-39 | Investment building | Mayté & Thymo | Construction (residential building) | - |  |  | O |  | N/A | 30 | 181 | 91100 | N | - | - | - | - | 68% | 80% | 16% | 16% | 84.8% | Regular | 60 | 49 | -0.4 | 64.1 | 42.9 | -0.5 | 7.9 | 15.5 | 3.4 | 13.9 | 16.2 | 3 | 16 | 17 | 2.5 | 25.6 | 20 | 1.8 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [31 empty] | 1 | 1
C2016-40 | Artes Project (1) | Mayté & Thymo | Construction (commercial building) | - |  |  | O |  | N/A | 100 | 334 | - | Y | - | - | - | - | 22% | 26% | 100% | 35% | - | N/A | 19.7 | 39.4 | 1.5 | 29.4 | 38.1 | 1.2 | 0 | 0 |  | 0 | 0 |  | 51 | 1.5 | 3 | 100 | 0 | [40 empty] | 1 | 1
C2016-41 | Artes Project (2) | Mayté & Thymo | Construction (commercial building) | - |  |  | O |  | N/A | 50 | 51 | - | N | - | - | - | - | 30% | 44% | 2% | 58% | - | N/A | 30.1 | 44.8 | 0.9 | 8.1 | 22.4 | 3.2 | 5.6 | 12.1 | 2.8 | 7.7 | 13.2 | 2.2 | 32.8 | 20.3 | -0.4 | 64.9 | 36.6 | -0.2 | [39 empty] | 1 | 1
C2016-42 | Shared bike app development | Mayté & Thymo | Mobility | - | [5 empty] | 39 | 350 | 1703350 | Y | 8 | - | 0% | 0.6859% | 38% | 54% | 1% | 41% | 35.09% | Irregular | 40.6 | 49.1 | 0.4 | 47.5 | 43.9 | 0.3 | 7.8 | 13 | 2.1 | 17.7 | 15.8 | 1.7 | 17 | 15.7 | 1.6 | 11.1 | 11 | 1.8 | 11.11 | 16.47 | 1.8 | 34.54 | 18.9 | -0.5 | 54.4 | 43.55 | 0 | 26.88 | 32.28 | 1.2 | 45.5 | 23.16 | 0 | 56.63 | 38.62 | -0.1 | -8254.94 | 3735.31 | -11683 | -9716.94 | 135010.29 | 0 | 2.26 | 80.63 | 0 | 0.97 | 0.06 | 0.99 | 0.96 | 0.17 | 1 | 0.98 | 0.08 | 1 | 1 | 0.01 | 1 | 350 | 1715032.9999
C2016-43 | Mail delivery app | Mayté & Thymo | IT | - |  |  | O |  | N/A | 49 | 363 | - | N | - | - | - | - | 41% | 70% | 0% | 43% | - | N/A | 17.2 | 27.7 | 1.6 | 48.4 | 33.3 | 0.1 | 5.6 | 11.6 | 2.7 | 9.7 | 9.3 | 2.2 | 9.6 | 9 | 2.3 | 8.2 | 6.8 | 1.7 | [39 empty] | 1 | 1
C2017-01 | Apartment Construction | Mayté & Thymo | Construction (commercial building) | - |  |  | O |  | N/A | 52 | 383 | 758881192 | N | - | - | - | - | 45% | 52% | 7% | 56% | 85.56% | Regular | 46.2 | 48.7 | 0.2 | 56.9 | 44.4 | -0.2 | 8.2 | 11.2 | 1.4 | 11.5 | 10.7 | 1.2 | 14.5 | 13.5 | 1.3 | 13.8 | 22.2 | 3.4 | 42.31 | 49.4 | 0.3 | 100 | 0 |  | 100 | 0 | [31 empty] | 1 | 1
C2017-02 | Charging block network | Mayté & Thymo | Mobility | - |  |  | O |  | N/A | 25 | 278 | - | N | - | - | - | - | 45% | 64% | 18% | 3% | - | N/A | 47.8 | 48.2 | 0.1 | 69.3 | 34.6 | -0.8 | 9.6 | 15.5 | 2.3 | 15.4 | 17.3 | 2 | 17.2 | 18.5 | 1.9 | 17.1 | 21.1 | 2.8 | [39 empty] | 1 | 1
C2017-03 | Hydrogen Island | Mayté & Thymo | Construction (Civil) | - |  |  | O |  | N/A | 87 | 2804 | - | N | - | - | - | - | 37% | 49% | 0% | 51% | - | N/A | 33.3 | 47.1 | 0.7 | 36.7 | 45.4 | 0.6 | 5.9 | 10.2 | 1.7 | 12 | 9.1 | 1.3 | 11.8 | 9.1 | 1.2 | 8.8 | 7.4 | 1.3 | [39 empty] | 1 | 1
C2017-04 | Recy-call | Mayté & Thymo | Event management | - |  |  | O |  | N/A | 49 | 148 | 78350 | Y | 1 | - | - | - | 45% | 31% | 7% | 35% | 64.68% | Irregular | 26.5 | 44.1 | 1.1 | 9.4 | 16.7 | 3.8 | 6 | 12.8 | 2.9 | 9.5 | 13.4 | 2.5 | 23.1 | 19.7 | 0.6 | 43.1 | 34.3 | 0.9 | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [22 empty] | 1 | 1
C2017-05 | JobFair Gent | Mayté & Thymo | Event management | - |  |  | O |  | N/A | 30 | 126 | 34720 | Y | 6 | - | - | - | 41% | 54% | 0% | 54% | 86.43% | Regular | 24.1 | 35.3 | 1.4 | 50 | 34.6 | 0.2 | 6.9 | 15.4 | 2.9 | 13.8 | 14 | 2.2 | 14.7 | 13.3 | 2.1 | 12.1 | 12.4 | 1.5 | 16.17 | 15.22 | 1.9 | 17.18 | 14.6 | 1.8 | 12.93 | 12.41 | 1.4 | 33.33 | 26.4 | 1.4 | 34.17 | 25.61 | 1.3 | 23 | 20.83 | 1.7 | [21 empty] | 1 | 1
C2017-06 | Landing gear development | Mayté & Thymo | Engineering | - |  |  | O |  |  | 24 | 320 | 11562500 | Y | 4 | - | -10.94% | -7.565% | 70% | 71% | 71% | 0% | 83.22% | Regular | 71.6 | 39.4 | -1 | 86.2 | 25.2 | -2.4 | 14.3 | 14 | 0.9 | 18.2 | 16.8 | 1 | 20.8 | 17.1 | 0.8 | 16.2 | 21.8 | 2.9 | 18.3 | 14.93 | 0.9 | 20.71 | 15.01 | 0.8 | 15.56 | 21.13 | 3.3 | 46.75 | 30.82 | 1.1 | 44.25 | 30.29 | 1.4 | 33.25 | 27.9 | 1.6 | 731286.57 | 352177.77 | 874700 | 681239.2 | 393588.9 | 595000 | 188.79 | 131.87 | 280 | 1.12 | 0.04 | 1.08 | 1.12 | 0.06 | 1.05 | 1.15 | 0.05 | 1.12 | 1 | 0.01 | 1 | 285 | 10687800
C2018-01 | App development | Mayté & Thymo | IT | - |  |  |  |  | N/A | 22 | 110 | - | N | - | - | - | - | 80% | 82% | 40% | 4% | - | N/A | 77.9 | 38.6 | -1.4 | 92.7 | 15.3 | -2.5 | 16.2 | 12.7 | 0.7 | 19.7 | 14.4 | 0.6 | 18.5 | 14.7 | 0.6 | 14 | 11.5 | 1.8 | [39 empty] | 1 | 1
C2018-02 | eScooter | Mayté & Thymo | Mobility | - |  |  |  |  | N/A | 19 | 260 | 396760 | Y | 5 | - | - | - | 61% | 63% | 37% | 10% | 78.44% | Irregular | 63.5 | 45 | -0.6 | 80.2 | 30.7 | -1.3 | 13.6 | 17.5 | 1.9 | 18.7 | 17.1 | 1.9 | 18.3 | 16.7 | 2.2 | 13.2 | 11.8 | 2.2 | 15.25 | 19.78 | 3 | 15.5 | 19.47 | 3.2 | 11.66 | 15.46 | 3.2 | 43.6 | 25.71 | 1.6 | 42 | 26.22 | 1.7 | 30.4 | 23.7 | 1.8 | [21 empty] | 1 | 1
C2018-03 | Castelein | Mayté & Thymo | Construction (Industrial) | - |  |  |  |  | N/A | 20 | 177 | 1480224.75 | Y | 8 | - | - | - | 68% | 76% | 0% | 10% | 83.77% | Regular | 65.1 | 45.2 | -0.7 | 41.4 | 42.7 | 0.3 | 14.3 | 16.6 | 0.9 | 17.4 | 17.2 | 1 | 26.5 | 19.3 | 0.1 | 31.4 | 35.7 | 1.3 | 11.85 | 20.24 | 2.4 | 38.65 | 19.92 | -0.3 | 61.66 | 44.06 | -0.4 | 12.5 | 33.07 | 2.8 | 56.25 | 16.54 | 2.8 | 100 | 0 | [22 empty] | 1 | 1
C2018-04 | Christmas market (1) | Mayté & Thymo | Event management | - |  |  |  |  | N/A | 38 | 94 | 69080.3516 | N | - | - | - | - | 40% | 50% | 35% | 8% | 47.7% | Irregular | 29.7 | 43.1 | 1 | 18.9 | 31.5 | 1.5 | 1.4 | 5.9 | 4.2 | 2.7 | 9.2 | 5 | 48.2 | 19 | -1.9 | 87.2 | 25.3 | -1.6 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [31 empty] | 1 | 1
C2018-05 | Music festival | Mayté & Thymo | Event management | - |  |  |  |  | N/A | 30 | 265 | 1287700 | N | - | - | - | - | 55% | 43% | 30% | 17% | 84.28% | Regular | 57.7 | 45.1 | -0.3 | 78.9 | 31.1 | -1.3 | 8.6 | 14.9 | 2.4 | 15.4 | 15.9 | 1.8 | 23.6 | 18.1 | 0.9 | 28.4 | 33.6 | 1.5 | 10.31 | 16.14 | 1.5 | 39.98 | 16.31 | -1.3 | 65.22 | 43.09 | -0.5 | [30 empty] | 1 | 1
C2018-06 | Camera network | Mayté & Thymo | Construction (civil) | - |  |  |  |  | N/A | 17 | 21 | 37980 | Y | 2 | - | - | - | 50% | 37% | -5% | 36% | 70% | Irregular | 52.9 | 49.9 | -0.1 | 66.6 | 37.7 | -0.5 | 16.4 | 17.1 | 0.4 | 22 | 14.6 | 0.7 | 21.6 | 14.6 | 0.5 | 25.8 | 14.7 | 0.4 | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [22 empty] | 1 | 1
C2018-07 | WKB development | Mayté & Thymo | IT | - |  |  |  |  | N/A | 11 | 43 | 220271 | Y | 6 | - | - | - | 20% | 49% | 0% | 69% | 57.21% | Irregular | 27.3 | 44.5 | 1.2 | 45.2 | 35.9 | 0.7 | 15.6 | 27.1 | 1.7 | 19.7 | 22.9 | 2 | 19.9 | 22.3 | 2.1 | 14.5 | 16 | 2.1 | 24.72 | 17.55 | 1.7 | 29.14 | 16.77 | 1.5 | 22 | 27.64 | 2.4 | 0 | 0 |  | 50 | 0 |  | 100 | 0 | [22 empty] | 1 | 1
C2018-08 | Bikesharing platform | Mayté & Thymo | Mobility | - | [5 empty] | 23 | 393 | 5611571 | Y | 3 | - | 50.13% | 1.483% | 36% | 41% | 7% | 20% | 58.54% | Irregular | 31.5 | 45.6 | 0.9 | 48.1 | 40.4 | 0.3 | 9.1 | 16.8 | 1.9 | 16.1 | 17.7 | 1.6 | 16.1 | 17.4 | 1.8 | 12.3 | 12 | 1.6 | 17.77 | 16.67 | 0.7 | 23.34 | 18.5 | 0.5 | 25.22 | 30.63 | 1.9 | 52.33 | 25.77 | -1.7 | 51 | 23.37 | -1.7 | 36 | 17.72 | -1.7 | -51308.76 | 22497.95 | -83220.5 | -687493.27 | 1654633.02 | 0 | -690.59 | 418.47 | -1576 | 0.96 | 0.04 | 0.99 | 0.86 | 0.3 | 1 | 0.71 | 0.04 | 0.67 | 1 | 0.01 | 1 | 590 | 5694790.99
C2018-09 | CarSharing platform | Mayté & Thymo | Mobility | - |  |  |  |  | N/A | 41 | 214 | 439234 | Y | 5 | - | - | - | 50% | 50% | 9% | 20% | 71.78% | Irregular | 43.1 | 36.2 | 0.4 | 42.2 | 37.2 | 0 | 8.5 | 13.4 | 2.9 | 11.5 | 12 | 2.6 | 12.8 | 13 | 2.4 | 18.9 | 19.2 | 2.2 | 10.71 | 13.97 | 1.7 | 26.94 | 19.66 | 0.2 | 45.97 | 39.11 | 0.5 | 35.2 | 30.26 | 0.6 | 32.4 | 29.83 | 0.5 | 27.4 | 17.98 | 0.9 | [21 empty] | 1 | 1
C2018-10 | Fontein | Mayté & Thymo | Construction (Civil) | - | [5 empty] | 42 | 99 | 115115.23 | Y | 1 | - | 21.09% | 7.711e-06% | 58% | 62% | 4% | 39% | 59.92% | Irregular | 42.9 | 49.5 | 0.3 | 47.7 | 46.1 | 0.2 | 1.6 | 2.4 | 1.4 | 9 | 14.9 | 5.3 | 17 | 19.9 | 2.2 | 33.9 | 30.2 | 1.5 | 6.22 | 14.81 | 3 | 45.66 | 12.03 | -1.7 | 82.19 | 34.71 | -1.6 | 0 | 0 |  | 50 | 0 |  | 100 | 0 |  | 0 | 0 | 0 | -5406.18 | 8603.44 | 0 | -63.63 | 74.26 | -167 | 1 | 0 | 1 | 0.95 | 0.08 | 1 | 0.92 | 0.09 | 0.83 | 1 | 0 | 1 | 119.875 | 115115.2389
C2018-11 | Warehouse renovation | Mayté & Thymo | Construction (Industrial) | - |  |  |  |  | N/A | 36 | 9 | - | N | - | - | - | - | 60% | 71% | 0% | 72% | - | N/A | 61.1 | 48.7 | -0.5 | 47 | 45.6 | 0.3 | 7.2 | 16.8 | 2.2 | 8.9 | 15.4 | 2.2 | 38.7 | 18.1 | -0.9 | 67.9 | 38.9 | -0.5 | [39 empty] | 1 | 1
C2018-12 | Cornflakes new taste | Mayté & Thymo | Engineering | - |  |  |  |  | N/A | 31 | 275 | 750110 | Y | 2 | - | - | - | 34% | 26% | 2% | 43% | 56.86% | Irregular | 36.7 | 45.9 | 0.6 | 50 | 43.8 | 0.1 | 8.6 | 17.3 | 2.9 | 11.4 | 15.7 | 2.5 | 14.6 | 17.7 | 1.8 | 20.5 | 25.8 | 2 | 7 | 16.41 | 3.4 | 36.87 | 21.16 | -0.6 | 67.36 | 41.23 | -0.6 | 57.5 | 41.5 |  | 59 | 40 |  | 51.5 | 39.5 | [22 empty] | 1 | 1
C2018-13 | Christmas market (2) | Mayté & Thymo | Event management | - |  |  |  |  | JA | 31 | 132 | 58900 | Y | 2 | - | 40.34% | 42.48% | 56% | 72% | 25% | 12% | 86.74% | Regular | 30 | 45.8 | 0.9 | 38.7 | 39.3 | 0.8 | 5.8 | 16.1 | 2.8 | 12 | 17.2 | 2.3 | 18.1 | 19.2 | 1.3 | 30.3 | 27 | 1.6 | 9.26 | 16.24 | 1.9 | 36.42 | 19.09 | -0.9 | 62.74 | 40.54 | -0.2 | 50 | 50 |  | 75 | 25 |  | 99.5 | 0.5 |  | -11520.72 | 7211.05 | -25020 | -9559.1 | 7527.81 | 0 | -198.59 | 137.73 | -426 | 0.69 | 0.02 | 0.7 | 0.74 | 0.2 | 1 | 0.78 | 0.11 | 0.71 | 0.99 | 0.02 | 1 | 185.25 | 83920
C2019-01 | Lepelstraat | Jens Martens | Construction (residential building) | [6 empty] | 86 | 533 | 1292979 | N | - | - | 26.27% | -1.428% | 55% | 57% | 14% | 12% | - |  | 0.55814 | 0.49952 | -0.23832 | 0.63465 | 0.43156 | -0.44033 | 0 | 0 |  | 0 | 0 |  | 1 | 0 |  | 1 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0
C2019-02 | Social Housing | Jens Martens | Construction (residential building) | [6 empty] | 18 | 352 | 734602.11 | N | - | - | 0.8523% | 1.899% | 41% | 48% | 4% | 36% | -
C2019-03 | Emergency Department | Jens Martens | Construction (civil) | [6 empty] | 17 | 413 | 967878 | N | - | - | 26.15% | 0.31305 | 37% | 43% | 3% | 37% | -
C2019-04 | Nuclear Healthcare | Jens Martens | Construction (civil) | [6 empty] | 33 | 373 | 4318950 | N | - | - | 39.41% | -2% | 84% | 85% | 60% | 2% | -
C2019-05 | Fuel Tank Filter | Jens Martens | Engineering | [6 empty] | 15 | 510 | 1456000 | N | - | - | 0.9804% | 1.394% | 28% | 75% | 21% | 20% | -
C2019-06 | Production Line Change | Jens Martens | Engineering | [6 empty] | 23 | 480 | 1512000 | N | - | - | 4.375% | 1.459% | 27% | 61% | 3% | 22% | -
C2019-07 | Gluing Machinge | Jens Martens | Engineering | [6 empty] | 8 | 150 | 107500 | N | - | - | 26% | 8.651% | 42% | 33% | 0% | 25% | -
C2019-08 | Labeling Machine | Jens Martens | Engineering | [6 empty] | 7 | 115 | 114700 | N | - | - | 58.26% | 11.77% | 66% | 75% | 0% | 75% | -
C2019-09 | Recreation building | Mayté & Thymo | Construction (commercial building) | - |  |  |  |  | JA | 41 | 215 | 267500 | N | - | - | 0% | 18.49% | 56% | 60% | 64% | 8% | 77.58% | Irregular | 59 | 37.7 | -0.2 | 38.2 | 34.7 | 0.1 | 17 | 46.1 | 5.8 | 14 | 11.9 | 1.1 | 13.7 | 11.4 | 1.2 | 10 | 7.5 | 1.2 | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [10 empty] | -8500 | 7788.88 | -19500 | -5000 | 0 | -5000 | -122.67 | 81.67 | -120 | 0.9 | 0.05 | 0.83 | 0.92 | 0.03 | 0.95 | 0.83 | 0.11 | 0.88 | 0.9 | 0.02 | 0.93 | 215 | 316954.7872
C2019-10 | Family Residence (3) | Mayté & Thymo | Construction (residential building) | - |  |  |  |  | N/A | 49 | 115 | 209621.52 | N | - | - | - | - | 35% | 41% | 3% | 33% | 85.03% | Regular | 36.7 | 47.9 | 0.6 | 49.5 | 42.9 | 0.1 | 6.1 | 16.1 | 4.1 | 8.8 | 12.5 | 4 | 9.9 | 11.9 | 4.1 | 29.9 | 14 | -0.7 | 0 | 0 |  | 100 | 0 |  | 100 | 0
C2019-11 | Tournament infrastructure | Mayté & Thymo | Event management | - | [5 empty] | 30 | 27 | 126955.3 | Y | 1 | - | -16.2% | -1.932% | 27% | 62% | 0% | 23% | 75.17% | Irregular | 7 | 19 | 2.8 | 23.3 | 25.2 | 1.7 | 0.3 | 0.9 | 3.6 | 82.9 | 22.3 | -3.6 | 67.1 | 7.6 | 0.8 | 32.5 | 21.5 | 2.3 | 92.97 | 24.86 | -3.7 | 67.63 | 8.06 | 0.3 | 32.63 | 20.33 | 2.5 | 99 | 0 |  | 100 | 0 |  | 82 | 0 |  | 479.72 | 186.12 | 604 | 30899.54 | 19139.04 | 2453 | 44.39 | 19.37 | 31 | 1.01 | 0 | 1 | 3.79 | 4.88 | 1.02 | 1.96 | 0.97 | 1.19 | 0.81 | 0.22 | 1 | 22.625 | 124502.3
C2019-12 | Residential apartment building | Mayté & Thymo | Construction (residential building) | - |  |  |  |  | N/A | 52 | 289 | - | Y | 1 | - | - | - | 45% | 59% | 3% | 29% | - | N/A | 48.1 | 50 | 0.1 | 6.5 | 16 | 3.3 | 0 | 0 |  | 0 | 0 |  | 51 | 6.9 | 7.2 | 99.8 | 1.6 | -7.2 | [9 empty] | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [22 empty] | 1 | 1
C2019-13 | Weekend trip organisation | Mayté & Thymo | Event management | - |  |  |  |  | N/A | 19 | 2 | 3721.6 | Y | 2 | 1 | - | - | 77% | 85% | 50% | 5% | 67.82% | Irregular | 73.7 | 44 | -1.2 | 82.9 | 29.3 | -1.3 | 0 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [22 empty] | 1 | 1
C2019-14 | Weekend trip preparation | Mayté & Thymo | Event management | - |  |  |  |  | N/A | 24 | 67 | 2450 | Y | 1 | - | - | - | 43% | 39% | 18% | 9% | 47.83% | Irregular | 46 | 48.6 | 0.2 | 63.7 | 34.7 | -0.5 | 10.2 | 18.8 | 2.3 | 14.5 | 16.1 | 1.5 | 20.7 | 18.3 | 0.8 | 29.7 | 28.2 | 1.9 | 0 | 0 |  | 100 | 0 |  | 100 | 0 |  | 0 | 0 |  | 100 | 0 |  | 100 | 0 | [22 empty] | 1 | 1
C2019-15 | Electrical step sharing platform | Mayté & Thymo | Mobility | - |  |  |  |  | N/A | 30 | 400 | - | Y | 2 | - | - | - | 58% | 70% | 8% | 20% | - | N/A | 60 | 49 | -0.4 | 71.2 | 37.4 | -0.7 | 11.2 | 14.7 | 1.6 | 15.3 | 14.8 | 1.7 | 15.1 | 14 | 1.8 | 12 | 8.9 | 1.8 | [9 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [22 empty] | 1 | 1
C2019-16 | Lock Ganzepoot | Mayté & Thymo | Construction (civil) | - |  |  |  |  | N/A | 32 | 23 | 170000 | Y | 1 | - | - | - | 64% | 74% | 23% | 6% | 91.59% | Regular | 69.1 | 42.8 | -0.9 | 41.6 | 41.5 | 0.3 | 12.4 | 11.6 | 1.1 | 14.6 | 13.2 | 2.7 | 18.8 | 16.2 | 2.7 | 17.7 | 27.2 | 2.7 | 17.13 | 11.55 | 0.1 | 20.59 | 13.97 | 0.5 | 17.88 | 28.35 | 2.4 | 100 | 0 |  | 100 | 0 |  | 98 | 0 | [22 empty] | 1 | 1
C2019-17 | Wine production | Mayté & Thymo | Engineering | - |  |  |  |  | N/A | 25 | 93 | - | N | - | - | - | - | 45% | 48% | 5% | 37% | - | N/A | 50.5 | 41.5 | 0 | 74.4 | 32.5 | -1 | 13.5 | 16.4 | 1.6 | 12 | 15.4 | 2 | 11.6 | 15.7 | 1.9 | 12 | 9.5 | 1.1 | [39 empty] | 1 | 1
C2019-18 | Greenhouse | Mayté & Thymo | Construction (Industrial) | - |  |  |  |  | N/A | 23 | 163 | 2978315.3 | Y | 6 | - | - | - | 45% | 48% | 8% | 22% | 90.24% | Regular | 50.6 | 46 | 0 | 74.2 | 31.1 | -1.1 | 15.9 | 16.6 | 0.6 | 16.7 | 13.7 | 0.7 | 19.2 | 14.4 | 0.7 | 14.8 | 19.5 | 3.9 | 16.78 | 16.34 | 1.3 | 20.49 | 18.31 | 0.9 | 18.83 | 27.09 | 2.4 | 55.9 | 13.29 | -3.3 | 55.9 | 13.29 | -3.3 | 55.9 | 13.29 | -3.3 | [21 empty] | 1 | 1
C2019-19 | Traditional house | Mayté & Thymo | Construction (residential building) | - |  |  |  |  | N/A | 25 | 130 | 240840 | Y | 6 | - | - | - | 66% | 68% | 75% | 2% | 92.58% | Regular | 68.2 | 41 | -0.8 | 85.2 | 25.8 | -1.9 | 13.6 | 11.6 | 0.7 | 20.3 | 13 | 0.4 | 126.4 | 525.5 | 5 | 11.1 | 9.1 | 0.5 | 18.92 | 15.3 | 0.8 | 20.88 | 15.53 | 0.8 | 14.64 | 20.03 | 3.3 | 76.33 | 33.63 | -2.3 | 75.17 | 33.7 | -2.3 | 62.17 | 26.95 | -1.9 | [21 empty] | 1 | 1
C2019-20 | Paradice | Mayté & Thymo | Construction (commercial building) | - |  |  |  |  | N/A | 39 | 362 | 142020 | N | - | - | - | - | 57% | 68% | 17% | 18% | 84.62% | Regular | 56.7 | 46.2 | -0.3 | 27.1 | 36.6 | 1 | 7.3 | 14.4 | 2.9 | 11.8 | 13.7 | 2.7 | 13.7 | 13.8 | 2.4 | 21.1 | 18.4 | 2.2 | 11.33 | 15.66 | 3.7 | 18.55 | 19.32 | 1.8 | 30.45 | 30.69 | 1.4 | [30 empty] | 1 | 1
C2019-21 | Tanglewood 4 | Mayté & Thymo | Engineering | - |  |  |  |  | N/A | 31 | 671 | 13812919 | Y | 3 | - | - | - | 40% | 59% | 92% | 4% | 66.7% | Irregular | 38 | 44.5 | 0.5 | 35.6 | 36 | 0.6 | 9.7 | 15.4 | 1.7 | 12.4 | 14.5 | 2.2 | 12.6 | 14.1 | 2.3 | 9.8 | 10.3 | 2 | 13.9 | 15.62 | 2.4 | 13.91 | 14.93 | 2.5 | 10.58 | 10.77 | 2.3 | 0.16 | 0.2 | 3.9 | 0.16 | 0.2 | 3.9 | 0.16 | 0.2 | 3.9 | [21 empty] | 1 | 1
C2019-22 | BAM deelproject 1 | Mayté & Thymo | Construction (Civil) | - |  |  |  | ANTAL.ALS('[Analysis sheet (opgekuist 30_03).xlsx]baseline'!$N$141:$N$189;"<="&AK5) | N/A | 1419 | 1203 | - | N | - | - | - | - | 4% | 66% | 0% | 81% | - | N/A | 1.4 | 9.4 | 7.1 | 3.8 | 12.1 | 5.7 | 0.2 | 2.1 | 16.8 | 7.8 | 6.5 | 1.2 | 10.3 | 10.8 | 2.3 | 19.8 | 20.9 | 2.5 | [39 empty] | 1 | 1
C2019-23 | BAM deelproject 2 | Mayté & Thymo | Construction (Civil) | - |  |  |  |  | N/A | 646 | 1188 | - | N | - | - | - | - | 5% | 50% | 0% | 63% | - | N/A | 0.2 | 3.9 | 25.4 | 1.5 | 4.5 | 16.6 | 0.2 | 3.9 | 25.4 | 7.1 | 7.1 | 4.2 | 12.5 | 14.3 | 2.1 | 25.8 | 27.8 | 1.8 | [39 empty] | 1 | 1
C2019-24 | BAM deelproject 3a | Mayté & Thymo | Construction (Civil) | - |  |  |  |  | N/A | 1373 | 1041 | - | N | - | - | - | - | 1% | 61% | 0% | 78% | - | N/A | 0.8 | 8.6 | 11 | 3.5 | 10.2 | 7.2 | 0.1 | 2.4 | 22.3 | 6.5 | 7.1 | 2.2 | 19.2 | 18.7 | 0.9 | 36.9 | 38.2 | 0.9 | [39 empty] | 1 | 1
C2019-25 | BAM deelproject 3b | Mayté & Thymo | Construction (Civil) | - |  |  |  |  | N/A | 1796 | 1306 | - | N | - | - | - | - | 2% | 54% | 0% | 70% | - | N/A | 1.8 | 13.1 | 7.3 | 4.3 | 14.4 | 5.8 | 0.2 | 2.3 | 20.9 | 7.2 | 6.5 | 1.5 | 13.2 | 14.7 | 1.7 | 24.3 | 30 | 1.7 | [39 empty] | 1 | 1
C2019-26 | BAM deelproject 4 | Mayté & Thymo | Construction (Civil) | - |  |  |  |  | N/A | 676 | 897 | - | N | - | - | - | - | 7% | 62% | 0% | 79% | - | N/A | 7.5 | 26.4 | 3.2 | 6.2 | 14.8 | 5.1 | 0.4 | 3.8 | 20.8 | 7.3 | 7.2 | 3.3 | 13.1 | 15 | 1.8 | 28.8 | 28.5 | 1.6 | [39 empty] | 1 | 1
C2019-27 | BAM deelproject 6 | Mayté & Thymo | Construction (Civil) | - |  |  |  |  | N/A | 899 | 834 | - | N | - | - | - | - | 3% | 54% | 0% | 74% | - | N/A | 2.3 | 15.1 | 6.3 | 4 | 12.6 | 5.9 | 0.2 | 3.2 | 24.4 | 7.8 | 6.6 | 3 | 11.6 | 12.3 | 2.3 | 25.2 | 24.2 | 1.8 | [39 empty] | 1 | 1
C2019-28 | BAM deelproject 7 | Mayté & Thymo | Construction (Civil) | - |  |  |  |  | N/A | 132 | 863 | - | N | - | - | - | - | 16% | 21% | 0% | 38% | - | N/A | 11.5 | 16.8 | 1.3 | 27.7 | 28.4 | 0.9 | 2 | 6.6 | 6 | 8.4 | 9.5 | 3.1 | 12.9 | 14.9 | 1.8 | 22.2 | 27.5 | 2.2 | [39 empty] | 1 | 1
C2020-01 | Racing car upgrading | Marina Aristotile, Claudio Galli & others | Engineering | Car upgrade; Engineering project |  |  |  | G | N/A | 54 | 45 | N/A | N | - | - | - | - | 7% | 42% | 1% | 54% | - | N/A | 8 | 22.6 | 3.3 | 25 | 25.9 | 1.7 | 4 | 13 | 4.5 | 6 | 12.5 | 4.3 | 6 | 12.3 | 4.3 | 8 | 8.4 | 3.2
C2022-01 | Student kick-off Kramersplein | Boris Borysiewicz, Ellen Van Moere, Joallen Ghysbrecht, Lucas Baeteman & Mathias Brabants | Event management | Festival; Event; SKO; kramersplein; |  |  |  |  | N/A | 187 | 7.13 | - | N | - | - | - | - | 7% | 62% | 0% | 38% | - | N/A | 10.15 | 30.27 | 2.66 | 10.47 | 26.36 | 2.96 | 1.44 | 7.13 | 5.5 | 1.83 | 7.27 | 5.17 | 44.35 | 14.54 | -2.18 | 89.09 | 25.06 | -2
C2022-02 | Student kick-off Sint-Pietersplein | Boris Borysiewicz, Ellen Van Moere, Joallen Ghysbrecht, Lucas Baeteman & Mathias Brabants | Event management | Festival; Event; SKO; Student kick-off; |  |  |  |  | N/A | 159 | 3.78 | - | N | - | - | - | - | 8% | 68% | 0% | 35% | - | N/A | 6.92 | 19.42 | 3.56 | 11.78 | 22.06 | 1.99 | 1.97 | 7.53 | 4.79 | 2.03 | 6.87 | 4.6 | 44.42 | 14.08 | -2.06 | 88.52 | 25.39 | -1.88
C2023-01 | House renovation | Stef Pauwels & Emile Van de Walle | Construction (residential building) | Renovation of a house | G |  | G | G | G | 29 | 271 | 756647 | Y | 1 | - | - | - | 46% | 41% | 51% | 30% | - | N/A | 15.62 | 21.81 | 3.07 | 23.07 | 17.55 | 2.66 | 3.48 | 16.46 | 5.37 | 6.03 | 17.78 | 5.3 | 6.07 | 17.98 | 5.29 | 5.41 | 17.18 | 5.25 | 27.59 | 45.49 | 1.06 | 100 | 0 |  | 100 | 0 | [10 empty] | 17642.9 | 14684.83 |  | 7621.65 | 49032.29 | 50 | 19.2 | 29.18 | 65 | 2.73 | 3.43 | 1 | 0.9 | 0.33 | 1 | 0.9 | 0.33 | 1 | 0.9 | 0.33 | 1 | 203 | 756647
C2023-02 | Security | Stef Pauwels & Emile Van de Walle | IT | Security of a building | G |  |  | G | N/A | 66 | 189 | 607575 | Y | 3 | - | - | - | 33% | 54% | 5% | 15% | - | N/A | 4 | 18.89 | 5.1 | 13 | 13.92 | 1.6 | 0 | 1.32 | 5.1 | 9 | 9.36 | 2 | 10 | 11.89 | 2.1 | 9 | 18.85 | 4.3 | 8 | 11.25 | 3.6 | 11 | 14.54 | 2.5 | 11 | 23.05 | 3.4
C2023-03 | MetaBOF | Sven Cousaert, Jeroen De Cocker & others | IT | Data processing software |  |  |  | G | N/A | 109 | 230 | - | Y | 43 | - | - | - | 15% | 39% | 0% | 62% | - | N/A | 13 | 29 | 1.93 | 30 | 31.08 | 1.08 | 4 | 9.64 | 2.84 | 5 | 8.99 | 2.78 | 10 | 16.21 | 1.74 | 14 | 30.15 | 2.45 | 0 | 0 | - | 100 | 0 |  | 100 | 0
C2023-04 | Six-story apartment building | Stef Pauwels & Emile Van de Walle | Construction (residential building) | Six-story apartment building | G |  | G | G | G | 30 | 235 | 1619500 | Y | 2 | - | - | - | 55% | 56% | 19% | 34% | - | N/A | 53 | 46.61 | -0.1 | 66 | 39.97 | -0.58 | 12 | 13.44 | 1.15 | 13 | 12.92 | 1.43 | 13 | 12.73 | 1.46 | 8 | 8.47 | 1.7 | 3 | 18.26 | 5.48 | 100 | 0 |  | 100 | 0 | [13 empty] | -142500 | 378302.12 |  | -12.6 | 22.79 | -51 | 1 | 0 | 1 | 0.91 | 0.32 | 1 | 0.91 | 0.14 | 0.82 | 0.99 | 0.02 | 1 | 300 | 1619500
C2023-05 | IT data migration | Stef Pauwels & Emile Van de Walle | IT | Data transfer; Information system |  |  |  | G |  | 76 | 143 | 112000 | N | - | - | - | - | 83% | 86% | 13% | 28% | - | N/A | 85.75 | 33.99 | -2.07 | 89 | 28.82 | -2.52 | 8.3 | 9.49 | 3.72 | 8.89 | 9.54 | 3.47 | 8.87 | 9.49 | 3.54 | 6.32 | 6.83 | 2.61 | 6.52 | 11.34 | 4.8 | 6.22 | 11.18 | 4.83 | 6.49 | 8.4 | 3.22 | [9 empty] | -51000 | 35776.33 | -105800 | -22769.1 | 24088.65 |  | -62.5 | 43.87 | -125 | 0.5 | 0.16 | 0.51 | 0.66 | 0.3 | 1 | 0.57 | 0.22 | 0.53 | 0.98 | 0.04 | 1 | 299 | 217800
C2023-06 | Steel industry | Stef Pauwels & Emile Van de Walle | Engineering | Cleaning boiler; Industry project |  |  |  | G |  | 844 | 10.88 | 94825504 | N | - | - | - | - | 10% | 54% | 0% | 77% | - | N/A | 0.36 | 2.29 | 8.79 | 4.71 | 11.07 | 4 | 0.37 | 4.13 | 13.5 | 4.62 | 6.39 | 1.63 | 27.38 | 20.86 | 0.07 | 56.58 | 40.1 | 0.05 | 2.47 | 15.52 | 6.14 | 100 | 0 | 0 | 100 | 0 | 0 | [9 empty] | 4297440.06 | 7479481.78 | -684208 | -149675605 | 14453864.23 |  | 2.69 | 1.72 | 3.38 | 1.26 | 0.42 | 0.99 | 0.75 | 0.27 | 0.01 | 0.59 | 0.42 | 0.76 | 0.75 | 0.42 | 0.01 | 10.24 | 95509712
C2023-07 | Building Nevele | Stef Pauwels & Emile Van de Walle | Construction (residential building) | Building |  |  |  | G | G | 42 | 481 | €743 676 | N | - | - | 1.2% | 0% | 47% | 48% | 46% | 23% | - | N/A | 0.49 | 0.44 | 0.14 | 0.34 | 0.37 | 0.6 | 0.12 | 0.12 | 1.05 | 0.13 | 0.11 | 1.34 | 0.12 | 0.1 | 1.45 | 0.08 | 0.07 | 1.74 | 0 | 0 |  | 100 | 0 | [20 empty] | - | 0 | 1 | - | 1 | 1 | - | 1 | 1 | - | 1 | 1 | - | 1 | 348 | €743 676
C2023-08 | Family Home | Stef Pauwels & Emile Van de Walle | Construction (residential building) | Building; family home |  |  |  | G | G | 49 | 382 | €438 622 | N | - | - | 10.47% | 8.85% | 53% | 59% | 6% | 17% | - | N/A | 54.17 | 50.15 | -17.27 | 51.72 | 45.71 | 7.85 | 6.1 | 11.24 | 222.46 | 11.87 | 13.65 | 180.02 | 13.09 | 14.2 | 160.17 | 13.28 | 15.27 | 414.74 | 0 | 0 |  | 1 | 0 | [13 empty] | 3500 | 7000 |  | -5687.5 | 10718.7 | -1000 | -13.25 | 15.44 | -29 | 1.03 | 0.05 | 1 | 0.97 | 0.06 | 0.99 | 0.97 | 0.04 | 0.93 | 1 | 0 | 1 | 302 | € 477 438
C2023-09 | Wine Storage Expansion | Stef Pauwels & Emile Van de Walle | Construction (industrial) | Building; wine storage |  |  |  | G | G | 28 | 80 | € 458 688,44 | N | - | - | 50% | 1.2% | 61% | 69% | 0% | 61% | - | N/A | 36 | 48 | 0.61 | 27 | 37 | 1.32 | 11 | 18 | 1.59 | 18 | 17 | 1.57 | 20 | 18 | 1.43 | 17 | 21 | 3.1 | 0 | 0 |  | 1 | 0 | [13 empty] | 931.78 | 12878.33 | -5498.56 | 729.73 | 1631 |  | -0.39 | 0.9 | 0 | 1.02 | 0.06 | 0.99 | 1 | 0 | 1 | 0.99 | 0.02 | 1 | 0.99 | 0.02 | 1 | 120 | € 464 186,97
C2023-10 | UK Roap map | Matthias Danneel | Construction (Civil) | Roap map |  |  |  | G | N/A | 19 | 234 | - | N | - | - | - | - | 55% | 40% | 45% | 4% | - | N/A | 0.6 | 0.4 | -0.54 | 0.83 | 0.24 | -1.42 | 0.25 | 0.22 | 0.81 | 0.14 | 0.16 | 1.79 | 0.14 | 0.16 | 1.91 | 0.09 | 0.11 | 2.07
C2023-11 | Rail-net communication point 1 | Stef Pauwels & Emile Van de Walle | Construction (Civil) | Rail-net; Train; Communication; | [5 empty] | 279 | 401 | 8974809.3 | N | - | - | 80.21% | 10.66% | 6% | 40% | 0% | 44% | - | N/A | 0.79 | 3.95 | 6.01 | 12.6 | 15.24 | 2 | 0.67 | 5.47 | 11.17 | 2.65 | 4.57 | 9.41 | 8.77 | 16.05 | 2.17 | 14.57 | 32.15 | 2.27 | 16.08 | 36.8 | 1.86 | 100 | 0 |  | 100 | 0 | [10 empty] | 1854348.15 | 4765213.13 | 8974811 | -1815810.63 | 2133343.88 | 0 | -271.25 | 145.25 | -212 | 0.68 | 0.45 | 0 | 0.63 | 0.47 | 1 | 0.42 | 0.35 | 0.78 | 0.95 | 0.1 | 1 | 722.65 | 9931812
C2023-12 | Railroad construction | Stef Pauwels & Emile Van de Walle | Construction (Civil) | Railroad; Train; hardware; software; | [5 empty] | 73 | 383 | 7612805.15 | N | - | - | 5.22% | -37.06% | 12% | 40% | 1% | 49% | - | N/A | 6.18 | 10.88 | 3.35 | 31.45 | 22.21 | 1.04 | 3.23 | 7.63 | 3.73 | 3.91 | 7.96 | 6.07 | 3.91 | 7.9 | 5.6 | 3.57 | 5.68 | 5.39 | 5.56 | 23.07 | 3.96 | 100 | 0 |  | 100 | 0 | [10 empty] | 636912.13 | 1065504.88 | 329559 | -2311014.19 | 1138538.61 | -2121499.5 | -120.25 | 79.63 | -108 | 1.06 | 0.89 | 1.07 | 0.38 | 0.37 | 0.71 | 0.35 | 0.37 | 0.71 | 0.74 | 0.21 | 0.71 | 403 | 4791783
C2023-13 | Rail-net communication point 2 | Stef Pauwels &Emile Van de Walle | Construction (Civil) | Rail-net; Train; Communication; | [5 empty] | 232 | 533 | 1481000 | N | - | - | 21.9% | -46.1% | 18% | 64% | 0% | 70% | - | N/A | 15.25 | 35.25 | 1.97 | 7.81 | 17.91 | 4.04 | 1.29 | 6.46 | 9.05 | 3.34 | 6.16 | 8.59 | 5.65 | 11.61 | 3.79 | 8.57 | 21.05 | 3.95 | 4.29 | 20.31 | 4.54 | 100 | 0 |  | 100 | 0 | [31 empty] | 649.71 | 772404.13
C2023-14 | Building a sustainable future | Leonie Malfait, Jolien Plouy, Sarah Vanwildemeersch, Florence Seynaeve & Emma Verplancke | Construction (residential building) | Home; Sustainable; |  |  |  |  | N/A | 34 | 190 | - | N | - | - | - | - | 42% | 57% | 1% | 41% | - | N/A | 47.12 | 50.29 | 0.12 | 8.59 | 19.41 | 3.71 | 6.99 | 16.19 | 3.74 | 8.01 | 15.39 | 3.95 | 7.58 | 15.33 | 4.05 | 7.42 | 10.79 | 4.3
C2024-01 | Signalisation work Peru | Eder Vilca | Construction (Civil) | Signalisation, road, safety | [5 empty] | 66 | 84 | 201.312,14 € | 6 | N/A | N/A | Early | Under budget | 0.57 | 0.52 | 0 | 0.43 | N/A | N/A | 55.2 | 0.5 | -0.2 | 9.2 | 0.2 | 2 | 1.9 | 0.1 | 7.8 | 2.2 | 0.1 | 8 | 38.3 | 0.2 | -0.7 | 77 | 0.4 | -1.2 | 3.8 | 0.1 | 3.9 | 0.12 | 0.1 | -2.2 | 3.92 | 0.3 | -2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 11824.6 | 10952.4 | 26495.9 | -4774.5 | 39902.5 | 40589.4 | -0.1 | 14.2 | 11 | 1.2 | 0.1 | 1.15 | 1 | 0.5 | 1.25 | 1 | 0.6 | 1.18 | 0.7 | 0.3 | 1 | 36,2 | 174816.3
C2024-02 | Gas Pipeline | Rojin & Forough | Construction (Industrial) | Infrastructure |  |  | N/A | G | N/A | 13 | 58 | 37536 | N/A | N/A | N/A | N/A | N/A | 75% | 77% | 0% | 22% | N/A | N/A | 30.8 | 46.2 | 0.9 | 31.3 | 31.7 | 0.9 | 8.7 | 15.4 | 1.9 | 20.4 | 21 | 1 | 27.8 | 21.9 | 0.4 | 28.6 | 32.5 | 1.7 | 30.77 | 46.2 | 1.3 | 31.31 | 31.7 | 0.9 | 8.69 | 15.4 | 1.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C2024-03 | Learning management system implementation | Forough & Rojin | IT | - |  |  | N/A | G | N/A | 153 | 293 | 644405 | N/A | N/A | N/A | N/A | N/A | 35% | 56% | 0% | 57% | N/A | N/A | 26.3 | 43.3 | 1.1 | 30.9 | 40.5 | 1 | 2.2 | 7.2 | 7.7 | 6.7 | 9.9 | 3.4 | 23.3 | 20.6 | 0.5 | 40.8 | 42 | 0.6 | 7.22 | 9.55 | 2.8 | 23.65 | 19.9 | 0.5 | 40.18 | 42.36 | 0.7 | 18.74 | 18.58 | 1.8 | 24 | 19.9 | 1.2 | 22.79 | 42.36 | 2.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C2024-04 | New product development | Rojin & Forough | Engineering | - |  |  |  | G |  | 37 | 84 | 32481 | N/A | N/A | N/A | Late | Over budget | 58% | 57% | 10% | 8% | N/A | N/A | 57.4 | 43.8 | -0.4 | 36.3 | 41.4 | 0.5 | 7.2 | 13.7 | 4.7 | 11.4 | 14.5 | 3.8 | 23.3 | 23.4 | 1.6 | 35.9 | 35.7 | 0.9 | 11.1 | 13.62 | 2.3 | 20.8 | 18.5 | 0.9 | 33.5 | 34.75 | 1.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -149.22 | N/A | -3125 | 273.78 | N/A | 0 | 1 | N/A | 147.6 | 0.97 | N/A | 0.91 | 1.07 | N/A | 1 | 1.45 | N/A | 0.38 | 0.93 | N/A | 0.87 | 239 | 35606
C2024-05 | Product marketing | Forough & Rojin | Construction (Industrial) | - |  |  | N/A | G | N/A | 111 | 224 | 228090 | N/A | N/A | N/A | N/A | N/A | 71% | 79% | 11% | 3% | N/A | N/A | 9 | 28.6 | 2.9 | 16.6 | 27 | 2.3 | 0.4 | 1.8 | 5.1 | 9.9 | 8.7 | 1.1 | 17.1 | 14.4 | 1.3 | 26.6 | 29.3 | 1.7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | SUMMARY STATISTICS |  |  |  | nrAct | PD |  | nrProjects | 203
|  | Construction (civil) | Construction (Civil) | 40 | Construction works related to infrastructure (e.g. bridges) |  |  |  | Average | 95.6601 | 271.8167 | 40986522.6202 |  | 7.589 | 1.5 | 12.7% | 2.6% | 41.16% | 56.51% | 14.09% | 35.99% | 75.27%
|  | Construction (commercial) | Construction (commercial building) | 18 | Construction projects for the private sector (e.g. offices, stores) |  |  |  | StDev | 214.8445 | 303.1201 | 391594325.4891 |  | 7.414 | 0.70711 | 22.07% | 25.04% | 23.31% | 16.62% | 21.22% | 23.34% | 16.34%
|  | Construction (residential) | Construction (residential building) | 54 | Construction projects for housing (e.g. apartments) |  |  |  | Minimum | 7 | 2 | 1210 |  | 1 | 1 | -33.16% | -57.82% | 1% | 17% | -5% | 0% | 5%
|  | Construction (institutional) | Construction (institutional building) | 8 | Construction projects related to healthcare, education, recreation or public works |  |  |  | Maximum | 1796 | 2804 | 4999958016 |  | 43 | 2 | 100% | 143.6% | 95% | 100% | 100% | 100% | 95%
|  | Construction (industrial) | Construction (Industrial) | 15 | Construction of specialised facilities (e.g. factories, warehouses) |  |  |  | CountEmpty | 100.5% | 100.5% | 85.71% |  | 38.92% | 3.941% | 61.08% | 59.61% | 100.5% | 100.5% | 100.5% | 100.5% | 78.33%
|  | Engineering | Engineering | 14 | Design and construction of engines, machinery or processes |  |  |  | nrPos | [6 empty] | 77 | 71
|  | Mobility | Mobility | 6 | Development of vehicle sharing platforms |  |  |  | nrNeq | [6 empty] | 12 | 38
|  | Event management | Event management | 15 | Creation and development of events |  |  |  | nrZero | [6 empty] | 29 | 6
|  | IT | IT | 31 | Development of software |  |  |  | Average Lateness or Over Budget | [6 empty] | 21.47% | 13.72%
|  | Education | Education | 2 | Program development for educational purposes |  |  |  | Average Earliness or Under Budget | [6 empty] | -12.88% | -17.76%
|  |  |  | 203 | [5 empty] | # projects | # act (min) | # act (max) |  | # Res (min) | # Res (max)
[9 empty] | Construction (Civil) | 40 | 12 | 1796 |  | 1 | 20
[9 empty] | Construction (commercial building) | 18 | 7 | 373 |  | 5 | 12
[9 empty] | Construction (residential building) | 54 | 10 | 184 |  | 1 | 10
[9 empty] | Construction (institutional building) | 8 | 24 | 276 |  | 0 | 0
[9 empty] | Construction (Industrial) | 15 | 13 | 437 |  | 6 | 27
[9 empty] | Construction | 135 | 7 | 1796 |  | 0 | 27
[9 empty] | Engineering | 14 | 7 | 844 |  | 2 | 4
[9 empty] | Mobility | 6 | 19 | 41 |  | 2 | 8
[9 empty] | Event management | 15 | 19 | 187 |  | 1 | 15
[9 empty] | IT | 31 | 11 | 279 |  | 1 | 43
[9 empty] | Education | 2 | 112 | 134 |  | 1 | 3
203
Note on K3: # activities like in Patterson files of DB overview paper; with milestones but without start and end dummies
Note on M28: should actually be 1,538,854 €, but leave it because already used in multiple papers
Note on G34: Scenario 9
Note on D39: should in fact be Construction (industrial), but left it Production (now renamed to Engineering) because of DB paper
Note on B55: was initially deleted because no precedence relations, but added again because used in exp sm paper
Note on F55: no activities (month names instead) or precedence relations
Note on K92: prec rels for this and next 2 projs added myself
Note on C105: William Casaert & Jef Descheemaecker
Note on J110: alle activiteiten van de Residential House Finishing Works projecten zijn exact op tijd gedaan, maar dit is waarheidsgetrouw, wegens de grote buffers die werden toegepast voor elke activiteit (cfr. Parkinson & hidden earliness van Trietsch)