## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Project | 1 |  |  | 2016-08-23 13:00 | 2017-03-01 17:00 | 136d 4h |  |  | 0 |  |  | 0 | 190.1667
1 | Planning Phase | 1.1 |  |  | 2016-08-23 13:00 | 2016-10-12 12:00 | 36d |  |  | 0 |  |  | 0 | 49.9583
2 | Concept automatisation techniques | 1.1.1 |  | FS3 | 2016-08-23 13:00 | 2016-09-05 12:00 | 9d |  | 0 | 0 | 0 | 0 | 0 | 12.9583
3 | Research automatisation techniques | 1.1.2 | 2FS | FS4 | 2016-09-05 13:00 | 2016-09-26 12:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 20.9583
4 | Choices of different techniques | 1.1.3 | 3FS | FS5 | 2016-09-26 13:00 | 2016-10-06 12:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 9.9583
5 | Meeting with EMASC and ENTREC | 1.1.4 | 4FS | FS7;FS8 | 2016-10-06 13:00 | 2016-10-12 12:00 | 4d |  | 0 | 0 | 0 | 0 | 0 | 5.9583
6 | Design Phase | 1.2 |  |  | 2016-10-12 13:00 | 2016-11-22 17:00 | 29d 4h |  |  | 0 |  |  | 0 | 41.1667
7 | Testing supply hoppers candy (min. 70/min.) | 1.2.1 | 5FS | FS9 | 2016-10-12 13:00 | 2016-10-12 17:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
8 | Testing supply hoppers PP handles (min. 70/min.) | 1.2.2 | 5FS | FS9 | 2016-10-12 13:00 | 2016-10-12 17:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
9 | Elaboration of concept | 1.2.3 | 7FS;8FS | FS10 | 2016-10-13 08:00 | 2016-11-02 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 20.375
10 | Evaluation concept with Sweetpack | 1.2.4 | 9FS | FS11 | 2016-11-04 08:00 | 2016-11-08 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 4.375
11 | Adjustments of concept | 1.2.5 | 10FS | FS12 | 2016-11-09 08:00 | 2016-11-16 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0 | 7.375
12 | Definitive concept | 1.2.6 | 11FS | FS14;FS21;FS26;FS31 | 2016-11-18 08:00 | 2016-11-22 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 4.375
13 | Assembly Phase | 1.3 |  |  | 2016-11-23 08:00 | 2017-01-31 17:00 | 50d |  |  | 0 |  |  | 0 | 69.375
14 | Adaption robots according to concept | 1.3.1 | 12FS | FS16;FS17 | 2016-12-15 08:00 | 2016-12-20 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0 | 5.375
15 | Software development for robots | 1.3.2 |  |  | 2017-01-25 13:00 | 2017-01-27 17:00 | 2d 4h |  |  | 0 |  |  | 0 | 2.1667
16 | Handle picker robot | 1.3.2.1 | 14FS | FS18 | 2017-01-25 13:00 | 2017-01-25 17:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
17 | Candy picker robot | 1.3.2.2 | 14FS | FS18 | 2017-01-25 13:00 | 2017-01-25 17:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
18 | Shifting robot | 1.3.2.3 | 17FS;16FS | FS19 | 2017-01-26 08:00 | 2017-01-26 12:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
19 | Feeding Buffer 3.2 | 1.3.2.4 | 18FS |  | 2017-01-26 13:00 | 2017-01-27 17:00 | 1d 4h |  | 0 | 0 | 0 | 0 | 0 | 1.1667
20 | Production flowpacker | 1.3.3 |  |  | 2016-12-02 08:00 | 2017-01-30 12:00 | 41d 4h |  |  | 0 |  |  | 0 | 59.1667
21 | Customization standard flowpacker | 1.3.3.1 | 12FS | FS22 | 2016-12-02 08:00 | 2017-01-04 17:00 | 24d |  | 0 | 0 | 0 | 0 | 0 | 33.375
22 | Testing | 1.3.3.2 | 21FS | FS23 | 2017-01-05 08:00 | 2017-01-11 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 6.375
23 | Delivery flowpacker at Sweetpack | 1.3.3.3 | 22FS | FS24 | 2017-01-12 08:00 | 2017-01-12 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
24 | Feeding Buffer 3.3 | 1.3.3.4 | 23FS |  | 2017-01-13 08:00 | 2017-01-30 12:00 | 11d 4h |  | 0 | 0 | 0 | 0 | 0 | 17.1667
25 | Development turning station | 1.3.4 |  |  | 2016-11-23 08:00 | 2017-01-27 12:00 | 47d 4h |  |  | 0 |  |  | 0 | 65.1667
26 | Designing | 1.3.4.1 | 12FS | FS27;FS35 | 2016-11-23 08:00 | 2016-12-14 17:00 | 16d |  | 0 | 0 | 0 | 0 | 0 | 21.375
27 | Production of elements | 1.3.4.2 | 26FS | FS28 | 2016-12-22 08:00 | 2016-12-28 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 6.375
28 | Assembly of elements | 1.3.4.3 | 27FS | FS29 | 2016-12-29 08:00 | 2017-01-02 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 4.375
29 | Software programming | 1.3.4.4 | 28FS |  | 2017-01-26 13:00 | 2017-01-27 12:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.95833
30 | Development dispensing machine | 1.3.5 |  |  | 2016-12-21 08:00 | 2016-12-28 17:00 | 6d |  |  | 0 |  |  | 0 | 7.375
31 | Designing | 1.3.5.1 | 12FS | FS32 | 2016-12-21 08:00 | 2016-12-22 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375
32 | Production of elements | 1.3.5.2 | 31FS | FS33 | 2016-12-26 08:00 | 2016-12-27 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375
33 | Assembly of elements | 1.3.5.3 | 32FS |  | 2016-12-28 08:00 | 2016-12-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
34 | Development frame and conductors | 1.3.6 |  |  | 2016-12-23 08:00 | 2017-01-20 17:00 | 21d |  |  | 0 |  |  | 0 | 28.375
35 | Designing | 1.3.6.1 | 26FS | FS36 | 2016-12-23 08:00 | 2017-01-02 17:00 | 7d |  | 0 | 0 | 0 | 0 | 0 | 10.375
36 | Production of elements | 1.3.6.2 | 35FS | FS37 | 2017-01-03 08:00 | 2017-01-11 17:00 | 7d |  | 0 | 0 | 0 | 0 | 0 | 8.375
37 | Assembly of elements | 1.3.6.3 | 36FS |  | 2017-01-12 08:00 | 2017-01-20 17:00 | 7d |  | 0 | 0 | 0 | 0 | 0 | 8.375
38 | Erection of new production line | 1.3.7 |  |  | 2017-01-23 08:00 | 2017-01-30 17:00 | 6d |  |  | 0 |  |  | 0 | 7.375
39 | Installation frame and conductors | 1.3.7.1 |  | FS40;FS41;FS43 | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
40 | Feeding Buffer 3.7.1 | 1.3.7.2 | 39FS |  | 2017-01-24 13:00 | 2017-01-30 17:00 | 4d 4h |  | 0 | 0 | 0 | 0 | 0 | 6.1667
41 | Installation turning station | 1.3.7.3 | 39FS | FS42 | 2017-01-27 13:00 | 2017-01-27 17:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
42 | Installation new robots | 1.3.7.4 | 41FS |  | 2017-01-30 08:00 | 2017-01-30 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
43 | Installation dispensing machine | 1.3.7.5 | 39FS | FS44 | 2017-01-24 08:00 | 2017-01-24 12:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
44 | Feeding Buffer 3.7.4 | 1.3.7.6 | 43FS |  | 2017-01-24 13:00 | 2017-01-30 17:00 | 4d 4h |  | 0 | 0 | 0 | 0 | 0 | 6.1667
45 | Dismantling of hoppers from dummy production line | 1.3.8 | 46SF | FS54 | 2017-01-30 08:00 | 2017-01-30 12:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
46 | Delivery hoppers and flowpacker | 1.3.9 |  | SF45;FS47 | 2017-01-30 13:00 | 2017-01-30 17:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
47 | Integration of hoppers and flowpacker in new production line | 1.3.10 | 46FS | FS49 | 2017-01-31 08:00 | 2017-01-31 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
48 | Testing Phase | 1.4 |  |  | 2017-01-31 08:00 | 2017-02-09 17:00 | 8d |  |  | 0 |  |  | 0 | 9.375
49 | Testing of full production line | 1.4.1 | 47FS | FS51;FS52 | 2017-02-01 08:00 | 2017-02-08 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0 | 7.375
50 | Adjusting new production line | 1.4.2 |  |  | 2017-02-09 08:00 | 2017-02-09 17:00 | 1d |  |  | 0 |  |  | 0 | 0.375
51 | Possible adjustments software | 1.4.2.1 | 49FS |  | 2017-02-09 08:00 | 2017-02-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
52 | Possible adjustments production line | 1.4.2.2 | 49FS |  | 2017-02-09 08:00 | 2017-02-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
53 | Restructuring production lines | 1.4.3 |  |  | 2017-01-31 08:00 | 2017-02-09 17:00 | 8d |  |  | 0 |  |  | 0 | 9.375
54 | Disassembly of old dummy production line | 1.4.3.1 | 45FS | FS55 | 2017-01-31 08:00 | 2017-01-31 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
55 | Shutdown of whistle production lines | 1.4.3.2 | 54FS | FS56 | 2017-02-01 08:00 | 2017-02-01 12:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
56 | Reorganization whistle production lines | 1.4.3.3 | 55FS | FS57 | 2017-02-01 13:00 | 2017-02-06 12:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 4.9583
57 | Provisions dummy production line | 1.4.3.4 | 56FS | FS58 | 2017-02-06 13:00 | 2017-02-07 12:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.95833
58 | Feeding Buffer 4.3 | 1.4.3.5 | 57FS |  | 2017-02-07 13:00 | 2017-02-09 17:00 | 2d 4h |  | 0 | 0 | 0 | 0 | 0 | 2.1667
59 | Final Assembly Phase | 1.5 |  |  | 2017-02-10 08:00 | 2017-02-14 12:00 | 2d 4h |  |  | 0 |  |  | 0 | 4.1667
60 | Installation new production line | 1.5.1 |  |  | 2017-02-10 08:00 | 2017-02-13 17:00 | 2d |  |  | 0 |  |  | 0 | 3.375
61 | Construction | 1.5.1.1 |  | FS62 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
62 | Final tests | 1.5.1.2 | 61FS | FS63 | 2017-02-13 08:00 | 2017-02-13 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
63 | Evaluation | 1.5.2 | 62FS | FS64 | 2017-02-14 08:00 | 2017-02-14 12:00 | 4h |  | 0 | 0 | 0 | 0 | 0 | 0.16667
64 | Projectbuffer | 1.6 | 63FS |  | 2017-02-14 13:00 | 2017-03-01 17:00 | 11d 4h |  | 0 | 0 | 0 | 0 | 0 | 15.1667

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Project | 1092h |  |  |  |  | 99 | 100 | 101
1 | Planning Phase | 288h |  |  |  |  | 99 | 100 | 101
2 | Concept automatisation techniques | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Research automatisation techniques | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Choices of different techniques | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Meeting with EMASC and ENTREC | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Design Phase | 236h |  |  |  |  | 99 | 100 | 101
7 | Testing supply hoppers candy (min. 70/min.) | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Testing supply hoppers PP handles (min. 70/min.) | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Elaboration of concept | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Evaluation concept with Sweetpack | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Adjustments of concept | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Definitive concept | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Assembly Phase | 400h |  |  |  |  | 99 | 100 | 101
14 | Adaption robots according to concept | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Software development for robots | 20h |  |  |  |  | 99 | 100 | 101
16 | Handle picker robot | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Candy picker robot | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Shifting robot | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Feeding Buffer 3.2 | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Production flowpacker | 332h |  |  |  |  | 99 | 100 | 101
21 | Customization standard flowpacker | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Testing | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Delivery flowpacker at Sweetpack | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Feeding Buffer 3.3 | 92h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Development turning station | 380h |  |  |  |  | 99 | 100 | 101
26 | Designing | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Production of elements | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Assembly of elements | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Software programming | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Development dispensing machine | 48h |  |  |  |  | 99 | 100 | 101
31 | Designing | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Production of elements | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Assembly of elements | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Development frame and conductors | 168h |  |  |  |  | 99 | 100 | 101
35 | Designing | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Production of elements | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Assembly of elements | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Erection of new production line | 48h |  |  |  |  | 99 | 100 | 101
39 | Installation frame and conductors | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Feeding Buffer 3.7.1 | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Installation turning station | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Installation new robots | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Installation dispensing machine | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Feeding Buffer 3.7.4 | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Dismantling of hoppers from dummy production line | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Delivery hoppers and flowpacker | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Integration of hoppers and flowpacker in new production line | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Testing Phase | 64h |  |  |  |  | 99 | 100 | 101
49 | Testing of full production line | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Adjusting new production line | 8h |  |  |  |  | 99 | 100 | 101
51 | Possible adjustments software | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Possible adjustments production line | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Restructuring production lines | 64h |  |  |  |  | 99 | 100 | 101
54 | Disassembly of old dummy production line | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Shutdown of whistle production lines | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Reorganization whistle production lines | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Provisions dummy production line | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Feeding Buffer 4.3 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Final Assembly Phase | 20h |  |  |  |  | 99 | 100 | 101
60 | Installation new production line | 16h |  |  |  |  | 99 | 100 | 101
61 | Construction | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Final tests | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Evaluation | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Projectbuffer | 92h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))