## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Project | 1 |  |  | 2017-07-03 08:00 | 2018-07-25 17:00 | 278d |  |  | 0 |  |  | 0 | 387.375
1 | Research for possible docking stations | 1.1 |  |  | 2017-07-03 08:00 | 2017-12-22 17:00 | 125d |  |  | 0 |  |  | 0 | 172.375
2 | Analysis of electrical cars around Gent and Belgium | 1.1.1 |  | FS3;FS4;FS5;FS6 | 2017-07-03 08:00 | 2017-07-25 17:00 | 17d |  | 0 | 0 | 0 | 0 | 0 | 22.375
3 | Analysis of properties of electrical cars | 1.1.2 | 2FS | FS7 | 2017-07-27 08:00 | 2017-08-01 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0 | 5.375
4 | Analysis of locations and quantity for the ‘charging blocks’ | 1.1.3 | 2FS | FS7 | 2017-07-26 08:00 | 2017-08-31 17:00 | 27d |  | 0 | 0 | 0 | 0 | 0 | 36.375
5 | Analysis of the kind of ‘charging blocks’ | 1.1.4 | 2FS | FS7 | 2017-07-26 08:00 | 2017-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
6 | Research for amount of staff needed | 1.1.5 | 2FS | FS7 | 2017-07-26 08:00 | 2017-08-01 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 6.375
7 | Feasibility study | 1.1.6 | 3FS;6FS;5FS;4FS | FS9;FS14;FS16 | 2017-12-14 08:00 | 2017-12-22 17:00 | 7d |  | 0 | 0 | 0 | 0 | 0 | 8.375
8 | Meeting | 1.2 |  |  | 2017-12-25 08:00 | 2018-04-24 17:00 | 87d |  |  | 0 |  |  | 0 | 120.375
9 | Asking town for permission | 1.2.1 | 7FS | FS10;FS11;FS12;FS13 | 2017-12-25 08:00 | 2018-02-02 17:00 | 30d |  | 0 | 0 | 0 | 0 | 0 | 39.375
10 | Asking for blue prints power network town | 1.2.2 | 9FS | FS22 | 2018-02-05 08:00 | 2018-03-02 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 25.375
11 | Meeting with Eaindis for possbility of placing ‘charging blocks’ | 1.2.3 | 9FS | FS23 | 2018-03-12 08:00 | 2018-04-24 17:00 | 32d |  | 0 | 0 | 0 | 0 | 0 | 43.375
12 | Meeting with possible suppliers of the ‘charging blocks’ (Allego) | 1.2.4 | 9FS | FS23 | 2018-02-05 08:00 | 2018-03-21 17:00 | 33d |  | 0 | 0 | 0 | 0 | 0 | 44.375
13 | Meeting with possible contractors for placement ‘charging blocks’ | 1.2.5 | 9FS | FS23 | 2018-03-12 08:00 | 2018-03-30 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 18.375
14 | Hiring maintenance for possible defects of ‘charging blocks’ | 1.2.6 | 7FS | FS23 | 2017-12-25 08:00 | 2018-02-16 17:00 | 40d |  | 0 | 0 | 0 | 0 | 0 | 53.375
15 | App development | 1.3 |  |  | 2017-12-25 08:00 | 2018-04-10 17:00 | 77d |  |  | 0 |  |  | 0 | 106.375
16 | ICT contractor search | 1.3.1 | 7FS | FS17;FS18 | 2017-12-25 08:00 | 2018-01-12 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 18.375
17 | Developing app and website | 1.3.2 | 16FS | FS19 | 2018-01-15 08:00 | 2018-03-23 17:00 | 50d |  | 0 | 0 | 0 | 0 | 0 | 67.375
18 | Developing payment system | 1.3.3 | 16FS | FS20 | 2018-01-15 08:00 | 2018-03-09 17:00 | 40d |  | 0 | 0 | 0 | 0 | 0 | 53.375
19 | Testing & approving payment system | 1.3.4 | 17FS | FS23 | 2018-03-26 08:00 | 2018-04-10 17:00 | 12d |  | 0 | 0 | 0 | 0 | 0 | 15.375
20 | Testing & approving payment system | 1.3.5 | 18FS | FS23 | 2018-03-12 08:00 | 2018-03-23 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
21 | Construction | 1.4 |  |  | 2018-03-05 08:00 | 2018-07-19 17:00 | 99d |  |  | 0 |  |  | 0 | 136.375
22 | Drilling the holes where the charging blocks will be put by Eandis | 1.4.1 | 10FS | FS23 | 2018-03-05 08:00 | 2018-03-16 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
23 | Delivery and placing of the ‘charging blocks’by Allego | 1.4.2 | 14FS;22FS;13FS;19FS;20FS;12FS;11FS | FS24 | 2018-05-24 08:00 | 2018-06-06 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
24 | Installation of the ‘charging blocks’by Eandis | 1.4.3 | 23FS | FS25;FS26 | 2018-06-07 08:00 | 2018-06-18 17:00 | 8d |  | 0 | 0 | 0 | 0 | 0 | 11.375
25 | Installation of visibility marks | 1.4.4 | 24FS | FS27 | 2018-06-19 08:00 | 2018-06-22 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0 | 3.375
26 | Testing of the ‘charging blocks’ | 1.4.5 | 24FS | FS27 | 2018-06-19 08:00 | 2018-07-19 17:00 | 23d |  | 0 | 0 | 0 | 0 | 0 | 30.375
27 | Payment of delivery and construction firms | 1.4.6 | 26FS;25FS | FS29 | 2018-07-19 17:00 | 2018-07-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
28 | Marketing | 1.5 |  |  | 2018-07-20 08:00 | 2018-07-25 17:00 | 4d |  |  | 0 |  |  | 0 | 5.375
29 | Advertising for electrical cars and ‘charging blocks’ | 1.5.1 | 27FS | FS30 | 2018-07-20 08:00 | 2018-07-23 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 3.375
30 | Publicity for green city Gent | 1.5.2 | 29FS |  | 2018-07-24 08:00 | 2018-07-25 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Project | 2224h |  |  |  |  | 99 | 100 | 101
1 | Research for possible docking stations | 1000h |  |  |  |  | 99 | 100 | 101
2 | Analysis of electrical cars around Gent and Belgium | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Analysis of properties of electrical cars | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Analysis of locations and quantity for the ‘charging blocks’ | 216h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Analysis of the kind of ‘charging blocks’ | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Research for amount of staff needed | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Feasibility study | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Meeting | 696h |  |  |  |  | 99 | 100 | 101
9 | Asking town for permission | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Asking for blue prints power network town | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Meeting with Eaindis for possbility of placing ‘charging blocks’ | 256h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Meeting with possible suppliers of the ‘charging blocks’ (Allego) | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Meeting with possible contractors for placement ‘charging blocks’ | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Hiring maintenance for possible defects of ‘charging blocks’ | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | App development | 616h |  |  |  |  | 99 | 100 | 101
16 | ICT contractor search | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Developing app and website | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Developing payment system | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Testing & approving payment system | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Testing & approving payment system | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Construction | 792h |  |  |  |  | 99 | 100 | 101
22 | Drilling the holes where the charging blocks will be put by Eandis | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Delivery and placing of the ‘charging blocks’by Allego | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Installation of the ‘charging blocks’by Eandis | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Installation of visibility marks | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Testing of the ‘charging blocks’ | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Payment of delivery and construction firms | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Marketing | 32h |  |  |  |  | 99 | 100 | 101
29 | Advertising for electrical cars and ‘charging blocks’ | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Publicity for green city Gent | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))

## SV(t)
S