## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Railway Bridge (4) | 1 |  |  | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 | 339.375
1 | Voorbereidende studie | 1.1 |  |  | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 41.375
2 | Werfinrichting | 1.2 |  |  | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 6.375
3 | Afbraak brug | 1.3 |  | FS4 | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 1.375
4 | Uitgraving bouwputten | 1.4 | 3FS | FS5 | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 11.375
5 | Uitvoering paalfunderingen | 1.5 | 4FS | FS6 | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 25.375
6 | Uitvoeren van funderingsbalken | 1.6 | 5FS | FS7 | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 25.375
7 | Montage boogkist | 1.7 | 6FS | FS8 | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 1.375
8 | Plaatsen boogkist | 1.8 | 7FS |  | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 1.375
27 | 1e fase brug | 1.9 |  |  | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 | 32.375
9 | Opkuisen bekisting + plaatsen randkist | 1.9.1 |  | FS10 | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2.375
10 | Wapenen | 1.9.2 | 9FS | FS11 | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 7.375
11 | Betonneren | 1.9.3 | 10FS | FS12 | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 0.375
12 | Uitharden | 1.9.4 | 11FS | FS13 | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 11.375
28 | 2e fase brug | 1.10 |  |  | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 | 25.375
13 | Zakken bekisting + verschuiven en opkuisen | 1.10.1 | 12FS | FS14 | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2.375
14 | Wapenen | 1.10.2 | 13FS | FS15 | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 | 7.375
15 | Betonneren | 1.10.3 | 14FS | FS16 | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 0.375
16 | Uitharden | 1.10.4 | 15FS | FS17 | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 11.375
29 | 3e fase brug | 1.11 |  |  | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 | 25.375
17 | Zakken bekisting + verschuiven en opkuisen | 1.11.1 | 16FS | FS18 | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 | 1.375
18 | Plaatsen randbekisting | 1.11.2 | 17FS | FS19 | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 | 1.375
19 | Wapenen | 1.11.3 | 18FS | FS20 | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 | 6.375
20 | Betonneren | 1.11.4 | 19FS | FS21;FS22 | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 0.375
21 | Uitharden | 1.11.5 | 20FS |  | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 4.375
22 | Wapenen en betonneren voeg | 1.12 | 20FS | FS23 | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 | 6.375
23 | Plaatsen dakdichting | 1.13 | 22FS | FS24 | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 | 6.375
24 | Aanvullen boogbrug | 1.14 | 23FS | FS25 | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 | 6.375
25 | Wegeniswerken | 1.15 | 24FS | FS26 | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 | 27.375
26 | Afwerkingen | 1.16 | 25FS |  | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 | 53.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Railway Bridge (4) | 1984h |  |  |  |  | 99 | 100 | 101
1 | Voorbereidende studie | 240h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
2 | Werfinrichting | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
3 | Afbraak brug | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
4 | Uitgraving bouwputten | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
5 | Uitvoering paalfunderingen | 160h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
6 | Uitvoeren van funderingsbalken | 160h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
7 | Montage boogkist | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
8 | Plaatsen boogkist | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
27 | 1e fase brug | 200h |  |  |  |  | 99 | 100 | 101
9 | Opkuisen bekisting + plaatsen randkist | 24h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
10 | Wapenen | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
12 | Uitharden | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | 2e fase brug | 160h |  |  |  |  | 99 | 100 | 101
13 | Zakken bekisting + verschuiven en opkuisen | 24h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
14 | Wapenen | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
16 | Uitharden | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | 3e fase brug | 160h |  |  |  |  | 99 | 100 | 101
17 | Zakken bekisting + verschuiven en opkuisen | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
18 | Plaatsen randbekisting | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Wapenen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
21 | Uitharden | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Wapenen en betonneren voeg | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
23 | Plaatsen dakdichting | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
24 | Aanvullen boogbrug | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
25 | Wegeniswerken | 160h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
26 | Afwerkingen | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-02-03 07:00 |  | TP Name | T1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 6d | [5 empty] | 12275.3398 |  | 1.355% |  | 12275.3399 | 12835.3398
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 5d | 12275.3398 | 14000 | 25d | 0 | 0 | 12275.3398 | 14000 | 16.67% | Started | 12275.3399 | 12835.3398 | 100 | 16.6667 | 16.6667 | 100 | 46.7181 | 16.6667
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 |  | 0 | 0 | 25224.9395 | 5d | 0 | 0 | 0 | 25224.9395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 |  | 0 | 0 | 69058.8984 | 2d | 0 | 0 | 0 | 69058.8984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 |  | 0 | 0 | 8527.0901 | 10d | 0 | 0 | 0 | 8527.0901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 |  | 0 | 0 | 237488.3125 | 20d | 0 | 0 | 0 | 237488.3125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 |  | 0 | 0 | 95953.4062 | 20d | 0 | 0 | 0 | 95953.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 |  | 0 | 0 | 3650.99 | 2d | 0 | 0 | 0 | 3650.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 |  | 0 | 0 | 7971.3198 | 2d | 0 | 0 | 0 | 7971.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 |  | 0 | 0 | 6060.8401 | 3d | 0 | 0 | 0 | 6060.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 |  | 0 | 0 | 31167.6309 | 6d | 0 | 0 | 0 | 31167.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 |  | 0 | 0 | 19599.6406 | 1d | 0 | 0 | 0 | 19599.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 |  | 0 | 0 | 5921.4399 | 3d | 0 | 0 | 0 | 5921.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 |  | 0 | 0 | 20906.29 | 6d | 0 | 0 | 0 | 20906.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 |  | 0 | 0 | 4035.8 | 2d | 0 | 0 | 0 | 4035.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 |  | 0 | 0 | 2921.98 | 2d | 0 | 0 | 0 | 2921.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 |  | 0 | 0 | 18412.8799 | 5d | 0 | 0 | 0 | 18412.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 |  | 0 | 0 | 23264.21 | 5d | 0 | 0 | 0 | 23264.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 |  | 0 | 0 | 41119.3984 | 5d | 0 | 0 | 0 | 41119.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 |  | 0 | 0 | 48839.8906 | 20d | 0 | 0 | 0 | 48839.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-03-03 07:00 |  | TP Name | T2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 26d | [5 empty] | 44220.2793 |  | 4.879% |  | 44220.279 | 44780.2793
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 25d | 23475.3398 | 2800 | 5d | 0 | 0 | 23475.3398 | 2800 | 83.33% | Started | 23475.3395 | 24035.3398 | 100 | 83.3333 | 83.3333 | 100 | 89.3436 | 83.3333
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 1d | 20744.9395 | 4480 | 4d | 0 | 0 | 20744.9395 | 4480 | 20% | Started | 20744.9395 | 20744.9395 | 100 | 20 | 20 | 100 | 82.2398 | 20
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 |  | 0 | 0 | 69058.8984 | 2d | 0 | 0 | 0 | 69058.8984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 |  | 0 | 0 | 8527.0901 | 10d | 0 | 0 | 0 | 8527.0901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 |  | 0 | 0 | 237488.3125 | 20d | 0 | 0 | 0 | 237488.3125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 |  | 0 | 0 | 95953.4062 | 20d | 0 | 0 | 0 | 95953.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 |  | 0 | 0 | 3650.99 | 2d | 0 | 0 | 0 | 3650.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 |  | 0 | 0 | 7971.3198 | 2d | 0 | 0 | 0 | 7971.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 |  | 0 | 0 | 6060.8401 | 3d | 0 | 0 | 0 | 6060.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 |  | 0 | 0 | 31167.6309 | 6d | 0 | 0 | 0 | 31167.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 |  | 0 | 0 | 19599.6406 | 1d | 0 | 0 | 0 | 19599.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 |  | 0 | 0 | 5921.4399 | 3d | 0 | 0 | 0 | 5921.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 |  | 0 | 0 | 20906.29 | 6d | 0 | 0 | 0 | 20906.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 |  | 0 | 0 | 4035.8 | 2d | 0 | 0 | 0 | 4035.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 |  | 0 | 0 | 2921.98 | 2d | 0 | 0 | 0 | 2921.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 |  | 0 | 0 | 18412.8799 | 5d | 0 | 0 | 0 | 18412.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 |  | 0 | 0 | 23264.21 | 5d | 0 | 0 | 0 | 23264.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 |  | 0 | 0 | 41119.3984 | 5d | 0 | 0 | 0 | 41119.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 |  | 0 | 0 | 48839.8906 | 20d | 0 | 0 | 0 | 48839.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-04-07 07:00 |  | TP Name | T3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 53d | [5 empty] | 350574.5803 |  | 38.68% |  | 350574.5803 | 350574.5803
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 10d | 221488.3125 | 16000 | 10d | 0 | 0 | 221488.3125 | 16000 | 50% | Started | 221488.3125 | 221488.3125 | 100 | 50 | 50 | 100 | 93.2628 | 50
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 |  | 0 | 0 | 95953.4062 | 20d | 0 | 0 | 0 | 95953.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 |  | 0 | 0 | 3650.99 | 2d | 0 | 0 | 0 | 3650.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 |  | 0 | 0 | 7971.3198 | 2d | 0 | 0 | 0 | 7971.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 |  | 0 | 0 | 6060.8401 | 3d | 0 | 0 | 0 | 6060.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 |  | 0 | 0 | 31167.6309 | 6d | 0 | 0 | 0 | 31167.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 |  | 0 | 0 | 19599.6406 | 1d | 0 | 0 | 0 | 19599.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 |  | 0 | 0 | 5921.4399 | 3d | 0 | 0 | 0 | 5921.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 |  | 0 | 0 | 20906.29 | 6d | 0 | 0 | 0 | 20906.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 |  | 0 | 0 | 4035.8 | 2d | 0 | 0 | 0 | 4035.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 |  | 0 | 0 | 2921.98 | 2d | 0 | 0 | 0 | 2921.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 |  | 0 | 0 | 18412.8799 | 5d | 0 | 0 | 0 | 18412.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 |  | 0 | 0 | 23264.21 | 5d | 0 | 0 | 0 | 23264.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 |  | 0 | 0 | 41119.3984 | 5d | 0 | 0 | 0 | 41119.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 |  | 0 | 0 | 48839.8906 | 20d | 0 | 0 | 0 | 48839.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-05-05 07:00 |  | TP Name | T4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 73d | [5 empty] | 446927.9866 |  | 49.32% |  | 446927.9866 | 446927.9866
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 5d | 80353.4062 | 15600 | 15d | 0 | 0 | 80353.4062 | 15600 | 25% | Started | 80353.4062 | 80353.4062 | 100 | 25 | 25 | 100 | 83.7421 | 25
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 |  | 0 | 0 | 3650.99 | 2d | 0 | 0 | 0 | 3650.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 |  | 0 | 0 | 7971.3198 | 2d | 0 | 0 | 0 | 7971.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 |  | 0 | 0 | 6060.8401 | 3d | 0 | 0 | 0 | 6060.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 |  | 0 | 0 | 31167.6309 | 6d | 0 | 0 | 0 | 31167.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 |  | 0 | 0 | 19599.6406 | 1d | 0 | 0 | 0 | 19599.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 |  | 0 | 0 | 5921.4399 | 3d | 0 | 0 | 0 | 5921.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 |  | 0 | 0 | 20906.29 | 6d | 0 | 0 | 0 | 20906.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 |  | 0 | 0 | 4035.8 | 2d | 0 | 0 | 0 | 4035.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 |  | 0 | 0 | 2921.98 | 2d | 0 | 0 | 0 | 2921.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 |  | 0 | 0 | 18412.8799 | 5d | 0 | 0 | 0 | 18412.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 |  | 0 | 0 | 23264.21 | 5d | 0 | 0 | 0 | 23264.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 |  | 0 | 0 | 41119.3984 | 5d | 0 | 0 | 0 | 41119.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 |  | 0 | 0 | 48839.8906 | 20d | 0 | 0 | 0 | 48839.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-06-02 07:00 |  | TP Name | T5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 93d | [5 empty] | 466178.9766 |  | 51.44% |  | 466178.9766 | 466178.9766
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 100% | Finished | 95953.4062 | 95953.4062 | 100 | 100 | 100 | 100 | 100 | 100
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 100% | Finished | 3650.99 | 3650.99 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 |  | 0 | 0 | 7971.3198 | 2d | 0 | 0 | 0 | 7971.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 |  | 0 | 0 | 6060.8401 | 3d | 0 | 0 | 0 | 6060.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 |  | 0 | 0 | 31167.6309 | 6d | 0 | 0 | 0 | 31167.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 |  | 0 | 0 | 19599.6406 | 1d | 0 | 0 | 0 | 19599.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 |  | 0 | 0 | 5921.4399 | 3d | 0 | 0 | 0 | 5921.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 |  | 0 | 0 | 20906.29 | 6d | 0 | 0 | 0 | 20906.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 |  | 0 | 0 | 4035.8 | 2d | 0 | 0 | 0 | 4035.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 |  | 0 | 0 | 2921.98 | 2d | 0 | 0 | 0 | 2921.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 |  | 0 | 0 | 18412.8799 | 5d | 0 | 0 | 0 | 18412.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 |  | 0 | 0 | 23264.21 | 5d | 0 | 0 | 0 | 23264.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 |  | 0 | 0 | 41119.3984 | 5d | 0 | 0 | 0 | 41119.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 |  | 0 | 0 | 48839.8906 | 20d | 0 | 0 | 0 | 48839.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2014-07-07 07:00 |  | TP Name | T6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 120d | [5 empty] | 535620.8479 |  | 59.1% |  | 535620.848 | 530979.408
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 100% | Finished | 95953.4062 | 95953.4062 | 100 | 100 | 100 | 100 | 100 | 100
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 100% | Finished | 3650.99 | 3650.99 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 2014-06-02 07:00 | 2d | 7971.3198 | 0 | 0 | 0 | 0 | 7971.3198 | 0 | 100% | Finished | 7971.3198 | 7971.3198 | 100 | 100 | 100 | 100 | 100 | 100
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 21d | [5 empty] | 56829.1116 |  | 100% |  | 56829.1116 | 56829.1116
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2014-06-04 07:00 | 3d | 6060.8401 | 0 | 0 | 0 | 0 | 6060.8401 | 0 | 100% | Finished | 6060.8401 | 6060.8401 | 100 | 100 | 100 | 100 | 100 | 100
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 2014-06-10 07:00 | 6d | 31167.6309 | 0 | 0 | 0 | 0 | 31167.6309 | 0 | 100% | Finished | 31167.6309 | 31167.6309 | 100 | 100 | 100 | 100 | 100 | 100
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 2014-06-18 07:00 | 1d | 19599.6406 | 0 | 0 | 0 | 0 | 19599.6406 | 0 | 100% | Finished | 19599.6406 | 19599.6406 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-06-19 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 5d | [5 empty] | 4641.4399 |  | 10.29% |  | 4641.44 | 0
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2014-07-02 07:00 | 2d | 4641.4399 | 1280 | 1d | 0 | 0 | 4641.4399 | 1280 | 66.67% | Started | 4641.44 | 0 | 100 | 66.6667 | 66.6667 | 100 | 78.3836 | 66.6667
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 |  | 0 | 0 | 20906.29 | 6d | 0 | 0 | 0 | 20906.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 |  | 0 | 0 | 4035.8 | 2d | 0 | 0 | 0 | 4035.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 |  | 0 | 0 | 2921.98 | 2d | 0 | 0 | 0 | 2921.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 |  | 0 | 0 | 18412.8799 | 5d | 0 | 0 | 0 | 18412.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 |  | 0 | 0 | 23264.21 | 5d | 0 | 0 | 0 | 23264.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 |  | 0 | 0 | 41119.3984 | 5d | 0 | 0 | 0 | 41119.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 |  | 0 | 0 | 48839.8906 | 20d | 0 | 0 | 0 | 48839.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2014-08-04 07:00 |  | TP Name | T7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 140d | [5 empty] | 576101.1379 |  | 63.57% |  | 576101.1379 | 576101.1379
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 100% | Finished | 95953.4062 | 95953.4062 | 100 | 100 | 100 | 100 | 100 | 100
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 100% | Finished | 3650.99 | 3650.99 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 2014-06-02 07:00 | 2d | 7971.3198 | 0 | 0 | 0 | 0 | 7971.3198 | 0 | 100% | Finished | 7971.3198 | 7971.3198 | 100 | 100 | 100 | 100 | 100 | 100
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 21d | [5 empty] | 56829.1116 |  | 100% |  | 56829.1116 | 56829.1116
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2014-06-04 07:00 | 3d | 6060.8401 | 0 | 0 | 0 | 0 | 6060.8401 | 0 | 100% | Finished | 6060.8401 | 6060.8401 | 100 | 100 | 100 | 100 | 100 | 100
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 2014-06-10 07:00 | 6d | 31167.6309 | 0 | 0 | 0 | 0 | 31167.6309 | 0 | 100% | Finished | 31167.6309 | 31167.6309 | 100 | 100 | 100 | 100 | 100 | 100
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 2014-06-18 07:00 | 1d | 19599.6406 | 0 | 0 | 0 | 0 | 19599.6406 | 0 | 100% | Finished | 19599.6406 | 19599.6406 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-06-19 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 25d | [5 empty] | 45121.73 |  | 100% |  | 45121.73 | 45121.73
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2014-07-02 07:00 | 3d | 5921.4399 | 0 | 0 | 0 | 0 | 5921.4399 | 0 | 100% | Finished | 5921.4399 | 5921.4399 | 100 | 100 | 100 | 100 | 100 | 100
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 | 2014-07-08 07:00 | 6d | 20906.29 | 0 | 0 | 0 | 0 | 20906.29 | 0 | 100% | Finished | 20906.29 | 20906.29 | 100 | 100 | 100 | 100 | 100 | 100
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-07-15 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-07-16 07:00 | 3d | 1 | 0 | 7d | 0 | 0 | 1 | 0 | 30% | Started | 1 | 1 | 100 | 30 | 30 | 100 | 100 | 30
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 |  | 0 | 0 | 4035.8 | 2d | 0 | 0 | 0 | 4035.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 |  | 0 | 0 | 2921.98 | 2d | 0 | 0 | 0 | 2921.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 |  | 0 | 0 | 18412.8799 | 5d | 0 | 0 | 0 | 18412.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 |  | 0 | 0 | 23264.21 | 5d | 0 | 0 | 0 | 23264.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 |  | 0 | 0 | 41119.3984 | 5d | 0 | 0 | 0 | 41119.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 |  | 0 | 0 | 48839.8906 | 20d | 0 | 0 | 0 | 48839.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2014-09-01 07:00 |  | TP Name | T8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 160d | [5 empty] | 600191.7979 |  | 66.23% |  | 600191.7979 | 576101.1379
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 100% | Finished | 95953.4062 | 95953.4062 | 100 | 100 | 100 | 100 | 100 | 100
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 100% | Finished | 3650.99 | 3650.99 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 2014-06-02 07:00 | 2d | 7971.3198 | 0 | 0 | 0 | 0 | 7971.3198 | 0 | 100% | Finished | 7971.3198 | 7971.3198 | 100 | 100 | 100 | 100 | 100 | 100
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 21d | [5 empty] | 56829.1116 |  | 100% |  | 56829.1116 | 56829.1116
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2014-06-04 07:00 | 3d | 6060.8401 | 0 | 0 | 0 | 0 | 6060.8401 | 0 | 100% | Finished | 6060.8401 | 6060.8401 | 100 | 100 | 100 | 100 | 100 | 100
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 2014-06-10 07:00 | 6d | 31167.6309 | 0 | 0 | 0 | 0 | 31167.6309 | 0 | 100% | Finished | 31167.6309 | 31167.6309 | 100 | 100 | 100 | 100 | 100 | 100
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 2014-06-18 07:00 | 1d | 19599.6406 | 0 | 0 | 0 | 0 | 19599.6406 | 0 | 100% | Finished | 19599.6406 | 19599.6406 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-06-19 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 22d | [5 empty] | 45121.73 |  | 100% |  | 45121.73 | 45121.73
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2014-07-02 07:00 | 3d | 5921.4399 | 0 | 0 | 0 | 0 | 5921.4399 | 0 | 100% | Finished | 5921.4399 | 5921.4399 | 100 | 100 | 100 | 100 | 100 | 100
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 | 2014-07-08 07:00 | 6d | 20906.29 | 0 | 0 | 0 | 0 | 20906.29 | 0 | 100% | Finished | 20906.29 | 20906.29 | 100 | 100 | 100 | 100 | 100 | 100
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-07-15 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-07-16 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 10d | [5 empty] | 24090.6599 |  | 55.17% |  | 24090.66 | 0
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 | 2014-08-18 07:00 | 2d | 4035.8 | 0 | 0 | 0 | 0 | 4035.8 | 0 | 100% | Finished | 4035.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 | 2014-08-21 07:00 | 2d | 2921.98 | 0 | 0 | 0 | 0 | 2921.98 | 0 | 100% | Finished | 2921.98 | 0 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 | 2014-08-25 07:00 | 4d | 17132.8799 | 1280 | 1d | 0 | 0 | 17132.8799 | 1280 | 80% | Started | 17132.88 | 0 | 100 | 80 | 80 | 100 | 93.0483 | 80
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 |  | 0 | 0 | 18293 | 1d | 0 | 0 | 0 | 18293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 |  | 0 | 0 | 23264.21 | 5d | 0 | 0 | 0 | 23264.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 |  | 0 | 0 | 41119.3984 | 5d | 0 | 0 | 0 | 41119.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 |  | 0 | 0 | 48839.8906 | 20d | 0 | 0 | 0 | 48839.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2014-10-06 07:00 |  | TP Name | T9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 185d | [5 empty] | 759971.4258 |  | 83.86% |  | 759971.4259 | 725651.5352
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 100% | Finished | 95953.4062 | 95953.4062 | 100 | 100 | 100 | 100 | 100 | 100
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 100% | Finished | 3650.99 | 3650.99 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 2014-06-02 07:00 | 2d | 7971.3198 | 0 | 0 | 0 | 0 | 7971.3198 | 0 | 100% | Finished | 7971.3198 | 7971.3198 | 100 | 100 | 100 | 100 | 100 | 100
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 21d | [5 empty] | 56829.1116 |  | 100% |  | 56829.1116 | 56829.1116
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2014-06-04 07:00 | 3d | 6060.8401 | 0 | 0 | 0 | 0 | 6060.8401 | 0 | 100% | Finished | 6060.8401 | 6060.8401 | 100 | 100 | 100 | 100 | 100 | 100
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 2014-06-10 07:00 | 6d | 31167.6309 | 0 | 0 | 0 | 0 | 31167.6309 | 0 | 100% | Finished | 31167.6309 | 31167.6309 | 100 | 100 | 100 | 100 | 100 | 100
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 2014-06-18 07:00 | 1d | 19599.6406 | 0 | 0 | 0 | 0 | 19599.6406 | 0 | 100% | Finished | 19599.6406 | 19599.6406 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-06-19 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 22d | [5 empty] | 45121.73 |  | 100% |  | 45121.73 | 45121.73
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2014-07-02 07:00 | 3d | 5921.4399 | 0 | 0 | 0 | 0 | 5921.4399 | 0 | 100% | Finished | 5921.4399 | 5921.4399 | 100 | 100 | 100 | 100 | 100 | 100
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 | 2014-07-08 07:00 | 6d | 20906.29 | 0 | 0 | 0 | 0 | 20906.29 | 0 | 100% | Finished | 20906.29 | 20906.29 | 100 | 100 | 100 | 100 | 100 | 100
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-07-15 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-07-16 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 17d | [5 empty] | 43664.6599 |  | 100% |  | 43664.6599 | 43664.6599
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 | 2014-08-18 07:00 | 2d | 4035.8 | 0 | 0 | 0 | 0 | 4035.8 | 0 | 100% | Finished | 4035.8 | 4035.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 | 2014-08-21 07:00 | 2d | 2921.98 | 0 | 0 | 0 | 0 | 2921.98 | 0 | 100% | Finished | 2921.98 | 2921.98 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 | 2014-08-25 07:00 | 5d | 18412.8799 | 0 | 0 | 0 | 0 | 18412.8799 | 0 | 100% | Finished | 18412.8799 | 18412.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-09-02 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2014-09-03 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 | 2014-09-03 07:00 | 5d | 23264.21 | 0 | 0 | 0 | 0 | 23264.21 | 0 | 100% | Finished | 23264.21 | 23264.21 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 | 2014-09-15 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 | 2014-09-22 07:00 | 5d | 41119.3984 | 0 | 0 | 0 | 0 | 41119.3984 | 0 | 100% | Finished | 41119.3984 | 37279.3984 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 | 2014-10-01 07:00 | 3d | 30479.8906 | 18360 | 17d | 0 | 0 | 30479.8906 | 18360 | 15% | Started | 30479.8908 | 0 | 100 | 15 | 15 | 100 | 62.4078 | 15
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 |  | 0 | 0 | 127922.4414 | 40d | 0 | 0 | 0 | 127922.4414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2014-11-03 07:00 |  | TP Name | T10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 205d | [5 empty] | 848533.8672 |  | 93.63% |  | 848533.8674 | 775091.4258
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 100% | Finished | 95953.4062 | 95953.4062 | 100 | 100 | 100 | 100 | 100 | 100
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 100% | Finished | 3650.99 | 3650.99 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 2014-06-02 07:00 | 2d | 7971.3198 | 0 | 0 | 0 | 0 | 7971.3198 | 0 | 100% | Finished | 7971.3198 | 7971.3198 | 100 | 100 | 100 | 100 | 100 | 100
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 21d | [5 empty] | 56829.1116 |  | 100% |  | 56829.1116 | 56829.1116
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2014-06-04 07:00 | 3d | 6060.8401 | 0 | 0 | 0 | 0 | 6060.8401 | 0 | 100% | Finished | 6060.8401 | 6060.8401 | 100 | 100 | 100 | 100 | 100 | 100
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 2014-06-10 07:00 | 6d | 31167.6309 | 0 | 0 | 0 | 0 | 31167.6309 | 0 | 100% | Finished | 31167.6309 | 31167.6309 | 100 | 100 | 100 | 100 | 100 | 100
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 2014-06-18 07:00 | 1d | 19599.6406 | 0 | 0 | 0 | 0 | 19599.6406 | 0 | 100% | Finished | 19599.6406 | 19599.6406 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-06-19 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 22d | [5 empty] | 45121.73 |  | 100% |  | 45121.73 | 45121.73
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2014-07-02 07:00 | 3d | 5921.4399 | 0 | 0 | 0 | 0 | 5921.4399 | 0 | 100% | Finished | 5921.4399 | 5921.4399 | 100 | 100 | 100 | 100 | 100 | 100
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 | 2014-07-08 07:00 | 6d | 20906.29 | 0 | 0 | 0 | 0 | 20906.29 | 0 | 100% | Finished | 20906.29 | 20906.29 | 100 | 100 | 100 | 100 | 100 | 100
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-07-15 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-07-16 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 17d | [5 empty] | 43664.6599 |  | 100% |  | 43664.6599 | 43664.6599
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 | 2014-08-18 07:00 | 2d | 4035.8 | 0 | 0 | 0 | 0 | 4035.8 | 0 | 100% | Finished | 4035.8 | 4035.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 | 2014-08-21 07:00 | 2d | 2921.98 | 0 | 0 | 0 | 0 | 2921.98 | 0 | 100% | Finished | 2921.98 | 2921.98 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 | 2014-08-25 07:00 | 5d | 18412.8799 | 0 | 0 | 0 | 0 | 18412.8799 | 0 | 100% | Finished | 18412.8799 | 18412.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-09-02 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2014-09-03 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 | 2014-09-03 07:00 | 5d | 23264.21 | 0 | 0 | 0 | 0 | 23264.21 | 0 | 100% | Finished | 23264.21 | 23264.21 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 | 2014-09-15 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 | 2014-09-22 07:00 | 5d | 41119.3984 | 0 | 0 | 0 | 0 | 41119.3984 | 0 | 100% | Finished | 41119.3984 | 41119.3984 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 | 2014-10-01 07:00 | 20d | 48839.8906 | 0 | 0 | 0 | 0 | 48839.8906 | 0 | 100% | Finished | 48839.8906 | 45599.8906 | 100 | 100 | 100 | 100 | 100 | 100
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 | 2014-10-29 07:00 | 3d | 70202.4414 | 57720 | 37d | 0 | 0 | 70202.4414 | 57720 | 7.5% | Started | 70202.4416 | 0 | 100 | 7.5 | 7.5 | 100 | 54.8789 | 7.5

## TP11
| TP Status Date | 2014-12-01 07:00 |  | TP Name | T11
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 225d | [5 empty] | 879733.8672 |  | 97.07% |  | 879733.8664 | 870373.8672
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 100% | Finished | 95953.4062 | 95953.4062 | 100 | 100 | 100 | 100 | 100 | 100
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 100% | Finished | 3650.99 | 3650.99 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 2014-06-02 07:00 | 2d | 7971.3198 | 0 | 0 | 0 | 0 | 7971.3198 | 0 | 100% | Finished | 7971.3198 | 7971.3198 | 100 | 100 | 100 | 100 | 100 | 100
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 21d | [5 empty] | 56829.1116 |  | 100% |  | 56829.1116 | 56829.1116
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2014-06-04 07:00 | 3d | 6060.8401 | 0 | 0 | 0 | 0 | 6060.8401 | 0 | 100% | Finished | 6060.8401 | 6060.8401 | 100 | 100 | 100 | 100 | 100 | 100
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 2014-06-10 07:00 | 6d | 31167.6309 | 0 | 0 | 0 | 0 | 31167.6309 | 0 | 100% | Finished | 31167.6309 | 31167.6309 | 100 | 100 | 100 | 100 | 100 | 100
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 2014-06-18 07:00 | 1d | 19599.6406 | 0 | 0 | 0 | 0 | 19599.6406 | 0 | 100% | Finished | 19599.6406 | 19599.6406 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-06-19 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 22d | [5 empty] | 45121.73 |  | 100% |  | 45121.73 | 45121.73
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2014-07-02 07:00 | 3d | 5921.4399 | 0 | 0 | 0 | 0 | 5921.4399 | 0 | 100% | Finished | 5921.4399 | 5921.4399 | 100 | 100 | 100 | 100 | 100 | 100
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 | 2014-07-08 07:00 | 6d | 20906.29 | 0 | 0 | 0 | 0 | 20906.29 | 0 | 100% | Finished | 20906.29 | 20906.29 | 100 | 100 | 100 | 100 | 100 | 100
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-07-15 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-07-16 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 17d | [5 empty] | 43664.6599 |  | 100% |  | 43664.6599 | 43664.6599
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 | 2014-08-18 07:00 | 2d | 4035.8 | 0 | 0 | 0 | 0 | 4035.8 | 0 | 100% | Finished | 4035.8 | 4035.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 | 2014-08-21 07:00 | 2d | 2921.98 | 0 | 0 | 0 | 0 | 2921.98 | 0 | 100% | Finished | 2921.98 | 2921.98 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 | 2014-08-25 07:00 | 5d | 18412.8799 | 0 | 0 | 0 | 0 | 18412.8799 | 0 | 100% | Finished | 18412.8799 | 18412.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-09-02 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2014-09-03 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 | 2014-09-03 07:00 | 5d | 23264.21 | 0 | 0 | 0 | 0 | 23264.21 | 0 | 100% | Finished | 23264.21 | 23264.21 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 | 2014-09-15 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 | 2014-09-22 07:00 | 5d | 41119.3984 | 0 | 0 | 0 | 0 | 41119.3984 | 0 | 100% | Finished | 41119.3984 | 41119.3984 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 | 2014-10-01 07:00 | 20d | 48839.8906 | 0 | 0 | 0 | 0 | 48839.8906 | 0 | 100% | Finished | 48839.8906 | 48839.8906 | 100 | 100 | 100 | 100 | 100 | 100
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 | 2014-10-29 07:00 | 23d | 101402.4414 | 26520 | 17d | 0 | 0 | 101402.4414 | 26520 | 57.5% | Started | 101402.4407 | 92042.4414 | 100 | 57.5 | 57.5 | 100 | 79.2687 | 57.5

## TP12
| TP Status Date | 2015-01-05 07:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (4) | 2014-01-24 07:00 | 2014-12-29 16:00 | 248d |  |  | 674453.8672 |  |  | 906253.8672 |  | 242d | [5 empty] | 906253.8672 |  | 100% |  | 906253.8672 | 906253.8672
1 | Voorbereidende studie | 2014-01-24 07:00 | 2014-03-06 16:00 | 30d |  | 0 | 9475.3398 | 70 | 16800 | 26275.3398 | 2014-01-24 07:00 | 30d | 26275.3398 | 0 | 0 | 0 | 0 | 26275.3398 | 0 | 100% | Finished | 26275.3398 | 26275.3398 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2014-02-28 07:00 | 2014-03-06 16:00 | 5d |  | 0 | 19624.9395 | 140 | 5600 | 25224.9395 | 2014-02-28 07:00 | 5d | 25224.9395 | 0 | 0 | 0 | 0 | 25224.9395 | 0 | 100% | Finished | 25224.9395 | 25224.9395 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2014-03-08 07:00 | 2014-03-09 16:00 | 2d |  | 0 | 62658.8984 | 400 | 6400 | 69058.8984 | 2014-03-08 07:00 | 2d | 69058.8984 | 0 | 0 | 0 | 0 | 69058.8984 | 0 | 100% | Finished | 69058.8984 | 69058.8984 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2014-03-10 07:00 | 2014-03-21 16:00 | 10d |  | 0 | 2127.0901 | 80 | 6400 | 8527.0901 | 2014-03-10 07:00 | 10d | 8527.0901 | 0 | 0 | 0 | 0 | 8527.0901 | 0 | 100% | Finished | 8527.0901 | 8527.0901 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2014-03-24 07:00 | 2014-04-18 16:00 | 20d |  | 0 | 205488.3125 | 200 | 32000 | 237488.3125 | 2014-03-24 07:00 | 20d | 237488.3125 | 0 | 0 | 0 | 0 | 237488.3125 | 0 | 100% | Finished | 237488.3125 | 237488.3125 | 100 | 100 | 100 | 100 | 100 | 100
6 | Uitvoeren van funderingsbalken | 2014-04-28 07:00 | 2014-05-23 16:00 | 20d |  | 0 | 75153.4062 | 130 | 20800 | 95953.4062 | 2014-04-28 07:00 | 20d | 95953.4062 | 0 | 0 | 0 | 0 | 95953.4062 | 0 | 100% | Finished | 95953.4062 | 95953.4062 | 100 | 100 | 100 | 100 | 100 | 100
7 | Montage boogkist | 2014-05-27 07:00 | 2014-05-28 16:00 | 2d |  | 0 | 1810.99 | 115 | 1840 | 3650.99 | 2014-05-27 07:00 | 2d | 3650.99 | 0 | 0 | 0 | 0 | 3650.99 | 0 | 100% | Finished | 3650.99 | 3650.99 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plaatsen boogkist | 2014-06-02 07:00 | 2014-06-03 16:00 | 2d |  | 0 | 5811.3198 | 135 | 2160 | 7971.3198 | 2014-06-02 07:00 | 2d | 7971.3198 | 0 | 0 | 0 | 0 | 7971.3198 | 0 | 100% | Finished | 7971.3198 | 7971.3198 | 100 | 100 | 100 | 100 | 100 | 100
27 | 1e fase brug | 2014-06-02 07:00 | 2014-07-04 16:00 | 25d |  |  | 45189.1116 |  |  | 56829.1116 |  | 21d | [5 empty] | 56829.1116 |  | 100% |  | 56829.1116 | 56829.1116
9 | Opkuisen bekisting + plaatsen randkist | 2014-06-02 07:00 | 2014-06-04 16:00 | 3d |  | 0 | 3060.8401 | 125 | 3000 | 6060.8401 | 2014-06-04 07:00 | 3d | 6060.8401 | 0 | 0 | 0 | 0 | 6060.8401 | 0 | 100% | Finished | 6060.8401 | 6060.8401 | 100 | 100 | 100 | 100 | 100 | 100
10 | Wapenen | 2014-06-05 07:00 | 2014-06-12 16:00 | 6d |  | 0 | 24447.6309 | 140 | 6720 | 31167.6309 | 2014-06-10 07:00 | 6d | 31167.6309 | 0 | 0 | 0 | 0 | 31167.6309 | 0 | 100% | Finished | 31167.6309 | 31167.6309 | 100 | 100 | 100 | 100 | 100 | 100
11 | Betonneren | 2014-06-13 07:00 | 2014-06-13 16:00 | 1d |  | 0 | 17679.6406 | 240 | 1920 | 19599.6406 | 2014-06-18 07:00 | 1d | 19599.6406 | 0 | 0 | 0 | 0 | 19599.6406 | 0 | 100% | Finished | 19599.6406 | 19599.6406 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitharden | 2014-06-23 07:00 | 2014-07-04 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-06-19 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
28 | 2e fase brug | 2014-07-07 07:00 | 2014-08-01 16:00 | 20d |  |  | 32321.73 |  |  | 45121.73 |  | 22d | [5 empty] | 45121.73 |  | 100% |  | 45121.73 | 45121.73
13 | Zakken bekisting + verschuiven en opkuisen | 2014-07-07 07:00 | 2014-07-09 16:00 | 3d |  | 0 | 2081.4399 | 160 | 3840 | 5921.4399 | 2014-07-02 07:00 | 3d | 5921.4399 | 0 | 0 | 0 | 0 | 5921.4399 | 0 | 100% | Finished | 5921.4399 | 5921.4399 | 100 | 100 | 100 | 100 | 100 | 100
14 | Wapenen | 2014-07-10 07:00 | 2014-07-17 16:00 | 6d |  | 0 | 13226.29 | 160 | 7680 | 20906.29 | 2014-07-08 07:00 | 6d | 20906.29 | 0 | 0 | 0 | 0 | 20906.29 | 0 | 100% | Finished | 20906.29 | 20906.29 | 100 | 100 | 100 | 100 | 100 | 100
15 | Betonneren | 2014-07-18 07:00 | 2014-07-18 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-07-15 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
16 | Uitharden | 2014-07-21 07:00 | 2014-08-01 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-07-16 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
29 | 3e fase brug | 2014-09-01 07:00 | 2014-09-26 16:00 | 20d |  |  | 31904.6599 |  |  | 43664.6599 |  | 17d | [5 empty] | 43664.6599 |  | 100% |  | 43664.6599 | 43664.6599
17 | Zakken bekisting + verschuiven en opkuisen | 2014-09-01 07:00 | 2014-09-02 16:00 | 2d |  | 0 | 1475.8 | 160 | 2560 | 4035.8 | 2014-08-18 07:00 | 2d | 4035.8 | 0 | 0 | 0 | 0 | 4035.8 | 0 | 100% | Finished | 4035.8 | 4035.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen randbekisting | 2014-09-03 07:00 | 2014-09-04 16:00 | 2d |  | 0 | 1401.98 | 95 | 1520 | 2921.98 | 2014-08-21 07:00 | 2d | 2921.98 | 0 | 0 | 0 | 0 | 2921.98 | 0 | 100% | Finished | 2921.98 | 2921.98 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2014-09-05 07:00 | 2014-09-11 16:00 | 5d |  | 0 | 12012.8799 | 160 | 6400 | 18412.8799 | 2014-08-25 07:00 | 5d | 18412.8799 | 0 | 0 | 0 | 0 | 18412.8799 | 0 | 100% | Finished | 18412.8799 | 18412.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2014-09-12 07:00 | 2014-09-12 16:00 | 1d |  | 0 | 17013 | 160 | 1280 | 18293 | 2014-09-02 07:00 | 1d | 18293 | 0 | 0 | 0 | 0 | 18293 | 0 | 100% | Finished | 18293 | 18293 | 100 | 100 | 100 | 100 | 100 | 100
21 | Uitharden | 2014-09-22 07:00 | 2014-09-26 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2014-09-03 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen en betonneren voeg | 2014-09-18 07:00 | 2014-09-24 16:00 | 5d |  | 0 | 15864.21 | 185 | 7400 | 23264.21 | 2014-09-03 07:00 | 5d | 23264.21 | 0 | 0 | 0 | 0 | 23264.21 | 0 | 100% | Finished | 23264.21 | 23264.21 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen dakdichting | 2014-09-25 07:00 | 2014-10-01 16:00 | 5d |  | 0 | 39542.1289 | 145 | 5800 | 45342.1289 | 2014-09-15 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
24 | Aanvullen boogbrug | 2014-10-02 07:00 | 2014-10-08 16:00 | 5d |  | 0 | 34719.3984 | 160 | 6400 | 41119.3984 | 2014-09-22 07:00 | 5d | 41119.3984 | 0 | 0 | 0 | 0 | 41119.3984 | 0 | 100% | Finished | 41119.3984 | 41119.3984 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wegeniswerken | 2014-10-09 07:00 | 2014-11-05 16:00 | 20d |  | 0 | 27239.8906 | 135 | 21600 | 48839.8906 | 2014-10-01 07:00 | 20d | 48839.8906 | 0 | 0 | 0 | 0 | 48839.8906 | 0 | 100% | Finished | 48839.8906 | 48839.8906 | 100 | 100 | 100 | 100 | 100 | 100
26 | Afwerkingen | 2014-11-06 07:00 | 2014-12-29 16:00 | 40d |  | 0 | 65522.4414 | 195 | 62400 | 127922.4414 | 2014-10-29 07:00 | 40d | 127922.4414 | 0 | 0 | 0 | 0 | 127922.4414 | 0 | 100% | Finished | 127922.4414 | 127922.4414 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2014-01-25
1:00 - 2:00 | No | Tuesday | Yes | 2014-01-26
2:00 - 3:00 | No | Wednesday | Yes | 2014-02-01
3:00 - 4:00 | No | Thursday | Yes | 2014-02-02
4:00 - 5:00 | No | Friday | Yes | 2014-02-08
5:00 - 6:00 | No | Saturday | Yes | 2014-02-09
6:00 - 7:00 | No | Sunday | Yes | 2014-02-15
7:00 - 8:00 | Yes |  |  | 2014-02-16
8:00 - 9:00 | Yes |  |  | 2014-02-22
9:00 - 10:00 | Yes |  |  | 2014-02-23
10:00 - 11:00 | Yes |  |  | 2014-03-01
11:00 - 12:00 | Yes |  |  | 2014-03-02
12:00 - 13:00 | No |  |  | 2014-03-15
13:00 - 14:00 | Yes |  |  | 2014-03-16
14:00 - 15:00 | Yes |  |  | 2014-03-22
15:00 - 16:00 | Yes |  |  | 2014-03-23
16:00 - 17:00 | No |  |  | 2014-03-29
17:00 - 18:00 | No |  |  | 2014-03-30
18:00 - 19:00 | No |  |  | 2014-04-05
19:00 - 20:00 | No |  |  | 2014-04-06
20:00 - 21:00 | No |  |  | 2014-04-12
21:00 - 22:00 | No |  |  | 2014-04-13
22:00 - 23:00 | No |  |  | 2014-04-19
23:00 - 0:00 | No |  |  | 2014-04-20
2014-04-26
2014-04-27
Generated by PMConverter v1.1.3 |  |  |  | 2014-05-03
2014-05-04
2014-05-10
2014-05-11
2014-05-17
2014-05-18
2014-05-24
2014-05-25
2014-05-31
2014-06-01
2014-06-07
2014-06-08
2014-06-14
2014-06-15
2014-06-21
2014-06-22
2014-06-28
2014-06-29
2014-07-12
2014-07-13
2014-07-19
2014-07-20
2014-07-26
2014-07-27
2014-08-02
2014-08-03
2014-08-09
2014-08-10
2014-08-16
2014-08-17
2014-08-23
2014-08-24
2014-08-30
2014-08-31
2014-09-06
2014-09-07
2014-09-13
2014-09-14
2014-09-20
2014-09-21
2014-09-27
2014-09-28
2014-10-04
2014-10-05
2014-10-11
2014-10-12
2014-10-18
2014-10-19
2014-10-25
2014-10-26
2014-11-01
2014-11-02
2014-11-08
2014-11-09
2014-11-15
2014-11-16
2014-11-22
2014-11-23
2014-11-29
2014-11-30
2014-12-13
2014-12-14
2014-12-20
2014-12-21
2014-12-27
2014-12-28
2015-01-03
2015-01-04
2015-01-10
2015-01-11
2015-01-17
2015-01-18
2015-01-24
2015-01-25
2015-01-31
2015-02-01
2015-02-07
2015-02-08
2015-02-14
2015-02-15
2015-02-21
2015-02-22
2015-02-28
2015-03-01
2015-03-07
2015-03-08
2015-03-14
2015-03-15
2015-03-21
2015-03-22
2015-03-28
2015-03-29
2015-04-04
2015-04-05
2015-04-11
2015-04-12
2015-04-18
2015-04-19
2015-04-25
2015-04-26
2015-05-02
2015-05-03
2015-05-09
2015-05-10
2015-05-16
2015-05-17
2015-05-23
2015-05-24
2015-05-30
2015-05-31
2015-06-13
2015-06-14
2015-06-20
2015-06-21
2015-06-27
2015-06-28
2015-07-04
2015-07-05
2015-07-11
2015-07-12
2015-07-18
2015-07-19
2015-07-25
2015-07-26
2015-08-01
2015-08-02
2015-08-08
2015-08-09
2015-08-15
2015-08-16
2015-08-22
2015-08-23
2015-08-29
2015-08-30
2015-09-05
2015-09-06

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
T1 | 2014-01-24 07:00 | 2014-02-03 07:00 | 12835.3398 | 12275.3399 | 12275.3398 | 2014-01-30 16:00 | -559.9999 | 95.64% | 8.3446e-05 | 100% | -1d | 83.33% | 100% | 2014-12-30 08:00 | 2015-01-14 10:00 | 2015-01-14 10:00 | 2014-12-30 09:00 | 2015-01-14 10:00 | 2015-01-14 10:00 | 2014-12-30 16:00 | 2015-03-09 12:00 | 2015-03-09 12:00 | 906253.8671 | 906253.861 | 947037.0881 | 1085049.5726 | 947037.0817 | 1085049.5653 | 914123.3038 | 937080.7077 | 0.83333 | 1 | 0.95637 | 1 | -1 | 1 | 1 | 0.83333 | 1
T2 | 2014-02-03 07:00 | 2014-03-03 07:00 | 44780.2793 | 44220.279 | 44220.2793 | 2014-02-28 12:00 | -560.0003 | 98.75% | -0.0003171 | 100% | -3h | 98.56% | 99.21% | 2014-12-30 08:00 | 2015-01-02 08:00 | 2015-01-02 08:00 | 2014-12-30 10:00 | 2015-01-02 08:00 | 2015-01-02 08:00 | 2014-12-30 10:00 | 2015-01-02 12:00 | 2015-01-02 12:00 | 906253.8675 | 906253.8737 | 917170.5576 | 918868.9932 | 917170.5639 | 918868.9995 | 908415.3127 | 908747.7016 | 0.98558 | 1 | 0.98749 | 0.99207 | -0.375 | 1 | 1 | 0.98558 | 1
T3 | 2014-03-03 07:00 | 2014-04-07 07:00 | 350574.5803 | 350574.5803 | 350574.5803 | 2014-04-04 16:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T4 | 2014-04-07 07:00 | 2014-05-05 07:00 | 446927.9866 | 446927.9866 | 446927.9866 | 2014-05-02 16:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T5 | 2014-05-05 07:00 | 2014-06-02 07:00 | 466178.9766 | 466178.9766 | 466178.9766 | 2014-05-30 16:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T6 | 2014-06-02 07:00 | 2014-07-07 07:00 | 530979.408 | 535620.848 | 535620.8479 | 2014-07-08 16:00 | 4641.44 | 100.9% | 7.6294e-05 | 100% | 2d | 101.7% | 100% | 2014-12-26 14:00 | 2014-12-25 15:00 | 2014-12-25 15:00 | 2014-12-26 16:00 | 2014-12-25 15:00 | 2014-12-25 15:00 | 2014-12-25 16:00 | 2014-12-23 15:00 | 2014-12-23 15:00 | 906253.8671 | 906253.8671 | 903042.1345 | 900177.916 | 903042.1345 | 900177.9159 | 905607.0364 | 905022.5281 | 1.0167 | 1 | 1.0087 | 1 | 2 | 1 | 1 | 1.0167 | 1
T7 | 2014-07-07 07:00 | 2014-08-04 07:00 | 576101.1379 | 576101.1379 | 576101.1379 | 2014-08-01 16:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T8 | 2014-08-04 07:00 | 2014-09-01 07:00 | 576101.1379 | 600191.7979 | 600191.7979 | 2014-09-10 16:00 | 24090.66 | 104.2% | 7.6294e-05 | 100% | 8d | 105% | 100% | 2014-12-19 10:00 | 2014-12-15 16:00 | 2014-12-15 16:00 | 2014-12-19 09:00 | 2014-12-15 16:00 | 2014-12-15 16:00 | 2014-12-17 16:00 | 2014-12-12 09:00 | 2014-12-12 09:00 | 906253.8671 | 906253.8671 | 893969.0654 | 891679.4829 | 893969.0653 | 891679.4828 | 903715.3948 | 903223.5496 | 1.05 | 1 | 1.0418 | 1 | 8 | 1 | 1 | 1.05 | 1
T9 | 2014-09-01 07:00 | 2014-10-06 07:00 | 725651.5352 | 759971.4259 | 759971.4258 | 2014-10-13 16:00 | 34319.8908 | 104.7% | 0.00012875 | 100% | 6d | 103.2% | 100% | 2014-12-16 12:00 | 2014-12-12 14:00 | 2014-12-12 14:00 | 2014-12-17 09:00 | 2014-12-12 14:00 | 2014-12-12 14:00 | 2014-12-19 16:00 | 2014-12-18 09:00 | 2014-12-18 09:00 | 906253.8671 | 906253.867 | 899647.8326 | 901658.6071 | 899647.8326 | 901658.6071 | 904883.1391 | 905311.1231 | 1.0324 | 1 | 1.0473 | 1 | 6 | 1 | 1 | 1.0324 | 1
T10 | 2014-10-06 07:00 | 2014-11-03 07:00 | 775091.4258 | 848533.8674 | 848533.8672 | 2014-11-10 16:00 | 73442.4416 | 109.5% | 0.00018597 | 100% | 6d | 102.9% | 100% | 2014-12-03 15:00 | 2014-12-02 11:00 | 2014-12-02 11:00 | 2014-12-04 12:00 | 2014-12-02 11:00 | 2014-12-02 11:00 | 2014-12-19 16:00 | 2014-12-18 16:00 | 2014-12-18 16:00 | 906253.867 | 906253.867 | 901258.0762 | 904612.54 | 901258.0762 | 904612.54 | 905180.3786 | 905917.9601 | 1.0293 | 1 | 1.0948 | 1 | 6 | 1 | 1 | 1.0293 | 1
T11 | 2014-11-03 07:00 | 2014-12-01 07:00 | 870373.8672 | 879733.8664 | 879733.8672 | 2014-12-06 16:00 | 9359.9993 | 101.1% | -0.00074387 | 100% | 6d | 102.7% | 100% | 2014-12-25 11:00 | 2014-12-25 10:00 | 2014-12-25 10:00 | 2014-12-25 12:00 | 2014-12-25 10:00 | 2014-12-25 10:00 | 2014-12-19 16:00 | 2014-12-19 11:00 | 2014-12-19 11:00 | 906253.8679 | 906253.868 | 905971.7062 | 905565.0367 | 905971.7063 | 905565.0368 | 906196.9512 | 906113.1783 | 1.0267 | 1 | 1.0108 | 1 | 6 | 1 | 1 | 1.0267 | 1
Actual Schedule | 2014-12-01 07:00 | 2015-01-05 07:00 | 906253.8672 | 906253.8672 | 906253.8672 | 2014-12-29 16:00 | 0 | 100% | 0 | 100% | -4d | 98.41% | 100% | 2014-12-29 16:00 | 2014-12-29 16:00 | 2014-12-29 16:00 | 2015-01-02 16:00 | 2015-01-02 16:00 | 2015-01-02 16:00 | 2015-01-02 16:00 | 2015-01-02 16:00 | 2015-01-02 16:00 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 906253.8672 | 0.98413 | 1 | 1 | 1 | -4 | 1 | 1 | 0.98413 | 1