## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Eating Belgium | 1 |  |  | 2011-08-27 08:00 | 2012-06-21 10:00 | 299d 2h |  |  | 0 |  |  | 37760 | 299.0833
27 | LOCATION | 1.1 |  |  | 2011-08-27 08:00 | 2012-04-05 11:00 | 222d 3h |  |  | 0 |  |  | 720 | 222.125
1 | Determine the location (A) | 1.1.1 |  | FS23 | 2011-08-27 08:00 | 2011-08-27 17:00 | 1d | Team[5.00 #5] | 400 | 0 | 0 | 0 | 400 | 0.375
23 | Hand in document for using Grand Place (W) | 1.1.2 | 1FS | FS2+25w 5d;FS3+25w 5d;FS8+25w 5d;FS9+25w 5d;FS13+25w 5d | 2011-08-28 08:00 | 2011-08-28 17:00 | 1d | Team | 80 | 0 | 0 | 0 | 80 | 0.375
13 | Look for a big enough car park (M) | 1.1.3 | 23FS+25w 5d | FS11 | 2012-04-04 11:00 | 2012-04-05 11:00 | 1d | Team | 80 | 0 | 0 | 0 | 80 | 1
2 | Make a map of the Grand Place (B) | 1.1.4 | 23FS+25w 5d | FS5;FS22;FS11 | 2012-04-02 11:00 | 2012-04-04 11:00 | 2d | Team | 160 | 0 | 0 | 0 | 160 | 2
28 | FINDING & CONTACTING CHEFS | 1.2 |  |  | 2012-02-25 08:00 | 2012-04-21 17:00 | 57d |  |  | 0 |  |  | 18800 | 56.375
3 | Look for potential exhibitors (C) | 1.2.1 | 23FS+25w 5d | FS4 | 2012-02-25 08:00 | 2012-03-02 17:00 | 7d | Team[5.00 #5] | 2800 | 0 | 0 | 0 | 2800 | 6.375
4 | Contacting chefs (D) | 1.2.2 | 3FS | FS14;FS11 | 2012-03-03 08:00 | 2012-04-21 17:00 | 50d | Team[4.00 #5] | 16000 | 0 | 0 | 0 | 16000 | 49.375
30 | SECURITY & SAFETY | 1.3 |  |  | 2012-04-22 15:00 | 2012-05-02 15:00 | 10d |  |  | 0 |  |  | 880 | 10
22 | Look for some safety guards (V) | 1.3.1 | 2FS | FS24 | 2012-04-25 15:00 | 2012-05-02 15:00 | 7d | Team | 560 | 0 | 0 | 0 | 560 | 7
5 | Make a blueprint of the safety plan (E) | 1.3.2 | 2FS | FS6 | 2012-04-22 15:00 | 2012-04-23 15:00 | 1d | Team | 80 | 0 | 0 | 0 | 80 | 1
6 | Make appointment with city council, police and fire brigade (F) | 1.3.3 | 5FS | FS7 | 2012-04-23 15:00 | 2012-04-24 15:00 | 1d | Team | 80 | 0 | 0 | 0 | 80 | 1
7 | Draft a safety plan, get it approved from city (G) | 1.3.4 | 6FS | FS14;FS15;FS16;FS17;FS18;FS21 | 2012-04-24 15:00 | 2012-04-25 15:00 | 1d | Team[2.00 #5] | 160 | 0 | 0 | 0 | 160 | 1
31 | MUSIC | 1.4 |  |  | 2012-04-25 15:00 | 2012-04-26 15:00 | 1d |  |  | 0 |  |  | 80 | 1
8 | Get licenses of SABAM and ‘Billijke vergoeding' (H) | 1.4.1 | 23FS+25w 5d | FS24 | 2012-04-25 15:00 | 2012-04-26 15:00 | 1d | Team | 80 | 0 | 0 | 0 | 80 | 1
29 | FACILITIES & DECORATIONS | 1.5 |  |  | 2012-05-06 08:00 | 2012-06-06 17:00 | 32d |  |  | 0 |  |  | 3920 | 31.375
14 | Look for food and drink stands (N) | 1.5.1 | 4FS;7FS | FS24 | 2012-05-31 08:00 | 2012-06-06 17:00 | 7d | Team | 560 | 0 | 0 | 0 | 560 | 6.375
15 | Contact a brewer for drinks and refrigerators (O) | 1.5.2 | 7FS | FS24 | 2012-05-31 08:00 | 2012-06-04 17:00 | 5d | Team | 400 | 0 | 0 | 0 | 400 | 4.375
16 | Reserve two generators (P) | 1.5.3 | 7FS | FS24 | 2012-05-06 08:00 | 2012-05-08 17:00 | 3d | Team | 240 | 0 | 0 | 0 | 240 | 2.375
17 | Looking for the tableware (Q) | 1.5.4 | 7FS | FS24 | 2012-05-06 08:00 | 2012-05-11 17:00 | 6d | Team | 480 | 0 | 0 | 0 | 480 | 5.375
18 | The search for the restrooms (R) | 1.5.5 | 7FS | FS24 | 2012-05-06 08:00 | 2012-05-08 17:00 | 3d | Team | 240 | 0 | 0 | 0 | 240 | 2.375
21 | Look for appropriate decoration (U) | 1.5.6 | 7FS | FS24 | 2012-05-06 08:00 | 2012-05-30 17:00 | 25d | Team | 2000 | 0 | 0 | 0 | 2000 | 24.375
26 | SPONSORING | 1.6 |  |  | 2012-02-23 15:00 | 2012-03-30 17:00 | 36d 2h |  |  | 0 |  |  | 2640 | 36.0833
10 | Think about sponsor deals (J) | 1.6.1 |  | FS9 | 2012-02-23 15:00 | 2012-02-24 15:00 | 1d | Team[5.00 #5] | 400 | 0 | 0 | 0 | 400 | 1
9 | Recruitment of sponsors (I) | 1.6.2 | 10FS;23FS+25w 5d | FS11 | 2012-03-03 08:00 | 2012-03-30 17:00 | 28d | Team | 2240 | 0 | 0 | 0 | 2240 | 27.375
25 | MARKETING | 1.7 |  |  | 2012-04-22 08:00 | 2012-06-20 17:00 | 60d |  |  | 0 |  |  | 9920 | 59.375
11 | Design a flyer, a poster, an event guide and website (K) | 1.7.1 | 2FS;13FS;9FS;4FS | FS12 | 2012-04-22 08:00 | 2012-05-05 17:00 | 14d | Team[2.00 #5] | 2240 | 0 | 0 | 0 | 2240 | 13.375
12 | Send our designs to the printing house (L) | 1.7.2 | 11FS | FS19 | 2012-05-06 08:00 | 2012-05-26 17:00 | 21d | Team | 1680 | 0 | 0 | 0 | 1680 | 20.375
19 | Distribute posters and flyers (S) | 1.7.3 | 20FS;12FS | FS24 | 2012-05-27 08:00 | 2012-06-20 17:00 | 25d | volunteers[20.00 #20];Team[3.00 #5] | 6000 | 0 | 0 | 0 | 6000 | 24.375
20 | Search volunteers (T) | 1.8 |  | FS19 | 2012-02-21 15:00 | 2012-02-23 15:00 | 2d | Team[5.00 #5] | 800 | 0 | 0 | 0 | 800 | 2
24 | End | 1.9 | 15FS;16FS;17FS;18FS;21FS;14FS;8FS;19FS;22FS |  | 2012-06-21 08:00 | 2012-06-21 10:00 | 2h |  | 0 | 0 | 0 | 0 | 0 | 0.083333

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Team | Renewable | 5 mensen | 0 | 10 | 1[5.00 Team];23;13;2;3[5.00 Team];4[4.00 Team];22;5;6;7[2.00 Team];8;14;15;16;17;18;21;10[5.00 Team];9;11[2.00 Team];12;19[3.00 Team];20[5.00 Team]; | 37760
2 | volunteers | Renewable | 20 mensen | 0 | 0 | 19[20.00 volunteers]; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Eating Belgium | 2394h |  |  |  |  | 99 | 100 | 101
27 | LOCATION | 1779h |  |  |  |  | 99 | 100 | 101
1 | Determine the location (A) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Hand in document for using Grand Place (W) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Look for a big enough car park (M) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Make a map of the Grand Place (B) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | FINDING & CONTACTING CHEFS | 456h |  |  |  |  | 99 | 100 | 101
3 | Look for potential exhibitors (C) | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Contacting chefs (D) | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | SECURITY & SAFETY | 80h |  |  |  |  | 99 | 100 | 101
22 | Look for some safety guards (V) | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Make a blueprint of the safety plan (E) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Make appointment with city council, police and fire brigade (F) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Draft a safety plan, get it approved from city (G) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | MUSIC | 8h |  |  |  |  | 99 | 100 | 101
8 | Get licenses of SABAM and ‘Billijke vergoeding' (H) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | FACILITIES & DECORATIONS | 256h |  |  |  |  | 99 | 100 | 101
14 | Look for food and drink stands (N) | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Contact a brewer for drinks and refrigerators (O) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Reserve two generators (P) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Looking for the tableware (Q) | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | The search for the restrooms (R) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Look for appropriate decoration (U) | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | SPONSORING | 290h |  |  |  |  | 99 | 100 | 101
10 | Think about sponsor deals (J) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Recruitment of sponsors (I) | 224h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | MARKETING | 480h |  |  |  |  | 99 | 100 | 101
11 | Design a flyer, a poster, an event guide and website (K) | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Send our designs to the printing house (L) | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Distribute posters and flyers (S) | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Search volunteers (T) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | End | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | Yes
6:00 - 7:00 | No | Sunday | Yes
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold