## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Manufacturing Tool Cost Module | 1 |  |  | 2012-06-04 08:00 | 2012-08-03 15:00 | 44d 6h |  |  | 0 |  |  | 61698.9 | 60.2917
1 | Manufacturing Tool Cost Module | 1.1 |  |  | 2012-06-04 08:00 | 2012-08-03 15:00 | 44d 6h |  |  | 0 |  |  | 61698.9 | 60.2917
2 | Kick-Off | 1.1.1 |  |  | 2012-06-04 08:00 | 2012-06-04 15:00 | 6h |  |  | 0 |  |  | 804.9 | 0.29167
3 | Kick-Off meeting & brainstorming | 1.1.1.1 |  | FS4 | 2012-06-04 08:00 | 2012-06-04 10:00 | 2h | Dirk Pilu;Geert Engelrest | 268.3 | 0 | 0 | 0 | 268.3 | 0.083333
4 | Project team definition | 1.1.1.2 | 3FS | FS5 | 2012-06-04 10:00 | 2012-06-04 12:00 | 2h | Dirk Pilu;Geert Engelrest | 268.3 | 0 | 0 | 0 | 268.3 | 0.083333
5 | Project Objectives | 1.1.1.3 | 4FS | FS6 | 2012-06-04 13:00 | 2012-06-04 15:00 | 2h | Dirk Pilu;Geert Engelrest | 268.3 | 0 | 0 | 0 | 268.3 | 0.083333
6 | Signed Project Charter | 1.1.1.4 | 5FS | FS8 | 2012-06-04 15:00 | 2012-06-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
7 | Project spec's | 1.1.2 |  |  | 2012-06-04 15:00 | 2012-06-21 15:00 | 13d |  |  | 0 |  |  | 30825.6 | 17
8 | Define calculation model | 1.1.2.1 | 6FS | FS9 | 2012-06-04 15:00 | 2012-06-11 10:00 | 4d 4h | Dirk Pilu;Geert Engelrest;Hubert Lutters;Kristof Himpens;Youri Deweerdt | 10670.4 | 0 | 0 | 0 | 10670.4 | 6.7917
9 | Define dBase structure | 1.1.2.2 | 8FS | FS10 | 2012-06-11 10:00 | 2012-06-15 10:00 | 4d | Dirk Pilu;Geert Engelrest;Hubert Lutters;Kristof Himpens;Youri Deweerdt | 9484.8 | 0 | 0 | 0 | 9484.8 | 4
10 | Define Graphical User Interface | 1.1.2.3 | 9FS | FS11 | 2012-06-15 10:00 | 2012-06-19 10:00 | 2d | Dirk Pilu;Geert Engelrest;Hubert Lutters;Kristof Himpens;Youri Deweerdt | 4742.4 | 0 | 0 | 0 | 4742.4 | 4
11 | Review spec's | 1.1.2.4 | 10FS | FS12 | 2012-06-19 10:00 | 2012-06-20 10:00 | 1d | Dirk Pilu;Geert Engelrest;Hubert Lutters;Kristof Himpens;Youri Deweerdt | 2371.2 | 0 | 0 | 0 | 2371.2 | 1
12 | Update specifications | 1.1.2.5 | 11FS | FS13 | 2012-06-20 10:00 | 2012-06-21 15:00 | 1d 4h | Dirk Pilu;Geert Engelrest;Hubert Lutters;Kristof Himpens;Youri Deweerdt | 3556.8 | 0 | 0 | 0 | 3556.8 | 1.2083
13 | Spec's frozen | 1.1.2.6 | 12FS | FS16;FS20 | 2012-06-21 15:00 | 2012-06-21 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
14 | dBase creation / SetUp | 1.1.3 |  |  | 2012-06-21 15:00 | 2012-07-10 15:00 | 13d |  |  | 0 |  |  | 9282.8 | 19
15 | Maintenance cost | 1.1.3.1 |  |  | 2012-06-21 15:00 | 2012-06-28 15:00 | 5d |  |  | 0 |  |  | 2018 | 7
16 | HWL - spares | 1.1.3.1.1 | 13FS | FS17;FS18 | 2012-06-21 15:00 | 2012-06-25 15:00 | 2d | Hubert Lutters | 807.2 | 0 | 0 | 0 | 807.2 | 4
17 | TMS - Hours | 1.1.3.1.2 | 16FS | FS18 | 2012-06-25 15:00 | 2012-06-28 15:00 | 3d | Hubert Lutters | 1210.8 | 0 | 0 | 0 | 1210.8 | 3
18 | Maintenance cost | 1.1.3.1.3 | 17FS;16FS | FS30;FS32 | 2012-06-28 15:00 | 2012-06-28 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
19 | Improvement cost | 1.1.3.2 |  |  | 2012-06-21 15:00 | 2012-06-29 15:00 | 6d |  |  | 0 |  |  | 2421.6 | 8
20 | SPAR - spares | 1.1.3.2.1 | 13FS | FS21 | 2012-06-21 15:00 | 2012-06-25 15:00 | 2d | Kristof Himpens | 807.2 | 0 | 0 | 0 | 807.2 | 4
21 | SPAR - Hours toolshop | 1.1.3.2.2 | 20FS | FS22 | 2012-06-25 15:00 | 2012-06-27 15:00 | 2d | Kristof Himpens | 807.2 | 0 | 0 | 0 | 807.2 | 2
22 | SPAR - Hours design | 1.1.3.2.3 | 21FS | FS23 | 2012-06-27 15:00 | 2012-06-29 15:00 | 2d | Kristof Himpens | 807.2 | 0 | 0 | 0 | 807.2 | 2
23 | Improvement cost | 1.1.3.2.4 | 22FS | FS25;FS32 | 2012-06-29 15:00 | 2012-06-29 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
24 | COPQ linked | 1.1.3.3 |  |  | 2012-06-29 15:00 | 2012-07-10 15:00 | 7d |  |  | 0 |  |  | 2825.2 | 11
25 | Production scrap (confirmed / unconfirmed) | 1.1.3.3.1 | 23FS | FS26 | 2012-06-29 15:00 | 2012-07-04 15:00 | 3d | Kristof Himpens | 1210.8 | 0 | 0 | 0 | 1210.8 | 5
26 | Inventory scrap | 1.1.3.3.2 | 25FS | FS27 | 2012-07-04 15:00 | 2012-07-06 15:00 | 2d | Kristof Himpens | 807.2 | 0 | 0 | 0 | 807.2 | 2
27 | Sorting (intern / extern) | 1.1.3.3.3 | 26FS | FS28 | 2012-07-06 15:00 | 2012-07-10 15:00 | 2d | Kristof Himpens | 807.2 | 0 | 0 | 0 | 807.2 | 4
28 | COPQ | 1.1.3.3.4 | 27FS | FS32 | 2012-07-10 15:00 | 2012-07-10 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
29 | Operational losses linked | 1.1.3.4 |  |  | 2012-06-28 15:00 | 2012-07-05 15:00 | 5d |  |  | 0 |  |  | 2018 | 7
30 | Support hours, Lost capacity | 1.1.3.4.1 | 18FS | FS31 | 2012-06-28 15:00 | 2012-07-05 15:00 | 5d | Hubert Lutters | 2018 | 0 | 0 | 0 | 2018 | 7
31 | Operational losses | 1.1.3.4.2 | 30FS | FS32 | 2012-07-05 15:00 | 2012-07-05 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
32 | dBase frozen | 1.1.3.5 | 18FS;23FS;28FS;31FS | FS34;FS35 | 2012-07-10 15:00 | 2012-07-10 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
33 | dBase functionality / Calculation model - implementation | 1.1.4 |  |  | 2012-07-10 15:00 | 2012-07-24 15:00 | 10d |  |  | 0 |  |  | 8072 | 14
34 | Calculation function | 1.1.4.1 | 32FS | FS36 | 2012-07-10 15:00 | 2012-07-17 15:00 | 5d | Hubert Lutters;Kristof Himpens | 4036 | 0 | 0 | 0 | 4036 | 7
35 | Analyze / export function | 1.1.4.2 | 32FS | FS36 | 2012-07-10 15:00 | 2012-07-17 15:00 | 5d | Hubert Lutters;Kristof Himpens | 4036 | 0 | 0 | 0 | 4036 | 7
36 | Functionality implemented | 1.1.4.3 | 35FS;34FS | FS38 | 2012-07-24 15:00 | 2012-07-24 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
37 | Evaluation - Update | 1.1.5 |  |  | 2012-07-24 15:00 | 2012-08-03 15:00 | 8d |  |  | 0 |  |  | 12713.6 | 10
38 | Calculation-Analyze verification | 1.1.5.1 | 36FS | FS39 | 2012-07-24 15:00 | 2012-07-30 15:00 | 4d | Dirk Pilu;Geert Engelrest;Hubert Lutters;Kristof Himpens;Youri Deweerdt | 9484.8 | 0 | 0 | 0 | 9484.8 | 6
39 | Update | 1.1.5.2 | 38FS | FS40 | 2012-07-30 15:00 | 2012-08-03 15:00 | 4d | Kristof Himpens;Hubert Lutters | 3228.8 | 0 | 0 | 0 | 3228.8 | 4
40 | Release | 1.1.5.3 | 39FS |  | 2012-08-03 15:00 | 2012-08-03 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Dirk Pilu | Renewable | 1 | 0 | 72.8 | 3;4;5;8;9;10;11;12;38; | 10337.5996
2 | Geert Engelrest | Renewable | 1 | 0 | 61.35 | 3;4;5;8;9;10;11;12;38; | 8711.6992
3 | Hubert Lutters | Renewable | 1 | 0 | 50.45 | 8;9;10;11;12;16;17;30;34;35;38;39; | 16547.6016
4 | Kristof Himpens | Renewable | 1 | 0 | 50.45 | 8;9;10;11;12;20;21;22;25;26;27;34;35;38;39; | 17758.4023
5 | Youri Deweerdt | Renewable | 1 | 0 | 61.35 | 8;9;10;11;12;38; | 8343.5996

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Manufacturing Tool Cost Module | 358h |  |  |  |  | 99 | 100 | 101
1 | Manufacturing Tool Cost Module | 358h |  |  |  |  | 99 | 100 | 101
2 | Kick-Off | 6h |  |  |  |  | 99 | 100 | 101
3 | Kick-Off meeting & brainstorming | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Project team definition | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Project Objectives | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Signed Project Charter | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Project spec's | 104h |  |  |  |  | 99 | 100 | 101
8 | Define calculation model | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Define dBase structure | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Define Graphical User Interface | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Review spec's | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Update specifications | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Spec's frozen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | dBase creation / SetUp | 104h |  |  |  |  | 99 | 100 | 101
15 | Maintenance cost | 40h |  |  |  |  | 99 | 100 | 101
16 | HWL - spares | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | TMS - Hours | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Maintenance cost | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Improvement cost | 48h |  |  |  |  | 99 | 100 | 101
20 | SPAR - spares | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | SPAR - Hours toolshop | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | SPAR - Hours design | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Improvement cost | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | COPQ linked | 56h |  |  |  |  | 99 | 100 | 101
25 | Production scrap (confirmed / unconfirmed) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Inventory scrap | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Sorting (intern / extern) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | COPQ | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Operational losses linked | 40h |  |  |  |  | 99 | 100 | 101
30 | Support hours, Lost capacity | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Operational losses | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | dBase frozen | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | dBase functionality / Calculation model - implementation | 80h |  |  |  |  | 99 | 100 | 101
34 | Calculation function | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Analyze / export function | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Functionality implemented | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Evaluation - Update | 64h |  |  |  |  | 99 | 100 | 101
38 | Calculation-Analyze verification | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Update | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Release | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold