## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Digipolis Talent Management Suite | 1 |  |  | 2012-08-15 08:00 | 2013-03-28 17:00 | 162d |  |  | 0 |  |  | 4899912 | 225.375
1 | Digipolis TMS (comp proj) | 1.1 |  |  | 2012-08-15 08:00 | 2013-03-28 17:00 | 162d |  |  | 0 |  |  | 4899912 | 225.375
2 | WP1 - Sched, Cal, Takes, Entitlements, Accum, Pos Time | 1.1.1 |  |  | 2012-08-15 08:00 | 2013-03-28 17:00 | 162d |  |  | 0 |  |  | 4729572 | 225.375
3 | WP1_Extension | 1.1.1.1 |  |  | 2012-08-15 08:00 | 2013-03-28 17:00 | 162d |  |  | 0 |  |  | 4687242 | 225.375
4 | WP1_E-TL-03_Extension TL - Compensatory TimeOff Plans | 1.1.1.1.1 |  |  | 2012-08-15 08:00 | 2013-03-28 17:00 | 162d |  |  | 0 |  |  | 4676112 | 225.375
5 | PS_WP1_E-TL-03_TD | 1.1.1.1.1.1 |  | FS6;FS10 | 2012-08-15 08:00 | 2012-08-30 11:00 | 11d 3h | Employee | 2730 | 0 | 0 | 0 | 2730 | 15.125
6 | PS_WP1_E-TL-03_Code | 1.1.1.1.1.2 | 5FS | FS7;FS11 | 2012-10-08 10:00 | 2012-10-23 14:00 | 11d 3h | Employee | 2730 | 0 | 0 | 0 | 2730 | 15.1667
7 | PS_WP1_E-TL-03_UTP | 1.1.1.1.1.3 | 6FS | FS8;FS9;FS12 | 2012-11-29 14:00 | 2012-12-06 09:00 | 4d 4h | Employee | 1080 | 0 | 0 | 0 | 1080 | 6.7917
8 | PS_WP1_E-TL-03_UTE | 1.1.1.1.1.4 | 7FS | FS13 | 2013-01-23 11:00 | 2013-01-30 14:00 | 5d 2h | Employee | 1260 | 0 | 111111 | 4666662 | 4667922 | 7.125
9 | PS_WP1_E-TL-03_UTE | 1.1.1.1.1.5 | 7FS | FS13 | 2013-01-23 10:00 | 2013-01-30 12:00 | 5d 2h | Employee | 1260 | 0 | 0 | 0 | 1260 | 7.0833
10 | PS_WP1_E-TL-03_TD_CHR00025 | 1.1.1.1.1.6 | 5FS |  | 2013-03-28 11:00 | 2013-03-28 16:00 | 4h | Employee | 120 | 0 | 0 | 0 | 120 | 0.20833
11 | PS_WP1_E-TL-03_Code_CHR00025 | 1.1.1.1.1.7 | 6FS |  | 2013-03-28 10:00 | 2013-03-28 15:00 | 4h | Employee | 120 | 0 | 0 | 0 | 120 | 0.20833
12 | PS_WP1_E-TL-03_UTP_CHR00025 | 1.1.1.1.1.8 | 7FS |  | 2013-03-28 15:00 | 2013-03-28 17:00 | 2h | Employee | 60 | 0 | 0 | 0 | 60 | 0.083333
13 | PS_WP1_E-TL-03_UTE_CHR00025 | 1.1.1.1.1.9 | 8FS;9FS |  | 2013-03-28 11:00 | 2013-03-28 15:00 | 3h | Employee | 90 | 0 | 0 | 0 | 90 | 0.16667
14 | WP1_E-TL-06_Extension - TL - Handling Recovery Time | 1.1.1.1.2 |  |  | 2013-01-04 09:00 | 2013-03-20 16:00 | 53d 6h |  |  | 0 |  |  | 1710 | 75.2917
15 | PS_WP1_E-TL-06_TD | 1.1.1.1.2.1 |  | FS16 | 2013-01-04 09:00 | 2013-01-08 10:00 | 2d 1h | Employee | 510 | 0 | 0 | 0 | 510 | 4.0417
16 | PS_WP1_E-TL-06_Code | 1.1.1.1.2.2 | 15FS | FS17 | 2013-02-07 14:00 | 2013-02-11 15:00 | 2d 1h | Employee | 510 | 0 | 0 | 0 | 510 | 4.0417
17 | PS_WP1_E-TL-06_UTP | 1.1.1.1.2.3 | 16FS | FS18 | 2013-03-07 13:00 | 2013-03-08 11:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.91667
18 | PS_WP1_E-TL-06_UTE | 1.1.1.1.2.4 | 17FS |  | 2013-03-18 16:00 | 2013-03-20 16:00 | 2d | Employee | 480 | 0 | 0 | 0 | 480 | 2
19 | WP1_E-TL-09_Extension - TL - Manage Schedules | 1.1.1.1.3 |  |  | 2012-10-26 08:00 | 2013-03-13 09:00 | 98d 1h |  |  | 0 |  |  | 4620 | 138.0417
20 | PS_WP1_E-TL-09_TD | 1.1.1.1.3.1 |  | FS21 | 2012-10-26 08:00 | 2012-11-02 15:00 | 5d 6h | Employee | 1380 | 0 | 0 | 0 | 1380 | 7.2917
21 | PS_WP1_E-TL-09_Code | 1.1.1.1.3.2 | 20FS | FS22 | 2012-11-26 08:00 | 2012-12-03 15:00 | 5d 6h | Employee | 1380 | 0 | 0 | 0 | 1380 | 7.2917
22 | PS_WP1_E-TL-09_UTP | 1.1.1.1.3.3 | 21FS | FS23;FS24 | 2013-02-05 11:00 | 2013-02-07 14:00 | 2d 2h | Employee | 540 | 0 | 0 | 0 | 540 | 2.125
23 | PS_WP1_E-TL-09_UTE | 1.1.1.1.3.4 | 22FS |  | 2013-03-08 08:00 | 2013-03-12 15:00 | 2d 6h | Employee | 660 | 0 | 0 | 0 | 660 | 4.2917
24 | PS_WP1_E-TL-09_UTE | 1.1.1.1.3.5 | 22FS |  | 2013-03-08 11:00 | 2013-03-13 09:00 | 2d 6h | Employee | 660 | 0 | 0 | 0 | 660 | 4.9167
25 | WP1_E-TL-14, E-TL-08_Extension - TL - Recovery Type Indicator/Extension - TL - Inconvenient Hours Eligibility | 1.1.1.1.4 |  |  | 2013-03-04 11:00 | 2013-03-28 17:00 | 18d 5h |  |  | 0 |  |  | 810 | 24.25
26 | PS_WP1_E-TL-14_TD | 1.1.1.1.4.1 |  | FS27;FS30 | 2013-03-04 11:00 | 2013-03-05 10:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.95833
27 | PS_WP1_E-TL-14_Code | 1.1.1.1.4.2 | 26FS | FS28;FS31 | 2013-03-15 16:00 | 2013-03-18 15:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 2.9583
28 | PS_WP1_E-TL-14_UTP | 1.1.1.1.4.3 | 27FS | FS29;FS32 | 2013-03-25 13:00 | 2013-03-25 16:00 | 3h | Employee | 90 | 0 | 0 | 0 | 90 | 0.125
29 | PS_WP1_E-TL-14_UTE | 1.1.1.1.4.4 | 28FS | FS33 | 2013-03-27 11:00 | 2013-03-28 09:00 | 6h | Employee | 180 | 0 | 0 | 0 | 180 | 0.91667
30 | PS_WP1_E-TL-14_TD_CHR00027 | 1.1.1.1.4.5 | 26FS |  | 2013-03-28 16:00 | 2013-03-28 17:00 | 1h | Employee | 30 | 0 | 0 | 0 | 30 | 0.041667
31 | PS_WP1_E-TL-14_Code_CHR00027 | 1.1.1.1.4.6 | 27FS |  | 2013-03-28 15:00 | 2013-03-28 16:00 | 1h | Employee | 30 | 0 | 0 | 0 | 30 | 0.041667
32 | PS_WP1_E-TL-14_UTP_CHR00027 | 1.1.1.1.4.7 | 28FS |  | 2013-03-28 16:00 | 2013-03-28 17:00 | 1h | Employee | 30 | 0 | 0 | 0 | 30 | 0.041667
33 | PS_WP1_E-TL-14_UTE_CHR00027 | 1.1.1.1.4.8 | 29FS |  | 2013-03-28 16:00 | 2013-03-28 17:00 | 1h | Employee | 30 | 0 | 0 | 0 | 30 | 0.041667
34 | WP1_E-TL-17_Extension - TL - Warning for Shifts | 1.1.1.1.5 |  |  | 2012-12-07 09:00 | 2013-03-15 14:00 | 70d 4h |  |  | 0 |  |  | 2190 | 98.2083
35 | PS_WP1_E-TL-17_TD | 1.1.1.1.5.1 |  | FS36 | 2012-12-07 09:00 | 2012-12-11 16:00 | 2d 6h | Employee | 660 | 0 | 0 | 0 | 660 | 4.2917
36 | PS_WP1_E-TL-17_Code | 1.1.1.1.5.2 | 35FS | FS37 | 2013-01-17 10:00 | 2013-01-21 17:00 | 2d 6h | Employee | 660 | 0 | 0 | 0 | 660 | 4.2917
37 | PS_WP1_E-TL-17_UTP | 1.1.1.1.5.3 | 36FS | FS38 | 2013-02-25 15:00 | 2013-02-26 16:00 | 1d 1h | Employee | 270 | 0 | 0 | 0 | 270 | 1.0417
38 | PS_WP1_E-TL-17_UTE | 1.1.1.1.5.4 | 37FS |  | 2013-03-13 09:00 | 2013-03-15 14:00 | 2d 4h | Employee | 600 | 0 | 0 | 0 | 600 | 2.2083
39 | WP1_E-AM-05_Extension - AM - Klein Verlet | 1.1.1.1.6 |  |  | 2012-12-27 10:00 | 2013-03-19 17:00 | 58d 6h |  |  | 0 |  |  | 1800 | 82.2917
40 | PS_WP1_E-AM-05_TD | 1.1.1.1.6.1 |  | FS41 | 2012-12-27 10:00 | 2012-12-31 12:00 | 2d 2h | Employee | 540 | 0 | 0 | 0 | 540 | 4.0833
41 | PS_WP1_E-AM-05_Code | 1.1.1.1.6.2 | 40FS | FS42 | 2013-01-31 16:00 | 2013-02-05 09:00 | 2d 2h | Employee | 540 | 0 | 0 | 0 | 540 | 4.7083
42 | PS_WP1_E-AM-05_UTP | 1.1.1.1.6.3 | 41FS | FS43 | 2013-03-07 09:00 | 2013-03-07 17:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.33333
43 | PS_WP1_E-AM-05_UTE | 1.1.1.1.6.4 | 42FS |  | 2013-03-15 16:00 | 2013-03-19 17:00 | 2d 1h | Employee | 510 | 0 | 0 | 0 | 510 | 4.0417
44 | WP1_Extended_Config | 1.1.1.2 |  |  | 2012-08-15 08:00 | 2013-03-27 12:00 | 160d 4h |  |  | 0 |  |  | 28320 | 224.1667
45 | WP1_EC-AM-04_Ext Config - AM - Educational Leave | 1.1.1.2.1 |  |  | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  |  | 0 |  |  | 0 | -0.625
46 | PS_WP1_EC-AM-04_TD | 1.1.1.2.1.1 |  | FS47 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
47 | PS_WP1_EC-AM-04_Code | 1.1.1.2.1.2 | 46FS | FS48 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
48 | PS_WP1_EC-AM-04_UTP | 1.1.1.2.1.3 | 47FS | FS49 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
49 | PS_WP1_EC-AM-04_UTE | 1.1.1.2.1.4 | 48FS |  | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
50 | WP1_EC-AM-09_Ext Config - AM - Leave Without Pay | 1.1.1.2.2 |  |  | 2012-08-15 08:00 | 2013-03-27 12:00 | 160d 4h |  |  | 0 |  |  | 240 | 224.1667
51 | PS_WP1_EC-AM-09_TD | 1.1.1.2.2.1 |  | FS52 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
52 | PS_WP1_EC-AM-09_Code | 1.1.1.2.2.2 | 51FS | FS53 | 2012-08-15 09:00 | 2012-08-15 09:00 | 0 |  | 0 | 0 | 0 | 0 | 0
53 | PS_WP1_EC-AM-09_UTP | 1.1.1.2.2.3 | 52FS | FS54 | 2013-03-26 13:00 | 2013-03-27 12:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 0.95833
54 | PS_WP1_EC-AM-09_UTE | 1.1.1.2.2.4 | 53FS |  | 2013-03-27 12:00 | 2013-03-27 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
55 | WP1_EC-AM-19_Ext Config - AM - Unemployment/Retirement | 1.1.1.2.3 |  |  | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  |  | 0 |  |  | 0 | 0.375
56 | PS_WP1_EC-AM-19_TD | 1.1.1.2.3.1 |  | FS57 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
57 | PS_WP1_EC-AM-19_Code | 1.1.1.2.3.2 | 56FS | FS58 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
58 | PS_WP1_EC-AM-19_UTP | 1.1.1.2.3.3 | 57FS | FS59 | 2012-08-15 08:00 | 2012-08-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
59 | PS_WP1_EC-AM-19_UTE | 1.1.1.2.3.4 | 58FS |  | 2012-08-15 17:00 | 2012-08-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
60 | WP1_EC-AM-14_Ext Config - AM - Strike | 1.1.1.2.4 |  |  | 2013-02-18 09:00 | 2013-03-27 11:00 | 27d 2h |  |  | 0 |  |  | 960 | 37.0833
61 | PS_WP1_EC-AM-14_TD | 1.1.1.2.4.1 |  | FS62 | 2013-02-18 09:00 | 2013-02-19 09:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 1
62 | PS_WP1_EC-AM-14_Code | 1.1.1.2.4.2 | 61FS | FS63 | 2013-03-05 10:00 | 2013-03-06 10:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 1
63 | PS_WP1_EC-AM-14_UTP | 1.1.1.2.4.3 | 62FS | FS64 | 2013-03-20 11:00 | 2013-03-21 11:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 1
64 | PS_WP1_EC-AM-14_UTE | 1.1.1.2.4.4 | 63FS |  | 2013-03-26 11:00 | 2013-03-27 11:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 1
65 | WP1_EC-TL-04_Ext Config - TL - Rules | 1.1.1.2.5 |  |  | 2012-09-06 09:00 | 2013-03-25 17:00 | 142d 7h |  |  | 0 |  |  | 27120 | 200.3333
66 | PS_WP1_EC-TL-04_TD | 1.1.1.2.5.1 |  | FS70 | 2012-09-06 09:00 | 2012-09-19 10:00 | 9d 1h | Employee | 2190 | 0 | 0 | 0 | 2190 | 13.0417
67 | PS_WP1_EC-TL-04_TD | 1.1.1.2.5.2 |  | FS71 | 2012-09-07 10:00 | 2012-09-20 11:00 | 9d 1h | Employee | 2190 | 0 | 0 | 0 | 2190 | 13.0417
68 | PS_WP1_EC-TL-04_TD | 1.1.1.2.5.3 |  | FS72 | 2012-09-14 10:00 | 2012-09-27 11:00 | 9d 1h | Employee | 2190 | 0 | 0 | 0 | 2190 | 13.0417
69 | PS_WP1_EC-TL-04_TD | 1.1.1.2.5.4 |  | FS73 | 2012-10-30 10:00 | 2012-11-06 10:00 | 5d | Employee | 1200 | 0 | 0 | 0 | 1200 | 7
70 | PS_WP1_EC-TL-04_Code | 1.1.1.2.5.5 | 66FS | FS74 | 2012-09-28 08:00 | 2012-10-11 09:00 | 9d 1h | Employee | 2190 | 0 | 0 | 0 | 2190 | 13.0417
71 | PS_WP1_EC-TL-04_Code | 1.1.1.2.5.6 | 67FS | FS75 | 2012-10-01 14:00 | 2012-10-12 15:00 | 9d 1h | Employee | 2190 | 0 | 0 | 0 | 2190 | 11.0417
72 | PS_WP1_EC-TL-04_Code | 1.1.1.2.5.7 | 68FS | FS76 | 2012-10-08 11:00 | 2012-10-19 12:00 | 9d 1h | Employee | 2190 | 0 | 0 | 0 | 2190 | 11.0417
73 | PS_WP1_EC-TL-04_Code | 1.1.1.2.5.8 | 69FS | FS77 | 2012-11-22 14:00 | 2012-11-29 14:00 | 5d | Employee | 1200 | 0 | 0 | 0 | 1200 | 7
74 | PS_WP1_EC-TL-04_UTP | 1.1.1.2.5.9 | 70FS | FS78 | 2012-11-16 15:00 | 2012-11-22 12:00 | 3d 6h | Employee | 900 | 0 | 0 | 0 | 900 | 5.875
75 | PS_WP1_EC-TL-04_UTP | 1.1.1.2.5.10 | 71FS | FS79 | 2012-11-16 16:00 | 2012-11-22 14:00 | 3d 6h | Employee | 900 | 0 | 0 | 0 | 900 | 5.9167
76 | PS_WP1_EC-TL-04_UTP | 1.1.1.2.5.11 | 72FS | FS80 | 2012-11-20 10:00 | 2012-11-23 17:00 | 3d 6h | Employee | 900 | 0 | 0 | 0 | 900 | 3.2917
77 | PS_WP1_EC-TL-04_UTP | 1.1.1.2.5.12 | 73FS | FS81 | 2013-01-18 14:00 | 2013-01-22 11:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 3.875
78 | PS_WP1_EC-TL-04_UTE | 1.1.1.2.5.13 | 74FS |  | 2012-12-12 15:00 | 2012-12-25 11:00 | 8d 5h | Employee | 2070 | 0 | 0 | 0 | 2070 | 12.8333
79 | PS_WP1_EC-TL-04_UTE | 1.1.1.2.5.14 | 75FS |  | 2012-12-14 13:00 | 2012-12-27 09:00 | 8d 5h | Employee | 2070 | 0 | 0 | 0 | 2070 | 12.8333
80 | PS_WP1_EC-TL-04_UTE | 1.1.1.2.5.15 | 76FS |  | 2012-12-14 14:00 | 2012-12-27 10:00 | 8d 5h | Employee | 2070 | 0 | 0 | 0 | 2070 | 12.8333
81 | PS_WP1_EC-TL-04_UTE | 1.1.1.2.5.16 | 77FS |  | 2013-02-11 15:00 | 2013-02-18 09:00 | 4d 3h | Employee | 1050 | 0 | 0 | 0 | 1050 | 6.75
82 | WP1_EC-TL-04_Ext Config - TL - Rules - CHR00046 | 1.1.1.2.5.17 |  |  | 2013-02-06 11:00 | 2013-03-25 17:00 | 33d 5h |  |  | 0 |  |  | 1200 | 47.25
83 | PS_WP1_EC-TL-04_CHR00046_Code | 1.1.1.2.5.17.1 |  | FS84 | 2013-02-06 11:00 | 2013-02-11 11:00 | 3d | Employee | 720 | 0 | 0 | 0 | 720 | 5
84 | PS_WP1_EC-TL-04_CHR00046_UTP | 1.1.1.2.5.17.2 | 83FS | FS85 | 2013-03-19 09:00 | 2013-03-19 15:00 | 5h | Employee | 150 | 0 | 0 | 0 | 150 | 0.25
85 | PS_WP1_EC-TL-04_CHR00046_UTE | 1.1.1.2.5.17.3 | 84FS |  | 2013-03-22 14:00 | 2013-03-25 17:00 | 1d 3h | Employee | 330 | 0 | 0 | 0 | 330 | 3.125
86 | WP1_EC-AM-05_Ext Config - AM - Klein Verlet | 1.1.1.2.6 |  |  | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  |  | 0 |  |  | 0 | -0.625
87 | PS_WP1_EC-AM-05_TD | 1.1.1.2.6.1 |  | FS88 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
88 | PS_WP1_EC-AM-05_Code | 1.1.1.2.6.2 | 87FS | FS89 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
89 | PS_WP1_EC-AM-05_UTP | 1.1.1.2.6.3 | 88FS | FS90 | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
90 | PS_WP1_EC-AM-05_UTE | 1.1.1.2.6.4 | 89FS |  | 2012-08-15 08:00 | 2012-08-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
91 | WP1_Extended_Config_ONSHORE | 1.1.1.3 |  |  | 2012-10-12 15:00 | 2013-03-28 17:00 | 119d 2h |  |  | 0 |  |  | 14010 | 167.0833
92 | WP1_EC-AM-13_Ext Config - AM - Retirement Preparation | 1.1.1.3.1 |  |  | 2013-03-20 14:00 | 2013-03-28 16:00 | 6d 2h |  |  | 0 |  |  | 450 | 8.0833
93 | PS_WP1_EC-AM-13_TD/Code | 1.1.1.3.1.1 |  | FS94 | 2013-03-20 14:00 | 2013-03-21 15:00 | 1d 1h | Employee | 270 | 0 | 0 | 0 | 270 | 1.0417
94 | PS_WP1_EC-AM-13_UTP | 1.1.1.3.1.2 | 93FS | FS95 | 2013-03-28 09:00 | 2013-03-28 11:00 | 2h | Employee | 60 | 0 | 0 | 0 | 60 | 0.083333
95 | PS_WP1_EC-AM-13_UTE | 1.1.1.3.1.3 | 94FS |  | 2013-03-28 11:00 | 2013-03-28 16:00 | 4h | Employee | 120 | 0 | 0 | 0 | 120 | 0.20833
96 | WP1_EC-AM-16_Ext Config - AM - Thematic Leaves | 1.1.1.3.2 |  |  | 2013-03-20 15:00 | 2013-03-28 17:00 | 6d 2h |  |  | 0 |  |  | 450 | 8.0833
97 | PS_WP1_EC-AM-16_TD/Code | 1.1.1.3.2.1 |  | FS98 | 2013-03-20 15:00 | 2013-03-21 16:00 | 1d 1h | Employee | 270 | 0 | 0 | 0 | 270 | 1.0417
98 | PS_WP1_EC-AM-16_UTP | 1.1.1.3.2.2 | 97FS | FS99 | 2013-03-28 10:00 | 2013-03-28 12:00 | 2h | Employee | 60 | 0 | 0 | 0 | 60 | 0.083333
99 | PS_WP1_EC-AM-16_UTE | 1.1.1.3.2.3 | 98FS |  | 2013-03-28 13:00 | 2013-03-28 17:00 | 4h | Employee | 120 | 0 | 0 | 0 | 120 | 0.16667
100 | WP1_EC-AM-07_Ext Config - AM - Late/No Show | 1.1.1.3.3 |  |  | 2013-02-18 11:00 | 2013-03-27 11:00 | 27d |  |  | 0 |  |  | 960 | 37
101 | PS_WP1_EC-AM-07_TD/Code | 1.1.1.3.3.1 |  | FS102 | 2013-02-18 11:00 | 2013-02-20 15:00 | 2d 3h | Employee | 570 | 0 | 0 | 0 | 570 | 2.1667
102 | PS_WP1_EC-AM-07_UTP | 1.1.1.3.3.2 | 101FS | FS103 | 2013-03-21 16:00 | 2013-03-22 11:00 | 4h | Employee | 120 | 0 | 0 | 0 | 120 | 0.79167
103 | PS_WP1_EC-AM-07_UTE | 1.1.1.3.3.3 | 102FS |  | 2013-03-26 10:00 | 2013-03-27 11:00 | 1d 1h | Employee | 270 | 0 | 0 | 0 | 270 | 1.0417
104 | WP1_EC-AM-12_Ext Config - AM - Pregnancy Leave | 1.1.1.3.4 |  |  | 2013-02-06 14:00 | 2013-03-26 12:00 | 33d 7h |  |  | 0 |  |  | 1200 | 47.9167
105 | PS_WP1_EC-AM-12_TD/Code | 1.1.1.3.4.1 |  | FS106 | 2013-02-06 14:00 | 2013-02-11 14:00 | 3d | Employee | 720 | 0 | 0 | 0 | 720 | 5
106 | PS_WP1_EC-AM-12_UTP | 1.1.1.3.4.2 | 105FS | FS107 | 2013-03-20 08:00 | 2013-03-20 14:00 | 5h | Employee | 150 | 0 | 0 | 0 | 150 | 0.25
107 | PS_WP1_EC-AM-12_UTE | 1.1.1.3.4.3 | 106FS |  | 2013-03-25 09:00 | 2013-03-26 12:00 | 1d 3h | Employee | 330 | 0 | 0 | 0 | 330 | 1.125
108 | WP1_EC-AM-17_Ext Config - AM - Time Credit | 1.1.1.3.5 |  |  | 2013-01-14 14:00 | 2013-03-28 10:00 | 52d 5h |  |  | 0 |  |  | 2310 | 72.8333
109 | PS_WP1_EC-AM-17_TD/Code | 1.1.1.3.5.1 |  | FS110 | 2013-03-04 16:00 | 2013-03-06 14:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.9167
110 | PS_WP1_EC-AM-17_UTP | 1.1.1.3.5.2 | 109FS | FS111 | 2013-03-26 08:00 | 2013-03-26 11:00 | 3h | Employee | 90 | 0 | 0 | 0 | 90 | 0.125
111 | PS_WP1_EC-AM-17_UTE | 1.1.1.3.5.3 | 110FS |  | 2013-03-27 11:00 | 2013-03-28 10:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.95833
112 | WP1_EC-AM-01_Ext Config - AM - Annual Leave - CHR00007 | 1.1.1.3.5.4 |  |  | 2013-01-14 14:00 | 2013-03-22 14:00 | 49d |  |  | 0 |  |  | 1590 | 67
113 | PS_WP1_EC-AM-01_Code_­CHR00007 | 1.1.1.3.5.4.1 |  | FS114 | 2013-01-14 14:00 | 2013-01-18 14:00 | 4d | Employee | 960 | 0 | 0 | 0 | 960 | 4
114 | PS_WP1_EC-AM-01_UTP_CHR00007 | 1.1.1.3.5.4.2 | 113FS | FS115 | 2013-03-08 16:00 | 2013-03-11 14:00 | 6h | Employee | 180 | 0 | 0 | 0 | 180 | 2.9167
115 | PS_WP1_EC-AM-01_UTE_CHR00007 | 1.1.1.3.5.4.3 | 114FS |  | 2013-03-20 15:00 | 2013-03-22 14:00 | 1d 7h | Employee | 450 | 0 | 0 | 0 | 450 | 1.9583
116 | WP1_EC-AM-01_Ext Config - AM - Annual Leave | 1.1.1.3.6 |  |  | 2012-10-12 15:00 | 2013-01-29 17:00 | 77d 2h |  |  | 0 |  |  | 4800 | 109.0833
117 | PS_WP1_EC-AM-01_TD/Code | 1.1.1.3.6.1 |  | FS118 | 2012-10-12 15:00 | 2012-10-30 15:00 | 12d | Employee | 2880 | 0 | 0 | 0 | 2880 | 18
118 | PS_WP1_EC-AM-01_UTP | 1.1.1.3.6.2 | 117FS | FS119 | 2012-12-24 13:00 | 2012-12-26 16:00 | 2d 3h | Employee | 570 | 0 | 0 | 0 | 570 | 2.125
119 | PS_WP1_EC-AM-01_UTE | 1.1.1.3.6.3 | 118FS |  | 2013-01-22 11:00 | 2013-01-29 17:00 | 5d 5h | Employee | 1350 | 0 | 0 | 0 | 1350 | 7.25
120 | WP1_UPDATE SS & Forecasting: Ext Config - AM - Klein Verlet | 1.1.1.3.7 |  |  | 2012-12-20 09:00 | 2013-01-01 09:00 | 8d | Employee | 1920 | 0 | 0 | 0 | 1920 | 12
121 | WP1_UPDATE SS & Forecasting: Ext Config - AM - Leave Without Pay | 1.1.1.3.8 |  |  | 2013-02-06 14:00 | 2013-02-13 14:00 | 5d | Employee | 1200 | 0 | 0 | 0 | 1200 | 7
122 | WP1_UPDATE SS & Forecasting: Ext Config - AM - Educational Leave | 1.1.1.3.9 |  |  | 2013-03-05 10:00 | 2013-03-08 10:00 | 3d | Employee | 720 | 0 | 0 | 0 | 720 | 3
123 | WP2 - ESS, MSS, Approvals, Forecasting | 1.1.2 |  |  | 2012-08-15 08:00 | 2013-03-28 11:00 | 161d 3h |  |  | 0 |  |  | 55530 | 225.125
124 | WP2_Extension | 1.1.2.1 |  |  | 2012-08-15 08:00 | 2013-03-28 11:00 | 161d 3h |  |  | 0 |  |  | 45930 | 225.125
125 | WP2_E-TL-04_Extension - TL - Daily Hours Limit Warning | 1.1.2.1.1 |  |  | 2013-03-06 10:00 | 2013-03-28 11:00 | 16d 1h |  |  | 0 |  |  | 720 | 22.0417
126 | PS_WP2_E-TL-04_TD | 1.1.2.1.1.1 |  | FS127 | 2013-03-06 10:00 | 2013-03-07 09:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.95833
127 | PS_WP2_E-TL-04_Code | 1.1.2.1.1.2 | 126FS | FS128 | 2013-03-15 14:00 | 2013-03-18 12:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 2.9167
128 | PS_WP2_E-TL-04_UTP | 1.1.2.1.1.3 | 127FS | FS129 | 2013-03-25 16:00 | 2013-03-26 10:00 | 3h | Employee | 90 | 0 | 0 | 0 | 90 | 0.75
129 | PS_WP2_E-TL-04_UTE | 1.1.2.1.1.4 | 128FS |  | 2013-03-27 13:00 | 2013-03-28 11:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.91667
130 | WP2_E-TL-15_Extension - TL - Shifts in Work Schedule | 1.1.2.1.2 |  |  | 2013-01-18 14:00 | 2013-03-22 14:00 | 45d |  |  | 0 |  |  | 1440 | 63
131 | PS_WP2_E-TL-15_TD | 1.1.2.1.2.1 |  | FS132 | 2013-01-18 14:00 | 2013-01-22 11:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 3.875
132 | PS_WP2_E-TL-15_Code | 1.1.2.1.2.2 | 131FS | FS133 | 2013-02-13 14:00 | 2013-02-15 11:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.875
133 | PS_WP2_E-TL-15_UTP | 1.1.2.1.2.3 | 132FS | FS134 | 2013-03-14 16:00 | 2013-03-15 14:00 | 6h | Employee | 180 | 0 | 0 | 0 | 180 | 0.91667
134 | PS_WP2_E-TL-15_UTE | 1.1.2.1.2.4 | 133FS |  | 2013-03-20 16:00 | 2013-03-22 14:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.9167
135 | WP2_E-TL-05_Extension - TL - ESS | 1.1.2.1.3 |  |  | 2012-09-20 11:00 | 2013-01-21 12:00 | 87d 1h |  |  | 0 |  |  | 5790 | 123.0417
136 | PS_WP2_E-TL-05_TD | 1.1.2.1.3.1 |  | FS137 | 2012-09-20 11:00 | 2012-10-01 14:00 | 7d 2h | Employee | 1740 | 0 | 0 | 0 | 1740 | 11.125
137 | PS_WP2_E-TL-05_Code | 1.1.2.1.3.2 | 136FS | FS138 | 2012-10-24 13:00 | 2012-11-02 15:00 | 7d 2h | Employee | 1740 | 0 | 0 | 0 | 1740 | 9.0833
138 | PS_WP2_E-TL-05_UTP | 1.1.2.1.3.3 | 137FS | FS139 | 2012-12-04 10:00 | 2012-12-07 09:00 | 2d 7h | Employee | 690 | 0 | 0 | 0 | 690 | 2.9583
139 | PS_WP2_E-TL-05_UTE | 1.1.2.1.3.4 | 138FS |  | 2013-01-10 15:00 | 2013-01-21 12:00 | 6d 6h | Employee | 1620 | 0 | 0 | 0 | 1620 | 10.875
140 | WP2_E-AM-03_Extension - AM - ESS | 1.1.2.1.4 |  |  | 2012-08-15 08:00 | 2013-02-25 09:00 | 138d 1h |  |  | 0 |  |  | 13770 | 194.0417
141 | PS_WP2_E-AM-03_TD | 1.1.2.1.4.1 |  | FS142;FS143;FS144 | 2012-08-15 08:00 | 2012-09-07 10:00 | 17d 2h | Employee | 4140 | 0 | 0 | 0 | 4140 | 23.0833
142 | PS_WP2_E-AM-03_Code | 1.1.2.1.4.2 | 141FS | FS145 | 2012-11-02 15:00 | 2012-11-14 12:00 | 7d 6h | Employee | 1860 | 0 | 0 | 0 | 1860 | 11.875
143 | PS_WP2_E-AM-03_Code | 1.1.2.1.4.3 | 141FS | FS146 | 2012-11-13 15:00 | 2012-11-21 15:00 | 6d | Employee | 1440 | 0 | 0 | 0 | 1440 | 8
144 | PS_WP2_E-AM-03_Code | 1.1.2.1.4.4 | 141FS | FS147 | 2012-12-11 08:00 | 2012-12-14 12:00 | 3d 4h | Employee | 840 | 0 | 0 | 0 | 840 | 3.1667
145 | PS_WP2_E-AM-03_UTP | 1.1.2.1.4.5 | 142FS | FS148 | 2013-01-07 14:00 | 2013-01-10 15:00 | 3d 1h | Employee | 750 | 0 | 0 | 0 | 750 | 3.0417
146 | PS_WP2_E-AM-03_UTP | 1.1.2.1.4.6 | 143FS | FS149 | 2013-01-16 10:00 | 2013-01-18 14:00 | 2d 3h | Employee | 570 | 0 | 0 | 0 | 570 | 2.1667
147 | PS_WP2_E-AM-03_UTP | 1.1.2.1.4.7 | 144FS | FS150;FS151 | 2013-01-30 13:00 | 2013-01-31 16:00 | 1d 3h | Employee | 330 | 0 | 0 | 0 | 330 | 1.125
148 | PS_WP2_E-AM-03_UTE | 1.1.2.1.4.8 | 145FS |  | 2013-02-18 14:00 | 2013-02-22 14:00 | 4d | Employee | 960 | 0 | 0 | 0 | 960 | 4
149 | PS_WP2_E-AM-03_UTE | 1.1.2.1.4.9 | 146FS |  | 2013-02-18 09:00 | 2013-02-22 09:00 | 4d | Employee | 960 | 0 | 0 | 0 | 960 | 4
150 | PS_WP2_E-AM-03_UTE | 1.1.2.1.4.10 | 147FS |  | 2013-02-19 09:00 | 2013-02-25 09:00 | 4d | Employee | 960 | 0 | 0 | 0 | 960 | 6
151 | PS_WP2_E-AM-03_UTE | 1.1.2.1.4.11 | 147FS |  | 2013-02-15 13:00 | 2013-02-21 12:00 | 4d | Employee | 960 | 0 | 0 | 0 | 960 | 5.9583
152 | WP2_E-AM-06_Extension - AM - MSS | 1.1.2.1.5 |  |  | 2012-08-15 08:00 | 2013-03-07 09:00 | 146d 1h |  |  | 0 |  |  | 17130 | 204.0417
153 | PS_WP2_E-AM-06_TD | 1.1.2.1.5.1 |  | FS154;FS159 | 2012-08-15 08:00 | 2012-08-21 10:00 | 4d 2h | Employee | 1020 | 0 | 0 | 0 | 1020 | 6.0833
154 | PS_WP2_E-AM-06_Code | 1.1.2.1.5.2 | 153FS | FS155;FS160 | 2012-08-21 10:00 | 2012-08-27 12:00 | 4d 2h | Employee | 1020 | 0 | 0 | 0 | 1020 | 6.0833
155 | PS_WP2_E-AM-06_UTP | 1.1.2.1.5.3 | 154FS | FS156;FS157;FS161 | 2012-08-27 13:00 | 2012-08-29 10:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.875
156 | PS_WP2_E-AM-06_UTE | 1.1.2.1.5.4 | 155FS | FS162 | 2012-12-06 15:00 | 2012-12-10 15:00 | 2d | Employee | 480 | 0 | 0 | 0 | 480 | 4
157 | PS_WP2_E-AM-06_UTE | 1.1.2.1.5.5 | 155FS | FS162 | 2012-08-29 10:00 | 2012-10-15 12:00 | 33d 2h | Employee | 7980 | 0 | 0 | 0 | 7980 | 47.0833
158 | WP2_E-AM-06_Extension - AM - MSS - CHR00032 | 1.1.2.1.5.6 |  |  | 2012-12-24 15:00 | 2013-03-07 09:00 | 52d 3h |  |  | 0 |  |  | 6210 | 72.75
159 | PS_WP2_E-AM-06_TD_CHR00032 | 1.1.2.1.5.6.1 | 153FS |  | 2012-12-25 11:00 | 2013-01-04 09:00 | 7d 6h | Employee | 1860 | 0 | 0 | 0 | 1860 | 9.9167
160 | PS_WP2_E-AM-06_Code_CHR00032 | 1.1.2.1.5.6.2 | 154FS |  | 2012-12-24 15:00 | 2013-01-03 12:00 | 7d 6h | Employee | 1860 | 0 | 0 | 0 | 1860 | 9.875
161 | PS_WP2_E-AM-06_UTP_CHR00032 | 1.1.2.1.5.6.3 | 155FS |  | 2013-03-04 08:00 | 2013-03-07 09:00 | 3d 1h | Employee | 750 | 0 | 0 | 0 | 750 | 3.0417
162 | PS_WP2_E-AM-06_UTE_CHR00032 | 1.1.2.1.5.6.4 | 156FS;157FS |  | 2013-01-03 13:00 | 2013-01-14 15:00 | 7d 2h | Employee | 1740 | 0 | 0 | 0 | 1740 | 11.0833
163 | WP2_E-TL-11_Extension - TL - Overtime Prerequests | 1.1.2.1.6 |  |  | 2012-10-23 09:00 | 2013-02-18 09:00 | 84d |  |  | 0 |  |  | 4080 | 118
164 | PS_WP2_E-TL-11_TD | 1.1.2.1.6.1 |  | FS165 | 2012-10-23 09:00 | 2012-10-30 10:00 | 5d 1h | Employee | 1230 | 0 | 0 | 0 | 1230 | 7.0417
165 | PS_WP2_E-TL-11_Code | 1.1.2.1.6.2 | 164FS | FS166 | 2012-11-21 15:00 | 2012-11-28 16:00 | 5d 1h | Employee | 1230 | 0 | 0 | 0 | 1230 | 7.0417
166 | PS_WP2_E-TL-11_UTP | 1.1.2.1.6.3 | 165FS | FS167 | 2013-01-14 10:00 | 2013-01-16 10:00 | 2d | Employee | 480 | 0 | 0 | 0 | 480 | 2
167 | PS_WP2_E-TL-11_UTE | 1.1.2.1.6.4 | 166FS |  | 2013-02-11 11:00 | 2013-02-18 09:00 | 4d 6h | Employee | 1140 | 0 | 0 | 0 | 1140 | 6.9167
168 | WP2_E-TL-12_Extension - TL - Overtime Reporting | 1.1.2.1.7 |  |  | 2012-12-06 09:00 | 2013-03-13 09:00 | 69d |  |  | 0 |  |  | 2280 | 97
169 | PS_WP2_E-TL-12_TD | 1.1.2.1.7.1 |  | FS170 | 2012-12-06 09:00 | 2012-12-10 17:00 | 2d 7h | Employee | 690 | 0 | 0 | 0 | 690 | 4.3333
170 | PS_WP2_E-TL-12_Code | 1.1.2.1.7.2 | 169FS | FS171 | 2013-01-14 15:00 | 2013-01-17 14:00 | 2d 7h | Employee | 690 | 0 | 0 | 0 | 690 | 2.9583
171 | PS_WP2_E-TL-12_UTP | 1.1.2.1.7.3 | 170FS | FS172 | 2013-02-22 14:00 | 2013-02-25 15:00 | 1d 1h | Employee | 270 | 0 | 0 | 0 | 270 | 3.0417
172 | PS_WP2_E-TL-12_UTE | 1.1.2.1.7.4 | 171FS |  | 2013-03-08 13:00 | 2013-03-13 09:00 | 2d 5h | Employee | 630 | 0 | 0 | 0 | 630 | 4.8333
173 | WP2_E-AM-04_Extension - AM - Forecasting | 1.1.2.1.8 |  |  | 2013-03-06 14:00 | 2013-03-28 10:00 | 15d 5h |  |  | 0 |  |  | 720 | 21.8333
174 | PS_WP2_E-AM-04_TD | 1.1.2.1.8.1 |  | FS175 | 2013-03-06 14:00 | 2013-03-07 12:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.91667
175 | PS_WP2_E-AM-04_Code | 1.1.2.1.8.2 | 174FS | FS176 | 2013-03-18 08:00 | 2013-03-18 16:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.33333
176 | PS_WP2_E-AM-04_UTP | 1.1.2.1.8.3 | 175FS | FS177 | 2013-03-25 16:00 | 2013-03-26 10:00 | 3h | Employee | 90 | 0 | 0 | 0 | 90 | 0.75
177 | PS_WP2_E-AM-04_UTE | 1.1.2.1.8.4 | 176FS |  | 2013-03-27 11:00 | 2013-03-28 10:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.95833
178 | WP2_Report | 1.1.2.2 |  |  | 2013-01-30 14:00 | 2013-03-25 16:00 | 38d 2h |  |  | 0 |  |  | 1290 | 54.0833
179 | WP2_R-TL-03_Report - TL - Pending Approvals Request | 1.1.2.2.1 |  |  | 2013-01-30 14:00 | 2013-03-25 16:00 | 38d 2h |  |  | 0 |  |  | 1290 | 54.0833
180 | PSWP2_R-TL-03_TD | 1.1.2.2.1.1 |  | FS181 | 2013-01-30 14:00 | 2013-02-01 10:00 | 1d 5h | Employee | 390 | 0 | 0 | 0 | 390 | 1.8333
181 | PSWP2_R-TL-03_Code | 1.1.2.2.1.2 | 180FS | FS182 | 2013-02-22 09:00 | 2013-02-25 15:00 | 1d 5h | Employee | 390 | 0 | 0 | 0 | 390 | 3.25
182 | PSWP2_R-TL-03_UTP | 1.1.2.2.1.3 | 181FS | FS183 | 2013-03-18 13:00 | 2013-03-19 09:00 | 5h | Employee | 150 | 0 | 0 | 0 | 150 | 0.83333
183 | PSWP2_R-TL-03_UTE | 1.1.2.2.1.4 | 182FS |  | 2013-03-22 11:00 | 2013-03-25 16:00 | 1d 4h | Employee | 360 | 0 | 0 | 0 | 360 | 3.2083
184 | WP2_Workflow | 1.1.2.3 |  |  | 2012-10-19 13:00 | 2013-03-19 16:00 | 107d 3h |  |  | 0 |  |  | 7710 | 151.125
185 | WP2_W-AM-01,EC-AM-02_Workflow - AM - Approval Ext Config - AM - Approval | 1.1.2.3.1 |  |  | 2012-10-19 13:00 | 2013-03-15 14:00 | 105d 1h |  |  | 0 |  |  | 5790 | 147.0417
186 | PS_WP2_W-AM-01,EC-AM-02_TD | 1.1.2.3.1.1 |  | FS187;FS188 | 2012-10-19 13:00 | 2012-10-30 15:00 | 7d 2h | Employee | 1740 | 0 | 0 | 0 | 1740 | 11.0833
187 | PS_WP2_W-AM-01,EC-AM-02_Code | 1.1.2.3.1.2 | 186FS | FS189 | 2012-12-03 08:00 | 2012-12-06 15:00 | 3d 6h | Employee | 900 | 0 | 0 | 0 | 900 | 3.2917
188 | PS_WP2_W-AM-01,EC-AM-02_Code | 1.1.2.3.1.3 | 186FS | FS190 | 2013-01-09 15:00 | 2013-01-15 10:00 | 3d 4h | Employee | 840 | 0 | 0 | 0 | 840 | 5.7917
189 | PS_WP2_W-AM-01,EC-AM-02_UTP | 1.1.2.3.1.4 | 187FS | FS191 | 2013-01-17 14:00 | 2013-01-21 14:00 | 2d | Employee | 480 | 0 | 0 | 0 | 480 | 4
190 | PS_WP2_W-AM-01,EC-AM-02_UTP | 1.1.2.3.1.5 | 188FS | FS192 | 2013-02-28 15:00 | 2013-03-01 14:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.95833
191 | PS_WP2_W-AM-01,EC-AM-02_UTE | 1.1.2.3.1.6 | 189FS |  | 2013-02-13 08:00 | 2013-02-19 10:00 | 4d 2h | Employee | 1020 | 0 | 0 | 0 | 1020 | 6.0833
192 | PS_WP2_W-AM-01,EC-AM-02_UTE | 1.1.2.3.1.7 | 190FS |  | 2013-03-13 09:00 | 2013-03-15 14:00 | 2d 4h | Employee | 600 | 0 | 0 | 0 | 600 | 2.2083
193 | WP2_W-TL-01_Workflow - TL - Approval Process Error Notification | 1.1.2.3.2 |  |  | 2012-12-20 11:00 | 2013-03-19 16:00 | 63d 4h |  |  | 0 |  |  | 1920 | 89.2083
194 | PS_WP2_W-TL-01_TD | 1.1.2.3.2.1 |  | FS195 | 2012-12-20 11:00 | 2012-12-24 15:00 | 2d 3h | Employee | 570 | 0 | 0 | 0 | 570 | 4.1667
195 | WP2_W-TL-01_Code | 1.1.2.3.2.2 | 194FS | FS196 | 2013-01-24 15:00 | 2013-01-29 09:00 | 2d 3h | Employee | 570 | 0 | 0 | 0 | 570 | 4.75
196 | WP2_W-TL-01_UTP | 1.1.2.3.2.3 | 195FS | FS197 | 2013-03-01 11:00 | 2013-03-04 11:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 3
197 | WP2_W-TL-01_UTE | 1.1.2.3.2.4 | 196FS |  | 2013-03-15 14:00 | 2013-03-19 16:00 | 2d 2h | Employee | 540 | 0 | 0 | 0 | 540 | 4.0833
198 | WP2_Extended Config_ONSHORE | 1.1.2.4 |  |  | 2013-03-11 16:00 | 2013-03-28 11:00 | 12d 4h |  |  | 0 |  |  | 600 | 16.7917
199 | WP2_EC-AM-03 - Ext Config - AM - Collisions | 1.1.2.4.1 |  |  | 2013-03-11 16:00 | 2013-03-28 11:00 | 12d 4h |  |  | 0 |  |  | 600 | 16.7917
200 | PS_WP2_EC-AM-03_TD/Code | 1.1.2.4.1.1 |  | FS201 | 2013-03-11 16:00 | 2013-03-13 11:00 | 1d 4h | Employee | 360 | 0 | 0 | 0 | 360 | 1.7917
201 | PS_WP2_EC-AM-03_UTP | 1.1.2.4.1.2 | 200FS | FS202 | 2013-03-27 11:00 | 2013-03-27 14:00 | 2h | Employee | 60 | 0 | 0 | 0 | 60 | 0.125
202 | PS_WP2_EC-AM-03_UTE | 1.1.2.4.1.3 | 201FS |  | 2013-03-27 14:00 | 2013-03-28 11:00 | 6h | Employee | 180 | 0 | 0 | 0 | 180 | 0.875
203 | WP3 - Annual Leave Processing & BackOffice | 1.1.3 |  |  | 2012-10-19 08:00 | 2013-03-11 16:00 | 101d 7h |  |  | 0 |  |  | 19290 | 143.3333
204 | WP3_Extension | 1.1.3.1 |  |  | 2012-10-19 08:00 | 2013-03-11 16:00 | 101d 7h |  |  | 0 |  |  | 15960 | 143.3333
205 | WP3_E-AM-01_ Extension - AM - Annual Leave Processing | 1.1.3.1.1 |  |  | 2012-10-23 14:00 | 2013-02-18 11:00 | 83d 6h |  |  | 0 |  |  | 4080 | 117.875
206 | PS_WP3_E-AM-01_TD | 1.1.3.1.1.1 |  | FS207 | 2012-10-23 14:00 | 2012-10-30 15:00 | 5d 1h | Employee | 1230 | 0 | 0 | 0 | 1230 | 7.0417
207 | PS_WP3_E-AM-01_Code | 1.1.3.1.1.2 | 206FS | FS208 | 2012-11-20 14:00 | 2012-11-27 15:00 | 5d 1h | Employee | 1230 | 0 | 0 | 0 | 1230 | 7.0417
208 | PS_WP3_E-AM-01_UTP | 1.1.3.1.1.3 | 207FS | FS209 | 2013-01-10 14:00 | 2013-01-14 14:00 | 2d | Employee | 480 | 0 | 0 | 0 | 480 | 4
209 | PS_WP3_E-AM-01_UTE | 1.1.3.1.1.4 | 208FS |  | 2013-02-11 14:00 | 2013-02-18 11:00 | 4d 6h | Employee | 1140 | 0 | 0 | 0 | 1140 | 6.875
210 | WP3_E-AM-02_Extension - AM - Back Office | 1.1.3.1.2 |  |  | 2012-10-19 08:00 | 2013-03-11 16:00 | 101d 7h |  |  | 0 |  |  | 8790 | 143.3333
211 | PS_WP3_E-AM-02_TD | 1.1.3.1.2.1 |  | FS212;FS216 | 2012-10-19 08:00 | 2012-10-24 12:00 | 3d 4h | Employee | 840 | 0 | 0 | 0 | 840 | 5.1667
212 | PS_WP3_E-AM-02_Code | 1.1.3.1.2.2 | 211FS | FS213;FS217 | 2012-10-30 15:00 | 2012-11-05 10:00 | 3d 4h | Employee | 840 | 0 | 0 | 0 | 840 | 5.7917
213 | PS_WP3_E-AM-02_UTP | 1.1.3.1.2.3 | 212FS | FS214;FS218 | 2012-11-22 13:00 | 2012-11-23 16:00 | 1d 3h | Employee | 330 | 0 | 0 | 0 | 330 | 1.125
214 | PS_WP3_E-AM-02_UTE | 1.1.3.1.2.4 | 213FS | FS219 | 2012-11-27 15:00 | 2012-11-30 17:00 | 3d 2h | Employee | 780 | 0 | 0 | 0 | 780 | 3.0833
215 | WP3_E-AM-02_Extension - AM - Back Office - CHR00002, CHR00033 | 1.1.3.1.2.5 |  |  | 2012-12-27 09:00 | 2013-03-11 16:00 | 52d 6h |  |  | 0 |  |  | 6000 | 74.2917
216 | PS_WP3_E-AM-02_TD_CHR00002_CHR00033 | 1.1.3.1.2.5.1 | 211FS |  | 2012-12-27 09:00 | 2013-01-07 14:00 | 7d 4h | Employee | 1800 | 0 | 0 | 0 | 1800 | 11.2083
217 | PS_WP3_E-AM-02_Code_CHR00002_CHR00033 | 1.1.3.1.2.5.2 | 212FS |  | 2013-01-01 09:00 | 2013-01-10 14:00 | 7d 4h | Employee | 1800 | 0 | 0 | 0 | 1800 | 9.2083
218 | PS_WP3_E-AM-02_UTP_CHR00002_CHR00033 | 1.1.3.1.2.5.3 | 213FS |  | 2013-03-06 16:00 | 2013-03-11 16:00 | 3d | Employee | 720 | 0 | 0 | 0 | 720 | 5
219 | PS_WP3_E-AM-02_UTE_CHR00002_CHR00033 | 1.1.3.1.2.5.4 | 214FS |  | 2013-01-08 10:00 | 2013-01-17 10:00 | 7d | Employee | 1680 | 0 | 0 | 0 | 1680 | 9
220 | WP3_E-AM-08_Extension - AM - Work Schedule Overview | 1.1.3.1.3 |  |  | 2012-11-23 16:00 | 2013-02-28 16:00 | 69d |  |  | 0 |  |  | 3090 | 97
221 | PS_WP3_E-AM-08_TD | 1.1.3.1.3.1 |  | FS223 | 2012-11-23 16:00 | 2012-11-27 16:00 | 2d | Employee | 480 | 0 | 0 | 0 | 480 | 4
222 | PS_WP3_E-AM-08_TD | 1.1.3.1.3.2 |  | FS223 | 2012-11-23 16:00 | 2012-11-27 15:00 | 1d 7h | Employee | 450 | 0 | 0 | 0 | 450 | 3.9583
223 | PS_WP3_E-AM-08_Code | 1.1.3.1.3.3 | 221FS;222FS | FS224 | 2012-12-10 15:00 | 2012-12-14 14:00 | 3d 7h | Employee | 930 | 0 | 0 | 0 | 930 | 3.9583
224 | PS_WP3_E-AM-08_UTP | 1.1.3.1.3.4 | 223FS | FS225 | 2013-02-05 09:00 | 2013-02-06 14:00 | 1d 4h | Employee | 360 | 0 | 0 | 0 | 360 | 1.2083
225 | PS_WP3_E-AM-08_UTE | 1.1.3.1.3.5 | 224FS |  | 2013-02-25 10:00 | 2013-02-28 16:00 | 3d 5h | Employee | 870 | 0 | 0 | 0 | 870 | 3.25
226 | WP3_Interface | 1.1.3.2 |  |  | 2012-11-06 10:00 | 2013-02-27 11:00 | 81d 1h |  |  | 0 |  |  | 3330 | 113.0417
227 | WP3_I-AM-01_­Interface - AM - Excel2CI | 1.1.3.2.1 |  |  | 2012-11-06 10:00 | 2013-02-27 11:00 | 81d 1h |  |  | 0 |  |  | 3330 | 113.0417
228 | PS_WP3_I-AM-01_TD | 1.1.3.2.1.1 |  | FS229 | 2012-11-06 10:00 | 2012-11-12 10:00 | 4d | Employee | 960 | 0 | 0 | 0 | 960 | 6
229 | PS_WP3_I-AM-01_Code | 1.1.3.2.1.2 | 228FS | FS230 | 2012-12-03 15:00 | 2012-12-07 17:00 | 4d 2h | Employee | 1020 | 0 | 0 | 0 | 1020 | 4.0833
230 | PS_WP3_I-AM-01_UTP | 1.1.3.2.1.3 | 229FS | FS231 | 2013-01-23 08:00 | 2013-01-24 15:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.2917
231 | PS_WP3_I-AM-01_UTE | 1.1.3.2.1.4 | 230FS |  | 2013-02-21 13:00 | 2013-02-27 11:00 | 3d 7h | Employee | 930 | 0 | 0 | 0 | 930 | 5.9167
232 | WP4 - Annual & Monthly Processes | 1.1.4 |  |  | 2012-08-15 08:00 | 2012-11-20 14:00 | 69d 5h |  |  | 0 |  |  | 12780 | 97.25
233 | WP4_Extension | 1.1.4.1 |  |  | 2012-08-15 08:00 | 2012-11-20 14:00 | 69d 5h |  |  | 0 |  |  | 12780 | 97.25
234 | WP4_­E-TL-18_Extension - TL - Yearly Processes CHR00041, CHR00042, CHR00043 | 1.1.4.1.1 |  |  | 2012-08-15 08:00 | 2012-11-20 14:00 | 69d 5h |  |  | 0 |  |  | 12780 | 97.25
235 | PS_WP4_­E-TL-18_TD | 1.1.4.1.1.1 |  | FS236 | 2012-08-15 08:00 | 2012-09-05 17:00 | 16d | Employee | 3840 | 0 | 0 | 0 | 3840 | 21.375
236 | PS_WP4_­E-TL-18_Code | 1.1.4.1.1.2 | 235FS | FS237 | 2012-09-06 08:00 | 2012-09-27 17:00 | 16d | Employee | 3840 | 0 | 0 | 0 | 3840 | 21.375
237 | PS_WP4_­E-TL-18_UTP | 1.1.4.1.1.3 | 236FS | FS238 | 2012-10-10 14:00 | 2012-10-18 17:00 | 6d 3h | Employee | 1530 | 0 | 0 | 0 | 1530 | 8.125
238 | PS_WP4_­E-TL-18_UTE | 1.1.4.1.1.4 | 237FS |  | 2012-10-30 15:00 | 2012-11-20 14:00 | 14d 7h | Employee | 3570 | 0 | 0 | 0 | 3570 | 20.9583
239 | WP5 - TSM, Planning Tool | 1.1.5 |  |  | 2012-08-15 08:00 | 2013-03-28 10:00 | 161d 2h |  |  | 0 |  |  | 19380 | 225.0833
240 | WP5_Extension | 1.1.5.1 |  |  | 2012-08-15 08:00 | 2013-01-14 10:00 | 108d 2h |  |  | 0 |  |  | 12900 | 152.0833
241 | WP5_E-TL-13_Extension - TL - Planning Tool | 1.1.5.1.1 |  |  | 2012-08-15 08:00 | 2013-01-14 10:00 | 108d 2h |  |  | 0 |  |  | 12900 | 152.0833
242 | PS_WP5_E-TL-13_TD | 1.1.5.1.1.1 |  | FS243 | 2012-08-15 08:00 | 2012-09-06 09:00 | 16d 1h | Employee | 3870 | 0 | 0 | 0 | 3870 | 22.0417
243 | PS_WP5_E-TL-13_Code | 1.1.5.1.1.2 | 242FS | FS244 | 2012-09-14 10:00 | 2012-10-08 11:00 | 16d 1h | Employee | 3870 | 0 | 0 | 0 | 3870 | 24.0417
244 | PS_WP5_E-TL-13_UTP | 1.1.5.1.1.3 | 243FS | FS245;FS246 | 2012-11-05 10:00 | 2012-11-13 15:00 | 6d 4h | Employee | 1560 | 0 | 0 | 0 | 1560 | 8.2083
245 | PS_WP5_E-TL-13_UTE | 1.1.5.1.1.4 | 244FS |  | 2012-12-31 10:00 | 2013-01-09 15:00 | 7d 4h | Employee | 1800 | 0 | 0 | 0 | 1800 | 9.2083
246 | PS_WP5_E-TL-13_UTE | 1.1.5.1.1.5 | 244FS |  | 2013-01-02 15:00 | 2013-01-14 10:00 | 7d 4h | Employee | 1800 | 0 | 0 | 0 | 1800 | 11.7917
247 | WP5 - Extended Config - ONSHORE | 1.1.5.2 |  |  | 2012-11-12 10:00 | 2013-03-28 10:00 | 98d |  |  | 0 |  |  | 6480 | 136
248 | WP5_EC-AM-10_Ext Config - AM - Medical Leave | 1.1.5.2.1 |  |  | 2012-11-12 10:00 | 2013-03-27 11:00 | 97d 1h |  |  | 0 |  |  | 4560 | 135.0417
249 | PS_WP5_EC-AM-10_TD/Code | 1.1.5.2.1.1 |  | FS250;FS253 | 2012-11-12 10:00 | 2012-11-20 10:00 | 6d | Employee | 1440 | 0 | 0 | 0 | 1440 | 8
250 | PS_WP5_EC-AM-10_UTP | 1.1.5.2.1.2 | 249FS | FS251;FS254 | 2013-01-15 10:00 | 2013-01-16 12:00 | 1d 2h | Employee | 300 | 0 | 0 | 0 | 300 | 1.0833
251 | PS_WP5_EC-AM-10_UTE | 1.1.5.2.1.3 | 250FS | FS255 | 2013-01-31 14:00 | 2013-02-05 11:00 | 2d 6h | Employee | 660 | 0 | 0 | 0 | 660 | 4.875
252 | WP5_EC-AM-11_Ext Config - AM - Part Time - CHR00028 | 1.1.5.2.1.4 |  |  | 2013-01-30 08:00 | 2013-03-27 11:00 | 40d 3h |  |  | 0 |  |  | 2160 | 56.125
253 | PS_WP5_EC-AM-11_Code_CHR00028 | 1.1.5.2.1.4.1 | 249FS |  | 2013-01-30 08:00 | 2013-02-06 11:00 | 5d 3h | Employee | 1290 | 0 | 0 | 0 | 1290 | 7.125
254 | PS_WP5_EC-AM-11_UTP_CHR00028 | 1.1.5.2.1.4.2 | 250FS |  | 2013-03-26 10:00 | 2013-03-27 11:00 | 1d 1h | Employee | 270 | 0 | 0 | 0 | 270 | 1.0417
255 | PS_WP5_EC-AM-11_UTE_CHR00028 | 1.1.5.2.1.4.3 | 251FS |  | 2013-03-13 08:00 | 2013-03-15 12:00 | 2d 4h | Employee | 600 | 0 | 0 | 0 | 600 | 2.1667
256 | WP5_EC-AM-11_Ext Config - AM - Part Time | 1.1.5.2.2 |  |  | 2013-03-07 09:00 | 2013-03-28 10:00 | 15d 1h |  |  | 0 |  |  | 720 | 21.0417
257 | PS_WP5_EC-AM-11_TD/Code | 1.1.5.2.2.1 |  | FS258 | 2013-03-07 09:00 | 2013-03-08 16:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.2917
258 | PS_WP5_EC-AM-11_UTP | 1.1.5.2.2.2 | 257FS | FS259 | 2013-03-25 16:00 | 2013-03-26 10:00 | 3h | Employee | 90 | 0 | 0 | 0 | 90 | 0.75
259 | PS_WP5_EC-AM-11_UTE | 1.1.5.2.2.3 | 258FS |  | 2013-03-27 11:00 | 2013-03-28 10:00 | 7h | Employee | 210 | 0 | 0 | 0 | 210 | 0.95833
260 | WP5_EC-AM-18_Ext Config - AM - TSM | 1.1.5.2.3 |  |  | 2013-02-07 08:00 | 2013-03-26 11:00 | 33d 3h |  |  | 0 |  |  | 1200 | 47.125
261 | PS_WP5_EC-AM-18_TD/Code | 1.1.5.2.3.1 |  | FS262 | 2013-02-07 08:00 | 2013-02-11 17:00 | 3d | Employee | 720 | 0 | 0 | 0 | 720 | 4.375
262 | PS_WP5_EC-AM-18_UTP | 1.1.5.2.3.2 | 261FS | FS263 | 2013-03-19 15:00 | 2013-03-20 11:00 | 5h | Employee | 150 | 0 | 0 | 0 | 150 | 0.83333
263 | PS_WP5_EC-AM-18_UTE | 1.1.5.2.3.3 | 262FS |  | 2013-03-25 08:00 | 2013-03-26 11:00 | 1d 3h | Employee | 330 | 0 | 0 | 0 | 330 | 1.125
264 | WP6 - Integration, Security, Reporting | 1.1.6 |  |  | 2012-08-15 08:00 | 2013-03-25 16:00 | 158d 7h |  |  | 0 |  |  | 27720 | 222.3333
265 | WP6_Extension | 1.1.6.1 |  |  | 2012-08-15 08:00 | 2013-03-25 16:00 | 158d 7h |  |  | 0 |  |  | 27720 | 222.3333
266 | WP6_E-AM-09_Extension - BO Reporting AE for AM | 1.1.6.1.1 |  |  | 2012-09-03 08:00 | 2012-12-24 12:00 | 80d 4h |  |  | 0 |  |  | 7410 | 112.1667
267 | PS_WP6_E-AM-09_TD | 1.1.6.1.1.1 |  | FS268 | 2012-09-03 08:00 | 2012-09-14 10:00 | 9d 2h | Employee | 2220 | 0 | 0 | 0 | 2220 | 11.0833
268 | PS_WP6_E-AM-09_Code | 1.1.6.1.1.2 | 267FS | FS269 | 2012-09-27 11:00 | 2012-10-10 14:00 | 9d 2h | Employee | 2220 | 0 | 0 | 0 | 2220 | 13.125
269 | PS_WP6_E-AM-09_UTP | 1.1.6.1.1.3 | 268FS | FS270 | 2012-11-14 13:00 | 2012-11-20 10:00 | 3d 6h | Employee | 900 | 0 | 0 | 0 | 900 | 5.875
270 | PS_WP6_E-AM-09_UTE | 1.1.6.1.1.4 | 269FS |  | 2012-12-11 16:00 | 2012-12-24 12:00 | 8d 5h | Employee | 2070 | 0 | 0 | 0 | 2070 | 12.8333
271 | WP6_E-TL-02_Extension - TL - Automated TL Enrollment | 1.1.6.1.2 |  |  | 2012-11-02 15:00 | 2013-02-25 10:00 | 80d 4h |  |  | 0 |  |  | 3480 | 114.7917
272 | PS_WP6_E-TL-02_TD | 1.1.6.1.2.1 |  | FS273 | 2012-11-02 15:00 | 2012-11-09 09:00 | 4d 3h | Employee | 1050 | 0 | 0 | 0 | 1050 | 6.75
273 | PS_WP6_E-TL-02_Code | 1.1.6.1.2.2 | 272FS | FS274 | 2012-11-27 16:00 | 2012-12-04 10:00 | 4d 3h | Employee | 1050 | 0 | 0 | 0 | 1050 | 6.75
274 | PS_WP6_E-TL-02_UTP | 1.1.6.1.2.3 | 273FS | FS275 | 2013-01-21 14:00 | 2013-01-23 11:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.875
275 | PS_WP6_E-TL-02_UTE | 1.1.6.1.2.4 | 274FS |  | 2013-02-19 10:00 | 2013-02-25 10:00 | 4d | Employee | 960 | 0 | 0 | 0 | 960 | 6
276 | WP6_E-TL-16_Extension - TL - Timesheet prepopulation | 1.1.6.1.3 |  |  | 2012-08-15 08:00 | 2013-03-25 16:00 | 158d 7h |  |  | 0 |  |  | 13530 | 222.3333
277 | PS_WP6_E-TL-16_TD | 1.1.6.1.3.1 |  | FS278;FS283 | 2012-08-15 08:00 | 2012-08-31 17:00 | 13d | Employee | 3120 | 0 | 0 | 0 | 3120 | 16.375
278 | PS_WP6_E-TL-16_Code | 1.1.6.1.3.2 | 277FS | FS279;FS284 | 2012-09-19 10:00 | 2012-10-08 10:00 | 13d | Employee | 3120 | 0 | 0 | 0 | 3120 | 19
279 | PS_WP6_E-TL-16_UTP | 1.1.6.1.3.3 | 278FS | FS280;FS281;FS285 | 2012-10-30 15:00 | 2012-11-06 17:00 | 5d 2h | Employee | 1260 | 0 | 0 | 0 | 1260 | 7.0833
280 | PS_WP6_E-TL-16_UTE | 1.1.6.1.3.4 | 279FS | FS286 | 2012-12-06 15:00 | 2012-12-14 15:00 | 6d | Employee | 1440 | 0 | 0 | 0 | 1440 | 8
281 | PS_WP6_E-TL-16_UTE | 1.1.6.1.3.5 | 279FS | FS286 | 2012-11-27 15:00 | 2012-12-06 15:00 | 7d | Employee | 1680 | 0 | 0 | 0 | 1680 | 9
282 | WP6_E-TL-16_Extension - TL - Timesheet prepopulation | 1.1.6.1.3.6 |  |  | 2013-02-25 09:00 | 2013-03-25 16:00 | 20d 6h |  |  | 0 |  |  | 2910 | 28.2917
283 | PS_WP6_E-TL-16_TD_CHR00016 | 1.1.6.1.3.6.1 | 277FS |  | 2013-02-25 09:00 | 2013-02-28 15:00 | 3d 5h | Employee | 870 | 0 | 0 | 0 | 870 | 3.25
284 | PS_WP6_E-TL-16_Code_CHR00016 | 1.1.6.1.3.6.2 | 278FS |  | 2013-02-25 15:00 | 2013-03-01 11:00 | 3d 5h | Employee | 870 | 0 | 0 | 0 | 870 | 3.8333
285 | PS_WP6_E-TL-16_UTP_CHR00016 | 1.1.6.1.3.6.3 | 279FS |  | 2013-03-22 11:00 | 2013-03-25 16:00 | 1d 4h | Employee | 360 | 0 | 0 | 0 | 360 | 3.2083
286 | PS_WP6_E-TL-16_UTE_CHR00016 | 1.1.6.1.3.6.4 | 280FS;281FS |  | 2013-02-28 16:00 | 2013-03-06 10:00 | 3d 3h | Employee | 810 | 0 | 0 | 0 | 810 | 5.75
287 | WP6_E-AM-07_Extension - AM - Recovery Flex Time | 1.1.6.1.4 |  |  | 2012-11-07 08:00 | 2013-02-27 16:00 | 80d 7h |  |  | 0 |  |  | 3300 | 112.3333
288 | PS_WP6_E-AM-07_TD | 1.1.6.1.4.1 |  | FS289 | 2012-11-07 08:00 | 2012-11-13 09:00 | 4d 1h | Employee | 990 | 0 | 0 | 0 | 990 | 6.0417
289 | PS_WP6_E-AM-07_Code | 1.1.6.1.4.2 | 288FS | FS290 | 2012-12-05 10:00 | 2012-12-11 11:00 | 4d 1h | Employee | 990 | 0 | 0 | 0 | 990 | 6.0417
290 | PS_WP6_E-AM-07_UTP | 1.1.6.1.4.3 | 289FS | FS291 | 2013-01-25 14:00 | 2013-01-29 10:00 | 1d 5h | Employee | 390 | 0 | 0 | 0 | 390 | 3.8333
291 | PS_WP6_E-AM-07_UTE | 1.1.6.1.4.4 | 290FS |  | 2013-02-22 08:00 | 2013-02-27 16:00 | 3d 7h | Employee | 930 | 0 | 0 | 0 | 930 | 5.3333
292 | WP7 - Interfaces | 1.1.7 |  |  | 2012-08-30 11:00 | 2013-03-20 15:00 | 144d 3h |  |  | 0 |  |  | 15090 | 202.1667
293 | WP7_I-AM-02_Interface - AM - PS to PGP (Page/Navigation) - 10% | 1.1.7.1 |  |  | 2012-12-10 08:00 | 2013-03-15 16:00 | 69d 7h |  |  | 0 |  |  | 2190 | 95.3333
294 | PS_WP7_I-AM-02_Page/Navigation_TD | 1.1.7.1.1 |  | FS295 | 2012-12-10 08:00 | 2012-12-12 15:00 | 2d 6h | Employee | 660 | 0 | 0 | 0 | 660 | 2.2917
295 | PS_WP7_I-AM-02_Page/Navigation_Code | 1.1.7.1.2 | 294FS | FS296 | 2013-01-16 13:00 | 2013-01-21 10:00 | 2d 6h | Employee | 660 | 0 | 0 | 0 | 660 | 4.875
296 | PS_WP7_I-AM-02_Page/Navigation_UTP | 1.1.7.1.3 | 295FS | FS297 | 2013-02-26 16:00 | 2013-02-27 17:00 | 1d 1h | Employee | 270 | 0 | 0 | 0 | 270 | 1.0417
297 | PS_WP7_I-AM-02_Page/Navigation_UTE | 1.1.7.1.4 | 296FS |  | 2013-03-13 11:00 | 2013-03-15 16:00 | 2d 4h | Employee | 600 | 0 | 0 | 0 | 600 | 2.2083
298 | WP7_I-AM-02_Interface - AM - PS to PGP (App Engine) - 40% | 1.1.7.2 |  |  | 2012-08-30 11:00 | 2013-03-20 15:00 | 144d 3h |  |  | 0 |  |  | 12900 | 202.1667
299 | PS_WP7_I-AM-02_App Engine_TD | 1.1.7.2.1 |  | FS300;FS305 | 2012-08-30 11:00 | 2012-09-14 10:00 | 10d 7h | Employee | 2610 | 0 | 0 | 0 | 2610 | 14.9583
300 | PS_WP7_I-AM-02_App Engine_Code | 1.1.7.2.2 | 299FS | FS301;FS306 | 2012-10-11 09:00 | 2012-10-25 17:00 | 10d 7h | Employee | 2610 | 0 | 0 | 0 | 2610 | 14.3333
301 | PS_WP7_I-AM-02_App Engine_UTP | 1.1.7.2.3 | 300FS | FS302;FS303;FS304;FS307 | 2012-11-28 16:00 | 2012-12-05 10:00 | 4d 3h | Employee | 1050 | 0 | 0 | 0 | 1050 | 6.75
302 | PS_WP7_I-AM-02_App Engine_UTE | 1.1.7.2.4 | 301FS | FS308 | 2013-01-22 08:00 | 2013-01-25 10:00 | 3d 2h | Employee | 780 | 0 | 0 | 0 | 780 | 3.0833
303 | PS_WP7_I-AM-02_App Engine_UTE | 1.1.7.2.5 | 301FS | FS309 | 2013-01-22 11:00 | 2013-01-25 14:00 | 3d 2h | Employee | 780 | 0 | 0 | 0 | 780 | 3.125
304 | PS_WP7_I-AM-02_App Engine_UTE | 1.1.7.2.6 | 301FS |  | 2013-03-01 14:00 | 2013-03-06 16:00 | 3d 2h | Employee | 780 | 0 | 0 | 0 | 780 | 5.0833
305 | PS_WP7_I-AM-02_App Engine_TD_CHR00021 | 1.1.7.2.7 | 299FS |  | 2013-01-30 10:00 | 2013-02-06 14:00 | 5d 3h | Employee | 1290 | 0 | 0 | 0 | 1290 | 7.1667
306 | PS_WP7_I-AM-02_App Engine_Code_CHR00021 | 1.1.7.2.8 | 300FS |  | 2013-01-29 09:00 | 2013-02-05 12:00 | 5d 3h | Employee | 1290 | 0 | 0 | 0 | 1290 | 7.125
307 | PS_WP7_I-AM-02_App Engine_UTP_CHR00021 | 1.1.7.2.9 | 301FS |  | 2013-03-18 14:00 | 2013-03-20 15:00 | 2d 1h | Employee | 510 | 0 | 0 | 0 | 510 | 2.0417
308 | PS_WP7_I-AM-02_App Engine_UTE_CHR00021 | 1.1.7.2.10 | 302FS |  | 2013-03-13 13:00 | 2013-03-15 17:00 | 2d 4h | Employee | 600 | 0 | 0 | 0 | 600 | 2.1667
309 | PS_WP7_I-AM-02_App Engine_UTE_CHR00021 | 1.1.7.2.11 | 303FS |  | 2013-03-11 14:00 | 2013-03-14 09:00 | 2d 4h | Employee | 600 | 0 | 0 | 0 | 600 | 2.7917
310 | WP8 - Conversions | 1.1.8 |  |  | 2012-10-15 13:00 | 2013-03-28 16:00 | 118d 3h |  |  | 0 |  |  | 19500 | 164.125
311 | WP8_Build | 1.1.8.1 |  |  | 2012-10-15 13:00 | 2013-03-28 16:00 | 118d 3h |  |  | 0 |  |  | 19500 | 164.125
312 | WP8_C-TL-01_Conversion - Schift/Schedules | 1.1.8.1.1 |  |  | 2013-03-01 08:00 | 2013-03-27 11:00 | 18d 3h |  |  | 0 |  |  | 810 | 26.125
313 | PS_WP8_C-TL-01_TD | 1.1.8.1.1.1 |  | FS314 | 2013-03-01 08:00 | 2013-03-01 17:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 0.375
314 | PS_WP8_C-TL-01_Code | 1.1.8.1.1.2 | 313FS | FS315 | 2013-03-15 14:00 | 2013-03-18 14:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 3
315 | PS_WP8_C-TL-01_UTP | 1.1.8.1.1.3 | 314FS | FS316 | 2013-03-22 14:00 | 2013-03-22 17:00 | 3h | Employee | 90 | 0 | 0 | 0 | 90 | 0.125
316 | PS_WP8_C-TL-01_UTE | 1.1.8.1.1.4 | 315FS |  | 2013-03-26 11:00 | 2013-03-27 11:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 1
317 | WP8_C-TL-02_Conversion - Employee Paygroup Assignment | 1.1.8.1.2 |  |  | 2012-11-20 10:00 | 2013-03-05 10:00 | 75d |  |  | 0 |  |  | 2910 | 105
318 | PS_WP8_C-TL-02_TD | 1.1.8.1.2.1 |  | FS319 | 2012-11-20 10:00 | 2012-11-23 16:00 | 3d 5h | Employee | 870 | 0 | 0 | 0 | 870 | 3.25
319 | PS_WP8_C-TL-02_Code | 1.1.8.1.2.2 | 318FS | FS320 | 2012-12-14 15:00 | 2012-12-20 11:00 | 3d 5h | Employee | 870 | 0 | 0 | 0 | 870 | 5.8333
320 | PS_WP8_C-TL-02_UTP | 1.1.8.1.2.3 | 319FS | FS321 | 2013-02-08 13:00 | 2013-02-11 17:00 | 1d 4h | Employee | 360 | 0 | 0 | 0 | 360 | 3.1667
321 | PS_WP8_C-TL-02_UTE | 1.1.8.1.2.4 | 320FS |  | 2013-02-27 16:00 | 2013-03-05 10:00 | 3d 3h | Employee | 810 | 0 | 0 | 0 | 810 | 5.75
322 | WP8_C-TL-03_Conversion - Absence History | 1.1.8.1.3 |  |  | 2012-12-26 16:00 | 2013-03-20 15:00 | 59d 7h |  |  | 0 |  |  | 1860 | 83.9583
323 | PS_WP8_C-TL-03_TD | 1.1.8.1.3.1 |  | FS324 | 2012-12-26 16:00 | 2012-12-31 10:00 | 2d 3h | Employee | 570 | 0 | 0 | 0 | 570 | 4.75
324 | PS_WP8_C-TL-03_Code | 1.1.8.1.3.2 | 323FS | FS325 | 2013-01-29 10:00 | 2013-01-31 14:00 | 2d 3h | Employee | 570 | 0 | 0 | 0 | 570 | 2.1667
325 | PS_WP8_C-TL-03_UTP | 1.1.8.1.3.3 | 324FS | FS326 | 2013-03-06 10:00 | 2013-03-07 10:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 1
326 | PS_WP8_C-TL-03_UTE | 1.1.8.1.3.4 | 325FS |  | 2013-03-18 15:00 | 2013-03-20 15:00 | 2d | Employee | 480 | 0 | 0 | 0 | 480 | 2
327 | WP8_C-TL-04_Conversion - Absence Balance | 1.1.8.1.4 |  |  | 2012-12-17 09:00 | 2013-03-12 17:00 | 61d 7h |  |  | 0 |  |  | 2400 | 85.3333
328 | PS_WP8_C-TL-04_TD | 1.1.8.1.4.1 |  | FS329;FS330 | 2012-12-17 09:00 | 2012-12-20 09:00 | 3d | Employee | 720 | 0 | 0 | 0 | 720 | 3
329 | PS_WP8_C-TL-04_Code | 1.1.8.1.4.2 | 328FS | FS331 | 2013-01-25 10:00 | 2013-01-28 15:00 | 1d 4h | Employee | 360 | 0 | 0 | 0 | 360 | 3.2083
330 | PS_WP8_C-TL-04_Code | 1.1.8.1.4.3 | 328FS | FS331 | 2013-01-28 15:00 | 2013-01-30 10:00 | 1d 4h | Employee | 360 | 0 | 0 | 0 | 360 | 1.7917
331 | PS_WP8_C-TL-04_UTP | 1.1.8.1.4.4 | 329FS;330FS | FS332 | 2013-02-20 15:00 | 2013-02-21 17:00 | 1d 2h | Employee | 300 | 0 | 0 | 0 | 300 | 1.0833
332 | PS_WP8_C-TL-04_UTE | 1.1.8.1.4.5 | 331FS |  | 2013-03-08 10:00 | 2013-03-12 17:00 | 2d 6h | Employee | 660 | 0 | 0 | 0 | 660 | 4.2917
333 | WP8_C-TL-05_Conversion - Accumulators | 1.1.8.1.5 |  |  | 2013-02-15 11:00 | 2013-03-27 11:00 | 28d |  |  | 0 |  |  | 990 | 40
334 | PS_WP8_C-TL-05_TD | 1.1.8.1.5.1 |  | FS335 | 2013-02-15 11:00 | 2013-02-18 14:00 | 1d 2h | Employee | 300 | 0 | 0 | 0 | 300 | 3.125
335 | PS_WP8_C-TL-05_Code | 1.1.8.1.5.2 | 334FS | FS336 | 2013-03-07 10:00 | 2013-03-08 12:00 | 1d 2h | Employee | 300 | 0 | 0 | 0 | 300 | 1.0833
336 | PS_WP8_C-TL-05_UTP | 1.1.8.1.5.3 | 335FS | FS337 | 2013-03-21 16:00 | 2013-03-22 11:00 | 4h | Employee | 120 | 0 | 0 | 0 | 120 | 0.79167
337 | PS_WP8_C-TL-05_UTE | 1.1.8.1.5.4 | 336FS |  | 2013-03-26 10:00 | 2013-03-27 11:00 | 1d 1h | Employee | 270 | 0 | 0 | 0 | 270 | 1.0417
338 | WP8_C-TL-06_Conversion - Employee T&L Enrollment | 1.1.8.1.6 |  |  | 2012-11-13 09:00 | 2013-03-04 16:00 | 79d 6h |  |  | 0 |  |  | 3000 | 111.2917
339 | PS_WP8_C-TL-06_TD | 1.1.8.1.6.1 |  | FS340 | 2012-11-13 09:00 | 2012-11-16 16:00 | 3d 6h | Employee | 900 | 0 | 0 | 0 | 900 | 3.2917
340 | PS_WP8_C-TL-06_Code | 1.1.8.1.6.2 | 339FS | FS341 | 2012-12-11 11:00 | 2012-12-17 09:00 | 3d 6h | Employee | 900 | 0 | 0 | 0 | 900 | 5.9167
341 | PS_WP8_C-TL-06_UTP | 1.1.8.1.6.3 | 340FS | FS342 | 2013-02-05 13:00 | 2013-02-06 17:00 | 1d 4h | Employee | 360 | 0 | 0 | 0 | 360 | 1.1667
342 | PS_WP8_C-TL-06_UTE | 1.1.8.1.6.4 | 341FS |  | 2013-02-27 11:00 | 2013-03-04 16:00 | 3d 4h | Employee | 840 | 0 | 0 | 0 | 840 | 5.2083
343 | WP8_C-TL-07_Conversion - Compensatory Time Off Plan Enrollment | 1.1.8.1.7 |  |  | 2013-03-28 10:00 | 2013-03-28 16:00 | 5h |  |  | 0 |  |  | 150 | 0.25
344 | PS_WP8_C-TL-07_TD | 1.1.8.1.7.1 |  |  | 2013-03-28 10:00 | 2013-03-28 16:00 | 5h | Employee | 150 | 0 | 0 | 0 | 150 | 0.25
345 | WP8_C-TL-08_Conversion - Work Schedule Assignment | 1.1.8.1.8 |  |  | 2012-10-15 13:00 | 2013-02-08 12:00 | 84d |  |  | 0 |  |  | 4500 | 115.9583
346 | PS_WP8_C-TL-08_TD | 1.1.8.1.8.1 |  | FS347 | 2012-10-15 13:00 | 2012-10-23 09:00 | 5d 5h | Employee | 1350 | 0 | 0 | 0 | 1350 | 7.8333
347 | PS_WP8_C-TL-08_Code | 1.1.8.1.8.2 | 346FS | FS348 | 2012-11-09 09:00 | 2012-11-16 15:00 | 5d 5h | Employee | 1350 | 0 | 0 | 0 | 1350 | 7.25
348 | PS_WP8_C-TL-08_UTP | 1.1.8.1.8.3 | 347FS | FS349 | 2012-12-31 13:00 | 2013-01-02 15:00 | 2d 2h | Employee | 540 | 0 | 0 | 0 | 540 | 2.0833
349 | PS_WP8_C-TL-08_UTE | 1.1.8.1.8.4 | 348FS |  | 2013-02-01 10:00 | 2013-02-08 12:00 | 5d 2h | Employee | 1260 | 0 | 0 | 0 | 1260 | 7.0833
350 | WP8_C-TL-09_Conversion - Reported Overtime History | 1.1.8.1.9 |  |  | 2013-01-21 10:00 | 2013-03-25 12:00 | 45d 2h |  |  | 0 |  |  | 1440 | 63.0833
351 | PS_WP8_C-TL-09_TD | 1.1.8.1.9.1 |  | FS352 | 2013-01-21 10:00 | 2013-01-22 17:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.2917
352 | PS_WP8_C-TL-09_Code | 1.1.8.1.9.2 | 351FS | FS353 | 2013-02-13 15:00 | 2013-02-15 12:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.875
353 | PS_WP8_C-TL-09_UTP | 1.1.8.1.9.3 | 352FS | FS354 | 2013-03-14 09:00 | 2013-03-14 16:00 | 6h | Employee | 180 | 0 | 0 | 0 | 180 | 0.29167
354 | PS_WP8_C-TL-09_UTE | 1.1.8.1.9.4 | 353FS |  | 2013-03-21 15:00 | 2013-03-25 12:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 3.875
355 | WP8_C-TL-10_Conversion - Compensatory Time Off Plan Balance | 1.1.8.1.10 |  |  | 2013-01-21 13:00 | 2013-03-25 09:00 | 44d 5h |  |  | 0 |  |  | 1440 | 62.8333
356 | PS_WP8_C-TL-10_TD | 1.1.8.1.10.1 |  | FS357 | 2013-01-21 13:00 | 2013-01-23 10:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.875
357 | PS_WP8_C-TL-10_Code | 1.1.8.1.10.2 | 356FS | FS358 | 2013-02-12 08:00 | 2013-02-13 15:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 1.2917
358 | PS_WP8_C-TL-10_UTP | 1.1.8.1.10.3 | 357FS | FS359 | 2013-03-12 15:00 | 2013-03-13 12:00 | 6h | Employee | 180 | 0 | 0 | 0 | 180 | 0.875
359 | PS_WP8_C-TL-10_UTE | 1.1.8.1.10.4 | 358FS |  | 2013-03-21 11:00 | 2013-03-25 09:00 | 1d 6h | Employee | 420 | 0 | 0 | 0 | 420 | 3.9167
360 | TL MSS Security - CHR00026 | 1.1.9 |  |  | 2013-02-12 08:00 | 2013-03-21 16:00 | 27d 7h |  |  | 0 |  |  | 1050 | 37.3333
361 | PS_WPX_TL-MSS-Security_TD_CHR00026 | 1.1.9.1 |  | FS362 | 2013-02-12 08:00 | 2013-02-12 17:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 0.375
362 | PS_WPX_TL-MSS-Security_Code_CHR00026 | 1.1.9.2 | 361FS | FS363 | 2013-02-28 08:00 | 2013-02-28 17:00 | 1d | Employee | 240 | 0 | 0 | 0 | 240 | 0.375
363 | PS_WPX_TL-MSS-Security_CTP_CHR00026 | 1.1.9.3 | 362FS | FS364 | 2013-03-15 13:00 | 2013-03-15 16:00 | 3h | Employee | 90 | 0 | 0 | 0 | 90 | 0.125
364 | PS_WPX_TL-MSS-Security_CTE_CHR00026 | 1.1.9.4 | 363FS |  | 2013-03-19 16:00 | 2013-03-21 16:00 | 2d | Employee | 480 | 0 | 0 | 0 | 480 | 2

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee | Renewable | 6 | 0 | 30 | 5;6;7;8;9;10;11;12;13;15;16;17;18;20;21;22;23;24;26;27;28;29;30;31;32;33;35;36;37;38;40;41;42;43;53;61;62;63;64;66;67;68;69;70;71;72;73;74;75;76;77;78;79;80;81;83;84;85;93;94;95;97;98;99;101;102;103;105;106;107;109;110;111;113;114;115;117;118;119;120;121;122;126;127;128;129;131;132;133;134;136;137;138;139;141;142;143;144;145;146;147;148;149;150;151;153;154;155;156;157;159;160;161;162;164;165;166;167;169;170;171;172;174;175;176;177;180;181;182;183;186;187;188;189;190;191;192;194;195;196;197;200;201;202;206;207;208;209;211;212;213;214;216;217;218;219;221;222;223;224;225;228;229;230;231;235;236;237;238;242;243;244;245;246;249;250;251;253;254;255;257;258;259;261;262;263;267;268;269;270;272;273;274;275;277;278;279;280;281;283;284;285;286;288;289;290;291;294;295;296;297;299;300;301;302;303;304;305;306;307;308;309;313;314;315;316;318;319;320;321;323;324;325;326;328;329;330;331;332;334;335;336;337;339;340;341;342;344;346;347;348;349;351;352;353;354;356;357;358;359;361;362;363;364; | 233250

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Digipolis Talent Management Suite | 1296h |  |  |  |  | 99 | 100 | 101
1 | Digipolis TMS (comp proj) | 1296h |  |  |  |  | 99 | 100 | 101
2 | WP1 - Sched, Cal, Takes, Entitlements, Accum, Pos Time | 1296h |  |  |  |  | 99 | 100 | 101
3 | WP1_Extension | 1296h |  |  |  |  | 99 | 100 | 101
4 | WP1_E-TL-03_Extension TL - Compensatory TimeOff Plans | 1296h |  |  |  |  | 99 | 100 | 101
5 | PS_WP1_E-TL-03_TD | 91h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | PS_WP1_E-TL-03_Code | 91h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | PS_WP1_E-TL-03_UTP | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | PS_WP1_E-TL-03_UTE | 42h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | PS_WP1_E-TL-03_UTE | 42h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | PS_WP1_E-TL-03_TD_CHR00025 | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | PS_WP1_E-TL-03_Code_CHR00025 | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | PS_WP1_E-TL-03_UTP_CHR00025 | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | PS_WP1_E-TL-03_UTE_CHR00025 | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | WP1_E-TL-06_Extension - TL - Handling Recovery Time | 430h |  |  |  |  | 99 | 100 | 101
15 | PS_WP1_E-TL-06_TD | 17h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | PS_WP1_E-TL-06_Code | 17h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | PS_WP1_E-TL-06_UTP | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | PS_WP1_E-TL-06_UTE | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | WP1_E-TL-09_Extension - TL - Manage Schedules | 785h |  |  |  |  | 99 | 100 | 101
20 | PS_WP1_E-TL-09_TD | 46h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | PS_WP1_E-TL-09_Code | 46h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | PS_WP1_E-TL-09_UTP | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | PS_WP1_E-TL-09_UTE | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | PS_WP1_E-TL-09_UTE | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | WP1_E-TL-14, E-TL-08_Extension - TL - Recovery Type Indicator/Extension - TL - Inconvenient Hours Eligibility | 149h |  |  |  |  | 99 | 100 | 101
26 | PS_WP1_E-TL-14_TD | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | PS_WP1_E-TL-14_Code | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | PS_WP1_E-TL-14_UTP | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | PS_WP1_E-TL-14_UTE | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | PS_WP1_E-TL-14_TD_CHR00027 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | PS_WP1_E-TL-14_Code_CHR00027 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | PS_WP1_E-TL-14_UTP_CHR00027 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | PS_WP1_E-TL-14_UTE_CHR00027 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | WP1_E-TL-17_Extension - TL - Warning for Shifts | 564h |  |  |  |  | 99 | 100 | 101
35 | PS_WP1_E-TL-17_TD | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | PS_WP1_E-TL-17_Code | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | PS_WP1_E-TL-17_UTP | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | PS_WP1_E-TL-17_UTE | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | WP1_E-AM-05_Extension - AM - Klein Verlet | 470h |  |  |  |  | 99 | 100 | 101
40 | PS_WP1_E-AM-05_TD | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | PS_WP1_E-AM-05_Code | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | PS_WP1_E-AM-05_UTP | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | PS_WP1_E-AM-05_UTE | 17h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | WP1_Extended_Config | 1284h |  |  |  |  | 99 | 100 | 101
45 | WP1_EC-AM-04_Ext Config - AM - Educational Leave | 0 |  |  |  |  | 99 | 100 | 101
46 | PS_WP1_EC-AM-04_TD | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | PS_WP1_EC-AM-04_Code | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | PS_WP1_EC-AM-04_UTP | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | PS_WP1_EC-AM-04_UTE | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | WP1_EC-AM-09_Ext Config - AM - Leave Without Pay | 1284h |  |  |  |  | 99 | 100 | 101
51 | PS_WP1_EC-AM-09_TD | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | PS_WP1_EC-AM-09_Code | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | PS_WP1_EC-AM-09_UTP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | PS_WP1_EC-AM-09_UTE | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | WP1_EC-AM-19_Ext Config - AM - Unemployment/Retirement | 8h |  |  |  |  | 99 | 100 | 101
56 | PS_WP1_EC-AM-19_TD | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | PS_WP1_EC-AM-19_Code | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | PS_WP1_EC-AM-19_UTP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | PS_WP1_EC-AM-19_UTE | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | WP1_EC-AM-14_Ext Config - AM - Strike | 218h |  |  |  |  | 99 | 100 | 101
61 | PS_WP1_EC-AM-14_TD | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | PS_WP1_EC-AM-14_Code | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | PS_WP1_EC-AM-14_UTP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | PS_WP1_EC-AM-14_UTE | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | WP1_EC-TL-04_Ext Config - TL - Rules | 1143h |  |  |  |  | 99 | 100 | 101
66 | PS_WP1_EC-TL-04_TD | 73h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | PS_WP1_EC-TL-04_TD | 73h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | PS_WP1_EC-TL-04_TD | 73h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | PS_WP1_EC-TL-04_TD | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | PS_WP1_EC-TL-04_Code | 73h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | PS_WP1_EC-TL-04_Code | 73h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | PS_WP1_EC-TL-04_Code | 73h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | PS_WP1_EC-TL-04_Code | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | PS_WP1_EC-TL-04_UTP | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | PS_WP1_EC-TL-04_UTP | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | PS_WP1_EC-TL-04_UTP | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | PS_WP1_EC-TL-04_UTP | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | PS_WP1_EC-TL-04_UTE | 69h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | PS_WP1_EC-TL-04_UTE | 69h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | PS_WP1_EC-TL-04_UTE | 69h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | PS_WP1_EC-TL-04_UTE | 35h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | WP1_EC-TL-04_Ext Config - TL - Rules - CHR00046 | 269h |  |  |  |  | 99 | 100 | 101
83 | PS_WP1_EC-TL-04_CHR00046_Code | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | PS_WP1_EC-TL-04_CHR00046_UTP | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | PS_WP1_EC-TL-04_CHR00046_UTE | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | WP1_EC-AM-05_Ext Config - AM - Klein Verlet | 0 |  |  |  |  | 99 | 100 | 101
87 | PS_WP1_EC-AM-05_TD | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | PS_WP1_EC-AM-05_Code | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | PS_WP1_EC-AM-05_UTP | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | PS_WP1_EC-AM-05_UTE | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | WP1_Extended_Config_ONSHORE | 954h |  |  |  |  | 99 | 100 | 101
92 | WP1_EC-AM-13_Ext Config - AM - Retirement Preparation | 50h |  |  |  |  | 99 | 100 | 101
93 | PS_WP1_EC-AM-13_TD/Code | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | PS_WP1_EC-AM-13_UTP | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | PS_WP1_EC-AM-13_UTE | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | WP1_EC-AM-16_Ext Config - AM - Thematic Leaves | 50h |  |  |  |  | 99 | 100 | 101
97 | PS_WP1_EC-AM-16_TD/Code | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | PS_WP1_EC-AM-16_UTP | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | PS_WP1_EC-AM-16_UTE | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | WP1_EC-AM-07_Ext Config - AM - Late/No Show | 216h |  |  |  |  | 99 | 100 | 101
101 | PS_WP1_EC-AM-07_TD/Code | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | PS_WP1_EC-AM-07_UTP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | PS_WP1_EC-AM-07_UTE | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | WP1_EC-AM-12_Ext Config - AM - Pregnancy Leave | 271h |  |  |  |  | 99 | 100 | 101
105 | PS_WP1_EC-AM-12_TD/Code | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | PS_WP1_EC-AM-12_UTP | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | PS_WP1_EC-AM-12_UTE | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | WP1_EC-AM-17_Ext Config - AM - Time Credit | 421h |  |  |  |  | 99 | 100 | 101
109 | PS_WP1_EC-AM-17_TD/Code | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | PS_WP1_EC-AM-17_UTP | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | PS_WP1_EC-AM-17_UTE | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | WP1_EC-AM-01_Ext Config - AM - Annual Leave - CHR00007 | 392h |  |  |  |  | 99 | 100 | 101
113 | PS_WP1_EC-AM-01_Code_­CHR00007 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | PS_WP1_EC-AM-01_UTP_CHR00007 | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | PS_WP1_EC-AM-01_UTE_CHR00007 | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | WP1_EC-AM-01_Ext Config - AM - Annual Leave | 618h |  |  |  |  | 99 | 100 | 101
117 | PS_WP1_EC-AM-01_TD/Code | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | PS_WP1_EC-AM-01_UTP | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | PS_WP1_EC-AM-01_UTE | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | WP1_UPDATE SS & Forecasting: Ext Config - AM - Klein Verlet | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | WP1_UPDATE SS & Forecasting: Ext Config - AM - Leave Without Pay | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | WP1_UPDATE SS & Forecasting: Ext Config - AM - Educational Leave | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | WP2 - ESS, MSS, Approvals, Forecasting | 1291h |  |  |  |  | 99 | 100 | 101
124 | WP2_Extension | 1291h |  |  |  |  | 99 | 100 | 101
125 | WP2_E-TL-04_Extension - TL - Daily Hours Limit Warning | 129h |  |  |  |  | 99 | 100 | 101
126 | PS_WP2_E-TL-04_TD | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | PS_WP2_E-TL-04_Code | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | PS_WP2_E-TL-04_UTP | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | PS_WP2_E-TL-04_UTE | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | WP2_E-TL-15_Extension - TL - Shifts in Work Schedule | 360h |  |  |  |  | 99 | 100 | 101
131 | PS_WP2_E-TL-15_TD | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | PS_WP2_E-TL-15_Code | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | PS_WP2_E-TL-15_UTP | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | PS_WP2_E-TL-15_UTE | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | WP2_E-TL-05_Extension - TL - ESS | 697h |  |  |  |  | 99 | 100 | 101
136 | PS_WP2_E-TL-05_TD | 58h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | PS_WP2_E-TL-05_Code | 58h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | PS_WP2_E-TL-05_UTP | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | PS_WP2_E-TL-05_UTE | 54h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | WP2_E-AM-03_Extension - AM - ESS | 1105h |  |  |  |  | 99 | 100 | 101
141 | PS_WP2_E-AM-03_TD | 138h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | PS_WP2_E-AM-03_Code | 62h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | PS_WP2_E-AM-03_Code | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | PS_WP2_E-AM-03_Code | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | PS_WP2_E-AM-03_UTP | 25h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | PS_WP2_E-AM-03_UTP | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | PS_WP2_E-AM-03_UTP | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | PS_WP2_E-AM-03_UTE | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | PS_WP2_E-AM-03_UTE | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | PS_WP2_E-AM-03_UTE | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | PS_WP2_E-AM-03_UTE | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | WP2_E-AM-06_Extension - AM - MSS | 1169h |  |  |  |  | 99 | 100 | 101
153 | PS_WP2_E-AM-06_TD | 34h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | PS_WP2_E-AM-06_Code | 34h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | PS_WP2_E-AM-06_UTP | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | PS_WP2_E-AM-06_UTE | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | PS_WP2_E-AM-06_UTE | 266h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | WP2_E-AM-06_Extension - AM - MSS - CHR00032 | 419h |  |  |  |  | 99 | 100 | 101
159 | PS_WP2_E-AM-06_TD_CHR00032 | 62h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | PS_WP2_E-AM-06_Code_CHR00032 | 62h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
161 | PS_WP2_E-AM-06_UTP_CHR00032 | 25h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | PS_WP2_E-AM-06_UTE_CHR00032 | 58h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
163 | WP2_E-TL-11_Extension - TL - Overtime Prerequests | 672h |  |  |  |  | 99 | 100 | 101
164 | PS_WP2_E-TL-11_TD | 41h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | PS_WP2_E-TL-11_Code | 41h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
166 | PS_WP2_E-TL-11_UTP | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
167 | PS_WP2_E-TL-11_UTE | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
168 | WP2_E-TL-12_Extension - TL - Overtime Reporting | 552h |  |  |  |  | 99 | 100 | 101
169 | PS_WP2_E-TL-12_TD | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
170 | PS_WP2_E-TL-12_Code | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
171 | PS_WP2_E-TL-12_UTP | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
172 | PS_WP2_E-TL-12_UTE | 21h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
173 | WP2_E-AM-04_Extension - AM - Forecasting | 125h |  |  |  |  | 99 | 100 | 101
174 | PS_WP2_E-AM-04_TD | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
175 | PS_WP2_E-AM-04_Code | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
176 | PS_WP2_E-AM-04_UTP | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
177 | PS_WP2_E-AM-04_UTE | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
178 | WP2_Report | 306h |  |  |  |  | 99 | 100 | 101
179 | WP2_R-TL-03_Report - TL - Pending Approvals Request | 306h |  |  |  |  | 99 | 100 | 101
180 | PSWP2_R-TL-03_TD | 13h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
181 | PSWP2_R-TL-03_Code | 13h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
182 | PSWP2_R-TL-03_UTP | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
183 | PSWP2_R-TL-03_UTE | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
184 | WP2_Workflow | 859h |  |  |  |  | 99 | 100 | 101
185 | WP2_W-AM-01,EC-AM-02_Workflow - AM - Approval Ext Config - AM - Approval | 841h |  |  |  |  | 99 | 100 | 101
186 | PS_WP2_W-AM-01,EC-AM-02_TD | 58h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
187 | PS_WP2_W-AM-01,EC-AM-02_Code | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
188 | PS_WP2_W-AM-01,EC-AM-02_Code | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
189 | PS_WP2_W-AM-01,EC-AM-02_UTP | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
190 | PS_WP2_W-AM-01,EC-AM-02_UTP | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
191 | PS_WP2_W-AM-01,EC-AM-02_UTE | 34h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
192 | PS_WP2_W-AM-01,EC-AM-02_UTE | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
193 | WP2_W-TL-01_Workflow - TL - Approval Process Error Notification | 508h |  |  |  |  | 99 | 100 | 101
194 | PS_WP2_W-TL-01_TD | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
195 | WP2_W-TL-01_Code | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
196 | WP2_W-TL-01_UTP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
197 | WP2_W-TL-01_UTE | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
198 | WP2_Extended Config_ONSHORE | 100h |  |  |  |  | 99 | 100 | 101
199 | WP2_EC-AM-03 - Ext Config - AM - Collisions | 100h |  |  |  |  | 99 | 100 | 101
200 | PS_WP2_EC-AM-03_TD/Code | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
201 | PS_WP2_EC-AM-03_UTP | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
202 | PS_WP2_EC-AM-03_UTE | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
203 | WP3 - Annual Leave Processing & BackOffice | 815h |  |  |  |  | 99 | 100 | 101
204 | WP3_Extension | 815h |  |  |  |  | 99 | 100 | 101
205 | WP3_E-AM-01_ Extension - AM - Annual Leave Processing | 670h |  |  |  |  | 99 | 100 | 101
206 | PS_WP3_E-AM-01_TD | 41h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
207 | PS_WP3_E-AM-01_Code | 41h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
208 | PS_WP3_E-AM-01_UTP | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
209 | PS_WP3_E-AM-01_UTE | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
210 | WP3_E-AM-02_Extension - AM - Back Office | 815h |  |  |  |  | 99 | 100 | 101
211 | PS_WP3_E-AM-02_TD | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
212 | PS_WP3_E-AM-02_Code | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
213 | PS_WP3_E-AM-02_UTP | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
214 | PS_WP3_E-AM-02_UTE | 26h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
215 | WP3_E-AM-02_Extension - AM - Back Office - CHR00002, CHR00033 | 422h |  |  |  |  | 99 | 100 | 101
216 | PS_WP3_E-AM-02_TD_CHR00002_CHR00033 | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
217 | PS_WP3_E-AM-02_Code_CHR00002_CHR00033 | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
218 | PS_WP3_E-AM-02_UTP_CHR00002_CHR00033 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
219 | PS_WP3_E-AM-02_UTE_CHR00002_CHR00033 | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
220 | WP3_E-AM-08_Extension - AM - Work Schedule Overview | 552h |  |  |  |  | 99 | 100 | 101
221 | PS_WP3_E-AM-08_TD | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
222 | PS_WP3_E-AM-08_TD | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
223 | PS_WP3_E-AM-08_Code | 31h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
224 | PS_WP3_E-AM-08_UTP | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
225 | PS_WP3_E-AM-08_UTE | 29h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
226 | WP3_Interface | 649h |  |  |  |  | 99 | 100 | 101
227 | WP3_I-AM-01_­Interface - AM - Excel2CI | 649h |  |  |  |  | 99 | 100 | 101
228 | PS_WP3_I-AM-01_TD | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
229 | PS_WP3_I-AM-01_Code | 34h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
230 | PS_WP3_I-AM-01_UTP | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
231 | PS_WP3_I-AM-01_UTE | 31h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
232 | WP4 - Annual & Monthly Processes | 557h |  |  |  |  | 99 | 100 | 101
233 | WP4_Extension | 557h |  |  |  |  | 99 | 100 | 101
234 | WP4_­E-TL-18_Extension - TL - Yearly Processes CHR00041, CHR00042, CHR00043 | 557h |  |  |  |  | 99 | 100 | 101
235 | PS_WP4_­E-TL-18_TD | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
236 | PS_WP4_­E-TL-18_Code | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
237 | PS_WP4_­E-TL-18_UTP | 51h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
238 | PS_WP4_­E-TL-18_UTE | 119h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
239 | WP5 - TSM, Planning Tool | 1290h |  |  |  |  | 99 | 100 | 101
240 | WP5_Extension | 866h |  |  |  |  | 99 | 100 | 101
241 | WP5_E-TL-13_Extension - TL - Planning Tool | 866h |  |  |  |  | 99 | 100 | 101
242 | PS_WP5_E-TL-13_TD | 129h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
243 | PS_WP5_E-TL-13_Code | 129h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
244 | PS_WP5_E-TL-13_UTP | 52h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
245 | PS_WP5_E-TL-13_UTE | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
246 | PS_WP5_E-TL-13_UTE | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
247 | WP5 - Extended Config - ONSHORE | 784h |  |  |  |  | 99 | 100 | 101
248 | WP5_EC-AM-10_Ext Config - AM - Medical Leave | 777h |  |  |  |  | 99 | 100 | 101
249 | PS_WP5_EC-AM-10_TD/Code | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
250 | PS_WP5_EC-AM-10_UTP | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
251 | PS_WP5_EC-AM-10_UTE | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
252 | WP5_EC-AM-11_Ext Config - AM - Part Time - CHR00028 | 323h |  |  |  |  | 99 | 100 | 101
253 | PS_WP5_EC-AM-11_Code_CHR00028 | 43h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
254 | PS_WP5_EC-AM-11_UTP_CHR00028 | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
255 | PS_WP5_EC-AM-11_UTE_CHR00028 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
256 | WP5_EC-AM-11_Ext Config - AM - Part Time | 121h |  |  |  |  | 99 | 100 | 101
257 | PS_WP5_EC-AM-11_TD/Code | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
258 | PS_WP5_EC-AM-11_UTP | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
259 | PS_WP5_EC-AM-11_UTE | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
260 | WP5_EC-AM-18_Ext Config - AM - TSM | 267h |  |  |  |  | 99 | 100 | 101
261 | PS_WP5_EC-AM-18_TD/Code | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
262 | PS_WP5_EC-AM-18_UTP | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
263 | PS_WP5_EC-AM-18_UTE | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
264 | WP6 - Integration, Security, Reporting | 1271h |  |  |  |  | 99 | 100 | 101
265 | WP6_Extension | 1271h |  |  |  |  | 99 | 100 | 101
266 | WP6_E-AM-09_Extension - BO Reporting AE for AM | 644h |  |  |  |  | 99 | 100 | 101
267 | PS_WP6_E-AM-09_TD | 74h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
268 | PS_WP6_E-AM-09_Code | 74h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
269 | PS_WP6_E-AM-09_UTP | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
270 | PS_WP6_E-AM-09_UTE | 69h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
271 | WP6_E-TL-02_Extension - TL - Automated TL Enrollment | 644h |  |  |  |  | 99 | 100 | 101
272 | PS_WP6_E-TL-02_TD | 35h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
273 | PS_WP6_E-TL-02_Code | 35h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
274 | PS_WP6_E-TL-02_UTP | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
275 | PS_WP6_E-TL-02_UTE | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
276 | WP6_E-TL-16_Extension - TL - Timesheet prepopulation | 1271h |  |  |  |  | 99 | 100 | 101
277 | PS_WP6_E-TL-16_TD | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
278 | PS_WP6_E-TL-16_Code | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
279 | PS_WP6_E-TL-16_UTP | 42h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
280 | PS_WP6_E-TL-16_UTE | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
281 | PS_WP6_E-TL-16_UTE | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
282 | WP6_E-TL-16_Extension - TL - Timesheet prepopulation | 166h |  |  |  |  | 99 | 100 | 101
283 | PS_WP6_E-TL-16_TD_CHR00016 | 29h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
284 | PS_WP6_E-TL-16_Code_CHR00016 | 29h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
285 | PS_WP6_E-TL-16_UTP_CHR00016 | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
286 | PS_WP6_E-TL-16_UTE_CHR00016 | 27h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
287 | WP6_E-AM-07_Extension - AM - Recovery Flex Time | 647h |  |  |  |  | 99 | 100 | 101
288 | PS_WP6_E-AM-07_TD | 33h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
289 | PS_WP6_E-AM-07_Code | 33h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
290 | PS_WP6_E-AM-07_UTP | 13h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
291 | PS_WP6_E-AM-07_UTE | 31h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
292 | WP7 - Interfaces | 1155h |  |  |  |  | 99 | 100 | 101
293 | WP7_I-AM-02_Interface - AM - PS to PGP (Page/Navigation) - 10% | 559h |  |  |  |  | 99 | 100 | 101
294 | PS_WP7_I-AM-02_Page/Navigation_TD | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
295 | PS_WP7_I-AM-02_Page/Navigation_Code | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
296 | PS_WP7_I-AM-02_Page/Navigation_UTP | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
297 | PS_WP7_I-AM-02_Page/Navigation_UTE | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
298 | WP7_I-AM-02_Interface - AM - PS to PGP (App Engine) - 40% | 1155h |  |  |  |  | 99 | 100 | 101
299 | PS_WP7_I-AM-02_App Engine_TD | 87h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
300 | PS_WP7_I-AM-02_App Engine_Code | 87h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
301 | PS_WP7_I-AM-02_App Engine_UTP | 35h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
302 | PS_WP7_I-AM-02_App Engine_UTE | 26h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
303 | PS_WP7_I-AM-02_App Engine_UTE | 26h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
304 | PS_WP7_I-AM-02_App Engine_UTE | 26h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
305 | PS_WP7_I-AM-02_App Engine_TD_CHR00021 | 43h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
306 | PS_WP7_I-AM-02_App Engine_Code_CHR00021 | 43h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
307 | PS_WP7_I-AM-02_App Engine_UTP_CHR00021 | 17h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
308 | PS_WP7_I-AM-02_App Engine_UTE_CHR00021 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
309 | PS_WP7_I-AM-02_App Engine_UTE_CHR00021 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
310 | WP8 - Conversions | 947h |  |  |  |  | 99 | 100 | 101
311 | WP8_Build | 947h |  |  |  |  | 99 | 100 | 101
312 | WP8_C-TL-01_Conversion - Schift/Schedules | 147h |  |  |  |  | 99 | 100 | 101
313 | PS_WP8_C-TL-01_TD | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
314 | PS_WP8_C-TL-01_Code | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
315 | PS_WP8_C-TL-01_UTP | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
316 | PS_WP8_C-TL-01_UTE | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
317 | WP8_C-TL-02_Conversion - Employee Paygroup Assignment | 600h |  |  |  |  | 99 | 100 | 101
318 | PS_WP8_C-TL-02_TD | 29h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
319 | PS_WP8_C-TL-02_Code | 29h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
320 | PS_WP8_C-TL-02_UTP | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
321 | PS_WP8_C-TL-02_UTE | 27h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
322 | WP8_C-TL-03_Conversion - Absence History | 479h |  |  |  |  | 99 | 100 | 101
323 | PS_WP8_C-TL-03_TD | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
324 | PS_WP8_C-TL-03_Code | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
325 | PS_WP8_C-TL-03_UTP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
326 | PS_WP8_C-TL-03_UTE | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
327 | WP8_C-TL-04_Conversion - Absence Balance | 495h |  |  |  |  | 99 | 100 | 101
328 | PS_WP8_C-TL-04_TD | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
329 | PS_WP8_C-TL-04_Code | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
330 | PS_WP8_C-TL-04_Code | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
331 | PS_WP8_C-TL-04_UTP | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
332 | PS_WP8_C-TL-04_UTE | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
333 | WP8_C-TL-05_Conversion - Accumulators | 224h |  |  |  |  | 99 | 100 | 101
334 | PS_WP8_C-TL-05_TD | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
335 | PS_WP8_C-TL-05_Code | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
336 | PS_WP8_C-TL-05_UTP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
337 | PS_WP8_C-TL-05_UTE | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
338 | WP8_C-TL-06_Conversion - Employee T&L Enrollment | 638h |  |  |  |  | 99 | 100 | 101
339 | PS_WP8_C-TL-06_TD | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
340 | PS_WP8_C-TL-06_Code | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
341 | PS_WP8_C-TL-06_UTP | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
342 | PS_WP8_C-TL-06_UTE | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
343 | WP8_C-TL-07_Conversion - Compensatory Time Off Plan Enrollment | 5h |  |  |  |  | 99 | 100 | 101
344 | PS_WP8_C-TL-07_TD | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
345 | WP8_C-TL-08_Conversion - Work Schedule Assignment | 672h |  |  |  |  | 99 | 100 | 101
346 | PS_WP8_C-TL-08_TD | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
347 | PS_WP8_C-TL-08_Code | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
348 | PS_WP8_C-TL-08_UTP | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
349 | PS_WP8_C-TL-08_UTE | 42h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
350 | WP8_C-TL-09_Conversion - Reported Overtime History | 362h |  |  |  |  | 99 | 100 | 101
351 | PS_WP8_C-TL-09_TD | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
352 | PS_WP8_C-TL-09_Code | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
353 | PS_WP8_C-TL-09_UTP | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
354 | PS_WP8_C-TL-09_UTE | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
355 | WP8_C-TL-10_Conversion - Compensatory Time Off Plan Balance | 357h |  |  |  |  | 99 | 100 | 101
356 | PS_WP8_C-TL-10_TD | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
357 | PS_WP8_C-TL-10_Code | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
358 | PS_WP8_C-TL-10_UTP | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
359 | PS_WP8_C-TL-10_UTE | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
360 | TL MSS Security - CHR00026 | 223h |  |  |  |  | 99 | 100 | 101
361 | PS_WPX_TL-MSS-Security_TD_CHR00026 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
362 | PS_WPX_TL-MSS-Security_Code_CHR00026 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
363 | PS_WPX_TL-MSS-Security_CTP_CHR00026 | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
364 | PS_WPX_TL-MSS-Security_CTE_CHR00026 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold