## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Timber House | 1 |  |  | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 | 368.375
2 | Voorbereiding | 1.1 |  |  | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 | 222.375
1 | Bouwvergunning | 1.1.1 | 3SS-4w |  | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 0.375
3 | Technische bespreking | 1.1.2 | 4SS-4w | SS1-4w | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 0.375
4 | Ondertekening definitief contract | 1.1.3 | 5FS-16w | SS3-4w | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 0.375
5 | Bestelling technisch bureau | 1.1.4 | 10SS-2w 4d | FS4-16w | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 0.375
6 | Bestelling projectleiders | 1.1.5 | 10SS-2w 4d |  | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 0.375
7 | Funderingen | 1.2 | 10SS-5w |  | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 7.375
9 | Montage | 1.3 |  |  | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 | 24.375
8 | Schrijnwerk (levering) | 1.3.1 | 10SS-1w | FS11+1w | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 0.375
10 | Montage houten kit | 1.3.2 |  | SS5-2w 4d;SS6-2w 4d;SS8-1w;FS14;FS32;SS7-5w;FS20+1d;FS22+1d;FS23+1d;FS24+1d;FS11 | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 11.375
11 | Schrijnwerk (plaatsing) | 1.3.3 | 10FS;8FS+1w | FS13+2d;FS17+2w | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 0.375
13 | Glas | 1.3.4 | 11FS+2d | FS19 | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 0.375
15 | Stelling | 1.4 |  |  | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 | 53.375
14 | Stelling (opbouw) | 1.4.1 | 10FS |  | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 0.375
16 | Stelling (afbraak) | 1.4.2 | 39FS |  | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 0.375
18 | Isolatie | 1.5 |  |  | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 | 13.375
17 | Muurisolatie | 1.5.1 | 11FS+2w | FS29 | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 6.375
19 | Pur | 1.5.2 | 13FS;22FS;23FS | FS25;FS24 | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 0.375
21 | Technieken (eerste fase) | 1.6 |  |  | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 | 10.375
20 | Elektriciteit (eerste fase) | 1.6.1 | 10FS+1d |  | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 6.375
22 | Sanitair - ventilatie (eerste fase) | 1.6.2 | 10FS+1d | FS19 | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 6.375
23 | Verwarming (eerste fase) | 1.6.3 | 10FS+1d | FS19 | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 6.375
24 | Vloerverwarming | 1.6.4 | 19FS;10FS+1d | FS25 | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2.375
25 | Chape | 1.7 | 24FS;19FS | FS35+1w | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 | 0.375
27 | Zinkwerken | 1.8 |  |  | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 | 77.375
26 | Goten | 1.8.1 | 32FS+1w 2d | FS34;FS28 | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 1.375
28 | Afleiders | 1.8.2 | 26FS;29FS;38FS |  | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 | 0.375
29 | Metselwerken | 1.9 | 17FS | FS30+2w;FS39;FS28 | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 22.375
30 | Voegwerken | 1.10 | 29FS+2w | SS31 | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 | 1.375
31 | Stabilisé | 1.11 | 30SS | FS40 | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 | 0.375
33 | Dakwerken | 1.12 |  |  | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 | 17.375
32 | Pannenlatten | 1.12.1 | 10FS | FS26+1w 2d;FS34 | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 0.375
34 | Pannen | 1.12.2 | 26FS;32FS | FS55 | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2.375
55 | Pannen (fase 2) | 1.12.3 | 34FS |  | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 0.375
35 | Vloeren (eerste fase) | 1.13 | 25FS+1w | FS42;FS38+1w | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 | 2.375
37 | Afwerking | 1.14 |  |  | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 | 58.375
38 | Afwerking (intern) | 1.14.1 | 35FS+1w | SS41+2w;FF43;SS44+1w;FS45;FS48;FS49;FS47;SS40-1w;FS28;SS54 | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 | 30.375
54 | Trappen | 1.14.2 | 38SS |  | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 | 0.375
39 | Afwerking (extern) | 1.14.3 | 29FS | FS16;FS49 | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 | 7.375
40 | Houten terras | 1.14.4 | 31FS;38SS-1w | FS49 | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 | 1.375
41 | Maatwerk | 1.14.5 | 38SS+2w | FS49 | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 | 1.375
42 | Gips | 1.14.6 | 35FS | FS49 | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 | 2.375
43 | Opstop gips | 1.14.7 | 38FF | FS49 | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 | 1.375
44 | Vloeren (tweede fase) | 1.15 | 38SS+1w | FS49;FS47 | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 | 1.375
46 | Technieken tweede fase | 1.16 |  |  | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 | 1.375
45 | Elektriciteit (tweede fase) | 1.16.1 | 38FS | FS49 | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 | 1.375
47 | Sanitair - ventilatie (tweede fase) | 1.16.2 | 44FS;38FS | FS49 | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 | 1.375
48 | Verwarming (tweede fase) | 1.16.3 | 38FS | FS49 | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 | 1.375
50 | Voorlopige oplevering | 1.17 |  |  | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 | 11.375
49 | Oplevering | 1.17.1 | 38FS;39FS;40FS;41FS;42FS;43FS;44FS;45FS;47FS;48FS | FS52+1w | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 | 0.375
52 | Parket | 1.17.2 | 49FS+1w |  | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 | 3.375
53 | Oplevering | 1.18 |  |  | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Timber House | 1728h |  |  |  |  | 99 | 100 | 101
2 | Voorbereiding | 952h |  |  |  |  | 99 | 100 | 101
1 | Bouwvergunning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Technische bespreking | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Ondertekening definitief contract | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Bestelling technisch bureau | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Bestelling projectleiders | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Funderingen | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Montage | 152h |  |  |  |  | 99 | 100 | 101
8 | Schrijnwerk (levering) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Montage houten kit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Schrijnwerk (plaatsing) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Glas | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Stelling | 288h |  |  |  |  | 99 | 100 | 101
14 | Stelling (opbouw) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Stelling (afbraak) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Isolatie | 80h |  |  |  |  | 99 | 100 | 101
17 | Muurisolatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Pur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Technieken (eerste fase) | 72h |  |  |  |  | 99 | 100 | 101
20 | Elektriciteit (eerste fase) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Sanitair - ventilatie (eerste fase) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Verwarming (eerste fase) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Vloerverwarming | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Chape | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Zinkwerken | 392h |  |  |  |  | 99 | 100 | 101
26 | Goten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Afleiders | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Metselwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Voegwerken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Stabilisé | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Dakwerken | 112h |  |  |  |  | 99 | 100 | 101
32 | Pannenlatten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Pannen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Pannen (fase 2) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Vloeren (eerste fase) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Afwerking | 304h |  |  |  |  | 99 | 100 | 101
38 | Afwerking (intern) | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Trappen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Afwerking (extern) | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Houten terras | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Maatwerk | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Gips | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Opstop gips | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Vloeren (tweede fase) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Technieken tweede fase | 16h |  |  |  |  | 99 | 100 | 101
45 | Elektriciteit (tweede fase) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Sanitair - ventilatie (tweede fase) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Verwarming (tweede fase) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Voorlopige oplevering | 80h |  |  |  |  | 99 | 100 | 101
49 | Oplevering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Parket | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Oplevering | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-09-23 17:00 |  | TP Name | 23/09/2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 40d | [5 empty] | 842.58 |  | 0.1682% |  | 842.58 | 842.58
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 40d | [5 empty] | 842.58 |  | 93.17% |  | 842.58 | 842.58
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 |  | 0 | 0 | 23047.4609 | 6d | 0 | 0 | 0 | 23047.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 |  | 0 | 0 | 1724.47 | 1d | 0 | 0 | 0 | 1724.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 |  | 0 | 0 | 169353.5 | 10d | 0 | 0 | 0 | 169353.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 |  | 0 | 0 | 1724.47 | 1d | 0 | 0 | 0 | 1724.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 |  | 0 | 0 | 13566.9102 | 1d | 0 | 0 | 0 | 13566.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 |  | 0 | 0 | 18367.6602 | 5d | 0 | 0 | 0 | 18367.6602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 |  | 0 | 0 | 3673.53 | 1d | 0 | 0 | 0 | 3673.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 |  | 0 | 0 | 8928.5703 | 5d | 0 | 0 | 0 | 8928.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 |  | 0 | 0 | 20995.9902 | 5d | 0 | 0 | 0 | 20995.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 |  | 0 | 0 | 10695.25 | 5d | 0 | 0 | 0 | 10695.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 |  | 0 | 0 | 10786.4102 | 3d | 0 | 0 | 0 | 10786.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 |  | 0 | 0 | 4263.7402 | 1d | 0 | 0 | 0 | 4263.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 |  | 0 | 0 | 6536.2002 | 2d | 0 | 0 | 0 | 6536.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 |  | 0 | 0 | 29433.6797 | 15d | 0 | 0 | 0 | 29433.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 |  | 0 | 0 | 13188.3799 | 3d | 0 | 0 | 0 | 13188.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 |  | 0 | 0 | 19974.6504 | 3d | 0 | 0 | 0 | 19974.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 |  | 0 | 0 | 1599.41 | 3d | 0 | 0 | 0 | 1599.41 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-02-08 17:00 |  | TP Name | 08/02/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 120d | [5 empty] | 904.3 |  | 0.1805% |  | 904.3 | 904.3
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 |  | 0 | 0 | 23047.4609 | 6d | 0 | 0 | 0 | 23047.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 |  | 0 | 0 | 1724.47 | 1d | 0 | 0 | 0 | 1724.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 |  | 0 | 0 | 169353.5 | 10d | 0 | 0 | 0 | 169353.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 |  | 0 | 0 | 1724.47 | 1d | 0 | 0 | 0 | 1724.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 |  | 0 | 0 | 13566.9102 | 1d | 0 | 0 | 0 | 13566.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 |  | 0 | 0 | 18367.6602 | 5d | 0 | 0 | 0 | 18367.6602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 |  | 0 | 0 | 3673.53 | 1d | 0 | 0 | 0 | 3673.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 |  | 0 | 0 | 8928.5703 | 5d | 0 | 0 | 0 | 8928.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 |  | 0 | 0 | 20995.9902 | 5d | 0 | 0 | 0 | 20995.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 |  | 0 | 0 | 10695.25 | 5d | 0 | 0 | 0 | 10695.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 |  | 0 | 0 | 10786.4102 | 3d | 0 | 0 | 0 | 10786.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 |  | 0 | 0 | 4263.7402 | 1d | 0 | 0 | 0 | 4263.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 |  | 0 | 0 | 6536.2002 | 2d | 0 | 0 | 0 | 6536.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 |  | 0 | 0 | 29433.6797 | 15d | 0 | 0 | 0 | 29433.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 |  | 0 | 0 | 13188.3799 | 3d | 0 | 0 | 0 | 13188.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 |  | 0 | 0 | 19974.6504 | 3d | 0 | 0 | 0 | 19974.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 |  | 0 | 0 | 1599.41 | 3d | 0 | 0 | 0 | 1599.41 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2012-02-27 17:00 |  | TP Name | 27/02/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 133d | [5 empty] | 198466.0508 |  | 38.93% |  | 195029.7309 | 195029.7309
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 6d | [5 empty] | 174514.2899 |  | 91.8% |  | 171077.97 | 171077.97
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 1d | 169353.5 | 0 | 9d | 3123.9299 | 0 | 172477.4299 | 0 | 10% | Started | 169353.5 | 169353.5 | 100 | 10 | 10 | 100 | 101.8446 | 10
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 |  | 0 | 0 | 1724.47 | 1d | 0 | 0 | 0 | 1724.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 |  | 0 | 0 | 13566.9102 | 1d | 0 | 0 | 0 | 13566.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 |  | 0 | 0 | 18367.6602 | 5d | 0 | 0 | 0 | 18367.6602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 |  | 0 | 0 | 3673.53 | 1d | 0 | 0 | 0 | 3673.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 |  | 0 | 0 | 8928.5703 | 5d | 0 | 0 | 0 | 8928.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 |  | 0 | 0 | 20995.9902 | 5d | 0 | 0 | 0 | 20995.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 |  | 0 | 0 | 10695.25 | 5d | 0 | 0 | 0 | 10695.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 |  | 0 | 0 | 10786.4102 | 3d | 0 | 0 | 0 | 10786.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 |  | 0 | 0 | 4263.7402 | 1d | 0 | 0 | 0 | 4263.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 |  | 0 | 0 | 6536.2002 | 2d | 0 | 0 | 0 | 6536.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 |  | 0 | 0 | 29433.6797 | 15d | 0 | 0 | 0 | 29433.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 |  | 0 | 0 | 13188.3799 | 3d | 0 | 0 | 0 | 13188.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 |  | 0 | 0 | 19974.6504 | 3d | 0 | 0 | 0 | 19974.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 |  | 0 | 0 | 1599.41 | 3d | 0 | 0 | 0 | 1599.41 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2012-03-02 17:00 |  | TP Name | 02/03/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 137d | [5 empty] | 198466.0508 |  | 38.93% |  | 195029.7309 | 195029.7309
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 10d | [5 empty] | 174514.2899 |  | 91.8% |  | 171077.97 | 171077.97
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 5d | 169353.5 | 0 | 5d | 3123.9299 | 0 | 172477.4299 | 0 | 50% | Started | 169353.5 | 169353.5 | 100 | 50 | 50 | 100 | 101.8446 | 50
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 |  | 0 | 0 | 1724.47 | 1d | 0 | 0 | 0 | 1724.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 |  | 0 | 0 | 13566.9102 | 1d | 0 | 0 | 0 | 13566.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 |  | 0 | 0 | 18367.6602 | 5d | 0 | 0 | 0 | 18367.6602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 |  | 0 | 0 | 3673.53 | 1d | 0 | 0 | 0 | 3673.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 |  | 0 | 0 | 8928.5703 | 5d | 0 | 0 | 0 | 8928.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 |  | 0 | 0 | 20995.9902 | 5d | 0 | 0 | 0 | 20995.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 |  | 0 | 0 | 10695.25 | 5d | 0 | 0 | 0 | 10695.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 |  | 0 | 0 | 10786.4102 | 3d | 0 | 0 | 0 | 10786.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 |  | 0 | 0 | 4263.7402 | 1d | 0 | 0 | 0 | 4263.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 |  | 0 | 0 | 6536.2002 | 2d | 0 | 0 | 0 | 6536.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 |  | 0 | 0 | 29433.6797 | 15d | 0 | 0 | 0 | 29433.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 |  | 0 | 0 | 13188.3799 | 3d | 0 | 0 | 0 | 13188.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 |  | 0 | 0 | 19974.6504 | 3d | 0 | 0 | 0 | 19974.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 |  | 0 | 0 | 1599.41 | 3d | 0 | 0 | 0 | 1599.41 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2012-03-28 17:00 |  | TP Name | 28/03/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 155d | [5 empty] | 311426.5719 |  | 58.57% |  | 293460.1517 | 312183.8321
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 190118.0601 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 3123.9299 | 0 | 172477.4299 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 101.8446 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 0 | 0 | 13566.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 100 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 10d | [5 empty] | 30.86 |  | 50% |  | 30.86 | 30.86
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 3d | [5 empty] | 18367.6602 |  | 83.33% |  | 18367.6602 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 3d | 18367.6602 | 0 | 1d | 0 | 0 | 18367.6602 | 0 | 75% | Started | 18367.6602 | 18367.6602 | 100 | 60 | 75 | 100 | 100 | 75
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 |  | 0 | 0 | 3673.53 | 1d | 0 | 0 | 0 | 3673.53 | 0% | Not Started | 0 | 3673.53 | 100 |  | 0 | 100 |  | 0
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 9d | [5 empty] | 44321.8707 |  | 79.02% |  | 40619.8105 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 798.06 | 0 | 9726.6303 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 108.9383 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d | 20995.9902 | 0 | 4h | 2278.8601 | 0 | 23274.8503 | 0 | 93.33% | Started | 20995.9902 | 20995.9902 | 100 | 140 | 93.3333 | 100 | 110.8538 | 93.3333
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d | 10695.25 | 0 | 4h | 625.14 | 0 | 11320.39 | 0 | 93.33% | Started | 10695.25 | 10695.25 | 100 | 140 | 93.3333 | 100 | 105.845 | 93.3333
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 |  | 0 | 0 | 10786.4102 | 3d | 0 | 0 | 0 | 10786.4102 | 0% | Not Started | 0 | 10786.4102 | 100 |  | 0 | 100 |  | 0
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 |  | 0 | 0 | 4263.7402 | 1d | 0 | 0 | 0 | 4263.7402 | 0% | Not Started | 0 | 4263.7402 | 100 |  | 0 | 100 |  | 0
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 7d | [5 empty] | 6536.2002 |  | 68.42% |  | 6536.2002 | 6536.2002
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 |  | 0 | 0 | 29433.6797 | 15d | 0 | 0 | 0 | 29433.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 13d | [5 empty] | 28100.1599 |  | 80% |  | 17584.5098 | 17584.5098
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 4d | 13188.3799 | 0 | 1d | 7886.7402 | 0 | 21075.1201 | 0 | 80% | Started | 13188.3799 | 13188.3799 | 100 | 133.3333 | 80 | 100 | 159.8007 | 80
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 |  | 0 | 0 | 19974.6504 | 3d | 0 | 0 | 0 | 19974.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 |  | 0 | 0 | 1599.41 | 3d | 0 | 0 | 0 | 1599.41 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2012-04-12 17:00 |  | TP Name | 12/04/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 164d | [5 empty] | 355320.1918 |  | 67.33% |  | 337353.7716 | 367587.7021
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 190118.0601 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 3123.9299 | 0 | 172477.4299 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 101.8446 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 0 | 0 | 13566.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 100 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 19d | [5 empty] | 30.86 |  | 50% |  | 30.86 | 30.86
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 100% |  | 22041.1902 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 100% | Finished | 18367.6602 | 18367.6602 | 100 | 80 | 100 | 100 | 100 | 100
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 100% | Finished | 3673.53 | 3673.53 | 100 | 100 | 100 | 100 | 100 | 100
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 55108.2808 |  | 100% |  | 51406.2207 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 798.06 | 0 | 9726.6303 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 108.9383 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 2278.8601 | 0 | 23274.8503 | 0 | 100% | Finished | 20995.9902 | 20995.9902 | 100 | 150 | 100 | 100 | 110.8538 | 100
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 100% | Finished | 10695.25 | 10695.25 | 100 | 150 | 100 | 100 | 105.845 | 100
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 100% | Finished | 10786.4102 | 10786.4102 | 100 | 100 | 100 | 100 | 100 | 100
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 |  | 0 | 0 | 4263.7402 | 1d | 0 | 0 | 0 | 4263.7402 | 0% | Not Started | 0 | 4263.7402 | 100 |  | 0 | 100 |  | 0
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 16d | [5 empty] | 6536.2002 |  | 68.42% |  | 6536.2002 | 6536.2002
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 6d | 29433.6797 | 0 | 15d | 0 | 0 | 29433.6797 | 0 | 28.57% | Started | 29433.6797 | 29433.6797 | 100 | 40 | 28.5714 | 100 | 100 | 28.5714
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 22d | [5 empty] | 28100.1599 |  | 80% |  | 17584.5098 | 21980.6396
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 100% | Finished | 13188.3799 | 13188.3799 | 100 | 166.6667 | 100 | 100 | 159.8007 | 100
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 4396.1299 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 |  | 0 | 0 | 19974.6504 | 3d | 0 | 0 | 0 | 19974.6504 | 0% | Not Started | 0 | 19974.6504 | 100 |  | 0 | 100 |  | 0
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1599.41
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 |  | 0 | 0 | 1599.41 | 3d | 0 | 0 | 0 | 1599.41 | 0% | Not Started | 0 | 1599.41 | 100 |  | 0 | 100 |  | 0
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2012-04-14 17:00 |  | TP Name | 14/04/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 165d | [5 empty] | 356670.192 |  | 67.33% |  | 337353.7716 | 367587.7021
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 191468.0603 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 4473.9302 | 0 | 173827.4302 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 102.6418 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 0 | 0 | 13566.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 100 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 20d | [5 empty] | 30.86 |  | 50% |  | 30.86 | 30.86
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 100% |  | 22041.1902 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 100% | Finished | 18367.6602 | 18367.6602 | 100 | 80 | 100 | 100 | 100 | 100
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 100% | Finished | 3673.53 | 3673.53 | 100 | 100 | 100 | 100 | 100 | 100
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 55108.2808 |  | 100% |  | 51406.2207 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 798.06 | 0 | 9726.6303 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 108.9383 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 2278.8601 | 0 | 23274.8503 | 0 | 100% | Finished | 20995.9902 | 20995.9902 | 100 | 150 | 100 | 100 | 110.8538 | 100
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 100% | Finished | 10695.25 | 10695.25 | 100 | 150 | 100 | 100 | 105.845 | 100
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 100% | Finished | 10786.4102 | 10786.4102 | 100 | 100 | 100 | 100 | 100 | 100
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 |  | 0 | 0 | 4263.7402 | 1d | 0 | 0 | 0 | 4263.7402 | 0% | Not Started | 0 | 4263.7402 | 100 |  | 0 | 100 |  | 0
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 17d | [5 empty] | 6536.2002 |  | 68.42% |  | 6536.2002 | 6536.2002
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 7d | 29433.6797 | 0 | 14d | 0 | 0 | 29433.6797 | 0 | 33.33% | Started | 29433.6797 | 29433.6797 | 100 | 46.6667 | 33.3333 | 100 | 100 | 33.3333
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 23d | [5 empty] | 28100.1599 |  | 80% |  | 17584.5098 | 21980.6396
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 100% | Finished | 13188.3799 | 13188.3799 | 100 | 166.6667 | 100 | 100 | 159.8007 | 100
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 4396.1299 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 |  | 0 | 0 | 19974.6504 | 3d | 0 | 0 | 0 | 19974.6504 | 0% | Not Started | 0 | 19974.6504 | 100 |  | 0 | 100 |  | 0
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1599.41
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 |  | 0 | 0 | 1599.41 | 3d | 0 | 0 | 0 | 1599.41 | 0% | Not Started | 0 | 1599.41 | 100 |  | 0 | 100 |  | 0
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2012-05-16 17:00 |  | TP Name | 16/05/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 186d | [5 empty] | 379465.9126 |  | 72.49% |  | 363191.5722 | 471174.5223
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 191468.0603 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 4473.9302 | 0 | 173827.4302 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 102.6418 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 0 | 0 | 13566.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 100 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 41d | [5 empty] | 30.86 |  | 50% |  | 30.86 | 61.72
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 30.86 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 100% |  | 22041.1902 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 100% | Finished | 18367.6602 | 18367.6602 | 100 | 80 | 100 | 100 | 100 | 100
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 100% | Finished | 3673.53 | 3673.53 | 100 | 100 | 100 | 100 | 100 | 100
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 55108.2808 |  | 100% |  | 51406.2207 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 798.06 | 0 | 9726.6303 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 108.9383 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 2278.8601 | 0 | 23274.8503 | 0 | 100% | Finished | 20995.9902 | 20995.9902 | 100 | 150 | 100 | 100 | 110.8538 | 100
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 100% | Finished | 10695.25 | 10695.25 | 100 | 150 | 100 | 100 | 105.845 | 100
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 100% | Finished | 10786.4102 | 10786.4102 | 100 | 100 | 100 | 100 | 100 | 100
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 | 2012-04-16 08:00 | 2d | 4263.7402 | 0 | 0 | 0 | 0 | 4263.7402 | 0 | 100% | Finished | 4263.7402 | 4263.7402 | 100 | 200 | 100 | 100 | 100 | 100
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 38d | [5 empty] | 6536.2002 |  | 68.42% |  | 6536.2002 | 6536.2002
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 28d | 29433.6797 | 0 | 2d | 0 | 0 | 29433.6797 | 0 | 93.33% | Started | 29433.6797 | 29433.6797 | 100 | 186.6667 | 93.3333 | 100 | 100 | 93.3333
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 3213.1699 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 1962.25 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 44d | [5 empty] | 28100.1599 |  | 80% |  | 17584.5098 | 21980.6396
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 100% | Finished | 13188.3799 | 13188.3799 | 100 | 166.6667 | 100 | 100 | 159.8007 | 100
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 4396.1299 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 | 2012-05-16 08:00 | 1d | 19974.6504 | 0 | 0 | -3042.0801 | 0 | 16932.5703 | 0 | 100% | Finished | 19974.6504 | 19974.6504 | 100 | 33.3333 | 100 | 100 | 84.7703 | 100
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 3d | [5 empty] | 1599.41 |  | 1.792% |  | 1599.41 | 86081.1202
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 38565.1914 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 43852.3789 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 2064.1399 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 | 2012-05-14 08:00 | 3d | 1599.41 | 0 | 5d | 0 | 0 | 1599.41 | 0 | 37.5% | Started | 1599.41 | 1599.41 | 100 | 100 | 37.5 | 100 | 100 | 37.5
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 13898.8301 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2012-05-18 17:00 |  | TP Name | 18/05/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 186d | [5 empty] | 381248.7725 |  | 72.49% |  | 363191.5722 | 471174.5223
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 193250.9202 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 6256.79 | 0 | 175610.29 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 103.6945 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 0 | 0 | 13566.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 100 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 41d | [5 empty] | 30.86 |  | 50% |  | 30.86 | 61.72
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 |  | 0 | 0 | 30.86 | 1d | 0 | 0 | 0 | 30.86 | 0% | Not Started | 0 | 30.86 | 100 |  | 0 | 100 |  | 0
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 100% |  | 22041.1902 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 100% | Finished | 18367.6602 | 18367.6602 | 100 | 80 | 100 | 100 | 100 | 100
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 100% | Finished | 3673.53 | 3673.53 | 100 | 100 | 100 | 100 | 100 | 100
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 55108.2808 |  | 100% |  | 51406.2207 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 798.06 | 0 | 9726.6303 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 108.9383 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 2278.8601 | 0 | 23274.8503 | 0 | 100% | Finished | 20995.9902 | 20995.9902 | 100 | 150 | 100 | 100 | 110.8538 | 100
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 100% | Finished | 10695.25 | 10695.25 | 100 | 150 | 100 | 100 | 105.845 | 100
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 100% | Finished | 10786.4102 | 10786.4102 | 100 | 100 | 100 | 100 | 100 | 100
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 | 2012-04-16 08:00 | 2d | 4263.7402 | 0 | 0 | 0 | 0 | 4263.7402 | 0 | 100% | Finished | 4263.7402 | 4263.7402 | 100 | 200 | 100 | 100 | 100 | 100
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 38d | [5 empty] | 6536.2002 |  | 68.42% |  | 6536.2002 | 6536.2002
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 28d | 29433.6797 | 0 | 2d | 0 | 0 | 29433.6797 | 0 | 93.33% | Started | 29433.6797 | 29433.6797 | 100 | 186.6667 | 93.3333 | 100 | 100 | 93.3333
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 |  | 0 | 0 | 3213.1699 | 2d | 0 | 0 | 0 | 3213.1699 | 0% | Not Started | 0 | 3213.1699 | 100 |  | 0 | 100 |  | 0
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 |  | 0 | 0 | 1962.25 | 1d | 0 | 0 | 0 | 1962.25 | 0% | Not Started | 0 | 1962.25 | 100 |  | 0 | 100 |  | 0
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 44d | [5 empty] | 28100.1599 |  | 80% |  | 17584.5098 | 21980.6396
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 100% | Finished | 13188.3799 | 13188.3799 | 100 | 166.6667 | 100 | 100 | 159.8007 | 100
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 |  | 0 | 0 | 4396.1299 | 1d | 0 | 0 | 0 | 4396.1299 | 0% | Not Started | 0 | 4396.1299 | 100 |  | 0 | 100 |  | 0
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 | 2012-05-16 08:00 | 1d | 19974.6504 | 0 | 0 | -3042.0801 | 0 | 16932.5703 | 0 | 100% | Finished | 19974.6504 | 19974.6504 | 100 | 33.3333 | 100 | 100 | 84.7703 | 100
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 3d | [5 empty] | 1599.41 |  | 1.792% |  | 1599.41 | 86081.1202
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 |  | 0 | 0 | 38565.1914 | 20d | 0 | 0 | 0 | 38565.1914 | 0% | Not Started | 0 | 38565.1914 | 100 |  | 0 | 100 |  | 0
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 |  | 0 | 0 | 43852.3789 | 4d | 0 | 0 | 0 | 43852.3789 | 0% | Not Started | 0 | 43852.3789 | 100 |  | 0 | 100 |  | 0
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 |  | 0 | 0 | 2064.1399 | 2d | 0 | 0 | 0 | 2064.1399 | 0% | Not Started | 0 | 2064.1399 | 100 |  | 0 | 100 |  | 0
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 | 2012-05-14 08:00 | 3d | 1599.41 | 0 | 5d | 0 | 0 | 1599.41 | 0 | 37.5% | Started | 1599.41 | 1599.41 | 100 | 100 | 37.5 | 100 | 100 | 37.5
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 |  | 0 | 0 | 13898.8301 | 2d | 0 | 0 | 0 | 13898.8301 | 0% | Not Started | 0 | 13898.8301 | 100 |  | 0 | 100 |  | 0
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2012-06-22 17:00 |  | TP Name | 22/06/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 210d | [5 empty] | 502238.5021 |  | 94.04% |  | 471174.5223 | 501029.5121
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 193250.9202 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 6256.79 | 0 | 175610.29 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 103.6945 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 0 | 0 | 13566.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 100 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 48d | [5 empty] | 61.72 |  | 100% |  | 61.72 | 61.72
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-05-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 100% |  | 22041.1902 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 100% | Finished | 18367.6602 | 18367.6602 | 100 | 80 | 100 | 100 | 100 | 100
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 100% | Finished | 3673.53 | 3673.53 | 100 | 100 | 100 | 100 | 100 | 100
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 55108.2808 |  | 100% |  | 51406.2207 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 798.06 | 0 | 9726.6303 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 108.9383 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 2278.8601 | 0 | 23274.8503 | 0 | 100% | Finished | 20995.9902 | 20995.9902 | 100 | 150 | 100 | 100 | 110.8538 | 100
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 100% | Finished | 10695.25 | 10695.25 | 100 | 150 | 100 | 100 | 105.845 | 100
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 100% | Finished | 10786.4102 | 10786.4102 | 100 | 100 | 100 | 100 | 100 | 100
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 | 2012-04-16 08:00 | 2d | 4263.7402 | 0 | 0 | 0 | 0 | 4263.7402 | 0 | 100% | Finished | 4263.7402 | 4263.7402 | 100 | 200 | 100 | 100 | 100 | 100
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 62d | [5 empty] | 6536.2002 |  | 68.42% |  | 6536.2002 | 9552.6401
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 |  | 0 | 0 | 3016.4399 | 1d | 0 | 0 | 0 | 3016.4399 | 0% | Not Started | 0 | 3016.4399 | 100 |  | 0 | 100 |  | 0
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 30d | 29433.6797 | 0 | 0 | 0 | 0 | 29433.6797 | 0 | 100% | Finished | 29433.6797 | 29433.6797 | 100 | 200 | 100 | 100 | 100 | 100
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 | 2012-06-07 08:00 | 3d | 3213.1699 | 0 | 0 | 0 | 0 | 3213.1699 | 0 | 100% | Finished | 3213.1699 | 3213.1699 | 100 | 150 | 100 | 100 | 100 | 100
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 | 2012-06-07 08:00 | 1d | 1962.25 | 0 | 0 | 0 | 0 | 1962.25 | 0 | 100% | Finished | 1962.25 | 1962.25 | 100 | 100 | 100 | 100 | 100 | 100
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 67d | [5 empty] | 35125.1997 |  | 100% |  | 21980.6396 | 21980.6396
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 100% | Finished | 13188.3799 | 13188.3799 | 100 | 166.6667 | 100 | 100 | 159.8007 | 100
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-06-21 08:00 | 1d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 100 | 100 | 100 | 159.8006 | 100
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 | 2012-05-16 08:00 | 1d | 19974.6504 | 0 | 0 | -3042.0801 | 0 | 16932.5703 | 0 | 100% | Finished | 19974.6504 | 19974.6504 | 100 | 33.3333 | 100 | 100 | 84.7703 | 100
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 27d | [5 empty] | 100193.3099 |  | 96.47% |  | 86081.1202 | 89234.9203
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 | 2012-06-04 08:00 | 15d | 38565.1914 | 0 | 10d | 12637.9697 | 0 | 51203.1611 | 0 | 60% | Started | 38565.1914 | 38565.1914 | 100 | 75 | 60 | 100 | 132.7704 | 60
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 83.73 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 | 2012-05-23 08:00 | 4d | 43852.3789 | 0 | 0 | 1474.22 | 0 | 45326.5989 | 0 | 100% | Finished | 43852.3789 | 43852.3789 | 100 | 100 | 100 | 100 | 103.3618 | 100
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 | 2012-06-08 08:00 | 2d | 2064.1399 | 0 | 0 | 0 | 0 | 2064.1399 | 0 | 100% | Finished | 2064.1399 | 2064.1399 | 100 | 100 | 100 | 100 | 100 | 100
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 2003.3 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 | 2012-05-14 08:00 | 12d | 1599.41 | 0 | 0 | 0 | 0 | 1599.41 | 0 | 100% | Finished | 1599.41 | 1599.41 | 100 | 400 | 100 | 100 | 100 | 100
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 |  | 0 | 0 | 1066.77 | 2d | 0 | 0 | 0 | 1066.77 | 0% | Not Started | 0 | 1066.77 | 100 |  | 0 | 100 |  | 0
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 | 2012-06-15 08:00 | 2d | 13898.8301 | 0 | 0 | -3734.3201 | 0 | 10164.51 | 0 | 100% | Finished | 13898.8301 | 13898.8301 | 100 | 100 | 100 | 100 | 73.1321 | 100
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 22484.7498
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 |  | 0 | 0 | 3571.4299 | 2d | 0 | 0 | 0 | 3571.4299 | 0% | Not Started | 0 | 3571.4299 | 100 |  | 0 | 100 |  | 0
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 14635.2197 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 4278.1001 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1200
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 240 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 960 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2012-06-30 17:00 |  | TP Name | 30/06/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 215d | [5 empty] | 516833.7721 |  | 95.57% |  | 478829.1622 | 501029.5121
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 193250.9202 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 6256.79 | 0 | 175610.29 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 103.6945 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 0 | 0 | 13566.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 100 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 48d | [5 empty] | 61.72 |  | 100% |  | 61.72 | 61.72
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-05-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 100% |  | 22041.1902 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 100% | Finished | 18367.6602 | 18367.6602 | 100 | 80 | 100 | 100 | 100 | 100
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 100% | Finished | 3673.53 | 3673.53 | 100 | 100 | 100 | 100 | 100 | 100
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 60014.0109 |  | 100% |  | 51406.2207 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 5703.79 | 0 | 14632.3604 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 163.8825 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 2278.8601 | 0 | 23274.8503 | 0 | 100% | Finished | 20995.9902 | 20995.9902 | 100 | 150 | 100 | 100 | 110.8538 | 100
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 100% | Finished | 10695.25 | 10695.25 | 100 | 150 | 100 | 100 | 105.845 | 100
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 100% | Finished | 10786.4102 | 10786.4102 | 100 | 100 | 100 | 100 | 100 | 100
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 | 2012-04-16 08:00 | 2d | 4263.7402 | 0 | 0 | 0 | 0 | 4263.7402 | 0 | 100% | Finished | 4263.7402 | 4263.7402 | 100 | 200 | 100 | 100 | 100 | 100
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 63d | [5 empty] | 9306.0201 |  | 100% |  | 9552.6401 | 9552.6401
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 | 2012-06-25 08:00 | 1d | 3016.4399 | 0 | 0 | -246.62 | 0 | 2769.8199 | 0 | 100% | Finished | 3016.4399 | 3016.4399 | 100 | 100 | 100 | 100 | 91.8241 | 100
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 30d | 29433.6797 | 0 | 0 | 0 | 0 | 29433.6797 | 0 | 100% | Finished | 29433.6797 | 29433.6797 | 100 | 200 | 100 | 100 | 100 | 100
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 | 2012-06-07 08:00 | 3d | 3213.1699 | 0 | 0 | 0 | 0 | 3213.1699 | 0 | 100% | Finished | 3213.1699 | 3213.1699 | 100 | 150 | 100 | 100 | 100 | 100
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 | 2012-06-07 08:00 | 1d | 1962.25 | 0 | 0 | 0 | 0 | 1962.25 | 0 | 100% | Finished | 1962.25 | 1962.25 | 100 | 100 | 100 | 100 | 100 | 100
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 67d | [5 empty] | 35125.1997 |  | 100% |  | 21980.6396 | 21980.6396
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 100% | Finished | 13188.3799 | 13188.3799 | 100 | 166.6667 | 100 | 100 | 159.8007 | 100
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-06-21 08:00 | 1d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 100 | 100 | 100 | 159.8006 | 100
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 | 2012-05-16 08:00 | 1d | 19974.6504 | 0 | 0 | -3042.0801 | 0 | 16932.5703 | 0 | 100% | Finished | 19974.6504 | 19974.6504 | 100 | 33.3333 | 100 | 100 | 84.7703 | 100
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 32d | [5 empty] | 101260.08 |  | 97.66% |  | 87147.8903 | 89234.9203
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 | 2012-06-04 08:00 | 20d | 38565.1914 | 0 | 5d | 12637.9697 | 0 | 51203.1611 | 0 | 80% | Started | 38565.1914 | 38565.1914 | 100 | 100 | 80 | 100 | 132.7704 | 80
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 |  | 0 | 0 | 83.73 | 1d | 0 | 0 | 0 | 83.73 | 0% | Not Started | 0 | 83.73 | 100 |  | 0 | 100 |  | 0
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 | 2012-05-23 08:00 | 4d | 43852.3789 | 0 | 0 | 1474.22 | 0 | 45326.5989 | 0 | 100% | Finished | 43852.3789 | 43852.3789 | 100 | 100 | 100 | 100 | 103.3618 | 100
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 | 2012-06-08 08:00 | 2d | 2064.1399 | 0 | 0 | 0 | 0 | 2064.1399 | 0 | 100% | Finished | 2064.1399 | 2064.1399 | 100 | 100 | 100 | 100 | 100 | 100
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 |  | 0 | 0 | 2003.3 | 2d | 0 | 0 | 0 | 2003.3 | 0% | Not Started | 0 | 2003.3 | 100 |  | 0 | 100 |  | 0
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 | 2012-05-14 08:00 | 12d | 1599.41 | 0 | 0 | 0 | 0 | 1599.41 | 0 | 100% | Finished | 1599.41 | 1599.41 | 100 | 400 | 100 | 100 | 100 | 100
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 | 2012-06-27 08:00 | 2d | 1066.77 | 0 | 0 | 0 | 0 | 1066.77 | 0 | 100% | Finished | 1066.77 | 1066.77 | 100 | 100 | 100 | 100 | 100 | 100
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 | 2012-06-15 08:00 | 2d | 13898.8301 | 0 | 0 | -3734.3201 | 0 | 10164.51 | 0 | 100% | Finished | 13898.8301 | 13898.8301 | 100 | 100 | 100 | 100 | 73.1321 | 100
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 3d | [5 empty] | 5852.95 |  | 15.88% |  | 3571.4299 | 22484.7498
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 | 2012-06-27 08:00 | 2d | 3571.4299 | 0 | 0 | 2281.52 | 0 | 5852.95 | 0 | 100% | Finished | 3571.4299 | 3571.4299 | 100 | 100 | 100 | 100 | 163.8825 | 100
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 |  | 0 | 0 | 14635.2197 | 2d | 0 | 0 | 0 | 14635.2197 | 0% | Not Started | 0 | 14635.2197 | 100 |  | 0 | 100 |  | 0
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 |  | 0 | 0 | 4278.1001 | 2d | 0 | 0 | 0 | 4278.1001 | 0% | Not Started | 0 | 4278.1001 | 100 |  | 0 | 100 |  | 0
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1200
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 240 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 |  | 0 | 0 | 960 | 4d | 0 | 0 | 0 | 960 | 0% | Not Started | 0 | 960 | 100 |  | 0 | 100 |  | 0
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2012-08-22 17:00 |  | TP Name | 22/08/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 233d | [5 empty] | 544544.6519 |  | 99.95% |  | 500789.5121 | 501029.5121
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 192530.9202 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 5536.79 | 0 | 174890.29 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 103.2694 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 0 | 0 | 13566.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 100 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 48d | [5 empty] | 61.72 |  | 100% |  | 61.72 | 61.72
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-05-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 100% |  | 22041.1902 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 100% | Finished | 18367.6602 | 18367.6602 | 100 | 80 | 100 | 100 | 100 | 100
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 100% | Finished | 3673.53 | 3673.53 | 100 | 100 | 100 | 100 | 100 | 100
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 60014.0109 |  | 100% |  | 51406.2207 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 5703.79 | 0 | 14632.3604 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 163.8825 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 2278.8601 | 0 | 23274.8503 | 0 | 100% | Finished | 20995.9902 | 20995.9902 | 100 | 150 | 100 | 100 | 110.8538 | 100
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 100% | Finished | 10695.25 | 10695.25 | 100 | 150 | 100 | 100 | 105.845 | 100
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 100% | Finished | 10786.4102 | 10786.4102 | 100 | 100 | 100 | 100 | 100 | 100
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 | 2012-04-16 08:00 | 2d | 4263.7402 | 0 | 0 | 0 | 0 | 4263.7402 | 0 | 100% | Finished | 4263.7402 | 4263.7402 | 100 | 200 | 100 | 100 | 100 | 100
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 63d | [5 empty] | 9306.0201 |  | 100% |  | 9552.6401 | 9552.6401
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 | 2012-06-25 08:00 | 1d | 3016.4399 | 0 | 0 | -246.62 | 0 | 2769.8199 | 0 | 100% | Finished | 3016.4399 | 3016.4399 | 100 | 100 | 100 | 100 | 91.8241 | 100
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 30d | 29433.6797 | 0 | 0 | 0 | 0 | 29433.6797 | 0 | 100% | Finished | 29433.6797 | 29433.6797 | 100 | 200 | 100 | 100 | 100 | 100
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 | 2012-06-07 08:00 | 3d | 3213.1699 | 0 | 0 | 0 | 0 | 3213.1699 | 0 | 100% | Finished | 3213.1699 | 3213.1699 | 100 | 150 | 100 | 100 | 100 | 100
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 | 2012-06-07 08:00 | 1d | 1962.25 | 0 | 0 | 0 | 0 | 1962.25 | 0 | 100% | Finished | 1962.25 | 1962.25 | 100 | 100 | 100 | 100 | 100 | 100
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 67d | [5 empty] | 35125.1997 |  | 100% |  | 21980.6396 | 21980.6396
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 100% | Finished | 13188.3799 | 13188.3799 | 100 | 166.6667 | 100 | 100 | 159.8007 | 100
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-06-21 08:00 | 1d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 100 | 100 | 100 | 159.8006 | 100
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 | 2012-05-16 08:00 | 1d | 19974.6504 | 0 | 0 | -3042.0801 | 0 | 16932.5703 | 0 | 100% | Finished | 19974.6504 | 19974.6504 | 100 | 33.3333 | 100 | 100 | 84.7703 | 100
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 41d | [5 empty] | 110086.35 |  | 100% |  | 89234.9203 | 89234.9203
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 | 2012-06-04 08:00 | 25d | 38565.1914 | 0 | 0 | 12637.9697 | 0 | 51203.1611 | 0 | 100% | Finished | 38565.1914 | 38565.1914 | 100 | 125 | 100 | 100 | 132.7704 | 100
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 | 2012-07-12 08:00 | 1d | 83.73 | 0 | 0 | 3754.24 | 0 | 3837.97 | 0 | 100% | Finished | 83.73 | 83.73 | 100 | 100 | 100 | 100 | 4583.7452 | 100
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 | 2012-05-23 08:00 | 4d | 43852.3789 | 0 | 0 | 1474.22 | 0 | 45326.5989 | 0 | 100% | Finished | 43852.3789 | 43852.3789 | 100 | 100 | 100 | 100 | 103.3618 | 100
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 | 2012-06-08 08:00 | 2d | 2064.1399 | 0 | 0 | 0 | 0 | 2064.1399 | 0 | 100% | Finished | 2064.1399 | 2064.1399 | 100 | 100 | 100 | 100 | 100 | 100
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 | 2012-07-06 08:00 | 2d | 2003.3 | 0 | 0 | 2985 | 0 | 4988.3 | 0 | 100% | Finished | 2003.3 | 2003.3 | 100 | 100 | 100 | 100 | 249.0041 | 100
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 | 2012-05-14 08:00 | 12d | 1599.41 | 0 | 0 | 0 | 0 | 1599.41 | 0 | 100% | Finished | 1599.41 | 1599.41 | 100 | 400 | 100 | 100 | 100 | 100
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 | 2012-06-27 08:00 | 2d | 1066.77 | 0 | 0 | 0 | 0 | 1066.77 | 0 | 100% | Finished | 1066.77 | 1066.77 | 100 | 100 | 100 | 100 | 100 | 100
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 | 2012-06-15 08:00 | 2d | 13898.8301 | 0 | 0 | -3734.3201 | 0 | 10164.51 | 0 | 100% | Finished | 13898.8301 | 13898.8301 | 100 | 100 | 100 | 100 | 73.1321 | 100
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 10d | [5 empty] | 24497.5598 |  | 100% |  | 22484.7498 | 22484.7498
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 | 2012-06-27 08:00 | 2d | 3571.4299 | 0 | 0 | 2281.52 | 0 | 5852.95 | 0 | 100% | Finished | 3571.4299 | 3571.4299 | 100 | 100 | 100 | 100 | 163.8825 | 100
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 | 2012-07-09 08:00 | 2d | 14635.2197 | 0 | 0 | -518.77 | 0 | 14116.4497 | 0 | 100% | Finished | 14635.2197 | 14635.2197 | 100 | 100 | 100 | 100 | 96.4553 | 100
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 | 2012-07-03 08:00 | 2d | 4278.1001 | 0 | 0 | 250.06 | 0 | 4528.1601 | 0 | 100% | Finished | 4278.1001 | 4278.1001 | 100 | 100 | 100 | 100 | 105.8451 | 100
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 3d | [5 empty] | 960 |  | 80% |  | 960 | 1200
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 |  | 0 | 0 | 240 | 1d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 240 | 100 |  | 0 | 100 |  | 0
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 | 2012-08-20 08:00 | 2d | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 100% | Finished | 960 | 960 | 100 | 50 | 100 | 100 | 100 | 100
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2012-08-27 09:00 |  | TP Name | 24/08/2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Timber House | 2011-06-30 08:00 | 2012-07-02 17:00 | 216d |  |  | 501029.5121 |  |  | 501029.5121 |  | 235d | [5 empty] | 576624.0518 |  | 100% |  | 501029.5121 | 501029.5121
2 | Voorbereiding | 2011-06-30 08:00 | 2012-02-07 17:00 | 119d |  |  | 904.3 |  |  | 904.3 |  | 119d | [5 empty] | 904.3 |  | 100% |  | 904.3 | 904.3
1 | Bouwvergunning | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-06-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
3 | Technische bespreking | 2011-08-26 08:00 | 2011-08-26 17:00 | 1d |  | 0 | 780.86 | 0 | 0 | 780.86 | 2011-08-26 08:00 | 1d | 780.86 | 0 | 0 | 0 | 0 | 780.86 | 0 | 100% | Finished | 780.86 | 780.86 | 100 | 100 | 100 | 100 | 100 | 100
4 | Ondertekening definitief contract | 2011-09-23 08:00 | 2011-09-23 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2011-09-23 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
5 | Bestelling technisch bureau | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
6 | Bestelling projectleiders | 2012-02-07 08:00 | 2012-02-07 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-02-07 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingen | 2012-02-14 08:00 | 2012-02-21 17:00 | 6d |  | 0 | 23047.4609 | 0 | 0 | 23047.4609 | 2012-02-14 08:00 | 6d | 23047.4609 | 0 | 0 | 0 | 0 | 23047.4609 | 0 | 100% | Finished | 23047.4609 | 23047.4609 | 100 | 100 | 100 | 100 | 100 | 100
9 | Montage | 2012-02-20 08:00 | 2012-03-15 17:00 | 19d |  |  | 186369.3501 |  |  | 186369.3501 |  | 19d | [5 empty] | 195338.4602 |  | 100% |  | 186369.3501 | 186369.3501
8 | Schrijnwerk (levering) | 2012-02-20 08:00 | 2012-02-20 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-02-20 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
10 | Montage houten kit | 2012-02-27 08:00 | 2012-03-09 17:00 | 10d |  | 0 | 169353.5 | 0 | 0 | 169353.5 | 2012-02-27 08:00 | 12d | 169353.5 | 0 | 0 | 7519.3301 | 0 | 176872.8301 | 0 | 100% | Finished | 169353.5 | 169353.5 | 100 | 120 | 100 | 100 | 104.44 | 100
11 | Schrijnwerk (plaatsing) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 1724.47 | 0 | 0 | 1724.47 | 2012-03-15 08:00 | 1d | 1724.47 | 0 | 0 | 312.39 | 0 | 2036.86 | 0 | 100% | Finished | 1724.47 | 1724.47 | 100 | 100 | 100 | 100 | 118.1151 | 100
13 | Glas | 2012-03-15 08:00 | 2012-03-15 17:00 | 1d |  | 0 | 13566.9102 | 0 | 0 | 13566.9102 | 2012-03-15 08:00 | 1d | 13566.9102 | 0 | 0 | 825 | 0 | 14391.9102 | 0 | 100% | Finished | 13566.9102 | 13566.9102 | 100 | 100 | 100 | 100 | 106.081 | 100
15 | Stelling | 2012-03-12 08:00 | 2012-05-04 17:00 | 36d |  |  | 61.72 |  |  | 61.72 |  | 48d | [5 empty] | 61.72 |  | 100% |  | 61.72 | 61.72
14 | Stelling (opbouw) | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-03-15 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
16 | Stelling (afbraak) | 2012-05-04 08:00 | 2012-05-04 17:00 | 1d |  | 0 | 30.86 | 0 | 0 | 30.86 | 2012-05-30 08:00 | 1d | 30.86 | 0 | 0 | 0 | 0 | 30.86 | 0 | 100% | Finished | 30.86 | 30.86 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d |  |  | 22041.1902 |  |  | 22041.1902 |  | 6d | [5 empty] | 22041.1902 |  | 100% |  | 22041.1902 | 22041.1902
17 | Muurisolatie | 2012-03-27 08:00 | 2012-04-02 17:00 | 5d |  | 0 | 18367.6602 | 0 | 0 | 18367.6602 | 2012-03-26 08:00 | 4d | 18367.6602 | 0 | 0 | 0 | 0 | 18367.6602 | 0 | 100% | Finished | 18367.6602 | 18367.6602 | 100 | 80 | 100 | 100 | 100 | 100
19 | Pur | 2012-03-20 08:00 | 2012-03-20 17:00 | 1d |  | 0 | 3673.53 | 0 | 0 | 3673.53 | 2012-04-02 08:00 | 1d | 3673.53 | 0 | 0 | 0 | 0 | 3673.53 | 0 | 100% | Finished | 3673.53 | 3673.53 | 100 | 100 | 100 | 100 | 100 | 100
21 | Technieken (eerste fase) | 2012-03-13 08:00 | 2012-03-23 17:00 | 9d |  |  | 51406.2207 |  |  | 51406.2207 |  | 15d | [5 empty] | 61636.5109 |  | 100% |  | 51406.2207 | 51406.2207
20 | Elektriciteit (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 8928.5703 | 0 | 0 | 8928.5703 | 2012-03-16 08:00 | 5d | 8928.5703 | 0 | 0 | 5703.79 | 0 | 14632.3604 | 0 | 100% | Finished | 8928.5703 | 8928.5703 | 100 | 100 | 100 | 100 | 163.8825 | 100
22 | Sanitair - ventilatie (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 20995.9902 | 0 | 0 | 20995.9902 | 2012-03-20 08:00 | 7d 4h | 20995.9902 | 0 | 0 | 3901.3601 | 0 | 24897.3503 | 0 | 100% | Finished | 20995.9902 | 20995.9902 | 100 | 150 | 100 | 100 | 118.5815 | 100
23 | Verwarming (eerste fase) | 2012-03-13 08:00 | 2012-03-19 17:00 | 5d |  | 0 | 10695.25 | 0 | 0 | 10695.25 | 2012-03-20 08:00 | 7d 4h | 10695.25 | 0 | 0 | 625.14 | 0 | 11320.39 | 0 | 100% | Finished | 10695.25 | 10695.25 | 100 | 150 | 100 | 100 | 105.845 | 100
24 | Vloerverwarming | 2012-03-21 08:00 | 2012-03-23 17:00 | 3d |  | 0 | 10786.4102 | 0 | 0 | 10786.4102 | 2012-04-03 08:00 | 3d | 10786.4102 | 0 | 0 | 0 | 0 | 10786.4102 | 0 | 100% | Finished | 10786.4102 | 10786.4102 | 100 | 100 | 100 | 100 | 100 | 100
25 | Chape | 2012-03-26 08:00 | 2012-03-26 17:00 | 1d |  | 0 | 4263.7402 | 0 | 0 | 4263.7402 | 2012-04-16 08:00 | 2d | 4263.7402 | 0 | 0 | 0 | 0 | 4263.7402 | 0 | 100% | Finished | 4263.7402 | 4263.7402 | 100 | 200 | 100 | 100 | 100 | 100
27 | Zinkwerken | 2012-03-22 08:00 | 2012-06-07 17:00 | 49d |  |  | 9552.6401 |  |  | 9552.6401 |  | 63d | [5 empty] | 9306.0201 |  | 100% |  | 9552.6401 | 9552.6401
26 | Goten | 2012-03-22 08:00 | 2012-03-23 17:00 | 2d |  | 0 | 6536.2002 | 0 | 0 | 6536.2002 | 2012-03-20 08:00 | 2d | 6536.2002 | 0 | 0 | 0 | 0 | 6536.2002 | 0 | 100% | Finished | 6536.2002 | 6536.2002 | 100 | 100 | 100 | 100 | 100 | 100
28 | Afleiders | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 3016.4399 | 0 | 0 | 3016.4399 | 2012-06-25 08:00 | 1d | 3016.4399 | 0 | 0 | -246.62 | 0 | 2769.8199 | 0 | 100% | Finished | 3016.4399 | 3016.4399 | 100 | 100 | 100 | 100 | 91.8241 | 100
29 | Metselwerken | 2012-04-03 08:00 | 2012-04-25 17:00 | 15d |  | 0 | 29433.6797 | 0 | 0 | 29433.6797 | 2012-04-03 08:00 | 30d | 29433.6797 | 0 | 0 | 0 | 0 | 29433.6797 | 0 | 100% | Finished | 29433.6797 | 29433.6797 | 100 | 200 | 100 | 100 | 100 | 100
30 | Voegwerken | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 3213.1699 | 0 | 0 | 3213.1699 | 2012-06-07 08:00 | 3d | 3213.1699 | 0 | 0 | 0 | 0 | 3213.1699 | 0 | 100% | Finished | 3213.1699 | 3213.1699 | 100 | 150 | 100 | 100 | 100 | 100
31 | Stabilisé | 2012-05-14 08:00 | 2012-05-14 17:00 | 1d |  | 0 | 1962.25 | 0 | 0 | 1962.25 | 2012-06-07 08:00 | 1d | 1962.25 | 0 | 0 | 0 | 0 | 1962.25 | 0 | 100% | Finished | 1962.25 | 1962.25 | 100 | 100 | 100 | 100 | 100 | 100
33 | Dakwerken | 2012-03-12 08:00 | 2012-03-29 17:00 | 14d |  |  | 21980.6396 |  |  | 21980.6396 |  | 67d | [5 empty] | 35125.1997 |  | 100% |  | 21980.6396 | 21980.6396
32 | Pannenlatten | 2012-03-12 08:00 | 2012-03-12 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-03-12 08:00 | 2d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 200 | 100 | 100 | 159.8006 | 100
34 | Pannen | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 13188.3799 | 0 | 0 | 13188.3799 | 2012-03-23 08:00 | 5d | 13188.3799 | 0 | 0 | 7886.7402 | 0 | 21075.1201 | 0 | 100% | Finished | 13188.3799 | 13188.3799 | 100 | 166.6667 | 100 | 100 | 159.8007 | 100
55 | Pannen (fase 2) | 2012-03-29 08:00 | 2012-03-29 17:00 | 1d |  | 0 | 4396.1299 | 0 | 0 | 4396.1299 | 2012-06-21 08:00 | 1d | 4396.1299 | 0 | 0 | 2628.9099 | 0 | 7025.0398 | 0 | 100% | Finished | 4396.1299 | 4396.1299 | 100 | 100 | 100 | 100 | 159.8006 | 100
35 | Vloeren (eerste fase) | 2012-04-03 08:00 | 2012-04-05 17:00 | 3d |  | 0 | 19974.6504 | 0 | 0 | 19974.6504 | 2012-05-16 08:00 | 1d | 19974.6504 | 0 | 0 | -1364.45 | 0 | 18610.2004 | 0 | 100% | Finished | 19974.6504 | 19974.6504 | 100 | 33.3333 | 100 | 100 | 93.1691 | 100
37 | Afwerking | 2012-04-10 08:00 | 2012-06-07 17:00 | 38d |  |  | 89234.9203 |  |  | 89234.9203 |  | 41d | [5 empty] | 135169.0797 |  | 100% |  | 89234.9203 | 89234.9203
38 | Afwerking (intern) | 2012-05-07 08:00 | 2012-06-06 17:00 | 20d |  | 0 | 38565.1914 | 0 | 0 | 38565.1914 | 2012-06-04 08:00 | 25d | 38565.1914 | 0 | 0 | 12637.9697 | 0 | 51203.1611 | 0 | 100% | Finished | 38565.1914 | 38565.1914 | 100 | 125 | 100 | 100 | 132.7704 | 100
54 | Trappen | 2012-06-07 08:00 | 2012-06-07 17:00 | 1d |  | 0 | 83.73 | 0 | 0 | 83.73 | 2012-07-12 08:00 | 1d | 83.73 | 0 | 0 | 4439.25 | 0 | 4522.98 | 0 | 100% | Finished | 83.73 | 83.73 | 100 | 100 | 100 | 100 | 5401.8629 | 100
39 | Afwerking (extern) | 2012-04-26 08:00 | 2012-05-03 17:00 | 4d |  | 0 | 43852.3789 | 0 | 0 | 43852.3789 | 2012-05-23 08:00 | 4d | 43852.3789 | 0 | 0 | 1474.22 | 0 | 45326.5989 | 0 | 100% | Finished | 43852.3789 | 43852.3789 | 100 | 100 | 100 | 100 | 103.3618 | 100
40 | Houten terras | 2012-05-15 08:00 | 2012-05-16 17:00 | 2d |  | 0 | 2064.1399 | 0 | 0 | 2064.1399 | 2012-06-08 08:00 | 2d | 2064.1399 | 0 | 0 | 13095.7197 | 0 | 15159.8596 | 0 | 100% | Finished | 2064.1399 | 2064.1399 | 100 | 100 | 100 | 100 | 734.4395 | 100
41 | Maatwerk | 2012-05-23 08:00 | 2012-05-24 17:00 | 2d |  | 0 | 2003.3 | 0 | 0 | 2003.3 | 2012-07-06 08:00 | 2d | 2003.3 | 0 | 0 | 14287 | 0 | 16290.3 | 0 | 100% | Finished | 2003.3 | 2003.3 | 100 | 100 | 100 | 100 | 813.1732 | 100
42 | Gips | 2012-04-10 08:00 | 2012-04-12 17:00 | 3d |  | 0 | 1599.41 | 0 | 0 | 1599.41 | 2012-05-14 08:00 | 12d | 1599.41 | 0 | 0 | 0 | 0 | 1599.41 | 0 | 100% | Finished | 1599.41 | 1599.41 | 100 | 400 | 100 | 100 | 100 | 100
43 | Opstop gips | 2012-06-05 08:00 | 2012-06-06 17:00 | 2d |  | 0 | 1066.77 | 0 | 0 | 1066.77 | 2012-06-27 08:00 | 2d | 1066.77 | 0 | 0 | 0 | 0 | 1066.77 | 0 | 100% | Finished | 1066.77 | 1066.77 | 100 | 100 | 100 | 100 | 100 | 100
44 | Vloeren (tweede fase) | 2012-05-14 08:00 | 2012-05-15 17:00 | 2d |  | 0 | 13898.8301 | 0 | 0 | 13898.8301 | 2012-06-15 08:00 | 2d | 13898.8301 | 0 | 0 | -3734.3201 | 0 | 10164.51 | 0 | 100% | Finished | 13898.8301 | 13898.8301 | 100 | 100 | 100 | 100 | 73.1321 | 100
46 | Technieken tweede fase | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  |  | 22484.7498 |  |  | 22484.7498 |  | 10d | [5 empty] | 25146.5598 |  | 100% |  | 22484.7498 | 22484.7498
45 | Elektriciteit (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 3571.4299 | 0 | 0 | 3571.4299 | 2012-06-27 08:00 | 2d | 3571.4299 | 0 | 0 | 2281.52 | 0 | 5852.95 | 0 | 100% | Finished | 3571.4299 | 3571.4299 | 100 | 100 | 100 | 100 | 163.8825 | 100
47 | Sanitair - ventilatie (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 14635.2197 | 0 | 0 | 14635.2197 | 2012-07-09 08:00 | 2d | 14635.2197 | 0 | 0 | 130.23 | 0 | 14765.4497 | 0 | 100% | Finished | 14635.2197 | 14635.2197 | 100 | 100 | 100 | 100 | 100.8898 | 100
48 | Verwarming (tweede fase) | 2012-06-07 08:00 | 2012-06-08 17:00 | 2d |  | 0 | 4278.1001 | 0 | 0 | 4278.1001 | 2012-07-03 08:00 | 2d | 4278.1001 | 0 | 0 | 250.06 | 0 | 4528.1601 | 0 | 100% | Finished | 4278.1001 | 4278.1001 | 100 | 100 | 100 | 100 | 105.8451 | 100
50 | Voorlopige oplevering | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  |  | 1200 |  |  | 1200 |  | 5d | [5 empty] | 1200 |  | 100% |  | 1200 | 1200
49 | Oplevering | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 240 | 0 | 0 | 240 | 2012-08-24 08:00 | 1d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
52 | Parket | 2012-06-19 08:00 | 2012-06-22 17:00 | 4d |  | 0 | 960 | 0 | 0 | 960 | 2012-08-20 08:00 | 2d | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 100% | Finished | 960 | 960 | 100 | 50 | 100 | 100 | 100 | 100
53 | Oplevering | 2012-07-02 17:00 | 2012-07-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2012-01-02
1:00 - 2:00 | No | Tuesday | Yes | 2012-01-03
2:00 - 3:00 | No | Wednesday | Yes | 2012-01-04
3:00 - 4:00 | No | Thursday | Yes | 2012-01-05
4:00 - 5:00 | No | Friday | Yes | 2012-01-06
5:00 - 6:00 | No | Saturday | No | 2012-04-06
6:00 - 7:00 | No | Sunday | No | 2012-04-09
7:00 - 8:00 | No |  |  | 2012-04-30
8:00 - 9:00 | Yes |  |  | 2012-05-01
9:00 - 10:00 | Yes |  |  | 2012-05-17
10:00 - 11:00 | Yes |  |  | 2012-05-18
11:00 - 12:00 | Yes |  |  | 2012-05-28
12:00 - 13:00 | No |  |  | 2012-07-23
13:00 - 14:00 | Yes |  |  | 2012-07-24
14:00 - 15:00 | Yes |  |  | 2012-07-25
15:00 - 16:00 | Yes |  |  | 2012-07-26
16:00 - 17:00 | Yes |  |  | 2012-07-27
17:00 - 18:00 | No |  |  | 2012-07-30
18:00 - 19:00 | No |  |  | 2012-07-31
19:00 - 20:00 | No |  |  | 2012-08-01
20:00 - 21:00 | No |  |  | 2012-08-02
21:00 - 22:00 | No |  |  | 2012-08-03
22:00 - 23:00 | No |  |  | 2012-08-06
23:00 - 0:00 | No |  |  | 2012-08-07
2012-08-08
2012-08-09
Generated by PMConverter v1.1.3 |  |  |  | 2012-08-10
2012-08-13
2012-08-14
2012-08-15
2012-08-16
2012-08-17
2012-10-29
2012-10-30
2012-10-31
2012-11-01
2012-11-02
2012-12-24
2012-12-25
2012-12-26
2012-12-27
2012-12-28
2012-12-31
2011-08-01
2011-08-02
2011-08-03
2011-08-04
2011-08-05
2011-08-08
2011-08-09
2011-08-10
2011-08-11
2011-08-12
2011-08-13
2011-08-15
2011-12-26
2011-12-27
2011-12-28
2011-12-29
2011-12-30
2011-11-01
2011-11-02
2011-11-03
2011-11-04
2011-07-25
2011-07-26
2011-07-27
2011-07-28
2011-07-29
2011-10-31
2011-07-22
2011-11-11
2011-10-27
2011-10-28
2011-07-21
2011-08-16
2011-08-17
2011-08-18
2011-08-19

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
23/09/2011 | 2011-06-30 08:00 | 2011-09-23 17:00 | 842.58 | 842.58 | 842.58 | 2011-09-23 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
08/02/2012 | 2011-09-23 17:00 | 2012-02-08 17:00 | 904.3 | 904.3 | 904.3 | 2012-02-08 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 501029.5121 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
27/02/2012 | 2012-02-08 17:00 | 2012-02-27 17:00 | 195029.7309 | 195029.7309 | 198466.0508 | 2012-02-27 17:00 | 0 | 100% | -3436.3199 | 98.27% | 0 | 100% | 100% | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-06 15:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-04 12:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-04 12:00 | 504465.832 | 509857.3851 | 504465.832 | 504465.832 | 509857.3851 | 509857.3851 | 508763.9285 | 508763.9285 | 1 | 0.98269 | 1 | 1 | 0 | 0.98269 | 1 | 1 | 1
02/03/2012 | 2012-02-27 17:00 | 2012-03-02 17:00 | 195029.7309 | 195029.7309 | 198466.0508 | 2012-03-02 17:00 | 0 | 100% | -3436.3199 | 98.27% | 0 | 100% | 100% | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-06 15:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-04 11:00 | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-07-04 11:00 | 504465.832 | 509857.3851 | 504465.832 | 504465.832 | 509857.3851 | 509857.3851 | 508763.9285 | 508763.9285 | 1 | 0.98269 | 1 | 1 | 0 | 0.98269 | 1 | 1 | 1
28/03/2012 | 2012-03-02 17:00 | 2012-03-28 17:00 | 312183.8321 | 293460.1517 | 311426.5719 | 2012-03-23 17:00 | -18723.6804 | 94% | -17966.4202 | 94.23% | -3d | 98.06% | 94.77% | 2012-07-13 09:00 | 2012-07-20 15:00 | 2012-09-06 16:00 | 2012-07-16 10:00 | 2012-07-20 15:00 | 2012-08-24 11:00 | 2012-07-05 17:00 | 2012-07-09 10:00 | 2012-07-13 10:00 | 518995.9323 | 531703.8871 | 532239.5102 | 523092.696 | 545758.2725 | 536051.4657 | 531810.8038 | 529926.0488 | 0.98065 | 0.94231 | 0.94002 | 0.94768 | -3 | 0.94231 | 1 | 0.98065 | 1
12/04/2012 | 2012-03-28 17:00 | 2012-04-12 17:00 | 367587.7021 | 337353.7716 | 355320.1918 | 2012-04-02 17:00 | -30233.9305 | 91.78% | -17966.4202 | 94.94% | -6d | 96.34% | 97.26% | 2012-07-19 17:00 | 2012-08-27 11:00 | 2012-09-12 16:00 | 2012-07-20 12:00 | 2012-08-27 11:00 | 2012-08-31 09:00 | 2012-07-10 17:00 | 2012-07-13 10:00 | 2012-07-18 11:00 | 518995.9323 | 527712.7969 | 533664.6907 | 525211.4668 | 543162.768 | 534259.3515 | 528871.1809 | 527206.6558 | 0.96341 | 0.94944 | 0.91775 | 0.97265 | -6 | 0.94944 | 1 | 0.96341 | 1
14/04/2012 | 2012-04-12 17:00 | 2012-04-14 17:00 | 367587.7021 | 337353.7716 | 356670.192 | 2012-04-02 17:00 | -30233.9305 | 91.78% | -19316.4205 | 94.58% | -7d | 95.76% | 97.26% | 2012-07-19 17:00 | 2012-08-27 11:00 | 2012-09-13 16:00 | 2012-07-20 14:00 | 2012-08-27 11:00 | 2012-08-31 11:00 | 2012-07-11 17:00 | 2012-07-16 14:00 | 2012-07-19 17:00 | 520345.9325 | 529717.784 | 535014.6909 | 527597.3894 | 545226.4556 | 537384.4494 | 530751.8437 | 529289.5068 | 0.95758 | 0.94584 | 0.91775 | 0.97265 | -7 | 0.94584 | 1 | 0.95758 | 1
16/05/2012 | 2012-04-14 17:00 | 2012-05-16 17:00 | 471174.5223 | 363191.5722 | 379465.9126 | 2012-04-02 17:00 | -107982.9501 | 77.08% | -16274.3404 | 95.71% | -28d | 84.95% | 98.61% | 2012-10-03 12:00 | 2012-11-05 10:00 | 2012-11-21 15:00 | 2012-09-27 14:00 | 2012-11-05 10:00 | 2012-11-09 12:00 | 2012-09-06 17:00 | 2012-09-21 10:00 | 2012-09-26 11:00 | 517303.8525 | 523480.2666 | 558285.3854 | 541730.8292 | 566298.1511 | 549001.7977 | 529313.4819 | 526794.3872 | 0.84946 | 0.95711 | 0.77082 | 0.98611 | -28 | 0.95711 | 1 | 0.84946 | 1
18/05/2012 | 2012-05-16 17:00 | 2012-05-18 17:00 | 471174.5223 | 363191.5722 | 381248.7725 | 2012-04-02 17:00 | -107982.9501 | 77.08% | -18057.2003 | 95.26% | -28d | 84.95% | 98.61% | 2012-10-03 12:00 | 2012-11-05 10:00 | 2012-11-23 09:00 | 2012-09-27 14:00 | 2012-11-05 10:00 | 2012-11-09 16:00 | 2012-09-06 17:00 | 2012-09-21 10:00 | 2012-09-26 14:00 | 519086.7123 | 525939.7548 | 560068.2453 | 543513.689 | 568958.8123 | 551581.1948 | 531681.9217 | 529143.2669 | 0.84946 | 0.95264 | 0.77082 | 0.98611 | -28 | 0.95264 | 1 | 0.84946 | 1
22/06/2012 | 2012-05-18 17:00 | 2012-06-22 17:00 | 501029.5121 | 471174.5223 | 502238.5021 | 2012-05-22 17:00 | -29854.9898 | 94.04% | -31063.9798 | 93.81% | -22d | 89.52% | 100% | 2012-07-19 16:00 | 2012-07-20 14:00 | 2012-09-07 16:00 | 2012-07-19 12:00 | 2012-07-20 14:00 | 2012-08-20 17:00 | 2012-08-29 17:00 | 2012-09-04 10:00 | 2012-09-06 11:00 | 532093.4919 | 534061.7961 | 533985.191 | 535587.1609 | 536078.2127 | 537785.7986 | 534046.4455 | 534355.6028 | 0.89524 | 0.93815 | 0.94041 | 1 | -22 | 0.93815 | 1 | 0.89524 | 1
30/06/2012 | 2012-06-22 17:00 | 2012-06-30 17:00 | 501029.5121 | 478829.1622 | 516833.7721 | 2012-06-06 17:00 | -22200.3499 | 95.57% | -38004.6099 | 92.65% | -17d | 92.09% | 99.58% | 2012-07-16 14:00 | 2012-07-16 17:00 | 2012-09-06 17:00 | 2012-07-16 12:00 | 2012-07-16 17:00 | 2012-07-17 16:00 | 2012-08-22 17:00 | 2012-08-24 12:00 | 2012-08-28 09:00 | 539034.1219 | 540796.1609 | 540063.415 | 540940.2126 | 541907.1488 | 542853.5377 | 540645.9368 | 540824.8333 | 0.92093 | 0.92647 | 0.95569 | 0.99578 | -17 | 0.92647 | 1 | 0.92093 | 1
22/08/2012 | 2012-06-30 17:00 | 2012-08-22 17:00 | 501029.5121 | 500789.5121 | 544544.6519 | 2012-06-18 17:00 | -240 | 99.95% | -43755.1398 | 91.96% | -27d | 88.41% | 99.95% | 2012-07-03 09:00 | 2012-07-03 09:00 | 2012-08-24 17:00 | 2012-08-23 09:00 | 2012-08-23 09:00 | 2012-08-23 09:00 | 2012-09-05 17:00 | 2012-09-07 10:00 | 2012-09-10 10:00 | 544784.6519 | 544805.6213 | 544784.7669 | 544816.1082 | 544805.7463 | 544839.826 | 544801.1655 | 544807.6533 | 0.88412 | 0.91965 | 0.99952 | 0.99952 | -27 | 0.91965 | 1 | 0.88412 | 1
24/08/2012 | 2012-08-22 17:00 | 2012-08-27 09:00 | 501029.5121 | 501029.5121 | 576624.0518 | 2012-07-02 17:00 | 0 | 100% | -75594.5397 | 86.89% | -19d 1h | 91.87% | 100% | 2012-07-02 17:00 | 2012-07-02 17:00 | 2012-09-13 14:00 | 2012-08-27 09:00 | 2012-08-27 09:00 | 2012-08-27 09:00 | 2012-08-27 09:00 | 2012-08-27 09:00 | 2012-08-27 09:00 | 576624.0518 | 576624.0518 | 576624.0518 | 576624.0518 | 576624.0518 | 576624.0518 | 576624.0518 | 576624.0518 | 0.91866 | 0.8689 | 1 | 1 | -19.125 | 0.8689 | 1 | 0.91866 | 1