## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building (2) | 1 |  |  | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 | 764.375
1 | Sondering | 1.1 |  | FS2 | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 0.375
2 | Inrichting | 1.2 | 1FS | FS5 | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 0.375
3 | Bouwput + Paalfunderingen | 1.3 | 6FS | FS4 | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 34.375
4 | Bouw Kelders + Ondergrondse parkeergarage | 1.4 | 3FS | FS7 | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 69.375
5 | Afbraakwerken | 1.5 | 2FS | FS6 | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 27.375
6 | Voorbereidingen | 1.6 | 5FS | FS3 | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 6.375
7 | Ruwbouw | 1.7 | 4FS | FS8;FS11 | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 230.375
8 | Dakstructuur | 1.8 | 7FS | FS9;FS10 | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 27.375
9 | Dakisolatie | 1.9 | 8FS |  | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 13.375
10 | Dakbedekking & Zinkwerk | 1.10 | 8FS | FS12;FS13;FS14;FS22 | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 27.375
11 | Plaatsen Ramen | 1.11 | 7FS | FS18;FS23 | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 62.375
12 | Sanitaire technieken | 1.12 | 10FS | FS23 | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 97.375
13 | Elektriciteitstechnieken | 1.13 | 10FS | FS23 | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 97.375
14 | Ventilatietechnieken | 1.14 | 10FS | FS23 | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 55.375
15 | Deuren | 1.15 | 17FS |  | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 | 55.375
16 | Keukens | 1.16 | 17FS | FS25;FS26;FS27 | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 | 71.375
17 | Pleisterwerken | 1.17 | 24FS | FS15;FS16;FS19;FS20;FS21 | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 | 34.375
18 | Buitenpleisterwerk | 1.18 | 11FS |  | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 27.375
19 | Afwerking Ventilatie | 1.19 | 17FS | FS25;FS26;FS27 | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 | 27.375
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 1.20 | 17FS | FS25;FS26;FS27 | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 | 69.375
21 | Afwerking | 1.21 | 17FS | FS25;FS26;FS27 | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 | 34.375
22 | Liften | 1.22 | 10FS |  | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 13.375
23 | Chapewerken | 1.23 | 11FS;12FS;13FS;14FS | FS24 | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 41.375
24 | Vloeren | 1.24 | 23FS | FS17 | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 69.375
25 | Tuinaanleg | 1.25 | 16FS;19FS;20FS;21FS | FS28 | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 | 6.375
26 | Parking | 1.26 | 16FS;19FS;20FS;21FS | FS28 | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 | 6.375
27 | Brievenbussen | 1.27 | 16FS;19FS;20FS;21FS | FS28 | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 | 0.375
28 | Schilderwerken | 1.28 | 25FS;26FS;27FS | FS29 | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 | 6.375
29 | Opkuis | 1.29 | 28FS |  | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building (2) | 4376h |  |  |  |  | 99 | 100 | 101
1 | Sondering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Inrichting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Bouwput + Paalfunderingen | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Bouw Kelders + Ondergrondse parkeergarage | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Afbraakwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Voorbereidingen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Ruwbouw | 1320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Dakstructuur | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Dakisolatie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Dakbedekking & Zinkwerk | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Plaatsen Ramen | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Sanitaire technieken | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Elektriciteitstechnieken | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Ventilatietechnieken | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Deuren | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Keukens | 416h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Pleisterwerken | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Buitenpleisterwerk | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Afwerking Ventilatie | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Afwerking | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Liften | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Chapewerken | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Vloeren | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Tuinaanleg | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Parking | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Brievenbussen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Schilderwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Opkuis | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2008-12-02 17:00 |  | TP Name | 02/12, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 22d | [5 empty] | 33866.9805 |  | 0.9714% |  | 33866.9805 | 33866.9805
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 |  | 0 | 0 | 301581.3926 | 25d | 0 | 0 | 0 | 301581.3926 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 |  | 0 | 0 | 379002.7207 | 50d | 0 | 0 | 0 | 379002.7207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 |  | 0 | 0 | 1708.42 | 5d | 0 | 0 | 0 | 1708.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 |  | 0 | 0 | 813478.6998 | 165d | 0 | 0 | 0 | 813478.6998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 |  | 0 | 0 | 27971.0806 | 20d | 0 | 0 | 0 | 27971.0806 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 |  | 0 | 0 | 1922.65 | 10d | 0 | 0 | 0 | 1922.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 |  | 0 | 0 | 128810.8208 | 20d | 0 | 0 | 0 | 128810.8208 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 |  | 0 | 0 | 239770.3249 | 45d | 0 | 0 | 0 | 239770.3249 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2009-01-13 17:00 |  | TP Name | 13/01, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 52d | [5 empty] | 337156.7931 |  | 9.198% |  | 320689.7908 | 337156.7931
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 25d | 301581.3926 | 19760.4004 | 5d | 0 | 0 | 301581.3926 | 19760.4004 | 83.33% | Started | 285114.3903 | 301581.3926 | 100 | 100 | 83.3333 | 100 | 100 | 83.3333
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 |  | 0 | 0 | 379002.7207 | 50d | 0 | 0 | 0 | 379002.7207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 |  | 0 | 0 | 813478.6998 | 165d | 0 | 0 | 0 | 813478.6998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 |  | 0 | 0 | 27971.0806 | 20d | 0 | 0 | 0 | 27971.0806 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 |  | 0 | 0 | 1922.65 | 10d | 0 | 0 | 0 | 1922.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 |  | 0 | 0 | 128810.8208 | 20d | 0 | 0 | 0 | 128810.8208 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 |  | 0 | 0 | 239770.3249 | 45d | 0 | 0 | 0 | 239770.3249 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2009-03-24 17:00 |  | TP Name | 24/03, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 102d | [5 empty] | 726794.714 |  | 19.23% |  | 670533.5128 | 716159.5138
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 45d | 369877.5205 | 82126.8018 | 45d | 0 | 0 | 369877.5205 | 82126.8018 | 50% | Started | 333376.7197 | 379002.7207 | 100 | 90 | 50 | 100 | 97.5923 | 50
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 |  | 0 | 0 | 813478.6998 | 165d | 0 | 0 | 0 | 813478.6998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 |  | 0 | 0 | 27971.0806 | 20d | 0 | 0 | 0 | 27971.0806 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 |  | 0 | 0 | 1922.65 | 10d | 0 | 0 | 0 | 1922.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 |  | 0 | 0 | 128810.8208 | 20d | 0 | 0 | 0 | 128810.8208 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 |  | 0 | 0 | 239770.3249 | 45d | 0 | 0 | 0 | 239770.3249 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2009-05-18 17:00 |  | TP Name | 18/05, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 141d | [5 empty] | 797971.2755 |  | 20.37% |  | 710076.0474 | 1504276.9337
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 84d | 441054.082 | 10950.2402 | 6d | 0 | 0 | 441054.082 | 10950.2402 | 93.33% | Started | 372919.2543 | 379002.7207 | 100 | 168 | 93.3333 | 100 | 116.3723 | 93.3333
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 |  | 0 | 0 | 813478.6998 | 165d | 0 | 0 | 0 | 813478.6998 | 0% | Not Started | 0 | 788117.42 | 100 |  | 0 | 100 |  | 0
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 |  | 0 | 0 | 27971.0806 | 20d | 0 | 0 | 0 | 27971.0806 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 |  | 0 | 0 | 1922.65 | 10d | 0 | 0 | 0 | 1922.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 |  | 0 | 0 | 128810.8208 | 20d | 0 | 0 | 0 | 128810.8208 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 |  | 0 | 0 | 239770.3249 | 45d | 0 | 0 | 0 | 239770.3249 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2009-11-10 17:00 |  | TP Name | 10/11, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 267d | [5 empty] | 1613342.6156 |  | 43.56% |  | 1518567.8143 | 1529638.2136
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 120d | 804421.0999 | 12076.7999 | 60d | 0 | 0 | 804421.0999 | 12076.7999 | 66.67% | Started | 802408.3005 | 813478.6998 | 100 | 72.7273 | 66.6667 | 100 | 98.8866 | 66.6667
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 |  | 0 | 0 | 27971.0806 | 20d | 0 | 0 | 0 | 27971.0806 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 |  | 0 | 0 | 1922.65 | 10d | 0 | 0 | 0 | 1922.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 |  | 0 | 0 | 128810.8208 | 20d | 0 | 0 | 0 | 128810.8208 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 |  | 0 | 0 | 239770.3249 | 45d | 0 | 0 | 0 | 239770.3249 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2009-12-08 17:00 |  | TP Name | 08/12, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 287d | [5 empty] | 1617368.2156 |  | 43.66% |  | 1522257.9474 | 1773015.6191
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 140d | 808446.6998 | 8051.2 | 40d | 0 | 0 | 808446.6998 | 8051.2 | 77.78% | Started | 806098.4336 | 813478.6998 | 100 | 84.8485 | 77.7778 | 100 | 99.3814 | 77.7778
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 |  | 0 | 0 | 27971.0806 | 20d | 0 | 0 | 0 | 27971.0806 | 0% | Not Started | 0 | 27971.0806 | 100 |  | 0 | 100 |  | 0
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 |  | 0 | 0 | 1922.65 | 10d | 0 | 0 | 0 | 1922.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 |  | 0 | 0 | 128810.8208 | 20d | 0 | 0 | 0 | 128810.8208 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 |  | 0 | 0 | 239770.3249 | 45d | 0 | 0 | 0 | 239770.3249 | 0% | Not Started | 0 | 215406.325 | 100 |  | 0 | 100 |  | 0
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2010-01-05 17:00 |  | TP Name | 05/01, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 307d | [5 empty] | 1621393.8156 |  | 43.77% |  | 1525948.0805 | 1923240.2898
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 160d | 812472.2998 | 4025.6 | 20d | 0 | 0 | 812472.2998 | 4025.6 | 88.89% | Started | 809788.5667 | 813478.6998 | 100 | 96.9697 | 88.8889 | 100 | 99.8763 | 88.8889
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 |  | 0 | 0 | 27971.0806 | 20d | 0 | 0 | 0 | 27971.0806 | 0% | Not Started | 0 | 27971.0806 | 100 |  | 0 | 100 |  | 0
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 |  | 0 | 0 | 1922.65 | 10d | 0 | 0 | 0 | 1922.65 | 0% | Not Started | 0 | 1922.65 | 100 |  | 0 | 100 |  | 0
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 |  | 0 | 0 | 128810.8208 | 20d | 0 | 0 | 0 | 128810.8208 | 0% | Not Started | 0 | 128810.8208 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 |  | 0 | 0 | 239770.3249 | 45d | 0 | 0 | 0 | 239770.3249 | 0% | Not Started | 0 | 234897.5249 | 100 |  | 0 | 100 |  | 0
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2010-02-09 17:00 |  | TP Name | 09/02, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 332d | [5 empty] | 1841872.4207 |  | 50.16% |  | 1748850.7812 | 2277278.7008
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 5d | 15665.0802 | 8204.0002 | 10d | 0 | 0 | 15665.0802 | 8204.0002 | 33.33% | Started | 17032.4137 | 27971.0806 | 100 | 25 | 33.3333 | 100 | 56.0046 | 33.3333
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 |  | 0 | 0 | 1922.65 | 10d | 0 | 0 | 0 | 1922.65 | 0% | Not Started | 0 | 1922.65 | 100 |  | 0 | 100 |  | 0
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 |  | 0 | 0 | 128810.8208 | 20d | 0 | 0 | 0 | 128810.8208 | 0% | Not Started | 0 | 128810.8208 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 5d | 200787.925 | 29236.7999 | 30d | 0 | 0 | 200787.925 | 29236.7999 | 14.29% | Started | 202180.1538 | 239770.3249 | 100 | 11.1111 | 14.2857 | 100 | 83.7418 | 14.2857
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 190891.7028 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 43813.7786 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 20297.4904 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 38162.6392 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 56000 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2010-03-02 17:00 |  | TP Name | 02/03, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 347d | [5 empty] | 1974074.6914 |  | 54.22% |  | 1890278.4052 | 2306035.5002
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 5d | 1395.05 | 527.6 | 5d | 0 | 0 | 1395.05 | 527.6 | 50% | Started | 1395.05 | 1922.65 | 100 | 50 | 50 | 100 | 72.5587 | 50
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 5d | 107984.8204 | 13884.0002 | 10d | 0 | 0 | 107984.8204 | 13884.0002 | 33.33% | Started | 110298.8208 | 128810.8208 | 100 | 25 | 33.3333 | 100 | 83.8321 | 33.3333
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 20d | 215406.325 | 14618.4 | 15d | 0 | 0 | 215406.325 | 14618.4 | 57.14% | Started | 220975.2403 | 239770.3249 | 100 | 44.4444 | 57.1429 | 100 | 89.8386 | 57.1429
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 |  | 0 | 0 | 227647.7023 | 70d | 0 | 0 | 0 | 227647.7023 | 0% | Not Started | 0 | 203143.7026 | 100 |  | 0 | 100 |  | 0
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 |  | 0 | 0 | 79576.1772 | 70d | 0 | 0 | 0 | 79576.1772 | 0% | Not Started | 0 | 55734.5781 | 100 |  | 0 | 100 |  | 0
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 |  | 0 | 0 | 24881.4905 | 40d | 0 | 0 | 0 | 24881.4905 | 0% | Not Started | 0 | 24881.4905 | 100 |  | 0 | 100 |  | 0
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 |  | 0 | 0 | 38162.6392 | 20d | 0 | 0 | 0 | 38162.6392 | 0% | Not Started | 0 | 38162.6392 | 100 |  | 0 | 100 |  | 0
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 |  | 0 | 0 | 56000 | 10d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 56000 | 100 |  | 0 | 100 |  | 0
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2010-04-13 17:00 |  | TP Name | 13/04, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 377d | [5 empty] | 2336383.1029 |  | 64.73% |  | 2256840.9462 | 2354381.099
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 20d | 186807.7029 | 44107.1993 | 54d | 0 | 0 | 186807.7029 | 44107.1993 | 27.03% | Started | 185924.6752 | 227647.7023 | 100 | 28.5714 | 27.027 | 100 | 82.06 | 27.027
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 20d | 39840.1787 | 46093.7583 | 58d | 0 | 0 | 39840.1787 | 46093.7583 | 25.64% | Started | 38209.9847 | 79576.1772 | 100 | 28.5714 | 25.641 | 100 | 50.0655 | 25.641
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 20d | 18769.4904 | 12224.0002 | 40d | 0 | 0 | 18769.4904 | 12224.0002 | 33.33% | Started | 16732.1571 | 24881.4905 | 100 | 50 | 33.3333 | 100 | 75.4356 | 33.3333
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 15d | 31861.0394 | 6301.5997 | 5d | 0 | 0 | 31861.0394 | 6301.5997 | 75% | Started | 31861.0394 | 38162.6392 | 100 | 75 | 75 | 100 | 83.4875 | 75
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2010-05-25 17:00 |  | TP Name | 25/05, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 407d | [5 empty] | 2400198.3016 |  | 66.37% |  | 2313830.3137 | 2453181.4388
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 50d | 211311.7025 | 19603.1997 | 24d | 0 | 0 | 211311.7025 | 19603.1997 | 67.57% | Started | 209104.1358 | 227647.7023 | 100 | 71.4286 | 67.5676 | 100 | 92.824 | 67.5676
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 50d | 63681.7778 | 22252.1592 | 28d | 0 | 0 | 63681.7778 | 22252.1592 | 64.1% | Started | 59606.292 | 79576.1772 | 100 | 71.4286 | 64.1026 | 100 | 80.0262 | 64.1026
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 50d | 27937.4905 | 3056.0001 | 10d | 0 | 0 | 27937.4905 | 3056.0001 | 83.33% | Started | 22844.1569 | 24881.4905 | 100 | 125 | 83.3333 | 100 | 112.2822 | 83.3333
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 |  | 0 | 0 | 98800.3398 | 30d | 0 | 0 | 0 | 98800.3398 | 0% | Not Started | 0 | 98800.3398 | 100 |  | 0 | 100 |  | 0
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2010-08-03 17:00 |  | TP Name | 03/08, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 457d | [5 empty] | 2535028.5604 |  | 69.84% |  | 2434896.1197 | 2659758.0311
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 100% | Finished | 227647.7023 | 227647.7023 | 100 | 105.7143 | 100 | 100 | 101.4352 | 100
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 100% | Finished | 79576.1772 | 79576.1772 | 100 | 111.4286 | 100 | 100 | 107.9895 | 100
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 100% | Finished | 24881.4905 | 24881.4905 | 100 | 150 | 100 | 100 | 124.5644 | 100
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 27d | 89918.8999 | 20723.3599 | 7d | 0 | 0 | 89918.8999 | 20723.3599 | 79.41% | Started | 80515.0208 | 98800.3398 | 100 | 90 | 79.4118 | 100 | 91.0107 | 79.4118
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 |  | 0 | 0 | 206576.5923 | 50d | 0 | 0 | 0 | 206576.5923 | 0% | Not Started | 0 | 206576.5923 | 100 |  | 0 | 100 |  | 0
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2010-09-07 17:00 |  | TP Name | 07/09, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 482d | [5 empty] | 2649250.5109 |  | 73.05% |  | 2546680.0313 | 2803865.9015
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 100% | Finished | 227647.7023 | 227647.7023 | 100 | 105.7143 | 100 | 100 | 101.4352 | 100
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 100% | Finished | 79576.1772 | 79576.1772 | 100 | 111.4286 | 100 | 100 | 107.9895 | 100
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 100% | Finished | 24881.4905 | 24881.4905 | 100 | 150 | 100 | 100 | 124.5644 | 100
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 144107.8704 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 34d | 110642.2598 | 0 | 0 | 0 | 0 | 110642.2598 | 0 | 100% | Finished | 98800.3398 | 98800.3398 | 100 | 113.3333 | 100 | 100 | 111.9857 | 100
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 2010-08-18 08:00 | 15d | 93498.5906 | 113078.0017 | 35d | 0 | 0 | 93498.5906 | 113078.0017 | 30% | Started | 93498.5925 | 206576.5923 | 100 | 30 | 30 | 100 | 45.261 | 30
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2010-10-05 17:00 |  | TP Name | 05/10, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 502d | [5 empty] | 2713866.5119 |  | 74.9% |  | 2611296.0285 | 3159577.1657
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 100% | Finished | 227647.7023 | 227647.7023 | 100 | 105.7143 | 100 | 100 | 101.4352 | 100
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 100% | Finished | 79576.1772 | 79576.1772 | 100 | 111.4286 | 100 | 100 | 107.9895 | 100
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 100% | Finished | 24881.4905 | 24881.4905 | 100 | 150 | 100 | 100 | 124.5644 | 100
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 71336.6196 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 65885.8006 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 |  | 0 | 0 | 144107.8704 | 25d | 0 | 0 | 0 | 144107.8704 | 0% | Not Started | 0 | 144107.8704 | 100 |  | 0 | 100 |  | 0
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 25833.0305 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 146540.6143 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 46115.1992 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 34d | 110642.2598 | 0 | 0 | 0 | 0 | 110642.2598 | 0 | 100% | Finished | 98800.3398 | 98800.3398 | 100 | 113.3333 | 100 | 100 | 111.9857 | 100
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 2010-08-18 08:00 | 35d | 158114.5916 | 48462.0007 | 15d | 0 | 0 | 158114.5916 | 48462.0007 | 70% | Started | 158114.5896 | 206576.5923 | 100 | 70 | 70 | 100 | 76.5404 | 70
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2010-11-02 17:00 |  | TP Name | 02/11, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 522d | [5 empty] | 2843461.9835 |  | 78.62% |  | 2740891.5023 | 3305131.9679
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 100% | Finished | 227647.7023 | 227647.7023 | 100 | 105.7143 | 100 | 100 | 101.4352 | 100
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 100% | Finished | 79576.1772 | 79576.1772 | 100 | 111.4286 | 100 | 100 | 107.9895 | 100
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 100% | Finished | 24881.4905 | 24881.4905 | 100 | 150 | 100 | 100 | 124.5644 | 100
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 |  | 0 | 0 | 86234.2197 | 40d | 0 | 0 | 0 | 86234.2197 | 0% | Not Started | 0 | 86234.2197 | 100 |  | 0 | 100 |  | 0
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 |  | 0 | 0 | 169990.7615 | 52d | 0 | 0 | 0 | 169990.7615 | 0% | Not Started | 0 | 130951.4012 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 | 2010-10-27 08:00 | 5d | 81133.4709 | 62974.3994 | 20d | 0 | 0 | 81133.4709 | 62974.3994 | 20% | Started | 81133.4712 | 144107.8704 | 100 | 20 | 20 | 100 | 56.3005 | 20
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 |  | 0 | 0 | 25833.0305 | 20d | 0 | 0 | 0 | 25833.0305 | 0% | Not Started | 0 | 25833.0305 | 100 |  | 0 | 100 |  | 0
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 |  | 0 | 0 | 232155.8169 | 50d | 0 | 0 | 0 | 232155.8169 | 0% | Not Started | 0 | 203617.416 | 100 |  | 0 | 100 |  | 0
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 |  | 0 | 0 | 54629.999 | 25d | 0 | 0 | 0 | 54629.999 | 0% | Not Started | 0 | 54629.999 | 100 |  | 0 | 100 |  | 0
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 34d | 110642.2598 | 0 | 0 | 0 | 0 | 110642.2598 | 0 | 100% | Finished | 98800.3398 | 98800.3398 | 100 | 113.3333 | 100 | 100 | 111.9857 | 100
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 2010-08-18 08:00 | 50d | 206576.5923 | 0 | 0 | 0 | 0 | 206576.5923 | 0 | 100% | Finished | 206576.5923 | 206576.5923 | 100 | 100 | 100 | 100 | 100 | 100
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2010-12-02 17:00 |  | TP Name | 02/12, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 544d | [5 empty] | 3092616.4456 |  | 85.75% |  | 2989691.0605 | 3466447.3501
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 100% | Finished | 227647.7023 | 227647.7023 | 100 | 105.7143 | 100 | 100 | 101.4352 | 100
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 100% | Finished | 79576.1772 | 79576.1772 | 100 | 111.4286 | 100 | 100 | 107.9895 | 100
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 100% | Finished | 24881.4905 | 24881.4905 | 100 | 150 | 100 | 100 | 124.5644 | 100
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 | 2010-12-01 08:00 | 2d | 57928.7795 | 28305.4402 | 38d | 0 | 0 | 57928.7795 | 28305.4402 | 5% | Started | 57928.7796 | 86234.2197 | 100 | 5 | 5 | 100 | 67.1761 | 5
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 | 2010-12-01 08:00 | 2d | 7326.7601 | 172423.8416 | 53d | 0 | 0 | 7326.7601 | 172423.8416 | 3.636% | Started | 6971.8566 | 169990.7615 | 100 | 3.8462 | 3.6364 | 100 | 4.3101 | 3.6364
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 | 2010-10-27 08:00 | 25d | 144107.8704 | 0 | 0 | 0 | 0 | 144107.8704 | 0 | 100% | Finished | 144107.8704 | 144107.8704 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 | 2010-12-01 08:00 | 2d | 10291.1105 | 15541.92 | 18d | 0 | 0 | 10291.1105 | 15541.92 | 10% | Started | 10291.1105 | 25833.0305 | 100 | 10 | 10 | 100 | 39.837 | 10
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 | 2010-12-01 08:00 | 2d | 95171.4927 | 136984.3242 | 48d | 0 | 0 | 95171.4927 | 136984.3242 | 4% | Started | 95171.4925 | 232155.8169 | 100 | 4 | 4 | 100 | 40.9947 | 4
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 | 2010-12-01 08:00 | 2d | 15461.9199 | 39168.0791 | 23d | 0 | 0 | 15461.9199 | 39168.0791 | 8% | Started | 15461.9198 | 54629.999 | 100 | 8 | 8 | 100 | 28.303 | 8
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 34d | 110642.2598 | 0 | 0 | 0 | 0 | 110642.2598 | 0 | 100% | Finished | 98800.3398 | 98800.3398 | 100 | 113.3333 | 100 | 100 | 111.9857 | 100
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 2010-08-18 08:00 | 50d | 206576.5923 | 0 | 0 | 0 | 0 | 206576.5923 | 0 | 100% | Finished | 206576.5923 | 206576.5923 | 100 | 100 | 100 | 100 | 100 | 100
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 26480.9202 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 43770.6406 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 1826.09 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 21659.9702 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2011-01-04 17:00 |  | TP Name | 04/01, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 567d | [5 empty] | 3304922.4476 |  | 91.73% |  | 3197915.6775 | 3486375.4699
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 100% | Finished | 227647.7023 | 227647.7023 | 100 | 105.7143 | 100 | 100 | 101.4352 | 100
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 100% | Finished | 79576.1772 | 79576.1772 | 100 | 111.4286 | 100 | 100 | 107.9895 | 100
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 100% | Finished | 24881.4905 | 24881.4905 | 100 | 150 | 100 | 100 | 124.5644 | 100
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 | 2010-12-01 08:00 | 25d | 75061.0197 | 11173.2001 | 15d | 0 | 0 | 75061.0197 | 11173.2001 | 62.5% | Started | 75061.0197 | 86234.2197 | 100 | 62.5 | 62.5 | 100 | 87.0432 | 62.5
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 | 2010-12-01 08:00 | 25d | 82152.2007 | 97598.4009 | 30d | 0 | 0 | 82152.2007 | 97598.4009 | 45.45% | Started | 77715.9121 | 169990.7615 | 100 | 48.0769 | 45.4545 | 100 | 48.3275 | 45.4545
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 | 2010-10-27 08:00 | 25d | 144107.8704 | 0 | 0 | 0 | 0 | 144107.8704 | 0 | 100% | Finished | 144107.8704 | 144107.8704 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 | 2010-12-01 08:00 | 20d | 25833.0305 | 0 | 0 | 0 | 0 | 25833.0305 | 0 | 100% | Finished | 25833.0305 | 25833.0305 | 100 | 100 | 100 | 100 | 100 | 100
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 | 2010-12-01 08:00 | 25d | 160809.8147 | 71346.0022 | 25d | 0 | 0 | 160809.8147 | 71346.0022 | 50% | Started | 160809.8147 | 232155.8169 | 100 | 50 | 50 | 100 | 69.2681 | 50
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 | 2010-12-01 08:00 | 25d | 54629.999 | 0 | 0 | 0 | 0 | 54629.999 | 0 | 100% | Finished | 54629.999 | 54629.999 | 100 | 100 | 100 | 100 | 100 | 100
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 34d | 110642.2598 | 0 | 0 | 0 | 0 | 110642.2598 | 0 | 100% | Finished | 98800.3398 | 98800.3398 | 100 | 113.3333 | 100 | 100 | 111.9857 | 100
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 2010-08-18 08:00 | 50d | 206576.5923 | 0 | 0 | 0 | 0 | 206576.5923 | 0 | 100% | Finished | 206576.5923 | 206576.5923 | 100 | 100 | 100 | 100 | 100 | 100
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 26480.9202 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 43770.6406 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 1826.09 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 21659.9702 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 19928.1198 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2011-02-08 17:00 |  | TP Name | 08/02, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 592d | [5 empty] | 3468773.6506 |  | 96.3% |  | 3357330.5918 | 3486375.4699
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 100% | Finished | 227647.7023 | 227647.7023 | 100 | 105.7143 | 100 | 100 | 101.4352 | 100
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 100% | Finished | 79576.1772 | 79576.1772 | 100 | 111.4286 | 100 | 100 | 107.9895 | 100
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 100% | Finished | 24881.4905 | 24881.4905 | 100 | 150 | 100 | 100 | 124.5644 | 100
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 | 2010-12-01 08:00 | 40d | 86234.2197 | 0 | 0 | 0 | 0 | 86234.2197 | 0 | 100% | Finished | 86234.2197 | 86234.2197 | 100 | 100 | 100 | 100 | 100 | 100
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 | 2010-12-01 08:00 | 50d | 163484.2015 | 16266.4001 | 5d | 0 | 0 | 163484.2015 | 16266.4001 | 90.91% | Started | 154611.6242 | 169990.7615 | 100 | 96.1538 | 90.9091 | 100 | 96.1724 | 90.9091
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 | 2010-10-27 08:00 | 25d | 144107.8704 | 0 | 0 | 0 | 0 | 144107.8704 | 0 | 100% | Finished | 144107.8704 | 144107.8704 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 | 2010-12-01 08:00 | 20d | 25833.0305 | 0 | 0 | 0 | 0 | 25833.0305 | 0 | 100% | Finished | 25833.0305 | 25833.0305 | 100 | 100 | 100 | 100 | 100 | 100
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 | 2010-12-01 08:00 | 50d | 232155.8169 | 0 | 0 | 0 | 0 | 232155.8169 | 0 | 100% | Finished | 232155.8169 | 232155.8169 | 100 | 100 | 100 | 100 | 100 | 100
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 | 2010-12-01 08:00 | 25d | 54629.999 | 0 | 0 | 0 | 0 | 54629.999 | 0 | 100% | Finished | 54629.999 | 54629.999 | 100 | 100 | 100 | 100 | 100 | 100
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 34d | 110642.2598 | 0 | 0 | 0 | 0 | 110642.2598 | 0 | 100% | Finished | 98800.3398 | 98800.3398 | 100 | 113.3333 | 100 | 100 | 111.9857 | 100
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 2010-08-18 08:00 | 50d | 206576.5923 | 0 | 0 | 0 | 0 | 206576.5923 | 0 | 100% | Finished | 206576.5923 | 206576.5923 | 100 | 100 | 100 | 100 | 100 | 100
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 |  | 0 | 0 | 26480.9202 | 5d | 0 | 0 | 0 | 26480.9202 | 0% | Not Started | 0 | 26480.9202 | 100 |  | 0 | 100 |  | 0
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 |  | 0 | 0 | 43770.6406 | 5d | 0 | 0 | 0 | 43770.6406 | 0% | Not Started | 0 | 43770.6406 | 100 |  | 0 | 100 |  | 0
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 |  | 0 | 0 | 1826.09 | 1d | 0 | 0 | 0 | 1826.09 | 0% | Not Started | 0 | 1826.09 | 100 |  | 0 | 100 |  | 0
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 |  | 0 | 0 | 21659.9702 | 5d | 0 | 0 | 0 | 21659.9702 | 0% | Not Started | 0 | 21659.9702 | 100 |  | 0 | 100 |  | 0
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 |  | 0 | 0 | 19928.1198 | 3d | 0 | 0 | 0 | 19928.1198 | 0% | Not Started | 0 | 19928.1198 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2011-03-07 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (2) | 2008-11-03 08:00 | 2010-12-07 17:00 | 547d |  |  | 2235858.7426 |  |  | 3486375.4699 |  | 611d | [5 empty] | 3599114.1116 |  | 100% |  | 3486375.4699 | 3486375.4699
1 | Sondering | 2008-11-03 08:00 | 2008-11-03 17:00 | 1d |  | 0 | 918.25 | 0 | 0 | 918.25 | 2008-11-03 08:00 | 1d | 918.25 | 0 | 0 | 0 | 0 | 918.25 | 0 | 100% | Finished | 918.25 | 918.25 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2008-11-04 08:00 | 2008-11-04 17:00 | 1d |  | 0 | 23316.2305 | 0 | 0 | 23316.2305 | 2008-11-04 08:00 | 1d | 23316.2305 | 0 | 0 | 0 | 0 | 23316.2305 | 0 | 100% | Finished | 23316.2305 | 23316.2305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Paalfunderingen | 2008-12-10 08:00 | 2009-01-13 17:00 | 25d |  | 0 | 202779.3906 | 494.01 | 98802.002 | 301581.3926 | 2008-12-10 08:00 | 30d | 321341.793 | 0 | 0 | 0 | 0 | 321341.793 | 0 | 100% | Finished | 301581.3926 | 301581.3926 | 100 | 120 | 100 | 100 | 106.5523 | 100
4 | Bouw Kelders + Ondergrondse parkeergarage | 2009-01-14 08:00 | 2009-03-24 17:00 | 50d |  | 0 | 287750.7188 | 228.13 | 91252.002 | 379002.7207 | 2009-01-21 08:00 | 90d | 452004.3223 | 0 | 0 | 0 | 0 | 452004.3223 | 0 | 100% | Finished | 379002.7207 | 379002.7207 | 100 | 180 | 100 | 100 | 119.2615 | 100
5 | Afbraakwerken | 2008-11-05 08:00 | 2008-12-02 17:00 | 20d |  | 0 | 9632.5 | 0 | 0 | 9632.5 | 2008-11-05 08:00 | 20d | 9632.5 | 0 | 0 | 0 | 0 | 9632.5 | 0 | 100% | Finished | 9632.5 | 9632.5 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereidingen | 2008-12-03 08:00 | 2008-12-09 17:00 | 5d |  | 0 | 1708.42 | 0 | 0 | 1708.42 | 2008-12-03 08:00 | 5d | 1708.42 | 0 | 0 | 0 | 0 | 1708.42 | 0 | 100% | Finished | 1708.42 | 1708.42 | 100 | 100 | 100 | 100 | 100 | 100
7 | Ruwbouw | 2009-03-25 08:00 | 2009-11-10 17:00 | 165d |  | 0 | 780267.5 | 25.16 | 33211.1998 | 813478.6998 | 2009-05-27 08:00 | 180d | 816497.8998 | 0 | 0 | 0 | 0 | 816497.8998 | 0 | 100% | Finished | 813478.6998 | 813478.6998 | 100 | 109.0909 | 100 | 100 | 100.3711 | 100
8 | Dakstructuur | 2009-11-11 08:00 | 2009-12-08 17:00 | 20d |  | 0 | 11563.0801 | 102.55 | 16408.0005 | 27971.0806 | 2010-02-03 08:00 | 15d | 23869.0804 | 0 | 0 | 0 | 0 | 23869.0804 | 0 | 100% | Finished | 27971.0806 | 27971.0806 | 100 | 75 | 100 | 100 | 85.3349 | 100
9 | Dakisolatie | 2009-12-09 08:00 | 2009-12-22 17:00 | 10d |  | 0 | 867.45 | 13.19 | 1055.2 | 1922.65 | 2010-02-24 08:00 | 10d | 1922.65 | 0 | 0 | 0 | 0 | 1922.65 | 0 | 100% | Finished | 1922.65 | 1922.65 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakbedekking & Zinkwerk | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 101042.8203 | 173.55 | 27768.0005 | 128810.8208 | 2010-02-24 08:00 | 15d | 121868.8207 | 0 | 0 | 0 | 0 | 121868.8207 | 0 | 100% | Finished | 128810.8208 | 128810.8208 | 100 | 75 | 100 | 100 | 94.6107 | 100
11 | Plaatsen Ramen | 2009-11-11 08:00 | 2010-01-12 17:00 | 45d |  | 0 | 195915.125 | 121.82 | 43855.1999 | 239770.3249 | 2010-02-03 08:00 | 35d | 230024.7249 | 0 | 0 | 0 | 0 | 230024.7249 | 0 | 100% | Finished | 239770.3249 | 239770.3249 | 100 | 77.7778 | 100 | 100 | 95.9354 | 100
12 | Sanitaire technieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 170471.7031 | 102.1 | 57175.9991 | 227647.7023 | 2010-03-17 08:00 | 74d | 230914.9022 | 0 | 0 | 0 | 0 | 230914.9022 | 0 | 100% | Finished | 227647.7023 | 227647.7023 | 100 | 105.7143 | 100 | 100 | 101.4352 | 100
13 | Elektriciteitstechnieken | 2010-01-06 08:00 | 2010-04-13 17:00 | 70d |  | 0 | 23945.7793 | 99.34 | 55630.3979 | 79576.1772 | 2010-03-17 08:00 | 78d | 85933.937 | 0 | 0 | 0 | 0 | 85933.937 | 0 | 100% | Finished | 79576.1772 | 79576.1772 | 100 | 111.4286 | 100 | 100 | 107.9895 | 100
14 | Ventilatietechnieken | 2010-01-06 08:00 | 2010-03-02 17:00 | 40d |  | 0 | 12657.4902 | 38.2 | 12224.0002 | 24881.4905 | 2010-03-17 08:00 | 60d | 30993.4906 | 0 | 0 | 0 | 0 | 30993.4906 | 0 | 100% | Finished | 24881.4905 | 24881.4905 | 100 | 150 | 100 | 100 | 124.5644 | 100
15 | Deuren | 2010-09-08 08:00 | 2010-11-02 17:00 | 40d |  | 0 | 56439.0195 | 93.11 | 29795.2002 | 86234.2197 | 2010-12-01 08:00 | 40d | 86234.2197 | 0 | 0 | 0 | 0 | 86234.2197 | 0 | 100% | Finished | 86234.2197 | 86234.2197 | 100 | 100 | 100 | 100 | 100 | 100
16 | Keukens | 2010-09-08 08:00 | 2010-11-18 17:00 | 52d |  | 0 | 820.2 | 406.66 | 169170.5615 | 169990.7615 | 2010-12-01 08:00 | 55d | 179750.6016 | 0 | 0 | 0 | 0 | 179750.6016 | 0 | 100% | Finished | 169990.7615 | 169990.7615 | 100 | 105.7692 | 100 | 100 | 105.7414 | 100
17 | Pleisterwerken | 2010-08-04 08:00 | 2010-09-07 17:00 | 25d |  | 0 | 65389.8711 | 393.59 | 78717.9993 | 144107.8704 | 2010-10-27 08:00 | 25d | 144107.8704 | 0 | 0 | 0 | 0 | 144107.8704 | 0 | 100% | Finished | 144107.8704 | 144107.8704 | 100 | 100 | 100 | 100 | 100 | 100
18 | Buitenpleisterwerk | 2010-01-13 08:00 | 2010-02-09 17:00 | 20d |  | 0 | 12956.2402 | 157.54 | 25206.3989 | 38162.6392 | 2010-03-24 08:00 | 20d | 38162.6392 | 0 | 0 | 0 | 0 | 38162.6392 | 0 | 100% | Finished | 38162.6392 | 38162.6392 | 100 | 100 | 100 | 100 | 100 | 100
19 | Afwerking Ventilatie | 2010-09-08 08:00 | 2010-10-05 17:00 | 20d |  | 0 | 8564.2305 | 107.93 | 17268.8 | 25833.0305 | 2010-12-01 08:00 | 20d | 25833.0305 | 0 | 0 | 0 | 0 | 25833.0305 | 0 | 100% | Finished | 25833.0305 | 25833.0305 | 100 | 100 | 100 | 100 | 100 | 100
20 | Plaatsen Sanitaire Toestellen & Radiatoren | 2010-09-08 08:00 | 2010-11-16 17:00 | 50d |  | 0 | 89463.8125 | 356.73 | 142692.0044 | 232155.8169 | 2010-12-01 08:00 | 50d | 232155.8169 | 0 | 0 | 0 | 0 | 232155.8169 | 0 | 100% | Finished | 232155.8169 | 232155.8169 | 100 | 100 | 100 | 100 | 100 | 100
21 | Afwerking | 2010-09-08 08:00 | 2010-10-12 17:00 | 25d |  | 0 | 12056 | 212.87 | 42573.999 | 54629.999 | 2010-12-01 08:00 | 25d | 54629.999 | 0 | 0 | 0 | 0 | 54629.999 | 0 | 100% | Finished | 54629.999 | 54629.999 | 100 | 100 | 100 | 100 | 100 | 100
22 | Liften | 2010-01-06 08:00 | 2010-01-19 17:00 | 10d |  | 0 | 56000 | 0 | 0 | 56000 | 2010-03-17 08:00 | 10d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Chapewerken | 2010-04-14 08:00 | 2010-05-25 17:00 | 30d |  | 0 | 9985.9404 | 370.06 | 88814.3994 | 98800.3398 | 2010-06-28 08:00 | 34d | 110642.2598 | 0 | 0 | 0 | 0 | 110642.2598 | 0 | 100% | Finished | 98800.3398 | 98800.3398 | 100 | 113.3333 | 100 | 100 | 111.9857 | 100
24 | Vloeren | 2010-05-26 08:00 | 2010-08-03 17:00 | 50d |  | 0 | 45036.5898 | 403.85 | 161540.0024 | 206576.5923 | 2010-08-18 08:00 | 50d | 206576.5923 | 0 | 0 | 0 | 0 | 206576.5923 | 0 | 100% | Finished | 206576.5923 | 206576.5923 | 100 | 100 | 100 | 100 | 100 | 100
25 | Tuinaanleg | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 11376.9199 | 377.6 | 15104.0002 | 26480.9202 | 2011-02-16 08:00 | 8d | 35543.3203 | 0 | 0 | 0 | 0 | 35543.3203 | 0 | 100% | Finished | 26480.9202 | 26480.9202 | 100 | 160 | 100 | 100 | 134.2224 | 100
26 | Parking | 2010-11-19 08:00 | 2010-11-25 17:00 | 5d |  | 0 | 43770.6406 | 0 | 0 | 43770.6406 | 2011-02-16 08:00 | 5d | 43770.6406 | 0 | 0 | 0 | 0 | 43770.6406 | 0 | 100% | Finished | 43770.6406 | 43770.6406 | 100 | 100 | 100 | 100 | 100 | 100
27 | Brievenbussen | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 438.25 | 173.48 | 1387.84 | 1826.09 | 2011-02-16 08:00 | 1d | 1826.09 | 0 | 0 | 0 | 0 | 1826.09 | 0 | 100% | Finished | 1826.09 | 1826.09 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schilderwerken | 2010-11-26 08:00 | 2010-12-02 17:00 | 5d |  | 0 | 24.77 | 540.88 | 21635.2002 | 21659.9702 | 2011-02-28 08:00 | 3d | 13005.8901 | 0 | 0 | 0 | 0 | 13005.8901 | 0 | 100% | Finished | 21659.9702 | 21659.9702 | 100 | 60 | 100 | 100 | 60.0457 | 100
29 | Opkuis | 2010-12-03 08:00 | 2010-12-07 17:00 | 3d |  | 0 | 699.8 | 801.18 | 19228.3198 | 19928.1198 | 2011-03-03 08:00 | 3d | 19928.1198 | 0 | 0 | 0 | 0 | 19928.1198 | 0 | 100% | Finished | 19928.1198 | 19928.1198 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
02/12, 2008 | 2008-11-03 08:00 | 2008-12-02 17:00 | 33866.9805 | 33866.9805 | 33866.9805 | 2008-12-02 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2010-12-07 17:00 | 2010-12-07 17:00 | 2010-12-07 17:00 | 2010-12-07 17:00 | 2010-12-07 17:00 | 2010-12-07 17:00 | 2010-12-07 17:00 | 2010-12-07 17:00 | 2010-12-07 17:00 | 3486375.4699 | 3486375.4699 | 3486375.4699 | 3486375.4699 | 3486375.4699 | 3486375.4699 | 3486375.4699 | 3486375.4699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
13/01, 2009 | 2008-12-02 17:00 | 2009-01-13 17:00 | 337156.7931 | 320689.7908 | 337156.7931 | 2009-01-07 15:00 | -16467.0023 | 95.12% | -16467.0023 | 95.12% | -4d 2h | 91.83% | 100% | 2010-12-10 14:00 | 2011-01-17 09:00 | 2011-02-25 14:00 | 2010-12-10 12:00 | 2011-01-17 09:00 | 2011-02-22 17:00 | 2010-12-14 10:00 | 2011-02-14 14:00 | 2011-03-24 14:00 | 3502842.4722 | 3665396.3009 | 3665396.3009 | 3784605.0719 | 3836297.0566 | 3961627.0425 | 3665396.3009 | 3688573.926 | 0.91827 | 0.95116 | 0.95116 | 1 | -4.25 | 0.95116 | 1 | 0.91827 | 1
24/03, 2009 | 2009-01-13 17:00 | 2009-03-24 17:00 | 716159.5138 | 670533.5128 | 726794.714 | 2009-02-17 17:00 | -45626.001 | 93.63% | -56261.2012 | 92.26% | -25d | 75.49% | 100% | 2010-12-17 09:00 | 2011-01-28 10:00 | 2011-04-07 10:00 | 2010-12-16 12:00 | 2011-01-28 10:00 | 2011-03-25 14:00 | 2011-01-11 17:00 | 2011-08-12 14:00 | 2011-10-25 16:00 | 3542636.6711 | 3778900.2549 | 3734238.7394 | 4456871.0728 | 3986578.7195 | 4769843.6124 | 3769862.148 | 3894034.4177 | 0.7549 | 0.92259 | 0.93629 | 1 | -25 | 0.92259 | 1 | 0.7549 | 1
18/05, 2009 | 2009-03-24 17:00 | 2009-05-18 17:00 | 1504276.9337 | 710076.0474 | 797971.2755 | 2009-03-19 14:00 | -794200.8864 | 47.2% | -87895.2282 | 88.99% | -42d 3h | 69.95% | 100% | 2011-05-31 14:00 | 2013-04-11 15:00 | 2013-10-30 10:00 | 2011-03-22 12:00 | 2013-04-11 15:00 | 2013-10-04 15:00 | 2011-02-04 11:00 | 2011-11-01 17:00 | 2012-02-21 11:00 | 3574270.6981 | 3917928.919 | 6679486.6401 | 4767129.3854 | 7407517.3021 | 5258443.0396 | 4241277.1493 | 4057399.7122 | 0.69947 | 0.88985 | 0.47204 | 1 | -42.375 | 0.88985 | 1 | 0.69947 | 1
10/11, 2009 | 2009-05-18 17:00 | 2009-11-10 17:00 | 1529638.2136 | 1518567.8143 | 1613342.6156 | 2009-08-25 17:00 | -11070.3993 | 99.28% | -94774.8013 | 94.13% | -55d | 79.4% | 100% | 2010-12-09 15:00 | 2010-12-13 17:00 | 2011-01-31 11:00 | 2010-12-09 16:00 | 2010-12-13 17:00 | 2011-01-06 15:00 | 2011-02-22 17:00 | 2011-06-23 16:00 | 2011-08-01 10:00 | 3581150.2712 | 3703962.4221 | 3595495.6407 | 4091666.4083 | 3719203.0954 | 4246340.2021 | 3681329.669 | 3771485.5289 | 0.79401 | 0.94126 | 0.99276 | 1 | -55 | 0.94126 | 1 | 0.79401 | 1
08/12, 2009 | 2009-11-10 17:00 | 2009-12-08 17:00 | 1773015.6191 | 1522257.9474 | 1617368.2156 | 2009-09-21 10:00 | -250757.6717 | 85.86% | -95110.2682 | 94.12% | -56d 6h | 80.23% | 100% | 2011-02-01 11:00 | 2011-04-13 09:00 | 2011-06-07 16:00 | 2011-02-02 14:00 | 2011-04-13 09:00 | 2011-05-12 17:00 | 2011-02-24 15:00 | 2011-06-14 16:00 | 2011-07-19 12:00 | 3581485.7381 | 3704203.274 | 3905029.8114 | 4065584.1937 | 4047962.2942 | 4218548.0712 | 3741497.3831 | 3767684.8803 | 0.80226 | 0.94119 | 0.85857 | 1 | -56.75 | 0.94119 | 1 | 0.80226 | 1
05/01, 2010 | 2009-12-08 17:00 | 2010-01-05 17:00 | 1923240.2898 | 1525948.0805 | 1621393.8156 | 2009-10-15 14:00 | -397292.2093 | 79.34% | -95445.7351 | 94.11% | -58d 3h | 80.99% | 100% | 2011-03-04 11:00 | 2011-06-24 11:00 | 2011-08-24 12:00 | 2011-03-07 11:00 | 2011-06-24 11:00 | 2011-07-28 11:00 | 2011-02-28 11:00 | 2011-06-06 11:00 | 2011-07-07 12:00 | 3581821.205 | 3704442.961 | 4092233.4128 | 4042112.6031 | 4246780.6773 | 4193524.887 | 3771947.4787 | 3764224.2788 | 0.80985 | 0.94113 | 0.79343 | 1 | -58.375 | 0.94113 | 1 | 0.80985 | 1
09/02, 2010 | 2010-01-05 17:00 | 2010-02-09 17:00 | 2277278.7008 | 1748850.7812 | 1841872.4207 | 2009-11-19 12:00 | -528427.9196 | 76.8% | -93021.6395 | 94.95% | -58d 4h | 82.38% | 100% | 2011-04-01 16:00 | 2011-07-27 10:00 | 2011-09-19 09:00 | 2011-03-24 17:00 | 2011-07-27 10:00 | 2011-08-24 12:00 | 2011-02-28 12:00 | 2011-05-19 17:00 | 2011-06-14 14:00 | 3579397.1095 | 3671816.3125 | 4104402.7683 | 3951043.1581 | 4224747.1023 | 4063230.271 | 3744574.0508 | 3721586.2582 | 0.8238 | 0.9495 | 0.76796 | 0.99996 | -58.5 | 0.9495 | 1 | 0.8238 | 1
02/03, 2010 | 2010-02-09 17:00 | 2010-03-02 17:00 | 2306035.5002 | 1890278.4052 | 1974074.6914 | 2009-12-17 09:00 | -415757.095 | 81.97% | -83796.2861 | 95.76% | -53d 7h | 84.47% | 99.97% | 2011-03-09 10:00 | 2011-05-25 10:00 | 2011-07-05 16:00 | 2011-03-04 12:00 | 2011-05-25 10:00 | 2011-06-14 12:00 | 2011-02-21 16:00 | 2011-04-27 12:00 | 2011-05-16 16:00 | 3570171.756 | 3640926.9453 | 3921225.1655 | 3863526.9095 | 4007542.5977 | 3947286.5706 | 3690339.2435 | 3681149.6968 | 0.84474 | 0.95755 | 0.81971 | 0.99973 | -53.875 | 0.95755 | 1 | 0.84474 | 1
13/04, 2010 | 2010-03-02 17:00 | 2010-04-13 17:00 | 2354381.099 | 2256840.9462 | 2336383.1029 | 2010-02-01 12:00 | -97540.1527 | 95.86% | -79542.1567 | 96.6% | -51d 4h | 86.34% | 99.91% | 2010-12-29 10:00 | 2011-01-10 14:00 | 2011-02-07 15:00 | 2010-12-29 14:00 | 2011-01-10 14:00 | 2011-01-19 12:00 | 2011-02-17 12:00 | 2011-04-07 12:00 | 2011-04-20 14:00 | 3565917.6266 | 3609252.4606 | 3619057.8293 | 3760452.2748 | 3664265.5849 | 3810643.465 | 3611201.5229 | 3636868.1267 | 0.8634 | 0.96596 | 0.95857 | 0.99911 | -51.5 | 0.96596 | 1 | 0.8634 | 1
25/05, 2010 | 2010-04-13 17:00 | 2010-05-25 17:00 | 2453181.4388 | 2313830.3137 | 2400198.3016 | 2010-03-09 15:00 | -139351.1252 | 94.32% | -86367.9879 | 96.4% | -55d 2h | 86.43% | 99.91% | 2011-01-06 16:00 | 2011-01-21 17:00 | 2011-02-22 14:00 | 2011-01-10 09:00 | 2011-01-21 17:00 | 2011-02-01 11:00 | 2011-02-23 10:00 | 2011-04-06 16:00 | 2011-04-19 11:00 | 3572743.4579 | 3616510.8704 | 3643360.3419 | 3756917.2173 | 3689763.66 | 3807559.2554 | 3621787.5802 | 3642218.1059 | 0.86425 | 0.96402 | 0.9432 | 0.99912 | -55.25 | 0.96402 | 1 | 0.86425 | 1
03/08, 2010 | 2010-05-25 17:00 | 2010-08-03 17:00 | 2659758.0311 | 2434896.1197 | 2535028.5604 | 2010-05-17 15:00 | -224861.9114 | 91.55% | -100132.4407 | 96.05% | -56d 2h | 87.69% | 100% | 2011-01-26 10:00 | 2011-02-16 12:00 | 2011-03-23 09:00 | 2011-01-31 14:00 | 2011-02-16 12:00 | 2011-02-24 10:00 | 2011-02-24 10:00 | 2011-03-24 15:00 | 2011-04-04 14:00 | 3586507.9106 | 3629748.8493 | 3683611.7068 | 3734095.4676 | 3730845.9329 | 3783405.7831 | 3640113.4502 | 3649139.546 | 0.87691 | 0.9605 | 0.91546 | 1 | -56.25 | 0.9605 | 1 | 0.87691 | 1
07/09, 2010 | 2010-08-03 17:00 | 2010-09-07 17:00 | 2803865.9015 | 2546680.0313 | 2649250.5109 | 2010-06-15 17:00 | -257185.8701 | 90.83% | -102570.4796 | 96.13% | -60d | 87.55% | 100% | 2011-02-02 11:00 | 2011-02-23 10:00 | 2011-03-29 12:00 | 2011-02-08 10:00 | 2011-02-23 10:00 | 2011-03-02 09:00 | 2011-03-01 17:00 | 2011-03-25 15:00 | 2011-04-04 12:00 | 3588945.9495 | 3626793.2686 | 3683844.5571 | 3722551.936 | 3725514.0272 | 3765780.3905 | 3637694.5504 | 3644553.2115 | 0.87552 | 0.96128 | 0.90827 | 1 | -60 | 0.96128 | 1 | 0.87552 | 1
05/10, 2010 | 2010-09-07 17:00 | 2010-10-05 17:00 | 3159577.1657 | 2611296.0285 | 2713866.5119 | 2010-07-13 17:00 | -548281.1372 | 82.65% | -102570.4834 | 96.22% | -60d | 88.05% | 100% | 2011-04-06 17:00 | 2011-05-17 16:00 | 2011-06-22 16:00 | 2011-04-08 09:00 | 2011-05-17 16:00 | 2011-05-26 09:00 | 2011-03-01 17:00 | 2011-03-22 10:00 | 2011-03-28 17:00 | 3588945.9533 | 3623318.6634 | 3772682.1311 | 3707735.0178 | 3814271.9121 | 3746773.7066 | 3649722.2517 | 3639034.8958 | 0.88048 | 0.96221 | 0.82647 | 1 | -60 | 0.96221 | 1 | 0.88048 | 1
02/11, 2010 | 2010-10-05 17:00 | 2010-11-02 17:00 | 3305131.9679 | 2740891.5023 | 2843461.9835 | 2010-08-10 17:00 | -564240.4656 | 82.93% | -102570.4812 | 96.39% | -60d | 88.51% | 100% | 2011-04-11 12:00 | 2011-05-13 14:00 | 2011-06-17 10:00 | 2011-04-12 09:00 | 2011-05-13 14:00 | 2011-05-20 15:00 | 2011-03-01 17:00 | 2011-03-16 17:00 | 2011-03-22 14:00 | 3588945.9512 | 3616843.6805 | 3742411.4279 | 3685762.0509 | 3776052.1893 | 3717282.862 | 3639070.2332 | 3629710.1022 | 0.88506 | 0.96393 | 0.82928 | 1 | -60 | 0.96393 | 1 | 0.88506 | 1
02/12, 2010 | 2010-11-02 17:00 | 2010-12-02 17:00 | 3466447.3501 | 2989691.0605 | 3092616.4456 | 2010-09-09 16:00 | -476756.2896 | 86.25% | -102925.3851 | 96.67% | -60d 1h | 88.95% | 100% | 2011-03-22 15:00 | 2011-04-08 10:00 | 2011-05-10 09:00 | 2011-03-22 16:00 | 2011-04-08 10:00 | 2011-04-13 11:00 | 2011-03-02 09:00 | 2011-03-11 17:00 | 2011-03-16 11:00 | 3589300.855 | 3606400.0914 | 3668505.499 | 3651017.5176 | 3688331.4949 | 3670241.4589 | 3617725.9322 | 3614743.9091 | 0.88948 | 0.96672 | 0.86247 | 1 | -60.125 | 0.96672 | 1 | 0.88948 | 1
04/01, 2011 | 2010-12-02 17:00 | 2011-01-04 17:00 | 3486375.4699 | 3197915.6775 | 3304922.4476 | 2010-10-12 11:00 | -288459.7925 | 91.73% | -107006.7701 | 96.76% | -60d 5h | 89.31% | 99.92% | 2011-02-09 10:00 | 2011-02-15 11:00 | 2011-03-15 10:00 | 2011-03-10 16:00 | 2011-03-17 09:00 | 2011-03-18 16:00 | 2011-03-02 14:00 | 2011-03-09 12:00 | 2011-03-10 17:00 | 3593382.2401 | 3603034.5117 | 3619402.0168 | 3627917.6633 | 3629924.9468 | 3638725.5389 | 3606170.2801 | 3607699.6275 | 0.89308 | 0.96762 | 0.91726 | 0.99925 | -60.625 | 0.96762 | 1 | 0.89308 | 1
08/02, 2011 | 2011-01-04 17:00 | 2011-02-08 17:00 | 3486375.4699 | 3357330.5918 | 3468773.6506 | 2010-11-15 12:00 | -129044.8781 | 96.3% | -111443.0588 | 96.79% | -61d 4h | 89.61% | 99.88% | 2011-01-05 10:00 | 2011-01-05 17:00 | 2011-02-01 16:00 | 2011-03-10 16:00 | 2011-03-11 15:00 | 2011-03-14 12:00 | 2011-03-03 12:00 | 2011-03-07 11:00 | 2011-03-07 17:00 | 3597818.5287 | 3602102.0378 | 3602778.5945 | 3612778.491 | 3607226.7477 | 3617558.5803 | 3602236.802 | 3604108.7747 | 0.89611 | 0.96787 | 0.96299 | 0.99881 | -61.5 | 0.96787 | 1 | 0.89611 | 1
Actual Schedule | 2011-02-08 17:00 | 2011-03-07 17:00 | 3486375.4699 | 3486375.4699 | 3599114.1116 | 2010-12-07 17:00 | 0 | 100% | -112738.6416 | 96.87% | -64d | 89.53% | 100% | 2010-12-07 17:00 | 2010-12-07 17:00 | 2010-12-31 15:00 | 2011-03-07 17:00 | 2011-03-07 17:00 | 2011-03-07 17:00 | 2011-03-07 17:00 | 2011-03-07 17:00 | 2011-03-07 17:00 | 3599114.1116 | 3599114.1116 | 3599114.1116 | 3599114.1116 | 3599114.1116 | 3599114.1116 | 3599114.1116 | 3599114.1116 | 0.89525 | 0.96868 | 1 | 1 | -64 | 0.96868 | 1 | 0.89525 | 1