## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Industrial Complex (1) | 1 |  |  | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 | 358.375
67 | Ruwbouw | 1.1 |  |  | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 | 214.375
6 | Funderingswerken | 1.1.1 |  |  | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 | 92.0417
1 | Paalfundering | 1.1.1.1 |  | FS2+2d;FS3 | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 11.375
2 | Knippen van de palen | 1.1.1.2 | 1FS+2d |  | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 0.375
3 | Grondwerken | 1.1.1.3 | 1FS | FS4-1w 2d | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 28.375
4 | Funderingsbalken | 1.1.1.4 | 3FS-1w 2d |  | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 37.375
5 | Funderingsbalken en aanpassingen | 1.1.1.5 |  |  | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.041667
17 | Bovenbouw A | 1.1.2 |  |  | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 | 31.375
12 | Montage prefab | 1.1.2.1 |  |  | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 | 27.375
7 | Kolommen | 1.1.2.1.1 |  | FS9 | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 3.375
8 | balken | 1.1.2.1.2 | 9FS | FS10 | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 1.375
9 | Structurele wand | 1.1.2.1.3 | 7FS | FS8 | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2.375
10 | Welfsles | 1.1.2.1.4 | 8FS | FS13;FS18 | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 1.375
11 | SW-panelen | 1.1.2.1.5 | 20FS | FS21 | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 4.375
16 | Ruwbouwwerken | 1.1.2.2 |  |  | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 | 16.375
13 | Voorbereiding opstortbeton | 1.1.2.2.1 | 10FS | FS14 | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 1.375
14 | opstort niv 1 en 2 | 1.1.2.2.2 | 13FS | FS15 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 0.375
15 | Metselwerken | 1.1.2.2.3 | 14FS |  | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 11.375
27 | Bovenbouw B | 1.1.3 |  |  | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 | 19.375
22 | Montage prefab | 1.1.3.1 |  |  | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 | 14.375
18 | Kolommen | 1.1.3.1.1 | 10FS | FS19 | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 1.375
19 | Balken | 1.1.3.1.2 | 18FS | FS20 | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 3.375
20 | Welfsels | 1.1.3.1.3 | 19FS | FS11;FS23 | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 1.375
21 | SW-panelen | 1.1.3.1.4 | 11FS | FS28 | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 1.375
26 | Ruwbouwwerken | 1.1.3.2 |  |  | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 | 11.375
23 | voorbereiding opstortbeton | 1.1.3.2.1 | 20FS | FS24 | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 1.375
24 | Opstort niv 1 en 2 | 1.1.3.2.2 | 23FS | FS25 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 0.375
25 | metselwerken | 1.1.3.2.3 | 24FS | FS51+1w | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 6.375
38 | Bovenbouw C | 1.1.4 |  |  | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 | 67.375
33 | Montage prefab | 1.1.4.1 |  |  | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 | 60.375
28 | kolommen | 1.1.4.1.1 | 21FS | FS29 | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 5.375
29 | centrale kern | 1.1.4.1.2 | 28FS | FS30 | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 5.375
30 | balken | 1.1.4.1.3 | 29FS | FS31 | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 10.375
31 | welfsels | 1.1.4.1.4 | 30FS | FS34 | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 | 4.375
32 | SW panelen | 1.1.4.1.5 | 35FS |  | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 | 18.375
37 | Ruwbouwwerken | 1.1.4.2 |  |  | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 | 35.375
34 | voorbereiding opstortbeton | 1.1.4.2.1 | 31FS | FS35 | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 4.375
35 | opstort niv 1, 2 en 3 | 1.1.4.2.2 | 34FS | FS36;FS32;FS39 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 | 2.375
36 | Metselwerk | 1.1.4.2.3 | 35FS |  | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 | 25.375
47 | Draagvloer gv | 1.1.5 |  |  | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 | 63.375
39 | rioleringswerken | 1.1.5.1 | 35FS | FS40 | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 | 14.375
40 | aanvulling gestabiliseerd zand | 1.1.5.2 | 39FS | FS41-2d | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 | 13.375
41 | plaatsen vloerisolatie | 1.1.5.3 | 40FS-2d | FS42-2d | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 5.375
42 | plaatsen wapening | 1.1.5.4 | 41FS-2d | FS43 | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 5.375
43 | bekistingswerken | 1.1.5.5 | 42FS | FS44 | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 1.375
44 | stort vloerplaat gv | 1.1.5.6 | 43FS | FS46 | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 1.375
45 | vloerplaat centrum | 1.1.5.7 |  |  | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.041667
46 | metselwerken | 1.1.5.8 | 44FS | FS60 | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 | 22.375
50 | Regenwater afvoeren | 1.1.6 |  |  | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 | 21.0417
48 | RW deel 1 | 1.1.6.1 |  |  | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.041667
49 | RW deel 2 | 1.1.6.2 |  |  | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.041667
54 | Dakwerken deel 1 | 1.1.7 |  |  | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 | 32.375
51 | hellingsbeton | 1.1.7.1 | 25FS+1w | FS52+3d | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 | 4.375
52 | dampscherm + isolatie + afwerking | 1.1.7.2 | 51FS+3d | FS53 | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 | 14.375
53 | Aanwerken aan bestaande toestand | 1.1.7.3 | 52FS |  | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 | 7.375
58 | Dakwerken deel 2 | 1.1.8 |  |  | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 | 5.125
55 | hellingsbeton | 1.1.8.1 |  |  | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.041667
56 | dampscherm + isolatie + afwerking | 1.1.8.2 |  |  | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.041667
57 | Aanwerken aan bestaande toestand | 1.1.8.3 |  |  | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.041667
61 | Buitenschrijnwerk deel 1 | 1.1.9 |  |  | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 | 17.375
59 | Alu ramen | 1.1.9.1 |  |  | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.041667
60 | sectionaalpoorten | 1.1.9.2 | 46FS |  | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 7.375
66 | Buitenschrijnwerk deel 2 | 1.1.10 |  |  | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 | 26.375
62 | Alu ramen | 1.1.10.1 |  | FS63;FS64 | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 | 11.375
63 | gordijngevel elementen | 1.1.10.2 | 62FS | FS65 | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 7.375
64 | automatische deuren | 1.1.10.3 | 62FS |  | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 7.375
65 | vouwgeheel | 1.1.10.4 | 63FS |  | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 | 6.375
163 | Planning afwerking | 1.2 |  |  | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 | 141.375
80 | 1e verdieping landscape links | 1.2.1 |  |  | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 | 105.375
68 | HVAC plafond | 1.2.1.1 |  | SS69;SS81;FS116;FS130 | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 18.375
69 | Elektriciteit plafond | 1.2.1.2 | 68SS | FS70 | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 18.375
70 | Schilderwerk wanden | 1.2.1.3 | 69FS | FS71;FS156 | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2.375
71 | Structuur valse plafond | 1.2.1.4 | 70FS | FS72 | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 4.375
72 | elecktriciteit vloer | 1.2.1.5 | 71FS | FS73 | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 | 31.375
73 | Verhoogde vloer | 1.2.1.6 | 72FS | FS74;FS75 | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 4.375
74 | HVAC toestellen plafond | 1.2.1.7 | 73FS |  | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 7.375
75 | Elektriciteit toestellen plafond | 1.2.1.8 | 73FS | FS76 | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 7.375
76 | Binnenschrijnwerk | 1.2.1.9 | 75FS | FS77 | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 | 6.375
77 | Schilderwerk | 1.2.1.10 | 76FS | FS78 | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 7.375
78 | plafondtegels | 1.2.1.11 | 77FS | FS79 | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 5.375
79 | tapijt | 1.2.1.12 | 78FS |  | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 6.375
84 | Schacht | 1.2.2 |  |  | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 | 22.375
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 1.2.2.1 | 68SS | FS82;FS83;FS85 | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 | 8.375
82 | HVAC | 1.2.2.2 | 81FS |  | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 | 13.375
83 | Elektriciteit | 1.2.2.3 | 81FS |  | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 | 13.375
92 | 2e verdieping sanitair | 1.2.3 |  |  | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 | 62.375
85 | aan en afvoerleidingen | 1.2.3.1 | 81FS | FS86 | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 5.375
86 | montage toiletten | 1.2.3.2 | 85FS | FS87+2d;FS93 | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
87 | bezettingswerken (cementering) | 1.2.3.3 | 86FS+2d | FS88;FS95 | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 4.375
88 | pur en chape | 1.2.3.4 | 87FS | FS89 | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
89 | gyproc | 1.2.3.5 | 88FS | FS90 | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
90 | tegelwerken | 1.2.3.6 | 89FS | FS91 | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 | 35.375
91 | plafond | 1.2.3.7 | 90FS |  | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
100 | 1e verdieping sanitair | 1.2.4 |  |  | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 | 63.375
93 | aan en afvoerleidingen | 1.2.4.1 | 86FS | FS94 | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 5.375
94 | montage hangtoiletten | 1.2.4.2 | 93FS | FS101 | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
95 | bezettingswerken (cementering) | 1.2.4.3 | 87FS | FS96 | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 4.375
96 | pur en chape | 1.2.4.4 | 95FS | FS97 | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
97 | gyproc | 1.2.4.5 | 96FS | FS98 | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
98 | tegelwerken | 1.2.4.6 | 97FS | FS99 | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 15.375
99 | plafond | 1.2.4.7 | 98FS |  | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
107 | gv sanitair links | 1.2.5 |  |  | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 | 82.375
101 | aan en afvoerleidingen | 1.2.5.1 | 94FS | FS102;FS108 | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 | 32.375
102 | montage hangtoiletten | 1.2.5.2 | 101FS | FS103 | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 5.375
103 | bezettingswerken (cementering) | 1.2.5.3 | 102FS | FS104 | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 15.375
104 | gyproc | 1.2.5.4 | 103FS | FS105 | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
105 | tegelwerken | 1.2.5.5 | 104FS | FS106 | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 | 18.375
106 | plafond | 1.2.5.6 | 105FS |  | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 | 2.375
115 | Gelijkvloers sanitair rechts | 1.2.6 |  |  | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 | 40.375
108 | aan en afvoerleidingen | 1.2.6.1 | 101FS | FS109 | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 5.375
109 | montage hangtoiletten | 1.2.6.2 | 108FS | FS110 | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
110 | bezettingswerken (cementering) | 1.2.6.3 | 109FS | FS111 | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 6.375
111 | pur en chape | 1.2.6.4 | 110FS | FS112 | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
112 | gyproc | 1.2.6.5 | 111FS | FS113 | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 1.375
113 | tegelwerken | 1.2.6.6 | 112FS | FS114 | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 | 13.375
114 | plafond | 1.2.6.7 | 113FS |  | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 3.375
129 | 2e verdieping landscape rechts | 1.2.7 |  |  | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 | 115.375
116 | HVAC plafond | 1.2.7.1 | 68FS | SS117 | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 44.375
117 | Elektriciteit plafond | 1.2.7.2 | 116SS | FS118 | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 44.375
118 | Schilderwerken wanden | 1.2.7.3 | 117FS | FS119 | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 4.375
119 | structuur vals plafond | 1.2.7.4 | 118FS | FS120 | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 | 8.375
120 | Elektriciteit vloer | 1.2.7.5 | 119FS | FS121 | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 13.375
121 | verhoogde vloer | 1.2.7.6 | 120FS | FS122;FS123 | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 | 8.375
122 | HVAC toestellen plafond | 1.2.7.7 | 121FS |  | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 3.375
123 | Elektriciteit toestellen plafond | 1.2.7.8 | 121FS | FS124 | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 3.375
124 | Binnenschrijnwerk | 1.2.7.9 | 123FS | SS125 | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 6.375
125 | keuken | 1.2.7.10 | 124SS | FS126 | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 | 6.375
126 | Schilderwerken | 1.2.7.11 | 125FS | FS127 | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 7.375
127 | plafondtegels | 1.2.7.12 | 126FS | FS128 | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 3.375
128 | tapijt | 1.2.7.13 | 127FS |  | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 6.375
142 | 1e verdieping landscape rechts | 1.2.8 |  |  | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 | 105.375
130 | HVAC plafond | 1.2.8.1 | 68FS | SS131;FS143 | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 42.375
131 | Elektriciteit plafond | 1.2.8.2 | 130SS | FS132 | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 42.375
132 | Schilderwerken wanden | 1.2.8.3 | 131FS | FS133 | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2.375
133 | structuur valse plafond | 1.2.8.4 | 132FS | FS134 | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 4.375
134 | Elektriciteit vloer | 1.2.8.5 | 133FS | FS135 | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 13.375
135 | verhoogde vloer | 1.2.8.6 | 134FS | FS136;FS137 | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 6.375
136 | HVAC toestellen plafond | 1.2.8.7 | 135FS |  | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 5.375
137 | Elektriciteit toestellen plafond | 1.2.8.8 | 135FS | FS138 | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 5.375
138 | Binnenschrijnwerk | 1.2.8.9 | 137FS | FS139 | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 6.375
139 | schilderwerken | 1.2.8.10 | 138FS | FS140 | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 7.375
140 | plafondtegels | 1.2.8.11 | 139FS | FS141 | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 5.375
141 | tapijt | 1.2.8.12 | 140FS |  | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 6.375
155 | gv landscape rechts | 1.2.9 |  |  | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 | 72.375
143 | HVAC plafond | 1.2.9.1 | 130FS | SS144 | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 22.375
144 | Elektriciteit plafond | 1.2.9.2 | 143SS | FS145 | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 22.375
145 | Schilderwerk wanden | 1.2.9.3 | 144FS | FS146 | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 4.375
146 | structuur valse plafond | 1.2.9.4 | 145FS | FS147 | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2.375
147 | elektriciteit vloer | 1.2.9.5 | 146FS | FS148 | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 | 11.375
148 | verhoogde vloer | 1.2.9.6 | 147FS | FS149;FS150 | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 6.375
149 | HVAC toestellen plafond | 1.2.9.7 | 148FS |  | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 5.375
150 | Elektriciteit toestellen plafond | 1.2.9.8 | 148FS | FS151 | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 5.375
151 | Binnenschrijnwerk | 1.2.9.9 | 150FS | FS152 | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 | 1.375
152 | Schilderwerk | 1.2.9.10 | 151FS | FS153 | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 | 1.375
153 | plafondtegels | 1.2.9.11 | 152FS | FS154 | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 3.375
154 | tapijt | 1.2.9.12 | 153FS |  | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 6.375
162 | overige delen gv | 1.2.10 |  |  | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 | 117.375
156 | schilderwerk | 1.2.10.1 | 70FS | FS157 | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 | 53.375
157 | HVAC plafond | 1.2.10.2 | 156FS | FS158 | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 20.375
158 | Elektriciteit plafond | 1.2.10.3 | 157FS | FS159;SS160+1w | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 20.375
159 | binnenschrijnwerk | 1.2.10.4 | 158FS |  | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 | 8.375
160 | gyproc werken | 1.2.10.5 | 158SS+1w | FS161 | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 | 27.375
161 | Schilderwerken | 1.2.10.6 | 160FS |  | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 7.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Industrial Complex (1) | 2056h |  |  |  |  | 99 | 100 | 101
67 | Ruwbouw | 1240h |  |  |  |  | 99 | 100 | 101
6 | Funderingswerken | 529h |  |  |  |  | 99 | 100 | 101
1 | Paalfundering | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Knippen van de palen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Grondwerken | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Funderingsbalken | 224h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Funderingsbalken en aanpassingen | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Bovenbouw A | 192h |  |  |  |  | 99 | 100 | 101
12 | Montage prefab | 160h |  |  |  |  | 99 | 100 | 101
7 | Kolommen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | balken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Structurele wand | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Welfsles | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | SW-panelen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Ruwbouwwerken | 104h |  |  |  |  | 99 | 100 | 101
13 | Voorbereiding opstortbeton | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | opstort niv 1 en 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Bovenbouw B | 112h |  |  |  |  | 99 | 100 | 101
22 | Montage prefab | 88h |  |  |  |  | 99 | 100 | 101
18 | Kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Balken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Welfsels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | SW-panelen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Ruwbouwwerken | 64h |  |  |  |  | 99 | 100 | 101
23 | voorbereiding opstortbeton | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Opstort niv 1 en 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | metselwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Bovenbouw C | 384h |  |  |  |  | 99 | 100 | 101
33 | Montage prefab | 344h |  |  |  |  | 99 | 100 | 101
28 | kolommen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | centrale kern | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | balken | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | welfsels | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | SW panelen | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Ruwbouwwerken | 208h |  |  |  |  | 99 | 100 | 101
34 | voorbereiding opstortbeton | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | opstort niv 1, 2 en 3 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Metselwerk | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Draagvloer gv | 368h |  |  |  |  | 99 | 100 | 101
39 | rioleringswerken | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | aanvulling gestabiliseerd zand | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | plaatsen vloerisolatie | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | plaatsen wapening | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | bekistingswerken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | stort vloerplaat gv | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | vloerplaat centrum | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | metselwerken | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Regenwater afvoeren | 121h |  |  |  |  | 99 | 100 | 101
48 | RW deel 1 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | RW deel 2 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Dakwerken deel 1 | 184h |  |  |  |  | 99 | 100 | 101
51 | hellingsbeton | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | dampscherm + isolatie + afwerking | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Aanwerken aan bestaande toestand | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Dakwerken deel 2 | 27h |  |  |  |  | 99 | 100 | 101
55 | hellingsbeton | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | dampscherm + isolatie + afwerking | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Aanwerken aan bestaande toestand | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Buitenschrijnwerk deel 1 | 112h |  |  |  |  | 99 | 100 | 101
59 | Alu ramen | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | sectionaalpoorten | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Buitenschrijnwerk deel 2 | 152h |  |  |  |  | 99 | 100 | 101
62 | Alu ramen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | gordijngevel elementen | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | automatische deuren | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | vouwgeheel | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
163 | Planning afwerking | 816h |  |  |  |  | 99 | 100 | 101
80 | 1e verdieping landscape links | 608h |  |  |  |  | 99 | 100 | 101
68 | HVAC plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Elektriciteit plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | Schilderwerk wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Structuur valse plafond | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | elecktriciteit vloer | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | Verhoogde vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | HVAC toestellen plafond | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | Elektriciteit toestellen plafond | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | Binnenschrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | Schilderwerk | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | plafondtegels | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | tapijt | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | Schacht | 136h |  |  |  |  | 99 | 100 | 101
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | HVAC | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Elektriciteit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | 2e verdieping sanitair | 360h |  |  |  |  | 99 | 100 | 101
85 | aan en afvoerleidingen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | montage toiletten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | bezettingswerken (cementering) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | pur en chape | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | gyproc | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | tegelwerken | 208h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | plafond | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | 1e verdieping sanitair | 368h |  |  |  |  | 99 | 100 | 101
93 | aan en afvoerleidingen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | montage hangtoiletten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | bezettingswerken (cementering) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | pur en chape | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | gyproc | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | tegelwerken | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | plafond | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | gv sanitair links | 472h |  |  |  |  | 99 | 100 | 101
101 | aan en afvoerleidingen | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | montage hangtoiletten | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | bezettingswerken (cementering) | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | gyproc | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | tegelwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | plafond | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | Gelijkvloers sanitair rechts | 232h |  |  |  |  | 99 | 100 | 101
108 | aan en afvoerleidingen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | montage hangtoiletten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | bezettingswerken (cementering) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | pur en chape | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | gyproc | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | tegelwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | plafond | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | 2e verdieping landscape rechts | 672h |  |  |  |  | 99 | 100 | 101
116 | HVAC plafond | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | Elektriciteit plafond | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | Schilderwerken wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | structuur vals plafond | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | Elektriciteit vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | verhoogde vloer | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | HVAC toestellen plafond | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | Elektriciteit toestellen plafond | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | Binnenschrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | Schilderwerken | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | plafondtegels | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | tapijt | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | 1e verdieping landscape rechts | 608h |  |  |  |  | 99 | 100 | 101
130 | HVAC plafond | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | Elektriciteit plafond | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | Schilderwerken wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | structuur valse plafond | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | Elektriciteit vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | verhoogde vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | HVAC toestellen plafond | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | Elektriciteit toestellen plafond | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | Binnenschrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | schilderwerken | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | plafondtegels | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | tapijt | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | gv landscape rechts | 424h |  |  |  |  | 99 | 100 | 101
143 | HVAC plafond | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | Elektriciteit plafond | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | Schilderwerk wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | structuur valse plafond | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | elektriciteit vloer | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | verhoogde vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | HVAC toestellen plafond | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | Elektriciteit toestellen plafond | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | Binnenschrijnwerk | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | Schilderwerk | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | plafondtegels | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | tapijt | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | overige delen gv | 672h |  |  |  |  | 99 | 100 | 101
156 | schilderwerk | 304h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | HVAC plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | Elektriciteit plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
159 | binnenschrijnwerk | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | gyproc werken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
161 | Schilderwerken | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-12-11 17:00 |  | TP Name | 11/12, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 32d | [5 empty] | 60167.1203 |  | 3.322% |  | 74554.5746 | 66790.8005
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 32d | [5 empty] | 60167.1203 |  | 5.318% |  | 74554.5746 | 66790.8005
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 32d | [5 empty] | 60167.1203 |  | 72.53% |  | 74554.5746 | 66790.8005
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 7d | 11998.5597 | 17140.7996 | 10d | 0 | 0 | 11998.5597 | 17140.7996 | 41.18% | Started | 19762.3339 | 11998.5597 | 100 | 25 | 41.1765 | 100 | 25 | 41.1765
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 |  | 0 | 0 | 13493.1201 | 4d | 0 | 0 | 0 | 13493.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 |  | 0 | 0 | 3980.48 | 2d | 0 | 0 | 0 | 3980.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 |  | 0 | 0 | 292999.9219 | 3d | 0 | 0 | 0 | 292999.9219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 |  | 0 | 0 | 37872 | 2d | 0 | 0 | 0 | 37872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 |  | 0 | 0 | 13308.2402 | 3d | 0 | 0 | 0 | 13308.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 |  | 0 | 0 | 5881.1201 | 2d | 0 | 0 | 0 | 5881.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 |  | 0 | 0 | 2940.5601 | 1d | 0 | 0 | 0 | 2940.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 |  | 0 | 0 | 29405.6006 | 10d | 0 | 0 | 0 | 29405.6006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 |  | 0 | 0 | 6746.5601 | 2d | 0 | 0 | 0 | 6746.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 |  | 0 | 0 | 3980.48 | 2d | 0 | 0 | 0 | 3980.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 |  | 0 | 0 | 37872 | 2d | 0 | 0 | 0 | 37872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 |  | 0 | 0 | 8872.1602 | 2d | 0 | 0 | 0 | 8872.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 |  | 0 | 0 | 5881.1201 | 2d | 0 | 0 | 0 | 5881.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 |  | 0 | 0 | 2940.5601 | 1d | 0 | 0 | 0 | 2940.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 |  | 0 | 0 | 14702.8003 | 5d | 0 | 0 | 0 | 14702.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 |  | 0 | 0 | 13493.1201 | 4d | 0 | 0 | 0 | 13493.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 |  | 0 | 0 | 11057.9199 | 4d | 0 | 0 | 0 | 11057.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 |  | 0 | 0 | 17912.1599 | 9d | 0 | 0 | 0 | 17912.1599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 |  | 0 | 0 | 94680 | 5d | 0 | 0 | 0 | 94680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 |  | 0 | 0 | 57669.041 | 13d | 0 | 0 | 0 | 57669.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 |  | 0 | 0 | 14702.8003 | 5d | 0 | 0 | 0 | 14702.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 |  | 0 | 0 | 8821.6802 | 3d | 0 | 0 | 0 | 8821.6802 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 |  | 0 | 0 | 52930.0811 | 18d | 0 | 0 | 0 | 52930.0811 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 |  | 0 | 0 | 42922 | 11d | 0 | 0 | 0 | 42922 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 |  | 0 | 0 | 36080 | 10d | 0 | 0 | 0 | 36080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 |  | 0 | 0 | 14432 | 4d | 0 | 0 | 0 | 14432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 |  | 0 | 0 | 14432 | 4d | 0 | 0 | 0 | 14432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 |  | 0 | 0 | 7216 | 2d | 0 | 0 | 0 | 7216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 |  | 0 | 0 | 7216 | 2d | 0 | 0 | 0 | 7216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 |  | 0 | 0 | 61336 | 17d | 0 | 0 | 0 | 61336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 |  | 0 | 0 | 11050.5601 | 3d | 0 | 0 | 0 | 11050.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 |  | 0 | 0 | 40518.7202 | 11d | 0 | 0 | 0 | 40518.7202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 |  | 0 | 0 | 22101.1201 | 6d | 0 | 0 | 0 | 22101.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 |  | 0 | 0 | 74728.3203 | 8d | 0 | 0 | 0 | 74728.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 |  | 0 | 0 | 46705.2002 | 5d | 0 | 0 | 0 | 46705.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 |  | 0 | 0 | 57306.2402 | 24d | 0 | 0 | 0 | 57306.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 |  | 0 | 0 | 67547.5977 | 5d | 0 | 0 | 0 | 67547.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 |  | 0 | 0 | 4622.8002 | 7d | 0 | 0 | 0 | 4622.8002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 |  | 0 | 0 | 16028.8 | 10d | 0 | 0 | 0 | 16028.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 |  | 0 | 0 | 3641.6 | 10d | 0 | 0 | 0 | 3641.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 |  | 0 | 0 | 17170.4006 | 26d | 0 | 0 | 0 | 17170.4006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 |  | 0 | 0 | 15189.2006 | 23d | 0 | 0 | 0 | 15189.2006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 |  | 0 | 0 | 9906.0004 | 15d | 0 | 0 | 0 | 9906.0004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 |  | 0 | 0 | 1981.2001 | 3d | 0 | 0 | 0 | 1981.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 |  | 0 | 0 | 6604.0002 | 10d | 0 | 0 | 0 | 6604.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 |  | 0 | 0 | 2549.12 | 7d | 0 | 0 | 0 | 2549.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 |  | 0 | 0 | 16714.3201 | 7d | 0 | 0 | 0 | 16714.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 |  | 0 | 0 | 5425.6 | 5d | 0 | 0 | 0 | 5425.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 |  | 0 | 0 | 19102.0801 | 8d | 0 | 0 | 0 | 19102.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 |  | 0 | 0 | 43018.8789 | 2d | 0 | 0 | 0 | 43018.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 |  | 0 | 0 | 1484.8 | 2d | 0 | 0 | 0 | 1484.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 |  | 0 | 0 | 28211.2009 | 38d | 0 | 0 | 0 | 28211.2009 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 |  | 0 | 0 | 94566.083 | 7d | 0 | 0 | 0 | 94566.083 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 |  | 0 | 0 | 4291.2 | 20d | 0 | 0 | 0 | 4291.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-01-24 17:00 |  | TP Name | 24/01, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 64d | [5 empty] | 77307.9199 |  | 4.58% |  | 102786.4796 | 463759.6817
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 64d | [5 empty] | 77307.9199 |  | 7.332% |  | 102786.4796 | 463759.6817
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 64d | [5 empty] | 77307.9199 |  | 100% |  | 102786.4796 | 102786.4796
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 100% | Finished | 47994.2388 | 47994.2388 | 100 | 60.7143 | 100 | 100 | 60.7143 | 100
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 354226.6421
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 348345.522
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 |  | 0 | 0 | 13493.1201 | 4d | 0 | 0 | 0 | 13493.1201 | 0% | Not Started | 0 | 13493.1201 | 100 |  | 0 | 100 |  | 0
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 |  | 0 | 0 | 3980.48 | 2d | 0 | 0 | 0 | 3980.48 | 0% | Not Started | 0 | 3980.48 | 100 |  | 0 | 100 |  | 0
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 |  | 0 | 0 | 292999.9219 | 3d | 0 | 0 | 0 | 292999.9219 | 0% | Not Started | 0 | 292999.9219 | 100 |  | 0 | 100 |  | 0
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 |  | 0 | 0 | 37872 | 2d | 0 | 0 | 0 | 37872 | 0% | Not Started | 0 | 37872 | 100 |  | 0 | 100 |  | 0
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 |  | 0 | 0 | 13308.2402 | 3d | 0 | 0 | 0 | 13308.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 5881.1201
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 |  | 0 | 0 | 5881.1201 | 2d | 0 | 0 | 0 | 5881.1201 | 0% | Not Started | 0 | 5881.1201 | 100 |  | 0 | 100 |  | 0
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 |  | 0 | 0 | 2940.5601 | 1d | 0 | 0 | 0 | 2940.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 |  | 0 | 0 | 29405.6006 | 10d | 0 | 0 | 0 | 29405.6006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6746.5601
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6746.5601
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 |  | 0 | 0 | 6746.5601 | 2d | 0 | 0 | 0 | 6746.5601 | 0% | Not Started | 0 | 6746.5601 | 100 |  | 0 | 100 |  | 0
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 |  | 0 | 0 | 3980.48 | 2d | 0 | 0 | 0 | 3980.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 |  | 0 | 0 | 37872 | 2d | 0 | 0 | 0 | 37872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 |  | 0 | 0 | 8872.1602 | 2d | 0 | 0 | 0 | 8872.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 |  | 0 | 0 | 5881.1201 | 2d | 0 | 0 | 0 | 5881.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 |  | 0 | 0 | 2940.5601 | 1d | 0 | 0 | 0 | 2940.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 |  | 0 | 0 | 14702.8003 | 5d | 0 | 0 | 0 | 14702.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 |  | 0 | 0 | 13493.1201 | 4d | 0 | 0 | 0 | 13493.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 |  | 0 | 0 | 11057.9199 | 4d | 0 | 0 | 0 | 11057.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 |  | 0 | 0 | 17912.1599 | 9d | 0 | 0 | 0 | 17912.1599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 |  | 0 | 0 | 94680 | 5d | 0 | 0 | 0 | 94680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 |  | 0 | 0 | 57669.041 | 13d | 0 | 0 | 0 | 57669.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 |  | 0 | 0 | 14702.8003 | 5d | 0 | 0 | 0 | 14702.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 |  | 0 | 0 | 8821.6802 | 3d | 0 | 0 | 0 | 8821.6802 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 |  | 0 | 0 | 52930.0811 | 18d | 0 | 0 | 0 | 52930.0811 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 |  | 0 | 0 | 42922 | 11d | 0 | 0 | 0 | 42922 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 |  | 0 | 0 | 36080 | 10d | 0 | 0 | 0 | 36080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 |  | 0 | 0 | 14432 | 4d | 0 | 0 | 0 | 14432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 |  | 0 | 0 | 14432 | 4d | 0 | 0 | 0 | 14432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 |  | 0 | 0 | 7216 | 2d | 0 | 0 | 0 | 7216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 |  | 0 | 0 | 7216 | 2d | 0 | 0 | 0 | 7216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 |  | 0 | 0 | 61336 | 17d | 0 | 0 | 0 | 61336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 |  | 0 | 0 | 11050.5601 | 3d | 0 | 0 | 0 | 11050.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 |  | 0 | 0 | 40518.7202 | 11d | 0 | 0 | 0 | 40518.7202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 |  | 0 | 0 | 22101.1201 | 6d | 0 | 0 | 0 | 22101.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 |  | 0 | 0 | 74728.3203 | 8d | 0 | 0 | 0 | 74728.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 |  | 0 | 0 | 46705.2002 | 5d | 0 | 0 | 0 | 46705.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 |  | 0 | 0 | 57306.2402 | 24d | 0 | 0 | 0 | 57306.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 |  | 0 | 0 | 67547.5977 | 5d | 0 | 0 | 0 | 67547.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 |  | 0 | 0 | 4622.8002 | 7d | 0 | 0 | 0 | 4622.8002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 |  | 0 | 0 | 16028.8 | 10d | 0 | 0 | 0 | 16028.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 |  | 0 | 0 | 3641.6 | 10d | 0 | 0 | 0 | 3641.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 |  | 0 | 0 | 17170.4006 | 26d | 0 | 0 | 0 | 17170.4006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 |  | 0 | 0 | 15189.2006 | 23d | 0 | 0 | 0 | 15189.2006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 |  | 0 | 0 | 9906.0004 | 15d | 0 | 0 | 0 | 9906.0004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 |  | 0 | 0 | 1981.2001 | 3d | 0 | 0 | 0 | 1981.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 |  | 0 | 0 | 6604.0002 | 10d | 0 | 0 | 0 | 6604.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 |  | 0 | 0 | 2549.12 | 7d | 0 | 0 | 0 | 2549.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 |  | 0 | 0 | 16714.3201 | 7d | 0 | 0 | 0 | 16714.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 |  | 0 | 0 | 5425.6 | 5d | 0 | 0 | 0 | 5425.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 |  | 0 | 0 | 19102.0801 | 8d | 0 | 0 | 0 | 19102.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 |  | 0 | 0 | 43018.8789 | 2d | 0 | 0 | 0 | 43018.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 |  | 0 | 0 | 1484.8 | 2d | 0 | 0 | 0 | 1484.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 |  | 0 | 0 | 28211.2009 | 38d | 0 | 0 | 0 | 28211.2009 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 |  | 0 | 0 | 94566.083 | 7d | 0 | 0 | 0 | 94566.083 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 |  | 0 | 0 | 4291.2 | 20d | 0 | 0 | 0 | 4291.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-03-11 17:00 |  | TP Name | 11/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 96d | [5 empty] | 375237.6816 |  | 27.26% |  | 611796.6853 | 723746.9832
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 96d | [5 empty] | 375237.6816 |  | 43.64% |  | 611796.6853 | 723746.9832
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 75d | [5 empty] | 92734.6399 |  | 100% |  | 102786.4896 | 102786.4896
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 100% | Finished | 47994.2388 | 47994.2388 | 100 | 60.7143 | 100 | 100 | 60.7143 | 100
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-01-29 08:00 | 9d | 0.72 | 0 | 0 | 15426 | 0 | 15426.72 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 7200 | 100 | 100 | 154267203.448 | 100
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 18d | [5 empty] | 183963.8413 |  | 100% |  | 399881.043 | 399881.043
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 18d | [5 empty] | 166320.481 |  | 100% |  | 361653.7622 | 361653.7622
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-01-29 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-05 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2013-02-04 08:00 | 1d | 97666.6406 | 0 | 0 | 0 | 0 | 97666.6406 | 0 | 100% | Finished | 292999.9219 | 292999.9219 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-07 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 2013-02-19 08:00 | 3d | 13308.2402 | 0 | 0 | 0 | 0 | 13308.2402 | 0 | 100% | Finished | 13308.2402 | 13308.2402 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 6d | [5 empty] | 17643.3604 |  | 100% |  | 38227.2808 | 38227.2808
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-11 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 50 | 100 | 100 | 50 | 100
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-12 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 2013-02-13 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 29405.6006 | 29405.6006 | 100 | 40 | 100 | 100 | 40 | 100
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 11d | [5 empty] | 69233.4404 |  | 100% |  | 80995.6807 | 80995.6807
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 11d | [5 empty] | 57471.2002 |  | 100% |  | 57471.2002 | 57471.2002
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 2013-02-11 08:00 | 2d | 6746.5601 | 0 | 0 | 0 | 0 | 6746.5601 | 0 | 100% | Finished | 6746.5601 | 6746.5601 | 100 | 100 | 100 | 100 | 100 | 100
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-13 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-15 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 2013-02-22 08:00 | 2d | 8872.1602 | 0 | 0 | 0 | 0 | 8872.1602 | 0 | 100% | Finished | 8872.1602 | 8872.1602 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 4d | [5 empty] | 11762.2402 |  | 100% |  | 23524.4805 | 23524.4805
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-19 08:00 | 2d | 5881.1201 | 0 | 0 | 0 | 0 | 5881.1201 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 100 | 100 | 100 | 100 | 100
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-21 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-02-22 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 20 | 100 | 100 | 20 | 100
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 10d | [5 empty] | 29305.76 |  | 10.37% |  | 28133.4721 | 140083.76
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 10d | [5 empty] | 29305.76 |  | 14.44% |  | 28133.4721 | 137143.2
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-02-26 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 2013-03-04 08:00 | 5d | 13822.3999 | 0 | 0 | 0 | 0 | 13822.3999 | 0 | 100% | Finished | 11057.9199 | 11057.9199 | 100 | 125 | 100 | 100 | 125 | 100
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 2013-03-11 08:00 | 1d | 1990.24 | 7960.96 | 4d | 0 | 0 | 1990.24 | 7960.96 | 20% | Started | 3582.432 | 17912.1599 | 100 | 11.1111 | 20 | 100 | 11.1111 | 20
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 |  | 0 | 0 | 94680 | 5d | 0 | 0 | 0 | 94680 | 0% | Not Started | 0 | 94680 | 100 |  | 0 | 100 |  | 0
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 |  | 0 | 0 | 57669.041 | 13d | 0 | 0 | 0 | 57669.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2940.5601
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 |  | 0 | 0 | 14702.8003 | 5d | 0 | 0 | 0 | 14702.8003 | 0% | Not Started | 0 | 2940.5601 | 100 |  | 0 | 100 |  | 0
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 |  | 0 | 0 | 8821.6802 | 3d | 0 | 0 | 0 | 8821.6802 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 |  | 0 | 0 | 52930.0811 | 18d | 0 | 0 | 0 | 52930.0811 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 |  | 0 | 0 | 42922 | 11d | 0 | 0 | 0 | 42922 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 |  | 0 | 0 | 36080 | 10d | 0 | 0 | 0 | 36080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 |  | 0 | 0 | 14432 | 4d | 0 | 0 | 0 | 14432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 |  | 0 | 0 | 14432 | 4d | 0 | 0 | 0 | 14432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 |  | 0 | 0 | 7216 | 2d | 0 | 0 | 0 | 7216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 |  | 0 | 0 | 7216 | 2d | 0 | 0 | 0 | 7216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 |  | 0 | 0 | 61336 | 17d | 0 | 0 | 0 | 61336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.01
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 |  | 0 | 0 | 11050.5601 | 3d | 0 | 0 | 0 | 11050.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 |  | 0 | 0 | 40518.7202 | 11d | 0 | 0 | 0 | 40518.7202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 |  | 0 | 0 | 22101.1201 | 6d | 0 | 0 | 0 | 22101.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 |  | 0 | 0 | 74728.3203 | 8d | 0 | 0 | 0 | 74728.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 |  | 0 | 0 | 46705.2002 | 5d | 0 | 0 | 0 | 46705.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 |  | 0 | 0 | 57306.2402 | 24d | 0 | 0 | 0 | 57306.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 |  | 0 | 0 | 67547.5977 | 5d | 0 | 0 | 0 | 67547.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 |  | 0 | 0 | 4622.8002 | 7d | 0 | 0 | 0 | 4622.8002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 |  | 0 | 0 | 16028.8 | 10d | 0 | 0 | 0 | 16028.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 |  | 0 | 0 | 3641.6 | 10d | 0 | 0 | 0 | 3641.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 |  | 0 | 0 | 17170.4006 | 26d | 0 | 0 | 0 | 17170.4006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 |  | 0 | 0 | 15189.2006 | 23d | 0 | 0 | 0 | 15189.2006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 |  | 0 | 0 | 9906.0004 | 15d | 0 | 0 | 0 | 9906.0004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 |  | 0 | 0 | 1981.2001 | 3d | 0 | 0 | 0 | 1981.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 |  | 0 | 0 | 6604.0002 | 10d | 0 | 0 | 0 | 6604.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 |  | 0 | 0 | 2549.12 | 7d | 0 | 0 | 0 | 2549.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 |  | 0 | 0 | 16714.3201 | 7d | 0 | 0 | 0 | 16714.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 |  | 0 | 0 | 5425.6 | 5d | 0 | 0 | 0 | 5425.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 |  | 0 | 0 | 19102.0801 | 8d | 0 | 0 | 0 | 19102.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 |  | 0 | 0 | 43018.8789 | 2d | 0 | 0 | 0 | 43018.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 |  | 0 | 0 | 1484.8 | 2d | 0 | 0 | 0 | 1484.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 |  | 0 | 0 | 28211.2009 | 38d | 0 | 0 | 0 | 28211.2009 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 |  | 0 | 0 | 94566.083 | 7d | 0 | 0 | 0 | 94566.083 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 |  | 0 | 0 | 4291.2 | 20d | 0 | 0 | 0 | 4291.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-04-24 17:00 |  | TP Name | 24/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 128d | [5 empty] | 611809.5234 |  | 42.74% |  | 959188.0157 | 988580.7058
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 128d | [5 empty] | 611809.5234 |  | 68.43% |  | 959188.0157 | 988580.7058
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 75d | [5 empty] | 92734.6399 |  | 100% |  | 102786.4896 | 102786.4896
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 100% | Finished | 47994.2388 | 47994.2388 | 100 | 60.7143 | 100 | 100 | 60.7143 | 100
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-01-29 08:00 | 9d | 0.72 | 0 | 0 | 15426 | 0 | 15426.72 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 7200 | 100 | 100 | 154267203.448 | 100
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 18d | [5 empty] | 183963.8413 |  | 100% |  | 399881.043 | 399881.043
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 18d | [5 empty] | 166320.481 |  | 100% |  | 361653.7622 | 361653.7622
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-01-29 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-05 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2013-02-04 08:00 | 1d | 97666.6406 | 0 | 0 | 0 | 0 | 97666.6406 | 0 | 100% | Finished | 292999.9219 | 292999.9219 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-07 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 2013-02-19 08:00 | 3d | 13308.2402 | 0 | 0 | 0 | 0 | 13308.2402 | 0 | 100% | Finished | 13308.2402 | 13308.2402 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 6d | [5 empty] | 17643.3604 |  | 100% |  | 38227.2808 | 38227.2808
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-11 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 50 | 100 | 100 | 50 | 100
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-12 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 2013-02-13 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 29405.6006 | 29405.6006 | 100 | 40 | 100 | 100 | 40 | 100
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 11d | [5 empty] | 69233.4404 |  | 100% |  | 80995.6807 | 80995.6807
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 11d | [5 empty] | 57471.2002 |  | 100% |  | 57471.2002 | 57471.2002
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 2013-02-11 08:00 | 2d | 6746.5601 | 0 | 0 | 0 | 0 | 6746.5601 | 0 | 100% | Finished | 6746.5601 | 6746.5601 | 100 | 100 | 100 | 100 | 100 | 100
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-13 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-15 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 2013-02-22 08:00 | 2d | 8872.1602 | 0 | 0 | 0 | 0 | 8872.1602 | 0 | 100% | Finished | 8872.1602 | 8872.1602 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 4d | [5 empty] | 11762.2402 |  | 100% |  | 23524.4805 | 23524.4805
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-19 08:00 | 2d | 5881.1201 | 0 | 0 | 0 | 0 | 5881.1201 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 100 | 100 | 100 | 100 | 100
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-21 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-02-22 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 20 | 100 | 100 | 20 | 100
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 38d | [5 empty] | 191365.6018 |  | 100% |  | 271266.8025 | 271266.8025
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 37d | [5 empty] | 138435.5208 |  | 100% |  | 194812.241 | 194812.241
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-02-26 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 2013-03-04 08:00 | 5d | 13822.3999 | 0 | 0 | 0 | 0 | 13822.3999 | 0 | 100% | Finished | 11057.9199 | 11057.9199 | 100 | 125 | 100 | 100 | 125 | 100
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 2013-03-11 08:00 | 5d | 9951.2 | 0 | 0 | 0 | 0 | 9951.2 | 0 | 100% | Finished | 17912.1599 | 17912.1599 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 | 2013-03-18 08:00 | 3d | 56808 | 0 | 0 | 0 | 0 | 56808 | 0 | 100% | Finished | 94680 | 94680 | 100 | 60 | 100 | 100 | 60 | 100
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 | 2013-04-04 08:00 | 10d | 44360.8008 | 0 | 0 | 0 | 0 | 44360.8008 | 0 | 100% | Finished | 57669.041 | 57669.041 | 100 | 76.9231 | 100 | 100 | 76.9231 | 100
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 21d | [5 empty] | 52930.0811 |  | 100% |  | 76454.5615 | 76454.5615
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-03-21 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 80 | 100 | 100 | 80 | 100
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 | 2013-03-27 08:00 | 3d | 8821.6802 | 0 | 0 | 0 | 0 | 8821.6802 | 0 | 100% | Finished | 8821.6802 | 8821.6802 | 100 | 100 | 100 | 100 | 100 | 100
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 | 2013-04-04 08:00 | 11d | 32346.1606 | 0 | 0 | 0 | 0 | 32346.1606 | 0 | 100% | Finished | 52930.0811 | 52930.0811 | 100 | 61.1111 | 100 | 100 | 61.1111 | 100
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 15d | [5 empty] | 74512 |  | 56.77% |  | 104258 | 107866
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 | 2013-04-04 08:00 | 8d | 31216 | 0 | 0 | 0 | 0 | 31216 | 0 | 100% | Finished | 42922 | 42922 | 100 | 72.7273 | 100 | 100 | 72.7273 | 100
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 | 2013-04-16 08:00 | 5d | 18040 | 0 | 0 | 0 | 0 | 18040 | 0 | 100% | Finished | 36080 | 36080 | 100 | 50 | 100 | 100 | 50 | 100
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-19 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-23 08:00 | 3d | 10824 | 3608 | 1d | 0 | 0 | 10824 | 3608 | 75% | Started | 10824 | 14432 | 100 | 75 | 75 | 100 | 75 | 75
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 |  | 0 | 0 | 7216 | 2d | 0 | 0 | 0 | 7216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 |  | 0 | 0 | 7216 | 2d | 0 | 0 | 0 | 7216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 |  | 0 | 0 | 61336 | 17d | 0 | 0 | 0 | 61336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.02
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 25784.6401
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 |  | 0 | 0 | 11050.5601 | 3d | 0 | 0 | 0 | 11050.5601 | 0% | Not Started | 0 | 11050.5601 | 100 |  | 0 | 100 |  | 0
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 |  | 0 | 0 | 40518.7202 | 11d | 0 | 0 | 0 | 40518.7202 | 0% | Not Started | 0 | 14734.0801 | 100 |  | 0 | 100 |  | 0
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 |  | 0 | 0 | 22101.1201 | 6d | 0 | 0 | 0 | 22101.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.03
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 |  | 0 | 0 | 74728.3203 | 8d | 0 | 0 | 0 | 74728.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 |  | 0 | 0 | 46705.2002 | 5d | 0 | 0 | 0 | 46705.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 |  | 0 | 0 | 57306.2402 | 24d | 0 | 0 | 0 | 57306.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 |  | 0 | 0 | 67547.5977 | 5d | 0 | 0 | 0 | 67547.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 |  | 0 | 0 | 4622.8002 | 7d | 0 | 0 | 0 | 4622.8002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 |  | 0 | 0 | 16028.8 | 10d | 0 | 0 | 0 | 16028.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 |  | 0 | 0 | 3641.6 | 10d | 0 | 0 | 0 | 3641.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 |  | 0 | 0 | 17170.4006 | 26d | 0 | 0 | 0 | 17170.4006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 |  | 0 | 0 | 15189.2006 | 23d | 0 | 0 | 0 | 15189.2006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 |  | 0 | 0 | 9906.0004 | 15d | 0 | 0 | 0 | 9906.0004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 |  | 0 | 0 | 1981.2001 | 3d | 0 | 0 | 0 | 1981.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 |  | 0 | 0 | 6604.0002 | 10d | 0 | 0 | 0 | 6604.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 |  | 0 | 0 | 2549.12 | 7d | 0 | 0 | 0 | 2549.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 |  | 0 | 0 | 16714.3201 | 7d | 0 | 0 | 0 | 16714.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 |  | 0 | 0 | 5425.6 | 5d | 0 | 0 | 0 | 5425.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 |  | 0 | 0 | 19102.0801 | 8d | 0 | 0 | 0 | 19102.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 |  | 0 | 0 | 43018.8789 | 2d | 0 | 0 | 0 | 43018.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 |  | 0 | 0 | 1484.8 | 2d | 0 | 0 | 0 | 1484.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 |  | 0 | 0 | 28211.2009 | 38d | 0 | 0 | 0 | 28211.2009 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 |  | 0 | 0 | 94566.083 | 7d | 0 | 0 | 0 | 94566.083 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 |  | 0 | 0 | 4291.2 | 20d | 0 | 0 | 0 | 4291.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-06-06 17:00 |  | TP Name | 06/06, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 159d | [5 empty] | 795003.712 |  | 48.57% |  | 1090007.566 | 1407361.6074
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 159d | [5 empty] | 784078.9119 |  | 76.98% |  | 1079082.7659 | 1401806.7273
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 75d | [5 empty] | 92734.6399 |  | 100% |  | 102786.4896 | 102786.4896
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 100% | Finished | 47994.2388 | 47994.2388 | 100 | 60.7143 | 100 | 100 | 60.7143 | 100
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-01-29 08:00 | 9d | 0.72 | 0 | 0 | 15426 | 0 | 15426.72 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 7200 | 100 | 100 | 154267203.448 | 100
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 18d | [5 empty] | 183963.8413 |  | 100% |  | 399881.043 | 399881.043
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 18d | [5 empty] | 166320.481 |  | 100% |  | 361653.7622 | 361653.7622
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-01-29 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-05 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2013-02-04 08:00 | 1d | 97666.6406 | 0 | 0 | 0 | 0 | 97666.6406 | 0 | 100% | Finished | 292999.9219 | 292999.9219 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-07 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 2013-02-19 08:00 | 3d | 13308.2402 | 0 | 0 | 0 | 0 | 13308.2402 | 0 | 100% | Finished | 13308.2402 | 13308.2402 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 6d | [5 empty] | 17643.3604 |  | 100% |  | 38227.2808 | 38227.2808
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-11 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 50 | 100 | 100 | 50 | 100
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-12 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 2013-02-13 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 29405.6006 | 29405.6006 | 100 | 40 | 100 | 100 | 40 | 100
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 11d | [5 empty] | 69233.4404 |  | 100% |  | 80995.6807 | 80995.6807
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 11d | [5 empty] | 57471.2002 |  | 100% |  | 57471.2002 | 57471.2002
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 2013-02-11 08:00 | 2d | 6746.5601 | 0 | 0 | 0 | 0 | 6746.5601 | 0 | 100% | Finished | 6746.5601 | 6746.5601 | 100 | 100 | 100 | 100 | 100 | 100
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-13 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-15 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 2013-02-22 08:00 | 2d | 8872.1602 | 0 | 0 | 0 | 0 | 8872.1602 | 0 | 100% | Finished | 8872.1602 | 8872.1602 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 4d | [5 empty] | 11762.2402 |  | 100% |  | 23524.4805 | 23524.4805
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-19 08:00 | 2d | 5881.1201 | 0 | 0 | 0 | 0 | 5881.1201 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 100 | 100 | 100 | 100 | 100
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-21 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-02-22 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 20 | 100 | 100 | 20 | 100
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 38d | [5 empty] | 191365.6018 |  | 100% |  | 271266.8025 | 271266.8025
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 37d | [5 empty] | 138435.5208 |  | 100% |  | 194812.241 | 194812.241
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-02-26 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 2013-03-04 08:00 | 5d | 13822.3999 | 0 | 0 | 0 | 0 | 13822.3999 | 0 | 100% | Finished | 11057.9199 | 11057.9199 | 100 | 125 | 100 | 100 | 125 | 100
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 2013-03-11 08:00 | 5d | 9951.2 | 0 | 0 | 0 | 0 | 9951.2 | 0 | 100% | Finished | 17912.1599 | 17912.1599 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 | 2013-03-18 08:00 | 3d | 56808 | 0 | 0 | 0 | 0 | 56808 | 0 | 100% | Finished | 94680 | 94680 | 100 | 60 | 100 | 100 | 60 | 100
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 | 2013-04-04 08:00 | 10d | 44360.8008 | 0 | 0 | 0 | 0 | 44360.8008 | 0 | 100% | Finished | 57669.041 | 57669.041 | 100 | 76.9231 | 100 | 100 | 76.9231 | 100
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 21d | [5 empty] | 52930.0811 |  | 100% |  | 76454.5615 | 76454.5615
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-03-21 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 80 | 100 | 100 | 80 | 100
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 | 2013-03-27 08:00 | 3d | 8821.6802 | 0 | 0 | 0 | 0 | 8821.6802 | 0 | 100% | Finished | 8821.6802 | 8821.6802 | 100 | 100 | 100 | 100 | 100 | 100
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 | 2013-04-04 08:00 | 11d | 32346.1606 | 0 | 0 | 0 | 0 | 32346.1606 | 0 | 100% | Finished | 52930.0811 | 52930.0811 | 100 | 61.1111 | 100 | 100 | 61.1111 | 100
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 46d | [5 empty] | 164712 |  | 100% |  | 183634 | 183634.01
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 | 2013-04-04 08:00 | 8d | 31216 | 0 | 0 | 0 | 0 | 31216 | 0 | 100% | Finished | 42922 | 42922 | 100 | 72.7273 | 100 | 100 | 72.7273 | 100
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 | 2013-04-16 08:00 | 5d | 18040 | 0 | 0 | 0 | 0 | 18040 | 0 | 100% | Finished | 36080 | 36080 | 100 | 50 | 100 | 100 | 50 | 100
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-19 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-23 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-04-29 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-05-02 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 | 2013-05-06 08:00 | 20d | 72160 | 0 | 0 | 0 | 0 | 72160 | 0 | 100% | Finished | 61336 | 61336 | 100 | 117.6471 | 100 | 100 | 117.6471 | 100
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 9d | [5 empty] | 11288.5901 |  | 100% |  | 0.02 | 0.02
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-21 08:00 | 4d | 0.32 | 0 | 0 | 5016.8301 | 0 | 5017.1501 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 50171501.9026 | 100
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-27 08:00 | 5d | 0.4 | 0 | 0 | 6271.04 | 0 | 6271.44 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4000 | 100 | 100 | 62714401.7923 | 100
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 4d | [5 empty] | 14734.0801 |  | 55% |  | 40518.7202 | 73670.4004
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 |  | 0 | 0 | 11050.5601 | 3d | 0 | 0 | 0 | 11050.5601 | 0% | Not Started | 0 | 11050.5601 | 100 |  | 0 | 100 |  | 0
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 | 2013-06-03 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 40518.7202 | 40518.7202 | 100 | 36.3636 | 100 | 100 | 36.3636 | 100
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 |  | 0 | 0 | 22101.1201 | 6d | 0 | 0 | 0 | 22101.1201 | 0% | Not Started | 0 | 22101.1201 | 100 |  | 0 | 100 |  | 0
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.03
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0.01 | 1h | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 24d | [5 empty] | 56046.7183 |  | 1.784e-05% |  | 0.01 | 56046.2502
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-06 08:00 | 6d | 0.48 | 0 | 0 | 56046.2383 | 0 | 56046.7183 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4800 | 100 | 100 | 560467195.3398 | 100
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 56046.2402 | 100 |  | 0 | 100 |  | 0
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 233526.001
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 |  | 0 | 0 | 74728.3203 | 8d | 0 | 0 | 0 | 74728.3203 | 0% | Not Started | 0 | 74728.3203 | 100 |  | 0 | 100 |  | 0
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 56046.2402 | 100 |  | 0 | 100 |  | 0
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 56046.2402 | 100 |  | 0 | 100 |  | 0
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 |  | 0 | 0 | 46705.2002 | 5d | 0 | 0 | 0 | 46705.2002 | 0% | Not Started | 0 | 46705.2002 | 100 |  | 0 | 100 |  | 0
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 24d | [5 empty] | 10924.8001 |  | 1.297% |  | 10924.8001 | 5554.8801
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 24d | [5 empty] | 10924.8001 |  | 6.52% |  | 10924.8001 | 2913.28
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 |  | 0 | 0 | 57306.2402 | 24d | 0 | 0 | 0 | 57306.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 |  | 0 | 0 | 2184.96 | 6d | 0 | 0 | 0 | 2184.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 |  | 0 | 0 | 67547.5977 | 5d | 0 | 0 | 0 | 67547.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2641.6001
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 |  | 0 | 0 | 4622.8002 | 7d | 0 | 0 | 0 | 4622.8002 | 0% | Not Started | 0 | 2641.6001 | 100 |  | 0 | 100 |  | 0
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 |  | 0 | 0 | 16028.8 | 10d | 0 | 0 | 0 | 16028.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 |  | 0 | 0 | 3641.6 | 10d | 0 | 0 | 0 | 3641.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 |  | 0 | 0 | 17170.4006 | 26d | 0 | 0 | 0 | 17170.4006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 |  | 0 | 0 | 15189.2006 | 23d | 0 | 0 | 0 | 15189.2006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 |  | 0 | 0 | 9906.0004 | 15d | 0 | 0 | 0 | 9906.0004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 |  | 0 | 0 | 1981.2001 | 3d | 0 | 0 | 0 | 1981.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 |  | 0 | 0 | 6604.0002 | 10d | 0 | 0 | 0 | 6604.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 |  | 0 | 0 | 12017.2801 | 33d | 0 | 0 | 0 | 12017.2801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 |  | 0 | 0 | 2549.12 | 7d | 0 | 0 | 0 | 2549.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 |  | 0 | 0 | 16714.3201 | 7d | 0 | 0 | 0 | 16714.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 |  | 0 | 0 | 5425.6 | 5d | 0 | 0 | 0 | 5425.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 |  | 0 | 0 | 11288.9601 | 31d | 0 | 0 | 0 | 11288.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 |  | 0 | 0 | 19102.0801 | 8d | 0 | 0 | 0 | 19102.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 |  | 0 | 0 | 43018.8789 | 2d | 0 | 0 | 0 | 43018.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 |  | 0 | 0 | 1484.8 | 2d | 0 | 0 | 0 | 1484.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 |  | 0 | 0 | 28211.2009 | 38d | 0 | 0 | 0 | 28211.2009 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 |  | 0 | 0 | 94566.083 | 7d | 0 | 0 | 0 | 94566.083 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 |  | 0 | 0 | 4291.2 | 20d | 0 | 0 | 0 | 4291.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-07-19 17:00 |  | TP Name | 19/07, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 190d | [5 empty] | 1221194.3513 |  | 65.06% |  | 1460018.3371 | 1550527.8499
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 190d | [5 empty] | 1051447.7116 |  | 92.67% |  | 1299055.2868 | 1401806.7273
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 75d | [5 empty] | 92734.6399 |  | 100% |  | 102786.4896 | 102786.4896
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 100% | Finished | 47994.2388 | 47994.2388 | 100 | 60.7143 | 100 | 100 | 60.7143 | 100
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-01-29 08:00 | 9d | 0.72 | 0 | 0 | 15426 | 0 | 15426.72 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 7200 | 100 | 100 | 154267203.448 | 100
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 18d | [5 empty] | 183963.8413 |  | 100% |  | 399881.043 | 399881.043
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 18d | [5 empty] | 166320.481 |  | 100% |  | 361653.7622 | 361653.7622
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-01-29 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-05 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2013-02-04 08:00 | 1d | 97666.6406 | 0 | 0 | 0 | 0 | 97666.6406 | 0 | 100% | Finished | 292999.9219 | 292999.9219 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-07 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 2013-02-19 08:00 | 3d | 13308.2402 | 0 | 0 | 0 | 0 | 13308.2402 | 0 | 100% | Finished | 13308.2402 | 13308.2402 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 6d | [5 empty] | 17643.3604 |  | 100% |  | 38227.2808 | 38227.2808
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-11 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 50 | 100 | 100 | 50 | 100
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-12 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 2013-02-13 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 29405.6006 | 29405.6006 | 100 | 40 | 100 | 100 | 40 | 100
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 11d | [5 empty] | 69233.4404 |  | 100% |  | 80995.6807 | 80995.6807
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 11d | [5 empty] | 57471.2002 |  | 100% |  | 57471.2002 | 57471.2002
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 2013-02-11 08:00 | 2d | 6746.5601 | 0 | 0 | 0 | 0 | 6746.5601 | 0 | 100% | Finished | 6746.5601 | 6746.5601 | 100 | 100 | 100 | 100 | 100 | 100
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-13 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-15 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 2013-02-22 08:00 | 2d | 8872.1602 | 0 | 0 | 0 | 0 | 8872.1602 | 0 | 100% | Finished | 8872.1602 | 8872.1602 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 4d | [5 empty] | 11762.2402 |  | 100% |  | 23524.4805 | 23524.4805
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-19 08:00 | 2d | 5881.1201 | 0 | 0 | 0 | 0 | 5881.1201 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 100 | 100 | 100 | 100 | 100
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-21 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-02-22 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 20 | 100 | 100 | 20 | 100
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 38d | [5 empty] | 191365.6018 |  | 100% |  | 271266.8025 | 271266.8025
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 37d | [5 empty] | 138435.5208 |  | 100% |  | 194812.241 | 194812.241
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-02-26 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 2013-03-04 08:00 | 5d | 13822.3999 | 0 | 0 | 0 | 0 | 13822.3999 | 0 | 100% | Finished | 11057.9199 | 11057.9199 | 100 | 125 | 100 | 100 | 125 | 100
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 2013-03-11 08:00 | 5d | 9951.2 | 0 | 0 | 0 | 0 | 9951.2 | 0 | 100% | Finished | 17912.1599 | 17912.1599 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 | 2013-03-18 08:00 | 3d | 56808 | 0 | 0 | 0 | 0 | 56808 | 0 | 100% | Finished | 94680 | 94680 | 100 | 60 | 100 | 100 | 60 | 100
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 | 2013-04-04 08:00 | 10d | 44360.8008 | 0 | 0 | 0 | 0 | 44360.8008 | 0 | 100% | Finished | 57669.041 | 57669.041 | 100 | 76.9231 | 100 | 100 | 76.9231 | 100
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 21d | [5 empty] | 52930.0811 |  | 100% |  | 76454.5615 | 76454.5615
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-03-21 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 80 | 100 | 100 | 80 | 100
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 | 2013-03-27 08:00 | 3d | 8821.6802 | 0 | 0 | 0 | 0 | 8821.6802 | 0 | 100% | Finished | 8821.6802 | 8821.6802 | 100 | 100 | 100 | 100 | 100 | 100
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 | 2013-04-04 08:00 | 11d | 32346.1606 | 0 | 0 | 0 | 0 | 32346.1606 | 0 | 100% | Finished | 52930.0811 | 52930.0811 | 100 | 61.1111 | 100 | 100 | 61.1111 | 100
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 55d | [5 empty] | 175536.24 |  | 100% |  | 183634.01 | 183634.01
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 | 2013-04-04 08:00 | 8d | 31216 | 0 | 0 | 0 | 0 | 31216 | 0 | 100% | Finished | 42922 | 42922 | 100 | 72.7273 | 100 | 100 | 72.7273 | 100
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 | 2013-04-16 08:00 | 5d | 18040 | 0 | 0 | 0 | 0 | 18040 | 0 | 100% | Finished | 36080 | 36080 | 100 | 50 | 100 | 100 | 50 | 100
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-19 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-23 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-04-29 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-05-02 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-17 08:00 | 3d | 0.24 | 0 | 0 | 10824 | 0 | 10824.24 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 2400 | 100 | 100 | 108242402.4194 | 100
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 | 2013-05-06 08:00 | 20d | 72160 | 0 | 0 | 0 | 0 | 72160 | 0 | 100% | Finished | 61336 | 61336 | 100 | 117.6471 | 100 | 100 | 117.6471 | 100
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 9d | [5 empty] | 11288.5901 |  | 100% |  | 0.02 | 0.02
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-21 08:00 | 4d | 0.32 | 0 | 0 | 5016.8301 | 0 | 5017.1501 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 50171501.9026 | 100
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-27 08:00 | 5d | 0.4 | 0 | 0 | 6271.04 | 0 | 6271.44 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4000 | 100 | 100 | 62714401.7923 | 100
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 8d | [5 empty] | 40518.7202 |  | 100% |  | 73670.4004 | 73670.4004
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 | 2013-06-07 08:00 | 3d | 11050.5601 | 0 | 0 | 0 | 0 | 11050.5601 | 0 | 100% | Finished | 11050.5601 | 11050.5601 | 100 | 100 | 100 | 100 | 100 | 100
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 | 2013-06-03 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 40518.7202 | 40518.7202 | 100 | 36.3636 | 100 | 100 | 36.3636 | 100
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 | 2013-06-07 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 22101.1201 | 22101.1201 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 14d | [5 empty] | 62621.1989 |  | 100% |  | 0.03 | 0.03
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 3d | 0.24 | 0 | 0 | 11050.5596 | 0 | 11050.7996 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 2400 | 100 | 100 | 110507998.1731 | 100
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 10d | 0.8 | 0 | 0 | 36835.1992 | 0 | 36835.9992 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 8000 | 100 | 100 | 368360000.4208 | 100
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-21 08:00 | 4d | 0.32 | 0 | 0 | 14734.0801 | 0 | 14734.4001 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 147344004.0746 | 100
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 39d | [5 empty] | 93410.8784 |  | 100% |  | 56046.2502 | 56046.2502
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-06 08:00 | 6d | 0.48 | 0 | 0 | 56046.2383 | 0 | 56046.7183 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4800 | 100 | 100 | 560467195.3398 | 100
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-24 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 30d | [5 empty] | 130774.5605 |  | 56% |  | 130774.5605 | 233526.001
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 | 2013-06-10 08:00 | 10d | 93410.4004 | 0 | 0 | 0 | 0 | 93410.4004 | 0 | 100% | Finished | 74728.3203 | 74728.3203 | 100 | 125 | 100 | 100 | 125 | 100
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-10 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 |  | 0 | 0 | 56046.2402 | 6d | 0 | 0 | 0 | 56046.2402 | 0% | Not Started | 0 | 56046.2402 | 100 |  | 0 | 100 |  | 0
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 |  | 0 | 0 | 46705.2002 | 5d | 0 | 0 | 0 | 46705.2002 | 0% | Not Started | 0 | 46705.2002 | 100 |  | 0 | 100 |  | 0
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 55d | [5 empty] | 169746.6397 |  | 19.11% |  | 160963.0502 | 148721.1226
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 55d | [5 empty] | 93614.1582 |  | 52.87% |  | 88591.6708 | 47673.1203
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-06-07 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-06-12 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 |  | 0 | 0 | 57306.2402 | 24d | 0 | 0 | 0 | 57306.2402 | 0% | Not Started | 0 | 33428.6401 | 100 |  | 0 | 100 |  | 0
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 2184.96 | 0 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 2184.96 | 0 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 | 2013-06-27 08:00 | 5d | 67547.5977 | 0 | 0 | 0 | 0 | 67547.5977 | 0 | 100% | Finished | 67547.5977 | 0 | 100 | 100 | 100 | 100 | 100 | 100
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-07-04 08:00 | 12d | 8908.8003 | 7424.0002 | 10d | 0 | 0 | 8908.8003 | 7424.0002 | 54.55% | Started | 2429.6729 | 0 | 100 | 200 | 54.5455 | 100 | 200 | 54.5455
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 14d | [5 empty] | 22312.0002 |  | 100% |  | 24293.2003 | 24293.2003
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 | 2013-06-10 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 4622.8002 | 4622.8002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 | 2013-06-14 08:00 | 10d | 16028.8 | 0 | 0 | 0 | 0 | 16028.8 | 0 | 100% | Finished | 16028.8 | 16028.8 | 100 | 100 | 100 | 100 | 100 | 100
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 | 2013-06-14 08:00 | 10d | 3641.6 | 0 | 0 | 0 | 0 | 3641.6 | 0 | 100% | Finished | 3641.6 | 3641.6 | 100 | 100 | 100 | 100 | 100 | 100
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 26d | [5 empty] | 7264.4003 |  | 25.58% |  | 7264.4003 | 17170.4006
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-14 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-20 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-06-26 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 100 | 100 | 100 | 100 | 100
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 1320.8 | 100 |  | 0 | 100 |  | 0
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 1320.8 | 100 |  | 0 | 100 |  | 0
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 |  | 0 | 0 | 17170.4006 | 26d | 0 | 0 | 0 | 17170.4006 | 0% | Not Started | 0 | 7264.4003 | 100 |  | 0 | 100 |  | 0
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 20d | [5 empty] | 12547.6005 |  | 31.36% |  | 6006.4955 | 7264.4003
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-24 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-28 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-07-03 08:00 | 13d | 8585.2003 | 5283.2002 | 8d | 0 | 0 | 8585.2003 | 5283.2002 | 61.9% | Started | 2044.0954 | 3302.0001 | 100 | 260 | 61.9048 | 100 | 260 | 61.9048
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 14d | [5 empty] | 9245.6003 |  | 23.73% |  | 9245.5999 | 10566.4004
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 | 2013-07-02 08:00 | 14d | 9245.6003 | 5943.6002 | 9d | 0 | 0 | 9245.6003 | 5943.6002 | 60.87% | Started | 9245.5999 | 10566.4004 | 100 | 60.8696 | 60.8696 | 100 | 60.8696 | 60.8696
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 |  | 0 | 0 | 7924.8003 | 12d | 0 | 0 | 0 | 7924.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 |  | 0 | 0 | 9906.0004 | 15d | 0 | 0 | 0 | 9906.0004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 |  | 0 | 0 | 1981.2001 | 3d | 0 | 0 | 0 | 1981.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 |  | 0 | 0 | 2641.6001 | 4d | 0 | 0 | 0 | 2641.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 |  | 0 | 0 | 3302.0001 | 5d | 0 | 0 | 0 | 3302.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 |  | 0 | 0 | 6604.0002 | 10d | 0 | 0 | 0 | 6604.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 17d | [5 empty] | 12381.4401 |  | 8.371% |  | 13180.243 | 14566.4001
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 17d | 6190.7201 | 5098.2401 | 14d | 0 | 0 | 6190.7201 | 5098.2401 | 54.84% | Started | 6590.1215 | 7283.2001 | 100 | 51.5152 | 54.8387 | 100 | 51.5152 | 54.8387
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 17d | 6190.7201 | 5098.2401 | 14d | 0 | 0 | 6190.7201 | 5098.2401 | 54.84% | Started | 6590.1215 | 7283.2001 | 100 | 51.5152 | 54.8387 | 100 | 51.5152 | 54.8387
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 |  | 0 | 0 | 2549.12 | 7d | 0 | 0 | 0 | 2549.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 |  | 0 | 0 | 16714.3201 | 7d | 0 | 0 | 0 | 16714.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 |  | 0 | 0 | 5425.6 | 5d | 0 | 0 | 0 | 5425.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 17d | [5 empty] | 12381.4401 |  | 8.579% |  | 12381.4404 | 14566.4001
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 17d | 6190.7201 | 5098.2401 | 14d | 0 | 0 | 6190.7201 | 5098.2401 | 54.84% | Started | 6190.7202 | 7283.2001 | 100 | 54.8387 | 54.8387 | 100 | 54.8387 | 54.8387
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 17d | 6190.7201 | 5098.2401 | 14d | 0 | 0 | 6190.7201 | 5098.2401 | 54.84% | Started | 6190.7202 | 7283.2001 | 100 | 54.8387 | 54.8387 | 100 | 54.8387 | 54.8387
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 |  | 0 | 0 | 23877.6001 | 10d | 0 | 0 | 0 | 23877.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 |  | 0 | 0 | 6190.7201 | 17d | 0 | 0 | 0 | 6190.7201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 |  | 0 | 0 | 2227.2001 | 3d | 0 | 0 | 0 | 2227.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 |  | 0 | 0 | 19102.0801 | 8d | 0 | 0 | 0 | 19102.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 |  | 0 | 0 | 43018.8789 | 2d | 0 | 0 | 0 | 43018.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 |  | 0 | 0 | 1484.8 | 2d | 0 | 0 | 0 | 1484.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 12620.8004
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 |  | 0 | 0 | 28211.2009 | 38d | 0 | 0 | 0 | 28211.2009 | 0% | Not Started | 0 | 12620.8004 | 100 |  | 0 | 100 |  | 0
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 |  | 0 | 0 | 94566.083 | 7d | 0 | 0 | 0 | 94566.083 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 |  | 0 | 0 | 4291.2 | 20d | 0 | 0 | 0 | 4291.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-09-03 17:00 |  | TP Name | 03/09, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 222d | [5 empty] | 1519412.2766 |  | 83.86% |  | 1881917.3728 | 1839603.0514
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 206d | [5 empty] | 1107493.9518 |  | 100% |  | 1401806.7273 | 1401806.7273
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 75d | [5 empty] | 92734.6399 |  | 100% |  | 102786.4896 | 102786.4896
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 100% | Finished | 47994.2388 | 47994.2388 | 100 | 60.7143 | 100 | 100 | 60.7143 | 100
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-01-29 08:00 | 9d | 0.72 | 0 | 0 | 15426 | 0 | 15426.72 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 7200 | 100 | 100 | 154267203.448 | 100
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 18d | [5 empty] | 183963.8413 |  | 100% |  | 399881.043 | 399881.043
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 18d | [5 empty] | 166320.481 |  | 100% |  | 361653.7622 | 361653.7622
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-01-29 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-05 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2013-02-04 08:00 | 1d | 97666.6406 | 0 | 0 | 0 | 0 | 97666.6406 | 0 | 100% | Finished | 292999.9219 | 292999.9219 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-07 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 2013-02-19 08:00 | 3d | 13308.2402 | 0 | 0 | 0 | 0 | 13308.2402 | 0 | 100% | Finished | 13308.2402 | 13308.2402 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 6d | [5 empty] | 17643.3604 |  | 100% |  | 38227.2808 | 38227.2808
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-11 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 50 | 100 | 100 | 50 | 100
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-12 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 2013-02-13 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 29405.6006 | 29405.6006 | 100 | 40 | 100 | 100 | 40 | 100
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 11d | [5 empty] | 69233.4404 |  | 100% |  | 80995.6807 | 80995.6807
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 11d | [5 empty] | 57471.2002 |  | 100% |  | 57471.2002 | 57471.2002
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 2013-02-11 08:00 | 2d | 6746.5601 | 0 | 0 | 0 | 0 | 6746.5601 | 0 | 100% | Finished | 6746.5601 | 6746.5601 | 100 | 100 | 100 | 100 | 100 | 100
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-13 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-15 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 2013-02-22 08:00 | 2d | 8872.1602 | 0 | 0 | 0 | 0 | 8872.1602 | 0 | 100% | Finished | 8872.1602 | 8872.1602 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 4d | [5 empty] | 11762.2402 |  | 100% |  | 23524.4805 | 23524.4805
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-19 08:00 | 2d | 5881.1201 | 0 | 0 | 0 | 0 | 5881.1201 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 100 | 100 | 100 | 100 | 100
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-21 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-02-22 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 20 | 100 | 100 | 20 | 100
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 38d | [5 empty] | 191365.6018 |  | 100% |  | 271266.8025 | 271266.8025
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 37d | [5 empty] | 138435.5208 |  | 100% |  | 194812.241 | 194812.241
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-02-26 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 2013-03-04 08:00 | 5d | 13822.3999 | 0 | 0 | 0 | 0 | 13822.3999 | 0 | 100% | Finished | 11057.9199 | 11057.9199 | 100 | 125 | 100 | 100 | 125 | 100
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 2013-03-11 08:00 | 5d | 9951.2 | 0 | 0 | 0 | 0 | 9951.2 | 0 | 100% | Finished | 17912.1599 | 17912.1599 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 | 2013-03-18 08:00 | 3d | 56808 | 0 | 0 | 0 | 0 | 56808 | 0 | 100% | Finished | 94680 | 94680 | 100 | 60 | 100 | 100 | 60 | 100
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 | 2013-04-04 08:00 | 10d | 44360.8008 | 0 | 0 | 0 | 0 | 44360.8008 | 0 | 100% | Finished | 57669.041 | 57669.041 | 100 | 76.9231 | 100 | 100 | 76.9231 | 100
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 21d | [5 empty] | 52930.0811 |  | 100% |  | 76454.5615 | 76454.5615
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-03-21 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 80 | 100 | 100 | 80 | 100
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 | 2013-03-27 08:00 | 3d | 8821.6802 | 0 | 0 | 0 | 0 | 8821.6802 | 0 | 100% | Finished | 8821.6802 | 8821.6802 | 100 | 100 | 100 | 100 | 100 | 100
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 | 2013-04-04 08:00 | 11d | 32346.1606 | 0 | 0 | 0 | 0 | 32346.1606 | 0 | 100% | Finished | 52930.0811 | 52930.0811 | 100 | 61.1111 | 100 | 100 | 61.1111 | 100
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 55d | [5 empty] | 175536.24 |  | 100% |  | 183634.01 | 183634.01
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 | 2013-04-04 08:00 | 8d | 31216 | 0 | 0 | 0 | 0 | 31216 | 0 | 100% | Finished | 42922 | 42922 | 100 | 72.7273 | 100 | 100 | 72.7273 | 100
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 | 2013-04-16 08:00 | 5d | 18040 | 0 | 0 | 0 | 0 | 18040 | 0 | 100% | Finished | 36080 | 36080 | 100 | 50 | 100 | 100 | 50 | 100
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-19 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-23 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-04-29 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-05-02 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-17 08:00 | 3d | 0.24 | 0 | 0 | 10824 | 0 | 10824.24 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 2400 | 100 | 100 | 108242402.4194 | 100
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 | 2013-05-06 08:00 | 20d | 72160 | 0 | 0 | 0 | 0 | 72160 | 0 | 100% | Finished | 61336 | 61336 | 100 | 117.6471 | 100 | 100 | 117.6471 | 100
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 9d | [5 empty] | 11288.5901 |  | 100% |  | 0.02 | 0.02
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-21 08:00 | 4d | 0.32 | 0 | 0 | 5016.8301 | 0 | 5017.1501 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 50171501.9026 | 100
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-27 08:00 | 5d | 0.4 | 0 | 0 | 6271.04 | 0 | 6271.44 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4000 | 100 | 100 | 62714401.7923 | 100
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 8d | [5 empty] | 40518.7202 |  | 100% |  | 73670.4004 | 73670.4004
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 | 2013-06-07 08:00 | 3d | 11050.5601 | 0 | 0 | 0 | 0 | 11050.5601 | 0 | 100% | Finished | 11050.5601 | 11050.5601 | 100 | 100 | 100 | 100 | 100 | 100
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 | 2013-06-03 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 40518.7202 | 40518.7202 | 100 | 36.3636 | 100 | 100 | 36.3636 | 100
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 | 2013-06-07 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 22101.1201 | 22101.1201 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 14d | [5 empty] | 62621.1989 |  | 100% |  | 0.03 | 0.03
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 3d | 0.24 | 0 | 0 | 11050.5596 | 0 | 11050.7996 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 2400 | 100 | 100 | 110507998.1731 | 100
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 10d | 0.8 | 0 | 0 | 36835.1992 | 0 | 36835.9992 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 8000 | 100 | 100 | 368360000.4208 | 100
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-21 08:00 | 4d | 0.32 | 0 | 0 | 14734.0801 | 0 | 14734.4001 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 147344004.0746 | 100
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 39d | [5 empty] | 93410.8784 |  | 100% |  | 56046.2502 | 56046.2502
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-06 08:00 | 6d | 0.48 | 0 | 0 | 56046.2383 | 0 | 56046.7183 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4800 | 100 | 100 | 560467195.3398 | 100
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-24 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 46d | [5 empty] | 186820.8008 |  | 100% |  | 233526.001 | 233526.001
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 | 2013-06-10 08:00 | 10d | 93410.4004 | 0 | 0 | 0 | 0 | 93410.4004 | 0 | 100% | Finished | 74728.3203 | 74728.3203 | 100 | 125 | 100 | 100 | 125 | 100
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-10 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-08-05 08:00 | 2d | 18682.0801 | 0 | 0 | 0 | 0 | 18682.0801 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 | 2013-08-07 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 46705.2002 | 46705.2002 | 100 | 80 | 100 | 100 | 80 | 100
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 87d | [5 empty] | 411918.3248 |  | 57% |  | 480110.6455 | 437796.3241
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 87d | [5 empty] | 133535.6786 |  | 96.27% |  | 161318.0783 | 159861.4383
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-06-07 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-06-12 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 | 2013-08-09 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 100% | Finished | 57306.2402 | 57306.2402 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-08-23 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 100% | Finished | 11938.8 | 11938.8 | 100 | 100 | 100 | 100 | 100 | 100
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 2184.96 | 2184.96 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 2184.96 | 2184.96 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 | 2013-06-27 08:00 | 5d | 67547.5977 | 0 | 0 | 0 | 0 | 67547.5977 | 0 | 100% | Finished | 67547.5977 | 67547.5977 | 100 | 100 | 100 | 100 | 100 | 100
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-07-04 08:00 | 22d | 16332.8005 | 0 | 0 | 0 | 0 | 16332.8005 | 0 | 100% | Finished | 4454.4001 | 4454.4001 | 100 | 366.6667 | 100 | 100 | 366.6667 | 100
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-05 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 0 | 100 | 100 | 100 | 100 | 100 | 100
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 14d | [5 empty] | 22312.0002 |  | 100% |  | 24293.2003 | 24293.2003
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 | 2013-06-10 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 4622.8002 | 4622.8002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 | 2013-06-14 08:00 | 10d | 16028.8 | 0 | 0 | 0 | 0 | 16028.8 | 0 | 100% | Finished | 16028.8 | 16028.8 | 100 | 100 | 100 | 100 | 100 | 100
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 | 2013-06-14 08:00 | 10d | 3641.6 | 0 | 0 | 0 | 0 | 3641.6 | 0 | 100% | Finished | 3641.6 | 3641.6 | 100 | 100 | 100 | 100 | 100 | 100
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 54d | [5 empty] | 17830.8007 |  | 100% |  | 28397.201 | 28397.201
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-14 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-20 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-06-26 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 100 | 100 | 100 | 100 | 100
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-05 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-07 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 | 2013-08-09 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 17170.4006 | 17170.4006 | 100 | 38.4615 | 100 | 100 | 38.4615 | 100
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-27 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 46d | [5 empty] | 28397.201 |  | 100% |  | 19151.6007 | 19151.6007
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-24 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-28 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-07-03 08:00 | 21d | 13868.4005 | 0 | 0 | 0 | 0 | 13868.4005 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 420 | 100 | 100 | 420 | 100
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-01 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-05 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 2013-08-07 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 7924.8003 | 7924.8003 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-23 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 46d | [5 empty] | 29057.6011 |  | 77.97% |  | 30378.4012 | 31699.2012
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 | 2013-07-02 08:00 | 23d | 15189.2006 | 0 | 0 | 0 | 0 | 15189.2006 | 0 | 100% | Finished | 15189.2006 | 15189.2006 | 100 | 100 | 100 | 100 | 100 | 100
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-08-02 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 2013-08-08 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 7924.8003 | 7924.8003 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-26 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 | 2013-08-28 08:00 | 5d | 3302.0001 | 6604.0002 | 10d | 0 | 0 | 3302.0001 | 6604.0002 | 33.33% | Started | 3302.0002 | 4622.8002 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 |  | 0 | 0 | 1981.2001 | 3d | 0 | 0 | 0 | 1981.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 23d | [5 empty] | 13868.4005 |  | 77.78% |  | 13868.4007 | 15189.2006
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-08-02 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-08 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-08-12 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 100 | 100 | 100 | 100 | 100
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-21 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-23 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 | 2013-08-27 08:00 | 6d | 3962.4001 | 2641.6001 | 4d | 0 | 0 | 3962.4001 | 2641.6001 | 60% | Started | 3962.4003 | 5283.2002 | 100 | 60 | 60 | 100 | 60 | 60
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 |  | 0 | 0 | 1320.8 | 2d | 0 | 0 | 0 | 1320.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 49d | [5 empty] | 89897.9217 |  | 67.38% |  | 106089.6816 | 50300.7204
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 12017.2801 | 12017.2801 | 100 | 93.9394 | 100 | 100 | 93.9394 | 100
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 12017.2801 | 12017.2801 | 100 | 93.9394 | 100 | 100 | 93.9394 | 100
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-08-09 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 | 2013-08-14 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 2549.12 | 2549.12 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 2013-08-19 08:00 | 4d | 9551.04 | 0 | 0 | 0 | 0 | 9551.04 | 0 | 100% | Finished | 23877.6001 | 21489.8401 | 100 | 40 | 100 | 100 | 40 | 100
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 | 2013-08-19 08:00 | 4d | 9551.04 | 0 | 0 | 0 | 0 | 9551.04 | 0 | 100% | Finished | 16714.3201 | 0 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-23 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 1456.64 | 0 | 100 | 125 | 100 | 100 | 125 | 100
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-23 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 1456.64 | 0 | 100 | 125 | 100 | 100 | 125 | 100
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 2013-08-30 08:00 | 3d | 40528.3213 | 40528.3213 | 3d | 0 | 0 | 40528.3213 | 40528.3213 | 50% | Started | 33773.6011 | 0 | 100 | 60 | 50 | 100 | 60 | 50
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 |  | 0 | 0 | 5425.6 | 5d | 0 | 0 | 0 | 5425.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 49d | [5 empty] | 49775.2004 |  | 37.8% |  | 54550.7205 | 61714.0005
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 11288.9601 | 11288.9601 | 100 | 100 | 100 | 100 | 100 | 100
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 11288.9601 | 11288.9601 | 100 | 100 | 100 | 100 | 100 | 100
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-08-09 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-08-14 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 2013-08-21 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 100% | Finished | 23877.6001 | 23877.6001 | 100 | 80 | 100 | 100 | 80 | 100
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-09-02 08:00 | 2d | 4775.52 | 7163.28 | 3d | 0 | 0 | 4775.52 | 7163.28 | 40% | Started | 4775.5201 | 11938.8 | 100 | 40 | 40 | 100 | 40 | 40
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 |  | 0 | 0 | 67547.2021 | 5d | 0 | 0 | 0 | 67547.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 18d | [5 empty] | 11667.2001 |  | 12.88% |  | 13123.8402 | 14972.8002
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 2013-08-09 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 6190.7201 | 6190.7201 | 100 | 88.2353 | 100 | 100 | 88.2353 | 100
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 2013-08-09 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 6190.7201 | 6190.7201 | 100 | 88.2353 | 100 | 100 | 88.2353 | 100
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-09-03 08:00 | 1d | 742.4 | 1484.8 | 2d | 0 | 0 | 742.4 | 1484.8 | 33.33% | Started | 742.4 | 2227.2001 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 |  | 0 | 0 | 1092.48 | 3d | 0 | 0 | 0 | 1092.48 | 0% | Not Started | 0 | 364.16 | 100 |  | 0 | 100 |  | 0
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 |  | 0 | 0 | 19102.0801 | 8d | 0 | 0 | 0 | 19102.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 |  | 0 | 0 | 11938.8 | 5d | 0 | 0 | 0 | 11938.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 |  | 0 | 0 | 43018.8789 | 2d | 0 | 0 | 0 | 43018.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 |  | 0 | 0 | 1484.8 | 2d | 0 | 0 | 0 | 1484.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 |  | 0 | 0 | 1456.64 | 4d | 0 | 0 | 0 | 1456.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 24d | [5 empty] | 15576.3205 |  | 20.32% |  | 28939.521 | 32216.961
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 | 2013-08-01 08:00 | 20d | 14848.0005 | 0 | 0 | 0 | 0 | 14848.0005 | 0 | 100% | Finished | 28211.2009 | 28211.2009 | 100 | 52.6316 | 100 | 100 | 52.6316 | 100
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-09-02 08:00 | 2d | 728.32 | 4734.08 | 13d | 0 | 0 | 728.32 | 4734.08 | 13.33% | Started | 728.32 | 4005.76 | 100 | 13.3333 | 13.3333 | 100 | 13.3333 | 13.3333
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 |  | 0 | 0 | 5462.4001 | 15d | 0 | 0 | 0 | 5462.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 |  | 0 | 0 | 94566.083 | 7d | 0 | 0 | 0 | 94566.083 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 |  | 0 | 0 | 4291.2 | 20d | 0 | 0 | 0 | 4291.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2013-10-17 17:00 |  | TP Name | 17/10, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 254d | [5 empty] | 1823813.5621 |  | 96.96% |  | 2175895.37 | 2241863.5395
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 206d | [5 empty] | 1107493.9518 |  | 100% |  | 1401806.7273 | 1401806.7273
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 75d | [5 empty] | 92734.6399 |  | 100% |  | 102786.4896 | 102786.4896
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 100% | Finished | 47994.2388 | 47994.2388 | 100 | 60.7143 | 100 | 100 | 60.7143 | 100
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-01-29 08:00 | 9d | 0.72 | 0 | 0 | 15426 | 0 | 15426.72 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 7200 | 100 | 100 | 154267203.448 | 100
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 18d | [5 empty] | 183963.8413 |  | 100% |  | 399881.043 | 399881.043
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 18d | [5 empty] | 166320.481 |  | 100% |  | 361653.7622 | 361653.7622
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-01-29 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-05 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2013-02-04 08:00 | 1d | 97666.6406 | 0 | 0 | 0 | 0 | 97666.6406 | 0 | 100% | Finished | 292999.9219 | 292999.9219 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-07 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 2013-02-19 08:00 | 3d | 13308.2402 | 0 | 0 | 0 | 0 | 13308.2402 | 0 | 100% | Finished | 13308.2402 | 13308.2402 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 6d | [5 empty] | 17643.3604 |  | 100% |  | 38227.2808 | 38227.2808
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-11 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 50 | 100 | 100 | 50 | 100
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-12 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 2013-02-13 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 29405.6006 | 29405.6006 | 100 | 40 | 100 | 100 | 40 | 100
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 11d | [5 empty] | 69233.4404 |  | 100% |  | 80995.6807 | 80995.6807
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 11d | [5 empty] | 57471.2002 |  | 100% |  | 57471.2002 | 57471.2002
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 2013-02-11 08:00 | 2d | 6746.5601 | 0 | 0 | 0 | 0 | 6746.5601 | 0 | 100% | Finished | 6746.5601 | 6746.5601 | 100 | 100 | 100 | 100 | 100 | 100
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-13 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-15 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 2013-02-22 08:00 | 2d | 8872.1602 | 0 | 0 | 0 | 0 | 8872.1602 | 0 | 100% | Finished | 8872.1602 | 8872.1602 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 4d | [5 empty] | 11762.2402 |  | 100% |  | 23524.4805 | 23524.4805
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-19 08:00 | 2d | 5881.1201 | 0 | 0 | 0 | 0 | 5881.1201 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 100 | 100 | 100 | 100 | 100
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-21 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-02-22 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 20 | 100 | 100 | 20 | 100
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 38d | [5 empty] | 191365.6018 |  | 100% |  | 271266.8025 | 271266.8025
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 37d | [5 empty] | 138435.5208 |  | 100% |  | 194812.241 | 194812.241
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-02-26 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 2013-03-04 08:00 | 5d | 13822.3999 | 0 | 0 | 0 | 0 | 13822.3999 | 0 | 100% | Finished | 11057.9199 | 11057.9199 | 100 | 125 | 100 | 100 | 125 | 100
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 2013-03-11 08:00 | 5d | 9951.2 | 0 | 0 | 0 | 0 | 9951.2 | 0 | 100% | Finished | 17912.1599 | 17912.1599 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 | 2013-03-18 08:00 | 3d | 56808 | 0 | 0 | 0 | 0 | 56808 | 0 | 100% | Finished | 94680 | 94680 | 100 | 60 | 100 | 100 | 60 | 100
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 | 2013-04-04 08:00 | 10d | 44360.8008 | 0 | 0 | 0 | 0 | 44360.8008 | 0 | 100% | Finished | 57669.041 | 57669.041 | 100 | 76.9231 | 100 | 100 | 76.9231 | 100
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 21d | [5 empty] | 52930.0811 |  | 100% |  | 76454.5615 | 76454.5615
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-03-21 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 80 | 100 | 100 | 80 | 100
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 | 2013-03-27 08:00 | 3d | 8821.6802 | 0 | 0 | 0 | 0 | 8821.6802 | 0 | 100% | Finished | 8821.6802 | 8821.6802 | 100 | 100 | 100 | 100 | 100 | 100
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 | 2013-04-04 08:00 | 11d | 32346.1606 | 0 | 0 | 0 | 0 | 32346.1606 | 0 | 100% | Finished | 52930.0811 | 52930.0811 | 100 | 61.1111 | 100 | 100 | 61.1111 | 100
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 55d | [5 empty] | 175536.24 |  | 100% |  | 183634.01 | 183634.01
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 | 2013-04-04 08:00 | 8d | 31216 | 0 | 0 | 0 | 0 | 31216 | 0 | 100% | Finished | 42922 | 42922 | 100 | 72.7273 | 100 | 100 | 72.7273 | 100
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 | 2013-04-16 08:00 | 5d | 18040 | 0 | 0 | 0 | 0 | 18040 | 0 | 100% | Finished | 36080 | 36080 | 100 | 50 | 100 | 100 | 50 | 100
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-19 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-23 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-04-29 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-05-02 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-17 08:00 | 3d | 0.24 | 0 | 0 | 10824 | 0 | 10824.24 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 2400 | 100 | 100 | 108242402.4194 | 100
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 | 2013-05-06 08:00 | 20d | 72160 | 0 | 0 | 0 | 0 | 72160 | 0 | 100% | Finished | 61336 | 61336 | 100 | 117.6471 | 100 | 100 | 117.6471 | 100
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 9d | [5 empty] | 11288.5901 |  | 100% |  | 0.02 | 0.02
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-21 08:00 | 4d | 0.32 | 0 | 0 | 5016.8301 | 0 | 5017.1501 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 50171501.9026 | 100
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-27 08:00 | 5d | 0.4 | 0 | 0 | 6271.04 | 0 | 6271.44 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4000 | 100 | 100 | 62714401.7923 | 100
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 8d | [5 empty] | 40518.7202 |  | 100% |  | 73670.4004 | 73670.4004
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 | 2013-06-07 08:00 | 3d | 11050.5601 | 0 | 0 | 0 | 0 | 11050.5601 | 0 | 100% | Finished | 11050.5601 | 11050.5601 | 100 | 100 | 100 | 100 | 100 | 100
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 | 2013-06-03 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 40518.7202 | 40518.7202 | 100 | 36.3636 | 100 | 100 | 36.3636 | 100
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 | 2013-06-07 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 22101.1201 | 22101.1201 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 14d | [5 empty] | 62621.1989 |  | 100% |  | 0.03 | 0.03
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 3d | 0.24 | 0 | 0 | 11050.5596 | 0 | 11050.7996 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 2400 | 100 | 100 | 110507998.1731 | 100
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 10d | 0.8 | 0 | 0 | 36835.1992 | 0 | 36835.9992 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 8000 | 100 | 100 | 368360000.4208 | 100
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-21 08:00 | 4d | 0.32 | 0 | 0 | 14734.0801 | 0 | 14734.4001 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 147344004.0746 | 100
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 39d | [5 empty] | 93410.8784 |  | 100% |  | 56046.2502 | 56046.2502
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-06 08:00 | 6d | 0.48 | 0 | 0 | 56046.2383 | 0 | 56046.7183 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4800 | 100 | 100 | 560467195.3398 | 100
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-24 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 46d | [5 empty] | 186820.8008 |  | 100% |  | 233526.001 | 233526.001
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 | 2013-06-10 08:00 | 10d | 93410.4004 | 0 | 0 | 0 | 0 | 93410.4004 | 0 | 100% | Finished | 74728.3203 | 74728.3203 | 100 | 125 | 100 | 100 | 125 | 100
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-10 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-08-05 08:00 | 2d | 18682.0801 | 0 | 0 | 0 | 0 | 18682.0801 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 | 2013-08-07 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 46705.2002 | 46705.2002 | 100 | 80 | 100 | 100 | 80 | 100
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 119d | [5 empty] | 716319.6103 |  | 91.9% |  | 774088.6427 | 840056.8123
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 119d | [5 empty] | 133535.6786 |  | 96.27% |  | 161318.0783 | 167563.2785
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-06-07 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-06-12 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 | 2013-08-09 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 100% | Finished | 57306.2402 | 57306.2402 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-08-23 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 100% | Finished | 11938.8 | 11938.8 | 100 | 100 | 100 | 100 | 100 | 100
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 2184.96 | 2184.96 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 2184.96 | 2184.96 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 | 2013-06-27 08:00 | 5d | 67547.5977 | 0 | 0 | 0 | 0 | 67547.5977 | 0 | 100% | Finished | 67547.5977 | 67547.5977 | 100 | 100 | 100 | 100 | 100 | 100
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-07-04 08:00 | 22d | 16332.8005 | 0 | 0 | 0 | 0 | 16332.8005 | 0 | 100% | Finished | 4454.4001 | 4454.4001 | 100 | 366.6667 | 100 | 100 | 366.6667 | 100
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-05 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 6245.2002 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 14d | [5 empty] | 22312.0002 |  | 100% |  | 24293.2003 | 24293.2003
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 | 2013-06-10 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 4622.8002 | 4622.8002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 | 2013-06-14 08:00 | 10d | 16028.8 | 0 | 0 | 0 | 0 | 16028.8 | 0 | 100% | Finished | 16028.8 | 16028.8 | 100 | 100 | 100 | 100 | 100 | 100
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 | 2013-06-14 08:00 | 10d | 3641.6 | 0 | 0 | 0 | 0 | 3641.6 | 0 | 100% | Finished | 3641.6 | 3641.6 | 100 | 100 | 100 | 100 | 100 | 100
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 54d | [5 empty] | 17830.8007 |  | 100% |  | 28397.201 | 28397.201
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-14 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-20 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-06-26 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 100 | 100 | 100 | 100 | 100
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-05 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-07 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 | 2013-08-09 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 17170.4006 | 17170.4006 | 100 | 38.4615 | 100 | 100 | 38.4615 | 100
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-27 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 46d | [5 empty] | 28397.201 |  | 100% |  | 19151.6007 | 19151.6007
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-24 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-28 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-07-03 08:00 | 21d | 13868.4005 | 0 | 0 | 0 | 0 | 13868.4005 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 420 | 100 | 100 | 420 | 100
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-01 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-05 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 2013-08-07 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 7924.8003 | 7924.8003 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-23 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 59d | [5 empty] | 37642.8014 |  | 100% |  | 38963.6014 | 38963.6014
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 | 2013-07-02 08:00 | 23d | 15189.2006 | 0 | 0 | 0 | 0 | 15189.2006 | 0 | 100% | Finished | 15189.2006 | 15189.2006 | 100 | 100 | 100 | 100 | 100 | 100
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-08-02 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 2013-08-08 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 7924.8003 | 7924.8003 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-26 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 | 2013-08-28 08:00 | 15d | 9906.0004 | 0 | 0 | 0 | 0 | 9906.0004 | 0 | 100% | Finished | 9906.0004 | 9906.0004 | 100 | 100 | 100 | 100 | 100 | 100
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 | 2013-09-18 08:00 | 3d | 1981.2001 | 0 | 0 | 0 | 0 | 1981.2001 | 0 | 100% | Finished | 1981.2001 | 1981.2001 | 100 | 100 | 100 | 100 | 100 | 100
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 29d | [5 empty] | 17830.8007 |  | 100% |  | 17830.8007 | 17830.8007
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-08-02 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-08 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-08-12 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 100 | 100 | 100 | 100 | 100
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-21 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-23 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 | 2013-08-27 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 6604.0002 | 6604.0002 | 100 | 100 | 100 | 100 | 100 | 100
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-09-10 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 76d | [5 empty] | 148486.9634 |  | 100% |  | 157445.123 | 157445.123
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 12017.2801 | 12017.2801 | 100 | 93.9394 | 100 | 100 | 93.9394 | 100
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 12017.2801 | 12017.2801 | 100 | 93.9394 | 100 | 100 | 93.9394 | 100
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-08-09 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 | 2013-08-14 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 2549.12 | 2549.12 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 2013-08-19 08:00 | 4d | 9551.04 | 0 | 0 | 0 | 0 | 9551.04 | 0 | 100% | Finished | 23877.6001 | 23877.6001 | 100 | 40 | 100 | 100 | 40 | 100
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 | 2013-08-19 08:00 | 4d | 9551.04 | 0 | 0 | 0 | 0 | 9551.04 | 0 | 100% | Finished | 16714.3201 | 16714.3201 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-23 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 125 | 100 | 100 | 125 | 100
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-23 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 125 | 100 | 100 | 125 | 100
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 2013-08-30 08:00 | 6d | 81056.6426 | 0 | 0 | 0 | 0 | 81056.6426 | 0 | 100% | Finished | 67547.2021 | 67547.2021 | 100 | 120 | 100 | 100 | 120 | 100
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 | 2013-09-09 08:00 | 4d | 4340.48 | 0 | 0 | 0 | 0 | 4340.48 | 0 | 100% | Finished | 5425.6 | 5425.6 | 100 | 80 | 100 | 100 | 80 | 100
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-09-13 08:00 | 10d | 7424.0002 | 0 | 0 | 0 | 0 | 7424.0002 | 0 | 100% | Finished | 4454.4001 | 4454.4001 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-27 08:00 | 7d | 2549.12 | 0 | 0 | 0 | 0 | 2549.12 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 175 | 100 | 100 | 175 | 100
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 2013-10-08 08:00 | 3d | 3747.1201 | 0 | 0 | 0 | 0 | 3747.1201 | 0 | 100% | Finished | 6245.2002 | 6245.2002 | 100 | 60 | 100 | 100 | 60 | 100
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 81d | [5 empty] | 133310.0028 |  | 95.67% |  | 138085.5228 | 144330.723
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 11288.9601 | 11288.9601 | 100 | 100 | 100 | 100 | 100 | 100
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 11288.9601 | 11288.9601 | 100 | 100 | 100 | 100 | 100 | 100
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-08-09 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-08-14 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 2013-08-21 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 100% | Finished | 23877.6001 | 23877.6001 | 100 | 80 | 100 | 100 | 80 | 100
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-09-02 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 100% | Finished | 11938.8 | 11938.8 | 100 | 100 | 100 | 100 | 100 | 100
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-09 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-09 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 2013-09-13 08:00 | 5d | 67547.2021 | 0 | 0 | 0 | 0 | 67547.2021 | 0 | 100% | Finished | 67547.2021 | 67547.2021 | 100 | 100 | 100 | 100 | 100 | 100
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-09-20 08:00 | 6d | 4454.4001 | 0 | 0 | 0 | 0 | 4454.4001 | 0 | 100% | Finished | 4454.4001 | 4454.4001 | 100 | 100 | 100 | 100 | 100 | 100
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-30 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 6245.2002 | 100 |  | 0 | 100 |  | 0
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 50d | [5 empty] | 94158.9593 |  | 89.47% |  | 91138.5493 | 101860.7995
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 2013-08-09 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 6190.7201 | 6190.7201 | 100 | 88.2353 | 100 | 100 | 88.2353 | 100
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 2013-08-09 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 6190.7201 | 6190.7201 | 100 | 88.2353 | 100 | 100 | 88.2353 | 100
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-09-03 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-09-06 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 | 2013-09-27 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 100% | Finished | 19102.0801 | 19102.0801 | 100 | 100 | 100 | 100 | 100 | 100
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-10-09 08:00 | 5d | 11938.8 | 7163.28 | 3d | 0 | 0 | 11938.8 | 7163.28 | 62.5% | Started | 7461.75 | 11938.8 | 100 | 100 | 62.5 | 100 | 100 | 62.5
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-11 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-11 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 | 2013-09-17 08:00 | 2d | 43018.8789 | 0 | 0 | 0 | 0 | 43018.8789 | 0 | 100% | Finished | 43018.8789 | 43018.8789 | 100 | 100 | 100 | 100 | 100 | 100
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 | 2013-09-19 08:00 | 2d | 1484.8 | 0 | 0 | 0 | 0 | 1484.8 | 0 | 100% | Finished | 1484.8 | 1484.8 | 100 | 100 | 100 | 100 | 100 | 100
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-23 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 6245.2002 | 100 |  | 0 | 100 |  | 0
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 56d | [5 empty] | 82814.4023 |  | 68.42% |  | 97464.9651 | 140220.4841
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 | 2013-08-01 08:00 | 20d | 14848.0005 | 0 | 0 | 0 | 0 | 14848.0005 | 0 | 100% | Finished | 28211.2009 | 28211.2009 | 100 | 52.6316 | 100 | 100 | 52.6316 | 100
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-09-02 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-09-23 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 | 2013-10-14 08:00 | 4d | 54037.7617 | 40528.3213 | 3d | 0 | 0 | 54037.7617 | 40528.3213 | 57.14% | Started | 54037.7641 | 94566.083 | 100 | 57.1429 | 57.1429 | 100 | 57.1429 | 57.1429
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 | 2013-09-30 08:00 | 14d | 3003.84 | 0 | 0 | 0 | 0 | 3003.84 | 0 | 100% | Finished | 4291.2 | 4291.2 | 100 | 70 | 100 | 100 | 70 | 100
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 |  | 0 | 0 | 4454.4001 | 6d | 0 | 0 | 0 | 4454.4001 | 0% | Not Started | 0 | 2227.2001 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2013-11-20 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (1) | 2012-10-29 08:00 | 2013-10-22 17:00 | 257d |  |  | 0 |  |  | 2244090.7396 |  | 278d | [5 empty] | 1868796.2835 |  | 99.72% |  | 2237845.5394 | 2244090.7396
67 | Ruwbouw | 2012-10-29 08:00 | 2013-05-31 17:00 | 155d |  |  | 0 |  |  | 1401806.7273 |  | 206d | [5 empty] | 1107493.9518 |  | 100% |  | 1401806.7273 | 1401806.7273
6 | Funderingswerken | 2012-10-29 08:00 | 2013-01-29 09:00 | 66d 1h |  |  | 0 |  |  | 102786.4896 |  | 75d | [5 empty] | 92734.6399 |  | 100% |  | 102786.4896 | 102786.4896
1 | Paalfundering | 2012-10-29 08:00 | 2012-11-09 17:00 | 10d |  | 0 | 0 | 413.98 | 33118.4009 | 33118.4009 | 2012-10-29 08:00 | 8d | 26494.7207 | 0 | 0 | 0 | 0 | 26494.7207 | 0 | 100% | Finished | 33118.4009 | 33118.4009 | 100 | 80 | 100 | 100 | 80 | 100
2 | Knippen van de palen | 2012-11-15 08:00 | 2012-11-15 17:00 | 1d |  | 0 | 0 | 198.26 | 1586.08 | 1586.08 | 2012-11-15 08:00 | 1d | 1586.08 | 0 | 0 | 0 | 0 | 1586.08 | 0 | 100% | Finished | 1586.08 | 1586.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | Grondwerken | 2012-11-13 08:00 | 2012-12-11 17:00 | 21d |  | 0 | 0 | 119.57 | 20087.7599 | 20087.7599 | 2012-11-13 08:00 | 21d | 20087.7599 | 0 | 0 | 0 | 0 | 20087.7599 | 0 | 100% | Finished | 20087.7599 | 20087.7599 | 100 | 100 | 100 | 100 | 100 | 100
4 | Funderingsbalken | 2012-12-03 08:00 | 2013-01-09 17:00 | 28d |  | 0 | 0 | 214.26 | 47994.2388 | 47994.2388 | 2012-12-03 08:00 | 17d | 29139.3593 | 0 | 0 | 0 | 0 | 29139.3593 | 0 | 100% | Finished | 47994.2388 | 47994.2388 | 100 | 60.7143 | 100 | 100 | 60.7143 | 100
5 | Funderingsbalken en aanpassingen | 2013-01-29 08:00 | 2013-01-29 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-01-29 08:00 | 9d | 0.72 | 0 | 0 | 15426 | 0 | 15426.72 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 7200 | 100 | 100 | 154267203.448 | 100
17 | Bovenbouw A | 2013-01-08 08:00 | 2013-02-08 17:00 | 24d |  |  | 0 |  |  | 399881.043 |  | 18d | [5 empty] | 183963.8413 |  | 100% |  | 399881.043 | 399881.043
12 | Montage prefab | 2013-01-08 08:00 | 2013-02-04 17:00 | 20d |  |  | 0 |  |  | 361653.7622 |  | 18d | [5 empty] | 166320.481 |  | 100% |  | 361653.7622 | 361653.7622
7 | Kolommen | 2013-01-08 08:00 | 2013-01-11 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-01-29 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
8 | balken | 2013-01-17 08:00 | 2013-01-18 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-05 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
9 | Structurele wand | 2013-01-14 08:00 | 2013-01-16 17:00 | 3d |  | 0 | 0 | 12208.3301 | 292999.9219 | 292999.9219 | 2013-02-04 08:00 | 1d | 97666.6406 | 0 | 0 | 0 | 0 | 97666.6406 | 0 | 100% | Finished | 292999.9219 | 292999.9219 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
10 | Welfsles | 2013-01-21 08:00 | 2013-01-22 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-07 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
11 | SW-panelen | 2013-01-31 08:00 | 2013-02-04 17:00 | 3d |  | 0 | 0 | 554.51 | 13308.2402 | 13308.2402 | 2013-02-19 08:00 | 3d | 13308.2402 | 0 | 0 | 0 | 0 | 13308.2402 | 0 | 100% | Finished | 13308.2402 | 13308.2402 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouwwerken | 2013-01-23 08:00 | 2013-02-08 17:00 | 13d |  |  | 0 |  |  | 38227.2808 |  | 6d | [5 empty] | 17643.3604 |  | 100% |  | 38227.2808 | 38227.2808
13 | Voorbereiding opstortbeton | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-11 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 50 | 100 | 100 | 50 | 100
14 | opstort niv 1 en 2 | 2013-01-25 08:00 | 2013-01-25 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-12 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
15 | Metselwerken | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 367.57 | 29405.6006 | 29405.6006 | 2013-02-13 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 29405.6006 | 29405.6006 | 100 | 40 | 100 | 100 | 40 | 100
27 | Bovenbouw B | 2013-01-23 08:00 | 2013-02-11 17:00 | 14d |  |  | 0 |  |  | 80995.6807 |  | 11d | [5 empty] | 69233.4404 |  | 100% |  | 80995.6807 | 80995.6807
22 | Montage prefab | 2013-01-23 08:00 | 2013-02-06 17:00 | 11d |  |  | 0 |  |  | 57471.2002 |  | 11d | [5 empty] | 57471.2002 |  | 100% |  | 57471.2002 | 57471.2002
18 | Kolommen | 2013-01-23 08:00 | 2013-01-24 17:00 | 2d |  | 0 | 0 | 421.66 | 6746.5601 | 6746.5601 | 2013-02-11 08:00 | 2d | 6746.5601 | 0 | 0 | 0 | 0 | 6746.5601 | 0 | 100% | Finished | 6746.5601 | 6746.5601 | 100 | 100 | 100 | 100 | 100 | 100
19 | Balken | 2013-01-25 08:00 | 2013-01-28 17:00 | 2d |  | 0 | 0 | 248.78 | 3980.48 | 3980.48 | 2013-02-13 08:00 | 2d | 3980.48 | 0 | 0 | 0 | 0 | 3980.48 | 0 | 100% | Finished | 3980.48 | 3980.48 | 100 | 100 | 100 | 100 | 100 | 100
20 | Welfsels | 2013-01-29 08:00 | 2013-01-30 17:00 | 2d |  | 0 | 0 | 2367 | 37872 | 37872 | 2013-02-15 08:00 | 2d | 37872 | 0 | 0 | 0 | 0 | 37872 | 0 | 100% | Finished | 37872 | 37872 | 100 | 100 | 100 | 100 | 100 | 100
21 | SW-panelen | 2013-02-05 08:00 | 2013-02-06 17:00 | 2d |  | 0 | 0 | 554.51 | 8872.1602 | 8872.1602 | 2013-02-22 08:00 | 2d | 8872.1602 | 0 | 0 | 0 | 0 | 8872.1602 | 0 | 100% | Finished | 8872.1602 | 8872.1602 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken | 2013-01-31 08:00 | 2013-02-11 17:00 | 8d |  |  | 0 |  |  | 23524.4805 |  | 4d | [5 empty] | 11762.2402 |  | 100% |  | 23524.4805 | 23524.4805
23 | voorbereiding opstortbeton | 2013-01-31 08:00 | 2013-02-01 17:00 | 2d |  | 0 | 0 | 367.57 | 5881.1201 | 5881.1201 | 2013-02-19 08:00 | 2d | 5881.1201 | 0 | 0 | 0 | 0 | 5881.1201 | 0 | 100% | Finished | 5881.1201 | 5881.1201 | 100 | 100 | 100 | 100 | 100 | 100
24 | Opstort niv 1 en 2 | 2013-02-04 08:00 | 2013-02-04 17:00 | 1d |  | 0 | 0 | 367.57 | 2940.5601 | 2940.5601 | 2013-02-21 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 2940.5601 | 2940.5601 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken | 2013-02-05 08:00 | 2013-02-11 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-02-22 08:00 | 1d | 2940.5601 | 0 | 0 | 0 | 0 | 2940.5601 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 20 | 100 | 100 | 20 | 100
38 | Bovenbouw C | 2013-02-07 08:00 | 2013-04-15 17:00 | 48d |  |  | 0 |  |  | 271266.8025 |  | 38d | [5 empty] | 191365.6018 |  | 100% |  | 271266.8025 | 271266.8025
33 | Montage prefab | 2013-02-07 08:00 | 2013-04-08 17:00 | 43d |  |  | 0 |  |  | 194812.241 |  | 37d | [5 empty] | 138435.5208 |  | 100% |  | 194812.241 | 194812.241
28 | kolommen | 2013-02-07 08:00 | 2013-02-12 17:00 | 4d |  | 0 | 0 | 421.66 | 13493.1201 | 13493.1201 | 2013-02-26 08:00 | 4d | 13493.1201 | 0 | 0 | 0 | 0 | 13493.1201 | 0 | 100% | Finished | 13493.1201 | 13493.1201 | 100 | 100 | 100 | 100 | 100 | 100
29 | centrale kern | 2013-02-13 08:00 | 2013-02-18 17:00 | 4d |  | 0 | 0 | 345.56 | 11057.9199 | 11057.9199 | 2013-03-04 08:00 | 5d | 13822.3999 | 0 | 0 | 0 | 0 | 13822.3999 | 0 | 100% | Finished | 11057.9199 | 11057.9199 | 100 | 125 | 100 | 100 | 125 | 100
30 | balken | 2013-02-19 08:00 | 2013-03-01 17:00 | 9d |  | 0 | 0 | 248.78 | 17912.1599 | 17912.1599 | 2013-03-11 08:00 | 5d | 9951.2 | 0 | 0 | 0 | 0 | 9951.2 | 0 | 100% | Finished | 17912.1599 | 17912.1599 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
31 | welfsels | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 2367 | 94680 | 94680 | 2013-03-18 08:00 | 3d | 56808 | 0 | 0 | 0 | 0 | 56808 | 0 | 100% | Finished | 94680 | 94680 | 100 | 60 | 100 | 100 | 60 | 100
32 | SW panelen | 2013-03-21 08:00 | 2013-04-08 17:00 | 13d |  | 0 | 0 | 554.51 | 57669.041 | 57669.041 | 2013-04-04 08:00 | 10d | 44360.8008 | 0 | 0 | 0 | 0 | 44360.8008 | 0 | 100% | Finished | 57669.041 | 57669.041 | 100 | 76.9231 | 100 | 100 | 76.9231 | 100
37 | Ruwbouwwerken | 2013-03-11 08:00 | 2013-04-15 17:00 | 26d |  |  | 0 |  |  | 76454.5615 |  | 21d | [5 empty] | 52930.0811 |  | 100% |  | 76454.5615 | 76454.5615
34 | voorbereiding opstortbeton | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 367.57 | 14702.8003 | 14702.8003 | 2013-03-21 08:00 | 4d | 11762.2402 | 0 | 0 | 0 | 0 | 11762.2402 | 0 | 100% | Finished | 14702.8003 | 14702.8003 | 100 | 80 | 100 | 100 | 80 | 100
35 | opstort niv 1, 2 en 3 | 2013-03-18 08:00 | 2013-03-20 17:00 | 3d |  | 0 | 0 | 367.57 | 8821.6802 | 8821.6802 | 2013-03-27 08:00 | 3d | 8821.6802 | 0 | 0 | 0 | 0 | 8821.6802 | 0 | 100% | Finished | 8821.6802 | 8821.6802 | 100 | 100 | 100 | 100 | 100 | 100
36 | Metselwerk | 2013-03-21 08:00 | 2013-04-15 17:00 | 18d |  | 0 | 0 | 367.57 | 52930.0811 | 52930.0811 | 2013-04-04 08:00 | 11d | 32346.1606 | 0 | 0 | 0 | 0 | 32346.1606 | 0 | 100% | Finished | 52930.0811 | 52930.0811 | 100 | 61.1111 | 100 | 100 | 61.1111 | 100
47 | Draagvloer gv | 2013-03-21 08:00 | 2013-05-23 17:00 | 46d |  |  | 0 |  |  | 183634.01 |  | 55d | [5 empty] | 175536.24 |  | 100% |  | 183634.01 | 183634.01
39 | rioleringswerken | 2013-03-21 08:00 | 2013-04-04 17:00 | 11d |  | 0 | 0 | 487.75 | 42922 | 42922 | 2013-04-04 08:00 | 8d | 31216 | 0 | 0 | 0 | 0 | 31216 | 0 | 100% | Finished | 42922 | 42922 | 100 | 72.7273 | 100 | 100 | 72.7273 | 100
40 | aanvulling gestabiliseerd zand | 2013-04-05 08:00 | 2013-04-18 17:00 | 10d |  | 0 | 0 | 451 | 36080 | 36080 | 2013-04-16 08:00 | 5d | 18040 | 0 | 0 | 0 | 0 | 18040 | 0 | 100% | Finished | 36080 | 36080 | 100 | 50 | 100 | 100 | 50 | 100
41 | plaatsen vloerisolatie | 2013-04-17 08:00 | 2013-04-22 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-19 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
42 | plaatsen wapening | 2013-04-19 08:00 | 2013-04-24 17:00 | 4d |  | 0 | 0 | 451 | 14432 | 14432 | 2013-04-23 08:00 | 4d | 14432 | 0 | 0 | 0 | 0 | 14432 | 0 | 100% | Finished | 14432 | 14432 | 100 | 100 | 100 | 100 | 100 | 100
43 | bekistingswerken | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-04-29 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
44 | stort vloerplaat gv | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 451 | 7216 | 7216 | 2013-05-02 08:00 | 2d | 7216 | 0 | 0 | 0 | 0 | 7216 | 0 | 100% | Finished | 7216 | 7216 | 100 | 100 | 100 | 100 | 100 | 100
45 | vloerplaat centrum | 2013-05-02 08:00 | 2013-05-02 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-17 08:00 | 3d | 0.24 | 0 | 0 | 10824 | 0 | 10824.24 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 2400 | 100 | 100 | 108242402.4194 | 100
46 | metselwerken | 2013-05-01 08:00 | 2013-05-23 17:00 | 17d |  | 0 | 0 | 451 | 61336 | 61336 | 2013-05-06 08:00 | 20d | 72160 | 0 | 0 | 0 | 0 | 72160 | 0 | 100% | Finished | 61336 | 61336 | 100 | 117.6471 | 100 | 100 | 117.6471 | 100
50 | Regenwater afvoeren | 2013-02-27 08:00 | 2013-03-20 09:00 | 15d 1h |  |  | 0 |  |  | 0.02 |  | 9d | [5 empty] | 11288.5901 |  | 100% |  | 0.02 | 0.02
48 | RW deel 1 | 2013-02-27 08:00 | 2013-02-27 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-21 08:00 | 4d | 0.32 | 0 | 0 | 5016.8301 | 0 | 5017.1501 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 50171501.9026 | 100
49 | RW deel 2 | 2013-03-20 08:00 | 2013-03-20 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-27 08:00 | 5d | 0.4 | 0 | 0 | 6271.04 | 0 | 6271.44 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4000 | 100 | 100 | 62714401.7923 | 100
54 | Dakwerken deel 1 | 2013-04-11 08:00 | 2013-05-13 17:00 | 23d |  |  | 0 |  |  | 73670.4004 |  | 8d | [5 empty] | 40518.7202 |  | 100% |  | 73670.4004 | 73670.4004
51 | hellingsbeton | 2013-04-11 08:00 | 2013-04-15 17:00 | 3d |  | 0 | 0 | 460.44 | 11050.5601 | 11050.5601 | 2013-06-07 08:00 | 3d | 11050.5601 | 0 | 0 | 0 | 0 | 11050.5601 | 0 | 100% | Finished | 11050.5601 | 11050.5601 | 100 | 100 | 100 | 100 | 100 | 100
52 | dampscherm + isolatie + afwerking | 2013-04-19 08:00 | 2013-05-03 17:00 | 11d |  | 0 | 0 | 460.44 | 40518.7202 | 40518.7202 | 2013-06-03 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 40518.7202 | 40518.7202 | 100 | 36.3636 | 100 | 100 | 36.3636 | 100
53 | Aanwerken aan bestaande toestand | 2013-05-06 08:00 | 2013-05-13 17:00 | 6d |  | 0 | 0 | 460.44 | 22101.1201 | 22101.1201 | 2013-06-07 08:00 | 4d | 14734.0801 | 0 | 0 | 0 | 0 | 14734.0801 | 0 | 100% | Finished | 22101.1201 | 22101.1201 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
58 | Dakwerken deel 2 | 2013-04-19 14:00 | 2013-04-24 17:00 | 3d 3h |  |  | 0 |  |  | 0.03 |  | 14d | [5 empty] | 62621.1989 |  | 100% |  | 0.03 | 0.03
55 | hellingsbeton | 2013-04-19 14:00 | 2013-04-19 15:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 3d | 0.24 | 0 | 0 | 11050.5596 | 0 | 11050.7996 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 2400 | 100 | 100 | 110507998.1731 | 100
56 | dampscherm + isolatie + afwerking | 2013-04-24 15:00 | 2013-04-24 16:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-07 08:00 | 10d | 0.8 | 0 | 0 | 36835.1992 | 0 | 36835.9992 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 8000 | 100 | 100 | 368360000.4208 | 100
57 | Aanwerken aan bestaande toestand | 2013-04-24 16:00 | 2013-04-24 17:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-06-21 08:00 | 4d | 0.32 | 0 | 0 | 14734.0801 | 0 | 14734.4001 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 3200 | 100 | 100 | 147344004.0746 | 100
61 | Buitenschrijnwerk deel 1 | 2013-05-14 08:00 | 2013-05-31 17:00 | 14d |  |  | 0 |  |  | 56046.2502 |  | 39d | [5 empty] | 93410.8784 |  | 100% |  | 56046.2502 | 56046.2502
59 | Alu ramen | 2013-05-14 08:00 | 2013-05-14 09:00 | 1h |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 2013-05-06 08:00 | 6d | 0.48 | 0 | 0 | 56046.2383 | 0 | 56046.7183 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 4800 | 100 | 100 | 560467195.3398 | 100
60 | sectionaalpoorten | 2013-05-24 08:00 | 2013-05-31 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-24 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
66 | Buitenschrijnwerk deel 2 | 2013-04-25 08:00 | 2013-05-21 17:00 | 19d |  |  | 0 |  |  | 233526.001 |  | 46d | [5 empty] | 186820.8008 |  | 100% |  | 233526.001 | 233526.001
62 | Alu ramen | 2013-04-25 08:00 | 2013-05-06 17:00 | 8d |  | 0 | 0 | 1167.63 | 74728.3203 | 74728.3203 | 2013-06-10 08:00 | 10d | 93410.4004 | 0 | 0 | 0 | 0 | 93410.4004 | 0 | 100% | Finished | 74728.3203 | 74728.3203 | 100 | 125 | 100 | 100 | 125 | 100
63 | gordijngevel elementen | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-06-10 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
64 | automatische deuren | 2013-05-07 08:00 | 2013-05-14 17:00 | 6d |  | 0 | 0 | 1167.63 | 56046.2402 | 56046.2402 | 2013-08-05 08:00 | 2d | 18682.0801 | 0 | 0 | 0 | 0 | 18682.0801 | 0 | 100% | Finished | 56046.2402 | 56046.2402 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
65 | vouwgeheel | 2013-05-15 08:00 | 2013-05-21 17:00 | 5d |  | 0 | 0 | 1167.63 | 46705.2002 | 46705.2002 | 2013-08-07 08:00 | 4d | 37364.1602 | 0 | 0 | 0 | 0 | 37364.1602 | 0 | 100% | Finished | 46705.2002 | 46705.2002 | 100 | 80 | 100 | 100 | 80 | 100
163 | Planning afwerking | 2013-06-03 08:00 | 2013-10-22 17:00 | 102d |  |  | 0 |  |  | 842284.0123 |  | 143d | [5 empty] | 761302.3317 |  | 99.26% |  | 836038.8121 | 842284.0123
80 | 1e verdieping landscape links | 2013-06-03 08:00 | 2013-09-16 17:00 | 76d |  |  | 0 |  |  | 167563.2785 |  | 143d | [5 empty] | 133535.6786 |  | 96.27% |  | 161318.0783 | 167563.2785
68 | HVAC plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
69 | Elektriciteit plafond | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-05-06 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
70 | Schilderwerk wanden | 2013-06-24 08:00 | 2013-06-26 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-06-07 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
71 | Structuur valse plafond | 2013-06-27 08:00 | 2013-07-01 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-06-12 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
72 | elecktriciteit vloer | 2013-07-02 08:00 | 2013-08-02 17:00 | 24d |  | 0 | 0 | 298.47 | 57306.2402 | 57306.2402 | 2013-08-09 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 100% | Finished | 57306.2402 | 57306.2402 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
73 | Verhoogde vloer | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-08-23 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 100% | Finished | 11938.8 | 11938.8 | 100 | 100 | 100 | 100 | 100 | 100
74 | HVAC toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 2184.96 | 2184.96 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | Elektriciteit toestellen plafond | 2013-08-12 08:00 | 2013-08-19 17:00 | 6d |  | 0 | 0 | 45.52 | 2184.96 | 2184.96 | 2013-06-21 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 2184.96 | 2184.96 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
76 | Binnenschrijnwerk | 2013-08-20 08:00 | 2013-08-26 17:00 | 5d |  | 0 | 0 | 1688.6899 | 67547.5977 | 67547.5977 | 2013-06-27 08:00 | 5d | 67547.5977 | 0 | 0 | 0 | 0 | 67547.5977 | 0 | 100% | Finished | 67547.5977 | 67547.5977 | 100 | 100 | 100 | 100 | 100 | 100
77 | Schilderwerk | 2013-08-27 08:00 | 2013-09-03 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-07-04 08:00 | 22d | 16332.8005 | 0 | 0 | 0 | 0 | 16332.8005 | 0 | 100% | Finished | 4454.4001 | 4454.4001 | 100 | 366.6667 | 100 | 100 | 366.6667 | 100
78 | plafondtegels | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-05 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
79 | tapijt | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 |  | 0 | 0 | 6245.2002 | 5d | 0 | 0 | 0 | 6245.2002 | 0% | Not Started | 0 | 6245.2002 | 100 |  | 0 | 100 |  | 0
84 | Schacht | 2013-06-03 08:00 | 2013-06-25 17:00 | 17d |  |  | 0 |  |  | 24293.2003 |  | 14d | [5 empty] | 22312.0002 |  | 100% |  | 24293.2003 | 24293.2003
81 | Sanitair plaatsen aan een afvoerleiding in schacht | 2013-06-03 08:00 | 2013-06-11 17:00 | 7d |  | 0 | 0 | 82.55 | 4622.8002 | 4622.8002 | 2013-06-10 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 4622.8002 | 4622.8002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
82 | HVAC | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 200.36 | 16028.8 | 16028.8 | 2013-06-14 08:00 | 10d | 16028.8 | 0 | 0 | 0 | 0 | 16028.8 | 0 | 100% | Finished | 16028.8 | 16028.8 | 100 | 100 | 100 | 100 | 100 | 100
83 | Elektriciteit | 2013-06-12 08:00 | 2013-06-25 17:00 | 10d |  | 0 | 0 | 45.52 | 3641.6 | 3641.6 | 2013-06-14 08:00 | 10d | 3641.6 | 0 | 0 | 0 | 0 | 3641.6 | 0 | 100% | Finished | 3641.6 | 3641.6 | 100 | 100 | 100 | 100 | 100 | 100
92 | 2e verdieping sanitair | 2013-06-12 08:00 | 2013-08-13 17:00 | 45d |  |  | 0 |  |  | 28397.201 |  | 54d | [5 empty] | 17830.8007 |  | 100% |  | 28397.201 | 28397.201
85 | aan en afvoerleidingen | 2013-06-12 08:00 | 2013-06-17 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-14 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
86 | montage toiletten | 2013-06-18 08:00 | 2013-06-19 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-20 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
87 | bezettingswerken (cementering) | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-06-26 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 100 | 100 | 100 | 100 | 100
88 | pur en chape | 2013-07-01 08:00 | 2013-07-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-05 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
89 | gyproc | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-07 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
90 | tegelwerken | 2013-07-05 08:00 | 2013-08-09 17:00 | 26d |  | 0 | 0 | 82.55 | 17170.4006 | 17170.4006 | 2013-08-09 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 17170.4006 | 17170.4006 | 100 | 38.4615 | 100 | 100 | 38.4615 | 100
91 | plafond | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-27 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
100 | 1e verdieping sanitair | 2013-06-20 08:00 | 2013-08-22 17:00 | 46d |  |  | 0 |  |  | 19151.6007 |  | 46d | [5 empty] | 28397.201 |  | 100% |  | 19151.6007 | 19151.6007
93 | aan en afvoerleidingen | 2013-06-20 08:00 | 2013-06-25 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-06-24 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
94 | montage hangtoiletten | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-06-28 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | bezettingswerken (cementering) | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-07-03 08:00 | 21d | 13868.4005 | 0 | 0 | 0 | 0 | 13868.4005 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 420 | 100 | 100 | 420 | 100
96 | pur en chape | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-01 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
97 | gyproc | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-05 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
98 | tegelwerken | 2013-08-05 08:00 | 2013-08-20 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 2013-08-07 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 7924.8003 | 7924.8003 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
99 | plafond | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-23 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
107 | gv sanitair links | 2013-06-28 08:00 | 2013-09-18 17:00 | 59d |  |  | 0 |  |  | 38963.6014 |  | 59d | [5 empty] | 37642.8014 |  | 100% |  | 38963.6014 | 38963.6014
101 | aan en afvoerleidingen | 2013-06-28 08:00 | 2013-07-30 17:00 | 23d |  | 0 | 0 | 82.55 | 15189.2006 | 15189.2006 | 2013-07-02 08:00 | 23d | 15189.2006 | 0 | 0 | 0 | 0 | 15189.2006 | 0 | 100% | Finished | 15189.2006 | 15189.2006 | 100 | 100 | 100 | 100 | 100 | 100
102 | montage hangtoiletten | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-08-02 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
103 | bezettingswerken (cementering) | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 82.55 | 7924.8003 | 7924.8003 | 2013-08-08 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 7924.8003 | 7924.8003 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
104 | gyproc | 2013-08-22 08:00 | 2013-08-23 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-26 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | tegelwerken | 2013-08-26 08:00 | 2013-09-13 17:00 | 15d |  | 0 | 0 | 82.55 | 9906.0004 | 9906.0004 | 2013-08-28 08:00 | 15d | 9906.0004 | 0 | 0 | 0 | 0 | 9906.0004 | 0 | 100% | Finished | 9906.0004 | 9906.0004 | 100 | 100 | 100 | 100 | 100 | 100
106 | plafond | 2013-09-16 08:00 | 2013-09-18 17:00 | 3d |  | 0 | 0 | 82.55 | 1981.2001 | 1981.2001 | 2013-09-18 08:00 | 3d | 1981.2001 | 0 | 0 | 0 | 0 | 1981.2001 | 0 | 100% | Finished | 1981.2001 | 1981.2001 | 100 | 100 | 100 | 100 | 100 | 100
115 | Gelijkvloers sanitair rechts | 2013-07-31 08:00 | 2013-09-09 17:00 | 29d |  |  | 0 |  |  | 17830.8007 |  | 29d | [5 empty] | 17830.8007 |  | 100% |  | 17830.8007 | 17830.8007
108 | aan en afvoerleidingen | 2013-07-31 08:00 | 2013-08-05 17:00 | 4d |  | 0 | 0 | 82.55 | 2641.6001 | 2641.6001 | 2013-08-02 08:00 | 4d | 2641.6001 | 0 | 0 | 0 | 0 | 2641.6001 | 0 | 100% | Finished | 2641.6001 | 2641.6001 | 100 | 100 | 100 | 100 | 100 | 100
109 | montage hangtoiletten | 2013-08-06 08:00 | 2013-08-07 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-08 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
110 | bezettingswerken (cementering) | 2013-08-08 08:00 | 2013-08-14 17:00 | 5d |  | 0 | 0 | 82.55 | 3302.0001 | 3302.0001 | 2013-08-12 08:00 | 5d | 3302.0001 | 0 | 0 | 0 | 0 | 3302.0001 | 0 | 100% | Finished | 3302.0001 | 3302.0001 | 100 | 100 | 100 | 100 | 100 | 100
111 | pur en chape | 2013-08-19 08:00 | 2013-08-20 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-21 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
112 | gyproc | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-08-23 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
113 | tegelwerken | 2013-08-23 08:00 | 2013-09-05 17:00 | 10d |  | 0 | 0 | 82.55 | 6604.0002 | 6604.0002 | 2013-08-27 08:00 | 10d | 6604.0002 | 0 | 0 | 0 | 0 | 6604.0002 | 0 | 100% | Finished | 6604.0002 | 6604.0002 | 100 | 100 | 100 | 100 | 100 | 100
114 | plafond | 2013-09-06 08:00 | 2013-09-09 17:00 | 2d |  | 0 | 0 | 82.55 | 1320.8 | 1320.8 | 2013-09-10 08:00 | 2d | 1320.8 | 0 | 0 | 0 | 0 | 1320.8 | 0 | 100% | Finished | 1320.8 | 1320.8 | 100 | 100 | 100 | 100 | 100 | 100
129 | 2e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-17 17:00 | 84d |  |  | 0 |  |  | 157445.123 |  | 76d | [5 empty] | 148486.9634 |  | 100% |  | 157445.123 | 157445.123
116 | HVAC plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 12017.2801 | 12017.2801 | 100 | 93.9394 | 100 | 100 | 93.9394 | 100
117 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-07 17:00 | 33d |  | 0 | 0 | 45.52 | 12017.2801 | 12017.2801 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 12017.2801 | 12017.2801 | 100 | 93.9394 | 100 | 100 | 93.9394 | 100
118 | Schilderwerken wanden | 2013-08-08 08:00 | 2013-08-12 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-08-09 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
119 | structuur vals plafond | 2013-08-13 08:00 | 2013-08-21 17:00 | 7d |  | 0 | 0 | 45.52 | 2549.12 | 2549.12 | 2013-08-14 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 2549.12 | 2549.12 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
120 | Elektriciteit vloer | 2013-08-22 08:00 | 2013-09-04 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 2013-08-19 08:00 | 4d | 9551.04 | 0 | 0 | 0 | 0 | 9551.04 | 0 | 100% | Finished | 23877.6001 | 23877.6001 | 100 | 40 | 100 | 100 | 40 | 100
121 | verhoogde vloer | 2013-09-05 08:00 | 2013-09-13 17:00 | 7d |  | 0 | 0 | 298.47 | 16714.3201 | 16714.3201 | 2013-08-19 08:00 | 4d | 9551.04 | 0 | 0 | 0 | 0 | 9551.04 | 0 | 100% | Finished | 16714.3201 | 16714.3201 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
122 | HVAC toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-23 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 125 | 100 | 100 | 125 | 100
123 | Elektriciteit toestellen plafond | 2013-09-16 08:00 | 2013-09-19 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-08-23 08:00 | 5d | 1820.8 | 0 | 0 | 0 | 0 | 1820.8 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 125 | 100 | 100 | 125 | 100
124 | Binnenschrijnwerk | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 2013-08-30 08:00 | 6d | 81056.6426 | 0 | 0 | 0 | 0 | 81056.6426 | 0 | 100% | Finished | 67547.2021 | 67547.2021 | 100 | 120 | 100 | 100 | 120 | 100
125 | keuken | 2013-09-20 08:00 | 2013-09-26 17:00 | 5d |  | 0 | 0 | 135.64 | 5425.6 | 5425.6 | 2013-09-09 08:00 | 4d | 4340.48 | 0 | 0 | 0 | 0 | 4340.48 | 0 | 100% | Finished | 5425.6 | 5425.6 | 100 | 80 | 100 | 100 | 80 | 100
126 | Schilderwerken | 2013-09-27 08:00 | 2013-10-04 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-09-13 08:00 | 10d | 7424.0002 | 0 | 0 | 0 | 0 | 7424.0002 | 0 | 100% | Finished | 4454.4001 | 4454.4001 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
127 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-27 08:00 | 7d | 2549.12 | 0 | 0 | 0 | 0 | 2549.12 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 175 | 100 | 100 | 175 | 100
128 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 2013-10-08 08:00 | 3d | 3747.1201 | 0 | 0 | 0 | 0 | 3747.1201 | 0 | 100% | Finished | 6245.2002 | 6245.2002 | 100 | 60 | 100 | 100 | 60 | 100
142 | 1e verdieping landscape rechts | 2013-06-24 08:00 | 2013-10-07 17:00 | 76d |  |  | 0 |  |  | 144330.723 |  | 86d 1h | [5 empty] | 133310.0028 |  | 100% |  | 144330.723 | 144330.723
130 | HVAC plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 11288.9601 | 11288.9601 | 100 | 100 | 100 | 100 | 100 | 100
131 | Elektriciteit plafond | 2013-06-24 08:00 | 2013-08-05 17:00 | 31d |  | 0 | 0 | 45.52 | 11288.9601 | 11288.9601 | 2013-06-27 08:00 | 31d | 11288.9601 | 0 | 0 | 0 | 0 | 11288.9601 | 0 | 100% | Finished | 11288.9601 | 11288.9601 | 100 | 100 | 100 | 100 | 100 | 100
132 | Schilderwerken wanden | 2013-08-06 08:00 | 2013-08-08 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-08-09 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
133 | structuur valse plafond | 2013-08-09 08:00 | 2013-08-13 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-08-14 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
134 | Elektriciteit vloer | 2013-08-14 08:00 | 2013-08-27 17:00 | 10d |  | 0 | 0 | 298.47 | 23877.6001 | 23877.6001 | 2013-08-21 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 100% | Finished | 23877.6001 | 23877.6001 | 100 | 80 | 100 | 100 | 80 | 100
135 | verhoogde vloer | 2013-08-28 08:00 | 2013-09-03 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-09-02 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 100% | Finished | 11938.8 | 11938.8 | 100 | 100 | 100 | 100 | 100 | 100
136 | HVAC toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-09 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
137 | Elektriciteit toestellen plafond | 2013-09-04 08:00 | 2013-09-09 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-09 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
138 | Binnenschrijnwerk | 2013-09-10 08:00 | 2013-09-16 17:00 | 5d |  | 0 | 0 | 1688.6801 | 67547.2021 | 67547.2021 | 2013-09-13 08:00 | 5d | 67547.2021 | 0 | 0 | 0 | 0 | 67547.2021 | 0 | 100% | Finished | 67547.2021 | 67547.2021 | 100 | 100 | 100 | 100 | 100 | 100
139 | schilderwerken | 2013-09-17 08:00 | 2013-09-24 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-09-20 08:00 | 6d | 4454.4001 | 0 | 0 | 0 | 0 | 4454.4001 | 0 | 100% | Finished | 4454.4001 | 4454.4001 | 100 | 100 | 100 | 100 | 100 | 100
140 | plafondtegels | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-30 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
141 | tapijt | 2013-10-01 08:00 | 2013-10-07 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 2013-10-25 08:00 | 1h | 156.13 | 0 | 0 | -156.13 | 0 | 0 | 0 | 100% | Finished | 6245.2002 | 6245.2002 | 100 | 2.5 | 100 | 100 |  | 100
155 | gv landscape rechts | 2013-08-06 08:00 | 2013-10-17 17:00 | 53d |  |  | 0 |  |  | 101860.7995 |  | 55d 1h | [5 empty] | 94158.9593 |  | 100% |  | 101860.7995 | 101860.7995
143 | HVAC plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 2013-08-09 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 6190.7201 | 6190.7201 | 100 | 88.2353 | 100 | 100 | 88.2353 | 100
144 | Elektriciteit plafond | 2013-08-06 08:00 | 2013-08-28 17:00 | 17d |  | 0 | 0 | 45.52 | 6190.7201 | 6190.7201 | 2013-08-09 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 6190.7201 | 6190.7201 | 100 | 88.2353 | 100 | 100 | 88.2353 | 100
145 | Schilderwerk wanden | 2013-08-29 08:00 | 2013-09-02 17:00 | 3d |  | 0 | 0 | 92.8 | 2227.2001 | 2227.2001 | 2013-09-03 08:00 | 3d | 2227.2001 | 0 | 0 | 0 | 0 | 2227.2001 | 0 | 100% | Finished | 2227.2001 | 2227.2001 | 100 | 100 | 100 | 100 | 100 | 100
146 | structuur valse plafond | 2013-09-03 08:00 | 2013-09-05 17:00 | 3d |  | 0 | 0 | 45.52 | 1092.48 | 1092.48 | 2013-09-06 08:00 | 3d | 1092.48 | 0 | 0 | 0 | 0 | 1092.48 | 0 | 100% | Finished | 1092.48 | 1092.48 | 100 | 100 | 100 | 100 | 100 | 100
147 | elektriciteit vloer | 2013-09-06 08:00 | 2013-09-17 17:00 | 8d |  | 0 | 0 | 298.47 | 19102.0801 | 19102.0801 | 2013-09-27 08:00 | 8d | 19102.0801 | 0 | 0 | 0 | 0 | 19102.0801 | 0 | 100% | Finished | 19102.0801 | 19102.0801 | 100 | 100 | 100 | 100 | 100 | 100
148 | verhoogde vloer | 2013-09-18 08:00 | 2013-09-24 17:00 | 5d |  | 0 | 0 | 298.47 | 11938.8 | 11938.8 | 2013-10-09 08:00 | 5d | 11938.8 | 0 | 0 | 0 | 0 | 11938.8 | 0 | 100% | Finished | 11938.8 | 11938.8 | 100 | 100 | 100 | 100 | 100 | 100
149 | HVAC toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-11 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
150 | Elektriciteit toestellen plafond | 2013-09-25 08:00 | 2013-09-30 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-11 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
151 | Binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-02 17:00 | 2d |  | 0 | 0 | 2688.6799 | 43018.8789 | 43018.8789 | 2013-09-17 08:00 | 2d | 43018.8789 | 0 | 0 | 0 | 0 | 43018.8789 | 0 | 100% | Finished | 43018.8789 | 43018.8789 | 100 | 100 | 100 | 100 | 100 | 100
152 | Schilderwerk | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 92.8 | 1484.8 | 1484.8 | 2013-09-19 08:00 | 2d | 1484.8 | 0 | 0 | 0 | 0 | 1484.8 | 0 | 100% | Finished | 1484.8 | 1484.8 | 100 | 100 | 100 | 100 | 100 | 100
153 | plafondtegels | 2013-10-07 08:00 | 2013-10-10 17:00 | 4d |  | 0 | 0 | 45.52 | 1456.64 | 1456.64 | 2013-09-23 08:00 | 4d | 1456.64 | 0 | 0 | 0 | 0 | 1456.64 | 0 | 100% | Finished | 1456.64 | 1456.64 | 100 | 100 | 100 | 100 | 100 | 100
154 | tapijt | 2013-10-11 08:00 | 2013-10-17 17:00 | 5d |  | 0 | 0 | 156.13 | 6245.2002 | 6245.2002 | 2013-10-25 08:00 | 1h | 156.13 | 0 | 0 | -156.13 | 0 | 0 | 0 | 100% | Finished | 6245.2002 | 6245.2002 | 100 | 2.5 | 100 | 100 |  | 100
162 | overige delen gv | 2013-06-27 08:00 | 2013-10-22 17:00 | 84d |  |  | 0 |  |  | 142447.6841 |  | 62d | [5 empty] | 127797.1237 |  | 100% |  | 142447.6841 | 142447.6841
156 | schilderwerk | 2013-06-27 08:00 | 2013-08-19 17:00 | 38d |  | 0 | 0 | 92.8 | 28211.2009 | 28211.2009 | 2013-08-01 08:00 | 20d | 14848.0005 | 0 | 0 | 0 | 0 | 14848.0005 | 0 | 100% | Finished | 28211.2009 | 28211.2009 | 100 | 52.6316 | 100 | 100 | 52.6316 | 100
157 | HVAC plafond | 2013-08-20 08:00 | 2013-09-09 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-09-02 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
158 | Elektriciteit plafond | 2013-09-10 08:00 | 2013-09-30 17:00 | 15d |  | 0 | 0 | 45.52 | 5462.4001 | 5462.4001 | 2013-09-23 08:00 | 15d | 5462.4001 | 0 | 0 | 0 | 0 | 5462.4001 | 0 | 100% | Finished | 5462.4001 | 5462.4001 | 100 | 100 | 100 | 100 | 100 | 100
159 | binnenschrijnwerk | 2013-10-01 08:00 | 2013-10-09 17:00 | 7d |  | 0 | 0 | 1688.6801 | 94566.083 | 94566.083 | 2013-10-14 08:00 | 7d | 94566.083 | 0 | 0 | 0 | 0 | 94566.083 | 0 | 100% | Finished | 94566.083 | 94566.083 | 100 | 100 | 100 | 100 | 100 | 100
160 | gyproc werken | 2013-09-17 08:00 | 2013-10-14 17:00 | 20d |  | 0 | 0 | 26.82 | 4291.2 | 4291.2 | 2013-09-30 08:00 | 14d | 3003.84 | 0 | 0 | 0 | 0 | 3003.84 | 0 | 100% | Finished | 4291.2 | 4291.2 | 100 | 70 | 100 | 100 | 70 | 100
161 | Schilderwerken | 2013-10-15 08:00 | 2013-10-22 17:00 | 6d |  | 0 | 0 | 92.8 | 4454.4001 | 4454.4001 | 2013-10-18 08:00 | 6d | 4454.4001 | 0 | 0 | 0 | 0 | 4454.4001 | 0 | 100% | Finished | 4454.4001 | 4454.4001 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
11/12, 2012 | 2012-10-29 08:00 | 2012-12-11 17:00 | 66790.8005 | 74554.5746 | 60167.1203 | 2012-12-18 14:00 | 7763.7742 | 111.6% | 14387.4543 | 123.9% | 4d 5h | 114.5% | 99.78% | 2013-10-22 09:00 | 2013-09-16 10:00 | 2013-07-15 15:00 | 2013-10-17 10:00 | 2013-09-16 10:00 | 2013-07-23 17:00 | 2013-10-16 11:00 | 2013-09-06 12:00 | 2013-07-17 11:00 | 2229703.2853 | 1811028.7415 | 2003777.6607 | 1955734.5545 | 1628701.9789 | 1589930.175 | 1846458.2346 | 1838175.0276 | 1.1445 | 1.2391 | 1.1162 | 0.99781 | 4.625 | 1.2391 | 1 | 1.1445 | 1
24/01, 2013 | 2012-12-11 17:00 | 2013-01-24 17:00 | 463759.6817 | 102786.4796 | 77307.9199 | 2013-01-08 14:00 | -360973.2021 | 22.16% | 25478.5597 | 133% | -12d 3h | 80.66% | 97.94% | 2013-12-19 11:00 | 2017-04-07 12:00 | 2016-03-02 09:00 | 2013-12-31 16:00 | 2017-04-07 12:00 | 2016-03-23 17:00 | 2013-11-08 11:00 | 2014-01-16 14:00 | 2013-10-21 12:00 | 2218612.1799 | 1687828.8644 | 9738603.7088 | 2731903.0316 | 7343776.0765 | 2073885.9431 | 2009918.4116 | 1825331.2663 | 0.80664 | 1.3296 | 0.22164 | 0.97944 | -12.375 | 1.3296 | 1 | 0.80664 | 1
11/03, 2013 | 2013-01-24 17:00 | 2013-03-11 17:00 | 723746.9832 | 611796.6853 | 375237.6816 | 2013-02-20 15:00 | -111950.2979 | 84.53% | 236559.0037 | 163% | -13d 2h | 86.2% | 100% | 2013-11-08 16:00 | 2013-12-26 17:00 | 2013-07-16 12:00 | 2013-11-12 16:00 | 2013-12-26 17:00 | 2013-09-05 14:00 | 2013-11-11 10:00 | 2013-12-19 09:00 | 2013-08-30 17:00 | 2007531.736 | 1376384.3884 | 2306218.8817 | 2268896.0407 | 1559580.3337 | 1536688.8459 | 1483077.0086 | 1480577.2532 | 0.86198 | 1.6304 | 0.84532 | 1 | -13.25 | 1.6304 | 1 | 0.86198 | 1
24/04, 2013 | 2013-03-11 17:00 | 2013-04-24 17:00 | 988580.7058 | 959188.0157 | 611809.5234 | 2013-04-19 14:00 | -29392.6901 | 97.03% | 347378.4923 | 156.8% | -3d 3h | 97.36% | 98.61% | 2013-10-28 11:00 | 2013-11-01 16:00 | 2013-06-20 17:00 | 2013-10-28 15:00 | 2013-11-01 16:00 | 2013-08-26 10:00 | 2013-10-28 11:00 | 2013-10-31 17:00 | 2013-08-23 15:00 | 1896712.2473 | 1431373.2693 | 1936085.9124 | 1931509.0112 | 1456487.4105 | 1453568.0749 | 1498998.9924 | 1498586.9149 | 0.97363 | 1.5678 | 0.97027 | 0.98608 | -3.375 | 1.5678 | 1 | 0.97363 | 1
06/06, 2013 | 2013-04-24 17:00 | 2013-06-06 17:00 | 1407361.6074 | 1090007.566 | 795003.712 | 2013-05-02 17:00 | -317354.0414 | 77.45% | 295003.854 | 137.1% | -25d | 84.28% | 93.84% | 2013-12-12 11:00 | 2014-02-04 16:00 | 2013-10-01 17:00 | 2013-12-11 16:00 | 2014-02-04 16:00 | 2013-11-29 17:00 | 2013-11-26 17:00 | 2013-12-27 17:00 | 2013-11-04 12:00 | 1949086.8856 | 1636741.3619 | 2285096.4425 | 2164400.9105 | 1881811.9956 | 1793781.9682 | 1716973.0836 | 1707025.8949 | 0.84277 | 1.3711 | 0.7745 | 0.93835 | -25 | 1.3711 | 1 | 0.84277 | 1
19/07, 2013 | 2013-06-06 17:00 | 2013-07-19 17:00 | 1550527.8499 | 1460018.3371 | 1221194.3513 | 2013-06-28 15:00 | -90509.5128 | 94.16% | 238823.9858 | 119.6% | -15d 2h | 91.97% | 92.87% | 2013-11-06 11:00 | 2013-11-13 16:00 | 2013-09-12 10:00 | 2013-11-07 09:00 | 2013-11-13 16:00 | 2013-10-25 11:00 | 2013-11-13 10:00 | 2013-11-22 11:00 | 2013-11-01 15:00 | 2005266.7538 | 1877011.3123 | 2053873.0002 | 2073690.8118 | 1917666.7425 | 1934242.8354 | 1906106.5027 | 1908735.8592 | 0.91974 | 1.1956 | 0.94163 | 0.92872 | -15.25 | 1.1956 | 1 | 0.91974 | 1
03/09, 2013 | 2013-07-19 17:00 | 2013-09-03 17:00 | 1839603.0514 | 1881917.3728 | 1519412.2766 | 2013-09-10 16:00 | 42314.3214 | 102.3% | 362505.0962 | 123.9% | 4d 7h | 102.2% | 97.56% | 2013-10-16 09:00 | 2013-10-15 10:00 | 2013-08-07 16:00 | 2013-10-15 16:00 | 2013-10-15 10:00 | 2013-10-07 14:00 | 2013-10-16 09:00 | 2013-10-15 12:00 | 2013-10-07 15:00 | 1881585.6435 | 1811821.852 | 1873442.289 | 1873803.4058 | 1805247.1145 | 1805538.671 | 1822367.9997 | 1822420.8429 | 1.022 | 1.2386 | 1.023 | 0.97559 | 4.875 | 1.2386 | 1 | 1.022 | 1
17/10, 2013 | 2013-09-03 17:00 | 2013-10-17 17:00 | 2241863.5395 | 2175895.37 | 1823813.5621 | 2013-10-04 14:00 | -65968.1696 | 97.06% | 352081.8079 | 119.3% | -9d 3h | 96.31% | 99.3% | 2013-11-01 12:00 | 2013-11-01 15:00 | 2013-09-03 17:00 | 2013-11-01 12:00 | 2013-11-01 15:00 | 2013-10-30 17:00 | 2013-11-05 11:00 | 2013-11-05 16:00 | 2013-11-01 15:00 | 1892008.9317 | 1880974.2334 | 1894076.4593 | 1894622.4487 | 1882707.2141 | 1883164.8569 | 1883188.618 | 1883266.0953 | 0.96309 | 1.193 | 0.97057 | 0.99299 | -9.375 | 1.193 | 1 | 0.96309 | 1
Actual Schedule | 2013-10-17 17:00 | 2013-11-20 17:00 | 2244090.7396 | 2237845.5394 | 1868796.2835 | 2013-10-16 15:00 | -6245.2002 | 99.72% | 369049.2559 | 119.7% | -25d 2h | 90.92% | 99.72% | 2013-10-23 15:00 | 2013-10-23 15:00 | 2013-08-26 10:00 | 2013-11-21 15:00 | 2013-11-21 15:00 | 2013-11-21 14:00 | 2013-11-27 10:00 | 2013-11-27 14:00 | 2013-11-26 16:00 | 1875041.4837 | 1874011.5706 | 1875058.9123 | 1875665.386 | 1874026.125 | 1874532.5834 | 1874192.0445 | 1874275.4028 | 0.90917 | 1.1975 | 0.99722 | 0.99721 | -25.25 | 1.1975 | 1 | 0.90917 | 1