## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Industrial Complex (2) | 1 |  |  | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 | 414.375
6 | Voobereindende werken | 1.1 |  |  | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 | 35.375
1 | plaatsen werfhekkens | 1.1.1 |  | FS2-1d | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 0.375
2 | Afbraakwerken | 1.1.2 | 1FS-1d | FS3;FS4-1d;FS8 | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 3.375
3 | Werfinrichting | 1.1.3 | 2FS |  | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 0.375
4 | uitzetten assen | 1.1.4 | 2FS-1d | FS5;FS7;FS8 | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 0.375
5 | Fundering torenkraan | 1.1.5 | 4FS;14FS-2w |  | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 0.375
13 | Riolering + Parkings | 1.2 |  |  | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 | 25.375
7 | droogzuiging | 1.2.1 | 4FS | FS9+1w | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 0.375
8 | Rechterdeel parking aanvullen + onderfundering | 1.2.2 | 4FS;2FS |  | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 6.375
9 | Plaatsing RW-putten + riolering | 1.2.3 | 7FS+1w | FS10-1w | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 11.375
10 | Linkerdeel parking aanvullen + onderfundering | 1.2.4 | 9FS-1w | FS11-3d;FS12 | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 4.375
11 | Overige parkeerplaatsen aanvullen + onderfundering | 1.2.5 | 10FS-3d | FS12;FS14 | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2.375
12 | Uitbraak bestaande parking | 1.2.6 | 10FS;11FS |  | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 1.375
39 | Productiehal | 1.3 |  |  | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 | 194.375
14 | Funderingswerken productiehal | 1.3.1 | 11FS | FS5-2w;FS15;SS34-3d;FS41;FS81 | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 18.375
26 | Ruwbouwwerken + onder dak productiehal | 1.3.2 |  |  | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 | 80.375
15 | Kolommen + balken + betonwanden + staalconstructie dak | 1.3.2.1 | 14FS | SS16+3w 2d;SS17-4d;FS18-2d;FS19-4d;FS20;FS40-2w 3d;FS42 | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 32.375
16 | Metselwerken technische lokalen + montage welfsels | 1.3.2.2 | 15SS+3w 2d |  | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 9.375
17 | uitbraak bestaande gevelelementen + schoring | 1.3.2.3 | 15SS-4d |  | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 6.375
18 | staalconstructie rolbrug en spuitcabine | 1.3.2.4 | 15FS-2d | FS19-2d;FS20 | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 6.375
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 1.3.2.5 | 15FS-4d;18FS-2d | FS23-1w | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 15.375
20 | Veiligheidsnetten + steeldeck | 1.3.2.6 | 15FS;18FS | FS21-1w 2d | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 16.375
21 | Isolatie + dakbedekking + RWA | 1.3.2.7 | 20FS-1w 2d | FS22-1d | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 20.375
22 | Rookkoepels | 1.3.2.8 | 21FS-1d |  | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 1.375
23 | Netwapening + polybetonvloer | 1.3.2.9 | 19FS-1w | FS24+3d;FS25+3d;FS30;FS31+6w | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 13.375
24 | Metselwerken | 1.3.2.10 | 23FS+3d | FS27 | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 4.375
25 | Brandwerende schildering | 1.3.2.11 | 23FS+3d |  | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 4.375
29 | Binnenafwerking productiehal | 1.3.3 |  |  | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 | 5.375
27 | Stalen binnentrap | 1.3.3.1 | 24FS;87FS+6w |  | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 4.375
28 | Binnendeuren | 1.3.3.2 | 87FS;35FS-2w |  | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 0.375
33 | Gevelbekleding productiehal | 1.3.4 |  |  | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 | 85.375
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 1.3.4.1 | 23FS |  | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 13.375
31 | Montage poorten | 1.3.4.2 | 23FS+6w | FS32 | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 | 3.375
32 | Gevelbekleding metaalcassettes | 1.3.4.3 | 31FS |  | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 13.375
38 | Technieken productiehal | 1.3.5 |  |  | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 | 176.375
34 | Afbraakwerken | 1.3.5.1 | 14SS-3d |  | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 1.375
35 | HVAC | 1.3.5.2 |  | FS28-2w | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 73.375
36 | Sanitair | 1.3.5.3 |  |  | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 73.375
37 | Elecktriciteit | 1.3.5.4 |  |  | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 73.375
60 | Stockruimte | 1.4 |  |  | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 | 194.375
40 | Afbraak | 1.4.1 | 15FS-2w 3d | FS41;FS55-1d | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 6.375
41 | Funderingswerken stockruimte | 1.4.2 | 40FS;14FS | FS42;FS61;FS81 | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 7.375
51 | Ruwbouwwerken + onder dak stockruimte | 1.4.3 |  |  | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 | 85.375
42 | Kolommen + balken + betonwanden + staalconstructie dak | 1.4.3.1 | 41FS;15FS | SS43-2d;FS44;FS45;FS63 | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 12.375
43 | Uitbraak bestaande gevelelementen | 1.4.3.2 | 42SS-2d |  | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 0.375
44 | Nivelleren + rioleringswerken | 1.4.3.3 | 42FS | FS45-1w | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 0.375
45 | Onderfundering betonvloer + vloerisolatie rondom | 1.4.3.4 | 44FS-1w;42FS | FS46;FS49-2d | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 7.375
46 | Veiligheidsnetten + steeldeck | 1.4.3.5 | 45FS | FS47;FS48 | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 6.375
47 | Paaltjes leeflijn | 1.4.3.6 | 46FS | FS48 | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 0.375
48 | Isolatie + dakbedeking + RWA | 1.4.3.7 | 46FS;47FS | FS49 | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 9.375
49 | Netbewapening + polybetonvloer | 1.4.3.8 | 45FS-2d;48FS | FS50+1w;FS52+6w;FS53+5w 4d | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 8.375
50 | Brandwerende schildering | 1.4.3.9 | 49FS+1w |  | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2.375
54 | Gevelbekledingen stockruimte | 1.4.4 |  |  | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 | 2.375
52 | Alu buitenschrijnwerk + beglazing | 1.4.4.1 | 49FS+6w |  | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 0.375
53 | Montage poorten | 1.4.4.2 | 49FS+5w 4d | FS80 | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 | 2.375
59 | technieken stockruimte | 1.4.5 |  |  | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 | 188.375
55 | Afbraakwerken | 1.4.5.1 | 40FS-1d |  | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 0.375
56 | HVAC | 1.4.5.2 |  |  | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 | 42.375
57 | Sanitair | 1.4.5.3 |  |  | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 | 42.375
58 | Elektriciteit | 1.4.5.4 |  |  | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 | 84.375
79 | Straalcabine | 1.5 |  |  | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 | 106.375
61 | Funderingswerken | 1.5.1 | 41FS | FS62 | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 5.375
67 | Ruwbouwwerken + straalcabine | 1.5.2 |  |  | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 | 31.375
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 1.5.2.1 | 61FS | SS74-1d | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 1.375
63 | Kolommen + balken + betonwanden + staalconstructie | 1.5.2.2 | 42FS | FS64 | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 5.375
64 | Welfsels + opstort | 1.5.2.3 | 63FS | FS71;FS72 | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 0.375
65 | Netwapening + polybetonvloer | 1.5.2.4 | 72FS | FS66+3d;FS68+6w;FS69+6w | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 1.375
66 | Brandwerende schildering | 1.5.2.5 | 65FS+3d |  | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 0.375
70 | Gevelbekledingen straalcabine | 1.5.3 |  |  | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 | 0.375
68 | Alu buitenschrijnwerk + beglazing | 1.5.3.1 | 65FS+6w |  | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 0.375
69 | Montage poorten | 1.5.3.2 | 65FS+6w |  | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 0.375
73 | Dakwerken | 1.5.4 |  |  | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 | 5.375
72 | Isolatie + roofing | 1.5.4.1 | 64FS;71FS | FS65 | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 4.375
71 | paaltjes leeflijn | 1.5.4.2 | 64FS | FS72 | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 0.375
78 | Technieken straalcabine | 1.5.5 |  |  | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 | 101.375
77 | Elektriciteit | 1.5.5.1 |  |  | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 66.375
74 | Afbraakwerken | 1.5.5.2 | 62SS-1d |  | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 0.375
75 | HVAC | 1.5.5.3 |  |  | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 66.375
76 | Sanitair | 1.5.5.4 |  |  | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 66.375
80 | Opkuis | 1.6 | 53FS |  | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 | 8.375
83 | Funderingswerken kantoor | 1.7 |  |  | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 | 23.375
81 | Funderingswerken kantoor | 1.7.1 | 14FS;41FS | FS82-1w;FS84 | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 20.375
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 1.7.2 | 81FS-1w | FS84-2d | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 9.375
88 | Ruwbouw kantoor niv 0 | 1.8 |  |  | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 | 29.375
84 | Vloerplaat gelijkvloers | 1.8.1 | 81FS;82FS-2d | FS85;FS86 | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 6.375
85 | Kolommen + balken gelijkvloers | 1.8.2 | 84FS | FS87-3d | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 15.375
86 | Metselwerken gelijkvloers | 1.8.3 | 84FS | FS87-1w 1d | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 19.375
87 | Afdek 0 + wapenen + opstort | 1.8.4 | 86FS-1w 1d;85FS-3d | FS27+6w;FS28;FS89;FS90;FS94+8w | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 9.375
92 | Ruwbouw kantoor niv +1 | 1.9 |  |  | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 | 29.375
89 | Kolommen + balken 1ste | 1.9.1 | 87FS | FS91 | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 15.375
90 | Metselwerken 1ste | 1.9.2 | 87FS | FS91 | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 13.375
91 | Afdek 1 + wapenen + opstort | 1.9.3 | 89FS;90FS | FS93;FS95;FS153 | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 9.375
93 | Metselwerken dakplaat | 1.10 | 91FS | FS98;FS159 | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 4.375
97 | Gevelbekledingen kantoor | 1.11 |  |  | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 | 57.375
94 | Buitenschrijnwerk + beglazing gelijkvloers | 1.11.1 | 87FS+8w | FS96;FS104-1w 1d | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 | 15.375
95 | Buitenschrijnwerk + beglazing 1ste | 1.11.2 | 91FS | FS96;FS124 | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 13.375
96 | Gevelbekleding metaalcasettes | 1.11.3 | 94FS;95FS |  | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 11.375
102 | Dakwerken kantoor | 1.12 |  |  | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 | 28.375
98 | Hellingsbeton | 1.12.1 | 93FS;153FS | FS99+1w | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 0.375
99 | isolatie + dakbedekking + ballast | 1.12.2 | 98FS+1w | FS100-2d;FS101;FS103;FS104;FS124 | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 | 13.375
100 | RW-afvoeren | 1.12.3 | 99FS-2d |  | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 | 3.375
101 | Lichtstraat | 1.12.4 | 99FS |  | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 | 6.375
123 | Niv 0 | 1.13 |  |  | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 | 172.375
103 | Cementage | 1.13.1 | 99FS;104FS |  | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 0.375
104 | Pleisterwerken | 1.13.2 | 99FS;124FS;94FS-1w 1d | FS103;FS105;SS144-2w;SS149-2w;SS155-2w | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 13.375
105 | Uitvullingslaag polystyreenkorrels | 1.13.3 | 104FS | FS106 | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 0.375
106 | Vloerisolatie PU platen | 1.13.4 | 105FS | FS107 | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 4.375
107 | Chape | 1.13.5 | 106FS | FS108+2d | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 6.375
108 | Polybetonvloer | 1.13.6 | 107FS+2d | FS109+6w;FS110+1d | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 0.375
109 | Stalen trappen kantoor | 1.13.7 | 108FS+6w |  | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 | 9.375
110 | Lichte scheidingswanden en voorzetwanden | 1.13.8 | 108FS+1d | FS111;FS113;FS114 | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 13.375
111 | Vloerbekleding keramische tegels | 1.13.9 | 110FS | FS112 | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2.375
112 | Faience | 1.13.10 | 111FS |  | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 13.375
113 | Binnendeuren en binnenramen | 1.13.11 | 110FS | FS114;FS115 | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 13.375
114 | Zichtwanden op binnenwanden | 1.13.12 | 110FS;113FS | FS115 | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 8.375
115 | Vast meubilair | 1.13.13 | 113FS;114FS | FS116 | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 6.375
116 | Plafonds | 1.13.14 | 115FS | FS117;SS146-5w 4d;SS151-5w;SS157-5w | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 15.375
117 | Vloerbekleding tapijt | 1.13.15 | 116FS | FS118 | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2.375
118 | Plinten | 1.13.16 | 117FS | FS119 | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 4.375
119 | Schilderwerken | 1.13.17 | 118FS | FS120 | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 | 22.375
120 | Binnenzonnewering | 1.13.18 | 119FS | FS121;FS122 | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 1.375
121 | Allerhande aanwerkingen | 1.13.19 | 120FS | FS122 | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 11.375
122 | Opkuis | 1.13.20 | 120FS;121FS | SS141 | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 8.375
142 | Niv +1 | 1.14 |  |  | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 | 181.375
124 | Pleisterwerken | 1.14.1 | 99FS;95FS | FS104;FS125;SS143-2w;SS148-2w;SS154-2w | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 5.375
125 | Pur uitvullingslaag | 1.14.2 | 124FS | FS126 | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 0.375
126 | Chape | 1.14.3 | 125FS | FS127+2d;FS128 | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 6.375
127 | Polybetonvloer | 1.14.4 | 126FS+2d | FS128 | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 0.375
128 | Lichte scheidingswanden en voorzetwanden | 1.14.5 | 126FS;127FS | FS129;FS130;FS131 | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 | 21.375
129 | Vloerbekleding keramische tegels | 1.14.6 | 128FS |  | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 4.375
130 | Faience | 1.14.7 | 128FS;135FS |  | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 3.375
131 | Binnendeuren en binnenramen | 1.14.8 | 128FS | FS132;FS133 | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 13.375
132 | Zichtwanden op binnenwanden | 1.14.9 | 131FS | FS133 | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 8.375
133 | Vast meubilair | 1.14.10 | 131FS;132FS | FS134 | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 4.375
134 | Plafonds | 1.14.11 | 133FS | FS135;SS145-3w;SS150-3w;SS156-3w | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 15.375
135 | Vloerbekleding tapijt | 1.14.12 | 134FS | FS130;FS136;FS137;FS138 | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 8.375
136 | Plinten | 1.14.13 | 135FS |  | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 4.375
137 | Borstweringen | 1.14.14 | 135FS |  | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 5.375
138 | Schilderwerken | 1.14.15 | 135FS | FS139 | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 | 24.375
139 | Binnenzonneweringen en gordijnen | 1.14.16 | 138FS | FS140 | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 1.375
140 | Allerhande aanwerkingen | 1.14.17 | 139FS | FS141 | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 13.375
141 | Opkuis | 1.14.18 | 140FS;122SS |  | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 8.375
147 | HVAC | 1.15 |  |  | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 | 119.375
143 | Leidingen in vloeren en wanden 1ste | 1.15.1 | 124SS-2w |  | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 | 13.375
144 | Leidingen in vloeren en wanden gelijkvloers | 1.15.2 | 104SS-2w |  | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 | 13.375
145 | Leidingen in plafonds 1ste | 1.15.3 | 134SS-3w |  | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 | 18.375
146 | Leidingen in plafonds gelijkvloers | 1.15.4 | 116SS-5w 4d |  | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 | 34.375
152 | Sanitair | 1.16 |  |  | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 | 119.375
148 | Leidingen in vloeren en wanden 1ste | 1.16.1 | 124SS-2w |  | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 | 13.375
149 | Leidingen in vloeren en wanden gelijkvloers | 1.16.2 | 104SS-2w |  | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 | 13.375
150 | Leidingen in plafonds 1ste | 1.16.3 | 134SS-3w |  | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 | 18.375
151 | Leidingen in plafonds gelijkvloers | 1.16.4 | 116SS-5w |  | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 | 34.375
158 | Elektriciteit | 1.17 |  |  | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 | 139.375
153 | Leidingen op dakplaat | 1.17.1 | 91FS | FS98 | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 | 4.375
154 | Leidingen in vloeren en wanden 1ste | 1.17.2 | 124SS-2w |  | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 13.375
155 | Leidingen in vloeren en wanden gelijkvloers | 1.17.3 | 104SS-2w |  | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 13.375
156 | Leidingen in plafonds 1ste | 1.17.4 | 134SS-3w |  | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 | 18.375
157 | Leidingen in plafonds gelijkvloers | 1.17.5 | 116SS-5w |  | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 | 34.375
161 | Bestaande loods | 1.18 |  |  | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 | 23.375
159 | Kolommen + balken + welfsels | 1.18.1 | 93FS | FS160 | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 7.375
160 | Metselwerken | 1.18.2 | 159FS | FS163 | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 15.375
162 | Bestaande kantoren | 1.19 |  |  | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 | 55.375
166 | Omgevingswerken | 1.20 |  |  | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 | 179.375
163 | Laadkade | 1.20.1 | 160FS | FS164+6w | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 | 20.375
164 | Dockleveler | 1.20.2 | 163FS+6w |  | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 | 1.375
165 | Buitenaanleg | 1.20.3 |  |  | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 | 48.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Industrial Complex (2) | 2376h |  |  |  |  | 99 | 100 | 101
6 | Voobereindende werken | 208h |  |  |  |  | 99 | 100 | 101
1 | plaatsen werfhekkens | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Afbraakwerken | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Werfinrichting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | uitzetten assen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Fundering torenkraan | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Riolering + Parkings | 144h |  |  |  |  | 99 | 100 | 101
7 | droogzuiging | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Rechterdeel parking aanvullen + onderfundering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Plaatsing RW-putten + riolering | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Linkerdeel parking aanvullen + onderfundering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Overige parkeerplaatsen aanvullen + onderfundering | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Uitbraak bestaande parking | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Productiehal | 1112h |  |  |  |  | 99 | 100 | 101
14 | Funderingswerken productiehal | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Ruwbouwwerken + onder dak productiehal | 472h |  |  |  |  | 99 | 100 | 101
15 | Kolommen + balken + betonwanden + staalconstructie dak | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Metselwerken technische lokalen + montage welfsels | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | uitbraak bestaande gevelelementen + schoring | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | staalconstructie rolbrug en spuitcabine | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Veiligheidsnetten + steeldeck | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Isolatie + dakbedekking + RWA | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Rookkoepels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Netwapening + polybetonvloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Metselwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Brandwerende schildering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Binnenafwerking productiehal | 32h |  |  |  |  | 99 | 100 | 101
27 | Stalen binnentrap | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Binnendeuren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Gevelbekleding productiehal | 496h |  |  |  |  | 99 | 100 | 101
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Montage poorten | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Gevelbekleding metaalcassettes | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Technieken productiehal | 1016h |  |  |  |  | 99 | 100 | 101
34 | Afbraakwerken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | HVAC | 432h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Sanitair | 432h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Elecktriciteit | 432h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Stockruimte | 1112h |  |  |  |  | 99 | 100 | 101
40 | Afbraak | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Funderingswerken stockruimte | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Ruwbouwwerken + onder dak stockruimte | 496h |  |  |  |  | 99 | 100 | 101
42 | Kolommen + balken + betonwanden + staalconstructie dak | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Uitbraak bestaande gevelelementen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Nivelleren + rioleringswerken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Onderfundering betonvloer + vloerisolatie rondom | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Veiligheidsnetten + steeldeck | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Paaltjes leeflijn | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Isolatie + dakbedeking + RWA | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Netbewapening + polybetonvloer | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Brandwerende schildering | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Gevelbekledingen stockruimte | 24h |  |  |  |  | 99 | 100 | 101
52 | Alu buitenschrijnwerk + beglazing | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Montage poorten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | technieken stockruimte | 1080h |  |  |  |  | 99 | 100 | 101
55 | Afbraakwerken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | HVAC | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Sanitair | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Elektriciteit | 488h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | Straalcabine | 616h |  |  |  |  | 99 | 100 | 101
61 | Funderingswerken | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Ruwbouwwerken + straalcabine | 192h |  |  |  |  | 99 | 100 | 101
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Kolommen + balken + betonwanden + staalconstructie | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Welfsels + opstort | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Netwapening + polybetonvloer | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Brandwerende schildering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | Gevelbekledingen straalcabine | 8h |  |  |  |  | 99 | 100 | 101
68 | Alu buitenschrijnwerk + beglazing | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Montage poorten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | Dakwerken | 32h |  |  |  |  | 99 | 100 | 101
72 | Isolatie + roofing | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | paaltjes leeflijn | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | Technieken straalcabine | 592h |  |  |  |  | 99 | 100 | 101
77 | Elektriciteit | 392h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Afbraakwerken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | HVAC | 392h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | Sanitair | 392h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | Opkuis | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Funderingswerken kantoor | 144h |  |  |  |  | 99 | 100 | 101
81 | Funderingswerken kantoor | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | Ruwbouw kantoor niv 0 | 176h |  |  |  |  | 99 | 100 | 101
84 | Vloerplaat gelijkvloers | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | Kolommen + balken gelijkvloers | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | Metselwerken gelijkvloers | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | Afdek 0 + wapenen + opstort | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | Ruwbouw kantoor niv +1 | 176h |  |  |  |  | 99 | 100 | 101
89 | Kolommen + balken 1ste | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | Metselwerken 1ste | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | Afdek 1 + wapenen + opstort | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Metselwerken dakplaat | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | Gevelbekledingen kantoor | 336h |  |  |  |  | 99 | 100 | 101
94 | Buitenschrijnwerk + beglazing gelijkvloers | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | Buitenschrijnwerk + beglazing 1ste | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | Gevelbekleding metaalcasettes | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | Dakwerken kantoor | 168h |  |  |  |  | 99 | 100 | 101
98 | Hellingsbeton | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | isolatie + dakbedekking + ballast | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | RW-afvoeren | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | Lichtstraat | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | Niv 0 | 984h |  |  |  |  | 99 | 100 | 101
103 | Cementage | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | Pleisterwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | Uitvullingslaag polystyreenkorrels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | Vloerisolatie PU platen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | Polybetonvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | Stalen trappen kantoor | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | Lichte scheidingswanden en voorzetwanden | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | Vloerbekleding keramische tegels | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | Faience | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | Binnendeuren en binnenramen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | Zichtwanden op binnenwanden | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | Vast meubilair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | Plafonds | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | Vloerbekleding tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | Plinten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | Schilderwerken | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | Binnenzonnewering | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | Allerhande aanwerkingen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | Opkuis | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | Niv +1 | 1040h |  |  |  |  | 99 | 100 | 101
124 | Pleisterwerken | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | Pur uitvullingslaag | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | Polybetonvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | Lichte scheidingswanden en voorzetwanden | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | Vloerbekleding keramische tegels | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | Faience | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | Binnendeuren en binnenramen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | Zichtwanden op binnenwanden | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | Vast meubilair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | Plafonds | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | Vloerbekleding tapijt | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | Plinten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | Borstweringen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | Schilderwerken | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | Binnenzonneweringen en gordijnen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | Allerhande aanwerkingen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | Opkuis | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | HVAC | 688h |  |  |  |  | 99 | 100 | 101
143 | Leidingen in vloeren en wanden 1ste | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | Leidingen in vloeren en wanden gelijkvloers | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | Leidingen in plafonds 1ste | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | Leidingen in plafonds gelijkvloers | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | Sanitair | 688h |  |  |  |  | 99 | 100 | 101
148 | Leidingen in vloeren en wanden 1ste | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | Leidingen in vloeren en wanden gelijkvloers | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | Leidingen in plafonds 1ste | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | Leidingen in plafonds gelijkvloers | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | Elektriciteit | 800h |  |  |  |  | 99 | 100 | 101
153 | Leidingen op dakplaat | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | Leidingen in vloeren en wanden 1ste | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | Leidingen in vloeren en wanden gelijkvloers | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | Leidingen in plafonds 1ste | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | Leidingen in plafonds gelijkvloers | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
161 | Bestaande loods | 144h |  |  |  |  | 99 | 100 | 101
159 | Kolommen + balken + welfsels | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | Metselwerken | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | Bestaande kantoren | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
166 | Omgevingswerken | 1024h |  |  |  |  | 99 | 100 | 101
163 | Laadkade | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | Dockleveler | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | Buitenaanleg | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-04-11 17:00 |  | TP Name | 11/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 39d | [5 empty] | 531720 |  | 6.188% |  | 371280.0015 | 309448
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 22d | [5 empty] | 94264 |  | 7.188% |  | 94264.0003 | 89464
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 4d | [5 empty] | 19200 |  | 3.81% |  | 19200.0003 | 14400
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 |  | 0 | 0 | 120000 | 25d | 0 | 0 | 0 | 120000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 |  | 0 | 0 | 38400 | 8d | 0 | 0 | 0 | 38400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 4d | 19200 | 4800 | 1d | 0 | 0 | 19200 | 4800 | 80% | Started | 19200.0003 | 14400 | 100 | 80 | 80 | 100 | 80 | 80
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 |  | 0 | 0 | 24000 | 5d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 |  | 0 | 0 | 62400 | 13d | 0 | 0 | 0 | 62400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 |  | 0 | 0 | 72000 | 15d | 0 | 0 | 0 | 72000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 |  | 0 | 0 | 9600 | 2d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 |  | 0 | 0 | 48000 | 10d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 |  | 0 | 0 | 24000 | 5d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 |  | 0 | 0 | 24000 | 5d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 |  | 0 | 0 | 15488 | 4d | 0 | 0 | 0 | 15488 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 22d | [5 empty] | 7504 |  | 1.189% |  | 7504 | 7504
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 |  | 0 | 0 | 311040 | 54d | 0 | 0 | 0 | 311040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 |  | 0 | 0 | 55728 | 54d | 0 | 0 | 0 | 55728 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 |  | 0 | 0 | 257040 | 54d | 0 | 0 | 0 | 257040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 19d | [5 empty] | 217472 |  | 7.127% |  | 57032.0012 | 0
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 18d | 202464 | 11248 | 1d | 0 | 0 | 202464 | 11248 | 94.74% | Started | 53280.0012 | 0 | 100 | 360 | 94.7368 | 100 | 360 | 94.7368
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 |  | 0 | 0 | 27024 | 6d | 0 | 0 | 0 | 27024 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 |  | 0 | 0 | 43200 | 9d | 0 | 0 | 0 | 43200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 |  | 0 | 0 | 28800 | 6d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 |  | 0 | 0 | 24000 | 5d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 |  | 0 | 0 | 38400 | 8d | 0 | 0 | 0 | 38400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 |  | 0 | 0 | 33600 | 7d | 0 | 0 | 0 | 33600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 |  | 0 | 0 | 14400 | 3d | 0 | 0 | 0 | 14400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 |  | 0 | 0 | 11616 | 3d | 0 | 0 | 0 | 11616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 13d | [5 empty] | 15008 |  | 0.7435% |  | 3752 | 0
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 0 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 |  | 0 | 0 | 178560 | 31d | 0 | 0 | 0 | 178560 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 |  | 0 | 0 | 31992 | 31d | 0 | 0 | 0 | 31992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 |  | 0 | 0 | 290360 | 61d | 0 | 0 | 0 | 290360 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 |  | 0 | 0 | 18016 | 4d | 0 | 0 | 0 | 18016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 |  | 0 | 0 | 9600 | 2d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 |  | 0 | 0 | 19200 | 4d | 0 | 0 | 0 | 19200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 |  | 0 | 0 | 9600 | 2d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 |  | 0 | 0 | 49992 | 3d | 0 | 0 | 0 | 49992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 |  | 0 | 0 | 16664 | 1d | 0 | 0 | 0 | 16664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 |  | 0 | 0 | 233240 | 49d | 0 | 0 | 0 | 233240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 |  | 0 | 0 | 3752 | 1d | 0 | 0 | 0 | 3752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 |  | 0 | 0 | 282240 | 49d | 0 | 0 | 0 | 282240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 |  | 0 | 0 | 50568 | 49d | 0 | 0 | 0 | 50568 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 |  | 0 | 0 | 1400 | 7d | 0 | 0 | 0 | 1400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 |  | 0 | 0 | 67560 | 15d | 0 | 0 | 0 | 67560 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 |  | 0 | 0 | 40000 | 8d | 0 | 0 | 0 | 40000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 |  | 0 | 0 | 24000 | 5d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 |  | 0 | 0 | 67200 | 14d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 |  | 0 | 0 | 38400 | 8d | 0 | 0 | 0 | 38400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 |  | 0 | 0 | 48000 | 10d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 |  | 0 | 0 | 38400 | 8d | 0 | 0 | 0 | 38400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 |  | 0 | 0 | 14400 | 3d | 0 | 0 | 0 | 14400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 |  | 0 | 0 | 46464 | 12d | 0 | 0 | 0 | 46464 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 |  | 0 | 0 | 16664 | 1d | 0 | 0 | 0 | 16664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 |  | 0 | 0 | 166640 | 10d | 0 | 0 | 0 | 166640 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 |  | 0 | 0 | 66656 | 4d | 0 | 0 | 0 | 66656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 |  | 0 | 0 | 83320 | 5d | 0 | 0 | 0 | 83320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 |  | 0 | 0 | 31232 | 8d | 0 | 0 | 0 | 31232 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 |  | 0 | 0 | 62464 | 16d | 0 | 0 | 0 | 62464 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 |  | 0 | 0 | 86400 | 15d | 0 | 0 | 0 | 86400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 |  | 0 | 0 | 144000 | 25d | 0 | 0 | 0 | 144000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 |  | 0 | 0 | 15480 | 15d | 0 | 0 | 0 | 15480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 |  | 0 | 0 | 25800 | 25d | 0 | 0 | 0 | 25800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 |  | 0 | 0 | 14280 | 3d | 0 | 0 | 0 | 14280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 |  | 0 | 0 | 71400 | 15d | 0 | 0 | 0 | 71400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 |  | 0 | 0 | 119000 | 25d | 0 | 0 | 0 | 119000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 |  | 0 | 0 | 28800 | 6d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 |  | 0 | 0 | 192000 | 40d | 0 | 0 | 0 | 192000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 |  | 0 | 0 | 28800 | 15d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 |  | 0 | 0 | 3840 | 2d | 0 | 0 | 0 | 3840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 |  | 0 | 0 | 67200 | 35d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-06-05 17:00 |  | TP Name | 05/06, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 78d | [5 empty] | 1048832 |  | 14.44% |  | 866592.0016 | 794376
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 61d | [5 empty] | 353464 |  | 26.95% |  | 353464.0014 | 353464
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 43d | [5 empty] | 278400 |  | 55.24% |  | 278400.0014 | 278400
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 100% | Finished | 120000 | 120000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 8d | 38400 | 19200 | 4d | 0 | 0 | 38400 | 19200 | 66.67% | Started | 38400.0011 | 38400 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 6d | 28800 | 33600 | 7d | 0 | 0 | 28800 | 33600 | 46.15% | Started | 28800.0001 | 28800 | 100 | 46.1538 | 46.1538 | 100 | 46.1538 | 46.1538
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 |  | 0 | 0 | 72000 | 15d | 0 | 0 | 0 | 72000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 |  | 0 | 0 | 9600 | 2d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 1d | 4800 | 43200 | 9d | 0 | 0 | 4800 | 43200 | 10% | Started | 4800.0001 | 4800 | 100 | 10 | 10 | 100 | 10 | 10
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 |  | 0 | 0 | 24000 | 5d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 |  | 0 | 0 | 24000 | 5d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 |  | 0 | 0 | 15488 | 4d | 0 | 0 | 0 | 15488 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 61d | [5 empty] | 7504 |  | 1.189% |  | 7504 | 7504
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 |  | 0 | 0 | 311040 | 54d | 0 | 0 | 0 | 311040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 |  | 0 | 0 | 55728 | 54d | 0 | 0 | 0 | 55728 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 |  | 0 | 0 | 257040 | 54d | 0 | 0 | 0 | 257040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 58d | [5 empty] | 312752 |  | 16.87% |  | 135016 | 135016
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 100% | Finished | 56240 | 56240 | 100 | 380 | 100 | 100 | 380 | 100
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 100% | Finished | 27024 | 27024 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 11d | [5 empty] | 48000 |  | 24.39% |  | 48000 | 48000
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 100% | Finished | 43200 | 43200 | 100 | 100 | 100 | 100 | 100 | 100
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 |  | 0 | 0 | 28800 | 6d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 |  | 0 | 0 | 24000 | 5d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 |  | 0 | 0 | 38400 | 8d | 0 | 0 | 0 | 38400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 |  | 0 | 0 | 33600 | 7d | 0 | 0 | 0 | 33600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 |  | 0 | 0 | 14400 | 3d | 0 | 0 | 0 | 14400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 |  | 0 | 0 | 11616 | 3d | 0 | 0 | 0 | 11616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 52d | [5 empty] | 15008 |  | 0.7435% |  | 3752 | 3752
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 3752 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 |  | 0 | 0 | 178560 | 31d | 0 | 0 | 0 | 178560 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 |  | 0 | 0 | 31992 | 31d | 0 | 0 | 0 | 31992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 |  | 0 | 0 | 290360 | 61d | 0 | 0 | 0 | 290360 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 17d | [5 empty] | 35872 |  | 4.417% |  | 31368 | 31368
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 100% | Finished | 18016 | 18016 | 100 | 125 | 100 | 100 | 125 | 100
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 11d | [5 empty] | 9600 |  | 20% |  | 9600 | 9600
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 |  | 0 | 0 | 19200 | 4d | 0 | 0 | 0 | 19200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 |  | 0 | 0 | 9600 | 2d | 0 | 0 | 0 | 9600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 |  | 0 | 0 | 4800 | 1d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 |  | 0 | 0 | 49992 | 3d | 0 | 0 | 0 | 49992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 |  | 0 | 0 | 16664 | 1d | 0 | 0 | 0 | 16664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 12d | [5 empty] | 3752 |  | 0.6585% |  | 3752 | 3752
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 |  | 0 | 0 | 233240 | 49d | 0 | 0 | 0 | 233240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 100% | Finished | 3752 | 3752 | 100 | 100 | 100 | 100 | 100 | 100
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 |  | 0 | 0 | 282240 | 49d | 0 | 0 | 0 | 282240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 |  | 0 | 0 | 50568 | 49d | 0 | 0 | 0 | 50568 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 |  | 0 | 0 | 1400 | 7d | 0 | 0 | 0 | 1400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 100% |  | 107560 | 54544
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 49544 | 100 | 100 | 100 | 100 | 100 | 100
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 100% | Finished | 40000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 4d | [5 empty] | 19200 |  | 10.26% |  | 19200.0003 | 0
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 4d | 19200 | 4800 | 1d | 0 | 0 | 19200 | 4800 | 80% | Started | 19200.0003 | 0 | 100 | 80 | 80 | 100 | 80 | 80
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 |  | 0 | 0 | 67200 | 14d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 |  | 0 | 0 | 38400 | 8d | 0 | 0 | 0 | 38400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 |  | 0 | 0 | 48000 | 10d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 |  | 0 | 0 | 38400 | 8d | 0 | 0 | 0 | 38400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 |  | 0 | 0 | 14400 | 3d | 0 | 0 | 0 | 14400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 |  | 0 | 0 | 46464 | 12d | 0 | 0 | 0 | 46464 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 |  | 0 | 0 | 16664 | 1d | 0 | 0 | 0 | 16664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 |  | 0 | 0 | 166640 | 10d | 0 | 0 | 0 | 166640 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 |  | 0 | 0 | 66656 | 4d | 0 | 0 | 0 | 66656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 |  | 0 | 0 | 83320 | 5d | 0 | 0 | 0 | 83320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 |  | 0 | 0 | 31232 | 8d | 0 | 0 | 0 | 31232 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 |  | 0 | 0 | 62464 | 16d | 0 | 0 | 0 | 62464 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 |  | 0 | 0 | 86400 | 15d | 0 | 0 | 0 | 86400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 |  | 0 | 0 | 144000 | 25d | 0 | 0 | 0 | 144000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 |  | 0 | 0 | 15480 | 15d | 0 | 0 | 0 | 15480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 |  | 0 | 0 | 25800 | 25d | 0 | 0 | 0 | 25800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 |  | 0 | 0 | 14280 | 3d | 0 | 0 | 0 | 14280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 |  | 0 | 0 | 71400 | 15d | 0 | 0 | 0 | 71400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 |  | 0 | 0 | 119000 | 25d | 0 | 0 | 0 | 119000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 |  | 0 | 0 | 28800 | 6d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 |  | 0 | 0 | 192000 | 40d | 0 | 0 | 0 | 192000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 |  | 0 | 0 | 28800 | 15d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 |  | 0 | 0 | 3840 | 2d | 0 | 0 | 0 | 3840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 |  | 0 | 0 | 67200 | 35d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-07-30 17:00 |  | TP Name | 30/07, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 117d | [5 empty] | 2435456 |  | 37.56% |  | 2253215.9972 | 2104416
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 100d | [5 empty] | 929688 |  | 70.89% |  | 929688 | 929688
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 60d | [5 empty] | 504000 |  | 100% |  | 504000 | 504000
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 100% | Finished | 120000 | 120000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 13d | 62400 | 0 | 0 | 0 | 0 | 62400 | 0 | 100% | Finished | 62400 | 62400 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2013-06-06 08:00 | 15d | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 100% | Finished | 72000 | 72000 | 100 | 100 | 100 | 100 | 100 | 100
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-26 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 30d | [5 empty] | 38720 |  | 41.67% |  | 38720 | 38720
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-06-19 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 |  | 0 | 0 | 15488 | 4d | 0 | 0 | 0 | 15488 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 100d | [5 empty] | 319408 |  | 50.59% |  | 319408 | 319408
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 2013-06-24 08:00 | 27d | 155520 | 155520 | 27d | 0 | 0 | 155520 | 155520 | 50% | Started | 155520 | 155520 | 100 | 50 | 50 | 100 | 50 | 50
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 2013-06-24 08:00 | 27d | 27864 | 27864 | 27d | 0 | 0 | 27864 | 27864 | 50% | Started | 27864 | 27864 | 100 | 50 | 50 | 100 | 50 | 50
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 2013-06-24 08:00 | 27d | 128520 | 128520 | 27d | 0 | 0 | 128520 | 128520 | 50% | Started | 128520 | 128520 | 100 | 50 | 50 | 100 | 50 | 50
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 97d | [5 empty] | 447152 |  | 33.67% |  | 269416 | 269416
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 100% | Finished | 56240 | 56240 | 100 | 380 | 100 | 100 | 380 | 100
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 100% | Finished | 27024 | 27024 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 50d | [5 empty] | 182400 |  | 92.68% |  | 182400 | 182400
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 100% | Finished | 43200 | 43200 | 100 | 100 | 100 | 100 | 100 | 100
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-06 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2013-06-06 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-14 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-21 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-24 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 2013-07-04 08:00 | 7d | 33600 | 0 | 0 | 0 | 0 | 33600 | 0 | 100% | Finished | 33600 | 33600 | 100 | 100 | 100 | 100 | 100 | 100
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 |  | 0 | 0 | 14400 | 3d | 0 | 0 | 0 | 14400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 |  | 0 | 0 | 11616 | 3d | 0 | 0 | 0 | 11616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 91d | [5 empty] | 15008 |  | 0.7435% |  | 3752 | 3752
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 3752 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 |  | 0 | 0 | 178560 | 31d | 0 | 0 | 0 | 178560 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 |  | 0 | 0 | 31992 | 31d | 0 | 0 | 0 | 31992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 |  | 0 | 0 | 290360 | 61d | 0 | 0 | 0 | 290360 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 56d | [5 empty] | 395072 |  | 54.99% |  | 390567.9969 | 390568
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 100% | Finished | 18016 | 18016 | 100 | 125 | 100 | 100 | 125 | 100
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 28d | [5 empty] | 48000 |  | 100% |  | 48000 | 48000
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 2013-06-06 08:00 | 4d | 19200 | 0 | 0 | 0 | 0 | 19200 | 0 | 100% | Finished | 19200 | 19200 | 100 | 100 | 100 | 100 | 100 | 100
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-12 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-19 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-28 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 |  | 0 | 0 | 3872 | 1d | 0 | 0 | 0 | 3872 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 4d | [5 empty] | 66656 |  | 100% |  | 66656 | 66656
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 2013-06-14 08:00 | 3d | 49992 | 0 | 0 | 0 | 0 | 49992 | 0 | 100% | Finished | 49992 | 49992 | 100 | 100 | 100 | 100 | 100 | 100
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2013-06-13 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 51d | [5 empty] | 257896 |  | 45.26% |  | 257895.9969 | 257896
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 2013-07-01 08:00 | 22d | 104720 | 128520 | 27d | 0 | 0 | 104720 | 128520 | 44.9% | Started | 104719.9987 | 104720 | 100 | 44.898 | 44.898 | 100 | 44.898 | 44.898
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 100% | Finished | 3752 | 3752 | 100 | 100 | 100 | 100 | 100 | 100
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 2013-07-01 08:00 | 22d | 126720 | 155520 | 27d | 0 | 0 | 126720 | 155520 | 44.9% | Started | 126719.9985 | 126720 | 100 | 44.898 | 44.898 | 100 | 44.898 | 44.898
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 2013-07-01 08:00 | 22d | 22704 | 27864 | 27d | 0 | 0 | 22704 | 27864 | 44.9% | Started | 22703.9997 | 22704 | 100 | 44.898 | 44.898 | 100 | 44.898 | 44.898
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 |  | 0 | 0 | 1400 | 7d | 0 | 0 | 0 | 1400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 100% |  | 107560 | 107560
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 100% | Finished | 40000 | 40000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 21d | [5 empty] | 187200 |  | 100% |  | 187200 | 187200
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-06-06 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 2013-06-06 08:00 | 14d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-19 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 20d | [5 empty] | 139200 |  | 96.67% |  | 139200 | 0
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-07-03 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 0 | 100 | 100 | 100 | 100 | 100 | 100
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-07-03 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 0 | 100 | 100 | 100 | 100 | 100 | 100
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-07-22 08:00 | 7d | 33600 | 4800 | 1d | 0 | 0 | 33600 | 4800 | 87.5% | Started | 33600 | 0 | 100 | 87.5 | 87.5 | 100 | 87.5 | 87.5
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-07-29 08:00 | 2d | 9600 | 4800 | 1d | 0 | 0 | 9600 | 4800 | 66.67% | Started | 9600.0003 | 0 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 |  | 0 | 0 | 46464 | 12d | 0 | 0 | 0 | 46464 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 |  | 0 | 0 | 16664 | 1d | 0 | 0 | 0 | 16664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 |  | 0 | 0 | 166640 | 10d | 0 | 0 | 0 | 166640 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 |  | 0 | 0 | 66656 | 4d | 0 | 0 | 0 | 66656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 |  | 0 | 0 | 83320 | 5d | 0 | 0 | 0 | 83320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 |  | 0 | 0 | 31232 | 8d | 0 | 0 | 0 | 31232 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 |  | 0 | 0 | 62464 | 16d | 0 | 0 | 0 | 62464 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 |  | 0 | 0 | 86400 | 15d | 0 | 0 | 0 | 86400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 |  | 0 | 0 | 144000 | 25d | 0 | 0 | 0 | 144000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 |  | 0 | 0 | 15480 | 15d | 0 | 0 | 0 | 15480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 |  | 0 | 0 | 25800 | 25d | 0 | 0 | 0 | 25800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 |  | 0 | 0 | 14280 | 3d | 0 | 0 | 0 | 14280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 |  | 0 | 0 | 71400 | 15d | 0 | 0 | 0 | 71400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 |  | 0 | 0 | 119000 | 25d | 0 | 0 | 0 | 119000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 |  | 0 | 0 | 28800 | 6d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 |  | 0 | 0 | 192000 | 40d | 0 | 0 | 0 | 192000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 |  | 0 | 0 | 28800 | 15d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 |  | 0 | 0 | 3840 | 2d | 0 | 0 | 0 | 3840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 |  | 0 | 0 | 67200 | 35d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-09-23 17:00 |  | TP Name | 23/09, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 156d | [5 empty] | 3465320 |  | 56.64% |  | 3398241.2932 | 3513608
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 136d | [5 empty] | 1311416 |  | 100% |  | 1311416 | 1311416
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 60d | [5 empty] | 504000 |  | 100% |  | 504000 | 504000
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 100% | Finished | 120000 | 120000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 13d | 62400 | 0 | 0 | 0 | 0 | 62400 | 0 | 100% | Finished | 62400 | 62400 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2013-06-06 08:00 | 15d | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 100% | Finished | 72000 | 72000 | 100 | 100 | 100 | 100 | 100 | 100
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-26 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 8d | [5 empty] | 15616 |  | 100% |  | 15616 | 15616
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2013-09-09 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2013-09-18 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 62d | [5 empty] | 92928 |  | 100% |  | 92928 | 92928
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-06-19 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 | 2013-08-26 08:00 | 4d | 15488 | 0 | 0 | 0 | 0 | 15488 | 0 | 100% | Finished | 15488 | 15488 | 100 | 100 | 100 | 100 | 100 | 100
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-08-30 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 127d | [5 empty] | 631312 |  | 100% |  | 631312 | 631312
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 2013-06-24 08:00 | 54d | 311040 | 0 | 0 | 0 | 0 | 311040 | 0 | 100% | Finished | 311040 | 311040 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 2013-06-24 08:00 | 54d | 55728 | 0 | 0 | 0 | 0 | 55728 | 0 | 100% | Finished | 55728 | 55728 | 100 | 100 | 100 | 100 | 100 | 100
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 2013-06-24 08:00 | 54d | 257040 | 0 | 0 | 0 | 0 | 257040 | 0 | 100% | Finished | 257040 | 257040 | 100 | 100 | 100 | 100 | 100 | 100
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 136d | [5 empty] | 765840 |  | 87.88% |  | 703265.2932 | 588104
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 100% | Finished | 56240 | 56240 | 100 | 380 | 100 | 100 | 380 | 100
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 100% | Finished | 27024 | 27024 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 62d | [5 empty] | 196800 |  | 100% |  | 196800 | 196800
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 100% | Finished | 43200 | 43200 | 100 | 100 | 100 | 100 | 100 | 100
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-06 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2013-06-06 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-14 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-21 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-24 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 2013-07-04 08:00 | 7d | 33600 | 0 | 0 | 0 | 0 | 33600 | 0 | 100% | Finished | 33600 | 33600 | 100 | 100 | 100 | 100 | 100 | 100
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-08-13 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 3d | [5 empty] | 15488 |  | 100% |  | 15488 | 15488
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-09-19 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 | 2013-09-18 08:00 | 3d | 11616 | 0 | 0 | 0 | 0 | 11616 | 0 | 100% | Finished | 11616 | 11616 | 100 | 100 | 100 | 100 | 100 | 100
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 130d | [5 empty] | 303808 |  | 80.79% |  | 407713.2932 | 292552
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 3752 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 | 2013-08-20 08:00 | 25d | 144000 | 34560 | 6d | 0 | 0 | 144000 | 34560 | 80.65% | Started | 144000.001 | 144000 | 100 | 80.6452 | 80.6452 | 100 | 80.6452 | 80.6452
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 | 2013-08-20 08:00 | 25d | 25800 | 6192 | 6d | 0 | 0 | 25800 | 6192 | 80.65% | Started | 25800.0002 | 25800 | 100 | 80.6452 | 80.6452 | 100 | 80.6452 | 80.6452
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 | 2013-08-20 08:00 | 25d | 119000 | 28560 | 6d | 0 | 0 | 119000 | 28560 | 80.65% | Started | 234161.292 | 119000 | 100 | 40.9836 | 80.6452 | 100 | 40.9836 | 80.6452
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 83d | [5 empty] | 714720 |  | 100% |  | 710216 | 710216
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 100% | Finished | 18016 | 18016 | 100 | 125 | 100 | 100 | 125 | 100
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 28d | [5 empty] | 48000 |  | 100% |  | 48000 | 48000
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 2013-06-06 08:00 | 4d | 19200 | 0 | 0 | 0 | 0 | 19200 | 0 | 100% | Finished | 19200 | 19200 | 100 | 100 | 100 | 100 | 100 | 100
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-12 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-19 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-28 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 1d | [5 empty] | 7744 |  | 100% |  | 7744 | 7744
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 4d | [5 empty] | 66656 |  | 100% |  | 66656 | 66656
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 2013-06-14 08:00 | 3d | 49992 | 0 | 0 | 0 | 0 | 49992 | 0 | 100% | Finished | 49992 | 49992 | 100 | 100 | 100 | 100 | 100 | 100
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2013-06-13 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 78d | [5 empty] | 569800 |  | 100% |  | 569800 | 569800
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 2013-07-01 08:00 | 49d | 233240 | 0 | 0 | 0 | 0 | 233240 | 0 | 100% | Finished | 233240 | 233240 | 100 | 100 | 100 | 100 | 100 | 100
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 100% | Finished | 3752 | 3752 | 100 | 100 | 100 | 100 | 100 | 100
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 2013-07-01 08:00 | 49d | 282240 | 0 | 0 | 0 | 0 | 282240 | 0 | 100% | Finished | 282240 | 282240 | 100 | 100 | 100 | 100 | 100 | 100
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 2013-07-01 08:00 | 49d | 50568 | 0 | 0 | 0 | 0 | 50568 | 0 | 100% | Finished | 50568 | 50568 | 100 | 100 | 100 | 100 | 100 | 100
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 | 2013-09-23 08:00 | 1d | 200 | 1200 | 6d | 0 | 0 | 200 | 1200 | 14.29% | Started | 200 | 200 | 100 | 14.2857 | 14.2857 | 100 | 14.2857 | 14.2857
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 100% |  | 107560 | 107560
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 100% | Finished | 40000 | 40000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 21d | [5 empty] | 187200 |  | 100% |  | 187200 | 187200
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-06-06 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 2013-06-06 08:00 | 14d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-19 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 21d | [5 empty] | 144000 |  | 100% |  | 144000 | 144000
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-07-03 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-07-03 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-07-22 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-07-29 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 38720
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 |  | 0 | 0 | 46464 | 12d | 0 | 0 | 0 | 46464 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 38720 | 100 |  | 0 | 100 |  | 0
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 83320
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 |  | 0 | 0 | 16664 | 1d | 0 | 0 | 0 | 16664 | 0% | Not Started | 0 | 16664 | 100 |  | 0 | 100 |  | 0
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 |  | 0 | 0 | 166640 | 10d | 0 | 0 | 0 | 166640 | 0% | Not Started | 0 | 66656 | 100 |  | 0 | 100 |  | 0
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 |  | 0 | 0 | 66656 | 4d | 0 | 0 | 0 | 66656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 |  | 0 | 0 | 83320 | 5d | 0 | 0 | 0 | 83320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 |  | 0 | 0 | 31232 | 8d | 0 | 0 | 0 | 31232 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 |  | 0 | 0 | 62464 | 16d | 0 | 0 | 0 | 62464 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 23040
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 23040 | 100 |  | 0 | 100 |  | 0
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 |  | 0 | 0 | 86400 | 15d | 0 | 0 | 0 | 86400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 |  | 0 | 0 | 144000 | 25d | 0 | 0 | 0 | 144000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4128
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 4128 | 100 |  | 0 | 100 |  | 0
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 |  | 0 | 0 | 15480 | 15d | 0 | 0 | 0 | 15480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 |  | 0 | 0 | 25800 | 25d | 0 | 0 | 0 | 25800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 33320
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 |  | 0 | 0 | 14280 | 3d | 0 | 0 | 0 | 14280 | 0% | Not Started | 0 | 14280 | 100 |  | 0 | 100 |  | 0
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 19040 | 100 |  | 0 | 100 |  | 0
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 |  | 0 | 0 | 71400 | 15d | 0 | 0 | 0 | 71400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 |  | 0 | 0 | 119000 | 25d | 0 | 0 | 0 | 119000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48000
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 |  | 0 | 0 | 28800 | 6d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 28800 | 100 |  | 0 | 100 |  | 0
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 19200 | 100 |  | 0 | 100 |  | 0
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 |  | 0 | 0 | 192000 | 40d | 0 | 0 | 0 | 192000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 |  | 0 | 0 | 28800 | 15d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 |  | 0 | 0 | 3840 | 2d | 0 | 0 | 0 | 3840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 |  | 0 | 0 | 67200 | 35d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-11-15 17:00 |  | TP Name | 15/11, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 195d | [5 empty] | 3535832 |  | 58.28% |  | 3496392 | 4524912
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 136d | [5 empty] | 1311416 |  | 100% |  | 1311416 | 1311416
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 60d | [5 empty] | 504000 |  | 100% |  | 504000 | 504000
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 100% | Finished | 120000 | 120000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 13d | 62400 | 0 | 0 | 0 | 0 | 62400 | 0 | 100% | Finished | 62400 | 62400 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2013-06-06 08:00 | 15d | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 100% | Finished | 72000 | 72000 | 100 | 100 | 100 | 100 | 100 | 100
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-26 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 8d | [5 empty] | 15616 |  | 100% |  | 15616 | 15616
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2013-09-09 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2013-09-18 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 62d | [5 empty] | 92928 |  | 100% |  | 92928 | 92928
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-06-19 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 | 2013-08-26 08:00 | 4d | 15488 | 0 | 0 | 0 | 0 | 15488 | 0 | 100% | Finished | 15488 | 15488 | 100 | 100 | 100 | 100 | 100 | 100
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-08-30 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 127d | [5 empty] | 631312 |  | 100% |  | 631312 | 631312
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 2013-06-24 08:00 | 54d | 311040 | 0 | 0 | 0 | 0 | 311040 | 0 | 100% | Finished | 311040 | 311040 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 2013-06-24 08:00 | 54d | 55728 | 0 | 0 | 0 | 0 | 55728 | 0 | 100% | Finished | 55728 | 55728 | 100 | 100 | 100 | 100 | 100 | 100
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 2013-06-24 08:00 | 54d | 257040 | 0 | 0 | 0 | 0 | 257040 | 0 | 100% | Finished | 257040 | 257040 | 100 | 100 | 100 | 100 | 100 | 100
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 142d | [5 empty] | 835152 |  | 100% |  | 800216 | 800216
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 100% | Finished | 56240 | 56240 | 100 | 380 | 100 | 100 | 380 | 100
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 100% | Finished | 27024 | 27024 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 62d | [5 empty] | 196800 |  | 100% |  | 196800 | 196800
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 100% | Finished | 43200 | 43200 | 100 | 100 | 100 | 100 | 100 | 100
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-06 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2013-06-06 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-14 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-21 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-24 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 2013-07-04 08:00 | 7d | 33600 | 0 | 0 | 0 | 0 | 33600 | 0 | 100% | Finished | 33600 | 33600 | 100 | 100 | 100 | 100 | 100 | 100
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-08-13 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 3d | [5 empty] | 15488 |  | 100% |  | 15488 | 15488
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-09-19 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 | 2013-09-18 08:00 | 3d | 11616 | 0 | 0 | 0 | 0 | 11616 | 0 | 100% | Finished | 11616 | 11616 | 100 | 100 | 100 | 100 | 100 | 100
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 136d | [5 empty] | 373120 |  | 100% |  | 504664 | 504664
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 3752 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 | 2013-08-20 08:00 | 31d | 178560 | 0 | 0 | 0 | 0 | 178560 | 0 | 100% | Finished | 178560 | 178560 | 100 | 100 | 100 | 100 | 100 | 100
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 | 2013-08-20 08:00 | 31d | 31992 | 0 | 0 | 0 | 0 | 31992 | 0 | 100% | Finished | 31992 | 31992 | 100 | 100 | 100 | 100 | 100 | 100
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 | 2013-08-20 08:00 | 31d | 147560 | 0 | 0 | 0 | 0 | 147560 | 0 | 100% | Finished | 290360 | 290360 | 100 | 50.8197 | 100 | 100 | 50.8197 | 100
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 83d | [5 empty] | 714720 |  | 100% |  | 710216 | 710216
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 100% | Finished | 18016 | 18016 | 100 | 125 | 100 | 100 | 125 | 100
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 28d | [5 empty] | 48000 |  | 100% |  | 48000 | 48000
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 2013-06-06 08:00 | 4d | 19200 | 0 | 0 | 0 | 0 | 19200 | 0 | 100% | Finished | 19200 | 19200 | 100 | 100 | 100 | 100 | 100 | 100
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-12 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-19 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-28 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 1d | [5 empty] | 7744 |  | 100% |  | 7744 | 7744
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 4d | [5 empty] | 66656 |  | 100% |  | 66656 | 66656
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 2013-06-14 08:00 | 3d | 49992 | 0 | 0 | 0 | 0 | 49992 | 0 | 100% | Finished | 49992 | 49992 | 100 | 100 | 100 | 100 | 100 | 100
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2013-06-13 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 78d | [5 empty] | 569800 |  | 100% |  | 569800 | 569800
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 2013-07-01 08:00 | 49d | 233240 | 0 | 0 | 0 | 0 | 233240 | 0 | 100% | Finished | 233240 | 233240 | 100 | 100 | 100 | 100 | 100 | 100
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 100% | Finished | 3752 | 3752 | 100 | 100 | 100 | 100 | 100 | 100
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 2013-07-01 08:00 | 49d | 282240 | 0 | 0 | 0 | 0 | 282240 | 0 | 100% | Finished | 282240 | 282240 | 100 | 100 | 100 | 100 | 100 | 100
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 2013-07-01 08:00 | 49d | 50568 | 0 | 0 | 0 | 0 | 50568 | 0 | 100% | Finished | 50568 | 50568 | 100 | 100 | 100 | 100 | 100 | 100
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 | 2013-09-23 08:00 | 7d | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 100% | Finished | 1400 | 1400 | 100 | 100 | 100 | 100 | 100 | 100
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 100% |  | 107560 | 107560
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 100% | Finished | 40000 | 40000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 21d | [5 empty] | 187200 |  | 100% |  | 187200 | 187200
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-06-06 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 2013-06-06 08:00 | 14d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-19 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 21d | [5 empty] | 144000 |  | 100% |  | 144000 | 144000
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-07-03 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-07-03 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-07-22 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-07-29 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 123904
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 |  | 0 | 0 | 46464 | 12d | 0 | 0 | 0 | 46464 | 0% | Not Started | 0 | 46464 | 100 |  | 0 | 100 |  | 0
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 38720 | 100 |  | 0 | 100 |  | 0
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 38720 | 100 |  | 0 | 100 |  | 0
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 333280
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 |  | 0 | 0 | 16664 | 1d | 0 | 0 | 0 | 16664 | 0% | Not Started | 0 | 16664 | 100 |  | 0 | 100 |  | 0
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 |  | 0 | 0 | 166640 | 10d | 0 | 0 | 0 | 166640 | 0% | Not Started | 0 | 166640 | 100 |  | 0 | 100 |  | 0
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 |  | 0 | 0 | 66656 | 4d | 0 | 0 | 0 | 66656 | 0% | Not Started | 0 | 66656 | 100 |  | 0 | 100 |  | 0
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 |  | 0 | 0 | 83320 | 5d | 0 | 0 | 0 | 83320 | 0% | Not Started | 0 | 83320 | 100 |  | 0 | 100 |  | 0
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 89792
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 19520 | 100 |  | 0 | 100 |  | 0
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 19520 | 100 |  | 0 | 100 |  | 0
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 |  | 0 | 0 | 31232 | 8d | 0 | 0 | 0 | 31232 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 121024
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 15616 | 100 |  | 0 | 100 |  | 0
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 19520 | 100 |  | 0 | 100 |  | 0
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 |  | 0 | 0 | 62464 | 16d | 0 | 0 | 0 | 62464 | 0% | Not Started | 0 | 62464 | 100 |  | 0 | 100 |  | 0
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 7808 | 100 |  | 0 | 100 |  | 0
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 7808 | 100 |  | 0 | 100 |  | 0
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 115200
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 57600 | 100 |  | 0 | 100 |  | 0
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 57600 | 100 |  | 0 | 100 |  | 0
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 |  | 0 | 0 | 86400 | 15d | 0 | 0 | 0 | 86400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 |  | 0 | 0 | 144000 | 25d | 0 | 0 | 0 | 144000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 20640
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 10320 | 100 |  | 0 | 100 |  | 0
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 10320 | 100 |  | 0 | 100 |  | 0
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 |  | 0 | 0 | 15480 | 15d | 0 | 0 | 0 | 15480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 |  | 0 | 0 | 25800 | 25d | 0 | 0 | 0 | 25800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 109480
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 |  | 0 | 0 | 14280 | 3d | 0 | 0 | 0 | 14280 | 0% | Not Started | 0 | 14280 | 100 |  | 0 | 100 |  | 0
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 47600 | 100 |  | 0 | 100 |  | 0
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 47600 | 100 |  | 0 | 100 |  | 0
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 |  | 0 | 0 | 71400 | 15d | 0 | 0 | 0 | 71400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 |  | 0 | 0 | 119000 | 25d | 0 | 0 | 0 | 119000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 86400
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 |  | 0 | 0 | 28800 | 6d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 28800 | 100 |  | 0 | 100 |  | 0
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 57600 | 100 |  | 0 | 100 |  | 0
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 |  | 0 | 0 | 192000 | 40d | 0 | 0 | 0 | 192000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 28800
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 |  | 0 | 0 | 28800 | 15d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 28800 | 100 |  | 0 | 100 |  | 0
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 |  | 0 | 0 | 3840 | 2d | 0 | 0 | 0 | 3840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 |  | 0 | 0 | 67200 | 35d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2014-01-09 17:00 |  | TP Name | 09/01, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 234d | [5 empty] | 3535832 |  | 58.28% |  | 3496392 | 5209720
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 136d | [5 empty] | 1311416 |  | 100% |  | 1311416 | 1311416
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 60d | [5 empty] | 504000 |  | 100% |  | 504000 | 504000
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 100% | Finished | 120000 | 120000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 13d | 62400 | 0 | 0 | 0 | 0 | 62400 | 0 | 100% | Finished | 62400 | 62400 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2013-06-06 08:00 | 15d | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 100% | Finished | 72000 | 72000 | 100 | 100 | 100 | 100 | 100 | 100
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-26 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 8d | [5 empty] | 15616 |  | 100% |  | 15616 | 15616
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2013-09-09 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2013-09-18 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 62d | [5 empty] | 92928 |  | 100% |  | 92928 | 92928
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-06-19 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 | 2013-08-26 08:00 | 4d | 15488 | 0 | 0 | 0 | 0 | 15488 | 0 | 100% | Finished | 15488 | 15488 | 100 | 100 | 100 | 100 | 100 | 100
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-08-30 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 127d | [5 empty] | 631312 |  | 100% |  | 631312 | 631312
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 2013-06-24 08:00 | 54d | 311040 | 0 | 0 | 0 | 0 | 311040 | 0 | 100% | Finished | 311040 | 311040 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 2013-06-24 08:00 | 54d | 55728 | 0 | 0 | 0 | 0 | 55728 | 0 | 100% | Finished | 55728 | 55728 | 100 | 100 | 100 | 100 | 100 | 100
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 2013-06-24 08:00 | 54d | 257040 | 0 | 0 | 0 | 0 | 257040 | 0 | 100% | Finished | 257040 | 257040 | 100 | 100 | 100 | 100 | 100 | 100
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 142d | [5 empty] | 835152 |  | 100% |  | 800216 | 800216
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 100% | Finished | 56240 | 56240 | 100 | 380 | 100 | 100 | 380 | 100
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 100% | Finished | 27024 | 27024 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 62d | [5 empty] | 196800 |  | 100% |  | 196800 | 196800
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 100% | Finished | 43200 | 43200 | 100 | 100 | 100 | 100 | 100 | 100
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-06 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2013-06-06 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-14 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-21 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-24 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 2013-07-04 08:00 | 7d | 33600 | 0 | 0 | 0 | 0 | 33600 | 0 | 100% | Finished | 33600 | 33600 | 100 | 100 | 100 | 100 | 100 | 100
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-08-13 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 3d | [5 empty] | 15488 |  | 100% |  | 15488 | 15488
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-09-19 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 | 2013-09-18 08:00 | 3d | 11616 | 0 | 0 | 0 | 0 | 11616 | 0 | 100% | Finished | 11616 | 11616 | 100 | 100 | 100 | 100 | 100 | 100
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 136d | [5 empty] | 373120 |  | 100% |  | 504664 | 504664
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 3752 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 | 2013-08-20 08:00 | 31d | 178560 | 0 | 0 | 0 | 0 | 178560 | 0 | 100% | Finished | 178560 | 178560 | 100 | 100 | 100 | 100 | 100 | 100
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 | 2013-08-20 08:00 | 31d | 31992 | 0 | 0 | 0 | 0 | 31992 | 0 | 100% | Finished | 31992 | 31992 | 100 | 100 | 100 | 100 | 100 | 100
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 | 2013-08-20 08:00 | 31d | 147560 | 0 | 0 | 0 | 0 | 147560 | 0 | 100% | Finished | 290360 | 290360 | 100 | 50.8197 | 100 | 100 | 50.8197 | 100
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 83d | [5 empty] | 714720 |  | 100% |  | 710216 | 710216
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 100% | Finished | 18016 | 18016 | 100 | 125 | 100 | 100 | 125 | 100
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 28d | [5 empty] | 48000 |  | 100% |  | 48000 | 48000
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 2013-06-06 08:00 | 4d | 19200 | 0 | 0 | 0 | 0 | 19200 | 0 | 100% | Finished | 19200 | 19200 | 100 | 100 | 100 | 100 | 100 | 100
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-12 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-19 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-28 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 1d | [5 empty] | 7744 |  | 100% |  | 7744 | 7744
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 4d | [5 empty] | 66656 |  | 100% |  | 66656 | 66656
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 2013-06-14 08:00 | 3d | 49992 | 0 | 0 | 0 | 0 | 49992 | 0 | 100% | Finished | 49992 | 49992 | 100 | 100 | 100 | 100 | 100 | 100
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2013-06-13 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 78d | [5 empty] | 569800 |  | 100% |  | 569800 | 569800
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 2013-07-01 08:00 | 49d | 233240 | 0 | 0 | 0 | 0 | 233240 | 0 | 100% | Finished | 233240 | 233240 | 100 | 100 | 100 | 100 | 100 | 100
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 100% | Finished | 3752 | 3752 | 100 | 100 | 100 | 100 | 100 | 100
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 2013-07-01 08:00 | 49d | 282240 | 0 | 0 | 0 | 0 | 282240 | 0 | 100% | Finished | 282240 | 282240 | 100 | 100 | 100 | 100 | 100 | 100
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 2013-07-01 08:00 | 49d | 50568 | 0 | 0 | 0 | 0 | 50568 | 0 | 100% | Finished | 50568 | 50568 | 100 | 100 | 100 | 100 | 100 | 100
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 | 2013-09-23 08:00 | 7d | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 100% | Finished | 1400 | 1400 | 100 | 100 | 100 | 100 | 100 | 100
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 100% |  | 107560 | 107560
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 100% | Finished | 40000 | 40000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 21d | [5 empty] | 187200 |  | 100% |  | 187200 | 187200
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-06-06 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 2013-06-06 08:00 | 14d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-19 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 21d | [5 empty] | 144000 |  | 100% |  | 144000 | 144000
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-07-03 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-07-03 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-07-22 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-07-29 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 123904
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 |  | 0 | 0 | 46464 | 12d | 0 | 0 | 0 | 46464 | 0% | Not Started | 0 | 46464 | 100 |  | 0 | 100 |  | 0
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 38720 | 100 |  | 0 | 100 |  | 0
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 38720 | 100 |  | 0 | 100 |  | 0
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 333280
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 |  | 0 | 0 | 16664 | 1d | 0 | 0 | 0 | 16664 | 0% | Not Started | 0 | 16664 | 100 |  | 0 | 100 |  | 0
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 |  | 0 | 0 | 166640 | 10d | 0 | 0 | 0 | 166640 | 0% | Not Started | 0 | 166640 | 100 |  | 0 | 100 |  | 0
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 |  | 0 | 0 | 66656 | 4d | 0 | 0 | 0 | 66656 | 0% | Not Started | 0 | 66656 | 100 |  | 0 | 100 |  | 0
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 |  | 0 | 0 | 83320 | 5d | 0 | 0 | 0 | 83320 | 0% | Not Started | 0 | 83320 | 100 |  | 0 | 100 |  | 0
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 249856
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 19520 | 100 |  | 0 | 100 |  | 0
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 19520 | 100 |  | 0 | 100 |  | 0
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 |  | 0 | 0 | 31232 | 8d | 0 | 0 | 0 | 31232 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 11712 | 100 |  | 0 | 100 |  | 0
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 27328 | 100 |  | 0 | 100 |  | 0
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 249856
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 15616 | 100 |  | 0 | 100 |  | 0
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 19520 | 100 |  | 0 | 100 |  | 0
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 |  | 0 | 0 | 3904 | 1d | 0 | 0 | 0 | 3904 | 0% | Not Started | 0 | 3904 | 100 |  | 0 | 100 |  | 0
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 |  | 0 | 0 | 62464 | 16d | 0 | 0 | 0 | 62464 | 0% | Not Started | 0 | 62464 | 100 |  | 0 | 100 |  | 0
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 11712 | 100 |  | 0 | 100 |  | 0
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 27328 | 100 |  | 0 | 100 |  | 0
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 19520 | 100 |  | 0 | 100 |  | 0
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 |  | 0 | 0 | 46848 | 12d | 0 | 0 | 0 | 46848 | 0% | Not Started | 0 | 46848 | 100 |  | 0 | 100 |  | 0
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 322560
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 57600 | 100 |  | 0 | 100 |  | 0
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 57600 | 100 |  | 0 | 100 |  | 0
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 |  | 0 | 0 | 86400 | 15d | 0 | 0 | 0 | 86400 | 0% | Not Started | 0 | 86400 | 100 |  | 0 | 100 |  | 0
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 |  | 0 | 0 | 144000 | 25d | 0 | 0 | 0 | 144000 | 0% | Not Started | 0 | 120960 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 57792
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 10320 | 100 |  | 0 | 100 |  | 0
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 10320 | 100 |  | 0 | 100 |  | 0
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 |  | 0 | 0 | 15480 | 15d | 0 | 0 | 0 | 15480 | 0% | Not Started | 0 | 15480 | 100 |  | 0 | 100 |  | 0
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 |  | 0 | 0 | 25800 | 25d | 0 | 0 | 0 | 25800 | 0% | Not Started | 0 | 21672 | 100 |  | 0 | 100 |  | 0
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 257040
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 |  | 0 | 0 | 14280 | 3d | 0 | 0 | 0 | 14280 | 0% | Not Started | 0 | 14280 | 100 |  | 0 | 100 |  | 0
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 47600 | 100 |  | 0 | 100 |  | 0
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 47600 | 100 |  | 0 | 100 |  | 0
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 |  | 0 | 0 | 71400 | 15d | 0 | 0 | 0 | 71400 | 0% | Not Started | 0 | 71400 | 100 |  | 0 | 100 |  | 0
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 |  | 0 | 0 | 119000 | 25d | 0 | 0 | 0 | 119000 | 0% | Not Started | 0 | 76160 | 100 |  | 0 | 100 |  | 0
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 86400
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 |  | 0 | 0 | 28800 | 6d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 28800 | 100 |  | 0 | 100 |  | 0
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 |  | 0 | 0 | 57600 | 12d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 57600 | 100 |  | 0 | 100 |  | 0
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 |  | 0 | 0 | 192000 | 40d | 0 | 0 | 0 | 192000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 32640
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 |  | 0 | 0 | 28800 | 15d | 0 | 0 | 0 | 28800 | 0% | Not Started | 0 | 28800 | 100 |  | 0 | 100 |  | 0
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 |  | 0 | 0 | 3840 | 2d | 0 | 0 | 0 | 3840 | 0% | Not Started | 0 | 3840 | 100 |  | 0 | 100 |  | 0
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 |  | 0 | 0 | 67200 | 35d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2014-03-05 17:00 |  | TP Name | 05/03, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 273d | [5 empty] | 4747840 |  | 83.02% |  | 4980792.0002 | 5746416
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 136d | [5 empty] | 1311416 |  | 100% |  | 1311416 | 1311416
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 60d | [5 empty] | 504000 |  | 100% |  | 504000 | 504000
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 100% | Finished | 120000 | 120000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 13d | 62400 | 0 | 0 | 0 | 0 | 62400 | 0 | 100% | Finished | 62400 | 62400 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2013-06-06 08:00 | 15d | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 100% | Finished | 72000 | 72000 | 100 | 100 | 100 | 100 | 100 | 100
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-26 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 8d | [5 empty] | 15616 |  | 100% |  | 15616 | 15616
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2013-09-09 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2013-09-18 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 62d | [5 empty] | 92928 |  | 100% |  | 92928 | 92928
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-06-19 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 | 2013-08-26 08:00 | 4d | 15488 | 0 | 0 | 0 | 0 | 15488 | 0 | 100% | Finished | 15488 | 15488 | 100 | 100 | 100 | 100 | 100 | 100
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-08-30 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 127d | [5 empty] | 631312 |  | 100% |  | 631312 | 631312
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 2013-06-24 08:00 | 54d | 311040 | 0 | 0 | 0 | 0 | 311040 | 0 | 100% | Finished | 311040 | 311040 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 2013-06-24 08:00 | 54d | 55728 | 0 | 0 | 0 | 0 | 55728 | 0 | 100% | Finished | 55728 | 55728 | 100 | 100 | 100 | 100 | 100 | 100
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 2013-06-24 08:00 | 54d | 257040 | 0 | 0 | 0 | 0 | 257040 | 0 | 100% | Finished | 257040 | 257040 | 100 | 100 | 100 | 100 | 100 | 100
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 142d | [5 empty] | 835152 |  | 100% |  | 800216 | 800216
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 100% | Finished | 56240 | 56240 | 100 | 380 | 100 | 100 | 380 | 100
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 100% | Finished | 27024 | 27024 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 62d | [5 empty] | 196800 |  | 100% |  | 196800 | 196800
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 100% | Finished | 43200 | 43200 | 100 | 100 | 100 | 100 | 100 | 100
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-06 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2013-06-06 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-14 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-21 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-24 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 2013-07-04 08:00 | 7d | 33600 | 0 | 0 | 0 | 0 | 33600 | 0 | 100% | Finished | 33600 | 33600 | 100 | 100 | 100 | 100 | 100 | 100
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-08-13 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 3d | [5 empty] | 15488 |  | 100% |  | 15488 | 15488
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-09-19 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 | 2013-09-18 08:00 | 3d | 11616 | 0 | 0 | 0 | 0 | 11616 | 0 | 100% | Finished | 11616 | 11616 | 100 | 100 | 100 | 100 | 100 | 100
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 136d | [5 empty] | 373120 |  | 100% |  | 504664 | 504664
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 3752 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 | 2013-08-20 08:00 | 31d | 178560 | 0 | 0 | 0 | 0 | 178560 | 0 | 100% | Finished | 178560 | 178560 | 100 | 100 | 100 | 100 | 100 | 100
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 | 2013-08-20 08:00 | 31d | 31992 | 0 | 0 | 0 | 0 | 31992 | 0 | 100% | Finished | 31992 | 31992 | 100 | 100 | 100 | 100 | 100 | 100
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 | 2013-08-20 08:00 | 31d | 147560 | 0 | 0 | 0 | 0 | 147560 | 0 | 100% | Finished | 290360 | 290360 | 100 | 50.8197 | 100 | 100 | 50.8197 | 100
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 83d | [5 empty] | 714720 |  | 100% |  | 710216 | 710216
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 100% | Finished | 18016 | 18016 | 100 | 125 | 100 | 100 | 125 | 100
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 28d | [5 empty] | 48000 |  | 100% |  | 48000 | 48000
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 2013-06-06 08:00 | 4d | 19200 | 0 | 0 | 0 | 0 | 19200 | 0 | 100% | Finished | 19200 | 19200 | 100 | 100 | 100 | 100 | 100 | 100
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-12 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-19 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-28 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 1d | [5 empty] | 7744 |  | 100% |  | 7744 | 7744
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 4d | [5 empty] | 66656 |  | 100% |  | 66656 | 66656
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 2013-06-14 08:00 | 3d | 49992 | 0 | 0 | 0 | 0 | 49992 | 0 | 100% | Finished | 49992 | 49992 | 100 | 100 | 100 | 100 | 100 | 100
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2013-06-13 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 78d | [5 empty] | 569800 |  | 100% |  | 569800 | 569800
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 2013-07-01 08:00 | 49d | 233240 | 0 | 0 | 0 | 0 | 233240 | 0 | 100% | Finished | 233240 | 233240 | 100 | 100 | 100 | 100 | 100 | 100
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 100% | Finished | 3752 | 3752 | 100 | 100 | 100 | 100 | 100 | 100
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 2013-07-01 08:00 | 49d | 282240 | 0 | 0 | 0 | 0 | 282240 | 0 | 100% | Finished | 282240 | 282240 | 100 | 100 | 100 | 100 | 100 | 100
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 2013-07-01 08:00 | 49d | 50568 | 0 | 0 | 0 | 0 | 50568 | 0 | 100% | Finished | 50568 | 50568 | 100 | 100 | 100 | 100 | 100 | 100
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 | 2013-09-23 08:00 | 7d | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 100% | Finished | 1400 | 1400 | 100 | 100 | 100 | 100 | 100 | 100
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 100% |  | 107560 | 107560
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 100% | Finished | 40000 | 40000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 21d | [5 empty] | 187200 |  | 100% |  | 187200 | 187200
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-06-06 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 2013-06-06 08:00 | 14d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-19 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 21d | [5 empty] | 144000 |  | 100% |  | 144000 | 144000
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-07-03 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-07-03 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-07-22 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-07-29 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 25d | [5 empty] | 19360 |  | 31.25% |  | 38720 | 123904
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 |  | 0 | 0 | 46464 | 12d | 0 | 0 | 0 | 46464 | 0% | Not Started | 0 | 46464 | 100 |  | 0 | 100 |  | 0
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 |  | 0 | 0 | 38720 | 10d | 0 | 0 | 0 | 38720 | 0% | Not Started | 0 | 38720 | 100 |  | 0 | 100 |  | 0
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2014-01-30 08:00 | 5d | 19360 | 0 | 0 | 0 | 0 | 19360 | 0 | 100% | Finished | 38720 | 38720 | 100 | 50 | 100 | 100 | 50 | 100
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 19d | [5 empty] | 333280 |  | 100% |  | 333280 | 333280
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2014-01-28 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 | 2014-02-05 08:00 | 10d | 166640 | 0 | 0 | 0 | 0 | 166640 | 0 | 100% | Finished | 166640 | 166640 | 100 | 100 | 100 | 100 | 100 | 100
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 | 2014-02-17 08:00 | 4d | 66656 | 0 | 0 | 0 | 0 | 66656 | 0 | 100% | Finished | 66656 | 66656 | 100 | 100 | 100 | 100 | 100 | 100
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 | 2014-02-17 08:00 | 5d | 83320 | 0 | 0 | 0 | 0 | 83320 | 0 | 100% | Finished | 83320 | 83320 | 100 | 100 | 100 | 100 | 100 | 100
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 28d | [5 empty] | 195200 |  | 50% |  | 253760.0005 | 433344
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-01-27 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-01-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 39040 | 39040 | 100 | 100 | 100 | 100 | 100 | 100
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-10 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-11 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-12 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-24 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 | 2014-01-30 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 31232 | 31232 | 100 | 62.5 | 100 | 100 | 62.5 | 100
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-26 08:00 | 6d | 23424 | 15616 | 4d | 0 | 0 | 23424 | 15616 | 60% | Started | 23424.0009 | 39040 | 100 | 60 | 60 | 100 | 60 | 60
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-01-27 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 11712 | 11712 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-04 08:00 | 8d | 31232 | 0 | 0 | 0 | 0 | 31232 | 0 | 100% | Finished | 39040 | 39040 | 100 | 80 | 100 | 100 | 80 | 100
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-27 08:00 | 2d | 7808 | 0 | 0 | 0 | 0 | 7808 | 0 | 100% | Finished | 39040 | 39040 | 100 | 20 | 100 | 100 | 20 | 100
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 27328 | 100 |  | 0 | 100 |  | 0
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 |  | 0 | 0 | 19520 | 5d | 0 | 0 | 0 | 19520 | 0% | Not Started | 0 | 19520 | 100 |  | 0 | 100 |  | 0
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 2014-02-27 08:00 | 5d | 19520 | 27328 | 7d | 0 | 0 | 19520 | 27328 | 41.67% | Started | 19519.9995 | 46848 | 100 | 41.6667 | 41.6667 | 100 | 41.6667 | 41.6667
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 11712 | 100 |  | 0 | 100 |  | 0
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 11712 | 100 |  | 0 | 100 |  | 0
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 66368 | 100 |  | 0 | 100 |  | 0
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 28d | [5 empty] | 222528 |  | 51.72% |  | 234240 | 425536
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 2014-01-27 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 15616 | 15616 | 100 | 100 | 100 | 100 | 100 | 100
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-01-31 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-03 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-12 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 | 2014-02-12 08:00 | 16d | 62464 | 0 | 0 | 0 | 0 | 62464 | 0 | 100% | Finished | 62464 | 62464 | 100 | 100 | 100 | 100 | 100 | 100
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-01-27 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 2014-01-30 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 7808 | 7808 | 100 | 150 | 100 | 100 | 150 | 100
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-04 08:00 | 2d | 7808 | 0 | 0 | 0 | 0 | 7808 | 0 | 100% | Finished | 39040 | 39040 | 100 | 20 | 100 | 100 | 20 | 100
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-02-27 08:00 | 5d | 19520 | 19520 | 5d | 0 | 0 | 19520 | 19520 | 50% | Started | 13664 | 27328 | 100 | 71.4286 | 50 | 100 | 71.4286 | 50
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-27 08:00 | 5d | 19520 | 19520 | 5d | 0 | 0 | 19520 | 19520 | 50% | Started | 9760 | 19520 | 100 | 100 | 50 | 100 | 100 | 50
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 2014-02-11 08:00 | 12d | 46848 | 0 | 0 | 0 | 0 | 46848 | 0 | 100% | Finished | 46848 | 46848 | 100 | 100 | 100 | 100 | 100 | 100
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 27328 | 100 |  | 0 | 100 |  | 0
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 11712 | 100 |  | 0 | 100 |  | 0
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 |  | 0 | 0 | 15616 | 4d | 0 | 0 | 0 | 15616 | 0% | Not Started | 0 | 15616 | 100 |  | 0 | 100 |  | 0
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 |  | 0 | 0 | 66368 | 17d | 0 | 0 | 0 | 66368 | 0% | Not Started | 0 | 66368 | 100 |  | 0 | 100 |  | 0
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 7808 | 100 |  | 0 | 100 |  | 0
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 |  | 0 | 0 | 27328 | 7d | 0 | 0 | 0 | 27328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 32d | [5 empty] | 115200 |  | 66.67% |  | 230400 | 345600
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 57600 | 100 |  | 0 | 100 |  | 0
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 |  | 0 | 0 | 57600 | 10d | 0 | 0 | 0 | 57600 | 0% | Not Started | 0 | 57600 | 100 |  | 0 | 100 |  | 0
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 | 2014-01-21 08:00 | 10d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 86400 | 86400 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 | 2014-02-06 08:00 | 10d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 144000 | 144000 | 100 | 40 | 100 | 100 | 40 | 100
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 32d | [5 empty] | 20640 |  | 66.67% |  | 41280 | 61920
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 10320 | 100 |  | 0 | 100 |  | 0
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 |  | 0 | 0 | 10320 | 10d | 0 | 0 | 0 | 10320 | 0% | Not Started | 0 | 10320 | 100 |  | 0 | 100 |  | 0
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 | 2014-01-21 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 15480 | 15480 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 | 2014-02-06 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 25800 | 25800 | 100 | 40 | 100 | 100 | 40 | 100
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 6d | [5 empty] | 52360 |  | 33.11% |  | 99280.002 | 299880
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 | 2014-02-26 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 14280 | 14280 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 2014-02-27 08:00 | 5d | 23800 | 9520 | 2d | 0 | 0 | 23800 | 9520 | 71.43% | Started | 34000.0008 | 47600 | 100 | 50 | 71.4286 | 100 | 50 | 71.4286
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 |  | 0 | 0 | 47600 | 10d | 0 | 0 | 0 | 47600 | 0% | Not Started | 0 | 47600 | 100 |  | 0 | 100 |  | 0
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 | 2014-02-27 08:00 | 5d | 23800 | 9520 | 2d | 0 | 0 | 23800 | 9520 | 71.43% | Started | 51000.0012 | 71400 | 100 | 33.3333 | 71.4286 | 100 | 33.3333 | 71.4286
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 |  | 0 | 0 | 119000 | 25d | 0 | 0 | 0 | 119000 | 0% | Not Started | 0 | 119000 | 100 |  | 0 | 100 |  | 0
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 19d | [5 empty] | 86400 |  | 100% |  | 86400 | 86400
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2014-01-27 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2014-02-05 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 | 2014-01-27 08:00 | 28d | 134400 | 57600 | 12d | 0 | 0 | 134400 | 57600 | 70% | Started | 134399.9977 | 76800 | 100 | 70 | 70 | 100 | 70 | 70
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 24d | [5 empty] | 32640 |  | 32.69% |  | 32640 | 63360
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 | 2014-01-31 08:00 | 15d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 | 2014-02-17 08:00 | 2d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 3840 | 3840 | 100 | 100 | 100 | 100 | 100 | 100
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 |  | 0 | 0 | 67200 | 35d | 0 | 0 | 0 | 67200 | 0% | Not Started | 0 | 30720 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2014-04-29 17:00 |  | TP Name | 29/04, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 312d | [5 empty] | 5391120 |  | 98.05% |  | 5882480 | 5999600
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 136d | [5 empty] | 1311416 |  | 100% |  | 1311416 | 1311416
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 60d | [5 empty] | 504000 |  | 100% |  | 504000 | 504000
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 100% | Finished | 120000 | 120000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 13d | 62400 | 0 | 0 | 0 | 0 | 62400 | 0 | 100% | Finished | 62400 | 62400 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2013-06-06 08:00 | 15d | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 100% | Finished | 72000 | 72000 | 100 | 100 | 100 | 100 | 100 | 100
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-26 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 8d | [5 empty] | 15616 |  | 100% |  | 15616 | 15616
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2013-09-09 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2013-09-18 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 62d | [5 empty] | 92928 |  | 100% |  | 92928 | 92928
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-06-19 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 | 2013-08-26 08:00 | 4d | 15488 | 0 | 0 | 0 | 0 | 15488 | 0 | 100% | Finished | 15488 | 15488 | 100 | 100 | 100 | 100 | 100 | 100
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-08-30 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 127d | [5 empty] | 631312 |  | 100% |  | 631312 | 631312
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 2013-06-24 08:00 | 54d | 311040 | 0 | 0 | 0 | 0 | 311040 | 0 | 100% | Finished | 311040 | 311040 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 2013-06-24 08:00 | 54d | 55728 | 0 | 0 | 0 | 0 | 55728 | 0 | 100% | Finished | 55728 | 55728 | 100 | 100 | 100 | 100 | 100 | 100
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 2013-06-24 08:00 | 54d | 257040 | 0 | 0 | 0 | 0 | 257040 | 0 | 100% | Finished | 257040 | 257040 | 100 | 100 | 100 | 100 | 100 | 100
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 142d | [5 empty] | 835152 |  | 100% |  | 800216 | 800216
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 100% | Finished | 56240 | 56240 | 100 | 380 | 100 | 100 | 380 | 100
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 100% | Finished | 27024 | 27024 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 62d | [5 empty] | 196800 |  | 100% |  | 196800 | 196800
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 100% | Finished | 43200 | 43200 | 100 | 100 | 100 | 100 | 100 | 100
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-06 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2013-06-06 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-14 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-21 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-24 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 2013-07-04 08:00 | 7d | 33600 | 0 | 0 | 0 | 0 | 33600 | 0 | 100% | Finished | 33600 | 33600 | 100 | 100 | 100 | 100 | 100 | 100
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-08-13 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 3d | [5 empty] | 15488 |  | 100% |  | 15488 | 15488
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-09-19 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 | 2013-09-18 08:00 | 3d | 11616 | 0 | 0 | 0 | 0 | 11616 | 0 | 100% | Finished | 11616 | 11616 | 100 | 100 | 100 | 100 | 100 | 100
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 136d | [5 empty] | 373120 |  | 100% |  | 504664 | 504664
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 3752 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 | 2013-08-20 08:00 | 31d | 178560 | 0 | 0 | 0 | 0 | 178560 | 0 | 100% | Finished | 178560 | 178560 | 100 | 100 | 100 | 100 | 100 | 100
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 | 2013-08-20 08:00 | 31d | 31992 | 0 | 0 | 0 | 0 | 31992 | 0 | 100% | Finished | 31992 | 31992 | 100 | 100 | 100 | 100 | 100 | 100
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 | 2013-08-20 08:00 | 31d | 147560 | 0 | 0 | 0 | 0 | 147560 | 0 | 100% | Finished | 290360 | 290360 | 100 | 50.8197 | 100 | 100 | 50.8197 | 100
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 83d | [5 empty] | 714720 |  | 100% |  | 710216 | 710216
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 100% | Finished | 18016 | 18016 | 100 | 125 | 100 | 100 | 125 | 100
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 28d | [5 empty] | 48000 |  | 100% |  | 48000 | 48000
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 2013-06-06 08:00 | 4d | 19200 | 0 | 0 | 0 | 0 | 19200 | 0 | 100% | Finished | 19200 | 19200 | 100 | 100 | 100 | 100 | 100 | 100
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-12 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-19 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-28 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 1d | [5 empty] | 7744 |  | 100% |  | 7744 | 7744
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 4d | [5 empty] | 66656 |  | 100% |  | 66656 | 66656
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 2013-06-14 08:00 | 3d | 49992 | 0 | 0 | 0 | 0 | 49992 | 0 | 100% | Finished | 49992 | 49992 | 100 | 100 | 100 | 100 | 100 | 100
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2013-06-13 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 78d | [5 empty] | 569800 |  | 100% |  | 569800 | 569800
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 2013-07-01 08:00 | 49d | 233240 | 0 | 0 | 0 | 0 | 233240 | 0 | 100% | Finished | 233240 | 233240 | 100 | 100 | 100 | 100 | 100 | 100
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 100% | Finished | 3752 | 3752 | 100 | 100 | 100 | 100 | 100 | 100
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 2013-07-01 08:00 | 49d | 282240 | 0 | 0 | 0 | 0 | 282240 | 0 | 100% | Finished | 282240 | 282240 | 100 | 100 | 100 | 100 | 100 | 100
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 2013-07-01 08:00 | 49d | 50568 | 0 | 0 | 0 | 0 | 50568 | 0 | 100% | Finished | 50568 | 50568 | 100 | 100 | 100 | 100 | 100 | 100
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 | 2013-09-23 08:00 | 7d | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 100% | Finished | 1400 | 1400 | 100 | 100 | 100 | 100 | 100 | 100
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 100% |  | 107560 | 107560
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 100% | Finished | 40000 | 40000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 21d | [5 empty] | 187200 |  | 100% |  | 187200 | 187200
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-06-06 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 2013-06-06 08:00 | 14d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-19 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 21d | [5 empty] | 144000 |  | 100% |  | 144000 | 144000
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-07-03 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-07-03 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-07-22 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-07-29 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 51d | [5 empty] | 104544 |  | 100% |  | 123904 | 123904
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 | 2014-03-26 08:00 | 12d | 46464 | 0 | 0 | 0 | 0 | 46464 | 0 | 100% | Finished | 46464 | 46464 | 100 | 100 | 100 | 100 | 100 | 100
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2014-03-13 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2014-01-30 08:00 | 5d | 19360 | 0 | 0 | 0 | 0 | 19360 | 0 | 100% | Finished | 38720 | 38720 | 100 | 50 | 100 | 100 | 50 | 100
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 19d | [5 empty] | 333280 |  | 100% |  | 333280 | 333280
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2014-01-28 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 | 2014-02-05 08:00 | 10d | 166640 | 0 | 0 | 0 | 0 | 166640 | 0 | 100% | Finished | 166640 | 166640 | 100 | 100 | 100 | 100 | 100 | 100
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 | 2014-02-17 08:00 | 4d | 66656 | 0 | 0 | 0 | 0 | 66656 | 0 | 100% | Finished | 66656 | 66656 | 100 | 100 | 100 | 100 | 100 | 100
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 | 2014-02-17 08:00 | 5d | 83320 | 0 | 0 | 0 | 0 | 83320 | 0 | 100% | Finished | 83320 | 83320 | 100 | 100 | 100 | 100 | 100 | 100
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 67d | [5 empty] | 363072 |  | 86.15% |  | 437248 | 507520
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-01-27 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-01-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 39040 | 39040 | 100 | 100 | 100 | 100 | 100 | 100
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-10 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-11 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-12 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-24 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 | 2014-01-30 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 31232 | 31232 | 100 | 62.5 | 100 | 100 | 62.5 | 100
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-26 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 39040 | 39040 | 100 | 100 | 100 | 100 | 100 | 100
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-01-27 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 11712 | 11712 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-04 08:00 | 8d | 31232 | 0 | 0 | 0 | 0 | 31232 | 0 | 100% | Finished | 39040 | 39040 | 100 | 80 | 100 | 100 | 80 | 100
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-27 08:00 | 2d | 7808 | 0 | 0 | 0 | 0 | 7808 | 0 | 100% | Finished | 39040 | 39040 | 100 | 20 | 100 | 100 | 20 | 100
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-03-17 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 27328 | 27328 | 100 | 142.8571 | 100 | 100 | 142.8571 | 100
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-03-17 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 19520 | 19520 | 100 | 200 | 100 | 100 | 200 | 100
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 46848 | 46848 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 11712 | 100 |  | 0 | 100 |  | 0
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 |  | 0 | 0 | 11712 | 3d | 0 | 0 | 0 | 11712 | 0% | Not Started | 0 | 11712 | 100 |  | 0 | 100 |  | 0
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 | 2014-04-01 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 66368 | 66368 | 100 | 58.8235 | 100 | 100 | 58.8235 | 100
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 7808 | 100 |  | 0 | 100 |  | 0
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-04-22 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 27328 | 27328 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 67d | [5 empty] | 382592 |  | 89.66% |  | 406016 | 452864
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 2014-01-27 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 15616 | 15616 | 100 | 100 | 100 | 100 | 100 | 100
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-01-31 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-03 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-12 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 | 2014-02-12 08:00 | 16d | 62464 | 0 | 0 | 0 | 0 | 62464 | 0 | 100% | Finished | 62464 | 62464 | 100 | 100 | 100 | 100 | 100 | 100
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-01-27 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 2014-01-30 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 7808 | 7808 | 100 | 150 | 100 | 100 | 150 | 100
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-04 08:00 | 2d | 7808 | 0 | 0 | 0 | 0 | 7808 | 0 | 100% | Finished | 39040 | 39040 | 100 | 20 | 100 | 100 | 20 | 100
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 27328 | 27328 | 100 | 142.8571 | 100 | 100 | 142.8571 | 100
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 19520 | 19520 | 100 | 200 | 100 | 100 | 200 | 100
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 2014-02-11 08:00 | 12d | 46848 | 0 | 0 | 0 | 0 | 46848 | 0 | 100% | Finished | 46848 | 46848 | 100 | 100 | 100 | 100 | 100 | 100
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-03-17 08:00 | 7d | 27328 | 0 | 0 | 0 | 0 | 27328 | 0 | 100% | Finished | 27328 | 27328 | 100 | 100 | 100 | 100 | 100 | 100
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-03-26 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 2014-04-07 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 15616 | 15616 | 100 | 100 | 100 | 100 | 100 | 100
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 | 2014-03-26 08:00 | 13d | 50752 | 0 | 0 | 0 | 0 | 50752 | 0 | 100% | Finished | 66368 | 66368 | 100 | 76.4706 | 100 | 100 | 76.4706 | 100
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 |  | 0 | 0 | 7808 | 2d | 0 | 0 | 0 | 7808 | 0% | Not Started | 0 | 7808 | 100 |  | 0 | 100 |  | 0
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 |  | 0 | 0 | 39040 | 10d | 0 | 0 | 0 | 39040 | 0% | Not Started | 0 | 39040 | 100 |  | 0 | 100 |  | 0
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-04-24 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 27328 | 27328 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 41d | [5 empty] | 138240 |  | 100% |  | 345600 | 345600
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 | 2014-03-17 08:00 | 2d | 11520 | 0 | 0 | 0 | 0 | 11520 | 0 | 100% | Finished | 57600 | 57600 | 100 | 20 | 100 | 100 | 20 | 100
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 | 2014-03-17 08:00 | 2d | 11520 | 0 | 0 | 0 | 0 | 11520 | 0 | 100% | Finished | 57600 | 57600 | 100 | 20 | 100 | 100 | 20 | 100
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 | 2014-01-21 08:00 | 10d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 86400 | 86400 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 | 2014-02-06 08:00 | 10d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 144000 | 144000 | 100 | 40 | 100 | 100 | 40 | 100
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 70d | [5 empty] | 41280 |  | 100% |  | 61920 | 61920
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 | 2014-04-15 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 10320 | 10320 | 100 | 100 | 100 | 100 | 100 | 100
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 | 2014-04-15 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 10320 | 10320 | 100 | 100 | 100 | 100 | 100 | 100
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 | 2014-01-21 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 15480 | 15480 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 | 2014-02-06 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 25800 | 25800 | 100 | 40 | 100 | 100 | 40 | 100
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 20d | [5 empty] | 138040 |  | 100% |  | 299880 | 299880
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 | 2014-02-26 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 14280 | 14280 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 2014-02-27 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 100% | Finished | 47600 | 47600 | 100 | 70 | 100 | 100 | 70 | 100
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 2014-03-17 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 100% | Finished | 47600 | 47600 | 100 | 70 | 100 | 100 | 70 | 100
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 | 2014-02-27 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 100% | Finished | 71400 | 71400 | 100 | 46.6667 | 100 | 100 | 46.6667 | 100
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 | 2014-03-17 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 100% | Finished | 119000 | 119000 | 100 | 28 | 100 | 100 | 28 | 100
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 19d | [5 empty] | 86400 |  | 100% |  | 86400 | 86400
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2014-01-27 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2014-02-05 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 | 2014-01-27 08:00 | 35d | 168000 | 0 | 0 | 0 | 0 | 168000 | 0 | 100% | Finished | 192000 | 192000 | 100 | 87.5 | 100 | 100 | 87.5 | 100
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 62d | [5 empty] | 99840 |  | 100% |  | 99840 | 99840
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 | 2014-01-31 08:00 | 15d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 | 2014-02-17 08:00 | 2d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 3840 | 3840 | 100 | 100 | 100 | 100 | 100 | 100
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 | 2014-03-11 08:00 | 35d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100

## TP9
| TP Status Date | 2014-07-04 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Industrial Complex (2) | 2013-02-18 08:00 | 2014-04-08 17:00 | 297d |  |  | 0 |  |  | 5999600 |  | 313d | [5 empty] | 5414544 |  | 100% |  | 5999600 | 5999600
6 | Voobereindende werken | 2013-02-18 08:00 | 2013-03-25 17:00 | 26d |  |  | 0 |  |  | 89984 |  | 5d | [5 empty] | 89984 |  | 100% |  | 89984 | 89984
1 | plaatsen werfhekkens | 2013-02-18 08:00 | 2013-02-18 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraakwerken | 2013-02-18 08:00 | 2013-02-21 17:00 | 4d |  | 0 | 0 | 1406 | 44992 | 44992 | 2013-02-18 08:00 | 4d | 44992 | 0 | 0 | 0 | 0 | 44992 | 0 | 100% | Finished | 44992 | 44992 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-18 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
4 | uitzetten assen | 2013-02-21 08:00 | 2013-02-21 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-22 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
5 | Fundering torenkraan | 2013-03-25 08:00 | 2013-03-25 17:00 | 1d |  | 0 | 0 | 1406 | 11248 | 11248 | 2013-02-21 08:00 | 1d | 11248 | 0 | 0 | 0 | 0 | 11248 | 0 | 100% | Finished | 11248 | 11248 | 100 | 100 | 100 | 100 | 100 | 100
13 | Riolering + Parkings | 2013-02-22 08:00 | 2013-03-19 17:00 | 18d |  |  | 0 |  |  | 130000 |  | 18d | [5 empty] | 130000 |  | 100% |  | 130000 | 130000
7 | droogzuiging | 2013-02-22 08:00 | 2013-02-22 17:00 | 1d |  | 0 | 0 | 625 | 5000 | 5000 | 2013-02-22 08:00 | 1d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Rechterdeel parking aanvullen + onderfundering | 2013-02-22 08:00 | 2013-02-28 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-02-22 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsing RW-putten + riolering | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 625 | 50000 | 50000 | 2013-03-04 08:00 | 10d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Linkerdeel parking aanvullen + onderfundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-03-11 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
11 | Overige parkeerplaatsen aanvullen + onderfundering | 2013-03-13 08:00 | 2013-03-15 17:00 | 3d |  | 0 | 0 | 625 | 15000 | 15000 | 2013-03-13 08:00 | 3d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 15000 | 15000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Uitbraak bestaande parking | 2013-03-18 08:00 | 2013-03-19 17:00 | 2d |  | 0 | 0 | 625 | 10000 | 10000 | 2013-03-18 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
39 | Productiehal | 2013-03-13 08:00 | 2013-09-23 17:00 | 139d |  |  | 0 |  |  | 1311416 |  | 136d | [5 empty] | 1311416 |  | 100% |  | 1311416 | 1311416
14 | Funderingswerken productiehal | 2013-03-18 08:00 | 2013-04-05 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-03-18 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ruwbouwwerken + onder dak productiehal | 2013-04-09 08:00 | 2013-06-28 17:00 | 59d |  |  | 0 |  |  | 504000 |  | 60d | [5 empty] | 504000 |  | 100% |  | 504000 | 504000
15 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-04-15 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 600 | 120000 | 120000 | 2013-04-15 08:00 | 25d | 120000 | 0 | 0 | 0 | 0 | 120000 | 0 | 100% | Finished | 120000 | 120000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Metselwerken technische lokalen + montage welfsels | 2013-05-13 08:00 | 2013-05-22 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-05-13 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
17 | uitbraak bestaande gevelelementen + schoring | 2013-04-09 08:00 | 2013-04-15 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-04-08 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
18 | staalconstructie rolbrug en spuitcabine | 2013-05-22 08:00 | 2013-05-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-22 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
19 | Onderfunderingen betonvloer + rioleringswerken + vloerisolatie rondom | 2013-05-27 08:00 | 2013-06-11 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-05-27 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
20 | Veiligheidsnetten + steeldeck | 2013-05-29 08:00 | 2013-06-14 17:00 | 13d |  | 0 | 0 | 600 | 62400 | 62400 | 2013-05-29 08:00 | 13d | 62400 | 0 | 0 | 0 | 0 | 62400 | 0 | 100% | Finished | 62400 | 62400 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie + dakbedekking + RWA | 2013-06-06 08:00 | 2013-06-26 17:00 | 15d |  | 0 | 0 | 600 | 72000 | 72000 | 2013-06-06 08:00 | 15d | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 100% | Finished | 72000 | 72000 | 100 | 100 | 100 | 100 | 100 | 100
22 | Rookkoepels | 2013-06-26 08:00 | 2013-06-27 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-26 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
23 | Netwapening + polybetonvloer | 2013-06-05 08:00 | 2013-06-18 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-06-05 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
24 | Metselwerken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
25 | Brandwerende schildering | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-24 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
29 | Binnenafwerking productiehal | 2013-09-18 08:00 | 2013-09-23 17:00 | 4d |  |  | 0 |  |  | 15616 |  | 8d | [5 empty] | 15616 |  | 100% |  | 15616 | 15616
27 | Stalen binnentrap | 2013-09-19 08:00 | 2013-09-23 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2013-09-09 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
28 | Binnendeuren | 2013-09-18 08:00 | 2013-09-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2013-09-18 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
33 | Gevelbekleding productiehal | 2013-06-19 08:00 | 2013-09-12 17:00 | 62d |  |  | 0 |  |  | 92928 |  | 62d | [5 empty] | 92928 |  | 100% |  | 92928 | 92928
30 | Alu buitenschrijnwerk + beglazing + polycarbonaatplaten | 2013-06-19 08:00 | 2013-07-02 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-06-19 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
31 | Montage poorten | 2013-08-26 08:00 | 2013-08-29 17:00 | 4d |  | 0 | 0 | 484 | 15488 | 15488 | 2013-08-26 08:00 | 4d | 15488 | 0 | 0 | 0 | 0 | 15488 | 0 | 100% | Finished | 15488 | 15488 | 100 | 100 | 100 | 100 | 100 | 100
32 | Gevelbekleding metaalcassettes | 2013-08-30 08:00 | 2013-09-12 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2013-08-30 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
38 | Technieken productiehal | 2013-03-13 08:00 | 2013-09-05 17:00 | 127d |  |  | 0 |  |  | 631312 |  | 127d | [5 empty] | 631312 |  | 100% |  | 631312 | 631312
34 | Afbraakwerken | 2013-03-13 08:00 | 2013-03-14 17:00 | 2d |  | 0 | 0 | 469 | 7504 | 7504 | 2013-03-13 08:00 | 2d | 7504 | 0 | 0 | 0 | 0 | 7504 | 0 | 100% | Finished | 7504 | 7504 | 100 | 100 | 100 | 100 | 100 | 100
35 | HVAC | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 720 | 311040 | 311040 | 2013-06-24 08:00 | 54d | 311040 | 0 | 0 | 0 | 0 | 311040 | 0 | 100% | Finished | 311040 | 311040 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 129 | 55728 | 55728 | 2013-06-24 08:00 | 54d | 55728 | 0 | 0 | 0 | 0 | 55728 | 0 | 100% | Finished | 55728 | 55728 | 100 | 100 | 100 | 100 | 100 | 100
37 | Elecktriciteit | 2013-06-24 08:00 | 2013-09-05 17:00 | 54d |  | 0 | 0 | 595 | 257040 | 257040 | 2013-06-24 08:00 | 54d | 257040 | 0 | 0 | 0 | 0 | 257040 | 0 | 100% | Finished | 257040 | 257040 | 100 | 100 | 100 | 100 | 100 | 100
60 | Stockruimte | 2013-05-02 08:00 | 2013-11-12 17:00 | 139d |  |  | 0 |  |  | 800216 |  | 142d | [5 empty] | 835152 |  | 100% |  | 800216 | 800216
40 | Afbraak | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d |  | 0 | 0 | 1406 | 56240 | 56240 | 2013-03-18 08:00 | 19d | 213712 | 0 | 0 | 0 | 0 | 213712 | 0 | 100% | Finished | 56240 | 56240 | 100 | 380 | 100 | 100 | 380 | 100
41 | Funderingswerken stockruimte | 2013-05-13 08:00 | 2013-05-20 17:00 | 6d |  | 0 | 0 | 563 | 27024 | 27024 | 2013-04-29 08:00 | 8d | 36032 | 0 | 0 | 0 | 0 | 36032 | 0 | 100% | Finished | 27024 | 27024 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
51 | Ruwbouwwerken + onder dak stockruimte | 2013-05-22 08:00 | 2013-08-15 17:00 | 62d |  |  | 0 |  |  | 196800 |  | 62d | [5 empty] | 196800 |  | 100% |  | 196800 | 196800
42 | Kolommen + balken + betonwanden + staalconstructie dak | 2013-05-24 08:00 | 2013-06-05 17:00 | 9d |  | 0 | 0 | 600 | 43200 | 43200 | 2013-05-24 08:00 | 9d | 43200 | 0 | 0 | 0 | 0 | 43200 | 0 | 100% | Finished | 43200 | 43200 | 100 | 100 | 100 | 100 | 100 | 100
43 | Uitbraak bestaande gevelelementen | 2013-05-22 08:00 | 2013-05-22 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-05-22 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
44 | Nivelleren + rioleringswerken | 2013-06-06 08:00 | 2013-06-06 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-06 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
45 | Onderfundering betonvloer + vloerisolatie rondom | 2013-06-06 08:00 | 2013-06-13 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2013-06-06 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
46 | Veiligheidsnetten + steeldeck | 2013-06-14 08:00 | 2013-06-20 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-06-14 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
47 | Paaltjes leeflijn | 2013-06-21 08:00 | 2013-06-21 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-21 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
48 | Isolatie + dakbedeking + RWA | 2013-06-24 08:00 | 2013-07-03 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-24 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
49 | Netbewapening + polybetonvloer | 2013-07-04 08:00 | 2013-07-12 17:00 | 7d |  | 0 | 0 | 600 | 33600 | 33600 | 2013-07-04 08:00 | 7d | 33600 | 0 | 0 | 0 | 0 | 33600 | 0 | 100% | Finished | 33600 | 33600 | 100 | 100 | 100 | 100 | 100 | 100
50 | Brandwerende schildering | 2013-08-13 08:00 | 2013-08-15 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-08-13 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
54 | Gevelbekledingen stockruimte | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  |  | 0 |  |  | 15488 |  | 3d | [5 empty] | 15488 |  | 100% |  | 15488 | 15488
52 | Alu buitenschrijnwerk + beglazing | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-09-19 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
53 | Montage poorten | 2013-09-18 08:00 | 2013-09-20 17:00 | 3d |  | 0 | 0 | 484 | 11616 | 11616 | 2013-09-18 08:00 | 3d | 11616 | 0 | 0 | 0 | 0 | 11616 | 0 | 100% | Finished | 11616 | 11616 | 100 | 100 | 100 | 100 | 100 | 100
59 | technieken stockruimte | 2013-05-08 08:00 | 2013-11-12 17:00 | 135d |  |  | 0 |  |  | 504664 |  | 136d | [5 empty] | 373120 |  | 100% |  | 504664 | 504664
55 | Afbraakwerken | 2013-05-08 08:00 | 2013-05-08 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-03-26 08:00 | 4d | 15008 | 0 | 0 | 0 | 0 | 15008 | 0 | 100% | Finished | 3752 | 3752 | 100 | 400 | 100 | 100 | 400 | 100
56 | HVAC | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 720 | 178560 | 178560 | 2013-08-20 08:00 | 31d | 178560 | 0 | 0 | 0 | 0 | 178560 | 0 | 100% | Finished | 178560 | 178560 | 100 | 100 | 100 | 100 | 100 | 100
57 | Sanitair | 2013-08-20 08:00 | 2013-10-01 17:00 | 31d |  | 0 | 0 | 129 | 31992 | 31992 | 2013-08-20 08:00 | 31d | 31992 | 0 | 0 | 0 | 0 | 31992 | 0 | 100% | Finished | 31992 | 31992 | 100 | 100 | 100 | 100 | 100 | 100
58 | Elektriciteit | 2013-08-20 08:00 | 2013-11-12 17:00 | 61d |  | 0 | 0 | 595 | 290360 | 290360 | 2013-08-20 08:00 | 31d | 147560 | 0 | 0 | 0 | 0 | 147560 | 0 | 100% | Finished | 290360 | 290360 | 100 | 50.8197 | 100 | 100 | 50.8197 | 100
79 | Straalcabine | 2013-05-22 08:00 | 2013-09-05 17:00 | 77d |  |  | 0 |  |  | 710216 |  | 83d | [5 empty] | 714720 |  | 100% |  | 710216 | 710216
61 | Funderingswerken | 2013-05-22 08:00 | 2013-05-27 17:00 | 4d |  | 0 | 0 | 563 | 18016 | 18016 | 2013-05-14 08:00 | 5d | 22520 | 0 | 0 | 0 | 0 | 22520 | 0 | 100% | Finished | 18016 | 18016 | 100 | 125 | 100 | 100 | 125 | 100
67 | Ruwbouwwerken + straalcabine | 2013-05-28 08:00 | 2013-06-28 17:00 | 24d |  |  | 0 |  |  | 48000 |  | 28d | [5 empty] | 48000 |  | 100% |  | 48000 | 48000
62 | Uitbraak bestaande gevelelementen + onderfundering + riolering + vloerisolatie rondom | 2013-05-28 08:00 | 2013-05-29 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-05-22 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
63 | Kolommen + balken + betonwanden + staalconstructie | 2013-06-06 08:00 | 2013-06-11 17:00 | 4d |  | 0 | 0 | 600 | 19200 | 19200 | 2013-06-06 08:00 | 4d | 19200 | 0 | 0 | 0 | 0 | 19200 | 0 | 100% | Finished | 19200 | 19200 | 100 | 100 | 100 | 100 | 100 | 100
64 | Welfsels + opstort | 2013-06-12 08:00 | 2013-06-12 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-12 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
65 | Netwapening + polybetonvloer | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 600 | 9600 | 9600 | 2013-06-19 08:00 | 2d | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 100% | Finished | 9600 | 9600 | 100 | 100 | 100 | 100 | 100 | 100
66 | Brandwerende schildering | 2013-06-28 08:00 | 2013-06-28 17:00 | 1d |  | 0 | 0 | 600 | 4800 | 4800 | 2013-06-28 08:00 | 1d | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 100% | Finished | 4800 | 4800 | 100 | 100 | 100 | 100 | 100 | 100
70 | Gevelbekledingen straalcabine | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  |  | 0 |  |  | 7744 |  | 1d | [5 empty] | 7744 |  | 100% |  | 7744 | 7744
68 | Alu buitenschrijnwerk + beglazing | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
69 | Montage poorten | 2013-08-28 08:00 | 2013-08-28 17:00 | 1d |  | 0 | 0 | 484 | 3872 | 3872 | 2013-08-28 08:00 | 1d | 3872 | 0 | 0 | 0 | 0 | 3872 | 0 | 100% | Finished | 3872 | 3872 | 100 | 100 | 100 | 100 | 100 | 100
73 | Dakwerken | 2013-06-13 08:00 | 2013-06-18 17:00 | 4d |  |  | 0 |  |  | 66656 |  | 4d | [5 empty] | 66656 |  | 100% |  | 66656 | 66656
72 | Isolatie + roofing | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 2083 | 49992 | 49992 | 2013-06-14 08:00 | 3d | 49992 | 0 | 0 | 0 | 0 | 49992 | 0 | 100% | Finished | 49992 | 49992 | 100 | 100 | 100 | 100 | 100 | 100
71 | paaltjes leeflijn | 2013-06-13 08:00 | 2013-06-13 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2013-06-13 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
78 | Technieken straalcabine | 2013-05-27 08:00 | 2013-09-05 17:00 | 74d |  |  | 0 |  |  | 569800 |  | 78d | [5 empty] | 569800 |  | 100% |  | 569800 | 569800
77 | Elektriciteit | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 595 | 233240 | 233240 | 2013-07-01 08:00 | 49d | 233240 | 0 | 0 | 0 | 0 | 233240 | 0 | 100% | Finished | 233240 | 233240 | 100 | 100 | 100 | 100 | 100 | 100
74 | Afbraakwerken | 2013-05-27 08:00 | 2013-05-27 17:00 | 1d |  | 0 | 0 | 469 | 3752 | 3752 | 2013-05-21 08:00 | 1d | 3752 | 0 | 0 | 0 | 0 | 3752 | 0 | 100% | Finished | 3752 | 3752 | 100 | 100 | 100 | 100 | 100 | 100
75 | HVAC | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 720 | 282240 | 282240 | 2013-07-01 08:00 | 49d | 282240 | 0 | 0 | 0 | 0 | 282240 | 0 | 100% | Finished | 282240 | 282240 | 100 | 100 | 100 | 100 | 100 | 100
76 | Sanitair | 2013-07-01 08:00 | 2013-09-05 17:00 | 49d |  | 0 | 0 | 129 | 50568 | 50568 | 2013-07-01 08:00 | 49d | 50568 | 0 | 0 | 0 | 0 | 50568 | 0 | 100% | Finished | 50568 | 50568 | 100 | 100 | 100 | 100 | 100 | 100
80 | Opkuis | 2013-09-23 08:00 | 2013-10-01 17:00 | 7d |  | 0 | 0 | 25 | 1400 | 1400 | 2013-09-23 08:00 | 7d | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 100% | Finished | 1400 | 1400 | 100 | 100 | 100 | 100 | 100 | 100
83 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-14 17:00 | 18d |  |  | 0 |  |  | 107560 |  | 15d | [5 empty] | 107560 |  | 100% |  | 107560 | 107560
81 | Funderingswerken kantoor | 2013-05-22 08:00 | 2013-06-11 17:00 | 15d |  | 0 | 0 | 563 | 67560 | 67560 | 2013-04-15 08:00 | 15d | 67560 | 0 | 0 | 0 | 0 | 67560 | 0 | 100% | Finished | 67560 | 67560 | 100 | 100 | 100 | 100 | 100 | 100
82 | Rioleringswerken kantoor + aanvulling stabilisé + steenslag | 2013-06-05 08:00 | 2013-06-14 17:00 | 8d |  | 0 | 0 | 625 | 40000 | 40000 | 2013-04-15 08:00 | 8d | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 100% | Finished | 40000 | 40000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Ruwbouw kantoor niv 0 | 2013-06-13 08:00 | 2013-07-12 17:00 | 22d |  |  | 0 |  |  | 187200 |  | 21d | [5 empty] | 187200 |  | 100% |  | 187200 | 187200
84 | Vloerplaat gelijkvloers | 2013-06-13 08:00 | 2013-06-19 17:00 | 5d |  | 0 | 0 | 600 | 24000 | 24000 | 2013-05-31 08:00 | 5d | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 100% | Finished | 24000 | 24000 | 100 | 100 | 100 | 100 | 100 | 100
85 | Kolommen + balken gelijkvloers | 2013-06-20 08:00 | 2013-07-05 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-06-06 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
86 | Metselwerken gelijkvloers | 2013-06-20 08:00 | 2013-07-09 17:00 | 14d |  | 0 | 0 | 600 | 67200 | 67200 | 2013-06-06 08:00 | 14d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100
87 | Afdek 0 + wapenen + opstort | 2013-07-03 08:00 | 2013-07-12 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-06-19 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
92 | Ruwbouw kantoor niv +1 | 2013-08-06 08:00 | 2013-09-04 17:00 | 22d |  |  | 0 |  |  | 144000 |  | 21d | [5 empty] | 144000 |  | 100% |  | 144000 | 144000
89 | Kolommen + balken 1ste | 2013-08-06 08:00 | 2013-08-21 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2013-07-03 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
90 | Metselwerken 1ste | 2013-08-06 08:00 | 2013-08-19 17:00 | 10d |  | 0 | 0 | 600 | 48000 | 48000 | 2013-07-03 08:00 | 10d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 100 | 100 | 100 | 100 | 100 | 100
91 | Afdek 1 + wapenen + opstort | 2013-08-26 08:00 | 2013-09-04 17:00 | 8d |  | 0 | 0 | 600 | 38400 | 38400 | 2013-07-22 08:00 | 8d | 38400 | 0 | 0 | 0 | 0 | 38400 | 0 | 100% | Finished | 38400 | 38400 | 100 | 100 | 100 | 100 | 100 | 100
93 | Metselwerken dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 600 | 14400 | 14400 | 2013-07-29 08:00 | 3d | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 100% | Finished | 14400 | 14400 | 100 | 100 | 100 | 100 | 100 | 100
97 | Gevelbekledingen kantoor | 2013-09-05 08:00 | 2013-11-01 17:00 | 42d |  |  | 0 |  |  | 123904 |  | 51d | [5 empty] | 104544 |  | 100% |  | 123904 | 123904
94 | Buitenschrijnwerk + beglazing gelijkvloers | 2013-10-03 08:00 | 2013-10-18 17:00 | 12d |  | 0 | 0 | 484 | 46464 | 46464 | 2014-03-26 08:00 | 12d | 46464 | 0 | 0 | 0 | 0 | 46464 | 0 | 100% | Finished | 46464 | 46464 | 100 | 100 | 100 | 100 | 100 | 100
95 | Buitenschrijnwerk + beglazing 1ste | 2013-09-05 08:00 | 2013-09-18 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2014-03-13 08:00 | 10d | 38720 | 0 | 0 | 0 | 0 | 38720 | 0 | 100% | Finished | 38720 | 38720 | 100 | 100 | 100 | 100 | 100 | 100
96 | Gevelbekleding metaalcasettes | 2013-10-21 08:00 | 2013-11-01 17:00 | 10d |  | 0 | 0 | 484 | 38720 | 38720 | 2014-01-30 08:00 | 5d | 19360 | 0 | 0 | 0 | 0 | 19360 | 0 | 100% | Finished | 38720 | 38720 | 100 | 50 | 100 | 100 | 50 | 100
102 | Dakwerken kantoor | 2013-09-10 08:00 | 2013-10-08 17:00 | 21d |  |  | 0 |  |  | 333280 |  | 19d | [5 empty] | 333280 |  | 100% |  | 333280 | 333280
98 | Hellingsbeton | 2013-09-10 08:00 | 2013-09-10 17:00 | 1d |  | 0 | 0 | 2083 | 16664 | 16664 | 2014-01-28 08:00 | 1d | 16664 | 0 | 0 | 0 | 0 | 16664 | 0 | 100% | Finished | 16664 | 16664 | 100 | 100 | 100 | 100 | 100 | 100
99 | isolatie + dakbedekking + ballast | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 2083 | 166640 | 166640 | 2014-02-05 08:00 | 10d | 166640 | 0 | 0 | 0 | 0 | 166640 | 0 | 100% | Finished | 166640 | 166640 | 100 | 100 | 100 | 100 | 100 | 100
100 | RW-afvoeren | 2013-09-30 08:00 | 2013-10-03 17:00 | 4d |  | 0 | 0 | 2083 | 66656 | 66656 | 2014-02-17 08:00 | 4d | 66656 | 0 | 0 | 0 | 0 | 66656 | 0 | 100% | Finished | 66656 | 66656 | 100 | 100 | 100 | 100 | 100 | 100
101 | Lichtstraat | 2013-10-02 08:00 | 2013-10-08 17:00 | 5d |  | 0 | 0 | 2083 | 83320 | 83320 | 2014-02-17 08:00 | 5d | 83320 | 0 | 0 | 0 | 0 | 83320 | 0 | 100% | Finished | 83320 | 83320 | 100 | 100 | 100 | 100 | 100 | 100
123 | Niv 0 | 2013-10-11 08:00 | 2014-04-01 17:00 | 123d |  |  | 0 |  |  | 507520 |  | 68d | [5 empty] | 378688 |  | 100% |  | 507520 | 507520
103 | Cementage | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-01-27 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
104 | Pleisterwerken | 2013-10-11 08:00 | 2013-10-24 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-01-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 39040 | 39040 | 100 | 100 | 100 | 100 | 100 | 100
105 | Uitvullingslaag polystyreenkorrels | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-10 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
106 | Vloerisolatie PU platen | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-11 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
107 | Chape | 2013-11-05 08:00 | 2013-11-11 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-12 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
108 | Polybetonvloer | 2013-11-15 08:00 | 2013-11-15 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-24 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
109 | Stalen trappen kantoor | 2014-01-13 08:00 | 2014-01-22 17:00 | 8d |  | 0 | 0 | 488 | 31232 | 31232 | 2014-01-30 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 31232 | 31232 | 100 | 62.5 | 100 | 100 | 62.5 | 100
110 | Lichte scheidingswanden en voorzetwanden | 2013-11-19 08:00 | 2013-12-02 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-26 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 39040 | 39040 | 100 | 100 | 100 | 100 | 100 | 100
111 | Vloerbekleding keramische tegels | 2013-12-03 08:00 | 2013-12-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-01-27 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 11712 | 11712 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
112 | Faience | 2013-12-06 08:00 | 2013-12-19 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-04 08:00 | 8d | 31232 | 0 | 0 | 0 | 0 | 31232 | 0 | 100% | Finished | 39040 | 39040 | 100 | 80 | 100 | 100 | 80 | 100
113 | Binnendeuren en binnenramen | 2013-12-03 08:00 | 2013-12-16 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-27 08:00 | 2d | 7808 | 0 | 0 | 0 | 0 | 7808 | 0 | 100% | Finished | 39040 | 39040 | 100 | 20 | 100 | 100 | 20 | 100
114 | Zichtwanden op binnenwanden | 2013-12-17 08:00 | 2013-12-25 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-03-17 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 27328 | 27328 | 100 | 142.8571 | 100 | 100 | 142.8571 | 100
115 | Vast meubilair | 2014-01-09 08:00 | 2014-01-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-03-17 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 19520 | 19520 | 100 | 200 | 100 | 100 | 200 | 100
116 | Plafonds | 2014-01-16 08:00 | 2014-01-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 46848 | 46848 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
117 | Vloerbekleding tapijt | 2014-02-03 08:00 | 2014-02-05 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 11712 | 11712 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
118 | Plinten | 2014-02-06 08:00 | 2014-02-10 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 11712 | 11712 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
119 | Schilderwerken | 2014-02-11 08:00 | 2014-03-05 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 | 2014-04-01 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 66368 | 66368 | 100 | 58.8235 | 100 | 100 | 58.8235 | 100
120 | Binnenzonnewering | 2014-03-06 08:00 | 2014-03-07 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 7808 | 7808 | 100 | 50 | 100 | 100 | 50 | 100
121 | Allerhande aanwerkingen | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 39040 | 39040 | 100 | 10 | 100 | 100 | 10 | 100
122 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-04-22 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 27328 | 27328 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
142 | Niv +1 | 2013-10-02 08:00 | 2014-04-01 17:00 | 130d |  |  | 0 |  |  | 452864 |  | 68d | [5 empty] | 390400 |  | 100% |  | 452864 | 452864
124 | Pleisterwerken | 2013-10-02 08:00 | 2013-10-07 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 2014-01-27 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 15616 | 15616 | 100 | 100 | 100 | 100 | 100 | 100
125 | Pur uitvullingslaag | 2013-10-08 08:00 | 2013-10-08 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-01-31 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
126 | Chape | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-03 08:00 | 5d | 19520 | 0 | 0 | 0 | 0 | 19520 | 0 | 100% | Finished | 19520 | 19520 | 100 | 100 | 100 | 100 | 100 | 100
127 | Polybetonvloer | 2013-10-18 08:00 | 2013-10-18 17:00 | 1d |  | 0 | 0 | 488 | 3904 | 3904 | 2014-02-12 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 3904 | 3904 | 100 | 100 | 100 | 100 | 100 | 100
128 | Lichte scheidingswanden en voorzetwanden | 2013-10-21 08:00 | 2013-11-11 17:00 | 16d |  | 0 | 0 | 488 | 62464 | 62464 | 2014-02-12 08:00 | 16d | 62464 | 0 | 0 | 0 | 0 | 62464 | 0 | 100% | Finished | 62464 | 62464 | 100 | 100 | 100 | 100 | 100 | 100
129 | Vloerbekleding keramische tegels | 2013-11-14 08:00 | 2013-11-18 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-01-27 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
130 | Faience | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 2014-01-30 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 7808 | 7808 | 100 | 150 | 100 | 100 | 150 | 100
131 | Binnendeuren en binnenramen | 2013-11-14 08:00 | 2013-11-27 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-02-04 08:00 | 2d | 7808 | 0 | 0 | 0 | 0 | 7808 | 0 | 100% | Finished | 39040 | 39040 | 100 | 20 | 100 | 100 | 20 | 100
132 | Zichtwanden op binnenwanden | 2013-11-28 08:00 | 2013-12-06 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 27328 | 27328 | 100 | 142.8571 | 100 | 100 | 142.8571 | 100
133 | Vast meubilair | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 488 | 19520 | 19520 | 2014-02-27 08:00 | 10d | 39040 | 0 | 0 | 0 | 0 | 39040 | 0 | 100% | Finished | 19520 | 19520 | 100 | 200 | 100 | 100 | 200 | 100
134 | Plafonds | 2013-12-16 08:00 | 2013-12-31 17:00 | 12d |  | 0 | 0 | 488 | 46848 | 46848 | 2014-02-11 08:00 | 12d | 46848 | 0 | 0 | 0 | 0 | 46848 | 0 | 100% | Finished | 46848 | 46848 | 100 | 100 | 100 | 100 | 100 | 100
135 | Vloerbekleding tapijt | 2014-01-15 08:00 | 2014-01-23 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-03-17 08:00 | 7d | 27328 | 0 | 0 | 0 | 0 | 27328 | 0 | 100% | Finished | 27328 | 27328 | 100 | 100 | 100 | 100 | 100 | 100
136 | Plinten | 2014-01-24 08:00 | 2014-01-28 17:00 | 3d |  | 0 | 0 | 488 | 11712 | 11712 | 2014-03-26 08:00 | 3d | 11712 | 0 | 0 | 0 | 0 | 11712 | 0 | 100% | Finished | 11712 | 11712 | 100 | 100 | 100 | 100 | 100 | 100
137 | Borstweringen | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  | 0 | 0 | 488 | 15616 | 15616 | 2014-04-07 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 15616 | 15616 | 100 | 100 | 100 | 100 | 100 | 100
138 | Schilderwerken | 2014-01-24 08:00 | 2014-02-17 17:00 | 17d |  | 0 | 0 | 488 | 66368 | 66368 | 2014-03-26 08:00 | 13d | 50752 | 0 | 0 | 0 | 0 | 50752 | 0 | 100% | Finished | 66368 | 66368 | 100 | 76.4706 | 100 | 100 | 76.4706 | 100
139 | Binnenzonneweringen en gordijnen | 2014-02-18 08:00 | 2014-02-19 17:00 | 2d |  | 0 | 0 | 488 | 7808 | 7808 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 7808 | 7808 | 100 | 50 | 100 | 100 | 50 | 100
140 | Allerhande aanwerkingen | 2014-02-20 08:00 | 2014-03-05 17:00 | 10d |  | 0 | 0 | 488 | 39040 | 39040 | 2014-04-30 08:00 | 1d | 3904 | 0 | 0 | 0 | 0 | 3904 | 0 | 100% | Finished | 39040 | 39040 | 100 | 10 | 100 | 100 | 10 | 100
141 | Opkuis | 2014-03-24 08:00 | 2014-04-01 17:00 | 7d |  | 0 | 0 | 488 | 27328 | 27328 | 2014-04-24 08:00 | 4d | 15616 | 0 | 0 | 0 | 0 | 15616 | 0 | 100% | Finished | 27328 | 27328 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
147 | HVAC | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 345600 |  | 41d | [5 empty] | 138240 |  | 100% |  | 345600 | 345600
143 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 | 2014-03-17 08:00 | 2d | 11520 | 0 | 0 | 0 | 0 | 11520 | 0 | 100% | Finished | 57600 | 57600 | 100 | 20 | 100 | 100 | 20 | 100
144 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 720 | 57600 | 57600 | 2014-03-17 08:00 | 2d | 11520 | 0 | 0 | 0 | 0 | 11520 | 0 | 100% | Finished | 57600 | 57600 | 100 | 20 | 100 | 100 | 20 | 100
145 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 720 | 86400 | 86400 | 2014-01-21 08:00 | 10d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 86400 | 86400 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
146 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 720 | 144000 | 144000 | 2014-02-06 08:00 | 10d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 144000 | 144000 | 100 | 40 | 100 | 100 | 40 | 100
152 | Sanitair | 2013-09-18 08:00 | 2014-01-15 17:00 | 86d |  |  | 0 |  |  | 61920 |  | 70d | [5 empty] | 41280 |  | 100% |  | 61920 | 61920
148 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 | 2014-04-15 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 10320 | 10320 | 100 | 100 | 100 | 100 | 100 | 100
149 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 129 | 10320 | 10320 | 2014-04-15 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 10320 | 10320 | 100 | 100 | 100 | 100 | 100 | 100
150 | Leidingen in plafonds 1ste | 2013-11-25 08:00 | 2013-12-13 17:00 | 15d |  | 0 | 0 | 129 | 15480 | 15480 | 2014-01-21 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 15480 | 15480 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
151 | Leidingen in plafonds gelijkvloers | 2013-12-12 08:00 | 2014-01-15 17:00 | 25d |  | 0 | 0 | 129 | 25800 | 25800 | 2014-02-06 08:00 | 10d | 10320 | 0 | 0 | 0 | 0 | 10320 | 0 | 100% | Finished | 25800 | 25800 | 100 | 40 | 100 | 100 | 40 | 100
158 | Elektriciteit | 2013-09-05 08:00 | 2014-01-22 17:00 | 100d |  |  | 0 |  |  | 299880 |  | 20d | [5 empty] | 138040 |  | 100% |  | 299880 | 299880
153 | Leidingen op dakplaat | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 595 | 14280 | 14280 | 2014-02-26 08:00 | 1d | 4760 | 0 | 0 | 0 | 0 | 4760 | 0 | 100% | Finished | 14280 | 14280 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
154 | Leidingen in vloeren en wanden 1ste | 2013-09-18 08:00 | 2013-10-01 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 2014-02-27 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 100% | Finished | 47600 | 47600 | 100 | 70 | 100 | 100 | 70 | 100
155 | Leidingen in vloeren en wanden gelijkvloers | 2013-09-27 08:00 | 2013-10-10 17:00 | 10d |  | 0 | 0 | 595 | 47600 | 47600 | 2014-03-17 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 100% | Finished | 47600 | 47600 | 100 | 70 | 100 | 100 | 70 | 100
156 | Leidingen in plafonds 1ste | 2013-12-02 08:00 | 2013-12-20 17:00 | 15d |  | 0 | 0 | 595 | 71400 | 71400 | 2014-02-27 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 100% | Finished | 71400 | 71400 | 100 | 46.6667 | 100 | 100 | 46.6667 | 100
157 | Leidingen in plafonds gelijkvloers | 2013-12-19 08:00 | 2014-01-22 17:00 | 25d |  | 0 | 0 | 595 | 119000 | 119000 | 2014-03-17 08:00 | 7d | 33320 | 0 | 0 | 0 | 0 | 33320 | 0 | 100% | Finished | 119000 | 119000 | 100 | 28 | 100 | 100 | 28 | 100
161 | Bestaande loods | 2013-09-10 08:00 | 2013-10-03 17:00 | 18d |  |  | 0 |  |  | 86400 |  | 19d | [5 empty] | 86400 |  | 100% |  | 86400 | 86400
159 | Kolommen + balken + welfsels | 2013-09-10 08:00 | 2013-09-17 17:00 | 6d |  | 0 | 0 | 600 | 28800 | 28800 | 2014-01-27 08:00 | 6d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
160 | Metselwerken | 2013-09-18 08:00 | 2013-10-03 17:00 | 12d |  | 0 | 0 | 600 | 57600 | 57600 | 2014-02-05 08:00 | 12d | 57600 | 0 | 0 | 0 | 0 | 57600 | 0 | 100% | Finished | 57600 | 57600 | 100 | 100 | 100 | 100 | 100 | 100
162 | Bestaande kantoren | 2014-02-12 08:00 | 2014-04-08 17:00 | 40d |  | 0 | 0 | 600 | 192000 | 192000 | 2014-01-27 08:00 | 35d | 168000 | 0 | 0 | 0 | 0 | 168000 | 0 | 100% | Finished | 192000 | 192000 | 100 | 87.5 | 100 | 100 | 87.5 | 100
166 | Omgevingswerken | 2013-10-04 08:00 | 2014-04-01 17:00 | 128d |  |  | 0 |  |  | 99840 |  | 62d | [5 empty] | 99840 |  | 100% |  | 99840 | 99840
163 | Laadkade | 2013-10-04 08:00 | 2013-10-24 17:00 | 15d |  | 0 | 0 | 240 | 28800 | 28800 | 2014-01-31 08:00 | 15d | 28800 | 0 | 0 | 0 | 0 | 28800 | 0 | 100% | Finished | 28800 | 28800 | 100 | 100 | 100 | 100 | 100 | 100
164 | Dockleveler | 2013-12-10 08:00 | 2013-12-11 17:00 | 2d |  | 0 | 0 | 240 | 3840 | 3840 | 2014-02-17 08:00 | 2d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 3840 | 3840 | 100 | 100 | 100 | 100 | 100 | 100
165 | Buitenaanleg | 2014-02-12 08:00 | 2014-04-01 17:00 | 35d |  | 0 | 0 | 240 | 67200 | 67200 | 2014-03-11 08:00 | 35d | 67200 | 0 | 0 | 0 | 0 | 67200 | 0 | 100% | Finished | 67200 | 67200 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
11/04, 2013 | 2013-02-18 08:00 | 2013-04-11 17:00 | 309448 | 371280.0015 | 531720 | 2013-04-29 17:00 | 61832.0015 | 120% | -160439.9985 | 69.83% | 12d | 130.8% | 84.51% | 2014-04-03 17:00 | 2014-01-29 12:00 | 2014-06-27 12:00 | 2014-03-28 10:00 | 2014-01-29 12:00 | 2014-06-04 14:00 | 2014-03-21 17:00 | 2014-01-01 09:00 | 2014-04-24 11:00 | 6160039.9985 | 8592187.2951 | 5222714.2894 | 4835729.4106 | 7249818.129 | 6695606.7551 | 7579695.6101 | 7394284.1041 | 1.3077 | 0.69826 | 1.1998 | 0.8451 | 12 | 0.69826 | 1 | 1.3077 | 1
05/06, 2013 | 2013-04-11 17:00 | 2013-06-05 17:00 | 794376 | 866592.0016 | 1048832 | 2013-06-07 16:00 | 72216.0016 | 109.1% | -182239.9984 | 82.62% | 1d 7h | 102.4% | 93.25% | 2014-04-03 11:00 | 2014-03-05 10:00 | 2014-05-23 12:00 | 2014-03-28 16:00 | 2014-03-05 10:00 | 2014-05-01 09:00 | 2014-04-07 09:00 | 2014-03-28 17:00 | 2014-05-30 14:00 | 6181839.9984 | 7261286.113 | 5754089.3229 | 6061346.8529 | 6743581.5928 | 7115453.8568 | 6887251.4353 | 6977437.8978 | 1.024 | 0.82624 | 1.0909 | 0.93249 | 1.875 | 0.82624 | 1 | 1.024 | 1
30/07, 2013 | 2013-06-05 17:00 | 2013-07-30 17:00 | 2104416 | 2253215.9972 | 2435456 | 2013-08-07 15:00 | 148799.9972 | 107.1% | -182240.0028 | 92.52% | 5d 6h | 104.9% | 94.11% | 2014-03-28 14:00 | 2014-03-12 11:00 | 2014-04-11 16:00 | 2014-03-27 15:00 | 2014-03-12 11:00 | 2014-03-31 11:00 | 2014-04-01 10:00 | 2014-03-20 09:00 | 2014-04-08 12:00 | 6181840.0028 | 6484847.363 | 5934432.7725 | 6006347.4731 | 6217429.8477 | 6295161.0059 | 6361333.5239 | 6379156.1047 | 1.0491 | 0.92517 | 1.0707 | 0.94106 | 5.75 | 0.92517 | 1 | 1.0491 | 1
23/09, 2013 | 2013-07-30 17:00 | 2013-09-23 17:00 | 3513608 | 3398241.2932 | 3465320 | 2013-09-19 14:00 | -115366.7068 | 96.72% | -67078.7068 | 98.06% | -2d 3h | 98.48% | 95.51% | 2014-04-16 15:00 | 2014-04-23 09:00 | 2014-05-01 09:00 | 2014-04-16 09:00 | 2014-04-23 09:00 | 2014-04-28 09:00 | 2014-04-11 11:00 | 2014-04-15 14:00 | 2014-04-18 12:00 | 6066678.7068 | 6118027.5555 | 6154992.0905 | 6106894.9927 | 6208084.1784 | 6159037.6804 | 6125338.957 | 6115793.5426 | 0.98478 | 0.98064 | 0.96717 | 0.95515 | -2.375 | 0.98064 | 1 | 0.98478 | 1
15/11, 2013 | 2013-09-23 17:00 | 2013-11-15 17:00 | 4524912 | 3496392 | 3535832 | 2013-09-23 14:00 | -1028520 | 77.27% | -39440 | 98.88% | -39d 3h | 79.81% | 93.76% | 2014-06-18 16:00 | 2014-08-08 11:00 | 2014-08-14 15:00 | 2014-06-10 11:00 | 2014-08-08 11:00 | 2014-08-12 12:00 | 2014-06-03 11:00 | 2014-07-23 09:00 | 2014-07-25 09:00 | 6039040 | 6067276.6861 | 6775398.9358 | 6672381.7831 | 6811941.8978 | 6707762.6911 | 6183003.3217 | 6168870.1513 | 0.79808 | 0.98885 | 0.7727 | 0.93759 | -39.375 | 0.98885 | 1 | 0.79808 | 1
09/01, 2014 | 2013-11-15 17:00 | 2014-01-09 17:00 | 5209720 | 3496392 | 3535832 | 2013-09-23 14:00 | -1713328 | 67.11% | -39440 | 98.88% | -78d 3h | 66.51% | 93.76% | 2014-08-05 16:00 | 2014-10-29 12:00 | 2014-11-05 12:00 | 2014-07-24 17:00 | 2014-10-29 12:00 | 2014-10-31 16:00 | 2014-07-28 11:00 | 2014-11-04 14:00 | 2014-11-06 17:00 | 6039040 | 6067276.6861 | 7265680.593 | 7299691.7398 | 7307754.03 | 7342148.8293 | 6241118.9405 | 6244669.7139 | 0.66506 | 0.98885 | 0.67113 | 0.93759 | -78.375 | 0.98885 | 1 | 0.66506 | 1
05/03, 2014 | 2014-01-09 17:00 | 2014-03-05 17:00 | 5746416 | 4980792.0002 | 4747840 | 2013-12-19 16:00 | -765623.9998 | 86.68% | 232952.0002 | 104.9% | -54d 1h | 80.17% | 92.93% | 2014-05-30 16:00 | 2014-06-11 14:00 | 2014-05-20 14:00 | 2014-05-29 11:00 | 2014-06-11 14:00 | 2014-06-06 11:00 | 2014-06-24 09:00 | 2014-07-21 12:00 | 2014-07-14 16:00 | 5766647.9998 | 5718998.2763 | 5923254.3901 | 6018586.243 | 5868280.1745 | 5959153.3498 | 5753965.9222 | 5767055.8332 | 0.80174 | 1.0491 | 0.86676 | 0.92934 | -54.125 | 1.0491 | 1 | 0.80174 | 1
29/04, 2014 | 2014-03-05 17:00 | 2014-04-29 17:00 | 5999600 | 5882480 | 5391120 | 2014-03-24 12:00 | -117120 | 98.05% | 491360 | 109.1% | -26d 4h | 91.51% | 98.01% | 2014-04-16 15:00 | 2014-04-16 16:00 | 2014-03-12 14:00 | 2014-05-08 09:00 | 2014-05-08 10:00 | 2014-05-07 15:00 | 2014-05-15 12:00 | 2014-05-16 14:00 | 2014-05-15 12:00 | 5508240 | 5498457.0372 | 5510571.8557 | 5519111.0333 | 5500594.1144 | 5508420.0196 | 5500679.3409 | 5502036.7797 | 0.91506 | 1.0911 | 0.98048 | 0.98009 | -26.5 | 1.0911 | 1 | 0.91506 | 1
Actual Schedule | 2014-04-29 17:00 | 2014-07-04 17:00 | 5999600 | 5999600 | 5414544 | 2014-04-08 17:00 | 0 | 100% | 585056 | 110.8% | -63d | 82.5% | 100% | 2014-04-08 17:00 | 2014-04-08 17:00 | 2014-02-26 17:00 | 2014-07-04 17:00 | 2014-07-04 17:00 | 2014-07-04 17:00 | 2014-07-04 17:00 | 2014-07-04 17:00 | 2014-07-04 17:00 | 5414544 | 5414544 | 5414544 | 5414544 | 5414544 | 5414544 | 5414544 | 5414544 | 0.825 | 1.1081 | 1 | 1 | -63 | 1.1081 | 1 | 0.825 | 1