## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Tax Return System (1) | 1 |  |  | 2014-02-18 08:00 | 2014-06-16 17:00 | 85d |  |  | 0 |  |  | 18990 | 118.375
21 | supporting tasks | 1.1 |  |  | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h |  |  | 0 |  |  | 1890 | 2.25
1 | project management | 1.1.1 |  | FS20 | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h | Employee A | 1890 | 0 | 0 | 0 | 1890 | 2.25
22 | design | 1.2 |  |  | 2014-03-03 08:00 | 2014-04-01 17:00 | 22d |  |  | 0 |  |  | 6150 | 29.375
2 | design - corp/AIA | 1.2.1 |  | FS7 | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 1.3333
3 | design - DWH | 1.2.2 |  | FS7 | 2014-03-24 08:00 | 2014-03-26 12:00 | 2d 4h | Employee C | 1500 | 0 | 0 | 0 | 1500 | 2.1667
4 | design - DWH | 1.2.3 |  | FS7 | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee D | 1200 | 0 | 0 | 0 | 1200 | 1.375
5 | design - HP | 1.2.4 |  | FS7 | 2014-03-03 08:00 | 2014-03-05 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 | 2.3333
6 | deisgn - TGL | 1.2.5 |  | FS7 | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 0.375
7 | design validated | 1.2.6 | 2FS;3FS;4FS;5FS;6FS | FS20 | 2014-04-01 17:00 | 2014-04-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
23 | development | 1.3 |  |  | 2014-03-24 08:00 | 2014-04-24 16:00 | 23d 7h |  |  | 0 |  |  | 6450 | 31.3333
8 | development - corp/AIA | 1.3.1 |  | FS12 | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 1.3333
9 | development - DWH | 1.3.2 |  |  | 2014-04-22 08:00 | 2014-04-24 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 | 2.3333
10 | development - HP | 1.3.3 |  | FS12 | 2014-03-24 08:00 | 2014-03-26 16:00 | 2d 7h | Employee J | 1725 | 0 | 0 | 0 | 1725 | 2.3333
11 | development - TGL | 1.3.4 |  | FS12 | 2014-04-07 08:00 | 2014-04-10 09:00 | 3d 1h | Employee G | 1875 | 0 | 0 | 0 | 1875 | 3.0417
12 | development DWH completed | 1.3.5 | 8FS;10FS;11FS | FS20 | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
24 | test | 1.4 |  |  | 2014-05-05 08:00 | 2014-06-13 17:00 | 30d |  |  | 0 |  |  | 3900 | 39.375
13 | test TGL | 1.4.1 |  | FS17 | 2014-05-05 08:00 | 2014-05-05 15:00 | 6h | Employee G | 450 | 0 | 0 | 0 | 450 | 0.29167
14 | test corp/AIA | 1.4.2 |  | FS17 | 2014-06-02 08:00 | 2014-06-03 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 1.3333
15 | test DWH | 1.4.3 |  | FS17 | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 0.375
16 | test HP | 1.4.4 |  | FS17 | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 | 2.3333
17 | test DWH completed | 1.4.5 | 13FS;14FS;15FS;16FS | FS20 | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
25 | implementation | 1.5 |  |  | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d |  |  | 0 |  |  | 600 | 0.375
18 | execution | 1.5.1 |  |  | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 0.375
19 | implementation | 1.5.2 |  |  | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
20 | go live | 1.5.3 | 1FS;7FS;12FS;17FS |  | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 1890
2 | Employee B | Renewable | 1 | 0 | 75 | 2;8;14;18; | 3975
3 | Employee C | Renewable | 1 | 0 | 75 | 3;15; | 2100
4 | Employee D | Renewable | 1 | 0 | 75 | 4; | 1200
5 | Employee E | Renewable | 1 | 0 | 75 |  | 0
6 | Employee F | Renewable | 1 | 0 | 75 | 5;16; | 3450
7 | Employee G | Renewable | 1 | 0 | 75 | 6;11;13; | 2925
8 | Employee H | Renewable | 1 | 0 | 75 |  | 0
9 | Employee I | Renewable | 1 | 0 | 75 | 9; | 1725
10 | Employee J | Renewable | 1 | 0 | 75 | 10; | 1725

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Tax Return System (1) | 680h |  |  |  |  | 99 | 100 | 101
21 | supporting tasks | 21h |  |  |  |  | 99 | 100 | 101
1 | project management | 21h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | design | 176h |  |  |  |  | 99 | 100 | 101
2 | design - corp/AIA | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | design - DWH | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | design - DWH | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | design - HP | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | deisgn - TGL | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | development | 191h |  |  |  |  | 99 | 100 | 101
8 | development - corp/AIA | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | development - DWH | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | development - HP | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | development - TGL | 25h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | development DWH completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | test | 240h |  |  |  |  | 99 | 100 | 101
13 | test TGL | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | test corp/AIA | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | test DWH | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | test HP | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | test DWH completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | implementation | 8h |  |  |  |  | 99 | 100 | 101
18 | execution | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | implementation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-03-10 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Tax Return System (1) | 2014-02-18 08:00 | 2014-06-16 17:00 | 85d |  |  | 0 |  |  | 18990 |  | 15d | [5 empty] | 1350 |  | 16.49% |  | 3132.3 | 4215
21 | supporting tasks | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h |  |  | 0 |  |  | 1890 |  | 15d | [5 empty] | 450 |  | 27% |  | 510.3 | 1890
1 | project management | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h | Employee A | 1890 | 0 | 0 | 0 | 1890 | 2014-02-18 08:00 | 5h | 450 | 540 | 6h | 0 | 0 | 450 | 540 | 27% | Started | 510.3 | 1890 | 100 | 23.8095 | 27 | 100 | 23.8095 | 27
22 | design | 2014-03-03 08:00 | 2014-04-01 17:00 | 22d |  |  | 0 |  |  | 6150 |  | 11d | [5 empty] | 900 |  | 42.63% |  | 2622 | 2325
2 | design - corp/AIA | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-03-03 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 1125 | 600 | 100 | 26.6667 | 100 | 100 | 26.6667 | 100
3 | design - DWH | 2014-03-24 08:00 | 2014-03-26 12:00 | 2d 4h | Employee C | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d 4h | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | design - DWH | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee D | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | design - HP | 2014-03-03 08:00 | 2014-03-05 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 | 2014-03-10 08:00 | 6h | 450 | 1200 | 2d | 0 | 0 | 450 | 1200 | 52% | Started | 897 | 1725 | 100 | 26.087 | 52 | 100 | 26.087 | 52
6 | deisgn - TGL | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-02-24 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 600 | 0 | 100 | 25 | 100 | 100 | 25 | 100
7 | design validated | 2014-04-01 17:00 | 2014-04-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | development | 2014-03-24 08:00 | 2014-04-24 16:00 | 23d 7h |  |  | 0 |  |  | 6450 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | development - corp/AIA | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | development - DWH | 2014-04-22 08:00 | 2014-04-24 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | development - HP | 2014-03-24 08:00 | 2014-03-26 16:00 | 2d 7h | Employee J | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | development - TGL | 2014-04-07 08:00 | 2014-04-10 09:00 | 3d 1h | Employee G | 1875 | 0 | 0 | 0 | 1875 |  | 0 | 0 | 1875 | 3d 1h | 0 | 0 | 0 | 1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | development DWH completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | test | 2014-05-05 08:00 | 2014-06-13 17:00 | 30d |  |  | 0 |  |  | 3900 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | test TGL | 2014-05-05 08:00 | 2014-05-05 15:00 | 6h | Employee G | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | test corp/AIA | 2014-06-02 08:00 | 2014-06-03 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | test DWH | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | test HP | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | test DWH completed | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | implementation | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d |  |  | 0 |  |  | 600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | execution | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | implementation | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | go live | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-04-07 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Tax Return System (1) | 2014-02-18 08:00 | 2014-06-16 17:00 | 85d |  |  | 0 |  |  | 18990 |  | 35d | [5 empty] | 6045 |  | 64.64% |  | 12275.5264 | 11490
21 | supporting tasks | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h |  |  | 0 |  |  | 1890 |  | 35d | [5 empty] | 1620 |  | 94.74% |  | 1790.5264 | 1890
1 | project management | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h | Employee A | 1890 | 0 | 0 | 0 | 1890 | 2014-02-18 08:00 | 2d 2h | 1620 | 90 | 1h | 0 | 0 | 1620 | 90 | 94.74% | Started | 1790.5264 | 1890 | 100 | 85.7143 | 94.7368 | 100 | 85.7143 | 94.7368
22 | design | 2014-03-03 08:00 | 2014-04-01 17:00 | 22d |  |  | 0 |  |  | 6150 |  | 31d | [5 empty] | 3675 |  | 93.66% |  | 5760 | 6150
2 | design - corp/AIA | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-03-03 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 1125 | 1125 | 100 | 26.6667 | 100 | 100 | 26.6667 | 100
3 | design - DWH | 2014-03-24 08:00 | 2014-03-26 12:00 | 2d 4h | Employee C | 1500 | 0 | 0 | 0 | 1500 | 2014-03-31 08:00 | 1d 7h | 1125 | 75 | 1h | 0 | 0 | 1125 | 75 | 74% | Started | 1110 | 1500 | 100 | 75 | 74 | 100 | 75 | 74
4 | design - DWH | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee D | 1200 | 0 | 0 | 0 | 1200 | 2014-03-31 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
5 | design - HP | 2014-03-03 08:00 | 2014-03-05 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 1725 | 1725 | 100 | 52.1739 | 100 | 100 | 52.1739 | 100
6 | deisgn - TGL | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-02-24 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 600 | 600 | 100 | 25 | 100 | 100 | 25 | 100
7 | design validated | 2014-04-01 17:00 | 2014-04-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | development | 2014-03-24 08:00 | 2014-04-24 16:00 | 23d 7h |  |  | 0 |  |  | 6450 |  | 11d | [5 empty] | 750 |  | 73.26% |  | 4725 | 3450
8 | development - corp/AIA | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1125 | 1125 | 100 | 6.6667 | 100 | 100 | 6.6667 | 100
9 | development - DWH | 2014-04-22 08:00 | 2014-04-24 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | development - HP | 2014-03-24 08:00 | 2014-03-26 16:00 | 2d 7h | Employee J | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 1725 | 1725 | 100 | 17.3913 | 100 | 100 | 17.3913 | 100
11 | development - TGL | 2014-04-07 08:00 | 2014-04-10 09:00 | 3d 1h | Employee G | 1875 | 0 | 0 | 0 | 1875 | 2014-04-07 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 1875 | 600 | 100 | 20 | 100 | 100 | 20 | 100
12 | development DWH completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | test | 2014-05-05 08:00 | 2014-06-13 17:00 | 30d |  |  | 0 |  |  | 3900 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | test TGL | 2014-05-05 08:00 | 2014-05-05 15:00 | 6h | Employee G | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | test corp/AIA | 2014-06-02 08:00 | 2014-06-03 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | test DWH | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | test HP | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | test DWH completed | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | implementation | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d |  |  | 0 |  |  | 600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | execution | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | implementation | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | go live | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-06-17 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Tax Return System (1) | 2014-02-18 08:00 | 2014-06-16 17:00 | 85d |  |  | 0 |  |  | 18990 |  | 85d | [5 empty] | 8010 |  | 100% |  | 18990 | 18990
21 | supporting tasks | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h |  |  | 0 |  |  | 1890 |  | 2d 3h | [5 empty] | 1710 |  | 100% |  | 1890 | 1890
1 | project management | 2014-02-18 08:00 | 2014-02-20 14:00 | 2d 5h | Employee A | 1890 | 0 | 0 | 0 | 1890 | 2014-02-18 08:00 | 2d 3h | 1710 | 0 | 0 | 0 | 0 | 1710 | 0 | 100% | Finished | 1890 | 1890 | 100 | 90.4762 | 100 | 100 | 90.4762 | 100
22 | design | 2014-03-03 08:00 | 2014-04-01 17:00 | 22d |  |  | 0 |  |  | 6150 |  | 31d 7h | [5 empty] | 4050 |  | 100% |  | 6150 | 6150
2 | design - corp/AIA | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-03-03 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 1125 | 1125 | 100 | 26.6667 | 100 | 100 | 26.6667 | 100
3 | design - DWH | 2014-03-24 08:00 | 2014-03-26 12:00 | 2d 4h | Employee C | 1500 | 0 | 0 | 0 | 1500 | 2014-03-31 08:00 | 2d 4h | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
4 | design - DWH | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee D | 1200 | 0 | 0 | 0 | 1200 | 2014-03-31 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
5 | design - HP | 2014-03-03 08:00 | 2014-03-05 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 1725 | 1725 | 100 | 52.1739 | 100 | 100 | 52.1739 | 100
6 | deisgn - TGL | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-02-24 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 600 | 600 | 100 | 25 | 100 | 100 | 25 | 100
7 | design validated | 2014-04-01 17:00 | 2014-04-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
23 | development | 2014-03-24 08:00 | 2014-04-24 16:00 | 23d 7h |  |  | 0 |  |  | 6450 |  | 21d 1h | [5 empty] | 825 |  | 100% |  | 6450 | 6450
8 | development - corp/AIA | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1125 | 1125 | 100 | 6.6667 | 100 | 100 | 6.6667 | 100
9 | development - DWH | 2014-04-22 08:00 | 2014-04-24 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 | 2014-04-22 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1725 | 1725 | 100 | 4.3478 | 100 | 100 | 4.3478 | 100
10 | development - HP | 2014-03-24 08:00 | 2014-03-26 16:00 | 2d 7h | Employee J | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 1725 | 1725 | 100 | 17.3913 | 100 | 100 | 17.3913 | 100
11 | development - TGL | 2014-04-07 08:00 | 2014-04-10 09:00 | 3d 1h | Employee G | 1875 | 0 | 0 | 0 | 1875 | 2014-04-07 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 1875 | 1875 | 100 | 20 | 100 | 100 | 20 | 100
12 | development DWH completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
24 | test | 2014-05-05 08:00 | 2014-06-13 17:00 | 30d |  |  | 0 |  |  | 3900 |  | 35d 1h | [5 empty] | 825 |  | 100% |  | 3900 | 3900
13 | test TGL | 2014-05-05 08:00 | 2014-05-05 15:00 | 6h | Employee G | 450 | 0 | 0 | 0 | 450 | 2014-04-14 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 450 | 450 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
14 | test corp/AIA | 2014-06-02 08:00 | 2014-06-03 16:00 | 1d 7h | Employee B | 1125 | 0 | 0 | 0 | 1125 | 2014-06-02 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1125 | 1125 | 100 | 6.6667 | 100 | 100 | 6.6667 | 100
15 | test DWH | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2014-05-05 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
16 | test HP | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee F | 1725 | 0 | 0 | 0 | 1725 | 2014-04-21 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 1725 | 1725 | 100 | 8.6957 | 100 | 100 | 8.6957 | 100
17 | test DWH completed | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
25 | implementation | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d |  |  | 0 |  |  | 600 |  | 1d | [5 empty] | 600 |  | 100% |  | 600 | 600
18 | execution | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 2014-06-16 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
19 | implementation | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
20 | go live | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2014-02-18 08:00 | 2014-03-10 22:00 | 4215 | 3132.3 | 1350 | 2014-03-04 17:00 | -1082.7 | 74.31% | 1782.3 | 232% | -4d | 73.33% | 45.54% | 2014-06-23 16:00 | 2014-07-28 11:00 | 2014-04-28 10:00 | 2014-06-20 16:00 | 2014-07-28 11:00 | 2014-05-08 16:00 | 2014-06-20 17:00 | 2014-07-29 16:00 | 2014-05-09 12:00 | 17207.7 | 8184.5609 | 22689.0179 | 22974.1364 | 10546.9717 | 10669.8558 | 9259.8501 | 9267.5895 | 0.73333 | 2.3202 | 0.74313 | 0.45544 | -4 | 2.3202 | 1 | 0.73333 | 1
Tracking 2 | 2014-03-10 22:00 | 2014-04-07 22:00 | 11490 | 12275.5264 | 6045 | 2014-04-09 11:00 | 785.5264 | 106.8% | 6230.5264 | 203.1% | 1d 3h | 103.9% | 96.03% | 2014-06-11 12:00 | 2014-06-09 12:00 | 2014-04-14 09:00 | 2014-06-12 14:00 | 2014-06-09 12:00 | 2014-05-07 17:00 | 2014-06-13 14:00 | 2014-06-11 15:00 | 2014-05-08 17:00 | 12759.4736 | 9351.4972 | 12329.806 | 12505.6619 | 9139.9102 | 9226.5093 | 9697.6923 | 9709.2859 | 1.0393 | 2.0307 | 1.0684 | 0.96025 | 1.375 | 2.0307 | 1 | 1.0393 | 1
Closure | 2014-04-07 22:00 | 2014-06-17 08:00 | 18990 | 18990 | 8010 | 2014-06-16 17:00 | 0 | 100% | 10980 | 237.1% | 0 | 100% | 100% | 2014-06-16 17:00 | 2014-06-16 17:00 | 2014-04-08 16:00 | 2014-06-16 17:00 | 2014-06-16 17:00 | 2014-06-16 17:00 | 2014-06-16 17:00 | 2014-06-16 17:00 | 2014-06-16 17:00 | 8010 | 8010 | 8010 | 8010 | 8010 | 8010 | 8010 | 8010 | 1 | 2.3708 | 1 | 1 | 0 | 2.3708 | 1 | 1 | 1