## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Investment Product (1) | 1 |  |  | 2014-03-17 08:00 | 2014-05-06 17:00 | 37d |  |  | 0 |  |  | 4020 | 50.375
24 | supporting tasks | 1.1 |  |  | 2014-03-17 08:00 | 2014-03-31 10:00 | 10d 2h |  |  | 0 |  |  | 1020 | 14.0833
1 | project management | 1.1.1 |  | FS2;FS3;FS4 | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 0.375
2 | validation and support | 1.1.2 | 1FS |  | 2014-03-31 08:00 | 2014-03-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 0.083333
3 | validation and support | 1.1.3 | 1FS |  | 2014-03-31 08:00 | 2014-03-31 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 0.041667
4 | validation and support | 1.1.4 | 1FS |  | 2014-03-31 08:00 | 2014-03-31 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 0.041667
25 | analysis | 1.2 |  |  | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d |  |  | 0 |  |  | 300 | 0.375
5 | analysis - business analysis | 1.2.1 |  | FS6 | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee C | 300 | 0 | 0 | 0 | 300 | 0.16667
6 | analysis validated | 1.2.2 | 5FS | FS9;FS22 | 2014-03-17 17:00 | 2014-03-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
26 | design | 1.3 |  |  | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d |  |  | 0 |  |  | 900 | 4.375
7 | design - integration (mapping) | 1.3.1 |  | FS9 | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 0.16667
8 | design - user interface design | 1.3.2 |  | FS9 | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 | 0.375
9 | design validated | 1.3.3 | 7FS;8FS;6FS | FS10;FS12;FS22 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
27 | development | 1.4 |  |  | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d |  |  | 0 |  |  | 900 | 0.375
10 | development - coding | 1.4.1 | 9FS |  | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 0.375
12 | development - technical assembly | 1.4.2 | 9FS |  | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee D | 300 | 0 | 0 | 0 | 300 | 0.16667
28 | test ICT | 1.5 |  |  | 2014-03-24 08:00 | 2014-04-07 17:00 | 11d |  |  | 0 |  |  | 900 | 14.375
13 | test ICT - test coordination | 1.5.1 | 16FS |  | 2014-03-31 08:00 | 2014-03-31 12:00 | 4h | Employee B | 300 | 0 | 0 | 0 | 300 | 0.16667
16 | test ICT - test preparation | 1.5.2 |  | FS13;FS19 | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 0.16667
19 | test ICT - test execution | 1.5.3 | 16FS | FS20 | 2014-03-31 08:00 | 2014-03-31 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 0.16667
20 | ICT test completed | 1.5.4 | 19FS | FS22 | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
29 | implementation | 1.6 |  |  | 2014-04-07 17:00 | 2014-05-06 17:00 | 21d |  |  | 0 |  |  | 0 | 29
21 | full handover | 1.6.1 |  | FS22 | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
22 | go live | 1.6.2 | 20FS;21FS;9FS;6FS |  | 2014-05-06 17:00 | 2014-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 720
2 | Employee B | Renewable | 1 | 0 | 75 | 2;13; | 450
3 | Employee C | Renewable | 1 | 0 | 75 | 3;5; | 375
4 | Employee D | Renewable | 1 | 0 | 75 | 4;8;12; | 975
5 | Employee E | Renewable | 1 | 0 | 75 | 7; | 300
6 | Employee F | Renewable | 1 | 0 | 75 | 10; | 600
7 | Employee G | Renewable | 1 | 0 | 75 |  | 0
8 | Employee H | Renewable | 1 | 0 | 75 | 16;19; | 600

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Investment Product (1) | 296h |  |  |  |  | 99 | 100 | 101
24 | supporting tasks | 82h |  |  |  |  | 99 | 100 | 101
1 | project management | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | validation and support | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | validation and support | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | validation and support | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | analysis | 8h |  |  |  |  | 99 | 100 | 101
5 | analysis - business analysis | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | design | 40h |  |  |  |  | 99 | 100 | 101
7 | design - integration (mapping) | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | design - user interface design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | development | 8h |  |  |  |  | 99 | 100 | 101
10 | development - coding | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | development - technical assembly | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | test ICT | 88h |  |  |  |  | 99 | 100 | 101
13 | test ICT - test coordination | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | test ICT - test preparation | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | test ICT - test execution | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | ICT test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | implementation | 168h |  |  |  |  | 99 | 100 | 101
21 | full handover | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-03-24 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Investment Product (1) | 2014-03-17 08:00 | 2014-05-06 17:00 | 37d |  |  | 0 |  |  | 4020 |  | 6d | [5 empty] | 2760 |  | 82.1% |  | 3300.6 | 3120
24 | supporting tasks | 2014-03-17 08:00 | 2014-03-31 10:00 | 10d 2h |  |  | 0 |  |  | 1020 |  | 6d | [5 empty] | 435 |  | 58.88% |  | 600.6 | 720
1 | project management | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 2014-03-17 08:00 | 4h | 360 | 90 | 1h | 0 | 0 | 360 | 90 | 73% | Started | 525.6 | 720 | 100 | 50 | 73 | 100 | 50 | 73
2 | validation and support | 2014-03-31 08:00 | 2014-03-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2014-03-31 08:00 | 2014-03-31 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 0 | 100 | 100 | 100 | 100 | 100 | 100
4 | validation and support | 2014-03-31 08:00 | 2014-03-31 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | analysis | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d |  |  | 0 |  |  | 300 |  | 7h | [5 empty] | 300 |  | 100% |  | 300 | 300
5 | analysis - business analysis | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee C | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
6 | analysis validated | 2014-03-17 17:00 | 2014-03-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-17 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
26 | design | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d |  |  | 0 |  |  | 900 |  | 6d | [5 empty] | 675 |  | 66.67% |  | 600 | 900
7 | design - integration (mapping) | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 300 | 100 |  | 0 | 100 |  | 0
8 | design - user interface design | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 600 | 600 | 100 | 112.5 | 100 | 100 | 112.5 | 100
9 | design validated | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | development | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d |  |  | 0 |  |  | 900 |  | 5d 1h | [5 empty] | 300 |  | 100% |  | 900 | 900
10 | development - coding | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 600 | 600 | 100 | 37.5 | 100 | 100 | 37.5 | 100
12 | development - technical assembly | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee D | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
28 | test ICT | 2014-03-24 08:00 | 2014-04-07 17:00 | 11d |  |  | 0 |  |  | 900 |  | 6d | [5 empty] | 1050 |  | 100% |  | 900 | 300
13 | test ICT - test coordination | 2014-03-31 08:00 | 2014-03-31 12:00 | 4h | Employee B | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 300 | 0 | 100 | 50 | 100 | 100 | 50 | 100
16 | test ICT - test preparation | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
19 | test ICT - test execution | 2014-03-31 08:00 | 2014-03-31 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 300 | 0 | 100 | 200 | 100 | 100 | 200 | 100
20 | ICT test completed | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | implementation | 2014-04-07 17:00 | 2014-05-06 17:00 | 21d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | full handover | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | go live | 2014-05-06 17:00 | 2014-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-05-07 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Investment Product (1) | 2014-03-17 08:00 | 2014-05-06 17:00 | 37d |  |  | 0 |  |  | 4020 |  | 36d 7h | [5 empty] | 3240 |  | 100% |  | 4020 | 4020
24 | supporting tasks | 2014-03-17 08:00 | 2014-03-31 10:00 | 10d 2h |  |  | 0 |  |  | 1020 |  | 15d 2h | [5 empty] | 840 |  | 100% |  | 1020 | 1020
1 | project management | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 2014-03-17 08:00 | 6h | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 100% | Finished | 720 | 720 | 100 | 75 | 100 | 100 | 75 | 100
2 | validation and support | 2014-03-31 08:00 | 2014-03-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-04-07 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
3 | validation and support | 2014-03-31 08:00 | 2014-03-31 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
4 | validation and support | 2014-03-31 08:00 | 2014-03-31 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
25 | analysis | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d |  |  | 0 |  |  | 300 |  | 7h | [5 empty] | 300 |  | 100% |  | 300 | 300
5 | analysis - business analysis | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee C | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
6 | analysis validated | 2014-03-17 17:00 | 2014-03-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-17 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
26 | design | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d |  |  | 0 |  |  | 900 |  | 6d 7h | [5 empty] | 750 |  | 100% |  | 900 | 900
7 | design - integration (mapping) | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-25 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
8 | design - user interface design | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 600 | 600 | 100 | 112.5 | 100 | 100 | 112.5 | 100
9 | design validated | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | development | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d |  |  | 0 |  |  | 900 |  | 5d 1h | [5 empty] | 300 |  | 100% |  | 900 | 900
10 | development - coding | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 600 | 600 | 100 | 37.5 | 100 | 100 | 37.5 | 100
12 | development - technical assembly | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee D | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
28 | test ICT | 2014-03-24 08:00 | 2014-04-07 17:00 | 11d |  |  | 0 |  |  | 900 |  | 15d 7h | [5 empty] | 1050 |  | 100% |  | 900 | 900
13 | test ICT - test coordination | 2014-03-31 08:00 | 2014-03-31 12:00 | 4h | Employee B | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 300 | 300 | 100 | 50 | 100 | 100 | 50 | 100
16 | test ICT - test preparation | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
19 | test ICT - test execution | 2014-03-31 08:00 | 2014-03-31 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-24 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 300 | 300 | 100 | 200 | 100 | 100 | 200 | 100
20 | ICT test completed | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | implementation | 2014-04-07 17:00 | 2014-05-06 17:00 | 21d |  |  | 0 |  |  | 0 |  | 21d | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | full handover | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
22 | go live | 2014-05-06 17:00 | 2014-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-06 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2014-03-17 08:00 | 2014-03-24 22:00 | 3120 | 3300.6 | 2760 | 2014-03-31 09:00 | 180.6 | 105.8% | 540.6 | 119.6% | 4d 1h | 168.8% | 81.56% | 2014-05-05 11:00 | 2014-05-02 17:00 | 2014-04-25 10:00 | 2014-05-06 14:00 | 2014-05-02 17:00 | 2014-04-28 10:00 | 2014-04-30 16:00 | 2014-04-15 16:00 | 2014-04-11 11:00 | 3479.4 | 3361.5706 | 3440.0363 | 3186.3111 | 3328.6543 | 3116.4863 | 3375.7809 | 3315.8665 | 1.6875 | 1.1959 | 1.0579 | 0.81562 | 4.125 | 1.1959 | 1 | 1.6875 | 1
Closure | 2014-03-24 22:00 | 2014-05-07 08:00 | 4020 | 4020 | 3240 | 2014-05-06 17:00 | 0 | 100% | 780 | 124.1% | 0 | 100% | 100% | 2014-05-06 17:00 | 2014-05-06 17:00 | 2014-04-25 16:00 | 2014-05-06 17:00 | 2014-05-06 17:00 | 2014-05-06 17:00 | 2014-05-06 17:00 | 2014-05-06 17:00 | 2014-05-06 17:00 | 3240 | 3240 | 3240 | 3240 | 3240 | 3240 | 3240 | 3240 | 1 | 1.2407 | 1 | 1 | 0 | 1.2407 | 1 | 1 | 1