## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Risk Profile Questionnaire | 1 |  |  | 2013-10-14 08:00 | 2014-05-13 10:00 | 151d 2h |  |  | 0 |  |  | 29880 | 211.0833
32 | supporting tasks | 1.1 |  |  | 2013-10-14 08:00 | 2013-12-17 17:00 | 47d |  |  | 0 |  |  | 8355 | 64.375
1 | project management | 1.1.1 |  | FS3;FS4 | 2013-10-14 08:00 | 2013-10-22 12:00 | 6d 4h | Employee A | 4680 | 0 | 0 | 0 | 4680 | 8.1667
2 | project management | 1.1.2 |  | FS3;FS4 | 2013-10-14 08:00 | 2013-10-15 17:00 | 2d | Employee B | 1200 | 0 | 0 | 0 | 1200 | 1.375
3 | validation and support | 1.1.3 | 1FS;2FS |  | 2013-12-12 08:00 | 2013-12-12 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 0.041667
4 | validation and support | 1.1.4 | 1FS;2FS |  | 2013-12-12 08:00 | 2013-12-17 17:00 | 4d | Employee D | 2400 | 0 | 0 | 0 | 2400 | 5.375
33 | analysis | 1.2 |  |  | 2014-02-07 08:00 | 2014-02-24 17:00 | 12d |  |  | 0 |  |  | 525 | 17.375
5 | analysis - conceptual design | 1.2.1 |  | FS6 | 2014-02-07 08:00 | 2014-02-07 16:00 | 7h | Employee C | 525 | 0 | 0 | 0 | 525 | 0.33333
6 | analysis validated | 1.2.2 | 5FS | FS28 | 2014-02-24 17:00 | 2014-02-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
34 | design | 1.3 |  |  | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h |  |  | 0 |  |  | 2700 | 6.1667
7 | design - ISP design | 1.3.1 |  | FS8 | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h | Employee D | 2700 | 0 | 0 | 0 | 2700 | 6.1667
8 | design validated | 1.3.2 | 7FS | FS28 | 2014-02-06 12:00 | 2014-02-06 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
35 | development | 1.4 |  |  | 2014-03-10 08:00 | 2014-03-25 17:00 | 12d |  |  | 0 |  |  | 3375 | 15.375
9 | development - build ISP | 1.4.1 |  | FS13 | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 0.375
10 | development - build ISP | 1.4.2 |  | FS13 | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 1.3333
11 | development - technical assembly test | 1.4.3 |  | FS13 | 2014-03-10 08:00 | 2014-03-12 10:00 | 2d 2h | Employee D | 1350 | 0 | 0 | 0 | 1350 | 2.0833
12 | development - bugfixing | 1.4.4 |  | FS13 | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 0.16667
13 | development completed | 1.4.5 | 9FS;10FS;11FS;12FS | FS28 | 2014-03-25 17:00 | 2014-03-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
36 | test ict | 1.5 |  |  | 2014-02-24 08:00 | 2014-03-28 17:00 | 25d |  |  | 0 |  |  | 6225 | 32.375
14 | test ict - regression testing | 1.5.1 | 16FS;17FS | FS20 | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee G | 1200 | 0 | 0 | 0 | 1200 | 1.375
15 | test ict - test coordination | 1.5.2 |  | FS16;FS17;FS20 | 2014-02-27 08:00 | 2014-02-28 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 1.0833
16 | test ict - test execution | 1.5.3 | 15FS;18FS;19FS | FS14;FS20 | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 0.375
17 | test ict - test execution | 1.5.4 | 15FS;18FS;19FS | FS14;FS20 | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee I | 600 | 0 | 0 | 0 | 600 | 0.375
18 | test ict - test preparation | 1.5.5 |  | FS16;FS17;FS20 | 2014-02-24 08:00 | 2014-02-25 14:00 | 1d 5h | Employee G | 975 | 0 | 0 | 0 | 975 | 1.25
19 | test ict - test preparation | 1.5.6 |  | FS16;FS17;FS20 | 2014-02-24 08:00 | 2014-02-27 12:00 | 3d 4h | Employee I | 2100 | 0 | 0 | 0 | 2100 | 3.1667
20 | ict test completed | 1.5.7 | 14FS;15FS;16FS;17FS;18FS;19FS | FS28 | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
37 | uat | 1.6 |  |  | 2014-03-21 17:00 | 2014-04-21 17:00 | 21d |  |  | 0 |  |  | 6450 | 31
21 | uat - test execution support | 1.6.1 |  | FS26 | 2014-03-31 08:00 | 2014-04-01 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 1.0833
22 | uat - test execution support | 1.6.2 |  | FS26 | 2014-03-31 08:00 | 2014-04-09 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 | 9.1667
23 | uat - test execution support | 1.6.3 |  | FS26 | 2014-03-31 08:00 | 2014-04-01 17:00 | 2d | Employee I | 1200 | 0 | 0 | 0 | 1200 | 1.375
24 | full handover | 1.6.4 |  | FS26 | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
25 | release handover | 1.6.5 |  | FS28 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
26 | uat completed | 1.6.6 | 21FS;22FS;23FS;24FS | FS28 | 2014-04-21 17:00 | 2014-04-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
38 | implementation | 1.7 |  |  | 2014-04-28 17:00 | 2014-05-09 17:00 | 9d |  |  | 0 |  |  | 0 | 11
27 | code freeze | 1.7.1 |  | FS28 | 2014-04-28 17:00 | 2014-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
28 | go live | 1.7.2 | 6FS;13FS;8FS;20FS;25FS;26FS;27FS | FS29;FS30;FS31 | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
39 | post implementation | 1.8 |  |  | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h |  |  | 0 |  |  | 2250 | 1.0833
29 | post implementation - post go live support | 1.8.1 | 28FS |  | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 1.0833
30 | post implementation - post go live support | 1.8.2 | 28FS |  | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee G | 750 | 0 | 0 | 0 | 750 | 1.0833
31 | post implementation - post go live support | 1.8.3 | 28FS |  | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 | 1.0833

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 4680
2 | Employee B | Renewable | 1 | 0 | 75 | 2; | 1200
3 | Employee C | Renewable | 1 | 0 | 75 | 3;5; | 600
4 | Employee D | Renewable | 1 | 0 | 75 | 4;7;11; | 6450
5 | Employee E | Renewable | 1 | 0 | 75 | 9; | 600
6 | Employee F | Renewable | 1 | 0 | 75 | 10;12; | 1425
7 | Employee G | Renewable | 1 | 0 | 75 | 14;16;18;22;30; | 8025
8 | Employee H | Renewable | 1 | 0 | 75 | 15;21;29; | 2250
9 | Employee I | Renewable | 1 | 0 | 75 | 17;19;23;31; | 4650

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Risk Profile Questionnaire | 1210h |  |  |  |  | 99 | 100 | 101
32 | supporting tasks | 376h |  |  |  |  | 99 | 100 | 101
1 | project management | 52h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | project management | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | validation and support | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | validation and support | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | analysis | 96h |  |  |  |  | 99 | 100 | 101
5 | analysis - conceptual design | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | design | 36h |  |  |  |  | 99 | 100 | 101
7 | design - ISP design | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | development | 96h |  |  |  |  | 99 | 100 | 101
9 | development - build ISP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | development - build ISP | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | development - technical assembly test | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | development - bugfixing | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | test ict | 200h |  |  |  |  | 99 | 100 | 101
14 | test ict - regression testing | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | test ict - test coordination | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | test ict - test execution | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | test ict - test execution | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | test ict - test preparation | 13h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | test ict - test preparation | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | ict test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | uat | 168h |  |  |  |  | 99 | 100 | 101
21 | uat - test execution support | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | uat - test execution support | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | uat - test execution support | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | full handover | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | release handover | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | uat completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | implementation | 72h |  |  |  |  | 99 | 100 | 101
27 | code freeze | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | post implementation | 10h |  |  |  |  | 99 | 100 | 101
29 | post implementation - post go live support | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | post implementation - post go live support | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | post implementation - post go live support | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-01-27 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Risk Profile Questionnaire | 2013-10-14 08:00 | 2014-05-13 10:00 | 151d 2h |  |  | 0 |  |  | 29880 |  | 76d | [5 empty] | 1050 |  | 3.695% |  | 1104 | 8355
32 | supporting tasks | 2013-10-14 08:00 | 2013-12-17 17:00 | 47d |  |  | 0 |  |  | 8355 |  | 76d | [5 empty] | 825 |  | 10.63% |  | 888 | 8355
1 | project management | 2013-10-14 08:00 | 2013-10-22 12:00 | 6d 4h | Employee A | 4680 | 0 | 0 | 0 | 4680 |  | 0 | 0 | 4680 | 6d 4h | 0 | 0 | 0 | 4680 | 0% | Not Started | 0 | 4680 | 100 |  | 0 | 100 |  | 0
2 | project management | 2013-10-14 08:00 | 2013-10-15 17:00 | 2d | Employee B | 1200 | 0 | 0 | 0 | 1200 | 2013-10-14 08:00 | 1d 3h | 825 | 75 | 1h | 0 | 0 | 825 | 75 | 74% | Started | 888 | 1200 | 100 | 68.75 | 74 | 100 | 68.75 | 74
3 | validation and support | 2013-12-12 08:00 | 2013-12-12 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 75 | 100 |  | 0 | 100 |  | 0
4 | validation and support | 2013-12-12 08:00 | 2013-12-17 17:00 | 4d | Employee D | 2400 | 0 | 0 | 0 | 2400 |  | 0 | 0 | 2400 | 4d | 0 | 0 | 0 | 2400 | 0% | Not Started | 0 | 2400 | 100 |  | 0 | 100 |  | 0
33 | analysis | 2014-02-07 08:00 | 2014-02-24 17:00 | 12d |  |  | 0 |  |  | 525 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
5 | analysis - conceptual design | 2014-02-07 08:00 | 2014-02-07 16:00 | 7h | Employee C | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | analysis validated | 2014-02-24 17:00 | 2014-02-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h |  |  | 0 |  |  | 2700 |  | 1d | [5 empty] | 225 |  | 8% |  | 216 | 0
7 | design - ISP design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h | Employee D | 2700 | 0 | 0 | 0 | 2700 | 2014-01-27 08:00 | 3h | 225 | 75 | 1h | 0 | 0 | 225 | 75 | 8% | Started | 216 | 0 | 100 | 8.3333 | 8 | 100 | 8.3333 | 8
8 | design validated | 2014-02-06 12:00 | 2014-02-06 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | development | 2014-03-10 08:00 | 2014-03-25 17:00 | 12d |  |  | 0 |  |  | 3375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | development - build ISP | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | development - build ISP | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | development - technical assembly test | 2014-03-10 08:00 | 2014-03-12 10:00 | 2d 2h | Employee D | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | development - bugfixing | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | development completed | 2014-03-25 17:00 | 2014-03-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | test ict | 2014-02-24 08:00 | 2014-03-28 17:00 | 25d |  |  | 0 |  |  | 6225 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | test ict - regression testing | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee G | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | test ict - test coordination | 2014-02-27 08:00 | 2014-02-28 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee I | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-25 14:00 | 1d 5h | Employee G | 975 | 0 | 0 | 0 | 975 |  | 0 | 0 | 975 | 1d 5h | 0 | 0 | 0 | 975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-27 12:00 | 3d 4h | Employee I | 2100 | 0 | 0 | 0 | 2100 |  | 0 | 0 | 2100 | 3d 4h | 0 | 0 | 0 | 2100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | ict test completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | uat | 2014-03-21 17:00 | 2014-04-21 17:00 | 21d |  |  | 0 |  |  | 6450 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | uat - test execution support | 2014-03-31 08:00 | 2014-04-09 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 |  | 0 | 0 | 4500 | 7d 4h | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 17:00 | 2d | Employee I | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | full handover | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | uat completed | 2014-04-21 17:00 | 2014-04-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | implementation | 2014-04-28 17:00 | 2014-05-09 17:00 | 9d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | code freeze | 2014-04-28 17:00 | 2014-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | post implementation | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h |  |  | 0 |  |  | 2250 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee G | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-03-03 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Risk Profile Questionnaire | 2013-10-14 08:00 | 2014-05-13 10:00 | 151d 2h |  |  | 0 |  |  | 29880 |  | 101d | [5 empty] | 7605 |  | 29.85% |  | 8919.45 | 15405
32 | supporting tasks | 2013-10-14 08:00 | 2013-12-17 17:00 | 47d |  |  | 0 |  |  | 8355 |  | 101d | [5 empty] | 2130 |  | 31.4% |  | 2623.2 | 8355
1 | project management | 2013-10-14 08:00 | 2013-10-22 12:00 | 6d 4h | Employee A | 4680 | 0 | 0 | 0 | 4680 | 2014-02-24 08:00 | 2h | 180 | 1530 | 2d 1h | 0 | 0 | 180 | 1530 | 14% | Started | 655.2 | 4680 | 100 | 3.8462 | 14 | 100 | 3.8462 | 14
2 | project management | 2013-10-14 08:00 | 2013-10-15 17:00 | 2d | Employee B | 1200 | 0 | 0 | 0 | 1200 | 2013-10-14 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
3 | validation and support | 2013-12-12 08:00 | 2013-12-12 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 75 | 100 |  | 0 | 100 |  | 0
4 | validation and support | 2013-12-12 08:00 | 2013-12-17 17:00 | 4d | Employee D | 2400 | 0 | 0 | 0 | 2400 | 2014-03-03 08:00 | 1d 2h | 750 | 75 | 1h | 0 | 0 | 750 | 75 | 32% | Started | 768 | 2400 | 100 | 31.25 | 32 | 100 | 31.25 | 32
33 | analysis | 2014-02-07 08:00 | 2014-02-24 17:00 | 12d |  |  | 0 |  |  | 525 |  | 15d 7h | [5 empty] | 525 |  | 100% |  | 525 | 525
5 | analysis - conceptual design | 2014-02-07 08:00 | 2014-02-07 16:00 | 7h | Employee C | 525 | 0 | 0 | 0 | 525 | 2014-02-03 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
6 | analysis validated | 2014-02-24 17:00 | 2014-02-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
34 | design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h |  |  | 0 |  |  | 2700 |  | 8d 3h | [5 empty] | 2700 |  | 100% |  | 2700 | 2700
7 | design - ISP design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h | Employee D | 2700 | 0 | 0 | 0 | 2700 | 2014-01-27 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 2700 | 2700 | 100 | 100 | 100 | 100 | 100 | 100
8 | design validated | 2014-02-06 12:00 | 2014-02-06 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-06 11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
35 | development | 2014-03-10 08:00 | 2014-03-25 17:00 | 12d |  |  | 0 |  |  | 3375 |  | 1d | [5 empty] | 150 |  | 33.33% |  | 1125 | 0
9 | development - build ISP | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | development - build ISP | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-03-03 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 1125 | 0 | 100 | 13.3333 | 100 | 100 | 13.3333 | 100
11 | development - technical assembly test | 2014-03-10 08:00 | 2014-03-12 10:00 | 2d 2h | Employee D | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | development - bugfixing | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | development completed | 2014-03-25 17:00 | 2014-03-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | test ict | 2014-02-24 08:00 | 2014-03-28 17:00 | 25d |  |  | 0 |  |  | 6225 |  | 6d | [5 empty] | 2100 |  | 31.27% |  | 1946.25 | 3825
14 | test ict - regression testing | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee G | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | test ict - test coordination | 2014-02-27 08:00 | 2014-02-28 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 3h | 225 | 75 | 1h | 0 | 0 | 225 | 75 | 26% | Started | 195 | 750 | 100 | 30 | 26 | 100 | 30 | 26
16 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee I | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-25 14:00 | 1d 5h | Employee G | 975 | 0 | 0 | 0 | 975 | 2014-02-24 08:00 | 1d 5h | 975 | 75 | 1h | 0 | 0 | 975 | 75 | 87% | Started | 848.25 | 975 | 100 | 100 | 87 | 100 | 100 | 87
19 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-27 12:00 | 3d 4h | Employee I | 2100 | 0 | 0 | 0 | 2100 | 2014-03-03 08:00 | 1d 4h | 900 | 75 | 1h | 0 | 0 | 900 | 75 | 43% | Started | 903 | 2100 | 100 | 42.8571 | 43 | 100 | 42.8571 | 43
20 | ict test completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | uat | 2014-03-21 17:00 | 2014-04-21 17:00 | 21d |  |  | 0 |  |  | 6450 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | uat - test execution support | 2014-03-31 08:00 | 2014-04-09 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 |  | 0 | 0 | 4500 | 7d 4h | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 17:00 | 2d | Employee I | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | full handover | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | uat completed | 2014-04-21 17:00 | 2014-04-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | implementation | 2014-04-28 17:00 | 2014-05-09 17:00 | 9d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | code freeze | 2014-04-28 17:00 | 2014-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | post implementation | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h |  |  | 0 |  |  | 2250 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee G | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-04-07 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Risk Profile Questionnaire | 2013-10-14 08:00 | 2014-05-13 10:00 | 151d 2h |  |  | 0 |  |  | 29880 |  | 126d | [5 empty] | 14475 |  | 58.45% |  | 17464.3589 | 26730
32 | supporting tasks | 2013-10-14 08:00 | 2013-12-17 17:00 | 47d |  |  | 0 |  |  | 8355 |  | 126d | [5 empty] | 4800 |  | 81.41% |  | 6801.8587 | 8355
1 | project management | 2013-10-14 08:00 | 2013-10-22 12:00 | 6d 4h | Employee A | 4680 | 0 | 0 | 0 | 4680 | 2014-02-24 08:00 | 1d 7h | 1350 | 540 | 6h | 0 | 0 | 1350 | 540 | 71.43% | Started | 3342.8586 | 4680 | 100 | 28.8462 | 71.4286 | 100 | 28.8462 | 71.4286
2 | project management | 2013-10-14 08:00 | 2013-10-15 17:00 | 2d | Employee B | 1200 | 0 | 0 | 0 | 1200 | 2013-10-14 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
3 | validation and support | 2013-12-12 08:00 | 2013-12-12 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
4 | validation and support | 2013-12-12 08:00 | 2013-12-17 17:00 | 4d | Employee D | 2400 | 0 | 0 | 0 | 2400 | 2014-03-03 08:00 | 3d 5h | 2175 | 75 | 1h | 0 | 0 | 2175 | 75 | 91% | Started | 2184.0001 | 2400 | 100 | 90.625 | 91 | 100 | 90.625 | 91
33 | analysis | 2014-02-07 08:00 | 2014-02-24 17:00 | 12d |  |  | 0 |  |  | 525 |  | 15d 7h | [5 empty] | 525 |  | 100% |  | 525 | 525
5 | analysis - conceptual design | 2014-02-07 08:00 | 2014-02-07 16:00 | 7h | Employee C | 525 | 0 | 0 | 0 | 525 | 2014-02-03 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
6 | analysis validated | 2014-02-24 17:00 | 2014-02-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
34 | design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h |  |  | 0 |  |  | 2700 |  | 8d 3h | [5 empty] | 2700 |  | 100% |  | 2700 | 2700
7 | design - ISP design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h | Employee D | 2700 | 0 | 0 | 0 | 2700 | 2014-01-27 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 2700 | 2700 | 100 | 100 | 100 | 100 | 100 | 100
8 | design validated | 2014-02-06 12:00 | 2014-02-06 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-06 11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
35 | development | 2014-03-10 08:00 | 2014-03-25 17:00 | 12d |  |  | 0 |  |  | 3375 |  | 26d | [5 empty] | 825 |  | 51.11% |  | 1725 | 3375
9 | development - build ISP | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 600 | 600 | 100 | 112.5 | 100 | 100 | 112.5 | 100
10 | development - build ISP | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-03-03 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 1125 | 1125 | 100 | 13.3333 | 100 | 100 | 13.3333 | 100
11 | development - technical assembly test | 2014-03-10 08:00 | 2014-03-12 10:00 | 2d 2h | Employee D | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 1350 | 100 |  | 0 | 100 |  | 0
12 | development - bugfixing | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 300 | 100 |  | 0 | 100 |  | 0
13 | development completed | 2014-03-25 17:00 | 2014-03-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
36 | test ict | 2014-02-24 08:00 | 2014-03-28 17:00 | 25d |  |  | 0 |  |  | 6225 |  | 31d | [5 empty] | 5550 |  | 79.72% |  | 4962.5002 | 6225
14 | test ict - regression testing | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee G | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 1200 | 100 |  | 0 | 100 |  | 0
15 | test ict - test coordination | 2014-02-27 08:00 | 2014-02-28 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d 3h | 825 | 75 | 1h | 0 | 0 | 825 | 75 | 91.67% | Started | 687.5002 | 750 | 100 | 110 | 91.6667 | 100 | 110 | 91.6667
16 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-03-24 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 600 | 600 | 100 | 150 | 100 | 100 | 150 | 100
17 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee I | 600 | 0 | 0 | 0 | 600 | 2014-03-10 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
18 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-25 14:00 | 1d 5h | Employee G | 975 | 0 | 0 | 0 | 975 | 2014-02-24 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 975 | 975 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
19 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-27 12:00 | 3d 4h | Employee I | 2100 | 0 | 0 | 0 | 2100 | 2014-03-03 08:00 | 3d 4h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 2100 | 2100 | 100 | 100 | 100 | 100 | 100 | 100
20 | ict test completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
37 | uat | 2014-03-21 17:00 | 2014-04-21 17:00 | 21d |  |  | 0 |  |  | 6450 |  | 17d | [5 empty] | 75 |  | 11.63% |  | 750 | 5550
21 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 750 | 750 | 100 | 10 | 100 | 100 | 10 | 100
22 | uat - test execution support | 2014-03-31 08:00 | 2014-04-09 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 |  | 0 | 0 | 4500 | 7d 4h | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 3600 | 100 |  | 0 | 100 |  | 0
23 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 17:00 | 2d | Employee I | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 1200 | 100 |  | 0 | 100 |  | 0
24 | full handover | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
26 | uat completed | 2014-04-21 17:00 | 2014-04-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | implementation | 2014-04-28 17:00 | 2014-05-09 17:00 | 9d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | code freeze | 2014-04-28 17:00 | 2014-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | post implementation | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h |  |  | 0 |  |  | 2250 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee G | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-05-13 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Risk Profile Questionnaire | 2013-10-14 08:00 | 2014-05-13 10:00 | 151d 2h |  |  | 0 |  |  | 29880 |  | 151d 2h | [5 empty] | 17400 |  | 100% |  | 29880 | 29430
32 | supporting tasks | 2013-10-14 08:00 | 2013-12-17 17:00 | 47d |  |  | 0 |  |  | 8355 |  | 110d 1h | [5 empty] | 5025 |  | 100% |  | 8355 | 8355
1 | project management | 2013-10-14 08:00 | 2013-10-22 12:00 | 6d 4h | Employee A | 4680 | 0 | 0 | 0 | 4680 | 2014-02-24 08:00 | 1d 7h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 4680 | 4680 | 100 | 28.8462 | 100 | 100 | 28.8462 | 100
2 | project management | 2013-10-14 08:00 | 2013-10-15 17:00 | 2d | Employee B | 1200 | 0 | 0 | 0 | 1200 | 2013-10-14 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
3 | validation and support | 2013-12-12 08:00 | 2013-12-12 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
4 | validation and support | 2013-12-12 08:00 | 2013-12-17 17:00 | 4d | Employee D | 2400 | 0 | 0 | 0 | 2400 | 2014-03-03 08:00 | 4d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
33 | analysis | 2014-02-07 08:00 | 2014-02-24 17:00 | 12d |  |  | 0 |  |  | 525 |  | 15d 7h | [5 empty] | 525 |  | 100% |  | 525 | 525
5 | analysis - conceptual design | 2014-02-07 08:00 | 2014-02-07 16:00 | 7h | Employee C | 525 | 0 | 0 | 0 | 525 | 2014-02-03 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
6 | analysis validated | 2014-02-24 17:00 | 2014-02-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
34 | design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h |  |  | 0 |  |  | 2700 |  | 8d 3h | [5 empty] | 2700 |  | 100% |  | 2700 | 2700
7 | design - ISP design | 2014-01-31 08:00 | 2014-02-06 12:00 | 4d 4h | Employee D | 2700 | 0 | 0 | 0 | 2700 | 2014-01-27 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 2700 | 2700 | 100 | 100 | 100 | 100 | 100 | 100
8 | design validated | 2014-02-06 12:00 | 2014-02-06 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-06 11:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
35 | development | 2014-03-10 08:00 | 2014-03-25 17:00 | 12d |  |  | 0 |  |  | 3375 |  | 26d 1h | [5 empty] | 975 |  | 100% |  | 3375 | 3375
9 | development - build ISP | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 600 | 600 | 100 | 112.5 | 100 | 100 | 112.5 | 100
10 | development - build ISP | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-03-03 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 1125 | 1125 | 100 | 13.3333 | 100 | 100 | 13.3333 | 100
11 | development - technical assembly test | 2014-03-10 08:00 | 2014-03-12 10:00 | 2d 2h | Employee D | 1350 | 0 | 0 | 0 | 1350 | 2014-04-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1350 | 1350 | 100 | 5.5556 | 100 | 100 | 5.5556 | 100
12 | development - bugfixing | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-04-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
13 | development completed | 2014-03-25 17:00 | 2014-03-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
36 | test ict | 2014-02-24 08:00 | 2014-03-28 17:00 | 25d |  |  | 0 |  |  | 6225 |  | 31d 1h | [5 empty] | 5700 |  | 100% |  | 6225 | 6225
14 | test ict - regression testing | 2014-03-24 08:00 | 2014-03-25 17:00 | 2d | Employee G | 1200 | 0 | 0 | 0 | 1200 | 2014-04-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1200 | 1200 | 100 | 6.25 | 100 | 100 | 6.25 | 100
15 | test ict - test coordination | 2014-02-27 08:00 | 2014-02-28 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 750 | 750 | 100 | 120 | 100 | 100 | 120 | 100
16 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-03-24 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 600 | 600 | 100 | 150 | 100 | 100 | 150 | 100
17 | test ict - test execution | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee I | 600 | 0 | 0 | 0 | 600 | 2014-03-10 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
18 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-25 14:00 | 1d 5h | Employee G | 975 | 0 | 0 | 0 | 975 | 2014-02-24 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 975 | 975 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
19 | test ict - test preparation | 2014-02-24 08:00 | 2014-02-27 12:00 | 3d 4h | Employee I | 2100 | 0 | 0 | 0 | 2100 | 2014-03-03 08:00 | 3d 4h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 2100 | 2100 | 100 | 100 | 100 | 100 | 100 | 100
20 | ict test completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
37 | uat | 2014-03-21 17:00 | 2014-04-21 17:00 | 21d |  |  | 0 |  |  | 6450 |  | 26d 7h | [5 empty] | 225 |  | 100% |  | 6450 | 6450
21 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 750 | 750 | 100 | 10 | 100 | 100 | 10 | 100
22 | uat - test execution support | 2014-03-31 08:00 | 2014-04-09 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 | 2014-04-09 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 4500 | 4500 | 100 | 1.6667 | 100 | 100 | 1.6667 | 100
23 | uat - test execution support | 2014-03-31 08:00 | 2014-04-01 17:00 | 2d | Employee I | 1200 | 0 | 0 | 0 | 1200 | 2014-04-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1200 | 1200 | 100 | 6.25 | 100 | 100 | 6.25 | 100
24 | full handover | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
26 | uat completed | 2014-04-21 17:00 | 2014-04-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
38 | implementation | 2014-04-28 17:00 | 2014-05-09 17:00 | 9d |  |  | 0 |  |  | 0 |  | 9d | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | code freeze | 2014-04-28 17:00 | 2014-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
28 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
39 | post implementation | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h |  |  | 0 |  |  | 2250 |  | 1d 2h | [5 empty] | 2250 |  | 100% |  | 2250 | 1800
29 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee H | 750 | 0 | 0 | 0 | 750 | 2014-05-12 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 600 | 100 | 100 | 100 | 100 | 100 | 100
30 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee G | 750 | 0 | 0 | 0 | 750 | 2014-05-12 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 600 | 100 | 100 | 100 | 100 | 100 | 100
31 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 | 2014-05-12 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 600 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-10-14 08:00 | 2014-01-27 22:00 | 8355 | 1104 | 1050 | 2013-10-14 15:00 | -7251 | 13.21% | 54 | 105.1% | -75d 2h | 0.9868% | 45.45% | 2014-07-02 17:00 | 2018-03-02 14:00 | 2017-12-14 14:00 | 2014-08-13 10:00 | 2018-03-02 14:00 | 2017-12-20 11:00 | 2014-08-26 12:00 | 2072-07-12 14:00 | 2069-09-02 15:00 | 29826 | 28418.4781 | 218824.8899 | 2917017.9993 | 208172.856 | 2774389.1132 | 34218.4993 | 35180.5127 | 0.0098684 | 1.0514 | 0.13214 | 0.45455 | -75.25 | 1.0514 | 1 | 0.0098684 | 1
Tracking 2 | 2014-01-27 22:00 | 2014-03-03 22:00 | 15405 | 8919.45 | 7605 | 2014-01-31 16:00 | -6485.55 | 57.9% | 1314.45 | 117.3% | -21d 1h | 79.08% | 35.45% | 2014-06-27 09:00 | 2014-10-14 10:00 | 2014-08-20 15:00 | 2014-07-10 15:00 | 2014-10-14 10:00 | 2014-09-10 14:00 | 2014-06-11 11:00 | 2014-07-08 10:00 | 2014-06-18 17:00 | 28565.55 | 25476.6157 | 43806.478 | 34109.107 | 38471.5041 | 30203.2246 | 27490.3189 | 26721.9059 | 0.79084 | 1.1728 | 0.579 | 0.35453 | -21.125 | 1.1728 | 1 | 0.79084 | 1
Tracking 3 | 2014-03-03 22:00 | 2014-04-07 22:00 | 26730 | 17464.3589 | 14475 | 2014-03-17 10:00 | -9265.6411 | 65.34% | 2989.3589 | 120.7% | -15d 6h | 87.5% | 82.91% | 2014-07-17 09:00 | 2014-09-02 12:00 | 2014-07-08 16:00 | 2014-07-11 16:00 | 2014-09-02 12:00 | 2014-08-07 12:00 | 2014-06-03 17:00 | 2014-06-11 16:00 | 2014-05-30 16:00 | 26890.6411 | 24765.4667 | 33477.7065 | 28664.3041 | 30225.03 | 26235.5334 | 25804.3042 | 25363.8596 | 0.875 | 1.2065 | 0.65336 | 0.82912 | -15.75 | 1.2065 | 1 | 0.875 | 1
Closure | 2014-04-07 22:00 | 2014-05-13 08:00 | 29430 | 29880 | 17400 | 2014-05-13 10:00 | 450 | 101.5% | 12480 | 171.7% | 2h | 100.2% | 100% | 2014-05-08 17:00 | 2014-05-08 17:00 | 2014-02-11 15:00 | 2014-05-08 17:00 | 2014-05-08 17:00 | 2014-05-09 16:00 | 2014-05-12 17:00 | 2014-05-12 17:00 | 2014-05-12 17:00 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 1.0017 | 1.7172 | 1.0153 | 1 | 0.25 | 1.7172 | 1 | 1.0017 | 1