## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | CRM System | 1 |  |  | 2013-06-20 08:00 | 2014-05-12 17:00 | 233d |  |  | 0 |  |  | 44130 | 326.375
28 | supporting tasks | 1.1 |  |  | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h |  |  | 0 |  |  | 17730 | 34.25
1 | project management | 1.1.1 |  | FS24 | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h | Employee I | 17730 | 0 | 0 | 0 | 17730 | 34.25
29 | requirements | 1.2 |  |  | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h |  |  | 0 |  |  | 675 | 1.0417
27 | requirements | 1.2.1 |  |  | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 1.0417
30 | analysis | 1.3 |  |  | 2013-06-20 08:00 | 2014-02-21 17:00 | 177d |  |  | 0 |  |  | 4200 | 246.375
2 | analysis - solution concept | 1.3.1 |  | FS4;FS11 | 2013-06-20 08:00 | 2013-06-21 12:00 | 1d 4h | Employee B | 900 | 0 | 0 | 0 | 900 | 1.1667
3 | analysis - solution concept | 1.3.2 |  | FS4;FS11 | 2013-06-20 08:00 | 2013-06-20 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 0.375
4 | analysis - conceptual design | 1.3.3 | 2FS;3FS |  | 2013-09-24 08:00 | 2013-09-30 12:00 | 4d 4h | Employee A | 2700 | 0 | 0 | 0 | 2700 | 6.1667
11 | analysis validated | 1.3.4 | 2FS;3FS | FS24 | 2014-02-21 17:00 | 2014-02-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
31 | design | 1.4 |  |  | 2014-01-06 08:00 | 2014-03-07 17:00 | 45d |  |  | 0 |  |  | 8925 | 60.375
5 | design - data design | 1.4.1 |  | FS9 | 2014-01-06 08:00 | 2014-01-09 16:00 | 3d 7h | Employee G | 2325 | 0 | 0 | 0 | 2325 | 3.3333
6 | design - data design | 1.4.2 |  | FS9 | 2014-01-06 08:00 | 2014-01-17 15:00 | 9d 6h | Employee A | 5850 | 0 | 0 | 0 | 5850 | 11.2917
7 | design - distributiekanaal | 1.4.3 |  | FS9 | 2014-01-07 08:00 | 2014-01-07 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 0.29167
8 | design - distributiekanaal | 1.4.4 |  | FS9 | 2014-01-07 08:00 | 2014-01-07 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 0.16667
9 | design completed | 1.4.5 | 5FS;6FS;7FS;8FS | FS24 | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
32 | build | 1.5 |  |  | 2014-01-20 08:00 | 2014-03-11 16:00 | 36d 7h |  |  | 0 |  |  | 6150 | 50.3333
10 | build - distributiekanaal | 1.5.1 |  | FS12;FS13;FS14 | 2014-01-20 08:00 | 2014-01-21 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 1.2917
12 | build - stored procedures A | 1.5.2 | 10FS | FS14 | 2014-01-30 08:00 | 2014-02-06 11:00 | 5d 3h | Employee F | 3225 | 0 | 0 | 0 | 3225 | 7.125
13 | build - stored procedures B | 1.5.3 | 10FS | FS14 | 2014-01-30 08:00 | 2014-01-31 10:00 | 1d 2h | Employee F | 750 | 0 | 0 | 0 | 750 | 1.0833
14 | build - technical assembly test | 1.5.4 | 12FS;10FS;13FS |  | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 1.3333
33 | development | 1.6 |  |  | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 2550 | 11.375
15 | development - bugfixing | 1.6.1 |  | FS17 | 2014-03-10 08:00 | 2014-03-10 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 0.16667
16 | development - bugfixing | 1.6.2 |  | FS17 | 2014-03-10 08:00 | 2014-03-13 15:00 | 3d 6h | Employee F | 2250 | 0 | 0 | 0 | 2250 | 3.2917
17 | development completed | 1.6.3 | 15FS;16FS | FS24 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
34 | UAT | 1.7 |  |  | 2013-10-21 08:00 | 2014-04-25 17:00 | 135d |  |  | 0 |  |  | 2700 | 186.375
18 | test ict - distributiekanaal - prep | 1.7.1 |  | FS19 | 2014-02-24 08:00 | 2014-02-24 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 0.375
37 | test ict - distributiekanaal - exec | 1.7.2 |  | FS19 | 2014-02-24 08:00 | 2014-02-26 10:00 | 2d 2h | Employee K | 1350 | 0 | 0 | 0 | 1350 | 2.0833
19 | ict test completed | 1.7.3 | 18FS;37FS | FS24 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
20 | uat - test execution support | 1.7.4 |  |  | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee K | 375 | 0 | 0 | 0 | 375 | 0.25
38 | uat - test execution support | 1.7.5 |  |  | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee L | 375 | 0 | 0 | 0 | 375 | 0.25
21 | full handover ict > uat | 1.7.6 |  | FS24 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
22 | uat completed | 1.7.7 |  | FS24 | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
23 | code freeze | 1.7.8 |  | FS24 | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
35 | implementation | 1.8 |  |  | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0
24 | go live | 1.8.1 | 1FS;11FS;9FS;17FS;19FS;21FS;22FS;23FS |  | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
36 | post implementation | 1.9 |  |  | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 | 0.375
25 | post implementation - post go live support | 1.9.1 |  |  | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 | 0.375
26 | post implementation - post go live support | 1.9.2 |  |  | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 75 | 4;6;25; | 9150
2 | Employee B | Renewable | 1 | 0 | 75 | 2; | 900
3 | Employee C | Renewable | 1 | 0 | 75 | 3; | 600
4 | Employee D | Renewable | 1 | 0 | 75 |  | 0
5 | Employee E | Renewable | 1 | 0 | 75 | 7;10;15; | 1800
6 | Employee F | Renewable | 1 | 0 | 75 | 12;13;14;16;26; | 7950
7 | Employee G | Renewable | 1 | 0 | 75 | 5; | 2325
8 | Employee H | Renewable | 1 | 0 | 75 | 8; | 300
9 | Employee I | Renewable | 1 | 0 | 90 | 1; | 17730
10 | Employee J | Renewable | 1 | 0 | 75 | 27; | 675
11 | Employee K | Renewable | 1 | 0 | 75 | 18;37;20; | 2325
12 | Employee L | Renewable | 1 | 0 | 75 | 38; | 375

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | CRM System | 1864h |  |  |  |  | 99 | 100 | 101
28 | supporting tasks | 197h |  |  |  |  | 99 | 100 | 101
1 | project management | 197h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | requirements | 9h |  |  |  |  | 99 | 100 | 101
27 | requirements | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | analysis | 1416h |  |  |  |  | 99 | 100 | 101
2 | analysis - solution concept | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | analysis - solution concept | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | analysis - conceptual design | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | design | 360h |  |  |  |  | 99 | 100 | 101
5 | design - data design | 31h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | design - data design | 78h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | design - distributiekanaal | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | design - distributiekanaal | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | design completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | build | 295h |  |  |  |  | 99 | 100 | 101
10 | build - distributiekanaal | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | build - stored procedures A | 43h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | build - stored procedures B | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | build - technical assembly test | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | development | 80h |  |  |  |  | 99 | 100 | 101
15 | development - bugfixing | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | development - bugfixing | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | UAT | 1080h |  |  |  |  | 99 | 100 | 101
18 | test ict - distributiekanaal - prep | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | test ict - distributiekanaal - exec | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | ict test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | uat - test execution support | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | uat - test execution support | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | full handover ict > uat | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | uat completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | code freeze | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | implementation | 0 |  |  |  |  | 99 | 100 | 101
24 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | post implementation | 8h |  |  |  |  | 99 | 100 | 101
25 | post implementation - post go live support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | post implementation - post go live support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-08-05 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | CRM System | 2013-06-20 08:00 | 2014-05-12 17:00 | 233d |  |  | 0 |  |  | 44130 |  | 33d | [5 empty] | 2340 |  | 7.664% |  | 3382.2 | 1500
28 | supporting tasks | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h |  |  | 0 |  |  | 17730 |  | 33d | [5 empty] | 1440 |  | 14% |  | 2482.2 | 0
1 | project management | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h | Employee I | 17730 | 0 | 0 | 0 | 17730 | 2013-06-20 08:00 | 2d | 1440 | 6750 | 9d 3h | 0 | 0 | 1440 | 6750 | 14% | Started | 2482.2 | 0 | 100 | 8.1218 | 14 | 100 | 8.1218 | 14
29 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h |  |  | 0 |  |  | 675 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | analysis | 2013-06-20 08:00 | 2014-02-21 17:00 | 177d |  |  | 0 |  |  | 4200 |  | 33d | [5 empty] | 900 |  | 21.43% |  | 900 | 1500
2 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-21 12:00 | 1d 4h | Employee B | 900 | 0 | 0 | 0 | 900 | 2013-06-20 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-20 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
4 | analysis - conceptual design | 2013-09-24 08:00 | 2013-09-30 12:00 | 4d 4h | Employee A | 2700 | 0 | 0 | 0 | 2700 |  | 0 | 0 | 2700 | 4d 4h | 0 | 0 | 0 | 2700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | analysis validated | 2014-02-21 17:00 | 2014-02-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | design | 2014-01-06 08:00 | 2014-03-07 17:00 | 45d |  |  | 0 |  |  | 8925 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
5 | design - data design | 2014-01-06 08:00 | 2014-01-09 16:00 | 3d 7h | Employee G | 2325 | 0 | 0 | 0 | 2325 |  | 0 | 0 | 2325 | 3d 7h | 0 | 0 | 0 | 2325 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | design - data design | 2014-01-06 08:00 | 2014-01-17 15:00 | 9d 6h | Employee A | 5850 | 0 | 0 | 0 | 5850 |  | 0 | 0 | 5850 | 9d 6h | 0 | 0 | 0 | 5850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | design completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | build | 2014-01-20 08:00 | 2014-03-11 16:00 | 36d 7h |  |  | 0 |  |  | 6150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | build - distributiekanaal | 2014-01-20 08:00 | 2014-01-21 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 |  | 0 | 0 | 1050 | 1d 6h | 0 | 0 | 0 | 1050 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | build - stored procedures A | 2014-01-30 08:00 | 2014-02-06 11:00 | 5d 3h | Employee F | 3225 | 0 | 0 | 0 | 3225 |  | 0 | 0 | 3225 | 5d 3h | 0 | 0 | 0 | 3225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | build - stored procedures B | 2014-01-30 08:00 | 2014-01-31 10:00 | 1d 2h | Employee F | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | build - technical assembly test | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | development | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 2550 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | development - bugfixing | 2014-03-10 08:00 | 2014-03-10 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - bugfixing | 2014-03-10 08:00 | 2014-03-13 15:00 | 3d 6h | Employee F | 2250 | 0 | 0 | 0 | 2250 |  | 0 | 0 | 2250 | 3d 6h | 0 | 0 | 0 | 2250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | UAT | 2013-10-21 08:00 | 2014-04-25 17:00 | 135d |  |  | 0 |  |  | 2700 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | test ict - distributiekanaal - prep | 2014-02-24 08:00 | 2014-02-24 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | test ict - distributiekanaal - exec | 2014-02-24 08:00 | 2014-02-26 10:00 | 2d 2h | Employee K | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | ict test completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee K | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee L | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | full handover ict > uat | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | uat completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-10-07 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | CRM System | 2013-06-20 08:00 | 2014-05-12 17:00 | 233d |  |  | 0 |  |  | 44130 |  | 78d | [5 empty] | 5325 |  | 17.55% |  | 7746.7499 | 12075
28 | supporting tasks | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h |  |  | 0 |  |  | 17730 |  | 78d | [5 empty] | 3600 |  | 35% |  | 6205.4999 | 7200
1 | project management | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h | Employee I | 17730 | 0 | 0 | 0 | 17730 | 2013-06-20 08:00 | 5d | 3600 | 4590 | 6d 3h | 0 | 0 | 3600 | 4590 | 35% | Started | 6205.4999 | 7200 | 100 | 20.3046 | 35 | 100 | 20.3046 | 35
29 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h |  |  | 0 |  |  | 675 |  | 11d | [5 empty] | 450 |  | 71% |  | 479.25 | 675
27 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-23 08:00 | 6h | 450 | 75 | 1h | 0 | 0 | 450 | 75 | 71% | Started | 479.25 | 675 | 100 | 66.6667 | 71 | 100 | 66.6667 | 71
30 | analysis | 2013-06-20 08:00 | 2014-02-21 17:00 | 177d |  |  | 0 |  |  | 4200 |  | 78d | [5 empty] | 1275 |  | 25.29% |  | 1062 | 4200
2 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-21 12:00 | 1d 4h | Employee B | 900 | 0 | 0 | 0 | 900 | 2013-06-20 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-20 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
4 | analysis - conceptual design | 2013-09-24 08:00 | 2013-09-30 12:00 | 4d 4h | Employee A | 2700 | 0 | 0 | 0 | 2700 | 2013-09-23 08:00 | 5h | 375 | 75 | 1h | 0 | 0 | 375 | 75 | 6% | Started | 162 | 2700 | 100 | 13.8889 | 6 | 100 | 13.8889 | 6
11 | analysis validated | 2014-02-21 17:00 | 2014-02-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | design | 2014-01-06 08:00 | 2014-03-07 17:00 | 45d |  |  | 0 |  |  | 8925 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
5 | design - data design | 2014-01-06 08:00 | 2014-01-09 16:00 | 3d 7h | Employee G | 2325 | 0 | 0 | 0 | 2325 |  | 0 | 0 | 2325 | 3d 7h | 0 | 0 | 0 | 2325 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | design - data design | 2014-01-06 08:00 | 2014-01-17 15:00 | 9d 6h | Employee A | 5850 | 0 | 0 | 0 | 5850 |  | 0 | 0 | 5850 | 9d 6h | 0 | 0 | 0 | 5850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | design completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | build | 2014-01-20 08:00 | 2014-03-11 16:00 | 36d 7h |  |  | 0 |  |  | 6150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | build - distributiekanaal | 2014-01-20 08:00 | 2014-01-21 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 |  | 0 | 0 | 1050 | 1d 6h | 0 | 0 | 0 | 1050 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | build - stored procedures A | 2014-01-30 08:00 | 2014-02-06 11:00 | 5d 3h | Employee F | 3225 | 0 | 0 | 0 | 3225 |  | 0 | 0 | 3225 | 5d 3h | 0 | 0 | 0 | 3225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | build - stored procedures B | 2014-01-30 08:00 | 2014-01-31 10:00 | 1d 2h | Employee F | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | build - technical assembly test | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | development | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 2550 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | development - bugfixing | 2014-03-10 08:00 | 2014-03-10 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - bugfixing | 2014-03-10 08:00 | 2014-03-13 15:00 | 3d 6h | Employee F | 2250 | 0 | 0 | 0 | 2250 |  | 0 | 0 | 2250 | 3d 6h | 0 | 0 | 0 | 2250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | UAT | 2013-10-21 08:00 | 2014-04-25 17:00 | 135d |  |  | 0 |  |  | 2700 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | test ict - distributiekanaal - prep | 2014-02-24 08:00 | 2014-02-24 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | test ict - distributiekanaal - exec | 2014-02-24 08:00 | 2014-02-26 10:00 | 2d 2h | Employee K | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | ict test completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee K | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee L | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | full handover ict > uat | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | uat completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-12-09 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | CRM System | 2013-06-20 08:00 | 2014-05-12 17:00 | 233d |  |  | 0 |  |  | 44130 |  | 123d | [5 empty] | 8940 |  | 29.14% |  | 12857.3997 | 23355
28 | supporting tasks | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h |  |  | 0 |  |  | 17730 |  | 123d | [5 empty] | 5940 |  | 58% |  | 10283.3997 | 17730
1 | project management | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h | Employee I | 17730 | 0 | 0 | 0 | 17730 | 2013-06-20 08:00 | 8d 2h | 5940 | 2340 | 3d 2h | 0 | 0 | 5940 | 2340 | 58% | Started | 10283.3997 | 17730 | 100 | 33.5025 | 58 | 100 | 33.5025 | 58
29 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h |  |  | 0 |  |  | 675 |  | 1d 1h | [5 empty] | 675 |  | 100% |  | 675 | 675
27 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-23 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
30 | analysis | 2013-06-20 08:00 | 2014-02-21 17:00 | 177d |  |  | 0 |  |  | 4200 |  | 123d | [5 empty] | 2250 |  | 43.43% |  | 1824 | 4200
2 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-21 12:00 | 1d 4h | Employee B | 900 | 0 | 0 | 0 | 900 | 2013-06-20 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-20 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - conceptual design | 2013-09-24 08:00 | 2013-09-30 12:00 | 4d 4h | Employee A | 2700 | 0 | 0 | 0 | 2700 | 2013-09-23 08:00 | 1d 2h | 750 | 75 | 1h | 0 | 0 | 750 | 75 | 12% | Started | 324 | 2700 | 100 | 27.7778 | 12 | 100 | 27.7778 | 12
11 | analysis validated | 2014-02-21 17:00 | 2014-02-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | design | 2014-01-06 08:00 | 2014-03-07 17:00 | 45d |  |  | 0 |  |  | 8925 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
5 | design - data design | 2014-01-06 08:00 | 2014-01-09 16:00 | 3d 7h | Employee G | 2325 | 0 | 0 | 0 | 2325 |  | 0 | 0 | 2325 | 3d 7h | 0 | 0 | 0 | 2325 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | design - data design | 2014-01-06 08:00 | 2014-01-17 15:00 | 9d 6h | Employee A | 5850 | 0 | 0 | 0 | 5850 |  | 0 | 0 | 5850 | 9d 6h | 0 | 0 | 0 | 5850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | design completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | build | 2014-01-20 08:00 | 2014-03-11 16:00 | 36d 7h |  |  | 0 |  |  | 6150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | build - distributiekanaal | 2014-01-20 08:00 | 2014-01-21 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 |  | 0 | 0 | 1050 | 1d 6h | 0 | 0 | 0 | 1050 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | build - stored procedures A | 2014-01-30 08:00 | 2014-02-06 11:00 | 5d 3h | Employee F | 3225 | 0 | 0 | 0 | 3225 |  | 0 | 0 | 3225 | 5d 3h | 0 | 0 | 0 | 3225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | build - stored procedures B | 2014-01-30 08:00 | 2014-01-31 10:00 | 1d 2h | Employee F | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | build - technical assembly test | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | development | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 2550 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | development - bugfixing | 2014-03-10 08:00 | 2014-03-10 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - bugfixing | 2014-03-10 08:00 | 2014-03-13 15:00 | 3d 6h | Employee F | 2250 | 0 | 0 | 0 | 2250 |  | 0 | 0 | 2250 | 3d 6h | 0 | 0 | 0 | 2250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | UAT | 2013-10-21 08:00 | 2014-04-25 17:00 | 135d |  |  | 0 |  |  | 2700 |  | 36d | [5 empty] | 75 |  | 2.778% |  | 75 | 750
18 | test ict - distributiekanaal - prep | 2014-02-24 08:00 | 2014-02-24 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | test ict - distributiekanaal - exec | 2014-02-24 08:00 | 2014-02-26 10:00 | 2d 2h | Employee K | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | ict test completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee K | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 375 | 100 |  | 0 | 100 |  | 0
38 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee L | 375 | 0 | 0 | 0 | 375 | 2013-10-21 08:00 | 1h | 75 | 75 | 1h | 0 | 0 | 75 | 75 | 20% | Started | 75 | 375 | 100 | 20 | 20 | 100 | 20 | 20
21 | full handover ict > uat | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | uat completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-02-10 22:00 |  | TP Name | Tracking 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | CRM System | 2013-06-20 08:00 | 2014-05-12 17:00 | 233d |  |  | 0 |  |  | 44130 |  | 168d | [5 empty] | 20805 |  | 65.98% |  | 29117.0995 | 37305
28 | supporting tasks | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h |  |  | 0 |  |  | 17730 |  | 168d | [5 empty] | 7830 |  | 77% |  | 13652.0997 | 17730
1 | project management | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h | Employee I | 17730 | 0 | 0 | 0 | 17730 | 2013-06-20 08:00 | 10d 7h | 7830 | 450 | 5h | 0 | 0 | 7830 | 450 | 77% | Started | 13652.0997 | 17730 | 100 | 44.1624 | 77 | 100 | 44.1624 | 77
29 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h |  |  | 0 |  |  | 675 |  | 1d 1h | [5 empty] | 675 |  | 100% |  | 675 | 675
27 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-23 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
30 | analysis | 2013-06-20 08:00 | 2014-02-21 17:00 | 177d |  |  | 0 |  |  | 4200 |  | 168d | [5 empty] | 2250 |  | 43.43% |  | 1824 | 4200
2 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-21 12:00 | 1d 4h | Employee B | 900 | 0 | 0 | 0 | 900 | 2013-06-20 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-20 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - conceptual design | 2013-09-24 08:00 | 2013-09-30 12:00 | 4d 4h | Employee A | 2700 | 0 | 0 | 0 | 2700 | 2013-09-23 08:00 | 1d 2h | 750 | 75 | 1h | 0 | 0 | 750 | 75 | 12% | Started | 324 | 2700 | 100 | 27.7778 | 12 | 100 | 27.7778 | 12
11 | analysis validated | 2014-02-21 17:00 | 2014-02-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | design | 2014-01-06 08:00 | 2014-03-07 17:00 | 45d |  |  | 0 |  |  | 8925 |  | 26d | [5 empty] | 6300 |  | 94.27% |  | 8413.4999 | 8925
5 | design - data design | 2014-01-06 08:00 | 2014-01-09 16:00 | 3d 7h | Employee G | 2325 | 0 | 0 | 0 | 2325 | 2014-01-06 08:00 | 3d 2h | 1950 | 1650 | 2d 6h | 0 | 0 | 1950 | 1650 | 78% | Started | 1813.4999 | 2325 | 100 | 83.871 | 78 | 100 | 83.871 | 78
6 | design - data design | 2014-01-06 08:00 | 2014-01-17 15:00 | 9d 6h | Employee A | 5850 | 0 | 0 | 0 | 5850 | 2014-01-27 08:00 | 6d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 5850 | 5850 | 100 | 61.5385 | 100 | 100 | 61.5385 | 100
7 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2014-01-06 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
8 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-01-06 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
9 | design completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | build | 2014-01-20 08:00 | 2014-03-11 16:00 | 36d 7h |  |  | 0 |  |  | 6150 |  | 16d | [5 empty] | 3675 |  | 72.8% |  | 4477.4999 | 5025
10 | build - distributiekanaal | 2014-01-20 08:00 | 2014-01-21 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 2014-01-20 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
12 | build - stored procedures A | 2014-01-30 08:00 | 2014-02-06 11:00 | 5d 3h | Employee F | 3225 | 0 | 0 | 0 | 3225 | 2014-01-27 08:00 | 3d 4h | 2100 | 5250 | 8d 6h | 0 | 0 | 2100 | 5250 | 90% | Started | 2902.4999 | 3225 | 100 | 65.1163 | 90 | 100 | 65.1163 | 90
13 | build - stored procedures B | 2014-01-30 08:00 | 2014-01-31 10:00 | 1d 2h | Employee F | 750 | 0 | 0 | 0 | 750 | 2014-02-03 08:00 | 7h | 525 | 75 | 1h | 0 | 0 | 525 | 75 | 70% | Started | 525 | 750 | 100 | 70 | 70 | 100 | 70 | 70
14 | build - technical assembly test | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | development | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 2550 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | development - bugfixing | 2014-03-10 08:00 | 2014-03-10 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - bugfixing | 2014-03-10 08:00 | 2014-03-13 15:00 | 3d 6h | Employee F | 2250 | 0 | 0 | 0 | 2250 |  | 0 | 0 | 2250 | 3d 6h | 0 | 0 | 0 | 2250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | UAT | 2013-10-21 08:00 | 2014-04-25 17:00 | 135d |  |  | 0 |  |  | 2700 |  | 81d | [5 empty] | 75 |  | 2.778% |  | 75 | 750
18 | test ict - distributiekanaal - prep | 2014-02-24 08:00 | 2014-02-24 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | test ict - distributiekanaal - exec | 2014-02-24 08:00 | 2014-02-26 10:00 | 2d 2h | Employee K | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | ict test completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee K | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 375 | 100 |  | 0 | 100 |  | 0
38 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee L | 375 | 0 | 0 | 0 | 375 | 2013-10-21 08:00 | 1h | 75 | 75 | 1h | 0 | 0 | 75 | 75 | 20% | Started | 75 | 375 | 100 | 20 | 20 | 100 | 20 | 20
21 | full handover ict > uat | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | uat completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-03-24 22:00 |  | TP Name | Tracking 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | CRM System | 2013-06-20 08:00 | 2014-05-12 17:00 | 233d |  |  | 0 |  |  | 44130 |  | 198d | [5 empty] | 32790 |  | 88.57% |  | 39087.4498 | 42930
28 | supporting tasks | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h |  |  | 0 |  |  | 17730 |  | 198d | [5 empty] | 9090 |  | 89% |  | 15779.6997 | 17730
1 | project management | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h | Employee I | 17730 | 0 | 0 | 0 | 17730 | 2013-06-20 08:00 | 12d 5h | 9090 | 90 | 1h | 0 | 0 | 9090 | 90 | 89% | Started | 15779.6997 | 17730 | 100 | 51.269 | 89 | 100 | 51.269 | 89
29 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h |  |  | 0 |  |  | 675 |  | 1d 1h | [5 empty] | 675 |  | 100% |  | 675 | 675
27 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-23 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
30 | analysis | 2013-06-20 08:00 | 2014-02-21 17:00 | 177d |  |  | 0 |  |  | 4200 |  | 187d 7h | [5 empty] | 7725 |  | 100% |  | 4200 | 4200
2 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-21 12:00 | 1d 4h | Employee B | 900 | 0 | 0 | 0 | 900 | 2013-06-20 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-20 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - conceptual design | 2013-09-24 08:00 | 2013-09-30 12:00 | 4d 4h | Employee A | 2700 | 0 | 0 | 0 | 2700 | 2013-09-23 08:00 | 10d 3h | 6225 | 0 | 0 | 0 | 0 | 6225 | 0 | 100% | Finished | 2700 | 2700 | 100 | 230.5556 | 100 | 100 | 230.5556 | 100
11 | analysis validated | 2014-02-21 17:00 | 2014-02-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
31 | design | 2014-01-06 08:00 | 2014-03-07 17:00 | 45d |  |  | 0 |  |  | 8925 |  | 56d | [5 empty] | 6825 |  | 99.74% |  | 8901.75 | 8925
5 | design - data design | 2014-01-06 08:00 | 2014-01-09 16:00 | 3d 7h | Employee G | 2325 | 0 | 0 | 0 | 2325 | 2014-01-06 08:00 | 4d 1h | 2475 | 1125 | 1d 7h | 0 | 0 | 2475 | 1125 | 99% | Started | 2301.75 | 2325 | 100 | 106.4516 | 99 | 100 | 106.4516 | 99
6 | design - data design | 2014-01-06 08:00 | 2014-01-17 15:00 | 9d 6h | Employee A | 5850 | 0 | 0 | 0 | 5850 | 2014-01-27 08:00 | 6d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 5850 | 5850 | 100 | 61.5385 | 100 | 100 | 61.5385 | 100
7 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2014-01-06 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
8 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-01-06 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
9 | design completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | build | 2014-01-20 08:00 | 2014-03-11 16:00 | 36d 7h |  |  | 0 |  |  | 6150 |  | 37d 6h | [5 empty] | 5250 |  | 100% |  | 6150 | 6150
10 | build - distributiekanaal | 2014-01-20 08:00 | 2014-01-21 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 2014-01-20 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
12 | build - stored procedures A | 2014-01-30 08:00 | 2014-02-06 11:00 | 5d 3h | Employee F | 3225 | 0 | 0 | 0 | 3225 | 2014-01-27 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 3225 | 3225 | 100 | 72.093 | 100 | 100 | 72.093 | 100
13 | build - stored procedures B | 2014-01-30 08:00 | 2014-01-31 10:00 | 1d 2h | Employee F | 750 | 0 | 0 | 0 | 750 | 2014-02-03 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
14 | build - technical assembly test | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-03-10 16:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
33 | development | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 2550 |  | 21d | [5 empty] | 2100 |  | 88.24% |  | 2250 | 2550
15 | development - bugfixing | 2014-03-10 08:00 | 2014-03-10 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 300 | 100 |  | 0 | 100 |  | 0
16 | development - bugfixing | 2014-03-10 08:00 | 2014-03-13 15:00 | 3d 6h | Employee F | 2250 | 0 | 0 | 0 | 2250 | 2014-02-24 08:00 | 3d 4h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 2250 | 2250 | 100 | 93.3333 | 100 | 100 | 93.3333 | 100
17 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | UAT | 2013-10-21 08:00 | 2014-04-25 17:00 | 135d |  |  | 0 |  |  | 2700 |  | 111d | [5 empty] | 1125 |  | 41.89% |  | 1131 | 2700
18 | test ict - distributiekanaal - prep | 2014-02-24 08:00 | 2014-02-24 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
37 | test ict - distributiekanaal - exec | 2014-02-24 08:00 | 2014-02-26 10:00 | 2d 2h | Employee K | 1350 | 0 | 0 | 0 | 1350 | 2014-03-17 08:00 | 1d 2h | 750 | 375 | 5h | 0 | 0 | 750 | 375 | 56% | Started | 756 | 1350 | 100 | 55.5556 | 56 | 100 | 55.5556 | 56
19 | ict test completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee K | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 375 | 100 |  | 0 | 100 |  | 0
38 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee L | 375 | 0 | 0 | 0 | 375 | 2013-10-21 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
21 | full handover ict > uat | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | uat completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2014-05-12 09:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | CRM System | 2013-06-20 08:00 | 2014-05-12 17:00 | 233d |  |  | 0 |  |  | 44130 |  | 233d | [5 empty] | 36870 |  | 100% |  | 44130 | 43080
28 | supporting tasks | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h |  |  | 0 |  |  | 17730 |  | 14d 1h | [5 empty] | 10170 |  | 100% |  | 17730 | 17730
1 | project management | 2013-09-24 08:00 | 2013-10-28 14:00 | 24d 5h | Employee I | 17730 | 0 | 0 | 0 | 17730 | 2013-06-20 08:00 | 14d 1h | 10170 | 0 | 0 | 0 | 0 | 10170 | 0 | 100% | Finished | 17730 | 17730 | 100 | 57.3604 | 100 | 100 | 57.3604 | 100
29 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h |  |  | 0 |  |  | 675 |  | 1d 1h | [5 empty] | 675 |  | 100% |  | 675 | 675
27 | requirements | 2013-09-24 08:00 | 2013-09-25 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-23 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
30 | analysis | 2013-06-20 08:00 | 2014-02-21 17:00 | 177d |  |  | 0 |  |  | 4200 |  | 187d 7h | [5 empty] | 7725 |  | 100% |  | 4200 | 4200
2 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-21 12:00 | 1d 4h | Employee B | 900 | 0 | 0 | 0 | 900 | 2013-06-20 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis - solution concept | 2013-06-20 08:00 | 2013-06-20 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - conceptual design | 2013-09-24 08:00 | 2013-09-30 12:00 | 4d 4h | Employee A | 2700 | 0 | 0 | 0 | 2700 | 2013-09-23 08:00 | 10d 3h | 6225 | 0 | 0 | 0 | 0 | 6225 | 0 | 100% | Finished | 2700 | 2700 | 100 | 230.5556 | 100 | 100 | 230.5556 | 100
11 | analysis validated | 2014-02-21 17:00 | 2014-02-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
31 | design | 2014-01-06 08:00 | 2014-03-07 17:00 | 45d |  |  | 0 |  |  | 8925 |  | 56d 7h | [5 empty] | 6900 |  | 100% |  | 8925 | 8925
5 | design - data design | 2014-01-06 08:00 | 2014-01-09 16:00 | 3d 7h | Employee G | 2325 | 0 | 0 | 0 | 2325 | 2014-01-06 08:00 | 4d 2h | 2550 | 0 | 0 | 0 | 0 | 2550 | 0 | 100% | Finished | 2325 | 2325 | 100 | 109.6774 | 100 | 100 | 109.6774 | 100
6 | design - data design | 2014-01-06 08:00 | 2014-01-17 15:00 | 9d 6h | Employee A | 5850 | 0 | 0 | 0 | 5850 | 2014-01-27 08:00 | 6d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 5850 | 5850 | 100 | 61.5385 | 100 | 100 | 61.5385 | 100
7 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2014-01-06 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
8 | design - distributiekanaal | 2014-01-07 08:00 | 2014-01-07 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-01-06 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
9 | design completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
32 | build | 2014-01-20 08:00 | 2014-03-11 16:00 | 36d 7h |  |  | 0 |  |  | 6150 |  | 37d 6h | [5 empty] | 5250 |  | 100% |  | 6150 | 6150
10 | build - distributiekanaal | 2014-01-20 08:00 | 2014-01-21 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 2014-01-20 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
12 | build - stored procedures A | 2014-01-30 08:00 | 2014-02-06 11:00 | 5d 3h | Employee F | 3225 | 0 | 0 | 0 | 3225 | 2014-01-27 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 3225 | 3225 | 100 | 72.093 | 100 | 100 | 72.093 | 100
13 | build - stored procedures B | 2014-01-30 08:00 | 2014-01-31 10:00 | 1d 2h | Employee F | 750 | 0 | 0 | 0 | 750 | 2014-02-03 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
14 | build - technical assembly test | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-03-10 16:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
33 | development | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 2550 |  | 26d 7h | [5 empty] | 2850 |  | 100% |  | 2550 | 2550
15 | development - bugfixing | 2014-03-10 08:00 | 2014-03-10 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-31 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 300 | 300 | 100 | 250 | 100 | 100 | 250 | 100
16 | development - bugfixing | 2014-03-10 08:00 | 2014-03-13 15:00 | 3d 6h | Employee F | 2250 | 0 | 0 | 0 | 2250 | 2014-02-24 08:00 | 3d 4h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 2250 | 2250 | 100 | 93.3333 | 100 | 100 | 93.3333 | 100
17 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-01 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
34 | UAT | 2013-10-21 08:00 | 2014-04-25 17:00 | 135d |  |  | 0 |  |  | 2700 |  | 134d 7h | [5 empty] | 2100 |  | 100% |  | 2700 | 2700
18 | test ict - distributiekanaal - prep | 2014-02-24 08:00 | 2014-02-24 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 2014-03-25 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
37 | test ict - distributiekanaal - exec | 2014-02-24 08:00 | 2014-02-26 10:00 | 2d 2h | Employee K | 1350 | 0 | 0 | 0 | 1350 | 2014-03-17 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 1350 | 1350 | 100 | 100 | 100 | 100 | 100 | 100
19 | ict test completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
20 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee K | 375 | 0 | 0 | 0 | 375 | 2014-03-31 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 375 | 375 | 100 | 80 | 100 | 100 | 80 | 100
38 | uat - test execution support | 2013-10-21 08:00 | 2013-10-21 14:00 | 5h | Employee L | 375 | 0 | 0 | 0 | 375 | 2013-10-21 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
21 | full handover ict > uat | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
22 | uat completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
23 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
35 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
36 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 1d | [5 empty] | 1200 |  | 100% |  | 1200 | 150
25 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 75 | 100 | 100 | 100 | 100 | 100 | 100
26 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 75 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-06-20 08:00 | 2013-08-05 22:00 | 1500 | 3382.2 | 2340 | 2013-09-24 17:00 | 1882.2 | 225.5% | 1042.2 | 144.5% | 36d | 209.1% | 47.37% | 2014-04-28 17:00 | 2013-11-12 11:00 | 2013-09-27 12:00 | 2014-03-14 14:00 | 2013-11-12 11:00 | 2013-10-11 14:00 | 2014-03-21 17:00 | 2013-11-22 11:00 | 2013-10-21 10:00 | 43087.8 | 30531.6657 | 20411.5806 | 21828.0783 | 14842.9562 | 15822.9705 | 27692.2173 | 28220.0072 | 2.0909 | 1.4454 | 2.2548 | 0.47368 | 36 | 1.4454 | 1 | 2.0909 | 1
Tracking 2 | 2013-08-05 22:00 | 2013-10-07 22:00 | 12075 | 7746.7499 | 5325 | 2013-09-30 09:00 | -4328.2501 | 64.16% | 2421.7499 | 145.5% | -5d 7h | 92.47% | 59.2% | 2014-06-12 16:00 | 2014-11-11 09:00 | 2014-06-04 14:00 | 2014-06-19 17:00 | 2014-11-11 09:00 | 2014-07-08 17:00 | 2014-05-20 16:00 | 2014-06-06 17:00 | 2014-03-24 14:00 | 41708.2501 | 30334.302 | 62036.234 | 44671.8771 | 44307.4541 | 32371.4548 | 33482.326 | 32300.1957 | 0.92468 | 1.4548 | 0.64155 | 0.59203 | -5.875 | 1.4548 | 1 | 0.92468 | 1
Tracking 3 | 2013-10-07 22:00 | 2013-12-09 22:00 | 23355 | 12857.3997 | 8940 | 2013-10-08 17:00 | -10497.6003 | 55.05% | 3917.3997 | 143.8% | -44d | 64.23% | 81.43% | 2014-07-29 11:00 | 2015-02-03 10:00 | 2014-08-06 10:00 | 2014-07-29 10:00 | 2015-02-03 10:00 | 2014-09-26 15:00 | 2014-07-11 17:00 | 2014-11-10 15:00 | 2014-07-30 15:00 | 40212.6003 | 30684.447 | 65745.5437 | 57630.2511 | 48437.999 | 42795.2783 | 33746.6413 | 33390.7143 | 0.64228 | 1.4382 | 0.55052 | 0.8143 | -44 | 1.4382 | 1 | 0.64228 | 1
Tracking 4 | 2013-12-09 22:00 | 2014-02-10 22:00 | 37305 | 29117.0995 | 20805 | 2014-01-10 11:00 | -8187.9005 | 78.05% | 8312.0995 | 140% | -21d 5h | 87.13% | 73.7% | 2014-07-11 10:00 | 2014-08-12 12:00 | 2014-04-15 10:00 | 2014-07-02 16:00 | 2014-08-12 12:00 | 2014-06-20 10:00 | 2014-06-11 14:00 | 2014-06-30 11:00 | 2014-05-20 17:00 | 35817.9005 | 31532.1466 | 40039.6169 | 38035.861 | 34548.6836 | 33116.9428 | 32573.1577 | 32408.0509 | 0.87128 | 1.3995 | 0.78051 | 0.73704 | -21.625 | 1.3995 | 1 | 0.87128 | 1
Tracking 5 | 2014-02-10 22:00 | 2014-03-24 22:00 | 42930 | 39087.4498 | 32790 | 2014-02-25 16:00 | -3842.5502 | 91.05% | 6297.4498 | 119.2% | -19d 1h | 90.34% | 91.5% | 2014-06-10 10:00 | 2014-06-12 16:00 | 2014-04-16 14:00 | 2014-06-05 15:00 | 2014-06-12 16:00 | 2014-05-30 14:00 | 2014-06-09 09:00 | 2014-06-16 16:00 | 2014-06-03 10:00 | 37832.5502 | 37020.1358 | 38328.2657 | 38371.6908 | 37435.9857 | 37472.4145 | 37229.8741 | 37235.4193 | 0.90341 | 1.1921 | 0.91049 | 0.915 | -19.125 | 1.1921 | 1 | 0.90341 | 1
Closure | 2014-03-24 22:00 | 2014-05-12 09:00 | 43080 | 44130 | 36870 | 2014-05-12 17:00 | 1050 | 102.4% | 7260 | 119.7% | 7h | 100.4% | 100% | 2014-05-05 12:00 | 2014-05-05 12:00 | 2014-03-12 17:00 | 2014-05-05 11:00 | 2014-05-05 12:00 | 2014-05-06 10:00 | 2014-05-12 09:00 | 2014-05-12 09:00 | 2014-05-12 09:00 | 36870 | 36870 | 36870 | 36870 | 36870 | 36870 | 36870 | 36870 | 1.0038 | 1.1969 | 1.0244 | 1 | 0.875 | 1.1969 | 1 | 1.0038 | 1