## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Social Apartments Ypres (1) | 1 |  |  | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 | 389.375
1 | grondwerken | 1.1 |  |  | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 11.375
2 | fundering | 1.2 |  | FS5 | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 4.375
3 | rioleringswerken | 1.3 |  |  | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 9.375
4 | regenputten | 1.4 |  |  | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 1.375
5 | wanden gelijkvloers | 1.5 | 2FS | FS6 | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 4.375
6 | predallen + vloerplaat | 1.6 | 5FS | FS7;FS11 | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 4.375
7 | wanden 1e verdiep | 1.7 | 6FS | FS8 | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 4.375
8 | predallen + vloerplaat | 1.8 | 7FS | FS9 | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 4.375
9 | wanden 2e verdiep | 1.9 | 8FS | FS13;FS15 | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 4.375
11 | gevel | 1.10 | 6FS |  | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 105.375
12 | plaatsen blauwe hardsteen | 1.11 |  | FS41 | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 6.9583
13 | schoorsteen | 1.12 | 9FS |  | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 14.375
14 | plaatsen betonnen trappen | 1.13 |  | FS23 | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 4
15 | houten dakstructuur | 1.14 | 9FS | FS16 | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 6.375
16 | hellingsbeton | 1.15 | 15FS | FS17 | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 7
17 | dakisolatie | 1.16 | 16FS | FS18 | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 7
18 | membranen + koepels plaatsen | 1.17 | 17FS | FS19;FS20 | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 4
19 | dakrandprofielen | 1.18 | 18FS |  | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 | 7
20 | kroonlijsten | 1.19 | 18FS |  | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 | 7
21 | afwerking dakverdichting | 1.20 |  |  | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 | 9
41 | opmeten buitenschrijnwerk | 1.21 | 12FS | SS22+8w | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 1.0833
22 | plaatsen buitendeuren en ramen | 1.22 | 41SS+8w | FS25 | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 | 27.375
23 | buitentrapleuningen | 1.23 | 14FS |  | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 | 1.9583
24 | andere afwerkingen | 1.24 |  |  | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 | 7.375
25 | pleisterwerken | 1.25 | 22FS | SS33;FS42 | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 | 27.375
42 | PUR + chape | 1.26 | 25FS | FS26+2w | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 | 13.375
26 | binnenvloeren | 1.27 | 42FS+2w | FS27;FS28;FS29 | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 | 13.375
27 | plaatsen plinten | 1.28 | 26FS |  | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 | 4.375
28 | plaatsen binnendeuren | 1.29 | 26FS |  | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 | 21.375
29 | keukens | 1.30 | 26FS |  | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 | 21.375
30 | venstertabletten + faience | 1.31 |  |  | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 | 7
31 | sanitair | 1.32 |  |  | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 29.375
33 | CLV | 1.33 | 25SS |  | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 29.375
34 | ventilatie | 1.34 | 35SS |  | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 30
35 | electriciteitsnet + toebehoren | 1.35 |  | SS34 | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 86.375
36 | tegels buiten | 1.36 |  |  | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 | 4.375
37 | plaatsen brievenbussen | 1.37 |  |  | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 | 1.375
38 | plaatsen afsluiting | 1.38 |  |  | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 | 4.375
39 | fietsrekken | 1.39 |  |  | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 | 0.375
40 | afwerking omgevingswerken | 1.40 |  |  | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Social Apartments Ypres (1) | 1952h |  |  |  |  | 99 | 100 | 101
1 | grondwerken | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | fundering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | rioleringswerken | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | regenputten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | wanden gelijkvloers | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | predallen + vloerplaat | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | wanden 1e verdiep | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | predallen + vloerplaat | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | wanden 2e verdiep | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | gevel | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | plaatsen blauwe hardsteen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | schoorsteen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | plaatsen betonnen trappen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | houten dakstructuur | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | hellingsbeton | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | dakisolatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | membranen + koepels plaatsen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | dakrandprofielen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | kroonlijsten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | afwerking dakverdichting | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | opmeten buitenschrijnwerk | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | plaatsen buitendeuren en ramen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | buitentrapleuningen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | andere afwerkingen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | pleisterwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | PUR + chape | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | binnenvloeren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | plaatsen plinten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | plaatsen binnendeuren | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | keukens | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | venstertabletten + faience | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | sanitair | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | CLV | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | ventilatie | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | electriciteitsnet + toebehoren | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | tegels buiten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | plaatsen brievenbussen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | plaatsen afsluiting | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | fietsrekken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | afwerking omgevingswerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-05-31 17:00 |  | TP Name | 31/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 11d | [5 empty] | 35599.6499 |  | 7.268% |  | 32045.8425 | 42254.6001
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 5d | 21812.5801 | 13087.548 | 3d | -4625.9102 | 0 | 17186.6699 | 13087.548 | 62.5% | Started | 13632.8625 | 21812.5801 | 100 | 100 | 62.5 | 100 | 78.7925 | 62.5
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 |  | 0 | 0 | 2029.04 | 2d | 0 | 0 | 0 | 2029.04 | 0% | Not Started | 0 | 2029.04 | 100 |  | 0 | 100 |  | 0
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 |  | 0 | 0 | 21831.3809 | 5d | 0 | 0 | 0 | 21831.3809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 |  | 0 | 0 | 8663.8096 | 5d | 0 | 0 | 0 | 8663.8096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 |  | 0 | 0 | 21831.3809 | 5d | 0 | 0 | 0 | 21831.3809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 |  | 0 | 0 | 17906.6992 | 5d | 0 | 0 | 0 | 17906.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 |  | 0 | 0 | 21831.3809 | 5d | 0 | 0 | 0 | 21831.3809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 |  | 0 | 0 | 37784.2617 | 60d | 0 | 0 | 0 | 37784.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 |  | 0 | 0 | 2059.53 | 5d | 0 | 0 | 0 | 2059.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 |  | 0 | 0 | 12872.6602 | 10d | 0 | 0 | 0 | 12872.6602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 |  | 0 | 0 | 3656.3799 | 2d | 0 | 0 | 0 | 3656.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 |  | 0 | 0 | 3148.28 | 5d | 0 | 0 | 0 | 3148.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 |  | 0 | 0 | 2339.1299 | 5d | 0 | 0 | 0 | 2339.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 |  | 0 | 0 | 5149.0098 | 5d | 0 | 0 | 0 | 5149.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 |  | 0 | 0 | 8453.9199 | 2d | 0 | 0 | 0 | 8453.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 |  | 0 | 0 | 5471.2998 | 5d | 0 | 0 | 0 | 5471.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 |  | 0 | 0 | 10 | 1d 2h | 0 | 0 | 0 | 10 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 |  | 0 | 0 | 40156.5195 | 10d | 0 | 0 | 0 | 40156.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 |  | 0 | 0 | 17037.9492 | 20d | 0 | 0 | 0 | 17037.9492 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 |  | 0 | 0 | 28179.6191 | 20d | 0 | 0 | 0 | 28179.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 |  | 0 | 0 | 12525.5703 | 20d | 0 | 0 | 0 | 12525.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 |  | 0 | 0 | 18585.5195 | 60d | 0 | 0 | 0 | 18585.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-06-30 16:00 |  | TP Name | 30/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 32d | [5 empty] | 94581.1714 |  | 21.45% |  | 94581.1714 | 115636.5591
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 |  | 0 | 0 | 17906.6992 | 5d | 0 | 0 | 0 | 17906.6992 | 0% | Not Started | 0 | 17906.6992 | 100 |  | 0 | 100 |  | 0
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 |  | 0 | 0 | 21831.3809 | 5d | 0 | 0 | 0 | 21831.3809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 |  | 0 | 0 | 37784.2617 | 60d | 0 | 0 | 0 | 37784.2617 | 0% | Not Started | 0 | 3148.6885 | 100 |  | 0 | 100 |  | 0
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 |  | 0 | 0 | 2059.53 | 5d | 0 | 0 | 0 | 2059.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 |  | 0 | 0 | 12872.6602 | 10d | 0 | 0 | 0 | 12872.6602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 |  | 0 | 0 | 3656.3799 | 2d | 0 | 0 | 0 | 3656.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 |  | 0 | 0 | 3148.28 | 5d | 0 | 0 | 0 | 3148.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 |  | 0 | 0 | 2339.1299 | 5d | 0 | 0 | 0 | 2339.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 |  | 0 | 0 | 5149.0098 | 5d | 0 | 0 | 0 | 5149.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 |  | 0 | 0 | 8453.9199 | 2d | 0 | 0 | 0 | 8453.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 |  | 0 | 0 | 5471.2998 | 5d | 0 | 0 | 0 | 5471.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 |  | 0 | 0 | 10 | 1d 2h | 0 | 0 | 0 | 10 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 |  | 0 | 0 | 40156.5195 | 10d | 0 | 0 | 0 | 40156.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 |  | 0 | 0 | 17037.9492 | 20d | 0 | 0 | 0 | 17037.9492 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 |  | 0 | 0 | 28179.6191 | 20d | 0 | 0 | 0 | 28179.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 |  | 0 | 0 | 12525.5703 | 20d | 0 | 0 | 0 | 12525.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 |  | 0 | 0 | 18585.5195 | 60d | 0 | 0 | 0 | 18585.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2012-07-31 16:00 |  | TP Name | 31/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 42d | [5 empty] | 107567.064 |  | 22.88% |  | 100878.5485 | 143765.3169
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 |  | 0 | 0 | 17906.6992 | 5d | 0 | 0 | 0 | 17906.6992 | 0% | Not Started | 0 | 17906.6992 | 100 |  | 0 | 100 |  | 0
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 |  | 0 | 0 | 21831.3809 | 5d | 0 | 0 | 0 | 21831.3809 | 0% | Not Started | 0 | 21831.3809 | 100 |  | 0 | 100 |  | 0
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 10d | 6297.377 | 31486.8848 | 50d | 6688.5156 | 0 | 12985.8926 | 31486.8848 | 16.67% | Started | 6297.3771 | 9446.0654 | 100 | 16.6667 | 16.6667 | 100 | 34.3685 | 16.6667
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 |  | 0 | 0 | 2059.53 | 5d | 0 | 0 | 0 | 2059.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 |  | 0 | 0 | 12872.6602 | 10d | 0 | 0 | 0 | 12872.6602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 |  | 0 | 0 | 3656.3799 | 2d | 0 | 0 | 0 | 3656.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 |  | 0 | 0 | 3148.28 | 5d | 0 | 0 | 0 | 3148.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 |  | 0 | 0 | 2339.1299 | 5d | 0 | 0 | 0 | 2339.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 |  | 0 | 0 | 5149.0098 | 5d | 0 | 0 | 0 | 5149.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 |  | 0 | 0 | 8453.9199 | 2d | 0 | 0 | 0 | 8453.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 |  | 0 | 0 | 5471.2998 | 5d | 0 | 0 | 0 | 5471.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 |  | 0 | 0 | 10 | 1d 2h | 0 | 0 | 0 | 10 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 |  | 0 | 0 | 40156.5195 | 10d | 0 | 0 | 0 | 40156.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 |  | 0 | 0 | 17037.9492 | 20d | 0 | 0 | 0 | 17037.9492 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 |  | 0 | 0 | 28179.6191 | 20d | 0 | 0 | 0 | 28179.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 |  | 0 | 0 | 12525.5703 | 20d | 0 | 0 | 0 | 12525.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 |  | 0 | 0 | 18585.5195 | 60d | 0 | 0 | 0 | 18585.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2012-08-31 16:00 |  | TP Name | 31/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 60d 7h | [5 empty] | 151867.7534 |  | 33.32% |  | 146914.0057 | 168524.276
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 20d | 12594.7539 | 25189.5078 | 40d | 4953.748 | 0 | 17548.502 | 25189.5078 | 33.33% | Started | 12594.7543 | 21332.3644 | 100 | 33.3333 | 33.3333 | 100 | 46.4439 | 33.3333
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 |  | 0 | 0 | 2059.53 | 5d | 0 | 0 | 0 | 2059.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 |  | 0 | 0 | 12872.6602 | 10d | 0 | 0 | 0 | 12872.6602 | 0% | Not Started | 0 | 12872.6602 | 100 |  | 0 | 100 |  | 0
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 |  | 0 | 0 | 3656.3799 | 2d | 0 | 0 | 0 | 3656.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 |  | 0 | 0 | 3148.28 | 5d | 0 | 0 | 0 | 3148.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 |  | 0 | 0 | 2339.1299 | 5d | 0 | 0 | 0 | 2339.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 |  | 0 | 0 | 5149.0098 | 5d | 0 | 0 | 0 | 5149.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 |  | 0 | 0 | 8453.9199 | 2d | 0 | 0 | 0 | 8453.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 |  | 0 | 0 | 5471.2998 | 5d | 0 | 0 | 0 | 5471.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 |  | 0 | 0 | 10 | 1d 2h | 0 | 0 | 0 | 10 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 |  | 0 | 0 | 40156.5195 | 10d | 0 | 0 | 0 | 40156.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 |  | 0 | 0 | 17037.9492 | 20d | 0 | 0 | 0 | 17037.9492 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 |  | 0 | 0 | 28179.6191 | 20d | 0 | 0 | 0 | 28179.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 |  | 0 | 0 | 12525.5703 | 20d | 0 | 0 | 0 | 12525.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 |  | 0 | 0 | 18585.5195 | 60d | 0 | 0 | 0 | 18585.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2012-09-30 16:00 |  | TP Name | 30/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 81d | [5 empty] | 168541.9536 |  | 37.88% |  | 167026.9381 | 193510.3932
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 40d | 25189.5078 | 12594.7539 | 20d | 1718.1943 | 0 | 26907.7021 | 12594.7539 | 66.67% | Started | 25189.5086 | 34005.8355 | 100 | 66.6667 | 66.6667 | 100 | 71.214 | 66.6667
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 |  | 0 | 0 | 2059.53 | 5d | 0 | 0 | 0 | 2059.53 | 0% | Not Started | 0 | 2059.53 | 100 |  | 0 | 100 |  | 0
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 3d | 3861.798 | 9010.8621 | 7d | -203.1779 | 0 | 3658.6201 | 9010.8621 | 30% | Started | 3861.7982 | 12872.6602 | 100 | 30 | 30 | 100 | 28.4216 | 30
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 |  | 0 | 0 | 3148.28 | 5d | 0 | 0 | 0 | 3148.28 | 0% | Not Started | 0 | 3148.28 | 100 |  | 0 | 100 |  | 0
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 |  | 0 | 0 | 2339.1299 | 5d | 0 | 0 | 0 | 2339.1299 | 0% | Not Started | 0 | 350.8695 | 100 |  | 0 | 100 |  | 0
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 |  | 0 | 0 | 5149.0098 | 5d | 0 | 0 | 0 | 5149.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 |  | 0 | 0 | 8453.9199 | 2d | 0 | 0 | 0 | 8453.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 |  | 0 | 0 | 5471.2998 | 5d | 0 | 0 | 0 | 5471.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 |  | 0 | 0 | 10 | 1d 2h | 0 | 0 | 0 | 10 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 |  | 0 | 0 | 40156.5195 | 10d | 0 | 0 | 0 | 40156.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 |  | 0 | 0 | 17037.9492 | 20d | 0 | 0 | 0 | 17037.9492 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 |  | 0 | 0 | 28179.6191 | 20d | 0 | 0 | 0 | 28179.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 |  | 0 | 0 | 12525.5703 | 20d | 0 | 0 | 0 | 12525.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 |  | 0 | 0 | 18585.5195 | 60d | 0 | 0 | 0 | 18585.5195 | 0% | Not Started | 0 | 3097.5866 | 100 |  | 0 | 100 |  | 0
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2012-10-31 16:00 |  | TP Name | 31/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 103d 7h | [5 empty] | 181695.7033 |  | 41.07% |  | 181107.0654 | 230467.5994
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 55d | 34635.5732 | 3148.6885 | 5d | 2801.2285 | 0 | 37436.8017 | 3148.6885 | 91.67% | Started | 34635.574 | 37784.2617 | 100 | 91.6667 | 91.6667 | 100 | 99.0804 | 91.6667
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 5d | 6436.3301 | 6436.3301 | 5d | -2212.5898 | 0 | 4223.7402 | 6436.3301 | 50% | Started | 6436.3301 | 12872.6602 | 100 | 50 | 50 | 100 | 32.8117 | 50
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 |  | 0 | 0 | 3148.28 | 5d | 0 | 0 | 0 | 3148.28 | 0% | Not Started | 0 | 3148.28 | 100 |  | 0 | 100 |  | 0
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 |  | 0 | 0 | 2339.1299 | 5d | 0 | 0 | 0 | 2339.1299 | 0% | Not Started | 0 | 2339.1299 | 100 |  | 0 | 100 |  | 0
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 |  | 0 | 0 | 5149.0098 | 5d | 0 | 0 | 0 | 5149.0098 | 0% | Not Started | 0 | 5149.0098 | 100 |  | 0 | 100 |  | 0
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 |  | 0 | 0 | 8453.9199 | 2d | 0 | 0 | 0 | 8453.9199 | 0% | Not Started | 0 | 8453.9199 | 100 |  | 0 | 100 |  | 0
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 |  | 0 | 0 | 5471.2998 | 5d | 0 | 0 | 0 | 5471.2998 | 0% | Not Started | 0 | 5471.2998 | 100 |  | 0 | 100 |  | 0
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 4534.79 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 485.7707 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 |  | 0 | 0 | 10 | 1d 2h | 0 | 0 | 0 | 10 | 0% | Not Started | 0 | 10 | 100 |  | 0 | 100 |  | 0
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 |  | 0 | 0 | 40156.5195 | 10d | 0 | 0 | 0 | 40156.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 |  | 0 | 0 | 17037.9492 | 20d | 0 | 0 | 0 | 17037.9492 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 |  | 0 | 0 | 28179.6191 | 20d | 0 | 0 | 0 | 28179.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 |  | 0 | 0 | 12525.5703 | 20d | 0 | 0 | 0 | 12525.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 |  | 0 | 0 | 18585.5195 | 60d | 0 | 0 | 0 | 18585.5195 | 0% | Not Started | 0 | 10183.3159 | 100 |  | 0 | 100 |  | 0
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2012-11-30 16:00 |  | TP Name | 30/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 122d 7h | [5 empty] | 211395.0503 |  | 47.43% |  | 209148.2892 | 237010.2331
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 55d | 34635.5732 | 3148.6885 | 5d | 2801.2285 | 0 | 37436.8017 | 3148.6885 | 91.67% | Started | 34635.574 | 37784.2617 | 100 | 91.6667 | 91.6667 | 100 | 99.0804 | 91.6667
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 9d | 11585.3941 | 1287.266 | 1d | 51.706 | 0 | 11637.1001 | 1287.266 | 90% | Started | 11585.3938 | 12872.6602 | 100 | 90 | 90 | 100 | 90.4017 | 90
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 100% | Finished | 3148.28 | 3148.28 | 100 | 100 | 100 | 100 | 100 | 100
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 100% | Finished | 2339.1299 | 2339.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 2d | 2059.6039 | 3089.4059 | 3d | -910.5941 | 0 | 1149.0098 | 3089.4059 | 40% | Started | 2059.6039 | 5149.0098 | 100 | 40 | 40 | 100 | 22.3152 | 40
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 |  | 0 | 0 | 8453.9199 | 2d | 0 | 0 | 0 | 8453.9199 | 0% | Not Started | 0 | 8453.9199 | 100 |  | 0 | 100 |  | 0
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 |  | 0 | 0 | 5471.2998 | 5d | 0 | 0 | 0 | 5471.2998 | 0% | Not Started | 0 | 5471.2998 | 100 |  | 0 | 100 |  | 0
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 4534.79 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 1142.99 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 80 | 100 | 100 | 100 | 100
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 |  | 0 | 0 | 40156.5195 | 10d | 0 | 0 | 0 | 40156.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 3d | 2555.6924 | 14482.2568 | 17d | 2985.3965 | 0 | 5541.0889 | 14482.2568 | 15% | Started | 2555.6925 | 0 | 100 | 15 | 15 | 100 | 32.522 | 15
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 5d | 7044.9048 | 21134.7144 | 15d | -3929.1665 | 0 | 3115.7383 | 21134.7144 | 25% | Started | 7044.9048 | 0 | 100 | 25 | 25 | 100 | 11.0567 | 25
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 4d | 2505.1141 | 9394.1777 | 15d | 870.3762 | 0 | 3375.4902 | 9394.1777 | 21.05% | Started | 2636.9622 | 0 | 100 | 20 | 21.0526 | 100 | 26.9488 | 21.0526
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 10d | 3097.5866 | 15487.9329 | 50d | 509.6634 | 0 | 3607.25 | 15487.9329 | 16.67% | Started | 3097.5867 | 16068.7304 | 100 | 16.6667 | 16.6667 | 100 | 19.4089 | 16.6667
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2012-12-31 16:00 |  | TP Name | 31/12, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 138d | [5 empty] | 213957.4301 |  | 48.49% |  | 213817.1235 | 267636.5859
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 55d | 34635.5732 | 3148.6885 | 5d | 2801.2285 | 0 | 37436.8017 | 3148.6885 | 91.67% | Started | 34635.574 | 37784.2617 | 100 | 91.6667 | 91.6667 | 100 | 99.0804 | 91.6667
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 12d | 15447.1922 | 0 | 0 | -2574.532 | 0 | 12872.6602 | 0 | 100% | Finished | 12872.6602 | 12872.6602 | 100 | 120 | 100 | 100 | 100 | 100
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 100% | Finished | 3148.28 | 3148.28 | 100 | 100 | 100 | 100 | 100 | 100
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 100% | Finished | 2339.1299 | 2339.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 2d | 2059.6039 | 3089.4059 | 3d | -910.5941 | 0 | 1149.0098 | 3089.4059 | 40% | Started | 2059.6039 | 5149.0098 | 100 | 40 | 40 | 100 | 22.3152 | 40
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 2012-12-03 08:00 | 2d | 8453.9199 | 12680.8799 | 3d | -7127.1001 | 0 | 1326.8198 | 12680.8799 | 40% | Started | 3381.568 | 8453.9199 | 100 | 100 | 40 | 100 | 15.6947 | 40
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 |  | 0 | 0 | 5471.2998 | 5d | 0 | 0 | 0 | 5471.2998 | 0% | Not Started | 0 | 5471.2998 | 100 |  | 0 | 100 |  | 0
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 4534.79 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 1142.99 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 80 | 100 | 100 | 100 | 100
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 |  | 0 | 0 | 40156.5195 | 10d | 0 | 0 | 0 | 40156.5195 | 0% | Not Started | 0 | 28109.5637 | 100 |  | 0 | 100 |  | 0
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 3d | 2555.6924 | 14482.2568 | 17d | 2985.3965 | 0 | 5541.0889 | 14482.2568 | 15% | Started | 2555.6925 | 0 | 100 | 15 | 15 | 100 | 32.522 | 15
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 5d | 7044.9048 | 21134.7144 | 15d | -3929.1665 | 0 | 3115.7383 | 21134.7144 | 25% | Started | 7044.9048 | 0 | 100 | 25 | 25 | 100 | 11.0567 | 25
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 4d | 2505.1141 | 9394.1777 | 15d | 870.3762 | 0 | 3375.4902 | 9394.1777 | 21.05% | Started | 2636.9622 | 0 | 100 | 20 | 21.0526 | 100 | 26.9488 | 21.0526
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 10d | 3097.5866 | 15487.9329 | 50d | 509.6634 | 0 | 3607.25 | 15487.9329 | 16.67% | Started | 3097.5867 | 18585.5195 | 100 | 16.6667 | 16.6667 | 100 | 19.4089 | 16.6667
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2013-01-31 16:00 |  | TP Name | 31/01, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 156d 7h | [5 empty] | 258129.5796 |  | 57.77% |  | 254726.2447 | 292161.4747
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 55d | 34635.5732 | 3148.6885 | 5d | 2801.2285 | 0 | 37436.8017 | 3148.6885 | 91.67% | Started | 34635.574 | 37784.2617 | 100 | 91.6667 | 91.6667 | 100 | 99.0804 | 91.6667
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 12d | 15447.1922 | 0 | 0 | -2574.532 | 0 | 12872.6602 | 0 | 100% | Finished | 12872.6602 | 12872.6602 | 100 | 120 | 100 | 100 | 100 | 100
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 100% | Finished | 3148.28 | 3148.28 | 100 | 100 | 100 | 100 | 100 | 100
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 100% | Finished | 2339.1299 | 2339.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 8d | 8238.4156 | 0 | 0 | -3089.4059 | 0 | 5149.0098 | 0 | 100% | Finished | 5149.0098 | 5149.0098 | 100 | 160 | 100 | 100 | 100 | 100
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 2012-12-03 08:00 | 5d | 21134.7998 | 0 | 0 | -12680.8799 | 0 | 8453.9199 | 0 | 100% | Finished | 8453.9199 | 8453.9199 | 100 | 250 | 100 | 100 | 100 | 100
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 | 2013-01-14 08:00 | 3d | 3282.7799 | 3282.7799 | 3d | -2785.3702 | 0 | 497.4097 | 3282.7799 | 50% | Started | 2735.6499 | 5471.2998 | 100 | 60 | 50 | 100 | 9.0913 | 50
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 4534.79 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 |  | 0 | 0 | 1142.99 | 5d | 0 | 0 | 0 | 1142.99 | 0% | Not Started | 0 | 1142.99 | 100 |  | 0 | 100 |  | 0
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 80 | 100 | 100 | 100 | 100
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 | 2013-01-21 08:00 | 8d 7h | 35638.9111 | 12046.9559 | 3d | -3091.2714 | 0 | 32547.6396 | 12046.9559 | 74.74% | Started | 30011.7136 | 40156.5195 | 100 | 88.75 | 74.7368 | 100 | 81.0519 | 74.7368
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 |  | 0 | 0 | 15720.2305 | 20d | 0 | 0 | 0 | 15720.2305 | 0% | Not Started | 0 | 12477.9329 | 100 |  | 0 | 100 |  | 0
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 3d | 2555.6924 | 14482.2568 | 17d | 2985.3965 | 0 | 5541.0889 | 14482.2568 | 15% | Started | 2555.6925 | 0 | 100 | 15 | 15 | 100 | 32.522 | 15
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 5d | 7044.9048 | 21134.7144 | 15d | -3929.1665 | 0 | 3115.7383 | 21134.7144 | 25% | Started | 7044.9048 | 0 | 100 | 25 | 25 | 100 | 11.0567 | 25
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 4d | 2505.1141 | 9394.1777 | 15d | 870.3762 | 0 | 3375.4902 | 9394.1777 | 21.05% | Started | 2636.9622 | 0 | 100 | 20 | 21.0526 | 100 | 26.9488 | 21.0526
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 10d | 3097.5866 | 15487.9329 | 50d | 509.6634 | 0 | 3607.25 | 15487.9329 | 16.67% | Started | 3097.5867 | 18585.5195 | 100 | 16.6667 | 16.6667 | 100 | 19.4089 | 16.6667
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2013-02-28 16:00 |  | TP Name | 28/02, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 176d 7h | [5 empty] | 274263.51 |  | 61.46% |  | 271017.9702 | 300612.5125
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 55d | 34635.5732 | 3148.6885 | 5d | 2801.2285 | 0 | 37436.8017 | 3148.6885 | 91.67% | Started | 34635.574 | 37784.2617 | 100 | 91.6667 | 91.6667 | 100 | 99.0804 | 91.6667
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 12d | 15447.1922 | 0 | 0 | -2574.532 | 0 | 12872.6602 | 0 | 100% | Finished | 12872.6602 | 12872.6602 | 100 | 120 | 100 | 100 | 100 | 100
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 100% | Finished | 3148.28 | 3148.28 | 100 | 100 | 100 | 100 | 100 | 100
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 100% | Finished | 2339.1299 | 2339.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 8d | 8238.4156 | 0 | 0 | -3089.4059 | 0 | 5149.0098 | 0 | 100% | Finished | 5149.0098 | 5149.0098 | 100 | 160 | 100 | 100 | 100 | 100
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 2012-12-03 08:00 | 5d | 21134.7998 | 0 | 0 | -12680.8799 | 0 | 8453.9199 | 0 | 100% | Finished | 8453.9199 | 8453.9199 | 100 | 250 | 100 | 100 | 100 | 100
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 | 2013-01-14 08:00 | 3d | 3282.7799 | 3282.7799 | 3d | -2785.3702 | 0 | 497.4097 | 3282.7799 | 50% | Started | 2735.6499 | 5471.2998 | 100 | 60 | 50 | 100 | 9.0913 | 50
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 4534.79 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 | 2013-02-04 08:00 | 2d | 457.196 | 457.196 | 2d | -43.496 | 0 | 413.7 | 457.196 | 50% | Started | 571.495 | 1142.99 | 100 | 40 | 50 | 100 | 36.1945 | 50
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 80 | 100 | 100 | 100 | 100
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 | 2013-01-21 08:00 | 8d 7h | 35638.9111 | 12046.9559 | 3d | -3091.2714 | 0 | 32547.6396 | 12046.9559 | 74.74% | Started | 30011.7136 | 40156.5195 | 100 | 88.75 | 74.7368 | 100 | 81.0519 | 74.7368
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 | 2013-02-04 08:00 | 15d | 11790.1729 | 0 | 0 | 3930.0576 | 0 | 15720.2305 | 0 | 100% | Finished | 15720.2305 | 15720.2305 | 100 | 75 | 100 | 100 | 100 | 100
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 |  | 0 | 0 | 5208.7402 | 10d | 0 | 0 | 0 | 5208.7402 | 0% | Not Started | 0 | 5208.7402 | 100 |  | 0 | 100 |  | 0
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 |  | 0 | 0 | 15135.6699 | 10d | 0 | 0 | 0 | 15135.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 3d | 2555.6924 | 14482.2568 | 17d | 2985.3965 | 0 | 5541.0889 | 14482.2568 | 15% | Started | 2555.6925 | 0 | 100 | 15 | 15 | 100 | 32.522 | 15
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 5d | 7044.9048 | 21134.7144 | 15d | -3929.1665 | 0 | 3115.7383 | 21134.7144 | 25% | Started | 7044.9048 | 0 | 100 | 25 | 25 | 100 | 11.0567 | 25
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 4d | 2505.1141 | 9394.1777 | 15d | 870.3762 | 0 | 3375.4902 | 9394.1777 | 21.05% | Started | 2636.9622 | 0 | 100 | 20 | 21.0526 | 100 | 26.9488 | 21.0526
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 10d | 3097.5866 | 15487.9329 | 50d | 509.6634 | 0 | 3607.25 | 15487.9329 | 16.67% | Started | 3097.5867 | 18585.5195 | 100 | 16.6667 | 16.6667 | 100 | 19.4089 | 16.6667
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 |  | 0 | 0 | 688.18 | 2d | 0 | 0 | 0 | 688.18 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2013-03-31 16:00 |  | TP Name | 31/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 198d | [5 empty] | 293099.8414 |  | 67.55% |  | 297848.4532 | 324006.1422
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 57d | 35895.0486 | 0 | 0 | 1889.2131 | 0 | 37784.2617 | 0 | 100% | Finished | 37784.2617 | 37784.2617 | 100 | 95 | 100 | 100 | 100 | 100
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 12d | 15447.1922 | 0 | 0 | -2574.532 | 0 | 12872.6602 | 0 | 100% | Finished | 12872.6602 | 12872.6602 | 100 | 120 | 100 | 100 | 100 | 100
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 100% | Finished | 3148.28 | 3148.28 | 100 | 100 | 100 | 100 | 100 | 100
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 100% | Finished | 2339.1299 | 2339.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 8d | 8238.4156 | 0 | 0 | -3089.4059 | 0 | 5149.0098 | 0 | 100% | Finished | 5149.0098 | 5149.0098 | 100 | 160 | 100 | 100 | 100 | 100
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 2012-12-03 08:00 | 5d | 21134.7998 | 0 | 0 | -12680.8799 | 0 | 8453.9199 | 0 | 100% | Finished | 8453.9199 | 8453.9199 | 100 | 250 | 100 | 100 | 100 | 100
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 | 2013-01-14 08:00 | 5d | 5471.2998 | 2188.5199 | 2d | -1373.6899 | 0 | 4097.6099 | 2188.5199 | 71.43% | Started | 3908.0714 | 5471.2998 | 100 | 100 | 71.4286 | 100 | 74.8928 | 71.4286
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 |  | 0 | 0 | 4534.79 | 5d | 0 | 0 | 0 | 4534.79 | 0% | Not Started | 0 | 4534.79 | 100 |  | 0 | 100 |  | 0
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 | 2013-02-04 08:00 | 2d | 457.196 | 457.196 | 2d | -43.496 | 0 | 413.7 | 457.196 | 50% | Started | 571.495 | 1142.99 | 100 | 40 | 50 | 100 | 36.1945 | 50
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 80 | 100 | 100 | 100 | 100
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 | 2013-01-21 08:00 | 8d 7h | 35638.9111 | 12046.9559 | 3d | -3091.2714 | 0 | 32547.6396 | 12046.9559 | 74.74% | Started | 30011.7136 | 40156.5195 | 100 | 88.75 | 74.7368 | 100 | 81.0519 | 74.7368
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 | 2013-02-04 08:00 | 15d | 11790.1729 | 0 | 0 | 3930.0576 | 0 | 15720.2305 | 0 | 100% | Finished | 15720.2305 | 15720.2305 | 100 | 75 | 100 | 100 | 100 | 100
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 | 2013-03-04 08:00 | 8d | 4166.9922 | 0 | 0 | 1041.748 | 0 | 5208.7402 | 0 | 100% | Finished | 5208.7402 | 5208.7402 | 100 | 80 | 100 | 100 | 100 | 100
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 | 2013-03-25 08:00 | 5d | 7567.835 | 7567.835 | 5d | -2606.165 | 0 | 4961.6699 | 7567.835 | 50% | Started | 7567.835 | 15135.6699 | 100 | 50 | 50 | 100 | 32.7813 | 50
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 |  | 0 | 0 | 5416.9302 | 5d | 0 | 0 | 0 | 5416.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 2138.6766 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 6119.2832 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 |  | 0 | 0 | 7144.3198 | 5d | 0 | 0 | 0 | 7144.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 5d | 4259.4873 | 12778.4619 | 15d | 3183.7217 | 0 | 7443.209 | 12778.4619 | 25% | Started | 4259.4873 | 0 | 100 | 25 | 25 | 100 | 43.6861 | 25
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 8d | 11271.8477 | 15498.7905 | 11d | -7475.2285 | 0 | 3796.6191 | 15498.7905 | 42.11% | Started | 11865.1029 | 0 | 100 | 40 | 42.1053 | 100 | 13.4729 | 42.1053
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 7d | 4383.9496 | 6262.7852 | 10d | 438.6207 | 0 | 4822.5703 | 6262.7852 | 41.18% | Started | 5157.5878 | 0 | 100 | 35 | 41.1765 | 100 | 38.5018 | 41.1765
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 10d | 3097.5866 | 15487.9329 | 50d | 509.6634 | 0 | 3607.25 | 15487.9329 | 16.67% | Started | 3097.5867 | 18585.5195 | 100 | 16.6667 | 16.6667 | 100 | 19.4089 | 16.6667
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 | 2013-03-19 08:00 | 2d | 688.18 | 0 | 0 | 0 | 0 | 688.18 | 0 | 100% | Finished | 688.18 | 0 | 100 | 100 | 100 | 100 | 100 | 100
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2013-04-30 16:00 |  | TP Name | 30/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 218d 7h | [5 empty] | 312105.8815 |  | 71.2% |  | 313964.3081 | 399580.0806
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 57d | 35895.0486 | 0 | 0 | 1889.2131 | 0 | 37784.2617 | 0 | 100% | Finished | 37784.2617 | 37784.2617 | 100 | 95 | 100 | 100 | 100 | 100
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 12d | 15447.1922 | 0 | 0 | -2574.532 | 0 | 12872.6602 | 0 | 100% | Finished | 12872.6602 | 12872.6602 | 100 | 120 | 100 | 100 | 100 | 100
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 100% | Finished | 3148.28 | 3148.28 | 100 | 100 | 100 | 100 | 100 | 100
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 100% | Finished | 2339.1299 | 2339.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 8d | 8238.4156 | 0 | 0 | -3089.4059 | 0 | 5149.0098 | 0 | 100% | Finished | 5149.0098 | 5149.0098 | 100 | 160 | 100 | 100 | 100 | 100
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 2012-12-03 08:00 | 5d | 21134.7998 | 0 | 0 | -12680.8799 | 0 | 8453.9199 | 0 | 100% | Finished | 8453.9199 | 8453.9199 | 100 | 250 | 100 | 100 | 100 | 100
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 | 2013-01-14 08:00 | 5d | 5471.2998 | 2188.5199 | 2d | -1373.6899 | 0 | 4097.6099 | 2188.5199 | 71.43% | Started | 3908.0714 | 5471.2998 | 100 | 100 | 71.4286 | 100 | 74.8928 | 71.4286
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 | 2013-04-08 08:00 | 3d | 2720.874 | 2720.874 | 3d | 608.916 | 0 | 3329.79 | 2720.874 | 50% | Started | 2267.395 | 4534.79 | 100 | 60 | 50 | 100 | 73.4277 | 50
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 | 2013-02-04 08:00 | 2d | 457.196 | 457.196 | 2d | -43.496 | 0 | 413.7 | 457.196 | 50% | Started | 571.495 | 1142.99 | 100 | 40 | 50 | 100 | 36.1945 | 50
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 80 | 100 | 100 | 100 | 100
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 | 2013-01-21 08:00 | 8d 7h | 35638.9111 | 12046.9559 | 3d | -3091.2714 | 0 | 32547.6396 | 12046.9559 | 74.74% | Started | 30011.7136 | 40156.5195 | 100 | 88.75 | 74.7368 | 100 | 81.0519 | 74.7368
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 2099.71 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 4970.3401 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 | 2013-02-04 08:00 | 15d | 11790.1729 | 0 | 0 | 3930.0576 | 0 | 15720.2305 | 0 | 100% | Finished | 15720.2305 | 15720.2305 | 100 | 75 | 100 | 100 | 100 | 100
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 | 2013-03-04 08:00 | 8d | 4166.9922 | 0 | 0 | 1041.748 | 0 | 5208.7402 | 0 | 100% | Finished | 5208.7402 | 5208.7402 | 100 | 80 | 100 | 100 | 100 | 100
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 | 2013-03-25 08:00 | 10d | 15135.6699 | 0 | 0 | 0 | 0 | 15135.6699 | 0 | 100% | Finished | 15135.6699 | 15135.6699 | 100 | 100 | 100 | 100 | 100 | 100
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 | 2013-04-22 08:00 | 4d | 4333.5441 | 4333.5441 | 4d | -2420.614 | 0 | 1912.9302 | 4333.5441 | 50% | Started | 2708.4651 | 5416.9302 | 100 | 80 | 50 | 100 | 35.3139 | 50
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 6416.0298 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 |  | 0 | 0 | 18357.8496 | 15d | 0 | 0 | 0 | 18357.8496 | 0% | Not Started | 0 | 18357.8496 | 100 |  | 0 | 100 |  | 0
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 | 2013-04-26 08:00 | 3d | 4286.5919 | 4286.5919 | 3d | -697.2721 | 0 | 3589.3198 | 4286.5919 | 50% | Started | 3572.1599 | 7144.3198 | 100 | 60 | 50 | 100 | 50.2402 | 50
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 5d | 4259.4873 | 12778.4619 | 15d | 3183.7217 | 0 | 7443.209 | 12778.4619 | 25% | Started | 4259.4873 | 10116.2823 | 100 | 25 | 25 | 100 | 43.6861 | 25
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 8d | 11271.8477 | 15498.7905 | 11d | -7475.2285 | 0 | 3796.6191 | 15498.7905 | 42.11% | Started | 11865.1029 | 16731.6489 | 100 | 40 | 42.1053 | 100 | 13.4729 | 42.1053
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 7d | 4383.9496 | 6262.7852 | 10d | 438.6207 | 0 | 4822.5703 | 6262.7852 | 41.18% | Started | 5157.5878 | 7280.4877 | 100 | 35 | 41.1765 | 100 | 38.5018 | 41.1765
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 10d | 3097.5866 | 15487.9329 | 50d | 509.6634 | 0 | 3607.25 | 15487.9329 | 16.67% | Started | 3097.5867 | 18585.5195 | 100 | 16.6667 | 16.6667 | 100 | 19.4089 | 16.6667
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 |  | 0 | 0 | 5298.2998 | 5d | 0 | 0 | 0 | 5298.2998 | 0% | Not Started | 0 | 5298.2998 | 100 |  | 0 | 100 |  | 0
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 | 2013-03-19 08:00 | 2d | 688.18 | 0 | 0 | 0 | 0 | 688.18 | 0 | 100% | Finished | 688.18 | 0 | 100 | 100 | 100 | 100 | 100 | 100
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2013-05-31 16:00 |  | TP Name | 31/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 240d | [5 empty] | 394349.9005 |  | 88.62% |  | 390783.0173 | 434093.7142
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 57d | 35895.0486 | 0 | 0 | 1889.2131 | 0 | 37784.2617 | 0 | 100% | Finished | 37784.2617 | 37784.2617 | 100 | 95 | 100 | 100 | 100 | 100
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 12d | 15447.1922 | 0 | 0 | -2574.532 | 0 | 12872.6602 | 0 | 100% | Finished | 12872.6602 | 12872.6602 | 100 | 120 | 100 | 100 | 100 | 100
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 100% | Finished | 3148.28 | 3148.28 | 100 | 100 | 100 | 100 | 100 | 100
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 100% | Finished | 2339.1299 | 2339.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 8d | 8238.4156 | 0 | 0 | -3089.4059 | 0 | 5149.0098 | 0 | 100% | Finished | 5149.0098 | 5149.0098 | 100 | 160 | 100 | 100 | 100 | 100
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 2012-12-03 08:00 | 5d | 21134.7998 | 0 | 0 | -12680.8799 | 0 | 8453.9199 | 0 | 100% | Finished | 8453.9199 | 8453.9199 | 100 | 250 | 100 | 100 | 100 | 100
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 | 2013-01-14 08:00 | 8d | 8754.0797 | 0 | 0 | -3282.7799 | 0 | 5471.2998 | 0 | 100% | Finished | 5471.2998 | 5471.2998 | 100 | 160 | 100 | 100 | 100 | 100
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 | 2013-04-08 08:00 | 5d | 4534.79 | 0 | 0 | 0 | 0 | 4534.79 | 0 | 100% | Finished | 4534.79 | 4534.79 | 100 | 100 | 100 | 100 | 100 | 100
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 | 2013-02-04 08:00 | 4d | 914.392 | 0 | 0 | 228.598 | 0 | 1142.99 | 0 | 100% | Finished | 1142.99 | 1142.99 | 100 | 80 | 100 | 100 | 100 | 100
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 80 | 100 | 100 | 100 | 100
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 | 2013-01-21 08:00 | 12d | 48187.8234 | 0 | 0 | -8031.3039 | 0 | 40156.5195 | 0 | 100% | Finished | 40156.5195 | 40156.5195 | 100 | 120 | 100 | 100 | 100 | 100
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 |  | 0 | 0 | 2099.71 | 2d | 0 | 0 | 0 | 2099.71 | 0% | Not Started | 0 | 2099.71 | 100 |  | 0 | 100 |  | 0
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 |  | 0 | 0 | 13254.2402 | 5d | 0 | 0 | 0 | 13254.2402 | 0% | Not Started | 0 | 13254.2402 | 100 |  | 0 | 100 |  | 0
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 | 2013-02-04 08:00 | 15d | 11790.1729 | 0 | 0 | 3930.0576 | 0 | 15720.2305 | 0 | 100% | Finished | 15720.2305 | 15720.2305 | 100 | 75 | 100 | 100 | 100 | 100
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 | 2013-03-04 08:00 | 8d | 4166.9922 | 0 | 0 | 1041.748 | 0 | 5208.7402 | 0 | 100% | Finished | 5208.7402 | 5208.7402 | 100 | 80 | 100 | 100 | 100 | 100
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 | 2013-03-25 08:00 | 10d | 15135.6699 | 0 | 0 | 0 | 0 | 15135.6699 | 0 | 100% | Finished | 15135.6699 | 15135.6699 | 100 | 100 | 100 | 100 | 100 | 100
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 | 2013-04-22 08:00 | 10d | 10833.8604 | 0 | 0 | -5416.9302 | 0 | 5416.9302 | 0 | 100% | Finished | 5416.9302 | 5416.9302 | 100 | 200 | 100 | 100 | 100 | 100
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 |  | 0 | 0 | 6416.0298 | 15d | 0 | 0 | 0 | 6416.0298 | 0% | Not Started | 0 | 6416.0298 | 100 |  | 0 | 100 |  | 0
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 | 2013-05-13 08:00 | 15d | 18357.8496 | 0 | 0 | 0 | 0 | 18357.8496 | 0 | 100% | Finished | 18357.8496 | 18357.8496 | 100 | 100 | 100 | 100 | 100 | 100
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 | 2013-04-26 08:00 | 8d | 11430.9117 | 0 | 0 | -4286.5919 | 0 | 7144.3198 | 0 | 100% | Finished | 7144.3198 | 7144.3198 | 100 | 160 | 100 | 100 | 100 | 100
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 6d | 5111.3848 | 12778.4619 | 15d | 2831.5645 | 0 | 7942.9492 | 12778.4619 | 28.57% | Started | 4867.9857 | 17037.9492 | 100 | 30 | 28.5714 | 100 | 46.6192 | 28.5714
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 15d | 21134.7144 | 2817.9619 | 2d | 4901.9048 | 0 | 26036.6191 | 2817.9619 | 88.24% | Started | 24864.37 | 28179.6191 | 100 | 75 | 88.2353 | 100 | 92.3952 | 88.2353
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 15d | 9394.1777 | 1252.557 | 2d | 826.3926 | 0 | 10220.5703 | 1252.557 | 88.24% | Started | 11051.9739 | 12525.5703 | 100 | 75 | 88.2353 | 100 | 81.5976 | 88.2353
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 30d | 9292.7598 | 1548.7933 | 5d | 6788.7598 | 0 | 16081.5195 | 1548.7933 | 85.71% | Started | 15930.4455 | 18585.5195 | 100 | 50 | 85.7143 | 100 | 86.5271 | 85.7143
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 | 2013-05-21 08:00 | 5d | 5298.2998 | 0 | 0 | 0 | 0 | 5298.2998 | 0 | 100% | Finished | 5298.2998 | 5298.2998 | 100 | 100 | 100 | 100 | 100 | 100
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 | 2013-03-19 08:00 | 2d | 688.18 | 0 | 0 | 0 | 0 | 688.18 | 0 | 100% | Finished | 688.18 | 688.18 | 100 | 100 | 100 | 100 | 100 | 100
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 |  | 0 | 0 | 2495.03 | 3d | 0 | 0 | 0 | 2495.03 | 0% | Not Started | 0 | 1559.3938 | 100 |  | 0 | 100 |  | 0
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 |  | 0 | 0 | 367.44 | 1d | 0 | 0 | 0 | 367.44 | 0% | Not Started | 0 | 367.44 | 100 |  | 0 | 100 |  | 0
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 |  | 0 | 0 | 5911.54 | 5d | 0 | 0 | 0 | 5911.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2013-06-21 16:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (1) | 2012-05-14 08:00 | 2013-06-07 17:00 | 244d |  |  | 0 |  |  | 440940.8905 |  | 254d | [5 empty] | 440940.8905 |  | 100% |  | 440940.8905 | 440940.8905
1 | grondwerken | 2012-05-14 08:00 | 2012-05-25 17:00 | 8d |  | 0 | 0 | 123.1494 | 7881.5601 | 7881.5601 | 2012-05-14 08:00 | 8d | 7881.5601 | 0 | 0 | 0 | 0 | 7881.5601 | 0 | 100% | Finished | 7881.5601 | 7881.5601 | 100 | 100 | 100 | 100 | 100 | 100
2 | fundering | 2012-05-21 08:00 | 2012-05-25 17:00 | 5d |  | 0 | 0 | 545.3145 | 21812.5801 | 21812.5801 | 2012-05-24 08:00 | 8d | 34900.1281 | 0 | 0 | -13087.548 | 0 | 21812.5801 | 0 | 100% | Finished | 21812.5801 | 21812.5801 | 100 | 160 | 100 | 100 | 100 | 100
3 | rioleringswerken | 2012-05-21 08:00 | 2012-05-30 17:00 | 7d |  | 0 | 0 | 188.0611 | 10531.4199 | 10531.4199 | 2012-05-21 08:00 | 7d | 10531.4199 | 0 | 0 | 0 | 0 | 10531.4199 | 0 | 100% | Finished | 10531.4199 | 10531.4199 | 100 | 100 | 100 | 100 | 100 | 100
4 | regenputten | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 126.815 | 2029.04 | 2029.04 | 2012-06-04 08:00 | 2d | 2029.04 | 0 | 0 | 0 | 0 | 2029.04 | 0 | 100% | Finished | 2029.04 | 2029.04 | 100 | 100 | 100 | 100 | 100 | 100
5 | wanden gelijkvloers | 2012-06-04 08:00 | 2012-06-08 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-04 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
6 | predallen + vloerplaat | 2012-06-11 08:00 | 2012-06-15 17:00 | 5d |  | 0 | 0 | 216.5952 | 8663.8096 | 8663.8096 | 2012-06-11 08:00 | 5d | 8663.8096 | 0 | 0 | 0 | 0 | 8663.8096 | 0 | 100% | Finished | 8663.8096 | 8663.8096 | 100 | 100 | 100 | 100 | 100 | 100
7 | wanden 1e verdiep | 2012-06-18 08:00 | 2012-06-22 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-06-18 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
8 | predallen + vloerplaat | 2012-06-25 08:00 | 2012-06-29 17:00 | 5d |  | 0 | 0 | 447.6675 | 17906.6992 | 17906.6992 | 2012-08-06 08:00 | 5d | 17906.6992 | 0 | 0 | 0 | 0 | 17906.6992 | 0 | 100% | Finished | 17906.6992 | 17906.6992 | 100 | 100 | 100 | 100 | 100 | 100
9 | wanden 2e verdiep | 2012-07-02 08:00 | 2012-07-06 17:00 | 5d |  | 0 | 0 | 545.7845 | 21831.3809 | 21831.3809 | 2012-08-13 08:00 | 5d | 21831.3809 | 0 | 0 | 0 | 0 | 21831.3809 | 0 | 100% | Finished | 21831.3809 | 21831.3809 | 100 | 100 | 100 | 100 | 100 | 100
11 | gevel | 2012-06-25 08:00 | 2012-10-08 17:00 | 60d |  | 0 | 0 | 78.7172 | 37784.2617 | 37784.2617 | 2012-07-02 08:00 | 57d | 35895.0486 | 0 | 0 | 1889.2131 | 0 | 37784.2617 | 0 | 100% | Finished | 37784.2617 | 37784.2617 | 100 | 95 | 100 | 100 | 100 | 100
12 | plaatsen blauwe hardsteen | 2012-09-03 13:00 | 2012-09-10 12:00 | 5d |  | 0 | 0 | 51.4883 | 2059.53 | 2059.53 | 2012-10-08 08:00 | 5d | 2059.53 | 0 | 0 | 0 | 0 | 2059.53 | 0 | 100% | Finished | 2059.53 | 2059.53 | 100 | 100 | 100 | 100 | 100 | 100
13 | schoorsteen | 2012-08-06 08:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 160.9083 | 12872.6602 | 12872.6602 | 2012-09-10 08:00 | 12d | 15447.1922 | 0 | 0 | -2574.532 | 0 | 12872.6602 | 0 | 100% | Finished | 12872.6602 | 12872.6602 | 100 | 120 | 100 | 100 | 100 | 100
14 | plaatsen betonnen trappen | 2012-09-06 10:00 | 2012-09-10 10:00 | 2d |  | 0 | 0 | 228.5237 | 3656.3799 | 3656.3799 | 2012-09-06 08:00 | 2d | 3656.3799 | 0 | 0 | 0 | 0 | 3656.3799 | 0 | 100% | Finished | 3656.3799 | 3656.3799 | 100 | 100 | 100 | 100 | 100 | 100
15 | houten dakstructuur | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d |  | 0 | 0 | 78.707 | 3148.28 | 3148.28 | 2012-11-05 08:00 | 5d | 3148.28 | 0 | 0 | 0 | 0 | 3148.28 | 0 | 100% | Finished | 3148.28 | 3148.28 | 100 | 100 | 100 | 100 | 100 | 100
16 | hellingsbeton | 2012-09-28 10:00 | 2012-10-05 10:00 | 5d |  | 0 | 0 | 58.4782 | 2339.1299 | 2339.1299 | 2012-11-13 08:00 | 5d | 2339.1299 | 0 | 0 | 0 | 0 | 2339.1299 | 0 | 100% | Finished | 2339.1299 | 2339.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | dakisolatie | 2012-10-05 10:00 | 2012-10-12 10:00 | 5d |  | 0 | 0 | 128.7252 | 5149.0098 | 5149.0098 | 2012-11-28 08:00 | 8d | 8238.4156 | 0 | 0 | -3089.4059 | 0 | 5149.0098 | 0 | 100% | Finished | 5149.0098 | 5149.0098 | 100 | 160 | 100 | 100 | 100 | 100
18 | membranen + koepels plaatsen | 2012-10-12 10:00 | 2012-10-16 10:00 | 2d |  | 0 | 0 | 528.37 | 8453.9199 | 8453.9199 | 2012-12-03 08:00 | 5d | 21134.7998 | 0 | 0 | -12680.8799 | 0 | 8453.9199 | 0 | 100% | Finished | 8453.9199 | 8453.9199 | 100 | 250 | 100 | 100 | 100 | 100
19 | dakrandprofielen | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 136.7825 | 5471.2998 | 5471.2998 | 2013-01-14 08:00 | 8d | 8754.0797 | 0 | 0 | -3282.7799 | 0 | 5471.2998 | 0 | 100% | Finished | 5471.2998 | 5471.2998 | 100 | 160 | 100 | 100 | 100 | 100
20 | kroonlijsten | 2012-10-16 10:00 | 2012-10-23 10:00 | 5d |  | 0 | 0 | 113.3698 | 4534.79 | 4534.79 | 2013-04-08 08:00 | 5d | 4534.79 | 0 | 0 | 0 | 0 | 4534.79 | 0 | 100% | Finished | 4534.79 | 4534.79 | 100 | 100 | 100 | 100 | 100 | 100
21 | afwerking dakverdichting | 2012-10-29 15:00 | 2012-11-07 15:00 | 5d |  | 0 | 0 | 28.5747 | 1142.99 | 1142.99 | 2013-02-04 08:00 | 4d | 914.392 | 0 | 0 | 228.598 | 0 | 1142.99 | 0 | 100% | Finished | 1142.99 | 1142.99 | 100 | 80 | 100 | 100 | 100 | 100
41 | opmeten buitenschrijnwerk | 2012-10-15 08:00 | 2012-10-16 10:00 | 1d 2h |  | 0 | 0 | 1 | 10 | 10 | 2012-11-13 08:00 | 1d | 8 | 0 | 0 | 2 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 80 | 100 | 100 | 100 | 100
22 | plaatsen buitendeuren en ramen | 2012-12-13 08:00 | 2013-01-09 17:00 | 10d |  | 0 | 0 | 501.9565 | 40156.5195 | 40156.5195 | 2013-01-21 08:00 | 12d | 48187.8234 | 0 | 0 | -8031.3039 | 0 | 40156.5195 | 0 | 100% | Finished | 40156.5195 | 40156.5195 | 100 | 120 | 100 | 100 | 100 | 100
23 | buitentrapleuningen | 2013-04-22 13:00 | 2013-04-24 12:00 | 2d |  | 0 | 0 | 131.2319 | 2099.71 | 2099.71 | 2013-06-10 08:00 | 2d | 2099.71 | 0 | 0 | 0 | 0 | 2099.71 | 0 | 100% | Finished | 2099.71 | 2099.71 | 100 | 100 | 100 | 100 | 100 | 100
24 | andere afwerkingen | 2013-04-29 08:00 | 2013-05-06 17:00 | 5d |  | 0 | 0 | 331.356 | 13254.2402 | 13254.2402 | 2013-06-10 08:00 | 5d | 13254.2402 | 0 | 0 | 0 | 0 | 13254.2402 | 0 | 100% | Finished | 13254.2402 | 13254.2402 | 100 | 100 | 100 | 100 | 100 | 100
25 | pleisterwerken | 2013-01-10 08:00 | 2013-02-06 17:00 | 20d |  | 0 | 0 | 98.2514 | 15720.2305 | 15720.2305 | 2013-02-04 08:00 | 15d | 11790.1729 | 0 | 0 | 3930.0576 | 0 | 15720.2305 | 0 | 100% | Finished | 15720.2305 | 15720.2305 | 100 | 75 | 100 | 100 | 100 | 100
42 | PUR + chape | 2013-02-07 08:00 | 2013-02-20 17:00 | 10d |  | 0 | 0 | 65.1093 | 5208.7402 | 5208.7402 | 2013-03-04 08:00 | 8d | 4166.9922 | 0 | 0 | 1041.748 | 0 | 5208.7402 | 0 | 100% | Finished | 5208.7402 | 5208.7402 | 100 | 80 | 100 | 100 | 100 | 100
26 | binnenvloeren | 2013-03-07 08:00 | 2013-03-20 17:00 | 10d |  | 0 | 0 | 189.1959 | 15135.6699 | 15135.6699 | 2013-03-25 08:00 | 10d | 15135.6699 | 0 | 0 | 0 | 0 | 15135.6699 | 0 | 100% | Finished | 15135.6699 | 15135.6699 | 100 | 100 | 100 | 100 | 100 | 100
27 | plaatsen plinten | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 135.4233 | 5416.9302 | 5416.9302 | 2013-04-22 08:00 | 10d | 10833.8604 | 0 | 0 | -5416.9302 | 0 | 5416.9302 | 0 | 100% | Finished | 5416.9302 | 5416.9302 | 100 | 200 | 100 | 100 | 100 | 100
28 | plaatsen binnendeuren | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 53.4669 | 6416.0298 | 6416.0298 | 2013-06-10 08:00 | 10d | 4277.3532 | 0 | 0 | 2138.6766 | 0 | 6416.0298 | 0 | 100% | Finished | 6416.0298 | 6416.0298 | 100 | 66.6667 | 100 | 100 | 100 | 100
29 | keukens | 2013-03-25 08:00 | 2013-04-15 17:00 | 15d |  | 0 | 0 | 152.9821 | 18357.8496 | 18357.8496 | 2013-05-13 08:00 | 15d | 18357.8496 | 0 | 0 | 0 | 0 | 18357.8496 | 0 | 100% | Finished | 18357.8496 | 18357.8496 | 100 | 100 | 100 | 100 | 100 | 100
30 | venstertabletten + faience | 2013-04-08 15:00 | 2013-04-15 15:00 | 5d |  | 0 | 0 | 178.608 | 7144.3198 | 7144.3198 | 2013-04-26 08:00 | 8d | 11430.9117 | 0 | 0 | -4286.5919 | 0 | 7144.3198 | 0 | 100% | Finished | 7144.3198 | 7144.3198 | 100 | 160 | 100 | 100 | 100 | 100
31 | sanitair | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 106.4872 | 17037.9492 | 17037.9492 | 2012-11-19 08:00 | 25d | 21297.4365 | 0 | 0 | -4259.4873 | 0 | 17037.9492 | 0 | 100% | Finished | 17037.9492 | 17037.9492 | 100 | 125 | 100 | 100 | 100 | 100
33 | CLV | 2013-04-15 08:00 | 2013-05-14 17:00 | 20d |  | 0 | 0 | 176.1226 | 28179.6191 | 28179.6191 | 2012-11-19 08:00 | 18d | 25361.6572 | 0 | 0 | 2817.9619 | 0 | 28179.6191 | 0 | 100% | Finished | 28179.6191 | 28179.6191 | 100 | 90 | 100 | 100 | 100 | 100
34 | ventilatie | 2013-04-15 10:00 | 2013-05-15 10:00 | 20d |  | 0 | 0 | 78.2848 | 12525.5703 | 12525.5703 | 2012-11-19 08:00 | 18d | 11273.0133 | 0 | 0 | 1252.557 | 0 | 12525.5703 | 0 | 100% | Finished | 12525.5703 | 12525.5703 | 100 | 90 | 100 | 100 | 100 | 100
35 | electriciteitsnet + toebehoren | 2012-09-17 08:00 | 2012-12-12 17:00 | 60d |  | 0 | 0 | 38.7198 | 18585.5195 | 18585.5195 | 2012-11-19 08:00 | 37d | 11461.0704 | 0 | 0 | 7124.4492 | 0 | 18585.5195 | 0 | 100% | Finished | 18585.5195 | 18585.5195 | 100 | 61.6667 | 100 | 100 | 100 | 100
36 | tegels buiten | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 132.4575 | 5298.2998 | 5298.2998 | 2013-05-21 08:00 | 5d | 5298.2998 | 0 | 0 | 0 | 0 | 5298.2998 | 0 | 100% | Finished | 5298.2998 | 5298.2998 | 100 | 100 | 100 | 100 | 100 | 100
37 | plaatsen brievenbussen | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 43.0112 | 688.18 | 688.18 | 2013-03-19 08:00 | 2d | 688.18 | 0 | 0 | 0 | 0 | 688.18 | 0 | 100% | Finished | 688.18 | 688.18 | 100 | 100 | 100 | 100 | 100 | 100
38 | plaatsen afsluiting | 2013-05-30 08:00 | 2013-06-03 17:00 | 3d |  | 0 | 0 | 103.9596 | 2495.03 | 2495.03 | 2013-06-10 08:00 | 3d | 2495.03 | 0 | 0 | 0 | 0 | 2495.03 | 0 | 100% | Finished | 2495.03 | 2495.03 | 100 | 100 | 100 | 100 | 100 | 100
39 | fietsrekken | 2013-05-29 08:00 | 2013-05-29 17:00 | 1d |  | 0 | 0 | 45.93 | 367.44 | 367.44 | 2013-06-10 08:00 | 1d | 367.44 | 0 | 0 | 0 | 0 | 367.44 | 0 | 100% | Finished | 367.44 | 367.44 | 100 | 100 | 100 | 100 | 100 | 100
40 | afwerking omgevingswerken | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 147.7885 | 5911.54 | 5911.54 | 2013-06-10 08:00 | 5d | 5911.54 | 0 | 0 | 0 | 0 | 5911.54 | 0 | 100% | Finished | 5911.54 | 5911.54 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2012-05-17
1:00 - 2:00 | No | Tuesday | Yes | 2012-05-28
2:00 - 3:00 | No | Wednesday | Yes | 2012-08-15
3:00 - 4:00 | No | Thursday | Yes | 2012-11-01
4:00 - 5:00 | No | Friday | Yes | 2012-11-02
5:00 - 6:00 | No | Saturday | No | 2012-11-12
6:00 - 7:00 | No | Sunday | No | 2012-12-24
7:00 - 8:00 | No |  |  | 2012-12-25
8:00 - 9:00 | Yes |  |  | 2012-12-26
9:00 - 10:00 | Yes |  |  | 2012-12-27
10:00 - 11:00 | Yes |  |  | 2012-12-28
11:00 - 12:00 | Yes |  |  | 2012-12-31
12:00 - 13:00 | No |  |  | 2013-01-01
13:00 - 14:00 | Yes |  |  | 2013-01-02
14:00 - 15:00 | Yes |  |  | 2013-01-03
15:00 - 16:00 | Yes |  |  | 2013-01-04
16:00 - 17:00 | Yes |  |  | 2012-07-23
17:00 - 18:00 | No |  |  | 2012-05-18
18:00 - 19:00 | No |  |  | 2012-07-16
19:00 - 20:00 | No |  |  | 2012-07-17
20:00 - 21:00 | No |  |  | 2012-07-18
21:00 - 22:00 | No |  |  | 2012-07-19
22:00 - 23:00 | No |  |  | 2012-07-20
23:00 - 0:00 | No |  |  | 2012-07-24
2012-07-25
2012-07-26
Generated by PMConverter v1.1.3 |  |  |  | 2012-07-27
2012-07-30
2012-07-31
2012-08-01
2012-08-02
2012-08-03
2013-07-15
2013-07-16
2013-07-17
2013-07-18
2013-07-19
2013-07-22
2013-07-23
2013-07-24
2013-07-25
2013-07-26
2013-07-29
2013-07-30
2013-07-31
2013-08-01
2013-08-02
2013-04-01
2013-05-01
2013-05-09
2013-05-20
2013-08-15
2013-11-01
2013-11-11
2014-04-01
2014-04-02
2014-04-03
2014-04-04

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
31/05, 2012 | 2012-05-14 08:00 | 2012-05-31 17:00 | 42254.6001 | 32045.8425 | 35599.6499 | 2012-05-24 16:00 | -10208.7576 | 75.84% | -3553.8074 | 90.02% | -4d 1h | 62.5% | 83.19% | 2013-06-17 14:00 | 2013-10-17 15:00 | 2013-12-10 11:00 | 2013-06-12 14:00 | 2013-10-17 15:00 | 2013-12-09 10:00 | 2013-06-14 09:00 | 2014-01-24 11:00 | 2014-03-25 12:00 | 444494.6979 | 489840.1818 | 574755.2898 | 689831.7267 | 634546.3621 | 762384.5009 | 504613.7959 | 519419.8859 | 0.625 | 0.90017 | 0.7584 | 0.83191 | -4.125 | 0.90017 | 1 | 0.625 | 1
30/06, 2012 | 2012-05-31 17:00 | 2012-06-30 16:00 | 115636.5591 | 94581.1714 | 94581.1714 | 2012-06-22 17:00 | -21055.3877 | 81.79% | 0 | 100% | -5d | 84.38% | 100% | 2013-06-25 14:00 | 2013-09-16 11:00 | 2013-09-16 11:00 | 2013-06-17 16:00 | 2013-09-16 11:00 | 2013-09-16 11:00 | 2013-06-14 17:00 | 2013-09-03 09:00 | 2013-09-03 09:00 | 440940.8905 | 440940.8905 | 518046.4926 | 505081.5792 | 518046.4926 | 505081.5792 | 454030.7835 | 452113.7847 | 0.84375 | 1 | 0.81792 | 1 | -5 | 1 | 1 | 0.84375 | 1
31/07, 2012 | 2012-06-30 16:00 | 2012-07-31 16:00 | 143765.3169 | 100878.5485 | 107567.064 | 2012-06-26 11:00 | -42886.7684 | 70.17% | -6688.5154 | 93.78% | -13d 5h | 67.56% | 95.09% | 2013-07-11 15:00 | 2013-11-26 15:00 | 2013-12-27 15:00 | 2013-06-26 12:00 | 2013-11-26 15:00 | 2013-12-24 17:00 | 2013-06-27 14:00 | 2013-12-16 09:00 | 2014-01-14 11:00 | 447629.4059 | 470176.4415 | 592201.023 | 610919.253 | 624333.5404 | 644292.8387 | 489404.8054 | 491655.513 | 0.6756 | 0.93782 | 0.70169 | 0.95094 | -13.625 | 0.93782 | 1 | 0.6756 | 1
31/08, 2012 | 2012-07-31 16:00 | 2012-08-31 16:00 | 168524.276 | 146914.0057 | 151867.7534 | 2012-08-07 14:00 | -21610.2703 | 87.18% | -4953.7477 | 96.74% | -17d 2h | 71.66% | 98.58% | 2013-06-25 17:00 | 2013-08-20 16:00 | 2013-09-03 11:00 | 2013-06-19 15:00 | 2013-08-20 16:00 | 2013-08-30 10:00 | 2013-07-03 10:00 | 2013-11-15 12:00 | 2013-11-28 16:00 | 445894.6382 | 455808.8393 | 489144.432 | 562157.4178 | 500516.9594 | 575991.8474 | 461938.1576 | 472426.8572 | 0.71663 | 0.96738 | 0.87177 | 0.98576 | -17.25 | 0.96738 | 1 | 0.71663 | 1
30/09, 2012 | 2012-08-31 16:00 | 2012-09-30 16:00 | 193510.3932 | 167026.9381 | 168541.9536 | 2012-08-29 11:00 | -26483.4551 | 86.31% | -1515.0155 | 99.1% | -22d 5h | 72.07% | 94.6% | 2013-06-28 14:00 | 2013-08-23 15:00 | 2013-08-28 10:00 | 2013-06-25 09:00 | 2013-08-23 15:00 | 2013-08-27 12:00 | 2013-07-10 14:00 | 2013-11-13 14:00 | 2013-11-15 16:00 | 442455.906 | 444940.4387 | 485887.1509 | 548619.5578 | 488765.6261 | 552067.0464 | 452262.0592 | 460890.0182 | 0.72068 | 0.99101 | 0.86314 | 0.94603 | -22.625 | 0.99101 | 1 | 0.72068 | 1
31/10, 2012 | 2012-09-30 16:00 | 2012-10-31 16:00 | 230467.5994 | 181107.0654 | 181695.7033 | 2012-09-17 12:00 | -49360.5339 | 78.58% | -588.6379 | 99.68% | -32d 3h | 68.83% | 96.36% | 2013-08-07 11:00 | 2013-10-02 12:00 | 2013-10-03 12:00 | 2013-07-10 10:00 | 2013-10-02 12:00 | 2013-10-03 09:00 | 2013-08-14 11:00 | 2013-12-05 12:00 | 2013-12-06 10:00 | 441529.5284 | 442374.0456 | 512346.9551 | 559181.5576 | 513421.6446 | 560408.4698 | 453894.6759 | 459570.9362 | 0.68833 | 0.99676 | 0.78582 | 0.9636 | -32.375 | 0.99676 | 1 | 0.68833 | 1
30/11, 2012 | 2012-10-31 16:00 | 2012-11-30 16:00 | 237010.2331 | 209148.2892 | 211395.0503 | 2012-10-12 14:00 | -27861.9439 | 88.24% | -2246.7611 | 98.94% | -32d 2h | 73.75% | 94.21% | 2013-07-01 11:00 | 2013-08-14 12:00 | 2013-08-20 12:00 | 2013-06-28 12:00 | 2013-08-14 12:00 | 2013-08-19 09:00 | 2013-08-14 10:00 | 2013-10-30 16:00 | 2013-11-05 09:00 | 443187.6516 | 445677.6676 | 474066.1851 | 525673.8462 | 476887.9116 | 529049.9645 | 450853.6257 | 458244.2103 | 0.73754 | 0.98937 | 0.88244 | 0.94214 | -32.25 | 0.98937 | 1 | 0.73754 | 1
31/12, 2012 | 2012-11-30 16:00 | 2012-12-31 16:00 | 267636.5859 | 213817.1235 | 213957.4301 | 2012-10-15 14:00 | -53819.4624 | 79.89% | -140.3066 | 99.93% | -46d 3h | 66.39% | 94.4% | 2013-08-09 15:00 | 2013-09-25 11:00 | 2013-09-25 14:00 | 2013-08-07 15:00 | 2013-09-25 11:00 | 2013-09-25 12:00 | 2013-09-04 11:00 | 2013-12-24 12:00 | 2013-12-24 14:00 | 441081.1971 | 441230.2355 | 498250.0469 | 556037.4284 | 498436.5995 | 556261.901 | 450727.9206 | 457583.1251 | 0.66395 | 0.99934 | 0.79891 | 0.94399 | -46.375 | 0.99934 | 1 | 0.66395 | 1
31/01, 2013 | 2012-12-31 16:00 | 2013-01-31 16:00 | 292161.4747 | 254726.2447 | 258129.5796 | 2012-12-18 15:00 | -37435.2299 | 87.19% | -3403.3348 | 98.68% | -22d 1h | 85.9% | 89.37% | 2013-07-08 15:00 | 2013-08-20 16:00 | 2013-08-26 14:00 | 2013-07-08 09:00 | 2013-08-20 16:00 | 2013-08-22 12:00 | 2013-07-10 09:00 | 2013-08-27 09:00 | 2013-08-28 15:00 | 444344.2253 | 446832.1935 | 471710.8129 | 474919.3573 | 474564.4193 | 477815.8323 | 451333.1873 | 451851.905 | 0.85896 | 0.98682 | 0.87187 | 0.89375 | -22.125 | 0.98682 | 1 | 0.85896 | 1
28/02, 2013 | 2013-01-31 16:00 | 2013-02-28 16:00 | 300612.5125 | 271017.9702 | 274263.51 | 2013-01-07 15:00 | -29594.5423 | 90.16% | -3245.5398 | 98.82% | -38d 1h | 78.45% | 89.81% | 2013-07-02 11:00 | 2013-08-06 14:00 | 2013-08-09 16:00 | 2013-07-03 11:00 | 2013-08-06 14:00 | 2013-08-07 15:00 | 2013-08-23 09:00 | 2013-10-02 17:00 | 2013-10-04 14:00 | 444186.4303 | 446221.3198 | 462741.6245 | 490876.9625 | 464998.7192 | 493470.9882 | 449289.5633 | 453616.1586 | 0.78445 | 0.98817 | 0.90155 | 0.89807 | -38.125 | 0.98817 | 1 | 0.78445 | 1
31/03, 2013 | 2013-02-28 16:00 | 2013-03-31 16:00 | 324006.1422 | 297848.4532 | 293099.8414 | 2013-02-13 14:00 | -26157.689 | 91.93% | 4748.6117 | 101.6% | -32d 3h | 83.65% | 89.15% | 2013-06-28 12:00 | 2013-07-09 11:00 | 2013-07-03 10:00 | 2013-07-01 17:00 | 2013-07-09 11:00 | 2013-07-08 11:00 | 2013-08-14 11:00 | 2013-09-05 15:00 | 2013-09-04 10:00 | 436192.2788 | 433910.9494 | 448758.9631 | 464162.8005 | 446277.2824 | 461435.5358 | 436649.5332 | 439073.9454 | 0.83649 | 1.0162 | 0.91927 | 0.89154 | -32.375 | 1.0162 | 1 | 0.83649 | 1
30/04, 2013 | 2013-03-31 16:00 | 2013-04-30 16:00 | 399580.0806 | 313964.3081 | 312105.8815 | 2013-03-19 15:00 | -85615.7724 | 78.57% | 1858.4267 | 100.6% | -29d 1h | 86.69% | 90.43% | 2013-09-05 11:00 | 2013-10-02 12:00 | 2013-09-30 15:00 | 2013-09-04 16:00 | 2013-10-02 12:00 | 2013-10-01 17:00 | 2013-08-09 09:00 | 2013-08-22 12:00 | 2013-08-22 09:00 | 439082.4638 | 438330.8603 | 473708.0499 | 458572.2818 | 472751.4897 | 457705.3136 | 444110.4235 | 441918.8491 | 0.86693 | 1.006 | 0.78574 | 0.9043 | -29.125 | 1.006 | 1 | 0.86693 | 1
31/05, 2013 | 2013-04-30 16:00 | 2013-05-31 16:00 | 434093.7142 | 390783.0173 | 394349.9005 | 2013-04-29 10:00 | -43310.6969 | 90.02% | -3566.8831 | 99.1% | -21d 5h | 90.95% | 95.98% | 2013-07-11 17:00 | 2013-08-06 17:00 | 2013-08-09 12:00 | 2013-07-11 16:00 | 2013-08-06 17:00 | 2013-08-07 11:00 | 2013-07-09 14:00 | 2013-07-12 10:00 | 2013-07-12 12:00 | 444507.7736 | 444965.591 | 450066.7983 | 449500.4733 | 450575.3559 | 450003.8617 | 445909.7114 | 445811.9073 | 0.90947 | 0.99096 | 0.90023 | 0.95981 | -21.625 | 0.99096 | 1 | 0.90947 | 1
Actual Schedule | 2013-05-31 16:00 | 2013-06-21 16:00 | 440940.8905 | 440940.8905 | 440940.8905 | 2013-06-07 17:00 | 0 | 100% | 0 | 100% | -9d 7h | 96.11% | 100% | 2013-06-07 17:00 | 2013-06-07 17:00 | 2013-06-07 17:00 | 2013-06-21 16:00 | 2013-06-21 16:00 | 2013-06-21 16:00 | 2013-06-21 16:00 | 2013-06-21 16:00 | 2013-06-21 16:00 | 440940.8905 | 440940.8905 | 440940.8905 | 440940.8905 | 440940.8905 | 440940.8905 | 440940.8905 | 440940.8905 | 0.9611 | 1 | 1 | 1 | -9.875 | 1 | 1 | 0.9611 | 1