## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Social Apartments Ypres (2) | 1 |  |  | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 | 445.375
1 | afbraak | 1.1 |  | FS2;FS3;FS6 | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 11.375
2 | onderbouw - metselwerk | 1.2 | 1FS | FS7 | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 0.375
3 | onderbouw - isolatie | 1.3 | 1FS | FS7 | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 0.375
4 | riolering | 1.4 | 6SS | FS5-1w | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 18.375
5 | fundering | 1.5 | 4FS-1w | FS7 | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 28.375
6 | grondwerken | 1.6 | 1FS | SS4;FS25;FS29 | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 28.375
7 | bovenbouw - metselwerk | 1.7 | 2FS;3FS;5FS | FS8-2w;SS9+16w;SS10+20w;FS12;FS13;FS14;FS15;FS16;FS17 | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 217.375
8 | bovenbouw - isolatie | 1.8 | 7FS-2w |  | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 32.375
9 | dakwerken | 1.9 | 7SS+16w |  | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 137.375
10 | buitenverdichting | 1.10 | 7SS+20w |  | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 25.375
11 | gevelbekleding | 1.11 |  |  | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 | 53.375
12 | buitentrappen | 1.12 | 7FS |  | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 | 2.375
13 | sanitair | 1.13 | 7FS | SS18+4w;SS19+4w | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 88.375
14 | verwarmingsinstallaties | 1.14 | 7FS | SS18+4w;SS19+4w | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 32.375
15 | electriciteit | 1.15 | 7FS | SS18+4w;SS19+4w | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 107.375
16 | ventilatie | 1.16 | 7FS | SS18+4w;SS19+4w | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 32.375
17 | liftinstallatie | 1.17 | 7FS |  | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 11.375
18 | pleisterwerken | 1.18 | 13SS+4w;14SS+4w;15SS+4w;16SS+4w | FS20-4w | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 72.375
19 | binnenplaatafwerking | 1.19 | 13SS+4w;14SS+4w;15SS+4w;16SS+4w | FS20-4w | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 46.375
20 | vloeren | 1.20 | 18FS-4w;19FS-4w | FS21-2w;FS22;FS23-1w | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 39.375
21 | binnendeuren &amp;amp;amp;amp; - ramen | 1.21 | 20FS-2w | FS24 | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 | 28.375
22 | binnentrappen | 1.22 | 20FS | FS24 | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 | 11.375
23 | keukeninstallatie | 1.23 | 20FS-1w | FS24 | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 | 25.375
24 | vast meubilair &amp;amp;amp;amp; faience | 1.24 | 21FS;22FS;23FS |  | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 | 11.375
25 | buitenverharding | 1.25 | 6FS |  | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 18.375
26 | buitenafsluiting | 1.26 |  |  | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 25.375
27 | brievenbussen | 1.27 |  |  | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 | 1.375
28 | fietsenrekken | 1.28 |  |  | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 | 1.375
29 | tuinaanleg | 1.29 | 6FS |  | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 45.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Social Apartments Ypres (2) | 2168h |  |  |  |  | 99 | 100 | 101
1 | afbraak | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | onderbouw - metselwerk | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | onderbouw - isolatie | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | riolering | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | fundering | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | grondwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | bovenbouw - metselwerk | 1000h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | bovenbouw - isolatie | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | dakwerken | 720h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | buitenverdichting | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | gevelbekleding | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | buitentrappen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | sanitair | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | verwarmingsinstallaties | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | electriciteit | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | ventilatie | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | liftinstallatie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | pleisterwerken | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | binnenplaatafwerking | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | vloeren | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | binnendeuren &amp;amp;amp;amp; - ramen | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | binnentrappen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | keukeninstallatie | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | vast meubilair &amp;amp;amp;amp; faience | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | buitenverharding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | buitenafsluiting | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | brievenbussen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | fietsenrekken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | tuinaanleg | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-04-30 09:00 |  | TP Name | 30/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 10d | [5 empty] | 85203.3076 |  | 4.626% |  | 60634.4419 | 19800
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 |  | 0 | 0 | 113.08 | 1d | 0 | 0 | 0 | 113.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 |  | 0 | 0 | 100.8 | 1d | 0 | 0 | 0 | 100.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 |  | 0 | 0 | 18801.6094 | 10d | 0 | 0 | 0 | 18801.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 6d | 16917.0387 | 25375.558 | 9d | 13316.9203 | 0 | 30233.959 | 25375.558 | 40% | Started | 22556.0519 | 0 | 100 | 30 | 40 | 100 | 53.6157 | 40
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 6d | 14643.0875 | 21964.6312 | 9d | 11488.7611 | 0 | 26131.8486 | 21964.6312 | 40% | Started | 14643.0877 | 0 | 100 | 40 | 40 | 100 | 71.3834 | 40
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 |  | 0 | 0 | 267780.25 | 125d | 0 | 0 | 0 | 267780.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 |  | 0 | 0 | 20641.9395 | 25d | 0 | 0 | 0 | 20641.9395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 |  | 0 | 0 | 76735.8125 | 90d | 0 | 0 | 0 | 76735.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 1d | 3635.3021 | 50894.2292 | 14d | 5402.1979 | 0 | 9037.5 | 50894.2292 | 6.667% | Started | 3635.3023 | 0 | 100 | 6.6667 | 6.6667 | 100 | 16.5736 | 6.6667
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 |  | 0 | 0 | 44615.1406 | 20d | 0 | 0 | 0 | 44615.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 |  | 0 | 0 | 7665.2402 | 30d | 0 | 0 | 0 | 7665.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-05-31 16:00 |  | TP Name | 31/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 25d 7h | [5 empty] | 148645.5532 |  | 11.5% |  | 150700.9754 | 92226.8479
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 |  | 0 | 0 | 113.08 | 1d | 0 | 0 | 0 | 113.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 |  | 0 | 0 | 100.8 | 1d | 0 | 0 | 0 | 100.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -2297.4489 | 0 | 14623.9995 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 77.7806 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 14d | 39473.0902 | 16917.0387 | 6d | 1124.9283 | 0 | 40598.0186 | 16917.0387 | 70% | Started | 39473.0896 | 22203.6133 | 100 | 70 | 70 | 100 | 71.9949 | 70
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 13d | 31726.6896 | 4881.0292 | 2d | 433.0292 | 0 | 32159.7188 | 4881.0292 | 86.67% | Started | 31726.6899 | 31421.6253 | 100 | 86.6667 | 86.6667 | 100 | 87.8496 | 86.6667
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 3d | 6426.726 | 261353.524 | 122d | -426.7104 | 0 | 6000.0156 | 261353.524 | 2.4% | Started | 6426.7261 | 0 | 100 | 2.4 | 2.4 | 100 | 2.2406 | 2.4
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 |  | 0 | 0 | 20641.9395 | 25d | 0 | 0 | 0 | 20641.9395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 |  | 0 | 0 | 76735.8125 | 90d | 0 | 0 | 0 | 76735.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 10d | 36353.0208 | 18176.5104 | 5d | -889.2201 | 0 | 35463.8008 | 18176.5104 | 66.67% | Started | 36353.0219 | 0 | 100 | 66.6667 | 66.6667 | 100 | 65.036 | 66.6667
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 |  | 0 | 0 | 44615.1406 | 20d | 0 | 0 | 0 | 44615.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 |  | 0 | 0 | 7665.2402 | 30d | 0 | 0 | 0 | 7665.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2012-06-30 16:00 |  | TP Name | 30/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 47d | [5 empty] | 210595.5785 |  | 16.17% |  | 211900.3484 | 169270.0255
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 |  | 0 | 0 | 113.08 | 1d | 0 | 0 | 0 | 113.08 | 0% | Not Started | 0 | 113.08 | 100 |  | 0 | 100 |  | 0
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 13d | 31726.6896 | 4881.0292 | 2d | 433.0292 | 0 | 32159.7188 | 4881.0292 | 86.67% | Started | 31726.6899 | 36607.7188 | 100 | 86.6667 | 86.6667 | 100 | 87.8496 | 86.6667
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 23d | 49271.566 | 218508.684 | 102d | 221.7152 | 0 | 49493.2812 | 218508.684 | 18.4% | Started | 49271.5661 | 19280.178 | 100 | 18.4 | 18.4 | 100 | 18.4828 | 18.4
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 1d | 825.6776 | 19816.2619 | 24d | 138.5216 | 0 | 964.1992 | 19816.2619 | 4% | Started | 825.6776 | 0 | 100 | 4 | 4 | 100 | 4.6711 | 4
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 |  | 0 | 0 | 76735.8125 | 90d | 0 | 0 | 0 | 76735.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 10d | 36353.0208 | 18176.5104 | 5d | -889.2201 | 0 | 35463.8008 | 18176.5104 | 66.67% | Started | 36353.0219 | 18176.5104 | 100 | 66.6667 | 66.6667 | 100 | 65.036 | 66.6667
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 |  | 0 | 0 | 44615.1406 | 20d | 0 | 0 | 0 | 44615.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP4
| TP Status Date | 2012-07-31 16:00 |  | TP Name | 31/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 57d | [5 empty] | 228759.4906 |  | 17.54% |  | 229863.9608 | 227045.4663
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 |  | 0 | 0 | 113.08 | 1d | 0 | 0 | 0 | 113.08 | 0% | Not Started | 0 | 113.08 | 100 |  | 0 | 100 |  | 0
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 13d | 31726.6896 | 4881.0292 | 2d | 433.0292 | 0 | 32159.7188 | 4881.0292 | 86.67% | Started | 31726.6899 | 36607.7188 | 100 | 86.6667 | 86.6667 | 100 | 87.8496 | 86.6667
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 31d | 66409.502 | 201370.748 | 94d | 736.9511 | 0 | 67146.4531 | 201370.748 | 24.8% | Started | 66409.5009 | 40702.598 | 100 | 24.8 | 24.8 | 100 | 25.0752 | 24.8
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 2d | 1651.3552 | 18990.5843 | 23d | -176.4157 | 0 | 1474.9395 | 18990.5843 | 8% | Started | 1651.3551 | 0 | 100 | 8 | 8 | 100 | 7.1454 | 8
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 |  | 0 | 0 | 76735.8125 | 90d | 0 | 0 | 0 | 76735.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 10d | 36353.0208 | 18176.5104 | 5d | -889.2201 | 0 | 35463.8008 | 18176.5104 | 66.67% | Started | 36353.0219 | 54529.5312 | 100 | 66.6667 | 66.6667 | 100 | 65.036 | 66.6667
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 |  | 0 | 0 | 44615.1406 | 20d | 0 | 0 | 0 | 44615.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP5
| TP Status Date | 2012-08-31 09:00 |  | TP Name | 31/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 75d 1h | [5 empty] | 271464.4613 |  | 20.81% |  | 272821.8798 | 265873.6025
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 13d | 31726.6896 | 4881.0292 | 2d | 433.0292 | 0 | 32159.7188 | 4881.0292 | 86.67% | Started | 31726.6899 | 36607.7188 | 100 | 86.6667 | 86.6667 | 100 | 87.8496 | 86.6667
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 51d | 109254.342 | 158525.908 | 74d | 484.0017 | 0 | 109738.3438 | 158525.908 | 40.8% | Started | 109254.34 | 79530.7342 | 100 | 40.8 | 40.8 | 100 | 40.9807 | 40.8
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 2d | 1651.3552 | 18990.5843 | 23d | -176.4157 | 0 | 1474.9395 | 18990.5843 | 8% | Started | 1651.3551 | 0 | 100 | 8 | 8 | 100 | 7.1454 | 8
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 |  | 0 | 0 | 76735.8125 | 90d | 0 | 0 | 0 | 76735.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 10d | 36353.0208 | 18176.5104 | 5d | -889.2201 | 0 | 35463.8008 | 18176.5104 | 66.67% | Started | 36353.0219 | 54529.5312 | 100 | 66.6667 | 66.6667 | 100 | 65.036 | 66.6667
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 |  | 0 | 0 | 44615.1406 | 20d | 0 | 0 | 0 | 44615.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP6
| TP Status Date | 2012-09-30 16:00 |  | TP Name | 30/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 96d | [5 empty] | 326531.3441 |  | 24.96% |  | 327221.8073 | 310592.9043
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 13d | 31726.6896 | 4881.0292 | 2d | 433.0292 | 0 | 32159.7188 | 4881.0292 | 86.67% | Started | 31726.6899 | 36607.7188 | 100 | 86.6667 | 86.6667 | 100 | 87.8496 | 86.6667
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 73d | 156383.666 | 111396.584 | 52d | 321.5606 | 0 | 156705.2266 | 111396.584 | 58.4% | Started | 156383.6637 | 124250.036 | 100 | 58.4 | 58.4 | 100 | 58.5201 | 58.4
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 2d | 1651.3552 | 18990.5843 | 23d | -176.4157 | 0 | 1474.9395 | 18990.5843 | 8% | Started | 1651.3551 | 0 | 100 | 8 | 8 | 100 | 7.1454 | 8
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 |  | 0 | 0 | 76735.8125 | 90d | 0 | 0 | 0 | 76735.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 |  | 0 | 0 | 44615.1406 | 20d | 0 | 0 | 0 | 44615.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP7
| TP Status Date | 2012-10-31 16:00 |  | TP Name | 31/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 116d | [5 empty] | 347661.5784 |  | 26.66% |  | 349469.9004 | 353437.7443
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 13d | 31726.6896 | 4881.0292 | 2d | 433.0292 | 0 | 32159.7188 | 4881.0292 | 86.67% | Started | 31726.6899 | 36607.7188 | 100 | 86.6667 | 86.6667 | 100 | 87.8496 | 86.6667
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 83d | 177806.086 | 89974.164 | 42d | -843.1954 | 0 | 176962.8906 | 89974.164 | 66.4% | Started | 177806.0792 | 167094.876 | 100 | 66.4 | 66.4 | 100 | 66.0851 | 66.4
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 3d | 2477.0327 | 18164.9067 | 22d | -129.523 | 0 | 2347.5098 | 18164.9067 | 12% | Started | 2477.0327 | 0 | 100 | 12 | 12 | 100 | 11.3725 | 12
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 |  | 0 | 0 | 76735.8125 | 90d | 0 | 0 | 0 | 76735.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 |  | 0 | 0 | 44615.1406 | 20d | 0 | 0 | 0 | 44615.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP8
| TP Status Date | 2012-11-30 16:00 |  | TP Name | 30/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 135d 7h | [5 empty] | 366368.7816 |  | 28.37% |  | 371874.3778 | 446143.1401
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 87d | 186375.054 | 81405.196 | 38d | -429.9603 | 0 | 185945.0938 | 81405.196 | 69.6% | Started | 186375.0486 | 209671.9358 | 100 | 69.6 | 69.6 | 100 | 69.4394 | 69.6
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 3d | 2477.0327 | 18164.9067 | 22d | -129.523 | 0 | 2347.5098 | 18164.9067 | 12% | Started | 2477.0327 | 0 | 100 | 12 | 12 | 100 | 11.3725 | 12
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 7d 7h | 6714.3836 | 69914.8514 | 82d | 285.6164 | 0 | 7000 | 69914.8514 | 8.762% | Started | 6723.7221 | 16945.8253 | 100 | 8.75 | 8.7622 | 100 | 9.1222 | 8.7622
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 1d | 2230.757 | 42384.3836 | 19d | 169.243 | 0 | 2400 | 42384.3836 | 5% | Started | 2230.7571 | 33182.5108 | 100 | 5 | 5 | 100 | 5.3793 | 5
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP9
| TP Status Date | 2012-12-31 16:00 |  | TP Name | 31/12, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 151d | [5 empty] | 374404.5941 |  | 29.03% |  | 380497.8185 | 536473.0441
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 87d | 186375.054 | 81405.196 | 38d | -429.9603 | 0 | 185945.0938 | 81405.196 | 69.6% | Started | 186375.0486 | 242073.346 | 100 | 69.6 | 69.6 | 100 | 69.4394 | 69.6
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 3d | 2477.0327 | 18164.9067 | 22d | -129.523 | 0 | 2347.5098 | 18164.9067 | 12% | Started | 2477.0327 | 0 | 100 | 12 | 12 | 100 | 11.3725 | 12
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 18d | 15347.1625 | 61388.65 | 72d | -311.35 | 0 | 15035.8125 | 61388.65 | 20% | Started | 15347.1627 | 29841.7049 | 100 | 20 | 20 | 100 | 19.5943 | 20
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 33599.9844 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 1d | 2230.757 | 42384.3836 | 19d | 169.243 | 0 | 2400 | 42384.3836 | 5% | Started | 2230.7571 | 44615.1406 | 100 | 5 | 5 | 100 | 5.3793 | 5
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP10
| TP Status Date | 2013-01-31 16:00 |  | TP Name | 31/01, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 169d 7h | [5 empty] | 377642.7425 |  | 29.29% |  | 383908.2988 | 680929.3584
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 87d | 186375.054 | 81405.196 | 38d | -429.9603 | 0 | 185945.0938 | 81405.196 | 69.6% | Started | 186375.0486 | 267780.25 | 100 | 69.6 | 69.6 | 100 | 69.4394 | 69.6
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 3d | 2477.0327 | 18164.9067 | 22d | -129.523 | 0 | 2347.5098 | 18164.9067 | 12% | Started | 2477.0327 | 11456.2764 | 100 | 12 | 12 | 100 | 11.3725 | 12
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 22d | 18757.6431 | 57978.1694 | 68d | -483.6821 | 0 | 18273.9609 | 57978.1694 | 24.44% | Started | 18757.6431 | 45934.91 | 100 | 24.4444 | 24.4444 | 100 | 23.8141 | 24.4444
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 97019.9549 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 3241.3858 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 14443.6605 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 4347.667 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 5747.245 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 1d | 2230.757 | 42384.3836 | 19d | 169.243 | 0 | 2400 | 42384.3836 | 5% | Started | 2230.7571 | 44615.1406 | 100 | 5 | 5 | 100 | 5.3793 | 5
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP11
| TP Status Date | 2013-02-28 16:00 |  | TP Name | 28/02, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 189d 7h | [5 empty] | 389299.2054 |  | 30.13% |  | 394938.4762 | 907753.6246
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 87d | 186375.054 | 81405.196 | 38d | -429.9603 | 0 | 185945.0938 | 81405.196 | 69.6% | Started | 186375.0486 | 267780.25 | 100 | 69.6 | 69.6 | 100 | 69.4394 | 69.6
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 5d | 4128.3879 | 16513.5516 | 20d | -299.0285 | 0 | 3829.3594 | 16513.5516 | 20% | Started | 4128.388 | 20641.9395 | 100 | 20 | 20 | 100 | 18.5514 | 20
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 33d | 28136.4646 | 48599.3479 | 57d | 312.1096 | 0 | 28448.5742 | 48599.3479 | 36.67% | Started | 28136.4652 | 62987.3128 | 100 | 36.6667 | 36.6667 | 100 | 37.0734 | 36.6667
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 100799.9531 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 19971.1189 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 88991.5855 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 26787.2384 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 35410.445 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 51566 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 1859.7726 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 1d | 2230.757 | 42384.3836 | 19d | 169.243 | 0 | 2400 | 42384.3836 | 5% | Started | 2230.7571 | 44615.1406 | 100 | 5 | 5 | 100 | 5.3793 | 5
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP12
| TP Status Date | 2013-03-31 16:00 |  | TP Name | 31/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 211d | [5 empty] | 447330.9115 |  | 34.36% |  | 450411.1055 | 1073594.9428
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 100d | 214224.2 | 53556.05 | 25d | -1044.7586 | 0 | 213179.4414 | 53556.05 | 80% | Started | 214224.2032 | 267780.25 | 100 | 80 | 80 | 100 | 79.6098 | 80
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 7d | 5779.743 | 14862.1964 | 18d | 147.9064 | 0 | 5927.6494 | 14862.1964 | 28% | Started | 5779.7431 | 20641.9395 | 100 | 28 | 28 | 100 | 28.7165 | 28
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 55d | 46894.1076 | 19610.2632 | 23d | 10253.5349 | 0 | 57147.6426 | 19610.2632 | 70.51% | Started | 54108.5848 | 76735.8125 | 100 | 61.1111 | 70.5128 | 100 | 74.4732 | 70.5128
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 |  | 0 | 0 | 86666.6094 | 20d | 0 | 0 | 0 | 86666.6094 | 0% | Not Started | 0 | 86666.6094 | 100 |  | 0 | 100 |  | 0
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 100799.9531 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 37641.8994 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 |  | 0 | 0 | 93184.9062 | 25d | 0 | 0 | 0 | 93184.9062 | 0% | Not Started | 0 | 93184.9062 | 100 |  | 0 | 100 |  | 0
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 |  | 0 | 0 | 78538.5 | 70d | 0 | 0 | 0 | 78538.5 | 0% | Not Started | 0 | 50489.0357 | 100 |  | 0 | 100 |  | 0
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 37079 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 |  | 0 | 0 | 51566 | 10d | 0 | 0 | 0 | 51566 | 0% | Not Started | 0 | 51566 | 100 |  | 0 | 100 |  | 0
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 11998.533 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 8052.9951 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 1d | 2230.757 | 42384.3836 | 19d | 169.243 | 0 | 2400 | 42384.3836 | 5% | Started | 2230.7571 | 44615.1406 | 100 | 5 | 5 | 100 | 5.3793 | 5
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 0 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP13
| TP Status Date | 2013-04-30 16:00 |  | TP Name | 30/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 227d 7h | [5 empty] | 553740.3177 |  | 41.55% |  | 544639.3553 | 1142947.9174
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 100d | 214224.2 | 53556.05 | 25d | -1044.7586 | 0 | 213179.4414 | 53556.05 | 80% | Started | 214224.2032 | 267780.25 | 100 | 80 | 80 | 100 | 79.6098 | 80
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 7d | 5779.743 | 14862.1964 | 18d | 147.9064 | 0 | 5927.6494 | 14862.1964 | 28% | Started | 5779.7431 | 20641.9395 | 100 | 28 | 28 | 100 | 28.7165 | 28
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 55d | 46894.1076 | 19610.2632 | 23d | 10253.5349 | 0 | 57147.6426 | 19610.2632 | 70.51% | Started | 54108.5848 | 76735.8125 | 100 | 61.1111 | 70.5128 | 100 | 74.4732 | 70.5128
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 8d 7h | 38458.3079 | 48208.3015 | 11d 1h | 1248.6921 | 0 | 39707 | 48208.3015 | 44.37% | Started | 38458.3074 | 86666.6094 | 100 | 44.375 | 44.375 | 100 | 45.8158 | 44.375
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 100799.9531 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 50189.1992 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 1d 7h | 6988.868 | 86196.0383 | 23d 1h | -1948.9617 | 0 | 5039.9062 | 86196.0383 | 7.5% | Started | 6988.8682 | 93184.9062 | 100 | 7.5 | 7.5 | 100 | 5.4085 | 7.5
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 7d 7h | 8835.5812 | 69702.9187 | 62d 1h | 6297.9187 | 0 | 15133.5 | 69702.9187 | 11.25% | Started | 8835.581 | 69422.4241 | 100 | 11.25 | 11.25 | 100 | 19.2689 | 11.25
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 |  | 0 | 0 | 37079 | 25d | 0 | 0 | 0 | 37079 | 0% | Not Started | 0 | 37079 | 100 |  | 0 | 100 |  | 0
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 6d 7h | 35451.625 | 10313.2 | 2d | 11077.375 | 0 | 46529 | 10313.2 | 77.46% | Started | 39945.4932 | 51566 | 100 | 68.75 | 77.4648 | 100 | 90.2319 | 77.4648
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 20097.5428 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 16105.9902 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 17408.5839 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 1d | 2230.757 | 42384.3836 | 19d | 169.243 | 0 | 2400 | 42384.3836 | 5% | Started | 2230.7571 | 44615.1406 | 100 | 5 | 5 | 100 | 5.3793 | 5
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 4311.6976 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP14
| TP Status Date | 2013-05-31 16:00 |  | TP Name | 31/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 245d 7h | [5 empty] | 594983.1077 |  | 45.25% |  | 593085.9938 | 1246638.8376
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 100d | 214224.2 | 53556.05 | 25d | -1044.7586 | 0 | 213179.4414 | 53556.05 | 80% | Started | 214224.2032 | 267780.25 | 100 | 80 | 80 | 100 | 79.6098 | 80
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 13d | 10733.8085 | 9908.1309 | 12d | -125.8691 | 0 | 10607.9395 | 9908.1309 | 52% | Started | 10733.8081 | 20641.9395 | 100 | 52 | 52 | 100 | 51.3902 | 52
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 55d | 46894.1076 | 19610.2632 | 23d | 10253.5349 | 0 | 57147.6426 | 19610.2632 | 70.51% | Started | 54108.5848 | 76735.8125 | 100 | 61.1111 | 70.5128 | 100 | 74.4732 | 70.5128
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 12d | 51999.9656 | 34666.6438 | 8d | -700.9656 | 0 | 51299 | 34666.6438 | 60% | Started | 51999.9677 | 86666.6094 | 100 | 60 | 60 | 100 | 59.1912 | 60
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 100799.9531 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 22414.0098 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 |  | 0 | 0 | 50189.1992 | 60d | 0 | 0 | 0 | 50189.1992 | 0% | Not Started | 0 | 50189.1992 | 100 |  | 0 | 100 |  | 0
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 5d | 18636.9813 | 74547.925 | 20d | -1260.075 | 0 | 17376.9062 | 74547.925 | 20% | Started | 18636.9815 | 93184.9062 | 100 | 20 | 20 | 100 | 18.6478 | 20
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 13d | 14585.7214 | 35903.3143 | 32d | 8421.2786 | 0 | 23007 | 35903.3143 | 28.89% | Started | 22688.901 | 78538.5 | 100 | 18.5714 | 28.8889 | 100 | 29.2939 | 28.8889
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 3d | 4449.48 | 32629.52 | 22d | 310.52 | 0 | 4760 | 32629.52 | 12% | Started | 4449.4799 | 37079 | 100 | 12 | 12 | 100 | 12.8375 | 12
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 6d 7h | 35451.625 | 10313.2 | 2d | 11077.375 | 0 | 46529 | 10313.2 | 77.46% | Started | 39945.4932 | 51566 | 100 | 68.75 | 77.4648 | 100 | 90.2319 | 77.4648
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 |  | 0 | 0 | 21597.3594 | 45d | 0 | 0 | 0 | 21597.3594 | 0% | Not Started | 0 | 21597.3594 | 100 |  | 0 | 100 |  | 0
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 |  | 0 | 0 | 16105.9902 | 30d | 0 | 0 | 0 | 16105.9902 | 0% | Not Started | 0 | 16105.9902 | 100 |  | 0 | 100 |  | 0
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 |  | 0 | 0 | 63303.9414 | 25d | 0 | 0 | 0 | 63303.9414 | 0% | Not Started | 0 | 62987.4217 | 100 |  | 0 | 100 |  | 0
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 9490.925 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 12237.7125 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | -59.8242 | 0 | 43563.8008 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 79.8903 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 1d | 2230.757 | 42384.3836 | 19d | 169.243 | 0 | 2400 | 42384.3836 | 5% | Started | 2230.7571 | 44615.1406 | 100 | 5 | 5 | 100 | 5.3793 | 5
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 7665.2402 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP15
| TP Status Date | 2013-06-30 09:00 |  | TP Name | 30/06, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 266d | [5 empty] | 726076.3988 |  | 55.67% |  | 729660.8784 | 1306660.09
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 116d | 248500.072 | 19280.178 | 9d | 79.5686 | 0 | 248579.6406 | 19280.178 | 92.8% | Started | 248500.0648 | 267780.25 | 100 | 92.8 | 92.8 | 100 | 92.8297 | 92.8
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 17d | 14036.5188 | 6605.4206 | 8d | -737.5794 | 0 | 13298.9395 | 6605.4206 | 68% | Started | 14036.519 | 20641.9395 | 100 | 68 | 68 | 100 | 64.4268 | 68
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 55d | 46894.1076 | 19610.2632 | 23d | 10253.5349 | 0 | 57147.6426 | 19610.2632 | 70.51% | Started | 54108.5848 | 76735.8125 | 100 | 61.1111 | 70.5128 | 100 | 74.4732 | 70.5128
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 19d | 82333.2789 | 8666.6609 | 2d | -3381.6695 | 0 | 78951.6094 | 8666.6609 | 90.48% | Started | 78412.6471 | 86666.6094 | 100 | 95 | 90.4762 | 100 | 91.0981 | 90.4762
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 100799.9531 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 22414.0098 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 2013-06-03 08:00 | 20d | 16729.7331 | 33459.4661 | 40d | -1210.0339 | 0 | 15519.6992 | 33459.4661 | 33.33% | Started | 16729.7336 | 50189.1992 | 100 | 33.3333 | 33.3333 | 100 | 30.9224 | 33.3333
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 8d | 29819.17 | 63365.7363 | 17d | 909.3261 | 0 | 30728.4961 | 63365.7363 | 32% | Started | 29819.1693 | 93184.9062 | 100 | 32 | 32 | 100 | 32.9758 | 32
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 20d | 22439.5714 | 28049.4643 | 25d | 12322.4286 | 0 | 34762 | 28049.4643 | 44.44% | Started | 34906.0003 | 78538.5 | 100 | 28.5714 | 44.4444 | 100 | 44.2611 | 44.4444
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 10d | 14831.6 | 22247.4 | 15d | -183.6 | 0 | 14648 | 22247.4 | 40% | Started | 14831.6002 | 37079 | 100 | 40 | 40 | 100 | 39.5048 | 40
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 6d 7h | 35451.625 | 10313.2 | 2d | 11307.375 | 0 | 46759 | 10313.2 | 77.46% | Started | 39945.4932 | 51566 | 100 | 68.75 | 77.4648 | 100 | 90.678 | 77.4648
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 2013-06-24 08:00 | 5d | 2399.7066 | 9598.8264 | 20d | -302.3472 | 0 | 2097.3594 | 9598.8264 | 20% | Started | 4319.4719 | 21597.3594 | 100 | 11.1111 | 20 | 100 | 9.7112 | 20
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 2013-06-10 08:00 | 12d | 6442.3961 | 8052.9951 | 15d | 218.5941 | 0 | 6660.9902 | 8052.9951 | 44.44% | Started | 7158.2179 | 16105.9902 | 100 | 40 | 44.4444 | 100 | 41.3572 | 44.4444
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 2013-06-24 08:00 | 5d | 12660.7883 | 62987.4217 | 24d 7h | -8474.675 | 0 | 4186.1133 | 62987.4217 | 16.74% | Started | 10594.8019 | 63303.9414 | 100 | 20 | 16.7364 | 100 | 6.6127 | 16.7364
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 21388 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 2936 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 50206 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 4063.3701 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | 1600.9062 | 0 | 45224.5312 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 82.9359 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 1d | 2230.757 | 42384.3836 | 19d | 169.243 | 0 | 2400 | 42384.3836 | 5% | Started | 2230.7571 | 44615.1406 | 100 | 5 | 5 | 100 | 5.3793 | 5
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 2140 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 700 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 7665.2402 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP16
| TP Status Date | 2013-07-31 16:00 |  | TP Name | 31/07, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 286d | [5 empty] | 795528.6253 |  | 60.8% |  | 796973.456 | 1310723.4601
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 118d | 252784.556 | 10711.21 | 5d | -467.4359 | 0 | 252317.1201 | 10711.21 | 95.93% | Started | 256894.8684 | 267780.25 | 100 | 94.4 | 95.935 | 100 | 94.2254 | 95.935
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 17d | 14036.5188 | 6605.4206 | 8d | -737.5794 | 0 | 13298.9395 | 6605.4206 | 68% | Started | 14036.519 | 20641.9395 | 100 | 68 | 68 | 100 | 64.4268 | 68
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 55d | 46894.1076 | 19610.2632 | 23d | 10253.5349 | 0 | 57147.6426 | 19610.2632 | 70.51% | Started | 54108.5848 | 76735.8125 | 100 | 61.1111 | 70.5128 | 100 | 74.4732 | 70.5128
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 19d | 82333.2789 | 8666.6609 | 2d | -3381.6695 | 0 | 78951.6094 | 8666.6609 | 90.48% | Started | 78412.6471 | 86666.6094 | 100 | 95 | 90.4762 | 100 | 91.0981 | 90.4762
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 100799.9531 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 22414.0098 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 2013-06-03 08:00 | 20d | 16729.7331 | 33459.4661 | 40d | -736.5339 | 0 | 15993.1992 | 33459.4661 | 33.33% | Started | 16729.7336 | 50189.1992 | 100 | 33.3333 | 33.3333 | 100 | 31.8658 | 33.3333
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 8d | 29819.17 | 63365.7363 | 17d | 909.3261 | 0 | 30728.4961 | 63365.7363 | 32% | Started | 29819.1693 | 93184.9062 | 100 | 32 | 32 | 100 | 32.9758 | 32
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 25d | 28049.4643 | 22439.5714 | 20d | 15320.0357 | 0 | 43369.5 | 22439.5714 | 55.56% | Started | 43632.5021 | 78538.5 | 100 | 35.7143 | 55.5556 | 100 | 55.2207 | 55.5556
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 10d | 14831.6 | 22247.4 | 15d | -183.6 | 0 | 14648 | 22247.4 | 40% | Started | 14831.6002 | 37079 | 100 | 40 | 40 | 100 | 39.5048 | 40
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 6d 7h | 35451.625 | 10313.2 | 2d | 11307.375 | 0 | 46759 | 10313.2 | 77.46% | Started | 39945.4932 | 51566 | 100 | 68.75 | 77.4648 | 100 | 90.678 | 77.4648
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 2013-06-24 08:00 | 25d | 11998.533 | 0 | 0 | 9598.8264 | 0 | 21597.3594 | 0 | 100% | Finished | 21597.3594 | 21597.3594 | 100 | 55.5556 | 100 | 100 | 100 | 100
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 2013-06-10 08:00 | 17d | 9126.7278 | 6979.2624 | 13d | -404.2874 | 0 | 8722.4404 | 6979.2624 | 56.67% | Started | 9126.7277 | 16105.9902 | 100 | 56.6667 | 56.6667 | 100 | 54.1565 | 56.6667
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 2013-06-24 08:00 | 12d | 30385.8919 | 32918.0495 | 13d | -3577.4817 | 0 | 26808.4102 | 32918.0495 | 48% | Started | 30385.8912 | 63303.9414 | 100 | 48 | 48 | 100 | 42.3487 | 48
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 21388 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 2936 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 50206 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 8126.7402 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | 1600.9062 | 0 | 45224.5312 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 82.9359 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 6d | 13384.5422 | 31230.5984 | 14d | 1465.4578 | 0 | 14850 | 31230.5984 | 30% | Started | 13384.5427 | 44615.1406 | 100 | 30 | 30 | 100 | 33.2847 | 30
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 2140 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 700 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 7665.2402 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP17
| TP Status Date | 2013-08-31 16:00 |  | TP Name | 31/08, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 295d | [5 empty] | 830827.0169 |  | 63.21% |  | 828548.5512 | 1310723.4601
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 118d | 252784.556 | 10711.21 | 5d | -467.4359 | 0 | 252317.1201 | 10711.21 | 95.93% | Started | 256894.8684 | 267780.25 | 100 | 94.4 | 95.935 | 100 | 94.2254 | 95.935
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 19d | 15687.874 | 4954.0655 | 6d | -509.6445 | 0 | 15178.2295 | 4954.0655 | 76% | Started | 15687.8738 | 20641.9395 | 100 | 76 | 76 | 100 | 73.531 | 76
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 55d | 46894.1076 | 19610.2632 | 23d | 10253.5349 | 0 | 57147.6426 | 19610.2632 | 70.51% | Started | 54108.5848 | 76735.8125 | 100 | 61.1111 | 70.5128 | 100 | 74.4732 | 70.5128
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 19d | 82333.2789 | 8666.6609 | 2d | -3381.6695 | 0 | 78951.6094 | 8666.6609 | 90.48% | Started | 78412.6471 | 86666.6094 | 100 | 95 | 90.4762 | 100 | 91.0981 | 90.4762
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 |  | 0 | 0 | 100799.9531 | 30d | 0 | 0 | 0 | 100799.9531 | 0% | Not Started | 0 | 100799.9531 | 100 |  | 0 | 100 |  | 0
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 22414.0098 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 2013-06-03 08:00 | 30d | 25094.5996 | 25094.5996 | 30d | -740.9004 | 0 | 24353.6992 | 25094.5996 | 50% | Started | 25094.5996 | 50189.1992 | 100 | 50 | 50 | 100 | 48.5238 | 50
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 8d | 29819.17 | 63365.7363 | 17d | 909.3261 | 0 | 30728.4961 | 63365.7363 | 32% | Started | 29819.1693 | 93184.9062 | 100 | 32 | 32 | 100 | 32.9758 | 32
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 33d | 37025.2929 | 13463.7429 | 12d | 20123.2071 | 0 | 57148.5 | 13463.7429 | 73.33% | Started | 57594.9012 | 78538.5 | 100 | 47.1429 | 73.3333 | 100 | 72.7649 | 73.3333
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 10d | 14831.6 | 22247.4 | 15d | -183.6 | 0 | 14648 | 22247.4 | 40% | Started | 14831.6002 | 37079 | 100 | 40 | 40 | 100 | 39.5048 | 40
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 6d 7h | 35451.625 | 10313.2 | 2d | 11307.375 | 0 | 46759 | 10313.2 | 77.46% | Started | 39945.4932 | 51566 | 100 | 68.75 | 77.4648 | 100 | 90.678 | 77.4648
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 2013-06-24 08:00 | 25d | 11998.533 | 0 | 0 | 9598.8264 | 0 | 21597.3594 | 0 | 100% | Finished | 21597.3594 | 21597.3594 | 100 | 55.5556 | 100 | 100 | 100 | 100
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 2013-06-10 08:00 | 17d | 9126.7278 | 6979.2624 | 13d | -404.2874 | 0 | 8722.4404 | 6979.2624 | 56.67% | Started | 9126.7277 | 16105.9902 | 100 | 56.6667 | 56.6667 | 100 | 54.1565 | 56.6667
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 2013-06-24 08:00 | 15d | 37982.3648 | 25321.5766 | 10d | 105.6469 | 0 | 38088.0117 | 25321.5766 | 60% | Started | 37982.3664 | 63303.9414 | 100 | 60 | 60 | 100 | 60.1669 | 60
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 21388 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 2936 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 50206 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 8126.7402 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | 1600.9062 | 0 | 45224.5312 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 82.9359 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 6d | 13384.5422 | 31230.5984 | 14d | 1465.4578 | 0 | 14850 | 31230.5984 | 30% | Started | 13384.5427 | 44615.1406 | 100 | 30 | 30 | 100 | 33.2847 | 30
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 2140 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 700 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 7665.2402 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP18
| TP Status Date | 2013-09-30 16:00 |  | TP Name | 30/09, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 315d 7h | [5 empty] | 968668.4916 |  | 73.5% |  | 963428.5249 | 1310723.4601
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 122d | 261353.524 | 4284.484 | 2d | -402.1539 | 0 | 260951.3701 | 4284.484 | 98.39% | Started | 263461.2178 | 267780.25 | 100 | 97.6 | 98.3871 | 100 | 97.4498 | 98.3871
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 20d | 16513.5516 | 3302.7103 | 4d | 544.9279 | 0 | 17058.4795 | 3302.7103 | 83.33% | Started | 17201.6158 | 20641.9395 | 100 | 80 | 83.3333 | 100 | 82.6399 | 83.3333
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 55d | 46894.1076 | 19610.2632 | 23d | 10253.5349 | 0 | 57147.6426 | 19610.2632 | 70.51% | Started | 54108.5848 | 76735.8125 | 100 | 61.1111 | 70.5128 | 100 | 74.4732 | 70.5128
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 19d | 82333.2789 | 8666.6609 | 2d | -3381.6695 | 0 | 78951.6094 | 8666.6609 | 90.48% | Started | 78412.6471 | 86666.6094 | 100 | 95 | 90.4762 | 100 | 91.0981 | 90.4762
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 | 2013-09-23 08:00 | 3d | 10079.9953 | 90719.9578 | 27d | -280.3703 | 0 | 9799.625 | 90719.9578 | 10% | Started | 10079.9955 | 100799.9531 | 100 | 10 | 10 | 100 | 9.7219 | 10
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 |  | 0 | 0 | 22414.0098 | 3d | 0 | 0 | 0 | 22414.0098 | 0% | Not Started | 0 | 22414.0098 | 100 |  | 0 | 100 |  | 0
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 2013-06-03 08:00 | 34d | 28440.5462 | 21748.653 | 26d | 746.653 | 0 | 29187.1992 | 21748.653 | 56.67% | Started | 28440.546 | 50189.1992 | 100 | 56.6667 | 56.6667 | 100 | 58.1543 | 56.6667
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 25d | 93184.9062 | 0 | 0 | -2100 | 0 | 91084.9062 | 0 | 100% | Finished | 93184.9062 | 93184.9062 | 100 | 100 | 100 | 100 | 97.7464 | 100
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 35d | 39269.25 | 11219.7857 | 10d | 21938.25 | 0 | 61207.5 | 11219.7857 | 77.78% | Started | 61085.501 | 78538.5 | 100 | 50 | 77.7778 | 100 | 77.9331 | 77.7778
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 23d | 34112.68 | 2966.32 | 2d | 29.32 | 0 | 34142 | 2966.32 | 92% | Started | 34112.6806 | 37079 | 100 | 92 | 92 | 100 | 92.0791 | 92
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 6d 7h | 35451.625 | 10313.2 | 2d | 11307.375 | 0 | 46759 | 10313.2 | 77.46% | Started | 39945.4932 | 51566 | 100 | 68.75 | 77.4648 | 100 | 90.678 | 77.4648
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 2013-06-24 08:00 | 25d | 11998.533 | 0 | 0 | 9598.8264 | 0 | 21597.3594 | 0 | 100% | Finished | 21597.3594 | 21597.3594 | 100 | 55.5556 | 100 | 100 | 100 | 100
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 2013-06-10 08:00 | 30d | 16105.9902 | 0 | 0 | -0.04 | 0 | 16105.9502 | 0 | 100% | Finished | 16105.9902 | 16105.9902 | 100 | 100 | 100 | 100 | 99.9998 | 100
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 2013-06-24 08:00 | 23d | 58239.6261 | 5064.3153 | 2d | 1249.3153 | 0 | 59488.9414 | 5064.3153 | 92% | Started | 58239.6272 | 63303.9414 | 100 | 92 | 92 | 100 | 93.9735 | 92
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 |  | 0 | 0 | 21388 | 20d | 0 | 0 | 0 | 21388 | 0% | Not Started | 0 | 21388 | 100 |  | 0 | 100 |  | 0
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 2936 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 |  | 0 | 0 | 50206 | 20d | 0 | 0 | 0 | 50206 | 0% | Not Started | 0 | 50206 | 100 |  | 0 | 100 |  | 0
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 |  | 0 | 0 | 8126.7402 | 10d | 0 | 0 | 0 | 8126.7402 | 0% | Not Started | 0 | 8126.7402 | 100 |  | 0 | 100 |  | 0
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | 1600.9062 | 0 | 45224.5312 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 82.9359 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 6d | 13384.5422 | 31230.5984 | 14d | 1465.4578 | 0 | 14850 | 31230.5984 | 30% | Started | 13384.5427 | 44615.1406 | 100 | 30 | 30 | 100 | 33.2847 | 30
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 2140 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 700 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 7665.2402 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP19
| TP Status Date | 2013-10-31 09:00 |  | TP Name | 31/10, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 335d 1h | [5 empty] | 1096390.2516 |  | 84.04% |  | 1101575.615 | 1310723.4601
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 0 | 0 | 113.08 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 100 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 122d | 261353.524 | 4284.484 | 2d | -402.1539 | 0 | 260951.3701 | 4284.484 | 98.39% | Started | 263461.2178 | 267780.25 | 100 | 97.6 | 98.3871 | 100 | 97.4498 | 98.3871
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 22d | 18164.9067 | 825.6776 | 1d | 773.5728 | 0 | 18938.4795 | 825.6776 | 95.65% | Started | 19744.464 | 20641.9395 | 100 | 88 | 95.6522 | 100 | 91.7476 | 95.6522
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 71d | 60536.0299 | 14494.5424 | 17d | -84.2174 | 0 | 60451.8125 | 14494.5424 | 80.68% | Started | 61911.8491 | 76735.8125 | 100 | 78.8889 | 80.6818 | 100 | 78.7791 | 80.6818
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 19d | 82333.2789 | 8666.6609 | 2d | -3381.6695 | 0 | 78951.6094 | 8666.6609 | 90.48% | Started | 78412.6471 | 86666.6094 | 100 | 95 | 90.4762 | 100 | 91.0981 | 90.4762
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 | 2013-09-23 08:00 | 12d | 40319.9812 | 60479.9719 | 18d | 684.6438 | 0 | 41004.625 | 60479.9719 | 40% | Started | 40319.9819 | 100799.9531 | 100 | 40 | 40 | 100 | 40.6792 | 40
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 | 2013-10-14 08:00 | 1d | 7471.3366 | 7471.3366 | 1d | -1965.0768 | 0 | 5506.2598 | 7471.3366 | 50% | Started | 11207.0049 | 22414.0098 | 100 | 33.3333 | 50 | 100 | 24.5662 | 50
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 2013-06-03 08:00 | 40d | 33459.4661 | 16729.7331 | 20d | -591.2669 | 0 | 32868.1992 | 16729.7331 | 66.67% | Started | 33459.4671 | 50189.1992 | 100 | 66.6667 | 66.6667 | 100 | 65.4886 | 66.6667
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 25d | 93184.9062 | 0 | 0 | -1380 | 0 | 91804.9062 | 0 | 100% | Finished | 93184.9062 | 93184.9062 | 100 | 100 | 100 | 100 | 98.5191 | 100
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 36d | 40391.2286 | 10097.8071 | 9d | 23027.2714 | 0 | 63418.5 | 10097.8071 | 80% | Started | 62830.8009 | 78538.5 | 100 | 51.4286 | 80 | 100 | 80.7483 | 80
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 24d | 35595.84 | 1483.16 | 1d | -133.84 | 0 | 35462 | 1483.16 | 96% | Started | 35595.8392 | 37079 | 100 | 96 | 96 | 100 | 95.639 | 96
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 6d 7h | 35451.625 | 10313.2 | 2d | 11307.375 | 0 | 46759 | 10313.2 | 77.46% | Started | 39945.4932 | 51566 | 100 | 68.75 | 77.4648 | 100 | 90.678 | 77.4648
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 2013-06-24 08:00 | 25d | 11998.533 | 0 | 0 | 9598.8264 | 0 | 21597.3594 | 0 | 100% | Finished | 21597.3594 | 21597.3594 | 100 | 55.5556 | 100 | 100 | 100 | 100
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 2013-06-10 08:00 | 30d | 16105.9902 | 0 | 0 | -0.04 | 0 | 16105.9502 | 0 | 100% | Finished | 16105.9902 | 16105.9902 | 100 | 100 | 100 | 100 | 99.9998 | 100
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 2013-06-24 08:00 | 24d | 60771.7838 | 2532.1577 | 1d | 1451.4077 | 0 | 62223.1914 | 2532.1577 | 96% | Started | 60771.7824 | 63303.9414 | 100 | 96 | 96 | 100 | 98.2928 | 96
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 | 2013-10-01 08:00 | 19d 1h | 20452.275 | 935.725 | 7h | -154.275 | 0 | 20298 | 935.725 | 95.63% | Started | 20452.2753 | 21388 | 100 | 95.625 | 95.625 | 100 | 94.9037 | 95.625
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 2936 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 | 2013-10-01 08:00 | 19d 1h | 48009.4875 | 0 | 0 | 2196.5125 | 0 | 50206 | 0 | 100% | Finished | 50206 | 50206 | 100 | 95.625 | 100 | 100 | 100 | 100
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 | 2013-10-18 08:00 | 6d 1h | 4977.6284 | 3250.6961 | 4d | -321.5481 | 0 | 4656.0803 | 3250.6961 | 60.49% | Started | 4916.1762 | 8126.7402 | 100 | 61.25 | 60.4938 | 100 | 57.2933 | 60.4938
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | 1600.9062 | 0 | 45224.5312 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 82.9359 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 6d | 13384.5422 | 31230.5984 | 14d | 1465.4578 | 0 | 14850 | 31230.5984 | 30% | Started | 13384.5427 | 44615.1406 | 100 | 30 | 30 | 100 | 33.2847 | 30
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 2140 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 700 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 2d | 511.016 | 7154.2242 | 28d | -60.7758 | 0 | 450.2402 | 7154.2242 | 6.667% | Started | 511.016 | 7665.2402 | 100 | 6.6667 | 6.6667 | 100 | 5.8738 | 6.6667

## TP20
| TP Status Date | 2013-11-30 16:00 |  | TP Name | 30/11, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 354d | [5 empty] | 1206014.12 |  | 92.67% |  | 1214681.3605 | 1310723.4601
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 137.72 | 0 | 250.8 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 221.7899 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 9d | 16921.4484 | 1880.1609 | 1d | -1147.8391 | 0 | 15773.6094 | 1880.1609 | 90% | Started | 16921.448 | 18801.6094 | 100 | 90 | 90 | 100 | 83.895 | 90
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 122d | 261353.524 | 4284.484 | 2d | -402.1539 | 0 | 260951.3701 | 4284.484 | 98.39% | Started | 263461.2178 | 267780.25 | 100 | 97.6 | 98.3871 | 100 | 97.4498 | 98.3871
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 22d | 18164.9067 | 825.6776 | 1d | 773.5728 | 0 | 18938.4795 | 825.6776 | 95.65% | Started | 19744.464 | 20641.9395 | 100 | 88 | 95.6522 | 100 | 91.7476 | 95.6522
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 71d | 60536.0299 | 14494.5424 | 17d | -84.2174 | 0 | 60451.8125 | 14494.5424 | 80.68% | Started | 61911.8491 | 76735.8125 | 100 | 78.8889 | 80.6818 | 100 | 78.7791 | 80.6818
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 19d | 82333.2789 | 8666.6609 | 2d | -3381.6695 | 0 | 78951.6094 | 8666.6609 | 90.48% | Started | 78412.6471 | 86666.6094 | 100 | 95 | 90.4762 | 100 | 91.0981 | 90.4762
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 | 2013-09-23 08:00 | 30d | 100799.9531 | 0 | 0 | 0 | 0 | 100799.9531 | 0 | 100% | Finished | 100799.9531 | 100799.9531 | 100 | 100 | 100 | 100 | 100 | 100
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 | 2013-10-14 08:00 | 1d | 7471.3366 | 7471.3366 | 1d | -1341.3268 | 0 | 6130.0098 | 7471.3366 | 50% | Started | 11207.0049 | 22414.0098 | 100 | 33.3333 | 50 | 100 | 27.349 | 50
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 2013-06-03 08:00 | 53d | 44333.7926 | 836.4867 | 1d | 1885.4066 | 0 | 46219.1992 | 836.4867 | 98.15% | Started | 49259.7702 | 50189.1992 | 100 | 88.3333 | 98.1481 | 100 | 92.0899 | 98.1481
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 25d | 93184.9062 | 0 | 0 | -1380 | 0 | 91804.9062 | 0 | 100% | Finished | 93184.9062 | 93184.9062 | 100 | 100 | 100 | 100 | 98.5191 | 100
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 45d | 50489.0357 | 0 | 0 | 27265.4643 | 0 | 77754.5 | 0 | 100% | Finished | 78538.5 | 78538.5 | 100 | 64.2857 | 100 | 100 | 99.0018 | 100
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 26d | 38562.16 | 0 | 0 | -256.16 | 0 | 38306 | 0 | 100% | Finished | 37079 | 37079 | 100 | 104 | 100 | 100 | 103.3092 | 100
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 6d 7h | 35451.625 | 10313.2 | 2d | 11307.375 | 0 | 46759 | 10313.2 | 77.46% | Started | 39945.4932 | 51566 | 100 | 68.75 | 77.4648 | 100 | 90.678 | 77.4648
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 2013-06-24 08:00 | 25d | 11998.533 | 0 | 0 | 9598.8264 | 0 | 21597.3594 | 0 | 100% | Finished | 21597.3594 | 21597.3594 | 100 | 55.5556 | 100 | 100 | 100 | 100
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 2013-06-10 08:00 | 30d | 16105.9902 | 0 | 0 | -0.04 | 0 | 16105.9502 | 0 | 100% | Finished | 16105.9902 | 16105.9902 | 100 | 100 | 100 | 100 | 99.9998 | 100
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 2013-06-24 08:00 | 24d | 60771.7838 | 2532.1577 | 1d | 1451.4077 | 0 | 62223.1914 | 2532.1577 | 96% | Started | 60771.7824 | 63303.9414 | 100 | 96 | 96 | 100 | 98.2928 | 96
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 | 2013-10-01 08:00 | 19d 1h | 20452.275 | 935.725 | 7h | -154.275 | 0 | 20298 | 935.725 | 95.63% | Started | 20452.2753 | 21388 | 100 | 95.625 | 95.625 | 100 | 94.9037 | 95.625
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 |  | 0 | 0 | 2936 | 10d | 0 | 0 | 0 | 2936 | 0% | Not Started | 0 | 2936 | 100 |  | 0 | 100 |  | 0
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 | 2013-10-01 08:00 | 19d 1h | 48009.4875 | 0 | 0 | 2196.5125 | 0 | 50206 | 0 | 100% | Finished | 50206 | 50206 | 100 | 95.625 | 100 | 100 | 100 | 100
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 | 2013-10-18 08:00 | 6d 1h | 4977.6284 | 3250.6961 | 4d | -321.5481 | 0 | 4656.0803 | 3250.6961 | 60.49% | Started | 4916.1762 | 8126.7402 | 100 | 61.25 | 60.4938 | 100 | 57.2933 | 60.4938
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 12d | 43623.625 | 10905.9062 | 3d | 1600.9062 | 0 | 45224.5312 | 10905.9062 | 80% | Started | 43623.6257 | 54529.5312 | 100 | 80 | 80 | 100 | 82.9359 | 80
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 14d | 31230.5984 | 13384.5422 | 6d | 375.7121 | 0 | 31606.3105 | 13384.5422 | 70% | Started | 31230.5979 | 44615.1406 | 100 | 70 | 70 | 100 | 70.8421 | 70
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 |  | 0 | 0 | 2140 | 2d | 0 | 0 | 0 | 2140 | 0% | Not Started | 0 | 2140 | 100 |  | 0 | 100 |  | 0
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 |  | 0 | 0 | 700 | 2d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 700 | 100 |  | 0 | 100 |  | 0
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 9d | 2299.5721 | 5365.6682 | 21d | -69.5721 | 0 | 2230 | 5365.6682 | 30% | Started | 2299.5722 | 7665.2402 | 100 | 30 | 30 | 100 | 29.0924 | 30

## TP21
| TP Status Date | 2013-12-31 16:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (2) | 2012-04-16 08:00 | 2013-07-05 17:00 | 271d |  |  | 0 |  |  | 1310723.4601 |  | 364d | [5 empty] | 1282185.9797 |  | 100% |  | 1310723.4601 | 1310723.4601
1 | afbraak | 2012-04-16 08:00 | 2012-04-27 17:00 | 10d |  | 0 | 0 | 247.5 | 19800 | 19800 | 2012-04-16 08:00 | 8d | 15840 | 0 | 0 | 3960 | 0 | 19800 | 0 | 100% | Finished | 19800 | 19800 | 100 | 80 | 100 | 100 | 100 | 100
2 | onderbouw - metselwerk | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 14.135 | 113.08 | 113.08 | 2012-08-20 08:00 | 1d | 113.08 | 0 | 0 | 137.72 | 0 | 250.8 | 0 | 100% | Finished | 113.08 | 113.08 | 100 | 100 | 100 | 100 | 221.7899 | 100
3 | onderbouw - isolatie | 2012-06-11 08:00 | 2012-06-11 17:00 | 1d |  | 0 | 0 | 12.6 | 100.8 | 100.8 | 2012-06-25 08:00 | 1d | 100.8 | 0 | 0 | 0 | 0 | 100.8 | 0 | 100% | Finished | 100.8 | 100.8 | 100 | 100 | 100 | 100 | 100 | 100
4 | riolering | 2012-05-07 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 235.0201 | 18801.6094 | 18801.6094 | 2012-05-21 08:00 | 10d | 18801.6094 | 0 | 0 | -2450 | 0 | 16351.6094 | 0 | 100% | Finished | 18801.6094 | 18801.6094 | 100 | 100 | 100 | 100 | 86.9692 | 100
5 | fundering | 2012-05-21 08:00 | 2012-06-18 17:00 | 20d |  | 0 | 0 | 352.4383 | 56390.1289 | 56390.1289 | 2012-04-23 08:00 | 20d | 56390.1289 | 0 | 0 | -0.2 | 0 | 56389.9289 | 0 | 100% | Finished | 56390.1289 | 56390.1289 | 100 | 100 | 100 | 100 | 99.9996 | 100
6 | grondwerken | 2012-05-07 08:00 | 2012-06-04 17:00 | 15d |  | 0 | 0 | 305.0643 | 36607.7188 | 36607.7188 | 2012-04-23 08:00 | 14d | 34167.2042 | 0 | 0 | -1682.4854 | 0 | 32484.7188 | 0 | 100% | Finished | 36607.7188 | 36607.7188 | 100 | 93.3333 | 100 | 100 | 88.7373 | 100
7 | bovenbouw - metselwerk | 2012-06-19 08:00 | 2013-01-22 17:00 | 125d |  | 0 | 0 | 267.7803 | 267780.25 | 267780.25 | 2012-05-29 08:00 | 125d | 267780.25 | 0 | 0 | -766.88 | 0 | 267013.37 | 0 | 100% | Finished | 267780.25 | 267780.25 | 100 | 100 | 100 | 100 | 99.7136 | 100
8 | bovenbouw - isolatie | 2013-01-14 08:00 | 2013-02-15 17:00 | 25d |  | 0 | 0 | 103.2097 | 20641.9395 | 20641.9395 | 2012-06-20 08:00 | 23d | 18990.5843 | 0 | 0 | 352.6552 | 0 | 19343.2395 | 0 | 100% | Finished | 20641.9395 | 20641.9395 | 100 | 92 | 100 | 100 | 93.7084 | 100
9 | dakwerken | 2012-11-05 08:00 | 2013-03-22 17:00 | 90d |  | 0 | 0 | 106.5775 | 76735.8125 | 76735.8125 | 2012-11-21 08:00 | 89d | 75883.1924 | 0 | 0 | -313.5299 | 0 | 75569.6625 | 0 | 100% | Finished | 76735.8125 | 76735.8125 | 100 | 98.8889 | 100 | 100 | 98.4803 | 100
10 | buitenverdichting | 2013-03-04 08:00 | 2013-03-29 17:00 | 20d |  | 0 | 0 | 541.6663 | 86666.6094 | 86666.6094 | 2013-04-18 08:00 | 19d | 82333.2789 | 0 | 0 | 973.3305 | 0 | 83306.6094 | 0 | 100% | Finished | 86666.6094 | 86666.6094 | 100 | 95 | 100 | 100 | 96.1231 | 100
11 | gevelbekleding | 2012-12-10 08:00 | 2013-02-01 17:00 | 30d |  | 0 | 0 | 419.9998 | 100799.9531 | 100799.9531 | 2013-09-23 08:00 | 30d | 100799.9531 | 0 | 0 | 0 | 0 | 100799.9531 | 0 | 100% | Finished | 100799.9531 | 100799.9531 | 100 | 100 | 100 | 100 | 100 | 100
12 | buitentrappen | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 933.9171 | 22414.0098 | 22414.0098 | 2013-10-14 08:00 | 2d | 14942.6732 | 0 | 0 | -5297.6038 | 0 | 9645.0693 | 0 | 100% | Finished | 22414.0098 | 22414.0098 | 100 | 66.6667 | 100 | 100 | 43.0314 | 100
13 | sanitair | 2013-01-28 08:00 | 2013-04-26 17:00 | 60d |  | 0 | 0 | 104.5608 | 50189.1992 | 50189.1992 | 2013-06-03 08:00 | 57d | 47679.7393 | 0 | 0 | -189.54 | 0 | 47490.1992 | 0 | 100% | Finished | 50189.1992 | 50189.1992 | 100 | 95 | 100 | 100 | 94.6223 | 100
14 | verwarmingsinstallaties | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 465.9245 | 93184.9062 | 93184.9062 | 2013-04-29 08:00 | 25d | 93184.9062 | 0 | 0 | 0 | 0 | 93184.9062 | 0 | 100% | Finished | 93184.9062 | 93184.9062 | 100 | 100 | 100 | 100 | 100 | 100
15 | electriciteit | 2013-01-28 08:00 | 2013-05-15 17:00 | 70d |  | 0 | 0 | 140.2473 | 78538.5 | 78538.5 | 2013-04-19 08:00 | 45d | 50489.0357 | 0 | 0 | 27265.4643 | 0 | 77754.5 | 0 | 100% | Finished | 78538.5 | 78538.5 | 100 | 64.2857 | 100 | 100 | 99.0018 | 100
16 | ventilatie | 2013-01-28 08:00 | 2013-03-01 17:00 | 25d |  | 0 | 0 | 185.395 | 37079 | 37079 | 2013-05-20 08:00 | 26d | 38562.16 | 0 | 0 | -256.16 | 0 | 38306 | 0 | 100% | Finished | 37079 | 37079 | 100 | 104 | 100 | 100 | 103.3092 | 100
17 | liftinstallatie | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 644.575 | 51566 | 51566 | 2013-04-22 08:00 | 10d | 51566 | 0 | 0 | -1127 | 0 | 50439 | 0 | 100% | Finished | 51566 | 51566 | 100 | 100 | 100 | 100 | 97.8145 | 100
18 | pleisterwerken | 2013-02-25 08:00 | 2013-05-08 17:00 | 45d |  | 0 | 0 | 59.9927 | 21597.3594 | 21597.3594 | 2013-06-24 08:00 | 25d | 11998.533 | 0 | 0 | 9598.8264 | 0 | 21597.3594 | 0 | 100% | Finished | 21597.3594 | 21597.3594 | 100 | 55.5556 | 100 | 100 | 100 | 100
19 | binnenplaatafwerking | 2013-03-11 08:00 | 2013-04-26 17:00 | 30d |  | 0 | 0 | 67.1083 | 16105.9902 | 16105.9902 | 2013-06-10 08:00 | 30d | 16105.9902 | 0 | 0 | -0.04 | 0 | 16105.9502 | 0 | 100% | Finished | 16105.9902 | 16105.9902 | 100 | 100 | 100 | 100 | 99.9998 | 100
20 | vloeren | 2013-04-22 08:00 | 2013-05-31 17:00 | 25d |  | 0 | 0 | 316.5197 | 63303.9414 | 63303.9414 | 2013-06-24 08:00 | 25d | 63303.9414 | 0 | 0 | 0 | 0 | 63303.9414 | 0 | 100% | Finished | 63303.9414 | 63303.9414 | 100 | 100 | 100 | 100 | 100 | 100
21 | binnendeuren &amp;amp;amp;amp; - ramen | 2013-05-20 08:00 | 2013-06-17 17:00 | 20d |  | 0 | 0 | 133.675 | 21388 | 21388 | 2013-10-01 08:00 | 20d | 21388 | 0 | 0 | 0 | 0 | 21388 | 0 | 100% | Finished | 21388 | 21388 | 100 | 100 | 100 | 100 | 100 | 100
22 | binnentrappen | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 36.7 | 2936 | 2936 | 2013-12-02 08:00 | 10d | 2936 | 0 | 0 | 0 | 0 | 2936 | 0 | 100% | Finished | 2936 | 2936 | 100 | 100 | 100 | 100 | 100 | 100
23 | keukeninstallatie | 2013-05-27 08:00 | 2013-06-21 17:00 | 20d |  | 0 | 0 | 313.7875 | 50206 | 50206 | 2013-10-01 08:00 | 19d 1h | 48009.4875 | 0 | 0 | 2196.5125 | 0 | 50206 | 0 | 100% | Finished | 50206 | 50206 | 100 | 95.625 | 100 | 100 | 100 | 100
24 | vast meubilair &amp;amp;amp;amp; faience | 2013-06-24 08:00 | 2013-07-05 17:00 | 10d |  | 0 | 0 | 101.5843 | 8126.7402 | 8126.7402 | 2013-10-18 08:00 | 10d | 8126.7402 | 0 | 0 | 0 | 0 | 8126.7402 | 0 | 100% | Finished | 8126.7402 | 8126.7402 | 100 | 100 | 100 | 100 | 100 | 100
25 | buitenverharding | 2012-06-25 08:00 | 2012-07-13 17:00 | 15d |  | 0 | 0 | 454.4128 | 54529.5312 | 54529.5312 | 2012-04-27 08:00 | 15d | 54529.5312 | 0 | 0 | -0.6 | 0 | 54528.9312 | 0 | 100% | Finished | 54529.5312 | 54529.5312 | 100 | 100 | 100 | 100 | 99.9989 | 100
26 | buitenafsluiting | 2012-11-12 08:00 | 2012-12-07 17:00 | 20d |  | 0 | 0 | 278.8446 | 44615.1406 | 44615.1406 | 2012-11-21 08:00 | 21d | 46845.8977 | 0 | 0 | -354.447 | 0 | 46491.4507 | 0 | 100% | Finished | 44615.1406 | 44615.1406 | 100 | 105 | 100 | 100 | 104.2055 | 100
27 | brievenbussen | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 133.75 | 2140 | 2140 | 2013-12-02 08:00 | 2d | 2140 | 0 | 0 | 0 | 0 | 2140 | 0 | 100% | Finished | 2140 | 2140 | 100 | 100 | 100 | 100 | 100 | 100
28 | fietsenrekken | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 43.75 | 700 | 700 | 2013-12-02 08:00 | 2d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
29 | tuinaanleg | 2013-04-08 08:00 | 2013-05-23 17:00 | 30d |  | 0 | 0 | 31.9385 | 7665.2402 | 7665.2402 | 2012-06-21 08:00 | 25d | 6387.7002 | 0 | 0 | 43.54 | 0 | 6431.2402 | 0 | 100% | Finished | 7665.2402 | 7665.2402 | 100 | 83.3333 | 100 | 100 | 83.9014 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2012-04-30
1:00 - 2:00 | No | Tuesday | Yes | 2012-05-01
2:00 - 3:00 | No | Wednesday | Yes | 2012-05-14
3:00 - 4:00 | No | Thursday | Yes | 2012-05-15
4:00 - 5:00 | No | Friday | Yes | 2012-05-16
5:00 - 6:00 | No | Saturday | No | 2012-05-17
6:00 - 7:00 | No | Sunday | No | 2012-05-18
7:00 - 8:00 | No |  |  | 2012-05-28
8:00 - 9:00 | Yes |  |  | 2012-07-16
9:00 - 10:00 | Yes |  |  | 2012-07-17
10:00 - 11:00 | Yes |  |  | 2012-07-18
11:00 - 12:00 | Yes |  |  | 2012-07-19
12:00 - 13:00 | No |  |  | 2012-07-20
13:00 - 14:00 | Yes |  |  | 2012-07-23
14:00 - 15:00 | Yes |  |  | 2012-07-24
15:00 - 16:00 | Yes |  |  | 2012-07-25
16:00 - 17:00 | Yes |  |  | 2012-07-26
17:00 - 18:00 | No |  |  | 2012-07-27
18:00 - 19:00 | No |  |  | 2012-07-30
19:00 - 20:00 | No |  |  | 2012-07-31
20:00 - 21:00 | No |  |  | 2012-08-01
21:00 - 22:00 | No |  |  | 2012-08-02
22:00 - 23:00 | No |  |  | 2012-08-03
23:00 - 0:00 | No |  |  | 2012-08-15
2012-10-29
2012-10-30
Generated by PMConverter v1.1.3 |  |  |  | 2012-10-31
2012-11-01
2012-11-02
2012-12-24
2012-12-25
2012-12-26
2012-12-27
2012-12-28
2012-12-31
2013-01-01
2013-01-02
2013-01-03
2013-01-04
2013-04-01
2013-04-02
2013-04-03
2013-04-04
2013-04-05
2013-05-01
2013-05-06
2013-05-07
2013-05-17
2013-05-24
2013-07-15
2013-07-16
2013-07-17
2013-07-18
2013-07-19
2013-07-22
2013-07-23
2013-07-24
2013-07-25
2013-07-26
2013-07-29
2013-07-30
2013-07-31
2013-08-01
2013-08-02
2013-08-15
2013-11-11
2013-10-28
2013-10-29
2013-10-30
2013-10-31
2013-11-01
2013-12-23
2013-12-24
2013-12-25
2013-12-26
2013-12-27
2013-12-30
2013-12-31
2014-01-01
2014-01-02
2014-01-03

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/04, 2012 | 2012-04-16 08:00 | 2012-04-30 09:00 | 19800 | 60634.4419 | 85203.3076 | 2012-05-23 15:00 | 40834.4419 | 306.2% | -24568.8657 | 71.16% | 10d 6h | 207.5% | 69.13% | 2013-06-25 12:00 | 2012-09-19 12:00 | 2012-11-15 11:00 | 2013-06-07 11:00 | 2012-09-19 12:00 | 2012-11-09 10:00 | 2013-06-21 10:00 | 2012-11-23 14:00 | 2013-02-14 12:00 | 1335292.3258 | 1841824.0638 | 493416.2274 | 687655.8465 | 658822.6878 | 931767.5275 | 1143001.094 | 1355211.9275 | 2.075 | 0.71164 | 3.0623 | 0.69131 | 10.75 | 0.71164 | 1 | 2.075 | 1
31/05, 2012 | 2012-04-30 09:00 | 2012-05-31 16:00 | 92226.8479 | 150700.9754 | 148645.5532 | 2012-06-26 16:00 | 58474.1275 | 163.4% | 2055.4222 | 101.4% | 18d | 169.6% | 80.13% | 2013-06-19 16:00 | 2013-01-25 16:00 | 2013-01-23 14:00 | 2013-06-13 14:00 | 2013-01-25 16:00 | 2013-01-23 17:00 | 2013-06-11 17:00 | 2013-01-17 16:00 | 2013-01-15 17:00 | 1308668.0379 | 1292846.4022 | 858562.7715 | 832761.3775 | 848880.156 | 823430.6693 | 1168116.4954 | 1157191.8709 | 1.6957 | 1.0138 | 1.634 | 0.80127 | 18 | 1.0138 | 1 | 1.6957 | 1
30/06, 2012 | 2012-05-31 16:00 | 2012-06-30 16:00 | 169270.0255 | 211900.3484 | 210595.5785 | 2012-07-11 12:00 | 42630.3229 | 125.2% | 1304.7699 | 100.6% | 7d 4h | 116% | 92.49% | 2013-06-25 09:00 | 2013-04-15 12:00 | 2013-04-12 09:00 | 2013-06-20 09:00 | 2013-04-15 12:00 | 2013-04-12 11:00 | 2013-06-26 12:00 | 2013-05-13 15:00 | 2013-05-10 12:00 | 1309418.6902 | 1302652.7207 | 1088356.3632 | 1158204.5005 | 1082951.5783 | 1152369.6278 | 1251812.2321 | 1270344.284 | 1.1596 | 1.0062 | 1.2518 | 0.92492 | 7.5 | 1.0062 | 1 | 1.1596 | 1
31/07, 2012 | 2012-06-30 16:00 | 2012-07-31 16:00 | 227045.4663 | 229863.9608 | 228759.4906 | 2012-08-07 11:00 | 2818.4945 | 101.2% | 1104.4701 | 100.5% | 1d 3h | 102.4% | 89.11% | 2013-07-05 11:00 | 2013-07-02 14:00 | 2013-07-01 11:00 | 2013-07-05 10:00 | 2013-07-02 14:00 | 2013-07-01 14:00 | 2013-07-04 14:00 | 2013-06-27 14:00 | 2013-06-26 14:00 | 1309618.9899 | 1304425.5832 | 1296365.9488 | 1284159.7726 | 1291236.2214 | 1279088.6945 | 1302803.9359 | 1300310.3962 | 1.0241 | 1.0048 | 1.0124 | 0.89108 | 1.375 | 1.0048 | 1 | 1.0241 | 1
31/08, 2012 | 2012-07-31 16:00 | 2012-08-31 09:00 | 265873.6025 | 272821.8798 | 271464.4613 | 2012-09-05 11:00 | 6948.2773 | 102.6% | 1357.4186 | 100.5% | 3d 2h | 104.3% | 90.86% | 2013-07-04 14:00 | 2013-06-27 09:00 | 2013-06-25 15:00 | 2013-07-03 17:00 | 2013-06-27 09:00 | 2013-06-26 09:00 | 2013-07-02 15:00 | 2013-06-20 15:00 | 2013-06-19 16:00 | 1309366.0415 | 1304201.9877 | 1282932.5752 | 1266327.0605 | 1277900.0405 | 1261377.1461 | 1299876.8435 | 1296398.0388 | 1.0433 | 1.005 | 1.0261 | 0.9086 | 3.25 | 1.005 | 1 | 1.0433 | 1
30/09, 2012 | 2012-08-31 09:00 | 2012-09-30 16:00 | 310592.9043 | 327221.8073 | 326531.3441 | 2012-10-10 16:00 | 16628.903 | 105.4% | 690.4632 | 100.2% | 7d 7h | 108.2% | 94.6% | 2013-07-02 12:00 | 2013-06-18 10:00 | 2013-06-17 14:00 | 2013-06-28 16:00 | 2013-06-18 10:00 | 2013-06-17 16:00 | 2013-06-26 09:00 | 2013-06-07 12:00 | 2013-06-07 09:00 | 1310032.9969 | 1307957.7326 | 1260052.9735 | 1235471.4997 | 1258083.1709 | 1233553.566 | 1297987.4503 | 1292550.1042 | 1.082 | 1.0021 | 1.0535 | 0.94605 | 7.875 | 1.0021 | 1 | 1.082 | 1
31/10, 2012 | 2012-09-30 16:00 | 2012-10-31 16:00 | 353437.7443 | 349469.9004 | 347661.5784 | 2012-10-25 09:00 | -3967.8439 | 98.88% | 1808.3219 | 100.5% | -1d 7h | 98.38% | 94.94% | 2013-07-08 16:00 | 2013-07-11 09:00 | 2013-07-09 14:00 | 2013-07-09 10:00 | 2013-07-11 09:00 | 2013-07-10 10:00 | 2013-07-09 16:00 | 2013-07-12 12:00 | 2013-07-11 14:00 | 1308915.1381 | 1303941.1593 | 1319829.1084 | 1324707.913 | 1314798.6555 | 1319652.2148 | 1307077.0683 | 1308023.5862 | 0.98384 | 1.0052 | 0.98877 | 0.94944 | -1.875 | 1.0052 | 1 | 0.98384 | 1
30/11, 2012 | 2012-10-31 16:00 | 2012-11-30 16:00 | 446143.1401 | 371874.3778 | 366368.7816 | 2012-11-12 14:00 | -74268.7624 | 83.35% | 5505.5962 | 101.5% | -14d 2h | 89.51% | 96.56% | 2013-08-20 11:00 | 2013-10-14 09:00 | 2013-10-07 10:00 | 2013-08-29 14:00 | 2013-10-14 09:00 | 2013-10-09 11:00 | 2013-08-19 10:00 | 2013-09-11 15:00 | 2013-09-09 10:00 | 1305217.8639 | 1291318.2132 | 1492719.7827 | 1415216.6258 | 1476044.168 | 1399688.4446 | 1325622.8435 | 1313699.4903 | 0.89512 | 1.015 | 0.83353 | 0.9656 | -14.25 | 1.015 | 1 | 0.89512 | 1
31/12, 2012 | 2012-11-30 16:00 | 2012-12-31 16:00 | 536473.0441 | 380497.8185 | 374404.5941 | 2012-11-14 10:00 | -155975.2257 | 70.93% | 6093.2244 | 101.6% | -27d 6h | 81.62% | 95.9% | 2013-09-12 10:00 | 2014-01-23 09:00 | 2014-01-14 17:00 | 2013-09-27 16:00 | 2014-01-23 09:00 | 2014-01-17 11:00 | 2013-09-05 15:00 | 2013-10-22 17:00 | 2013-10-18 09:00 | 1304630.2357 | 1289733.7677 | 1685952.1444 | 1514072.5201 | 1664949.2552 | 1495822.0807 | 1348594.2885 | 1327246.3311 | 0.81623 | 1.0163 | 0.70926 | 0.95903 | -27.75 | 1.0163 | 1 | 0.81623 | 1
31/01, 2013 | 2012-12-31 16:00 | 2013-01-31 16:00 | 680929.3584 | 383908.2988 | 377642.7425 | 2012-11-14 16:00 | -297021.0596 | 56.38% | 6265.5563 | 101.7% | -46d | 72.92% | 95.57% | 2013-10-23 11:00 | 2014-06-10 14:00 | 2014-05-29 16:00 | 2013-11-19 09:00 | 2014-06-10 14:00 | 2014-06-03 14:00 | 2013-10-01 17:00 | 2014-01-08 14:00 | 2013-12-20 11:00 | 1304457.9038 | 1289331.863 | 2021513.5707 | 1648623.3724 | 1994684.8586 | 1627880.3962 | 1378487.2956 | 1343965.5151 | 0.72921 | 1.0166 | 0.5638 | 0.95575 | -46 | 1.0166 | 1 | 0.72921 | 1
28/02, 2013 | 2013-01-31 16:00 | 2013-02-28 16:00 | 907753.6246 | 394938.4762 | 389299.2054 | 2012-11-16 17:00 | -512815.1484 | 43.51% | 5639.2708 | 101.4% | -63d 7h | 66.36% | 93.95% | 2014-01-15 17:00 | 2014-12-25 16:00 | 2014-12-12 17:00 | 2014-01-17 10:00 | 2014-12-25 16:00 | 2014-12-17 15:00 | 2013-10-25 16:00 | 2014-02-28 11:00 | 2014-02-25 10:00 | 1305084.1893 | 1292007.8247 | 2494202.0918 | 1769336.2992 | 2464146.4803 | 1749630.9442 | 1408419.9525 | 1359094.5633 | 0.66359 | 1.0145 | 0.43507 | 0.93955 | -63.875 | 1.0145 | 1 | 0.66359 | 1
31/03, 2013 | 2013-02-28 16:00 | 2013-03-31 16:00 | 1073594.9428 | 450411.1055 | 447330.9115 | 2012-12-03 14:00 | -623183.8374 | 41.95% | 3080.194 | 100.7% | -74d 3h | 64.75% | 89.91% | 2014-02-17 16:00 | 2015-01-27 17:00 | 2015-01-21 12:00 | 2014-02-07 12:00 | 2015-01-27 17:00 | 2015-01-22 17:00 | 2013-11-19 11:00 | 2014-03-14 12:00 | 2014-03-13 09:00 | 1307643.2661 | 1301759.9099 | 2497961.9504 | 1775974.3283 | 2483938.4475 | 1766888.2301 | 1414609.0871 | 1367440.3079 | 0.64751 | 1.0069 | 0.41954 | 0.8991 | -74.375 | 1.0069 | 1 | 0.64751 | 1
30/04, 2013 | 2013-03-31 16:00 | 2013-04-30 16:00 | 1142947.9174 | 544639.3553 | 553740.3177 | 2013-01-08 10:00 | -598308.5621 | 47.65% | -9100.9624 | 98.36% | -75d 5h | 66.81% | 77.32% | 2014-02-10 15:00 | 2014-10-10 15:00 | 2014-10-24 10:00 | 2014-02-04 10:00 | 2014-10-10 15:00 | 2014-10-20 11:00 | 2013-11-20 14:00 | 2014-02-25 14:00 | 2014-02-28 14:00 | 1319824.4225 | 1332625.7424 | 2161399.0806 | 1700350.5993 | 2188263.1729 | 1719510.5388 | 1422162.831 | 1386008.4263 | 0.66813 | 0.98356 | 0.47652 | 0.77316 | -75.625 | 0.98356 | 1 | 0.66813 | 1
31/05, 2013 | 2013-04-30 16:00 | 2013-05-31 16:00 | 1246638.8376 | 593085.9938 | 594983.1077 | 2013-01-17 11:00 | -653552.8438 | 47.57% | -1897.1139 | 99.68% | -86d 4h | 64.82% | 72.54% | 2014-02-26 09:00 | 2014-10-13 14:00 | 2014-10-15 12:00 | 2014-02-17 16:00 | 2014-10-13 14:00 | 2014-10-14 14:00 | 2013-12-05 12:00 | 2014-03-14 09:00 | 2014-03-14 14:00 | 1312620.574 | 1314916.0928 | 2103423.2769 | 1702114.791 | 2108248.3493 | 1705656.1914 | 1398969.7025 | 1369059.8814 | 0.6482 | 0.99681 | 0.47575 | 0.72539 | -86.5 | 0.99681 | 1 | 0.6482 | 1
30/06, 2013 | 2013-05-31 16:00 | 2013-06-30 09:00 | 1306660.09 | 729660.8784 | 726076.3988 | 2013-02-06 11:00 | -576999.2116 | 55.84% | 3584.4797 | 100.5% | -92d 5h | 65.18% | 75.88% | 2014-02-04 10:00 | 2014-06-17 10:00 | 2014-06-12 16:00 | 2014-01-31 12:00 | 2014-06-17 10:00 | 2014-06-16 10:00 | 2013-12-13 14:00 | 2014-03-11 15:00 | 2014-03-10 17:00 | 1307138.9804 | 1304284.4941 | 1766630.0418 | 1617569.6747 | 1761518.2927 | 1613190.1889 | 1360678.6086 | 1347994.9447 | 0.65179 | 1.0049 | 0.55842 | 0.75882 | -92.625 | 1.0049 | 1 | 0.65179 | 1
31/07, 2013 | 2013-06-30 09:00 | 2013-07-31 16:00 | 1310723.4601 | 796973.456 | 795528.6253 | 2013-02-13 10:00 | -513750.0041 | 60.8% | 1444.8307 | 100.2% | -97d 6h | 64.58% | 77.49% | 2014-01-16 10:00 | 2014-04-22 15:00 | 2014-04-21 16:00 | 2014-01-27 09:00 | 2014-05-02 16:00 | 2014-05-02 14:00 | 2013-12-20 15:00 | 2014-03-17 14:00 | 2014-03-17 11:00 | 1309278.6294 | 1308347.2536 | 1640455.364 | 1591012.5026 | 1638923.5989 | 1589570.3724 | 1352100.6528 | 1347580.1768 | 0.64583 | 1.0018 | 0.60804 | 0.77491 | -97.75 | 1.0018 | 1 | 0.64583 | 1
31/08, 2013 | 2013-07-31 16:00 | 2013-08-31 16:00 | 1310723.4601 | 828548.5512 | 830827.0169 | 2013-02-15 12:00 | -482174.9089 | 63.21% | -2278.4657 | 99.73% | -114d 4h | 61.19% | 75.71% | 2014-01-07 15:00 | 2014-03-28 15:00 | 2014-03-31 16:00 | 2014-02-21 12:00 | 2014-05-21 14:00 | 2014-05-22 09:00 | 2014-01-28 12:00 | 2014-04-17 16:00 | 2014-04-18 11:00 | 1313001.9258 | 1314327.8819 | 1593604.2423 | 1618869.1118 | 1595701.8403 | 1621036.1869 | 1352530.2213 | 1354828.2515 | 0.61186 | 0.99726 | 0.63213 | 0.75707 | -114.5 | 0.99726 | 1 | 0.61186 | 1
30/09, 2013 | 2013-08-31 16:00 | 2013-09-30 16:00 | 1310723.4601 | 963428.5249 | 968668.4916 | 2013-03-11 16:00 | -347294.9352 | 73.5% | -5239.9667 | 99.46% | -119d | 62.33% | 82.14% | 2013-11-14 15:00 | 2013-12-20 15:00 | 2014-01-07 15:00 | 2014-02-17 14:00 | 2014-03-31 15:00 | 2014-04-01 11:00 | 2014-02-03 17:00 | 2014-04-07 15:00 | 2014-04-08 12:00 | 1315963.4268 | 1317852.3203 | 1441155.6635 | 1525883.9209 | 1443725.4619 | 1528914.5456 | 1337080.9873 | 1346029.1967 | 0.62327 | 0.99459 | 0.73504 | 0.82139 | -119 | 0.99459 | 1 | 0.62327 | 1
31/10, 2013 | 2013-09-30 16:00 | 2013-10-31 09:00 | 1310723.4601 | 1101575.615 | 1096390.2516 | 2013-04-18 14:00 | -209147.8451 | 84.04% | 5185.3634 | 100.5% | -115d 3h | 65.56% | 85.57% | 2013-09-27 10:00 | 2013-10-09 12:00 | 2013-10-07 16:00 | 2014-01-31 12:00 | 2014-02-14 14:00 | 2014-02-14 10:00 | 2014-01-29 11:00 | 2014-03-07 11:00 | 2014-03-06 17:00 | 1305538.0967 | 1304553.5909 | 1345247.4189 | 1415409.1615 | 1344075.9924 | 1413907.468 | 1311591.6595 | 1320100.9967 | 0.6556 | 1.0047 | 0.84043 | 0.85566 | -115.375 | 1.0047 | 1 | 0.6556 | 1
30/11, 2013 | 2013-10-31 09:00 | 2013-11-30 16:00 | 1310723.4601 | 1214681.3605 | 1206014.12 | 2013-05-23 11:00 | -96042.0996 | 92.67% | 8667.2404 | 100.7% | -113d 5h | 67.9% | 93.13% | 2013-08-26 16:00 | 2013-08-28 11:00 | 2013-08-26 11:00 | 2014-01-20 17:00 | 2014-01-22 17:00 | 2014-01-22 15:00 | 2014-01-27 14:00 | 2014-02-17 09:00 | 2014-02-14 15:00 | 1302056.2196 | 1301370.9206 | 1309650.0506 | 1347455.2153 | 1308910.5665 | 1346445.9761 | 1302919.2056 | 1308017.8879 | 0.67903 | 1.0072 | 0.92673 | 0.9313 | -113.625 | 1.0072 | 1 | 0.67903 | 1
Actual Schedule | 2013-11-30 16:00 | 2013-12-31 16:00 | 1310723.4601 | 1310723.4601 | 1282185.9797 | 2013-07-05 17:00 | 0 | 100% | 28537.4804 | 102.2% | -98d | 73.44% | 100% | 2013-07-05 17:00 | 2013-07-05 17:00 | 2013-06-28 09:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 1282185.9797 | 1282185.9797 | 1282185.9797 | 1282185.9797 | 1282185.9797 | 1282185.9797 | 1282185.9797 | 1282185.9797 | 0.73442 | 1.0223 | 1 | 1 | -98 | 1.0223 | 1 | 0.73442 | 1