## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Social Apartments Ypres (3) | 1 |  |  | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 | 570.375
1 | werfinrichting | 1.1 |  |  | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 13.375
2 | aanvraag verslag Bom.be | 1.2 |  |  | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 43.375
3 | grondwerken + bom detectie | 1.3 |  | FS4 | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 28.375
4 | paalfundering | 1.4 | 3FS | FS5;FS6;FS7 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 11.375
5 | afkappen palen | 1.5 | 4FS |  | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 4.375
6 | rioleringwerken onder fundering | 1.6 | 4FS |  | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 4.375
7 | funderingsplaat (bekisten, ijzer, beton) | 1.7 | 4FS | FS9 | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 32.375
8 | montage kraan | 1.8 |  |  | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 0.375
9 | kelderwanden | 1.9 | 7FS | SS10+2w | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 21.375
10 | kolommen + balken + metalen profielen kelder | 1.10 | 9SS+2w | SS11+1w | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 16.375
11 | metselwerk kelderverdieping | 1.11 | 10SS+1w | FS12 | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 16.375
12 | afdek kelder + balken | 1.12 | 11FS | FS13 | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 13.375
13 | wanden gelijkvloers | 1.13 | 12FS | FS17-1w | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 17.375
14 | binnenzetten bouwmaterialen | 1.14 |  |  | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2.375
15 | verwarming helling | 1.15 |  |  | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 0.375
16 | helling - vloer en wanden | 1.16 |  |  | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 18.375
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 1.17 | 13FS-1w | FS18 | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 13.375
18 | wanden 1ste verdiep | 1.18 | 17FS | FS20-1w | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 36.375
19 | binnenzetten bouwmaterialen | 1.19 |  |  | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 4.375
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 1.20 | 18FS-1w | FS23;SS22+1w | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 34.375
21 | stelling plaatsen | 1.21 | 22SF+1w |  | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 11.375
22 | gevelmetselwerk + blauwe hardsteen | 1.22 | 20SS+1w | FS37;SF41+1w;SF21+1w;FS35-1w | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 109.375
23 | wanden 2de verdiep | 1.23 | 20FS | SS25;FS26-1w | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 15.375
24 | binnenzetten bouwmaterialen | 1.24 |  |  | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2.375
25 | prefabmontage | 1.25 | 23SS | FS36;SF38+1d | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 | 102.375
26 | afdek 2de verdiep (dakplaat) + balken | 1.26 | 23FS-1w | FS27 | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 13.375
27 | dakranden Ytong | 1.27 | 26FS | FS28 | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 | 6.375
28 | Hellingsbeton + dakverdichting | 1.28 | 27FS | FS29;FS30 | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 | 13.375
29 | dakverdicting-eindlaag | 1.29 | 28FS |  | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 | 6.375
30 | binnenwanden niv 0/1/2 | 1.30 | 28FS | SS53+1w;SS31+1w | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 | 48.375
53 | leiding technieken - sanitair | 1.31 | 30SS+1w | SS32+1w | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 | 48.375
31 | leidingen technieken - electriciteit | 1.32 | 30SS+1w | SS32+1w | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 | 48.375
32 | chape | 1.33 | 31SS+1w;53SS+1w | FS40;SS33+2w | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 | 42.375
33 | pleisterwerken | 1.34 | 32SS+2w | FS43 | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 | 55.375
34 | leuningen | 1.35 | 37SS-2w |  | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 | 13.375
35 | voegwerken | 1.36 | 22FS-1w |  | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 | 27.375
36 | dakverdichting boven trapzalen | 1.37 | 25FS |  | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 6.375
37 | stelling afbreken | 1.38 | 22FS | SS34-2w | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 | 3.375
38 | afbreken torenkraan | 1.39 | 25SF+1d | FS39 | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 0.375
39 | buitenaanleg - ABM | 1.40 | 38FS |  | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 | 27.375
40 | tegelwerken | 1.41 | 32FS | FS44+3w;FS46;FS54;SS42+2w | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 | 55.375
41 | buitenschrijnwerk | 1.42 | 22SF+1w |  | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 | 13.375
42 | binnenschrijnwerk | 1.43 | 40SS+2w |  | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 | 48.375
43 | schilderwerk | 1.44 | 33FS |  | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 | 55.375
44 | keukens | 1.45 | 40FS+3w |  | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 | 27.375
45 | lift | 1.46 |  |  | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 | 20.375
46 | afwerken technieken - sanitair | 1.47 | 40FS | FS47 | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 | 27.375
54 | afwerken technieken - electriciteit | 1.48 | 40FS | FS47 | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 | 27.375
47 | algemene opkuis | 1.49 | 46FS;54FS |  | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 | 14.375
48 | datum contract zonder VAA | 1.50 |  |  | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
49 | in orde brengen punten voor voorlopige oplevering | 1.51 |  |  | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 | 43.375
50 | oplevering contract + VAA-1-43 KD | 1.52 |  |  | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 0.375
51 | buitenaanleg - bouwheer | 1.53 |  |  | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Social Apartments Ypres (3) | 2864h |  |  |  |  | 99 | 100 | 101
1 | werfinrichting | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | aanvraag verslag Bom.be | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | grondwerken + bom detectie | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | paalfundering | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | afkappen palen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | rioleringwerken onder fundering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | funderingsplaat (bekisten, ijzer, beton) | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | montage kraan | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | kelderwanden | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | kolommen + balken + metalen profielen kelder | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | metselwerk kelderverdieping | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | afdek kelder + balken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | wanden gelijkvloers | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | binnenzetten bouwmaterialen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | verwarming helling | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | helling - vloer en wanden | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | wanden 1ste verdiep | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | binnenzetten bouwmaterialen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | stelling plaatsen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | gevelmetselwerk + blauwe hardsteen | 600h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | wanden 2de verdiep | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | binnenzetten bouwmaterialen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | prefabmontage | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | afdek 2de verdiep (dakplaat) + balken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | dakranden Ytong | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Hellingsbeton + dakverdichting | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | dakverdicting-eindlaag | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | binnenwanden niv 0/1/2 | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | leiding technieken - sanitair | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | leidingen technieken - electriciteit | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | chape | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | pleisterwerken | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | leuningen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | voegwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | dakverdichting boven trapzalen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | stelling afbreken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | afbreken torenkraan | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | buitenaanleg - ABM | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | tegelwerken | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | buitenschrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | binnenschrijnwerk | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | schilderwerk | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | keukens | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | lift | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | afwerken technieken - sanitair | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | afwerken technieken - electriciteit | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | algemene opkuis | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | datum contract zonder VAA | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | in orde brengen punten voor voorlopige oplevering | 256h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | oplevering contract + VAA-1-43 KD | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | buitenaanleg - bouwheer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-11-30 17:00 |  | TP Name | 30/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 14d | [5 empty] | 110 |  | 0.004022% |  | 100.9091 | 100.9091
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 2d | 0.90909 | 9.0909 | 20d | 9.0909 | 0 | 10 | 9.0909 | 9.091% | Started | 0.90909 | 0.90909 | 100 | 9.0909 | 9.0909 | 100 | 100 | 9.0909
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 |  | 0 | 0 | 91355.7031 | 21d | 0 | 0 | 0 | 91355.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 |  | 0 | 0 | 43580.25 | 10d | 0 | 0 | 0 | 43580.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 |  | 0 | 0 | 15568.9102 | 5d | 0 | 0 | 0 | 15568.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 |  | 0 | 0 | 107573.8125 | 20d | 0 | 0 | 0 | 107573.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 |  | 0 | 0 | 112336.2891 | 15d | 0 | 0 | 0 | 112336.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 |  | 0 | 0 | 23087.9004 | 10d | 0 | 0 | 0 | 23087.9004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 |  | 0 | 0 | 26678.2207 | 10d | 0 | 0 | 0 | 26678.2207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 |  | 0 | 0 | 1 | 15d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 |  | 0 | 0 | 117171.25 | 75d | 0 | 0 | 0 | 117171.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 |  | 0 | 0 | 541678.4375 | 70d | 0 | 0 | 0 | 541678.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 |  | 0 | 0 | 14570.25 | 5d | 0 | 0 | 0 | 14570.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 |  | 0 | 0 | 35815.7695 | 10d | 0 | 0 | 0 | 35815.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 |  | 0 | 0 | 74525.4297 | 5d | 0 | 0 | 0 | 74525.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 |  | 0 | 0 | 264787.6875 | 30d | 0 | 0 | 0 | 264787.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 |  | 0 | 0 | 97978.7969 | 30d | 0 | 0 | 0 | 97978.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-12-31 16:00 |  | TP Name | 31/12, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 29d | [5 empty] | 110 |  | 0.004294% |  | 107.7273 | 107.7273
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 17d | 7.7273 | 2.2727 | 5d | 2.2727 | 0 | 10 | 2.2727 | 77.27% | Started | 7.7273 | 7.7273 | 100 | 77.2727 | 77.2727 | 100 | 100 | 77.2727
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 |  | 0 | 0 | 91355.7031 | 21d | 0 | 0 | 0 | 91355.7031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 |  | 0 | 0 | 43580.25 | 10d | 0 | 0 | 0 | 43580.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 |  | 0 | 0 | 15568.9102 | 5d | 0 | 0 | 0 | 15568.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 |  | 0 | 0 | 107573.8125 | 20d | 0 | 0 | 0 | 107573.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 |  | 0 | 0 | 112336.2891 | 15d | 0 | 0 | 0 | 112336.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 |  | 0 | 0 | 23087.9004 | 10d | 0 | 0 | 0 | 23087.9004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 |  | 0 | 0 | 26678.2207 | 10d | 0 | 0 | 0 | 26678.2207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 |  | 0 | 0 | 1 | 15d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 |  | 0 | 0 | 117171.25 | 75d | 0 | 0 | 0 | 117171.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 |  | 0 | 0 | 541678.4375 | 70d | 0 | 0 | 0 | 541678.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 |  | 0 | 0 | 14570.25 | 5d | 0 | 0 | 0 | 14570.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 |  | 0 | 0 | 35815.7695 | 10d | 0 | 0 | 0 | 35815.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 |  | 0 | 0 | 74525.4297 | 5d | 0 | 0 | 0 | 74525.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 |  | 0 | 0 | 264787.6875 | 30d | 0 | 0 | 0 | 264787.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 |  | 0 | 0 | 97978.7969 | 30d | 0 | 0 | 0 | 97978.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-01-31 16:00 |  | TP Name | 31/01, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 47d 7h | [5 empty] | 44302.3438 |  | 2.583% |  | 64820.2879 | 21317.5739
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 26645.4134 | 6d 1h | -20517.946 | 0 | 44192.3438 | 26645.4134 | 70.83% | Started | 64710.2879 | 21207.5739 | 100 | 70.8333 | 70.8333 | 100 | 48.3739 | 70.8333
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 |  | 0 | 0 | 43580.25 | 10d | 0 | 0 | 0 | 43580.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 |  | 0 | 0 | 15568.9102 | 5d | 0 | 0 | 0 | 15568.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 |  | 0 | 0 | 107573.8125 | 20d | 0 | 0 | 0 | 107573.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 |  | 0 | 0 | 112336.2891 | 15d | 0 | 0 | 0 | 112336.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 |  | 0 | 0 | 23087.9004 | 10d | 0 | 0 | 0 | 23087.9004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 |  | 0 | 0 | 26678.2207 | 10d | 0 | 0 | 0 | 26678.2207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 |  | 0 | 0 | 1 | 15d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 |  | 0 | 0 | 117171.25 | 75d | 0 | 0 | 0 | 117171.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 |  | 0 | 0 | 541678.4375 | 70d | 0 | 0 | 0 | 541678.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 |  | 0 | 0 | 14570.25 | 5d | 0 | 0 | 0 | 14570.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 |  | 0 | 0 | 35815.7695 | 10d | 0 | 0 | 0 | 35815.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 |  | 0 | 0 | 74525.4297 | 5d | 0 | 0 | 0 | 74525.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 |  | 0 | 0 | 264787.6875 | 30d | 0 | 0 | 0 | 264787.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 |  | 0 | 0 | 97978.7969 | 30d | 0 | 0 | 0 | 97978.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-02-28 16:00 |  | TP Name | 28/02, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 67d 7h | [5 empty] | 135046.9531 |  | 5.382% |  | 135046.9531 | 108353.05
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 16887.3469 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 |  | 0 | 0 | 15568.9102 | 5d | 0 | 0 | 0 | 15568.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 |  | 0 | 0 | 107573.8125 | 20d | 0 | 0 | 0 | 107573.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 |  | 0 | 0 | 112336.2891 | 15d | 0 | 0 | 0 | 112336.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 |  | 0 | 0 | 23087.9004 | 10d | 0 | 0 | 0 | 23087.9004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 |  | 0 | 0 | 26678.2207 | 10d | 0 | 0 | 0 | 26678.2207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 |  | 0 | 0 | 1 | 15d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 |  | 0 | 0 | 117171.25 | 75d | 0 | 0 | 0 | 117171.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 |  | 0 | 0 | 541678.4375 | 70d | 0 | 0 | 0 | 541678.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 |  | 0 | 0 | 14570.25 | 5d | 0 | 0 | 0 | 14570.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 |  | 0 | 0 | 35815.7695 | 10d | 0 | 0 | 0 | 35815.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 |  | 0 | 0 | 74525.4297 | 5d | 0 | 0 | 0 | 74525.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 |  | 0 | 0 | 264787.6875 | 30d | 0 | 0 | 0 | 264787.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 |  | 0 | 0 | 97978.7969 | 30d | 0 | 0 | 0 | 97978.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-03-31 16:00 |  | TP Name | 31/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 89d | [5 empty] | 331829.9043 |  | 12.7% |  | 318724.007 | 231297.2227
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 80680.3594 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 5d | 37445.4297 | 74890.8594 | 10d | 13105.8984 | 0 | 50551.3281 | 74890.8594 | 33.33% | Started | 37445.4308 | 0 | 100 | 33.3333 | 33.3333 | 100 | 45 | 33.3333
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 0 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 |  | 0 | 0 | 26678.2207 | 10d | 0 | 0 | 0 | 26678.2207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 |  | 0 | 0 | 1 | 15d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 |  | 0 | 0 | 117171.25 | 75d | 0 | 0 | 0 | 117171.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 |  | 0 | 0 | 541678.4375 | 70d | 0 | 0 | 0 | 541678.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 |  | 0 | 0 | 14570.25 | 5d | 0 | 0 | 0 | 14570.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 |  | 0 | 0 | 35815.7695 | 10d | 0 | 0 | 0 | 35815.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 |  | 0 | 0 | 74525.4297 | 5d | 0 | 0 | 0 | 74525.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 |  | 0 | 0 | 264787.6875 | 30d | 0 | 0 | 0 | 264787.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 |  | 0 | 0 | 97978.7969 | 30d | 0 | 0 | 0 | 97978.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-04-30 16:00 |  | TP Name | 30/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 105d 7h | [5 empty] | 420294.0859 |  | 16.75% |  | 420294.0859 | 351452.5526
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 88932.8955 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 4328.9813 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 0 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 |  | 0 | 0 | 1 | 15d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 |  | 0 | 0 | 117171.25 | 75d | 0 | 0 | 0 | 117171.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 |  | 0 | 0 | 541678.4375 | 70d | 0 | 0 | 0 | 541678.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 |  | 0 | 0 | 14570.25 | 5d | 0 | 0 | 0 | 14570.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 |  | 0 | 0 | 35815.7695 | 10d | 0 | 0 | 0 | 35815.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 |  | 0 | 0 | 74525.4297 | 5d | 0 | 0 | 0 | 74525.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 |  | 0 | 0 | 264787.6875 | 30d | 0 | 0 | 0 | 264787.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 |  | 0 | 0 | 97978.7969 | 30d | 0 | 0 | 0 | 97978.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-05-31 16:00 |  | TP Name | 31/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 124d 7h | [5 empty] | 519338.3281 |  | 20.7% |  | 519338.3281 | 420293.6734
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 112336.2891 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 23087.9004 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 26678.2207 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0.5875 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 0 | 100 | 41.6667 | 100 | 100 | 100 | 100
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 66.6667 | 100 | 100 | 100 | 100
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 66.6667 | 100 | 100 | 100 | 100
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 50 | 100 | 100 | 100 | 100
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 0 | 100 | 33.3333 | 100 | 100 | 100 | 100
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 50 | 100 | 100 | 100 | 100
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 |  | 0 | 0 | 117171.25 | 75d | 0 | 0 | 0 | 117171.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 |  | 0 | 0 | 49470.1211 | 12d | 0 | 0 | 0 | 49470.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 |  | 0 | 0 | 1 | 3d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 |  | 0 | 0 | 541678.4375 | 70d | 0 | 0 | 0 | 541678.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 |  | 0 | 0 | 14570.25 | 5d | 0 | 0 | 0 | 14570.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 |  | 0 | 0 | 35815.7695 | 10d | 0 | 0 | 0 | 35815.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 |  | 0 | 0 | 74525.4297 | 5d | 0 | 0 | 0 | 74525.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 |  | 0 | 0 | 264787.6875 | 30d | 0 | 0 | 0 | 264787.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 |  | 0 | 0 | 97978.7969 | 30d | 0 | 0 | 0 | 97978.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2013-06-30 16:00 |  | TP Name | 30/06, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 145d | [5 empty] | 630470.1484 |  | 23.31% |  | 584973.0009 | 469867.107
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 112336.2891 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 23087.9004 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 26678.2207 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 0.9 | 100 | 50 | 100 | 100 | 100 | 100
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 0 | 100 | 33.3333 | 100 | 100 | 100 | 100
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-03 08:00 | 3d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-06-03 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 50 | 100 | 100 | 100 | 100
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 50 | 100 | 100 | 100 | 100
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 2013-06-19 08:00 | 8d | 12498.2667 | 78114.1667 | 50d | 49160.4326 | 0 | 61658.6992 | 78114.1667 | 13.79% | Started | 16161.5517 | 0 | 100 | 10.6667 | 13.7931 | 100 | 52.6227 | 13.7931
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-06-24 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 0 | 100 | 41.6667 | 100 | 100 | 100 | 100
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-24 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 66.6667 | 100 | 100 | 100 | 100
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 |  | 0 | 0 | 541678.4375 | 70d | 0 | 0 | 0 | 541678.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 |  | 0 | 0 | 14570.25 | 5d | 0 | 0 | 0 | 14570.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 |  | 0 | 0 | 35815.7695 | 10d | 0 | 0 | 0 | 35815.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 |  | 0 | 0 | 74525.4297 | 5d | 0 | 0 | 0 | 74525.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 |  | 0 | 0 | 264787.6875 | 30d | 0 | 0 | 0 | 264787.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 |  | 0 | 0 | 97978.7969 | 30d | 0 | 0 | 0 | 97978.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2013-07-31 09:00 |  | TP Name | 31/07, 13
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 155d | [5 empty] | 1042363.0083 |  | 36.18% |  | 907858.5161 | 506970.9979
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 112336.2891 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 23087.9004 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 26678.2207 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 37102.5908 | 100 | 33.3333 | 100 | 100 | 100 | 100
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-03 08:00 | 3d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-06-03 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 0.2 | 100 | 50 | 100 | 100 | 100 | 100
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 50 | 100 | 100 | 100 | 100
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 2013-06-19 08:00 | 20d | 31245.6667 | 31245.6667 | 20d | 75002.8831 | 0 | 106248.5498 | 31245.6667 | 50% | Started | 58585.625 | 0 | 100 | 26.6667 | 50 | 100 | 90.678 | 50
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-06-24 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 0 | 100 | 41.6667 | 100 | 100 | 100 | 100
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-24 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 66.6667 | 100 | 100 | 100 | 100
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 | 2013-07-01 08:00 | 10d | 77382.6339 | 386913.1696 | 50d | 68782.8036 | 0 | 146165.4375 | 386913.1696 | 16.67% | Started | 90279.7423 | 0 | 100 | 14.2857 | 16.6667 | 100 | 26.9838 | 16.6667
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-07-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 | 2013-07-01 08:00 | 5d | 14570.25 | 0 | 0 | 0 | 0 | 14570.25 | 0 | 100% | Finished | 14570.25 | 0 | 100 | 100 | 100 | 100 | 100 | 100
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 | 2013-07-08 08:00 | 5d | 17907.8848 | 3581.577 | 1d | 16415.6948 | 0 | 34323.5796 | 3581.577 | 83.33% | Started | 29846.4739 | 0 | 100 | 50 | 83.3333 | 100 | 95.8337 | 83.3333
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 | 2013-07-11 08:00 | 2d | 29810.1719 | 59620.3438 | 4d | 19900.457 | 0 | 49710.6289 | 59620.3438 | 33.33% | Started | 24841.8106 | 0 | 100 | 40 | 33.3333 | 100 | 66.7029 | 33.3333
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 |  | 0 | 0 | 95040.0625 | 30d | 0 | 0 | 0 | 95040.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 | 2013-07-01 08:00 | 10d | 88262.5625 | 176525.125 | 20d | -9960.875 | 0 | 78301.6875 | 176525.125 | 33.33% | Started | 88262.5651 | 0 | 100 | 33.3333 | 33.3333 | 100 | 29.5715 | 33.3333
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 | 2013-07-01 08:00 | 10d | 32659.599 | 65319.1979 | 20d | 11570.8268 | 0 | 44230.4258 | 65319.1979 | 33.33% | Started | 32659.5999 | 0 | 100 | 33.3333 | 33.3333 | 100 | 45.1429 | 33.3333
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 |  | 0 | 0 | 62467.8398 | 30d | 0 | 0 | 0 | 62467.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 |  | 0 | 0 | 66856.1484 | 30d | 0 | 0 | 0 | 66856.1484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 |  | 0 | 0 | 3896.05 | 10d | 0 | 0 | 0 | 3896.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2013-08-31 16:00 |  | TP Name | 31/08, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 173d | [5 empty] | 1604691.2698 |  | 58.02% |  | 1455628.6559 | 527151.7448
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 112336.2891 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 23087.9004 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 26678.2207 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 33.3333 | 100 | 100 | 100 | 100
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-03 08:00 | 3d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-06-03 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 2013-06-19 08:00 | 35d | 54679.9167 | 7811.4167 | 5d | 58398.7533 | 0 | 113078.6699 | 7811.4167 | 87.5% | Started | 102524.8438 | 7811.4167 | 100 | 46.6667 | 87.5 | 100 | 96.5072 | 87.5
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-06-24 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 0 | 100 | 41.6667 | 100 | 100 | 100 | 100
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-24 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 66.6667 | 100 | 100 | 100 | 100
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 | 2013-07-01 08:00 | 30d | 232147.9018 | 116073.9509 | 15d | 222095.5357 | 0 | 454243.4375 | 116073.9509 | 66.67% | Started | 361118.9691 | 0 | 100 | 42.8571 | 66.6667 | 100 | 83.8585 | 66.6667
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-07-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 | 2013-07-01 08:00 | 5d | 14570.25 | 0 | 0 | 0 | 0 | 14570.25 | 0 | 100% | Finished | 14570.25 | 0 | 100 | 100 | 100 | 100 | 100 | 100
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 | 2013-07-08 08:00 | 7d | 25071.0387 | 0 | 0 | 10744.7309 | 0 | 35815.7695 | 0 | 100% | Finished | 35815.7695 | 0 | 100 | 70 | 100 | 100 | 100 | 100
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 | 2013-07-11 08:00 | 7d | 104335.6016 | 0 | 0 | -29810.1719 | 0 | 74525.4297 | 0 | 100% | Finished | 74525.4297 | 0 | 100 | 140 | 100 | 100 | 100 | 100
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 | 2013-08-05 08:00 | 18d | 57024.0375 | 0 | 0 | 38016.025 | 0 | 95040.0625 | 0 | 100% | Finished | 95040.0625 | 0 | 100 | 60 | 100 | 100 | 100 | 100
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 | 2013-07-01 08:00 | 10d | 88262.5625 | 176525.125 | 20d | -9960.875 | 0 | 78301.6875 | 176525.125 | 33.33% | Started | 88262.5651 | 0 | 100 | 33.3333 | 33.3333 | 100 | 29.5715 | 33.3333
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 | 2013-07-01 08:00 | 10d | 32659.599 | 65319.1979 | 20d | 11570.8268 | 0 | 44230.4258 | 65319.1979 | 33.33% | Started | 32659.5999 | 0 | 100 | 33.3333 | 33.3333 | 100 | 45.1429 | 33.3333
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 | 2013-08-05 08:00 | 18d | 37480.7039 | 0 | 0 | 24987.1359 | 0 | 62467.8398 | 0 | 100% | Finished | 62467.8398 | 0 | 100 | 60 | 100 | 100 | 100 | 100
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 | 2013-08-26 08:00 | 5d | 11142.6914 | 33428.0742 | 15d | 48566.5068 | 0 | 59709.1982 | 33428.0742 | 25% | Started | 16714.0371 | 0 | 100 | 16.6667 | 25 | 100 | 89.31 | 25
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 |  | 0 | 0 | 116780.3203 | 10d | 0 | 0 | 0 | 116780.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 | 2013-08-21 08:00 | 8d | 3116.84 | 779.21 | 2d | 779.21 | 0 | 3896.05 | 779.21 | 80% | Started | 3116.8401 | 0 | 100 | 80 | 80 | 100 | 100 | 80
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2013-09-30 16:00 |  | TP Name | 30/09, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 193d 7h | [5 empty] | 1869633.5217 |  | 72.86% |  | 1828075.928 | 782064.7225
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 112336.2891 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 23087.9004 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 26678.2207 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 33.3333 | 100 | 100 | 100 | 100
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-03 08:00 | 3d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-06-03 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 2013-06-19 08:00 | 41d | 64053.6167 | 0 | 0 | 53117.6333 | 0 | 117171.25 | 0 | 100% | Finished | 117171.25 | 40424.0813 | 100 | 54.6667 | 100 | 100 | 100 | 100
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-06-24 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-24 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 | 2013-07-01 08:00 | 42d | 325007.0625 | 0 | 0 | 216671.375 | 0 | 541678.4375 | 0 | 100% | Finished | 541678.4375 | 161536.2483 | 100 | 60 | 100 | 100 | 100 | 100
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-07-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 | 2013-07-01 08:00 | 5d | 14570.25 | 0 | 0 | 0 | 0 | 14570.25 | 0 | 100% | Finished | 14570.25 | 11291.9438 | 100 | 100 | 100 | 100 | 100 | 100
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 | 2013-07-08 08:00 | 7d | 25071.0387 | 0 | 0 | 10744.7309 | 0 | 35815.7695 | 0 | 100% | Finished | 35815.7695 | 0 | 100 | 70 | 100 | 100 | 100 | 100
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 | 2013-07-11 08:00 | 7d | 104335.6016 | 0 | 0 | -29810.1719 | 0 | 74525.4297 | 0 | 100% | Finished | 74525.4297 | 0 | 100 | 140 | 100 | 100 | 100 | 100
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 | 2013-08-05 08:00 | 18d | 57024.0375 | 0 | 0 | 38016.025 | 0 | 95040.0625 | 0 | 100% | Finished | 95040.0625 | 0 | 100 | 60 | 100 | 100 | 100 | 100
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 | 2013-07-01 08:00 | 15d | 132393.8438 | 132393.8438 | 15d | -18913.1562 | 0 | 113480.6875 | 132393.8438 | 50% | Started | 132393.8438 | 0 | 100 | 50 | 50 | 100 | 42.8572 | 50
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 | 2013-07-01 08:00 | 15d | 48989.3984 | 48989.3984 | 15d | 16696.3789 | 0 | 65685.7773 | 48989.3984 | 50% | Started | 48989.3984 | 0 | 100 | 50 | 50 | 100 | 67.0408 | 50
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 | 2013-08-05 08:00 | 18d | 37480.7039 | 0 | 0 | 24987.1359 | 0 | 62467.8398 | 0 | 100% | Finished | 62467.8398 | 0 | 100 | 60 | 100 | 100 | 100 | 100
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 | 2013-08-26 08:00 | 5d | 11142.6914 | 33428.0742 | 15d | 48566.5068 | 0 | 59709.1982 | 33428.0742 | 25% | Started | 16714.0371 | 0 | 100 | 16.6667 | 25 | 100 | 89.31 | 25
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 | 2013-09-16 08:00 | 10d | 116780.3203 | 0 | 0 | 0 | 0 | 116780.3203 | 0 | 100% | Finished | 116780.3203 | 0 | 100 | 100 | 100 | 100 | 100 | 100
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 |  | 0 | 0 | 3595.29 | 20d | 0 | 0 | 0 | 3595.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 | 2013-08-21 08:00 | 8d | 3116.84 | 779.21 | 2d | 779.21 | 0 | 3896.05 | 779.21 | 80% | Started | 3116.8401 | 0 | 100 | 80 | 80 | 100 | 100 | 80
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2013-10-31 16:00 |  | TP Name | 31/10, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 213d | [5 empty] | 1966210.6914 |  | 78.37% |  | 1966245.8388 | 1060652.4196
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 112336.2891 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 23087.9004 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 26678.2207 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 33.3333 | 100 | 100 | 100 | 100
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-03 08:00 | 3d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-06-03 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 2013-06-19 08:00 | 41d | 64053.6167 | 0 | 0 | 53117.6333 | 0 | 117171.25 | 0 | 100% | Finished | 117171.25 | 70302.75 | 100 | 54.6667 | 100 | 100 | 100 | 100
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-06-24 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-24 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 | 2013-07-01 08:00 | 42d | 325007.0625 | 0 | 0 | 216671.375 | 0 | 541678.4375 | 0 | 100% | Finished | 541678.4375 | 309530.5357 | 100 | 60 | 100 | 100 | 100 | 100
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-07-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 | 2013-07-01 08:00 | 5d | 14570.25 | 0 | 0 | 0 | 0 | 14570.25 | 0 | 100% | Finished | 14570.25 | 14570.25 | 100 | 100 | 100 | 100 | 100 | 100
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 | 2013-07-08 08:00 | 7d | 25071.0387 | 0 | 0 | 10744.7309 | 0 | 35815.7695 | 0 | 100% | Finished | 35815.7695 | 35815.7695 | 100 | 70 | 100 | 100 | 100 | 100
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 | 2013-07-11 08:00 | 7d | 104335.6016 | 0 | 0 | -29810.1719 | 0 | 74525.4297 | 0 | 100% | Finished | 74525.4297 | 0 | 100 | 140 | 100 | 100 | 100 | 100
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 | 2013-08-05 08:00 | 18d | 57024.0375 | 0 | 0 | 38016.025 | 0 | 95040.0625 | 0 | 100% | Finished | 95040.0625 | 25344.0167 | 100 | 60 | 100 | 100 | 100 | 100
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 | 2013-07-01 08:00 | 23d | 203003.8937 | 88262.5625 | 10d | -32783.2063 | 0 | 170220.6875 | 88262.5625 | 69.7% | Started | 184548.9919 | 26478.7687 | 100 | 76.6667 | 69.697 | 100 | 64.2857 | 69.697
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 | 2013-07-01 08:00 | 30d | 97978.7969 | 0 | 0 | 0 | 0 | 97978.7969 | 0 | 100% | Finished | 97978.7969 | 9797.8797 | 100 | 100 | 100 | 100 | 100 | 100
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 | 2013-08-05 08:00 | 18d | 37480.7039 | 0 | 0 | 24987.1359 | 0 | 62467.8398 | 0 | 100% | Finished | 62467.8398 | 0 | 100 | 60 | 100 | 100 | 100 | 100
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 | 2013-08-26 08:00 | 15d | 33428.0742 | 11142.6914 | 5d | 30227.9841 | 0 | 63656.0583 | 11142.6914 | 75% | Started | 50142.1113 | 0 | 100 | 50 | 75 | 100 | 95.2135 | 75
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 | 2013-09-16 08:00 | 10d | 116780.3203 | 0 | 0 | 0 | 0 | 116780.3203 | 0 | 100% | Finished | 116780.3203 | 0 | 100 | 100 | 100 | 100 | 100 | 100
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 | 2013-10-07 08:00 | 15d | 2696.4675 | 0 | 0 | 898.8225 | 0 | 3595.29 | 0 | 100% | Finished | 3595.29 | 0 | 100 | 75 | 100 | 100 | 100 | 100
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-10-21 08:00 | 3d | 0.6 | 0 | 0 | 0.4 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 60 | 100 | 100 | 100 | 100
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 |  | 0 | 0 | 1 | 2d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-10-04 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 |  | 0 | 0 | 90123.9766 | 30d | 0 | 0 | 0 | 90123.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 | 2013-08-21 08:00 | 8d | 3116.84 | 779.21 | 2d | 779.21 | 0 | 3896.05 | 779.21 | 80% | Started | 3116.8401 | 0 | 100 | 80 | 80 | 100 | 100 | 80
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 |  | 0 | 0 | 60948.2617 | 35d | 0 | 0 | 0 | 60948.2617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 |  | 0 | 0 | 46709.9414 | 40d | 0 | 0 | 0 | 46709.9414 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 |  | 0 | 0 | 52911.1211 | 20d | 0 | 0 | 0 | 52911.1211 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 |  | 0 | 0 | 113480.4297 | 20d | 0 | 0 | 0 | 113480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 |  | 0 | 0 | 41990.9102 | 20d | 0 | 0 | 0 | 41990.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2013-11-30 16:00 |  | TP Name | 30/11, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 233d | [5 empty] | 2297905.679 |  | 90.62% |  | 2273753.2744 | 1663873.8523
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 112336.2891 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 23087.9004 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 26678.2207 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 33.3333 | 100 | 100 | 100 | 100
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-03 08:00 | 3d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-06-03 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 2013-06-19 08:00 | 41d | 64053.6167 | 0 | 0 | 53117.6333 | 0 | 117171.25 | 0 | 100% | Finished | 117171.25 | 101548.4167 | 100 | 54.6667 | 100 | 100 | 100 | 100
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-06-24 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-24 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 | 2013-07-01 08:00 | 42d | 325007.0625 | 0 | 0 | 216671.375 | 0 | 541678.4375 | 0 | 100% | Finished | 541678.4375 | 464295.8036 | 100 | 60 | 100 | 100 | 100 | 100
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-07-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 | 2013-07-01 08:00 | 5d | 14570.25 | 0 | 0 | 0 | 0 | 14570.25 | 0 | 100% | Finished | 14570.25 | 14570.25 | 100 | 100 | 100 | 100 | 100 | 100
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 | 2013-07-08 08:00 | 7d | 25071.0387 | 0 | 0 | 10744.7309 | 0 | 35815.7695 | 0 | 100% | Finished | 35815.7695 | 35815.7695 | 100 | 70 | 100 | 100 | 100 | 100
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 | 2013-07-11 08:00 | 7d | 104335.6016 | 0 | 0 | -29810.1719 | 0 | 74525.4297 | 0 | 100% | Finished | 74525.4297 | 74525.4297 | 100 | 140 | 100 | 100 | 100 | 100
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 | 2013-08-05 08:00 | 18d | 57024.0375 | 0 | 0 | 38016.025 | 0 | 95040.0625 | 0 | 100% | Finished | 95040.0625 | 88704.0583 | 100 | 60 | 100 | 100 | 100 | 100
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 | 2013-07-01 08:00 | 33d | 291266.4562 | 0 | 0 | -26478.7687 | 0 | 264787.6875 | 0 | 100% | Finished | 264787.6875 | 203003.8937 | 100 | 110 | 100 | 100 | 100 | 100
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 | 2013-07-01 08:00 | 30d | 97978.7969 | 0 | 0 | 0 | 0 | 97978.7969 | 0 | 100% | Finished | 97978.7969 | 75117.0776 | 100 | 100 | 100 | 100 | 100 | 100
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 | 2013-08-05 08:00 | 18d | 37480.7039 | 0 | 0 | 24987.1359 | 0 | 62467.8398 | 0 | 100% | Finished | 62467.8398 | 37480.7039 | 100 | 60 | 100 | 100 | 100 | 100
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 | 2013-08-26 08:00 | 20d | 44570.7656 | 0 | 0 | 22285.3828 | 0 | 66856.1484 | 0 | 100% | Finished | 66856.1484 | 0 | 100 | 66.6667 | 100 | 100 | 100 | 100
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 | 2013-09-16 08:00 | 10d | 116780.3203 | 0 | 0 | 0 | 0 | 116780.3203 | 0 | 100% | Finished | 116780.3203 | 0 | 100 | 100 | 100 | 100 | 100 | 100
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 | 2013-10-07 08:00 | 15d | 2696.4675 | 0 | 0 | 898.8225 | 0 | 3595.29 | 0 | 100% | Finished | 3595.29 | 0 | 100 | 75 | 100 | 100 | 100 | 100
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-10-21 08:00 | 3d | 0.6 | 0 | 0 | 0.4 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 60 | 100 | 100 | 100 | 100
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 | 2013-11-04 08:00 | 2d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-10-04 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 |  | 0 | 0 | 1 | 20d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 | 2013-11-04 08:00 | 19d | 57078.5185 | 0 | 0 | 33045.4581 | 0 | 90123.9766 | 0 | 100% | Finished | 90123.9766 | 0 | 100 | 63.3333 | 100 | 100 | 100 | 100
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 | 2013-08-21 08:00 | 8d | 3116.84 | 0 | 0 | 779.21 | 0 | 3896.05 | 0 | 100% | Finished | 3896.05 | 0 | 100 | 80 | 100 | 100 | 100 | 100
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 | 2013-11-12 08:00 | 14d | 24379.3047 | 26120.6836 | 15d | 15107.0566 | 0 | 39486.3613 | 26120.6836 | 48.28% | Started | 29423.2982 | 0 | 100 | 40 | 48.2759 | 100 | 64.7867 | 48.2759
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 | 2013-11-25 08:00 | 5d | 5838.7427 | 23354.9707 | 20d | 1207.8198 | 0 | 7046.5625 | 23354.9707 | 20% | Started | 9341.9884 | 0 | 100 | 12.5 | 20 | 100 | 15.0858 | 20
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 | 2013-11-20 08:00 | 8d | 21164.4484 | 13227.7803 | 5d | 17282.5525 | 0 | 38447.001 | 13227.7803 | 61.54% | Started | 32560.6911 | 0 | 100 | 40 | 61.5385 | 100 | 72.6634 | 61.5385
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 |  | 0 | 0 | 38883 | 15d | 0 | 0 | 0 | 38883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 | 2013-11-25 08:00 | 5d | 28370.1074 | 56740.2148 | 10d | 9456.9785 | 0 | 37827.0859 | 56740.2148 | 33.33% | Started | 37826.811 | 0 | 100 | 25 | 33.3333 | 100 | 33.3336 | 33.3333
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 | 2013-11-15 08:00 | 5d | 10497.7275 | 31493.1826 | 15d | 10498.1826 | 0 | 20995.9102 | 31493.1826 | 25% | Started | 10497.7275 | 0 | 100 | 25 | 25 | 100 | 50.0011 | 25
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 |  | 0 | 0 | 1 | 11d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 |  | 0 | 0 | 1 | 32d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 |  | 0 | 0 | 1 | 1d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2014-01-28 16:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Social Apartments Ypres (3) | 2012-11-13 08:00 | 2014-06-06 17:00 | 358d |  |  | 0 |  |  | 2509031.4221 |  | 265d | [5 empty] | 2509031.4207 |  | 100% |  | 2509031.4221 | 2101911.2693
1 | werfinrichting | 2012-11-13 08:00 | 2012-11-26 17:00 | 10d |  | 0 | 0 | 1.25 | 100 | 100 | 2012-11-13 08:00 | 10d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | aanvraag verslag Bom.be | 2012-11-29 08:00 | 2013-01-11 17:00 | 22d |  | 0 | 0 | 0.056818 | 10 | 10 | 2012-11-29 08:00 | 22d | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 100% | Finished | 10 | 10 | 100 | 100 | 100 | 100 | 100 | 100
3 | grondwerken + bom detectie | 2013-01-25 08:00 | 2013-02-22 17:00 | 21d |  | 0 | 0 | 543.7839 | 91355.7031 | 91355.7031 | 2013-01-11 08:00 | 14d 7h | 64710.2897 | 0 | 0 | 26645.4134 | 0 | 91355.7031 | 0 | 100% | Finished | 91355.7031 | 91355.7031 | 100 | 70.8333 | 100 | 100 | 100 | 100
4 | paalfundering | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 544.7531 | 43580.25 | 43580.25 | 2013-02-15 08:00 | 8d | 34864.2 | 0 | 0 | 8716.05 | 0 | 43580.25 | 0 | 100% | Finished | 43580.25 | 43580.25 | 100 | 80 | 100 | 100 | 100 | 100
5 | afkappen palen | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-03-01 08:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
6 | rioleringwerken onder fundering | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 389.2228 | 15568.9102 | 15568.9102 | 2013-03-04 08:00 | 5d | 15568.9102 | 0 | 0 | 0 | 0 | 15568.9102 | 0 | 100% | Finished | 15568.9102 | 15568.9102 | 100 | 100 | 100 | 100 | 100 | 100
7 | funderingsplaat (bekisten, ijzer, beton) | 2013-03-11 08:00 | 2013-04-12 17:00 | 20d |  | 0 | 0 | 672.3363 | 107573.8125 | 107573.8125 | 2013-03-04 08:00 | 18d | 96816.4312 | 0 | 0 | 10757.3813 | 0 | 107573.8125 | 0 | 100% | Finished | 107573.8125 | 107573.8125 | 100 | 90 | 100 | 100 | 100 | 100
8 | montage kraan | 2013-03-13 08:00 | 2013-03-13 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-02-27 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
9 | kelderwanden | 2013-04-15 08:00 | 2013-05-06 17:00 | 15d |  | 0 | 0 | 936.1357 | 112336.2891 | 112336.2891 | 2013-03-25 08:00 | 15d | 112336.2891 | 0 | 0 | 0 | 0 | 112336.2891 | 0 | 100% | Finished | 112336.2891 | 112336.2891 | 100 | 100 | 100 | 100 | 100 | 100
10 | kolommen + balken + metalen profielen kelder | 2013-04-29 08:00 | 2013-05-15 17:00 | 10d |  | 0 | 0 | 288.5988 | 23087.9004 | 23087.9004 | 2013-03-25 08:00 | 5d | 11543.9502 | 0 | 0 | 11543.9502 | 0 | 23087.9004 | 0 | 100% | Finished | 23087.9004 | 23087.9004 | 100 | 50 | 100 | 100 | 100 | 100
11 | metselwerk kelderverdieping | 2013-05-07 08:00 | 2013-05-23 17:00 | 10d |  | 0 | 0 | 333.4778 | 26678.2207 | 26678.2207 | 2013-04-08 08:00 | 10d | 26678.2207 | 0 | 0 | 0 | 0 | 26678.2207 | 0 | 100% | Finished | 26678.2207 | 26678.2207 | 100 | 100 | 100 | 100 | 100 | 100
12 | afdek kelder + balken | 2013-05-24 08:00 | 2013-06-06 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-04-15 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
13 | wanden gelijkvloers | 2013-06-07 08:00 | 2013-06-24 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-06 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
14 | binnenzetten bouwmaterialen | 2013-06-10 08:00 | 2013-06-12 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-05-13 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
15 | verwarming helling | 2013-06-10 08:00 | 2013-06-10 17:00 | 1d |  | 0 | 0 | 12.5 | 100 | 100 | 2013-05-16 08:00 | 1d | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | helling - vloer en wanden | 2013-06-10 08:00 | 2013-06-28 17:00 | 15d |  | 0 | 0 | 0.0083333 | 1 | 1 | 2013-05-13 08:00 | 10d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
17 | afdek gelijkvloers (vloerplaat 1ste) + balken | 2013-06-18 08:00 | 2013-07-01 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-21 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
18 | wanden 1ste verdiep | 2013-07-02 08:00 | 2013-08-07 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-05-27 08:00 | 4d | 16490.0404 | 0 | 0 | 32980.0807 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 33.3333 | 100 | 100 | 100 | 100
19 | binnenzetten bouwmaterialen | 2013-07-04 08:00 | 2013-07-08 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-03 08:00 | 3d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
20 | afdek 1ste verdiep (vloerplaat 2de) + balken | 2013-07-11 08:00 | 2013-08-14 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-06-03 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
21 | stelling plaatsen | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-05-24 08:00 | 5d | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 50 | 100 | 100 | 100 | 100
22 | gevelmetselwerk + blauwe hardsteen | 2013-08-26 08:00 | 2013-12-13 17:00 | 75d |  | 0 | 0 | 195.2854 | 117171.25 | 117171.25 | 2013-06-19 08:00 | 41d | 64053.6167 | 0 | 0 | 53117.6333 | 0 | 117171.25 | 0 | 100% | Finished | 117171.25 | 117171.25 | 100 | 54.6667 | 100 | 100 | 100 | 100
23 | wanden 2de verdiep | 2013-09-02 08:00 | 2013-09-17 17:00 | 12d |  | 0 | 0 | 515.3138 | 49470.1211 | 49470.1211 | 2013-06-24 08:00 | 5d | 20612.5505 | 0 | 0 | 28857.5706 | 0 | 49470.1211 | 0 | 100% | Finished | 49470.1211 | 49470.1211 | 100 | 41.6667 | 100 | 100 | 100 | 100
24 | binnenzetten bouwmaterialen | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 0.041667 | 1 | 1 | 2013-06-24 08:00 | 2d | 0.66667 | 0 | 0 | 0.33333 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 66.6667 | 100 | 100 | 100 | 100
25 | prefabmontage | 2013-09-02 08:00 | 2013-12-13 17:00 | 70d |  | 0 | 0 | 967.2829 | 541678.4375 | 541678.4375 | 2013-07-01 08:00 | 42d | 325007.0625 | 0 | 0 | 216671.375 | 0 | 541678.4375 | 0 | 100% | Finished | 541678.4375 | 541678.4375 | 100 | 60 | 100 | 100 | 100 | 100
26 | afdek 2de verdiep (dakplaat) + balken | 2013-09-11 08:00 | 2013-09-24 17:00 | 10d |  | 0 | 0 | 0.0125 | 1 | 1 | 2013-07-01 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
27 | dakranden Ytong | 2013-09-25 08:00 | 2013-10-01 17:00 | 5d |  | 0 | 0 | 364.2563 | 14570.25 | 14570.25 | 2013-07-01 08:00 | 5d | 14570.25 | 0 | 0 | 0 | 0 | 14570.25 | 0 | 100% | Finished | 14570.25 | 14570.25 | 100 | 100 | 100 | 100 | 100 | 100
28 | Hellingsbeton + dakverdichting | 2013-10-02 08:00 | 2013-10-15 17:00 | 10d |  | 0 | 0 | 447.6971 | 35815.7695 | 35815.7695 | 2013-07-08 08:00 | 7d | 25071.0387 | 0 | 0 | 10744.7309 | 0 | 35815.7695 | 0 | 100% | Finished | 35815.7695 | 35815.7695 | 100 | 70 | 100 | 100 | 100 | 100
29 | dakverdicting-eindlaag | 2013-11-15 08:00 | 2013-11-21 17:00 | 5d |  | 0 | 0 | 1863.1357 | 74525.4297 | 74525.4297 | 2013-07-11 08:00 | 7d | 104335.6016 | 0 | 0 | -29810.1719 | 0 | 74525.4297 | 0 | 100% | Finished | 74525.4297 | 74525.4297 | 100 | 140 | 100 | 100 | 100 | 100
30 | binnenwanden niv 0/1/2 | 2013-10-16 08:00 | 2013-12-03 17:00 | 30d |  | 0 | 0 | 396.0003 | 95040.0625 | 95040.0625 | 2013-08-05 08:00 | 18d | 57024.0375 | 0 | 0 | 38016.025 | 0 | 95040.0625 | 0 | 100% | Finished | 95040.0625 | 95040.0625 | 100 | 60 | 100 | 100 | 100 | 100
53 | leiding technieken - sanitair | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 1103.282 | 264787.6875 | 264787.6875 | 2013-07-01 08:00 | 33d | 291266.4562 | 0 | 0 | -26478.7687 | 0 | 264787.6875 | 0 | 100% | Finished | 264787.6875 | 264787.6875 | 100 | 110 | 100 | 100 | 100 | 100
31 | leidingen technieken - electriciteit | 2013-10-23 08:00 | 2013-12-10 17:00 | 30d |  | 0 | 0 | 408.245 | 97978.7969 | 97978.7969 | 2013-07-01 08:00 | 30d | 97978.7969 | 0 | 0 | 0 | 0 | 97978.7969 | 0 | 100% | Finished | 97978.7969 | 97978.7969 | 100 | 100 | 100 | 100 | 100 | 100
32 | chape | 2013-11-05 08:00 | 2013-12-17 17:00 | 30d |  | 0 | 0 | 260.2827 | 62467.8398 | 62467.8398 | 2013-08-05 08:00 | 18d | 37480.7039 | 0 | 0 | 24987.1359 | 0 | 62467.8398 | 0 | 100% | Finished | 62467.8398 | 62467.8398 | 100 | 60 | 100 | 100 | 100 | 100
33 | pleisterwerken | 2013-12-13 08:00 | 2014-02-06 17:00 | 30d |  | 0 | 0 | 278.5673 | 66856.1484 | 66856.1484 | 2013-08-26 08:00 | 20d | 44570.7656 | 0 | 0 | 22285.3828 | 0 | 66856.1484 | 0 | 100% | Finished | 66856.1484 | 50977.8132 | 100 | 66.6667 | 100 | 100 | 100 | 100
34 | leuningen | 2014-01-10 08:00 | 2014-01-23 17:00 | 10d |  | 0 | 0 | 1459.754 | 116780.3203 | 116780.3203 | 2013-09-16 08:00 | 10d | 116780.3203 | 0 | 0 | 0 | 0 | 116780.3203 | 0 | 100% | Finished | 116780.3203 | 116780.3203 | 100 | 100 | 100 | 100 | 100 | 100
35 | voegwerken | 2014-01-16 08:00 | 2014-02-12 17:00 | 20d |  | 0 | 0 | 22.4706 | 3595.29 | 3595.29 | 2013-10-07 08:00 | 15d | 2696.4675 | 0 | 0 | 898.8225 | 0 | 3595.29 | 0 | 100% | Finished | 3595.29 | 1595.41 | 100 | 75 | 100 | 100 | 100 | 100
36 | dakverdichting boven trapzalen | 2014-01-24 08:00 | 2014-01-30 17:00 | 5d |  | 0 | 0 | 0.025 | 1 | 1 | 2013-10-21 08:00 | 3d | 0.6 | 0 | 0 | 0.4 | 0 | 1 | 0 | 100% | Finished | 1 | 0.575 | 100 | 60 | 100 | 100 | 100 | 100
37 | stelling afbreken | 2014-01-24 08:00 | 2014-01-27 17:00 | 2d |  | 0 | 0 | 0.0625 | 1 | 1 | 2013-11-04 08:00 | 2d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
38 | afbreken torenkraan | 2014-01-27 08:00 | 2014-01-27 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-10-04 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
39 | buitenaanleg - ABM | 2014-01-28 08:00 | 2014-02-24 17:00 | 20d |  | 0 | 0 | 0.00625 | 1 | 1 | 2013-12-02 08:00 | 20d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0.04375 | 100 | 100 | 100 | 100 | 100 | 100
40 | tegelwerken | 2013-12-18 08:00 | 2014-02-11 17:00 | 30d |  | 0 | 0 | 375.5166 | 90123.9766 | 90123.9766 | 2013-11-04 08:00 | 19d | 57078.5185 | 0 | 0 | 33045.4581 | 0 | 90123.9766 | 0 | 100% | Finished | 90123.9766 | 59707.1345 | 100 | 63.3333 | 100 | 100 | 100 | 100
41 | buitenschrijnwerk | 2014-01-31 08:00 | 2014-02-13 17:00 | 10d |  | 0 | 0 | 48.7006 | 3896.05 | 3896.05 | 2013-08-21 08:00 | 8d | 3116.84 | 0 | 0 | 779.21 | 0 | 3896.05 | 0 | 100% | Finished | 3896.05 | 0 | 100 | 80 | 100 | 100 | 100 | 100
42 | binnenschrijnwerk | 2014-02-11 08:00 | 2014-03-31 17:00 | 35d |  | 0 | 0 | 217.6724 | 60948.2617 | 60948.2617 | 2013-11-12 08:00 | 30d | 52241.3672 | 0 | 0 | 8706.8945 | 0 | 60948.2617 | 0 | 100% | Finished | 60948.2617 | 0 | 100 | 85.7143 | 100 | 100 | 100 | 100
43 | schilderwerk | 2014-02-11 08:00 | 2014-04-07 17:00 | 40d |  | 0 | 0 | 145.9686 | 46709.9414 | 46709.9414 | 2013-11-25 08:00 | 25d | 29193.7134 | 0 | 0 | 17516.2266 | 0 | 46709.94 | 0 | 100% | Finished | 46709.9414 | 0 | 100 | 62.5 | 100 | 100 | 100 | 100
44 | keukens | 2014-03-05 08:00 | 2014-04-01 17:00 | 20d |  | 0 | 0 | 330.6945 | 52911.1211 | 52911.1211 | 2013-11-20 08:00 | 15d | 39683.3408 | 0 | 0 | 13227.7803 | 0 | 52911.1211 | 0 | 100% | Finished | 52911.1211 | 0 | 100 | 75 | 100 | 100 | 100 | 100
45 | lift | 2014-03-18 08:00 | 2014-04-07 17:00 | 15d |  | 0 | 0 | 324.025 | 38883 | 38883 | 2013-12-02 08:00 | 15d | 38883 | 0 | 0 | 0 | 0 | 38883 | 0 | 100% | Finished | 38883 | 0 | 100 | 100 | 100 | 100 | 100 | 100
46 | afwerken technieken - sanitair | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 709.2527 | 113480.4297 | 113480.4297 | 2013-11-25 08:00 | 15d | 85110.3223 | 0 | 0 | 28370.1074 | 0 | 113480.4297 | 0 | 100% | Finished | 113480.4297 | 0 | 100 | 75 | 100 | 100 | 100 | 100
54 | afwerken technieken - electriciteit | 2014-03-11 08:00 | 2014-04-07 17:00 | 20d |  | 0 | 0 | 262.4432 | 41990.9102 | 41990.9102 | 2013-11-15 08:00 | 20d | 41990.9102 | 0 | 0 | 0 | 0 | 41990.9102 | 0 | 100% | Finished | 41990.9102 | 0 | 100 | 100 | 100 | 100 | 100 | 100
47 | algemene opkuis | 2014-04-08 08:00 | 2014-04-22 17:00 | 11d |  | 0 | 0 | 0.011364 | 1 | 1 | 2013-12-02 08:00 | 11d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
48 | datum contract zonder VAA | 2014-04-23 17:00 | 2014-04-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
49 | in orde brengen punten voor voorlopige oplevering | 2014-04-22 08:00 | 2014-06-04 17:00 | 32d |  | 0 | 0 | 0.0039062 | 1 | 1 | 2013-12-02 08:00 | 32d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
50 | oplevering contract + VAA-1-43 KD | 2014-06-05 08:00 | 2014-06-05 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-12-02 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100
51 | buitenaanleg - bouwheer | 2014-06-06 08:00 | 2014-06-06 17:00 | 1d |  | 0 | 0 | 0.125 | 1 | 1 | 2013-12-02 08:00 | 1d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 0 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2012-12-24
1:00 - 2:00 | No | Tuesday | Yes | 2012-12-25
2:00 - 3:00 | No | Wednesday | Yes | 2012-12-26
3:00 - 4:00 | No | Thursday | Yes | 2012-12-27
4:00 - 5:00 | No | Friday | Yes | 2012-12-28
5:00 - 6:00 | No | Saturday | No | 2012-12-31
6:00 - 7:00 | No | Sunday | No | 2013-01-01
7:00 - 8:00 | No |  |  | 2013-01-02
8:00 - 9:00 | Yes |  |  | 2013-01-03
9:00 - 10:00 | Yes |  |  | 2013-01-04
10:00 - 11:00 | Yes |  |  | 2013-07-15
11:00 - 12:00 | Yes |  |  | 2013-07-16
12:00 - 13:00 | No |  |  | 2013-07-17
13:00 - 14:00 | Yes |  |  | 2013-07-18
14:00 - 15:00 | Yes |  |  | 2013-07-19
15:00 - 16:00 | Yes |  |  | 2013-07-22
16:00 - 17:00 | Yes |  |  | 2013-07-23
17:00 - 18:00 | No |  |  | 2013-07-24
18:00 - 19:00 | No |  |  | 2013-07-25
19:00 - 20:00 | No |  |  | 2013-07-26
20:00 - 21:00 | No |  |  | 2013-07-29
21:00 - 22:00 | No |  |  | 2013-07-30
22:00 - 23:00 | No |  |  | 2013-07-31
23:00 - 0:00 | No |  |  | 2013-08-01
2013-08-02
2013-04-04
Generated by PMConverter v1.1.3 |  |  |  | 2013-04-05
2013-10-28
2013-10-29
2013-10-30
2013-10-31
2013-04-01
2013-05-01
2013-05-09
2013-04-02
2013-04-03
2013-05-10
2013-05-20
2013-08-15
2013-08-16
2013-11-11
2013-12-23
2013-12-24
2013-12-25
2013-12-26
2013-12-27
2013-12-30
2013-12-31
2014-01-01
2014-01-02
2014-01-03

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/11, 2012 | 2012-11-13 08:00 | 2012-11-30 17:00 | 100.9091 | 100.9091 | 110 | 2012-11-30 17:00 | 2.7093e-08 | 100% | -9.0909 | 91.74% | 0 | 100% | 100% | 2014-06-06 17:00 | 2014-06-06 17:00 | 2014-07-23 10:00 | 2014-06-06 17:00 | 2014-06-06 17:00 | 2014-07-21 17:00 | 2014-06-06 17:00 | 2014-06-06 17:00 | 2014-07-21 17:00 | 2509040.513 | 2735070.2882 | 2509040.5124 | 2509040.513 | 2735070.2875 | 2735070.2882 | 2686663.9115 | 2686663.9116 | 1 | 0.91736 | 1 | 1 | 0 | 0.91736 | 1 | 1 | 1
31/12, 2012 | 2012-11-30 17:00 | 2012-12-31 16:00 | 107.7273 | 107.7273 | 110 | 2012-12-21 17:00 | -2.1674e-07 | 100% | -2.2727 | 97.93% | 0 | 100% | 100% | 2014-06-06 17:00 | 2014-06-06 17:00 | 2014-06-18 12:00 | 2014-06-06 17:00 | 2014-06-06 17:00 | 2014-06-17 17:00 | 2014-06-06 17:00 | 2014-06-06 17:00 | 2014-06-17 17:00 | 2509033.6948 | 2561964.5796 | 2509033.6999 | 2509033.6948 | 2561964.5848 | 2561964.5796 | 2551200.4848 | 2551200.4837 | 1 | 0.97934 | 1 | 1 | 0 | 0.97934 | 1 | 1 | 1
31/01, 2013 | 2012-12-31 16:00 | 2013-01-31 16:00 | 21317.5739 | 64820.2879 | 44302.3438 | 2013-02-14 16:00 | 43502.714 | 304.1% | 20517.9441 | 146.3% | 10d | 120.9% | 100% | 2014-05-29 15:00 | 2013-05-22 15:00 | 2013-03-19 12:00 | 2014-01-22 10:00 | 2013-05-22 15:00 | 2013-04-16 14:00 | 2014-05-23 17:00 | 2014-03-13 09:00 | 2013-11-07 12:00 | 2488513.478 | 1714833.0584 | 848134.8053 | 2066187.58 | 593693.0235 | 1426188.4425 | 1418499.1712 | 1774983.1106 | 1.2089 | 1.4631 | 3.0407 | 1 | 10 | 1.4631 | 1 | 1.2089 | 1
28/02, 2013 | 2013-01-31 16:00 | 2013-02-28 16:00 | 108353.05 | 135046.9531 | 135046.9531 | 2013-03-11 09:00 | 26693.9031 | 124.6% | 0 | 100% | 6d 2h | 109.2% | 99.22% | 2014-06-03 10:00 | 2014-02-28 10:00 | 2014-02-28 10:00 | 2014-05-15 10:00 | 2014-02-28 10:00 | 2014-02-28 10:00 | 2014-05-29 15:00 | 2014-04-25 16:00 | 2014-04-25 16:00 | 2509031.4221 | 2509031.4221 | 2039780.4693 | 2308864.0976 | 2039780.4693 | 2308864.0976 | 2397553.0317 | 2466102.2274 | 1.0921 | 1 | 1.2464 | 0.9922 | 6.25 | 1 | 1 | 1.0921 | 1
31/03, 2013 | 2013-02-28 16:00 | 2013-03-31 16:00 | 231297.2227 | 318724.007 | 331829.9043 | 2013-04-25 09:00 | 87426.7843 | 137.8% | -13105.8973 | 96.05% | 13d 1h | 114.7% | 92.66% | 2014-05-21 12:00 | 2014-01-21 15:00 | 2014-02-05 12:00 | 2014-04-22 11:00 | 2014-01-21 15:00 | 2014-01-30 16:00 | 2014-05-20 16:00 | 2014-04-03 17:00 | 2014-04-17 09:00 | 2522137.3194 | 2612202.5278 | 1921330.572 | 2240641.2624 | 1986690.6706 | 2319131.3828 | 2429825.0041 | 2526751.663 | 1.1475 | 0.9605 | 1.378 | 0.92664 | 13.125 | 0.9605 | 1 | 1.1475 | 1
30/04, 2013 | 2013-03-31 16:00 | 2013-04-30 16:00 | 351452.5526 | 420294.0859 | 420294.0859 | 2013-06-06 17:00 | 68841.5333 | 119.6% | 0 | 100% | 23d 1h | 121.8% | 100% | 2014-05-26 09:00 | 2014-03-18 11:00 | 2014-03-18 11:00 | 2014-05-09 10:00 | 2014-03-18 11:00 | 2014-03-18 11:00 | 2014-05-06 16:00 | 2014-03-10 16:00 | 2014-03-10 16:00 | 2509031.4221 | 2509031.4221 | 2166909.3563 | 2134596.919 | 2166909.3563 | 2134596.919 | 2430288.9969 | 2421606.8956 | 1.2184 | 1 | 1.1959 | 1 | 23.125 | 1 | 1 | 1.2184 | 1
31/05, 2013 | 2013-04-30 16:00 | 2013-05-31 16:00 | 420293.6734 | 519338.3281 | 519338.3281 | 2013-08-07 17:00 | 99044.6547 | 123.6% | 0 | 100% | 33d 1h | 126.5% | 100% | 2014-05-19 16:00 | 2014-03-04 15:00 | 2014-03-04 15:00 | 2014-04-28 14:00 | 2014-03-04 15:00 | 2014-03-04 15:00 | 2014-04-22 16:00 | 2014-02-21 17:00 | 2014-02-21 17:00 | 2509031.4221 | 2509031.4221 | 2129570.7608 | 2091888.4871 | 2129570.7608 | 2091888.4871 | 2419475.7306 | 2408790.2301 | 1.2653 | 1 | 1.2357 | 1 | 33.125 | 1 | 1 | 1.2653 | 1
30/06, 2013 | 2013-05-31 16:00 | 2013-06-30 16:00 | 469867.107 | 584973.0009 | 630470.1484 | 2013-09-06 11:00 | 115105.8939 | 124.5% | -45497.1476 | 92.78% | 32d 3h | 122.3% | 94.22% | 2014-05-15 14:00 | 2014-02-28 12:00 | 2014-04-01 16:00 | 2014-04-18 12:00 | 2014-02-28 12:00 | 2014-03-17 14:00 | 2014-04-23 14:00 | 2014-03-07 14:00 | 2014-03-25 09:00 | 2554528.5697 | 2704175.0829 | 2175929.106 | 2203343.8402 | 2296129.4813 | 2325676.4373 | 2571485.2543 | 2580020.6985 | 1.2233 | 0.92784 | 1.245 | 0.94222 | 32.375 | 0.92784 | 1 | 1.2233 | 1
31/07, 13 | 2013-06-30 16:00 | 2013-07-31 09:00 | 506970.9979 | 907858.5161 | 1042363.0083 | 2013-10-14 15:00 | 400887.5182 | 179.1% | -134504.4922 | 87.1% | 48d 6h | 131.5% | 83.58% | 2014-03-19 15:00 | 2013-10-08 16:00 | 2013-11-26 12:00 | 2013-12-04 11:00 | 2013-10-08 16:00 | 2013-10-17 14:00 | 2014-04-01 10:00 | 2014-02-07 11:00 | 2014-03-04 15:00 | 2643535.9143 | 2880758.9451 | 1936498.1753 | 2260433.1945 | 2068969.4739 | 2440897.3406 | 2560178.0613 | 2710820.1455 | 1.3145 | 0.87096 | 1.7908 | 0.83582 | 48.75 | 0.87096 | 1 | 1.3145 | 1
31/08, 2013 | 2013-07-31 09:00 | 2013-08-31 16:00 | 527151.7448 | 1455628.6559 | 1604691.2698 | 2013-11-20 16:00 | 928476.9111 | 276.1% | -149062.6139 | 90.71% | 52d 7h | 130.6% | 91.83% | 2013-11-20 12:00 | 2013-06-07 14:00 | 2013-06-26 16:00 | 2013-02-08 10:00 | 2013-06-07 14:00 | 2013-06-03 10:00 | 2014-03-26 09:00 | 2014-02-11 10:00 | 2014-02-25 12:00 | 2658094.036 | 2765966.9947 | 1986178.0617 | 2411503.3497 | 2025243.9444 | 2494124.3651 | 2428983.4267 | 2672170.0775 | 1.3056 | 0.90711 | 2.7613 | 0.91828 | 52.875 | 0.90711 | 1 | 1.3056 | 1
30/09, 2013 | 2013-08-31 16:00 | 2013-09-30 16:00 | 782064.7225 | 1828075.928 | 1869633.5217 | 2013-12-10 15:00 | 1046011.2054 | 233.7% | -41557.5938 | 97.78% | 45d 7h | 123.7% | 90.25% | 2013-10-21 15:00 | 2013-07-11 09:00 | 2013-08-06 14:00 | 2013-04-19 15:00 | 2013-07-11 09:00 | 2013-07-10 10:00 | 2014-04-04 09:00 | 2014-03-04 12:00 | 2014-03-06 14:00 | 2550589.0159 | 2566069.1561 | 2160951.4377 | 2420291.4839 | 2167573.9589 | 2432809.5744 | 2414520.9426 | 2531049.3554 | 1.2366 | 0.97777 | 2.3375 | 0.90246 | 45.875 | 0.97777 | 1 | 1.2366 | 1
31/10, 2013 | 2013-09-30 16:00 | 2013-10-31 16:00 | 1060652.4196 | 1966245.8388 | 1966210.6914 | 2014-01-14 17:00 | 905593.4193 | 185.4% | 35.1474 | 100% | 42d | 119.7% | 94.39% | 2013-11-25 15:00 | 2013-09-30 09:00 | 2013-09-30 09:00 | 2013-09-05 09:00 | 2013-09-30 09:00 | 2013-09-30 09:00 | 2014-04-09 17:00 | 2014-03-17 17:00 | 2014-03-17 17:00 | 2508996.2747 | 2508986.5722 | 2259005.6364 | 2419596.2963 | 2259000.4026 | 2419588.1918 | 2429822.5508 | 2488395.5995 | 1.1972 | 1 | 1.8538 | 0.94393 | 42 | 1 | 1 | 1.1972 | 1
30/11, 2013 | 2013-10-31 16:00 | 2013-11-30 16:00 | 1663873.8523 | 2273753.2744 | 2297905.679 | 2014-03-14 16:00 | 609879.4221 | 136.7% | -24152.4046 | 98.95% | 64d 7h | 127.8% | 98.65% | 2014-02-05 17:00 | 2014-01-23 17:00 | 2014-01-28 15:00 | 2014-02-07 14:00 | 2014-01-23 17:00 | 2014-01-24 10:00 | 2014-03-10 09:00 | 2014-02-18 17:00 | 2014-02-19 12:00 | 2533183.8267 | 2535683.013 | 2470076.1438 | 2481941.9641 | 2471904.9837 | 2483896.8458 | 2518844.898 | 2522562.4581 | 1.2784 | 0.98949 | 1.3665 | 0.98651 | 64.875 | 0.98949 | 1 | 1.2784 | 1
Actual Schedule | 2013-11-30 16:00 | 2014-01-28 16:00 | 2101911.2693 | 2509031.4221 | 2509031.4207 | 2014-06-06 17:00 | 407120.1528 | 119.4% | 0.0014063 | 100% | 93d 1h | 135.2% | 100% | 2014-03-18 16:00 | 2014-03-18 16:00 | 2014-03-18 16:00 | 2014-03-27 15:00 | 2014-03-18 16:00 | 2014-03-18 16:00 | 2014-01-28 16:00 | 2014-01-28 16:00 | 2014-01-28 16:00 | 2509031.4207 | 2509031.4207 | 2509031.4207 | 2509031.4207 | 2509031.4207 | 2509031.4207 | 2509031.4207 | 2509031.4207 | 1.3516 | 1 | 1.1937 | 1 | 93.125 | 1 | 1 | 1.3516 | 1