## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | IJzertoren Memorial Square | 1 |  |  | 2013-10-14 08:00 | 2013-12-20 17:00 | 50d |  |  | 0 |  |  | 214417.7109 | 67.375
1 | opbraak &amp;amp;amp; riolering | 1.1 |  | FS2 | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 615.3959 | 49231.6719 | 49231.6719 | 11.375
2 | grondwerken &amp;amp;amp; onderfundering | 1.2 | 1FS | FS3-1w | 2013-10-28 08:00 | 2013-11-08 17:00 | 10d |  | 0 | 0 | 374.8181 | 29985.4492 | 29985.4492 | 11.375
3 | fundering | 1.3 | 2FS-1w | FS4;FS8 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 208.5481 | 16683.8496 | 16683.8496 | 11.375
4 | boordstenen | 1.4 | 3FS | FS5 | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 26.563 | 1062.52 | 1062.52 | 4.375
5 | verharding | 1.5 | 4FS | FS6 | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 86.0285 | 3441.1399 | 3441.1399 | 4.375
6 | bekisting: voorbereding + beton gieten | 1.6 | 5FS | FS7 | 2013-12-02 08:00 | 2013-12-13 17:00 | 10d |  | 0 | 0 | 784.5386 | 62763.0898 | 62763.0898 | 11.375
7 | afwerking: straatmeubilair, signalisatie, ... | 1.7 | 6FS |  | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 426.514 | 17060.5605 | 17060.5605 | 4.375
8 | grondwerken &amp;amp;amp; onderfundering | 1.8 | 3FS | FS9 | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 242.015 | 9680.5996 | 9680.5996 | 4.375
9 | fundering | 1.9 | 8FS | FS10 | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 41.894 | 1675.76 | 1675.76 | 4.375
10 | boordstenen | 1.10 | 9FS | FS11 | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 86.625 | 3465 | 3465 | 4.375
11 | bekisting: voorbereding + beton gieten | 1.11 | 10FS | FS12 | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 190.6238 | 7624.9502 | 7624.9502 | 4.375
12 | afwerking: straatmeubilair, signalisatie, ... | 1.12 | 11FS |  | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 293.578 | 11743.1201 | 11743.1201 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | IJzertoren Memorial Square | 400h |  |  |  |  | 99 | 100 | 101
1 | opbraak &amp;amp;amp; riolering | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | grondwerken &amp;amp;amp; onderfundering | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | fundering | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | boordstenen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | verharding | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | bekisting: voorbereding + beton gieten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | afwerking: straatmeubilair, signalisatie, ... | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | grondwerken &amp;amp;amp; onderfundering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | fundering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | boordstenen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | bekisting: voorbereding + beton gieten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | afwerking: straatmeubilair, signalisatie, ... | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-10-31 17:00 |  | TP Name | 31/10, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | IJzertoren Memorial Square | 2013-10-14 08:00 | 2013-12-20 17:00 | 50d |  |  | 0 |  |  | 214417.7109 |  | 9d | [5 empty] | 29324.1816 |  | 15.53% |  | 33294.9596 | 61225.8516
1 | opbraak &amp;amp;amp; riolering | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 615.3959 | 49231.6719 | 49231.6719 | 2013-10-21 08:00 | 8d | 39385.3375 | 24615.8359 | 5d | -11056.6148 | 0 | 28328.7227 | 24615.8359 | 61.54% | Started | 30296.4146 | 49231.6719 | 100 | 80 | 61.5385 | 100 | 57.5417 | 61.5385
2 | grondwerken &amp;amp;amp; onderfundering | 2013-10-28 08:00 | 2013-11-08 17:00 | 10d |  | 0 | 0 | 374.8181 | 29985.4492 | 29985.4492 | 2013-10-31 08:00 | 1d | 2998.5449 | 26986.9043 | 9d | -2003.0859 | 0 | 995.459 | 26986.9043 | 10% | Started | 2998.545 | 11994.1797 | 100 | 10 | 10 | 100 | 3.3198 | 10
3 | fundering | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 208.5481 | 16683.8496 | 16683.8496 |  | 0 | 0 | 16683.8496 | 10d | 0 | 0 | 0 | 16683.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | boordstenen | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 26.563 | 1062.52 | 1062.52 |  | 0 | 0 | 1062.52 | 5d | 0 | 0 | 0 | 1062.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | verharding | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 86.0285 | 3441.1399 | 3441.1399 |  | 0 | 0 | 3441.1399 | 5d | 0 | 0 | 0 | 3441.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | bekisting: voorbereding + beton gieten | 2013-12-02 08:00 | 2013-12-13 17:00 | 10d |  | 0 | 0 | 784.5386 | 62763.0898 | 62763.0898 |  | 0 | 0 | 62763.0898 | 10d | 0 | 0 | 0 | 62763.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 426.514 | 17060.5605 | 17060.5605 |  | 0 | 0 | 17060.5605 | 5d | 0 | 0 | 0 | 17060.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | grondwerken &amp;amp;amp; onderfundering | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 242.015 | 9680.5996 | 9680.5996 |  | 0 | 0 | 9680.5996 | 5d | 0 | 0 | 0 | 9680.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | fundering | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 41.894 | 1675.76 | 1675.76 |  | 0 | 0 | 1675.76 | 5d | 0 | 0 | 0 | 1675.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | boordstenen | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 86.625 | 3465 | 3465 |  | 0 | 0 | 3465 | 5d | 0 | 0 | 0 | 3465 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | bekisting: voorbereding + beton gieten | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 190.6238 | 7624.9502 | 7624.9502 |  | 0 | 0 | 7624.9502 | 5d | 0 | 0 | 0 | 7624.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 293.578 | 11743.1201 | 11743.1201 |  | 0 | 0 | 11743.1201 | 5d | 0 | 0 | 0 | 11743.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-11-30 09:00 |  | TP Name | 30/11, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | IJzertoren Memorial Square | 2013-10-14 08:00 | 2013-12-20 17:00 | 50d |  |  | 0 |  |  | 214417.7109 |  | 30d | [5 empty] | 105692.2717 |  | 37.21% |  | 79787.1008 | 111760.9902
1 | opbraak &amp;amp;amp; riolering | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 615.3959 | 49231.6719 | 49231.6719 | 2013-10-21 08:00 | 12d | 59078.0062 | 4923.1672 | 1d | -20618.3842 | 0 | 38459.6221 | 4923.1672 | 92.31% | Started | 45444.6204 | 49231.6719 | 100 | 120 | 92.3077 | 100 | 78.1197 | 92.3077
2 | grondwerken &amp;amp;amp; onderfundering | 2013-10-28 08:00 | 2013-11-08 17:00 | 10d |  | 0 | 0 | 374.8181 | 29985.4492 | 29985.4492 | 2013-10-31 08:00 | 12d | 35982.5391 | 20989.8145 | 7d | 14777.4004 | 0 | 50759.9395 | 20989.8145 | 63.16% | Started | 18938.1777 | 29985.4492 | 100 | 120 | 63.1579 | 100 | 169.2819 | 63.1579
3 | fundering | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 208.5481 | 16683.8496 | 16683.8496 |  | 0 | 0 | 16683.8496 | 10d | 0 | 0 | 0 | 16683.8496 | 0% | Not Started | 0 | 16683.8496 | 100 |  | 0 | 100 |  | 0
4 | boordstenen | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 26.563 | 1062.52 | 1062.52 |  | 0 | 0 | 1062.52 | 5d | 0 | 0 | 0 | 1062.52 | 0% | Not Started | 0 | 1062.52 | 100 |  | 0 | 100 |  | 0
5 | verharding | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 86.0285 | 3441.1399 | 3441.1399 | 2013-11-13 08:00 | 3d | 2064.6839 | 0 | 0 | 4385.206 | 0 | 6449.8899 | 0 | 100% | Finished | 3441.1399 | 3441.1399 | 100 | 60 | 100 | 100 | 187.4347 | 100
6 | bekisting: voorbereding + beton gieten | 2013-12-02 08:00 | 2013-12-13 17:00 | 10d |  | 0 | 0 | 784.5386 | 62763.0898 | 62763.0898 | 2013-11-19 08:00 | 1d | 6276.309 | 56486.7809 | 9d | -2454.8793 | 0 | 3821.4297 | 56486.7809 | 10% | Started | 6276.3091 | 0 | 100 | 10 | 10 | 100 | 6.0887 | 10
7 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 426.514 | 17060.5605 | 17060.5605 | 2013-11-29 08:00 | 1d | 3412.1121 | 6824.2242 | 2d | 2789.2785 | 0 | 6201.3906 | 6824.2242 | 33.33% | Started | 5686.8537 | 0 | 100 | 20 | 33.3333 | 100 | 36.3493 | 33.3333
8 | grondwerken &amp;amp;amp; onderfundering | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 242.015 | 9680.5996 | 9680.5996 |  | 0 | 0 | 9680.5996 | 5d | 0 | 0 | 0 | 9680.5996 | 0% | Not Started | 0 | 9680.5996 | 100 |  | 0 | 100 |  | 0
9 | fundering | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 41.894 | 1675.76 | 1675.76 |  | 0 | 0 | 1675.76 | 5d | 0 | 0 | 0 | 1675.76 | 0% | Not Started | 0 | 1675.76 | 100 |  | 0 | 100 |  | 0
10 | boordstenen | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 86.625 | 3465 | 3465 |  | 0 | 0 | 3465 | 5d | 0 | 0 | 0 | 3465 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | bekisting: voorbereding + beton gieten | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 190.6238 | 7624.9502 | 7624.9502 |  | 0 | 0 | 7624.9502 | 5d | 0 | 0 | 0 | 7624.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 293.578 | 11743.1201 | 11743.1201 |  | 0 | 0 | 11743.1201 | 5d | 0 | 0 | 0 | 11743.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-12-31 16:00 |  | TP Name | 31/12, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | IJzertoren Memorial Square | 2013-10-14 08:00 | 2013-12-20 17:00 | 50d |  |  | 0 |  |  | 214417.7109 |  | 51d 7h | [5 empty] | 156594.4511 |  | 52.11% |  | 111730.4498 | 214417.7109
1 | opbraak &amp;amp;amp; riolering | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 615.3959 | 49231.6719 | 49231.6719 | 2013-10-21 08:00 | 13d | 64001.1734 | 0 | 0 | -24179.5016 | 0 | 39821.6719 | 0 | 100% | Finished | 49231.6719 | 49231.6719 | 100 | 130 | 100 | 100 | 80.8863 | 100
2 | grondwerken &amp;amp;amp; onderfundering | 2013-10-28 08:00 | 2013-11-08 17:00 | 10d |  | 0 | 0 | 374.8181 | 29985.4492 | 29985.4492 | 2013-10-31 08:00 | 18d | 53973.8086 | 2998.5449 | 1d | 4036.7109 | 0 | 58010.5195 | 2998.5449 | 94.74% | Started | 28407.2683 | 29985.4492 | 100 | 180 | 94.7368 | 100 | 193.4622 | 94.7368
3 | fundering | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 208.5481 | 16683.8496 | 16683.8496 |  | 0 | 0 | 16683.8496 | 10d | 0 | 0 | 0 | 16683.8496 | 0% | Not Started | 0 | 16683.8496 | 100 |  | 0 | 100 |  | 0
4 | boordstenen | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 26.563 | 1062.52 | 1062.52 | 2013-12-04 08:00 | 1d | 212.504 | 0 | 0 | 1371.806 | 0 | 1584.31 | 0 | 100% | Finished | 1062.52 | 1062.52 | 100 | 20 | 100 | 100 | 149.1087 | 100
5 | verharding | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 86.0285 | 3441.1399 | 3441.1399 | 2013-11-13 08:00 | 3d | 2064.6839 | 0 | 0 | 4385.206 | 0 | 6449.8899 | 0 | 100% | Finished | 3441.1399 | 3441.1399 | 100 | 60 | 100 | 100 | 187.4347 | 100
6 | bekisting: voorbereding + beton gieten | 2013-12-02 08:00 | 2013-12-13 17:00 | 10d |  | 0 | 0 | 784.5386 | 62763.0898 | 62763.0898 | 2013-11-19 08:00 | 1d | 6276.309 | 56486.7809 | 9d | 19162.1207 | 0 | 25438.4297 | 56486.7809 | 10% | Started | 6276.3091 | 62763.0898 | 100 | 10 | 10 | 100 | 40.5309 | 10
7 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 426.514 | 17060.5605 | 17060.5605 | 2013-11-29 08:00 | 2d | 6824.2242 | 3412.1121 | 1d | 337.8861 | 0 | 7162.1104 | 3412.1121 | 66.67% | Started | 11373.7074 | 17060.5605 | 100 | 40 | 66.6667 | 100 | 41.9805 | 66.6667
8 | grondwerken &amp;amp;amp; onderfundering | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 242.015 | 9680.5996 | 9680.5996 | 2013-12-09 08:00 | 3d | 5808.3598 | 7744.4797 | 4d | 3672.6498 | 0 | 9481.0096 | 7744.4797 | 42.86% | Started | 4148.8284 | 9680.5996 | 100 | 60 | 42.8571 | 100 | 97.9382 | 42.8571
9 | fundering | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 41.894 | 1675.76 | 1675.76 | 2013-12-18 08:00 | 2d | 670.304 | 335.152 | 1d | 1251.146 | 0 | 1921.45 | 335.152 | 66.67% | Started | 1117.1734 | 1675.76 | 100 | 40 | 66.6667 | 100 | 114.6614 | 66.6667
10 | boordstenen | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 86.625 | 3465 | 3465 |  | 0 | 0 | 3465 | 5d | 0 | 0 | 0 | 3465 | 0% | Not Started | 0 | 3465 | 100 |  | 0 | 100 |  | 0
11 | bekisting: voorbereding + beton gieten | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 190.6238 | 7624.9502 | 7624.9502 | 2013-12-09 08:00 | 7d | 10674.9303 | 1524.99 | 1d | -3949.8701 | 0 | 6725.0602 | 1524.99 | 87.5% | Started | 6671.8314 | 7624.9502 | 100 | 140 | 87.5 | 100 | 88.1981 | 87.5
12 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 293.578 | 11743.1201 | 11743.1201 |  | 0 | 0 | 11743.1201 | 5d | 0 | 0 | 0 | 11743.1201 | 0% | Not Started | 0 | 11743.1201 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-01-31 16:00 |  | TP Name | 31/01, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | IJzertoren Memorial Square | 2013-10-14 08:00 | 2013-12-20 17:00 | 50d |  |  | 0 |  |  | 214417.7109 |  | 74d 7h | [5 empty] | 194759.6012 |  | 88.89% |  | 190587.9334 | 214417.7109
1 | opbraak &amp;amp;amp; riolering | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 615.3959 | 49231.6719 | 49231.6719 | 2013-10-21 08:00 | 13d | 64001.1734 | 0 | 0 | -22757.8717 | 0 | 41243.3018 | 0 | 100% | Finished | 49231.6719 | 49231.6719 | 100 | 130 | 100 | 100 | 83.7739 | 100
2 | grondwerken &amp;amp;amp; onderfundering | 2013-10-28 08:00 | 2013-11-08 17:00 | 10d |  | 0 | 0 | 374.8181 | 29985.4492 | 29985.4492 | 2013-10-31 08:00 | 18d | 53973.8086 | 2998.5449 | 1d | 4094.3516 | 0 | 58068.1602 | 2998.5449 | 94.74% | Started | 28407.2683 | 29985.4492 | 100 | 180 | 94.7368 | 100 | 193.6545 | 94.7368
3 | fundering | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 208.5481 | 16683.8496 | 16683.8496 | 2014-01-06 08:00 | 2d | 3336.7699 | 0 | 0 | -1544.5805 | 0 | 1792.1895 | 0 | 100% | Finished | 16683.8496 | 16683.8496 | 100 | 20 | 100 | 100 | 10.7421 | 100
4 | boordstenen | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 26.563 | 1062.52 | 1062.52 | 2013-12-04 08:00 | 1d | 212.504 | 0 | 0 | 1371.806 | 0 | 1584.31 | 0 | 100% | Finished | 1062.52 | 1062.52 | 100 | 20 | 100 | 100 | 149.1087 | 100
5 | verharding | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 86.0285 | 3441.1399 | 3441.1399 | 2013-11-13 08:00 | 3d | 2064.6839 | 0 | 0 | 4385.206 | 0 | 6449.8899 | 0 | 100% | Finished | 3441.1399 | 3441.1399 | 100 | 60 | 100 | 100 | 187.4347 | 100
6 | bekisting: voorbereding + beton gieten | 2013-12-02 08:00 | 2013-12-13 17:00 | 10d |  | 0 | 0 | 784.5386 | 62763.0898 | 62763.0898 | 2013-11-19 08:00 | 7d | 43934.1629 | 0 | 0 | 14036.2868 | 0 | 57970.4497 | 0 | 100% | Finished | 62763.0898 | 62763.0898 | 100 | 70 | 100 | 100 | 92.3639 | 100
7 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 426.514 | 17060.5605 | 17060.5605 | 2013-11-29 08:00 | 3d | 10236.3363 | 0 | 0 | -756.3759 | 0 | 9479.9604 | 0 | 100% | Finished | 17060.5605 | 17060.5605 | 100 | 60 | 100 | 100 | 55.5665 | 100
8 | grondwerken &amp;amp;amp; onderfundering | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 242.015 | 9680.5996 | 9680.5996 | 2013-12-09 08:00 | 3d | 5808.3598 | 7744.4797 | 4d | 3716.4698 | 0 | 9524.8296 | 7744.4797 | 42.86% | Started | 4148.8284 | 9680.5996 | 100 | 60 | 42.8571 | 100 | 98.3909 | 42.8571
9 | fundering | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 41.894 | 1675.76 | 1675.76 | 2013-12-18 08:00 | 2d | 670.304 | 335.152 | 1d | 1251.146 | 0 | 1921.45 | 335.152 | 66.67% | Started | 1117.1734 | 1675.76 | 100 | 40 | 66.6667 | 100 | 114.6614 | 66.6667
10 | boordstenen | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 86.625 | 3465 | 3465 |  | 0 | 0 | 3465 | 5d | 0 | 0 | 0 | 3465 | 0% | Not Started | 0 | 3465 | 100 |  | 0 | 100 |  | 0
11 | bekisting: voorbereding + beton gieten | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 190.6238 | 7624.9502 | 7624.9502 | 2013-12-09 08:00 | 7d | 10674.9303 | 1524.99 | 1d | -3949.8701 | 0 | 6725.0602 | 1524.99 | 87.5% | Started | 6671.8314 | 7624.9502 | 100 | 140 | 87.5 | 100 | 88.1981 | 87.5
12 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 293.578 | 11743.1201 | 11743.1201 |  | 0 | 0 | 11743.1201 | 5d | 0 | 0 | 0 | 11743.1201 | 0% | Not Started | 0 | 11743.1201 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-02-28 16:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | IJzertoren Memorial Square | 2013-10-14 08:00 | 2013-12-20 17:00 | 50d |  |  | 0 |  |  | 214417.7109 |  | 94d | [5 empty] | 224789.6707 |  | 100% |  | 214417.7109 | 214417.7109
1 | opbraak &amp;amp;amp; riolering | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 615.3959 | 49231.6719 | 49231.6719 | 2013-10-21 08:00 | 13d | 64001.1734 | 0 | 0 | -22405.4918 | 0 | 41595.6816 | 0 | 100% | Finished | 49231.6719 | 49231.6719 | 100 | 130 | 100 | 100 | 84.4897 | 100
2 | grondwerken &amp;amp;amp; onderfundering | 2013-10-28 08:00 | 2013-11-08 17:00 | 10d |  | 0 | 0 | 374.8181 | 29985.4492 | 29985.4492 | 2013-10-31 08:00 | 19d | 56972.3535 | 0 | 0 | 2114.1758 | 0 | 59086.5293 | 0 | 100% | Finished | 29985.4492 | 29985.4492 | 100 | 190 | 100 | 100 | 197.0507 | 100
3 | fundering | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 208.5481 | 16683.8496 | 16683.8496 | 2014-01-06 08:00 | 2d | 3336.7699 | 0 | 0 | -1544.5805 | 0 | 1792.1895 | 0 | 100% | Finished | 16683.8496 | 16683.8496 | 100 | 20 | 100 | 100 | 10.7421 | 100
4 | boordstenen | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 26.563 | 1062.52 | 1062.52 | 2013-12-04 08:00 | 1d | 212.504 | 0 | 0 | 1371.806 | 0 | 1584.31 | 0 | 100% | Finished | 1062.52 | 1062.52 | 100 | 20 | 100 | 100 | 149.1087 | 100
5 | verharding | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 86.0285 | 3441.1399 | 3441.1399 | 2013-11-13 08:00 | 3d | 2064.6839 | 0 | 0 | 5165.706 | 0 | 7230.3899 | 0 | 100% | Finished | 3441.1399 | 3441.1399 | 100 | 60 | 100 | 100 | 210.1161 | 100
6 | bekisting: voorbereding + beton gieten | 2013-12-02 08:00 | 2013-12-13 17:00 | 10d |  | 0 | 0 | 784.5386 | 62763.0898 | 62763.0898 | 2013-11-19 08:00 | 7d | 43934.1629 | 0 | 0 | 14036.2868 | 0 | 57970.4497 | 0 | 100% | Finished | 62763.0898 | 62763.0898 | 100 | 70 | 100 | 100 | 92.3639 | 100
7 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 426.514 | 17060.5605 | 17060.5605 | 2013-11-29 08:00 | 3d | 10236.3363 | 0 | 0 | 5795.6242 | 0 | 16031.9606 | 0 | 100% | Finished | 17060.5605 | 17060.5605 | 100 | 60 | 100 | 100 | 93.9709 | 100
8 | grondwerken &amp;amp;amp; onderfundering | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 242.015 | 9680.5996 | 9680.5996 | 2013-12-09 08:00 | 7d | 13552.8395 | 0 | 0 | 3496.0302 | 0 | 17048.8696 | 0 | 100% | Finished | 9680.5996 | 9680.5996 | 100 | 140 | 100 | 100 | 176.1138 | 100
9 | fundering | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 41.894 | 1675.76 | 1675.76 | 2013-12-18 08:00 | 3d | 1005.456 | 0 | 0 | 1934.3541 | 0 | 2939.8101 | 0 | 100% | Finished | 1675.76 | 1675.76 | 100 | 60 | 100 | 100 | 175.4314 | 100
10 | boordstenen | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 86.625 | 3465 | 3465 | 2014-02-26 08:00 | 1d | 693 | 0 | 0 | 325.3701 | 0 | 1018.3701 | 0 | 100% | Finished | 3465 | 3465 | 100 | 20 | 100 | 100 | 29.3902 | 100
11 | bekisting: voorbereding + beton gieten | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 190.6238 | 7624.9502 | 7624.9502 | 2013-12-09 08:00 | 8d | 12199.9203 | 0 | 0 | -4456.4901 | 0 | 7743.4302 | 0 | 100% | Finished | 7624.9502 | 7624.9502 | 100 | 160 | 100 | 100 | 101.5538 | 100
12 | afwerking: straatmeubilair, signalisatie, ... | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 293.578 | 11743.1201 | 11743.1201 | 2014-02-21 08:00 | 5d | 11743.1201 | 0 | 0 | -995.44 | 0 | 10747.6801 | 0 | 100% | Finished | 11743.1201 | 11743.1201 | 100 | 100 | 100 | 100 | 91.5232 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
31/10, 2013 | 2013-10-14 08:00 | 2013-10-31 17:00 | 61225.8516 | 33294.9596 | 29324.1816 | 2013-10-22 15:00 | -27930.892 | 54.38% | 3970.7779 | 113.5% | -7d 2h | 48.21% | 91.17% | 2013-12-31 12:00 | 2014-02-18 17:00 | 2014-02-03 17:00 | 2013-12-31 11:00 | 2014-02-18 17:00 | 2014-02-05 14:00 | 2014-01-01 10:00 | 2014-03-06 15:00 | 2014-02-19 17:00 | 210446.933 | 188846.1192 | 362389.4515 | 404986.1845 | 322667.877 | 360184.4967 | 207403.7568 | 209589.5348 | 0.48214 | 1.1354 | 0.54381 | 0.91168 | -7.25 | 1.1354 | 1 | 0.48214 | 1
30/11, 2013 | 2013-10-31 17:00 | 2013-11-30 09:00 | 111760.9902 | 79787.1008 | 105692.2717 | 2013-11-07 10:00 | -31973.8895 | 71.39% | -25905.171 | 75.49% | -16d 6h | 52.14% | 81.09% | 2014-01-01 12:00 | 2014-01-17 17:00 | 2014-02-19 15:00 | 2014-01-03 17:00 | 2014-01-17 17:00 | 2014-02-04 11:00 | 2014-01-14 15:00 | 2014-02-24 16:00 | 2014-03-24 14:00 | 240322.8819 | 284034.5713 | 294274.7639 | 363887.9625 | 355503.4795 | 447718.5998 | 285992.6648 | 295793.2558 | 0.52143 | 0.7549 | 0.71391 | 0.81095 | -16.75 | 0.7549 | 1 | 0.52143 | 1
31/12, 2013 | 2013-11-30 09:00 | 2013-12-31 16:00 | 214417.7109 | 111730.4498 | 156594.4511 | 2013-11-29 16:00 | -102687.2611 | 52.11% | -44864.0013 | 71.35% | -22d | 61.32% | 78.22% | 2014-01-23 17:00 | 2014-02-24 17:00 | 2014-04-18 12:00 | 2014-02-07 09:00 | 2014-03-14 09:00 | 2014-04-14 09:00 | 2014-01-21 17:00 | 2014-02-04 12:00 | 2014-02-18 12:00 | 259281.7123 | 300514.5313 | 353657.7182 | 324059.3394 | 432786.073 | 391302.8256 | 308719.4144 | 304678.5218 | 0.61319 | 0.7135 | 0.52109 | 0.78223 | -22 | 0.7135 | 1 | 0.61319 | 1
31/01, 2014 | 2013-12-31 16:00 | 2014-01-31 16:00 | 214417.7109 | 190587.9334 | 194759.6012 | 2013-12-16 15:00 | -23829.7776 | 88.89% | -4171.6678 | 97.86% | -34d 1h | 57.28% | 92.71% | 2013-12-30 12:00 | 2013-12-31 10:00 | 2014-01-01 12:00 | 2014-02-13 15:00 | 2014-02-14 16:00 | 2014-02-17 09:00 | 2014-02-07 09:00 | 2014-02-12 10:00 | 2014-02-12 12:00 | 218589.3788 | 219110.9749 | 221568.8869 | 236364.0489 | 222155.6997 | 237274.7044 | 219565.8286 | 221313.3017 | 0.57277 | 0.97858 | 0.88886 | 0.92709 | -34.125 | 0.97858 | 1 | 0.57277 | 1
Actual Schedule | 2014-01-31 16:00 | 2014-02-28 16:00 | 214417.7109 | 214417.7109 | 224789.6707 | 2013-12-20 17:00 | 0 | 100% | -10371.9597 | 95.39% | -49d 7h | 50.06% | 100% | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-25 11:00 | 2014-02-28 16:00 | 2014-02-28 16:00 | 2014-02-28 16:00 | 2014-02-28 16:00 | 2014-02-28 16:00 | 2014-02-28 16:00 | 224789.6707 | 224789.6707 | 224789.6707 | 224789.6707 | 224789.6707 | 224789.6707 | 224789.6707 | 224789.6707 | 0.50063 | 0.95386 | 1 | 1 | -49.875 | 0.95386 | 1 | 0.50063 | 1