## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | SCM System | 1 |  |  | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 | 1012.375
1 | Project has started | 1.1 |  | FS2;FS3;FS4;FS5;FS6;FS7 | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -2.625
127 | Phase 1: Global Analysis and Analysis Early Validation | 1.2 |  |  | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 | 81.375
2 | Prepare next visit | 1.2.1 | 1FS | FS3;FS4;FS5;FS6;FS7 | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 4.375
3 | Global Analysis of the Planning Cycle | 1.2.2 | 1FS;2FS | FS9 | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 25.375
4 | Analyse details for Integration by Excel | 1.2.3 | 1FS;2FS | FS9 | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 6.375
5 | Analyse Master planning rules in detail for plant A | 1.2.4 | 1FS;2FS | FS9;FS14;FS15;FS16;FS17;FS18;FS19;FS20;FS21;FS22;FS23;FS24;FS25;FS26;FS27;FS28;FS29;FS30;FS12;FS13 | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 13.375
6 | Analyse gaps of Master planning rules in detail for plant B | 1.2.5 | 1FS;2FS |  | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 25.375
7 | Analyse gaps of Master planning rules for other plants | 1.2.6 | 1FS;2FS | FS9 | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 27.375
8 | Analyse DRP for Early Validation (incl. deployment engine) | 1.2.7 |  |  | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 18.375
9 | Validate concept internal + prepare document/presentation for next visit | 1.2.8 | 3FS;4FS;5FS;7FS | FS10 | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 13.375
10 | Validate Analysis with Business and get acceptance | 1.2.9 | 9FS | FS11 | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 6.375
11 | Phase 1: Global Analysis is accepted and phase is closed | 1.2.10 | 10FS | FS14;FS15;FS16;FS17;FS18;FS19;FS20;FS21;FS22;FS23;FS24;FS25;FS26;FS27;FS28;FS29;FS30;FS31 | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
128 | Phase 1: Global Analysis and Analysis Early Validation | 1.3 |  |  | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 | 102.375
135 | Minimum implementation needed for Early Validation | 1.3.1 |  |  | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 | 102.375
12 | Setup the environment | 1.3.1.1 | 5FS |  | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 11.375
13 | Received Master data for building the DRP model and MPS Model | 1.3.1.2 | 5FS | FS20 | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
131 | Model integration | 1.3.1.3 |  |  | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 | 18.375
14 | Model integration of Operational forecast and Sales Orders | 1.3.1.3.1 | 11FS;5FS | SS15+2h;FS19 | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 4.375
15 | Model integration of the DRP master data and network | 1.3.1.3.2 | 14SS+2h;11FS;5FS | SS16+5h | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 6.375
16 | Model integration of the MPS Master data (routings, BOM's,…) | 1.3.1.3.3 | 15SS+5h;11FS;5FS | SS17+7h | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 11.375
17 | Model integration of the inventory | 1.3.1.3.4 | 16SS+7h;11FS;5FS |  | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 4.375
18 | Coordination | 1.3.1.3.5 | 11FS;5FS |  | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 17.375
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 1.3.1.4 | 14FS;11FS;5FS |  | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 11.375
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 1.3.1.5 |  |  | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 | 53.375
20 | Check master data from Excel | 1.3.1.5.1 | 13FS;11FS;5FS | FS21 | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
21 | Build DRP model | 1.3.1.5.2 | 20FS;11FS;5FS | SS22+1d 6h | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 18.375
22 | Test off-line the DRP model | 1.3.1.5.3 | 21SS+1d 6h;11FS;5FS | FS23 | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 4.375
23 | Validate DRP with Business | 1.3.1.5.4 | 22FS;11FS;5FS |  | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
24 | Coordination | 1.3.1.5.5 | 11FS;5FS |  | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 52.375
133 | Build Master Planning model for Early validation (no campaigns) | 1.3.1.6 |  |  | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 | 67.375
25 | Check master data for two test plants | 1.3.1.6.1 | 11FS;5FS | FS26 | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 4.375
26 | Build Master Planning Model for two test plants | 1.3.1.6.2 | 25FS;11FS;5FS | SS27+2d 5h | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 25.375
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 1.3.1.6.3 | 26SS+2d 5h;11FS;5FS | SS28+7h | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 11.375
28 | Test off-line the Master Planning | 1.3.1.6.4 | 27SS+7h;11FS;5FS | FS29 | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 4.375
29 | Validate Master Planning with Business | 1.3.1.6.5 | 28FS;11FS;5FS | FS31 | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 11.375
30 | Coordination | 1.3.1.6.6 | 11FS;5FS | FS31 | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 66.375
31 | Phase 2: Early Validation is accepted | 1.3.2 | 11FS;29FS;30FS | FS32 | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
129 | Phase 3: Full Implementation of DRP and Master Planning | 1.4 |  |  | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 | 651
32 | Purchase Order for Implementation is received | 1.4.1 | 31FS | FS33;FS34;FS35;FS36;FS37;FS38;FS39 | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
136 | Analyse DRP and Master Planing | 1.4.2 |  |  | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 | 35
33 | Analyze remaining details for Integration (final) | 1.4.2.1 | 32FS | FS40;FS41;FS42 | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 32.375
34 | Analyze Order allocation rules in detail | 1.4.2.2 | 32FS | FS51;FS52;FS53;FS54;FS55;FS56 | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 32.375
35 | Analyze DRP rules in detail | 1.4.2.3 | 32FS | FS57;FS58;FS59;FS60;FS61;FS62;FS63;FS64;FS67;FS69;FS65;FS68 | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 32.375
36 | Analyse shape Campaign rules in detail for plant A | 1.4.2.4 | 32FS |  | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 32.375
37 | Analyse shape Campaign rules in detail for plant B | 1.4.2.5 | 32FS |  | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 32.375
38 | Analyse gaps of Master planning rules in detail for remaining plants | 1.4.2.6 | 32FS |  | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 32.375
39 | Analysis of DRP and Master Planning is finished | 1.4.2.7 | 32FS | FS40;FS41;FS42;FS49 | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
137 | Implement Integration | 1.4.3 |  |  | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 | 67.375
148 | Model integration | 1.4.3.1 |  |  | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 | 4.375
40 | Configure SAI2 | 1.4.3.1.1 | 33FS;39FS |  | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 0.041667
41 | Model integration of the feedback on Transport/Purchase orders | 1.4.3.1.2 | 33FS;39FS |  | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 4.375
42 | Model integration of the feedback on Manufacturing Orders | 1.4.3.1.3 | 33FS;39FS | FS43;FS44;FS45;FS57;FS58;FS59;FS60;FS61;FS62;FS63;FS64;FS67;FS69;FS65;FS68 | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 4.375
145 | Model integration from DRP | 1.4.3.2 |  |  | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 | 11.375
43 | Model integration of intercompany Transport orders | 1.4.3.2.1 | 42FS | FS46;FS47;FS48 | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
44 | Model integration of Purchase Orders | 1.4.3.2.2 | 42FS | FS46;FS47;FS48 | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
45 | Model Purchase requisitions to data warehouse | 1.4.3.2.3 | 42FS | FS46;FS47;FS48 | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 11.375
144 | Model integration from Master Planning | 1.4.3.3 |  |  | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 | 11.375
46 | Configure SAI3 and SAI4b | 1.4.3.3.1 | 43FS;44FS;45FS | FS50;FS50 | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 0.041667
47 | Model integration of Manufacturing Orders to ASI and Excel | 1.4.3.3.2 | 43FS;44FS;45FS |  | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 11.375
48 | Model integration of Manufacturing requisitions | 1.4.3.3.3 | 43FS;44FS;45FS | FS50 | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 11.375
49 | Coordination | 1.4.3.4 | 39FS | FS50 | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 31.375
50 | Implementation of the Integration is finished | 1.4.3.5 | 46FS;46FS;48FS;49FS |  | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
138 | Implement Order Allocation | 1.4.4 |  |  | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 | 21
51 | Received Forecast and Customer Orders from customer for off-line application testing | 1.4.4.1 | 34FS | FS52 | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
52 | Complete Order Allocation model with rules | 1.4.4.2 | 51FS;34FS | FS53 | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 4.375
53 | Off-line application testing + check data | 1.4.4.3 | 52FS;34FS | FS54 | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 4.375
54 | Validate Order Allocation with Business | 1.4.4.4 | 53FS;34FS | FS56 | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 4.375
55 | Coordination | 1.4.4.5 | 34FS | FS56 | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 17.375
56 | Implementation of the Order Allocation is finished | 1.4.4.6 | 54FS;55FS;34FS | FS57;FS58;FS70;FS71;FS72;FS73;FS74;FS75;FS76;FS77;FS78;FS79;FS80 | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
139 | Implement DRP for complete US Market | 1.4.5 |  |  | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 | 182
57 | Received Master data for building the DRP model | 1.4.5.1 | 35FS;42FS;56FS | FS58;FS59 | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
58 | Check master data | 1.4.5.2 | 57FS;35FS;42FS;56FS | FS59;FS60;FS71 | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
59 | Complete Build DRP model | 1.4.5.3 | 58FS;35FS;42FS;57FS | FS60;FS61;FS61 | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 18.375
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 1.4.5.4 | 59FS;35FS;42FS;58FS | FS62;FS62 | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
61 | Model manufacturing requirements for Master Planning | 1.4.5.5 | 59FS;35FS;42FS;59FS | FS62;FS63 | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
62 | Test off-line the DRP model | 1.4.5.6 | 60FS;61FS;35FS;42FS;60FS | FS63;FS64;FS72 | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 11.375
63 | Validate DRP with Business | 1.4.5.7 | 62FS;35FS;42FS;61FS | FS64;FS73 | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 18.375
64 | Integration test, Dry-run tests and GO-live of DRP | 1.4.5.8 | 63FS;35FS;42FS;62FS |  | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 18.375
65 | Interactive DRP with basic solvers is live | 1.4.5.9 | 35FS;42FS | FS67;FS76 | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
66 | Assistence after go-live | 1.4.5.10 |  | FS67 | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 18.375
67 | Adapt Solver for pushing surplus inventory to RDC's | 1.4.5.11 | 66FS;35FS;42FS;65FS | FS69;FS69 | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 39.375
68 | Coordination | 1.4.5.12 | 35FS;42FS | FS69 | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 178.375
69 | Implementation of DRP for the complete US Market is finished | 1.4.5.13 | 67FS;68FS;35FS;42FS;67FS | FS77 | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 1.4.6 |  |  | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 | 517
70 | Received Master Data for building the Master Planning model | 1.4.6.1 | 56FS | FS72 | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
71 | Check master data of plant A | 1.4.6.2 | 58FS;56FS | FS73 | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
72 | Test off-line the Master Planning | 1.4.6.3 | 62FS;70FS;56FS | FS74 | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 18.375
73 | Validate Master Planning with Business + on the job training | 1.4.6.4 | 63FS;71FS;56FS | FS75 | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 39.375
74 | Configure Shape Campaigns for plant A | 1.4.6.5 | 72FS;56FS | FS76 | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 60.375
75 | Validate Shape campaigns with plant A Business + on the job training | 1.4.6.6 | 73FS;56FS | FS77 | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 39.375
76 | Dry-run tests and GO-live of MPS in plant A | 1.4.6.7 | 65FS;74FS;56FS | FS78;FS82;FS83;FS84;FS85;FS86;FS87;FS88;FS89;FS90;FS91;FS92;FS93;FS94;FS95 | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 25.375
77 | Interactive MPS with basic solvers at plant A is live | 1.4.6.8 | 69FS;75FS;56FS | FS79 | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
78 | Assistence after go-live | 1.4.6.9 | 76FS;56FS | FS81 | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 18.375
79 | Refine basic Solver | 1.4.6.10 | 77FS;56FS | FS81 | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 39.375
80 | Coordination | 1.4.6.11 | 56FS | FS90;FS91 | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 329.375
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 1.4.6.12 | 78FS;79FS |  | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
141 | Implement Master Planning GO LIVE 2 | 1.4.7 |  |  | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 | 189
82 | Received Master Data for building the Master Planning model | 1.4.7.1 | 76FS | FS83 | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
83 | Check master data of go live 2 | 1.4.7.2 | 82FS;76FS | FS84 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
84 | Adapt Master Planning Model to go live 2 | 1.4.7.3 | 83FS;76FS | FS85;FS86 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 39.375
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 1.4.7.4 | 84FS;76FS | FS87 | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
86 | Adapt Shape Campaigns configuration for plant B | 1.4.7.5 | 84FS;76FS | FS87 | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 25.375
87 | Test off-line the Master Planning | 1.4.7.6 | 85FS;86FS;76FS | FS88 | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
88 | Validate Master Planning with plant B Business | 1.4.7.7 | 87FS;76FS | FS89 | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 11.375
89 | Validate Shape campaigns with plant B Business | 1.4.7.8 | 88FS;76FS | FS90 | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
90 | Dry-run tests and GO-live of MPS in plant B | 1.4.7.9 | 80FS;89FS;76FS | FS91 | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 11.375
91 | Interactive MPS with basic solvers at plant B is live | 1.4.7.10 | 80FS;90FS;76FS | FS92;FS96;FS97;FS98;FS99;FS100;FS101;FS102;FS103;FS104;FS105;FS106;FS107;FS108 | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
92 | Assistence after go-live | 1.4.7.11 | 91FS;76FS | FS93 | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 11.375
93 | Refine basic Solver | 1.4.7.12 | 92FS;76FS | FS95 | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 25.375
94 | Coordination | 1.4.7.13 | 76FS | FS95 | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 178.375
95 | Implementation of Master Planning in plant B with LUT is finished | 1.4.7.14 | 93FS;94FS;76FS | FS103;FS104 | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
142 | Implement Master Planning GO LIVE 3 | 1.4.8 |  |  | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 | 175
96 | Received Master Data for building the Master Planning model | 1.4.8.1 | 91FS | FS97;FS98 | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
97 | Analyse Added Value planning process | 1.4.8.2 | 96FS;91FS |  | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 46.375
98 | Check master data | 1.4.8.3 | 96FS;91FS | FS99;FS100 | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 11.375
99 | Adapt Master Planning Model to remaining plants | 1.4.8.4 | 98FS;91FS | FS101 | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 46.375
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 1.4.8.5 | 98FS;91FS | FS101 | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 25.375
101 | Test off-line the Master Planning | 1.4.8.6 | 99FS;100FS;91FS | FS102 | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 11.375
102 | Validate Master Planning with remaining plants Business | 1.4.8.7 | 101FS;91FS | FS103 | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 32.375
103 | Dry-run tests and GO-live of MPS in remaining plants | 1.4.8.8 | 95FS;102FS;91FS | FS104 | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 25.375
104 | Interactive MPS with basic solvers at remaining plants is live | 1.4.8.9 | 95FS;103FS;91FS | FS105 | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
105 | Assistence after go-live | 1.4.8.10 | 104FS;91FS | FS106 | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 11.375
106 | Refine basic Solver | 1.4.8.11 | 105FS;91FS | FS108 | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 4.375
107 | Coordination | 1.4.8.12 | 91FS | FS108 | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 168.375
108 | Implementation of Master Planning in remaining plants is finished | 1.4.8.13 | 106FS;107FS;91FS | FS109 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 1.4.9 | 108FS | FS110 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
130 | Phase 4: Implementation of S&OP Planning | 1.5 |  |  | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 | 200.375
152 | Analysis of S&OP Planning | 1.5.1 |  |  | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 | 32.375
110 | Analyze details for Integration with S&OP | 1.5.1.1 | 109FS | FS111 | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 4.375
111 | Analyze S&OP rules in detail | 1.5.1.2 | 110FS | FS112 | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 18.375
112 | Analyze integration of S&OP in DRP and Master Planning | 1.5.1.3 | 111FS | FS113 | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 4.375
113 | Analysis of S&OP Planning is finished | 1.5.1.4 | 112FS | FS114;FS124 | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
153 | Implementation of S&OP Planning | 1.5.2 |  |  | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 | 168
114 | Received Master data for building the S&OP model | 1.5.2.1 | 113FS | FS115 | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
115 | Check master data | 1.5.2.2 | 114FS | FS116 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 4.375
116 | Build S&OP model | 1.5.2.3 | 115FS | FS117 | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 | 53.375
117 | Configure basic solvers | 1.5.2.4 | 116FS | FS118 | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 18.375
118 | Test off-line the S&OP model | 1.5.2.5 | 117FS | FS119 | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 4.375
119 | Validate S&OP with Business | 1.5.2.6 | 118FS | FS120 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 18.375
120 | Integration test, Dry-run tests and GO-live of S&OP | 1.5.2.7 | 119FS | FS121 | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 4.375
121 | Interactive S&OP with basic solvers is live | 1.5.2.8 | 120FS | FS122 | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
122 | Assistence after go-live | 1.5.2.9 | 121FS | FS123 | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 4.375
123 | Refine basic Solver for S&OP | 1.5.2.10 | 122FS | FS125 | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 | 38.375
124 | Coordination | 1.5.2.11 | 113FS | FS125 | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 157.375
125 | Implementation of S&OP Planning is finished | 1.5.2.12 | 123FS;124FS | FS126 | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
126 | Project is closed | 1.6 | 125FS |  | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | SCM System | 5800h |  |  |  |  | 99 | 100 | 101
1 | Project has started | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | Phase 1: Global Analysis and Analysis Early Validation | 480h |  |  |  |  | 99 | 100 | 101
2 | Prepare next visit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Global Analysis of the Planning Cycle | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Analyse details for Integration by Excel | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Analyse Master planning rules in detail for plant A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Analyse gaps of Master planning rules in detail for plant B | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Analyse gaps of Master planning rules for other plants | 160h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
8 | Analyse DRP for Early Validation (incl. deployment engine) | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
9 | Validate concept internal + prepare document/presentation for next visit | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
10 | Validate Analysis with Business and get acceptance | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
11 | Phase 1: Global Analysis is accepted and phase is closed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | Phase 1: Global Analysis and Analysis Early Validation | 600h |  |  |  |  | 99 | 100 | 101
135 | Minimum implementation needed for Early Validation | 600h |  |  |  |  | 99 | 100 | 101
12 | Setup the environment | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Received Master data for building the DRP model and MPS Model | 0 | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
131 | Model integration | 120h |  |  |  |  | 99 | 100 | 101
14 | Model integration of Operational forecast and Sales Orders | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
15 | Model integration of the DRP master data and network | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
16 | Model integration of the MPS Master data (routings, BOM's,…) | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
17 | Model integration of the inventory | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
18 | Coordination | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 320h |  |  |  |  | 99 | 100 | 101
20 | Check master data from Excel | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
21 | Build DRP model | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
22 | Test off-line the DRP model | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
23 | Validate DRP with Business | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
24 | Coordination | 312h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | Build Master Planning model for Early validation (no campaigns) | 400h |  |  |  |  | 99 | 100 | 101
25 | Check master data for two test plants | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
26 | Build Master Planning Model for two test plants | 160h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
28 | Test off-line the Master Planning | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
29 | Validate Master Planning with Business | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
30 | Coordination | 392h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Phase 2: Early Validation is accepted | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | Phase 3: Full Implementation of DRP and Master Planning | 3720h |  |  |  |  | 99 | 100 | 101
32 | Purchase Order for Implementation is received | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | Analyse DRP and Master Planing | 200h |  |  |  |  | 99 | 100 | 101
33 | Analyze remaining details for Integration (final) | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Analyze Order allocation rules in detail | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Analyze DRP rules in detail | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Analyse shape Campaign rules in detail for plant A | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Analyse shape Campaign rules in detail for plant B | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Analyse gaps of Master planning rules in detail for remaining plants | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Analysis of DRP and Master Planning is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | Implement Integration | 400h |  |  |  |  | 99 | 100 | 101
148 | Model integration | 40h |  |  |  |  | 99 | 100 | 101
40 | Configure SAI2 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Model integration of the feedback on Transport/Purchase orders | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
42 | Model integration of the feedback on Manufacturing Orders | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
145 | Model integration from DRP | 80h |  |  |  |  | 99 | 100 | 101
43 | Model integration of intercompany Transport orders | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
44 | Model integration of Purchase Orders | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
45 | Model Purchase requisitions to data warehouse | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
144 | Model integration from Master Planning | 80h |  |  |  |  | 99 | 100 | 101
46 | Configure SAI3 and SAI4b | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Model integration of Manufacturing Orders to ASI and Excel | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
48 | Model integration of Manufacturing requisitions | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
49 | Coordination | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Implementation of the Integration is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | Implement Order Allocation | 120h |  |  |  |  | 99 | 100 | 101
51 | Received Forecast and Customer Orders from customer for off-line application testing | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Complete Order Allocation model with rules | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
53 | Off-line application testing + check data | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
54 | Validate Order Allocation with Business | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
55 | Coordination | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Implementation of the Order Allocation is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | Implement DRP for complete US Market | 1040h |  |  |  |  | 99 | 100 | 101
57 | Received Master data for building the DRP model | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Check master data | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Complete Build DRP model | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
61 | Model manufacturing requirements for Master Planning | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
62 | Test off-line the DRP model | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
63 | Validate DRP with Business | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
64 | Integration test, Dry-run tests and GO-live of DRP | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
65 | Interactive DRP with basic solvers is live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Assistence after go-live | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
67 | Adapt Solver for pushing surplus inventory to RDC's | 240h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
68 | Coordination | 1032h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
69 | Implementation of DRP for the complete US Market is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | Complete Implemention Master Planning GO LIVE 1 | 2952h |  |  |  |  | 99 | 100 | 101
70 | Received Master Data for building the Master Planning model | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Check master data of plant A | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
72 | Test off-line the Master Planning | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
73 | Validate Master Planning with Business + on the job training | 240h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
74 | Configure Shape Campaigns for plant A | 360h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
75 | Validate Shape campaigns with plant A Business + on the job training | 240h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
76 | Dry-run tests and GO-live of MPS in plant A | 160h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
77 | Interactive MPS with basic solvers at plant A is live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | Assistence after go-live | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
79 | Refine basic Solver | 240h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
80 | Coordination | 1888h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | Implement Master Planning GO LIVE 2 | 1080h |  |  |  |  | 99 | 100 | 101
82 | Received Master Data for building the Master Planning model | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Check master data of go live 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | Adapt Master Planning Model to go live 2 | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | Adapt Shape Campaigns configuration for plant B | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | Test off-line the Master Planning | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | Validate Master Planning with plant B Business | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | Validate Shape campaigns with plant B Business | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | Dry-run tests and GO-live of MPS in plant B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | Interactive MPS with basic solvers at plant B is live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | Assistence after go-live | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Refine basic Solver | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | Coordination | 1032h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | Implementation of Master Planning in plant B with LUT is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | Implement Master Planning GO LIVE 3 | 1000h |  |  |  |  | 99 | 100 | 101
96 | Received Master Data for building the Master Planning model | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | Analyse Added Value planning process | 280h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
98 | Check master data | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
99 | Adapt Master Planning Model to remaining plants | 280h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 160h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
101 | Test off-line the Master Planning | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
102 | Validate Master Planning with remaining plants Business | 200h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
103 | Dry-run tests and GO-live of MPS in remaining plants | 160h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
104 | Interactive MPS with basic solvers at remaining plants is live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | Assistence after go-live | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
106 | Refine basic Solver | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
107 | Coordination | 968h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | Implementation of Master Planning in remaining plants is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | Phase 4: Implementation of S&OP Planning | 1160h |  |  |  |  | 99 | 100 | 101
152 | Analysis of S&OP Planning | 200h |  |  |  |  | 99 | 100 | 101
110 | Analyze details for Integration with S&OP | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | Analyze S&OP rules in detail | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | Analyze integration of S&OP in DRP and Master Planning | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | Analysis of S&OP Planning is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | Implementation of S&OP Planning | 960h |  |  |  |  | 99 | 100 | 101
114 | Received Master data for building the S&OP model | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | Check master data | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
116 | Build S&OP model | 320h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
117 | Configure basic solvers | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
118 | Test off-line the S&OP model | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
119 | Validate S&OP with Business | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
120 | Integration test, Dry-run tests and GO-live of S&OP | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
121 | Interactive S&OP with basic solvers is live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | Assistence after go-live | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
123 | Refine basic Solver for S&OP | 232h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
124 | Coordination | 912h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | Implementation of S&OP Planning is finished | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | Project is closed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2010-11-01 08:00 |  | TP Name | T1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 20d | [5 empty] | 6000 |  | 1.599% |  | 6000 | 12375
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 20d | [5 empty] | 6000 |  | 13.33% |  | 6000 | 12375
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 8d | 1000 | 1500 | 12d | 0 | 0 | 1000 | 1500 | 40% | Started | 1000 | 1875 | 100 | 40 | 40 | 100 | 40 | 40
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 |  | 0 | 0 | 7500 | 10d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 2250 | 100 |  | 0 | 100 |  | 0
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 3250 | 100 |  | 0 | 100 |  | 0
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 |  | 0 | 0 | 10000 | 10d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 5d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 |  | 0 | 0 | 3500 | 5d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 |  | 0 | 0 | 1489.0823 | 39d | 0 | 0 | 0 | 1489.0823 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 |  | 0 | 0 | 15000 | 20d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 |  | 0 | 0 | 10000 | 10d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 |  | 0 | 0 | 3976.8009 | 49d | 0 | 0 | 0 | 3976.8009 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 |  | 0 | 0 | 4000 | 25d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 25d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 |  | 0 | 0 | 5000 | 25d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 |  | 0 | 0 | 125 | 1h | 0 | 0 | 0 | 125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 |  | 0 | 0 | 1482.3552 | 24d | 0 | 0 | 0 | 1482.3552 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2010-12-06 08:00 |  | TP Name | T2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 45d | [5 empty] | 19791.664 |  | 3.775% |  | 14166.664 | 44791.664
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 45d | [5 empty] | 19791.664 |  | 31.48% |  | 14166.664 | 42291.664
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 10d | 5000 | 5000 | 10d | 0 | 0 | 5000 | 5000 | 50% | Started | 1250 | 2500 | 100 | 200 | 50 | 100 | 200 | 50
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 5d | 3750 | 11250 | 15d | 0 | 0 | 3750 | 11250 | 25% | Started | 1875 | 7500 | 100 | 50 | 25 | 100 | 50 | 25
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 5d | 625 | 1875 | 15d | 0 | 0 | 625 | 1875 | 25% | Started | 625 | 625 | 100 | 25 | 25 | 100 | 25 | 25
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 5d | 1250 | 3750 | 15d | 0 | 0 | 1250 | 3750 | 25% | Started | 1250 | 5000 | 100 | 25 | 25 | 100 | 25 | 25
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 10d | 1666.664 | 833.332 | 5d | 0 | 0 | 1666.664 | 833.332 | 66.67% | Started | 1666.664 | 1666.664 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 |  | 0 | 0 | 10000 | 10d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 5d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2500
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2500
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 |  | 0 | 0 | 3500 | 5d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 |  | 0 | 0 | 1489.0823 | 39d | 0 | 0 | 0 | 1489.0823 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 |  | 0 | 0 | 15000 | 20d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 |  | 0 | 0 | 10000 | 10d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 |  | 0 | 0 | 3976.8009 | 49d | 0 | 0 | 0 | 3976.8009 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 |  | 0 | 0 | 4000 | 25d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 25d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 |  | 0 | 0 | 5000 | 25d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 |  | 0 | 0 | 125 | 1h | 0 | 0 | 0 | 125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 |  | 0 | 0 | 1482.3552 | 24d | 0 | 0 | 0 | 1482.3552 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-01-03 08:00 |  | TP Name | T3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 65d | [5 empty] | 46499.996 |  | 7.861% |  | 29499.996 | 64479.996
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 65d | [5 empty] | 46499.996 |  | 65.56% |  | 29499.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 4d | 4000 | 16000 | 16d | 0 | 0 | 4000 | 16000 | 20% | Started | 2000 | 10000 | 100 | 40 | 20 | 100 | 40 | 20
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 5d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 19480
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 19480
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 |  | 0 | 0 | 3500 | 5d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 3500 | 100 |  | 0 | 100 |  | 0
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 980 | 100 |  | 0 | 100 |  | 0
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000 | 100 |  | 0 | 100 |  | 0
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 |  | 0 | 0 | 1489.0823 | 39d | 0 | 0 | 0 | 1489.0823 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 |  | 0 | 0 | 15000 | 20d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 |  | 0 | 0 | 10000 | 10d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 |  | 0 | 0 | 3976.8009 | 49d | 0 | 0 | 0 | 3976.8009 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 |  | 0 | 0 | 4000 | 25d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 25d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 |  | 0 | 0 | 5000 | 25d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 |  | 0 | 0 | 125 | 1h | 0 | 0 | 0 | 125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 |  | 0 | 0 | 1482.3552 | 24d | 0 | 0 | 0 | 1482.3552 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-02-07 08:00 |  | TP Name | T4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 90d | [5 empty] | 72499.996 |  | 12.66% |  | 47499.996 | 94963.516
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 5d | [5 empty] | 2500 |  | 3.404% |  | 2500 | 49963.52
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 5d | [5 empty] | 2500 |  | 3.404% |  | 2500 | 49963.52
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 5d | 2500 | 2500 | 5d | 0 | 0 | 2500 | 2500 | 50% | Started | 2500 | 5000 | 100 | 50 | 50 | 100 | 50 | 50
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 |  | 0 | 0 | 3500 | 5d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 3500 | 100 |  | 0 | 100 |  | 0
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 980 | 100 |  | 0 | 100 |  | 0
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000 | 100 |  | 0 | 100 |  | 0
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10954.54
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 |  | 0 | 0 | 1489.0823 | 39d | 0 | 0 | 0 | 1489.0823 | 0% | Not Started | 0 | 954.54 | 100 |  | 0 | 100 |  | 0
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 19528.9801
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 |  | 0 | 0 | 15000 | 20d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 15000 | 100 |  | 0 | 100 |  | 0
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 |  | 0 | 0 | 10000 | 10d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 |  | 0 | 0 | 3976.8009 | 49d | 0 | 0 | 0 | 3976.8009 | 0% | Not Started | 0 | 2028.9801 | 100 |  | 0 | 100 |  | 0
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 |  | 0 | 0 | 4000 | 25d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 25d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 |  | 0 | 0 | 5000 | 25d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 |  | 0 | 0 | 125 | 1h | 0 | 0 | 0 | 125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 |  | 0 | 0 | 1482.3552 | 24d | 0 | 0 | 0 | 1482.3552 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-03-07 08:00 |  | TP Name | T5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 110d | [5 empty] | 89479.996 |  | 17.18% |  | 64479.996 | 113121.2424
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 25d | [5 empty] | 19480 |  | 26.52% |  | 19480 | 68121.2465
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 25d | [5 empty] | 19480 |  | 26.52% |  | 19480 | 68121.2465
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 |  | 0 | 0 | 1489.0823 | 39d | 0 | 0 | 0 | 1489.0823 | 0% | Not Started | 0 | 1489.0823 | 100 |  | 0 | 100 |  | 0
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 33652.1641
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 |  | 0 | 0 | 15000 | 20d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 15000 | 100 |  | 0 | 100 |  | 0
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 |  | 0 | 0 | 10000 | 10d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 |  | 0 | 0 | 3976.8009 | 49d | 0 | 0 | 0 | 3976.8009 | 0% | Not Started | 0 | 3652.1641 | 100 |  | 0 | 100 |  | 0
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 |  | 0 | 0 | 4000 | 25d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 25d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 |  | 0 | 0 | 5000 | 25d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 |  | 0 | 0 | 125 | 1h | 0 | 0 | 0 | 125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 |  | 0 | 0 | 1482.3552 | 24d | 0 | 0 | 0 | 1482.3552 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2011-04-04 08:00 |  | TP Name | T6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 130d | [5 empty] | 115366.812 |  | 23.89% |  | 89663.564 | 133772.3512
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 45d | [5 empty] | 45366.816 |  | 60.81% |  | 44663.568 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 45d | [5 empty] | 45366.816 |  | 60.81% |  | 44663.568 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 20d | [5 empty] | 10513.632 |  | 79.23% |  | 11875.9308 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 20d | 763.632 | 534.5424 | 14d | 0 | 0 | 763.632 | 534.5424 | 58.82% | Started | 875.9308 | 1489.0823 | 100 | 51.2821 | 58.8235 | 100 | 51.2821 | 58.8235
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 20d | [5 empty] | 15373.1841 |  | 34.14% |  | 13307.6372 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 15d | 11250 | 7500 | 10d | 0 | 0 | 11250 | 7500 | 60% | Started | 9000.0004 | 15000 | 100 | 75 | 60 | 100 | 75 | 60
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 |  | 0 | 0 | 5000 | 10d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 |  | 0 | 0 | 10000 | 10d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 20d | 1623.1841 | 1947.8209 | 24d | 0 | 0 | 1623.1841 | 1947.8209 | 45.45% | Started | 1807.6368 | 3976.8009 | 100 | 40.8163 | 45.4545 | 100 | 40.8163 | 45.4545
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 15326.472
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 14400
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 |  | 0 | 0 | 4000 | 25d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 2400 | 100 |  | 0 | 100 |  | 0
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 25d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 4500 | 100 |  | 0 | 100 |  | 0
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 |  | 0 | 0 | 5000 | 25d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 3000 | 100 |  | 0 | 100 |  | 0
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 926.472
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 |  | 0 | 0 | 125 | 1h | 0 | 0 | 0 | 125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 |  | 0 | 0 | 1482.3552 | 24d | 0 | 0 | 0 | 1482.3552 | 0% | Not Started | 0 | 926.472 | 100 |  | 0 | 100 |  | 0
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2011-05-02 08:00 |  | TP Name | T7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 150d | [5 empty] | 145024.5384 |  | 30.58% |  | 114751.0188 | 153003.2345
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 65d | [5 empty] | 75024.5425 |  | 94.97% |  | 69751.0229 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 65d | [5 empty] | 75024.5425 |  | 94.97% |  | 69751.0229 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 40d | [5 empty] | 41996.3681 |  | 90.52% |  | 35281.9405 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 10d | 10000 | 5000 | 5d | 0 | 0 | 10000 | 5000 | 66.67% | Started | 6666.6669 | 10000 | 100 | 100 | 66.6667 | 100 | 100 | 66.6667
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 40d | 3246.3681 | 324.6368 | 4d | 0 | 0 | 3246.3681 | 324.6368 | 90.91% | Started | 3615.2737 | 3976.8009 | 100 | 81.6327 | 90.9091 | 100 | 81.6327 | 90.9091
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 34557.3552
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 |  | 0 | 0 | 4000 | 25d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 4000 | 100 |  | 0 | 100 |  | 0
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 25d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 |  | 0 | 0 | 5000 | 25d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 25d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 7857.3552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 |  | 0 | 0 | 125 | 1h | 0 | 0 | 0 | 125 | 0% | Not Started | 0 | 125 | 100 |  | 0 | 100 |  | 0
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3250
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 1250 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 1250 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 750 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 |  | 0 | 0 | 1482.3552 | 24d | 0 | 0 | 0 | 1482.3552 | 0% | Not Started | 0 | 1482.3552 | 100 |  | 0 | 100 |  | 0
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2700
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 700 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2011-06-06 08:00 |  | TP Name | T8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 175d | [5 empty] | 168735.2064 |  | 35.82% |  | 134405.1253 | 170770.4943
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 20d | [5 empty] | 18386.0312 |  | 8.326% |  | 15959.2461 | 52324.6151
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 20d | [5 empty] | 17212.5 |  | 61.61% |  | 14785.7148 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 20d | 3200 | 2400 | 15d | 0 | 0 | 3200 | 2400 | 57.14% | Started | 2285.7144 | 4000 | 100 | 80 | 57.1429 | 100 | 80 | 57.1429
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 20d | 2000 | 1500 | 15d | 0 | 0 | 2000 | 1500 | 57.14% | Started | 1428.5715 | 2500 | 100 | 80 | 57.1429 | 100 | 80 | 57.1429
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 20d | 6000 | 4500 | 15d | 0 | 0 | 6000 | 4500 | 57.14% | Started | 4285.7145 | 7500 | 100 | 80 | 57.1429 | 100 | 80 | 57.1429
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 20d | 4000 | 3000 | 15d | 0 | 0 | 4000 | 3000 | 57.14% | Started | 2857.143 | 5000 | 100 | 80 | 57.1429 | 100 | 80 | 57.1429
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 20d | 2000 | 1500 | 15d | 0 | 0 | 2000 | 1500 | 57.14% | Started | 1428.5715 | 2500 | 100 | 80 | 57.1429 | 100 | 80 | 57.1429
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 20d | [5 empty] | 1173.5312 |  | 8% |  | 1173.5312 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 |  | 0 | 0 | 125 | 1h | 0 | 0 | 0 | 125 | 0% | Not Started | 0 | 125 | 100 |  | 0 | 100 |  | 0
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 62.5 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 19d | 1173.5312 | 308.824 | 5d | 0 | 0 | 1173.5312 | 308.824 | 79.17% | Started | 1173.5312 | 1482.3552 | 100 | 79.1667 | 79.1667 | 100 | 79.1667 | 79.1667
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 980 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6377.7839
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 3333.3359 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 544.448 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2796.976
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 296.976 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2011-07-04 08:00 |  | TP Name | T9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 195d | [5 empty] | 189944.0304 |  | 38.79% |  | 145553.2345 | 179028.5863
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 40d | [5 empty] | 39594.8552 |  | 14.14% |  | 27107.3552 | 60582.7071
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 40d | [5 empty] | 9482.3552 |  | 21.18% |  | 3107.3552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 5d | [5 empty] | 8000 |  | 52% |  | 1625 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 5d | 1500 | 1500 | 5d | 0 | 0 | 1500 | 1500 | 50% | Started | 750 | 1500 | 100 | 100 | 50 | 100 | 100 | 50
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 5d | 1500 | 1500 | 5d | 0 | 0 | 1500 | 1500 | 50% | Started | 750 | 1500 | 100 | 100 | 50 | 100 | 100 | 50
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 62.5 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 980 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 14338.8998
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 750 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 1088.896 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3093.952
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 593.952 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2011-08-01 08:00 |  | TP Name | T10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 215d | [5 empty] | 202694.0304 |  | 40.92% |  | 153553.2345 | 188120.0101
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 60d | [5 empty] | 52344.8552 |  | 18.32% |  | 35107.3552 | 69674.1308
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 60d | [5 empty] | 22232.3552 |  | 75.72% |  | 11107.3552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 |  | 0 | 0 | 62.5 | 1h | 0 | 0 | 0 | 62.5 | 0% | Not Started | 0 | 62.5 | 100 |  | 0 | 100 |  | 0
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 |  | 0 | 0 | 2000 | 10d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000 | 100 |  | 0 | 100 |  | 0
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 980 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 20633.3517
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 |  | 0 | 0 | 3511.6897 | 129d | 0 | 0 | 0 | 3511.6897 | 0% | Not Started | 0 | 1633.344 | 100 |  | 0 | 100 |  | 0
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 5890.9239
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 890.928 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2011-09-05 08:00 |  | TP Name | T11
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 240d | [5 empty] | 208830.1425 |  | 41.9% |  | 157222.7982 | 195838.446
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 85d | [5 empty] | 58480.9672 |  | 20.23% |  | 38776.9189 | 77392.5667
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 980 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 5d | [5 empty] | 136.112 |  | 0.2854% |  | 107.0637 | 23813.9076
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 5d | 136.112 | 4328.3617 | 159d | 0 | 0 | 136.112 | 4328.3617 | 3.049% | Started | 107.0637 | 2313.9041 | 100 | 3.876 | 3.0488 | 100 | 3.876 | 3.0488
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10428.8039
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4166.6599 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 1262.148 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2011-10-03 08:00 |  | TP Name | T12
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 260d | [5 empty] | 213541.2584 |  | 42.81% |  | 160651.0534 | 205013.2018
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 105d | [5 empty] | 63192.0832 |  | 22.02% |  | 42205.1742 | 86567.3226
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000 | 100 |  | 0 | 100 |  | 0
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 |  | 0 | 0 | 980 | 14d | 0 | 0 | 0 | 980 | 0% | Not Started | 0 | 980 | 100 |  | 0 | 100 |  | 0
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 25d | [5 empty] | 4847.228 |  | 9.425% |  | 3535.319 | 28525.0196
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 5d | 1666.6679 | 15000.0114 | 45d | 0 | 0 | 1666.6679 | 15000.0114 | 10% | Started | 500.0004 | 5000.0038 | 100 | 33.3333 | 10 | 100 | 33.3333 | 10
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 1666.6679 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 25d | 680.56 | 3783.9137 | 139d | 0 | 0 | 680.56 | 3783.9137 | 15.24% | Started | 535.3186 | 2858.3521 | 100 | 19.3798 | 15.2439 | 100 | 19.3798 | 15.2439
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 14892.4478
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 3333.336 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 1559.124 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2011-11-07 08:00 |  | TP Name | T13
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 285d | [5 empty] | 229305.1581 |  | 44.21% |  | 165909.8589 | 219926.659
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 130d | [5 empty] | 78955.9829 |  | 24.76% |  | 47463.9796 | 101480.7798
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 25d | [5 empty] | 6750 |  | 49.63% |  | 2223.4849 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 10d | 2000 | 1000 | 5d | 0 | 0 | 2000 | 1000 | 66.67% | Started | 666.6667 | 1000 | 100 | 200 | 66.6667 | 100 | 200 | 66.6667
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 25d | 1750 | 1330 | 19d | 0 | 0 | 1750 | 1330 | 56.82% | Started | 556.8182 | 980 | 100 | 178.5714 | 56.8182 | 100 | 178.5714 | 56.8182
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 50d | [5 empty] | 13861.1277 |  | 17.52% |  | 6570.6395 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 30d | 10000.0076 | 6666.6718 | 20d | 0 | 0 | 10000.0076 | 6666.6718 | 60% | Started | 3000.0024 | 5000.0038 | 100 | 200 | 60 | 100 | 200 | 60
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 50d | 1361.12 | 3103.3537 | 114d | 0 | 0 | 1361.12 | 3103.3537 | 30.49% | Started | 1070.6371 | 3511.6897 | 100 | 38.7597 | 30.4878 | 100 | 38.7597 | 30.4878
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 20819.2277
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 8888.8959 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 1930.344 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2011-12-05 08:00 |  | TP Name | T14
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 305d | [5 empty] | 243346.2779 |  | 45.46% |  | 170594.6302 | 223834.743
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 150d | [5 empty] | 92997.1027 |  | 27.21% |  | 52148.751 | 105388.8637
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 70d | [5 empty] | 21072.2474 |  | 23.99% |  | 8998.8958 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 70d | 1905.568 | 2558.9057 | 94d | 0 | 0 | 1905.568 | 2558.9057 | 42.68% | Started | 1498.892 | 3511.6897 | 100 | 54.2636 | 42.6829 | 100 | 54.2636 | 42.6829
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 24727.3116
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 10000.0079 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 2227.32 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2012-01-02 08:00 |  | TP Name | T15
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 325d | [5 empty] | 250390.7259 |  | 47.11% |  | 176772.8868 | 227256.7149
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 170d | [5 empty] | 100041.5507 |  | 30.43% |  | 58327.0075 | 108810.8357
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 90d | [5 empty] | 28116.6954 |  | 40.46% |  | 15177.1523 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 10d | 1500 | 1500 | 10d | 0 | 0 | 1500 | 1500 | 50% | Started | 750 | 1500 | 100 | 100 | 50 | 100 | 100 | 50
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 90d | 2450.0161 | 2014.4576 | 74d | 0 | 0 | 2450.0161 | 2014.4576 | 54.88% | Started | 1927.1485 | 3511.6897 | 100 | 69.7674 | 54.8781 | 100 | 69.7674 | 54.8781
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 28149.2836
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 10000.0079 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 625 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 2524.2959 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2012-02-06 09:00 |  | TP Name | T16
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 350d 1h | [5 empty] | 257571.2897 |  | 48.25% |  | 181058.206 | 229582.5688
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 195d 1h | [5 empty] | 107222.1145 |  | 32.67% |  | 62612.3267 | 111136.6896
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 115d 1h | [5 empty] | 35297.2593 |  | 51.88% |  | 19462.4715 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 15d | 5000.0038 | 3333.3359 | 10d | 0 | 0 | 5000.0038 | 3333.3359 | 60% | Started | 3000.0024 | 5000.0038 | 100 | 100 | 60 | 100 | 100 | 60
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 115d | 3130.5761 | 1333.8976 | 49d | 0 | 0 | 3130.5761 | 1333.8976 | 70.12% | Started | 2462.4653 | 3511.6897 | 100 | 89.1473 | 70.1219 | 100 | 89.1473 | 70.1219
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 1h | [5 empty] | 0 |  | 0% |  | 0 | 30439.0264
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 10000.0079 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 41.6667 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 2897.372 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 36.1111
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 31.25 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 4.8611 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2012-03-05 08:00 |  | TP Name | T17
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 370d | [5 empty] | 263115.7376 |  | 49.12% |  | 184319.7942 | 242244.3587
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 215d | [5 empty] | 112766.5624 |  | 34.37% |  | 65873.915 | 123798.4794
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 135d | [5 empty] | 40841.7071 |  | 60.58% |  | 22724.0598 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 10d | 1666.664 | 3333.3279 | 20d | 0 | 0 | 1666.664 | 3333.3279 | 33.33% | Started | 833.332 | 2499.996 | 100 | 66.6667 | 33.3333 | 100 | 66.6667 | 33.3333
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 135d | 3675.0241 | 789.4496 | 29d | 0 | 0 | 3675.0241 | 789.4496 | 82.32% | Started | 2890.7201 | 3511.6897 | 100 | 104.6512 | 82.3171 | 100 | 104.6512 | 82.3171
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 20d | [5 empty] | 0 |  | 0% |  | 0 | 37359.1513
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 10000.0079 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 1666.6679 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 |  | 0 | 0 | 3504.3167 | 236d | 0 | 0 | 0 | 3504.3167 | 0% | Not Started | 0 | 3192.4919 | 100 |  | 0 | 100 |  | 0
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 5777.776
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 777.776 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2012-04-02 08:00 |  | TP Name | T18
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 399d | [5 empty] | 270008.3623 |  | 50.57% |  | 189767.6238 | 254985.7825
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 244d | [5 empty] | 119659.1871 |  | 37.21% |  | 71321.7446 | 136539.9032
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 155d | [5 empty] | 45219.4831 |  | 68.38% |  | 25652.3122 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 1d | 166.6664 | 2333.3296 | 14d | 0 | 0 | 166.6664 | 2333.3296 | 6.667% | Started | 166.6664 | 2499.996 | 100 | 6.6667 | 6.6667 | 100 | 6.6667 | 6.6667
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 1d | 333.3336 | 4666.6702 | 14d | 0 | 0 | 333.3336 | 4666.6702 | 6.667% | Started | 666.6672 | 10000.0076 | 100 | 3.3333 | 6.6667 | 100 | 3.3333 | 6.6667
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 155d | 4219.4721 | 245.0016 | 9d | 0 | 0 | 4219.4721 | 245.0016 | 94.51% | Started | 3318.975 | 3511.6897 | 100 | 120.155 | 94.5122 | 100 | 120.155 | 94.5122
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 49d | [5 empty] | 2514.8488 |  | 5.477% |  | 2519.5772 | 44322.7991
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 |  | 0 | 0 | 2499.996 | 15d | 0 | 0 | 0 | 2499.996 | 0% | Not Started | 0 | 2499.996 | 100 |  | 0 | 100 |  | 0
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 10000.0079 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 8333.3397 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 1d | 14.8488 | 2643.0863 | 178d | 0 | 0 | 14.8488 | 2643.0863 | 0.5587% | Started | 19.5772 | 3489.4679 | 100 | 0.42373 | 0.55866 | 100 | 0.42373 | 0.55866
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 11555.5521
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 1555.5521 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2012-05-07 08:00 |  | TP Name | T19
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 434d | [5 empty] | 283457.9076 |  | 55.86% |  | 209616.4261 | 266389.5192
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 279d | [5 empty] | 133108.7324 |  | 47.57% |  | 91170.5468 | 147943.64
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 84d | [5 empty] | 8719.3927 |  | 22.84% |  | 10508.9948 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 |  | 0 | 0 | 10000.0079 | 45d | 0 | 0 | 0 | 10000.0079 | 0% | Not Started | 0 | 10000.0079 | 100 |  | 0 | 100 |  | 0
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 26d | 386.0688 | 2271.8664 | 153d | 0 | 0 | 386.0688 | 2271.8664 | 14.53% | Started | 509.0069 | 3504.3167 | 100 | 11.0169 | 14.5251 | 100 | 11.0169 | 14.5251
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 21277.7721
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 1250 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 2527.7721 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2012-06-04 08:00 |  | TP Name | T20
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 435d | [5 empty] | 283977.106 |  | 56.02% |  | 210230.1923 | 273167.2953
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 280d | [5 empty] | 133627.9308 |  | 47.89% |  | 91784.3131 | 154721.416
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 85d | [5 empty] | 9238.5911 |  | 24.18% |  | 11122.761 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 1d | 222.2224 | 9777.7855 | 44d | 0 | 0 | 222.2224 | 9777.7855 | 2.222% | Started | 222.2224 | 10000.0079 | 100 | 2.2222 | 2.2222 | 100 | 2.2222 | 2.2222
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 46d | 683.0448 | 1974.8904 | 133d | 0 | 0 | 683.0448 | 1974.8904 | 25.7% | Started | 900.5507 | 3504.3167 | 100 | 19.4915 | 25.6983 | 100 | 19.4915 | 25.6983
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 28055.5481
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 3500 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 1250 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 3305.5481 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2012-07-02 08:00 |  | TP Name | T21
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 455d | [5 empty] | 288421.5539 |  | 57.21% |  | 214674.6402 | 276695.0713
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 300d | [5 empty] | 138072.3787 |  | 50.2% |  | 96228.761 | 158249.1921
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 105d | [5 empty] | 13683.039 |  | 33.84% |  | 15567.2089 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 21d | 4666.6703 | 5333.3375 | 24d | 0 | 0 | 4666.6703 | 5333.3375 | 46.67% | Started | 4666.6704 | 10000.0079 | 100 | 46.6667 | 46.6667 | 100 | 46.6667 | 46.6667
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 |  | 0 | 0 | 4999.9919 | 30d | 0 | 0 | 0 | 4999.9919 | 0% | Not Started | 0 | 4999.9919 | 100 |  | 0 | 100 |  | 0
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 46d | 683.0448 | 1974.8904 | 133d | 0 | 0 | 683.0448 | 1974.8904 | 25.7% | Started | 900.5507 | 3504.3167 | 100 | 19.4915 | 25.6983 | 100 | 19.4915 | 25.6983
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 31583.3242
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 3500 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 4083.3242 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 |  | 0 | 0 | 2500.0081 | 35d | 0 | 0 | 0 | 2500.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 |  | 0 | 0 | 6000.0081 | 35d | 0 | 0 | 0 | 6000.0081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 |  | 0 | 0 | 2491.1479 | 121d | 0 | 0 | 0 | 2491.1479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2012-08-06 08:00 |  | TP Name | T22
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 480d | [5 empty] | 302104.4619 |  | 61.01% |  | 228926.9968 | 292125.2546
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 325d | [5 empty] | 151755.2867 |  | 57.64% |  | 110481.1176 | 173679.3754
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 130d | [5 empty] | 19851.2389 |  | 47.71% |  | 21948.1862 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 1d | 166.6664 | 4833.3255 | 29d | 0 | 0 | 166.6664 | 4833.3255 | 3.333% | Started | 166.6664 | 4999.9919 | 100 | 3.3333 | 3.3333 | 100 | 3.3333 | 3.3333
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 91d | 1351.2408 | 1306.6944 | 88d | 0 | 0 | 1351.2408 | 1306.6944 | 50.84% | Started | 1781.5241 | 3504.3167 | 100 | 38.5593 | 50.838 | 100 | 38.5593 | 50.838
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 25d | [5 empty] | 0 |  | 0% |  | 0 | 38766.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 |  | 0 | 0 | 7500 | 30d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 7500 | 100 |  | 0 | 100 |  | 0
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 3500 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 3750 | 100 |  | 0 | 100 |  | 0
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 |  | 0 | 0 | 5016.6554 | 129d | 0 | 0 | 0 | 5016.6554 | 0% | Not Started | 0 | 5016.6554 | 100 |  | 0 | 100 |  | 0
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 25d | [5 empty] | 7514.7081 |  | 31.5% |  | 7871.3792 | 8246.8521
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 714.288 | 10d | 0 | 0 | 1785.7201 | 714.288 | 71.43% | Started | 1785.7201 | 1785.7201 | 100 | 71.4286 | 71.4286 | 100 | 71.4286 | 71.4286
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 10d | 1714.288 | 2571.432 | 15d | 0 | 0 | 1714.288 | 2571.432 | 40% | Started | 2400.0033 | 2571.432 | 100 | 28.5714 | 40 | 100 | 28.5714 | 40
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 10d | 1250 | 625 | 5d | 0 | 0 | 1250 | 625 | 66.67% | Started | 1666.6667 | 1875 | 100 | 50 | 66.6667 | 100 | 50 | 66.6667
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 25d | 514.7 | 1955.8599 | 95d | 0 | 0 | 514.7 | 1955.8599 | 20.83% | Started | 518.9891 | 514.7 | 100 | 20.6612 | 20.8333 | 100 | 20.6612 | 20.8333
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2012-09-03 08:00 |  | TP Name | 23
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 500d | [5 empty] | 318715.1787 |  | 66.24% |  | 248575.9899 | 298554.8787
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 345d | [5 empty] | 168366.0035 |  | 67.89% |  | 130130.1107 | 180108.9994
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 150d | [5 empty] | 23481.5429 |  | 55.81% |  | 25673.0578 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 21d | 3499.9943 | 1499.9976 | 9d | 0 | 0 | 3499.9943 | 1499.9976 | 70% | Started | 3499.9943 | 4999.9919 | 100 | 70 | 70 | 100 | 70 | 70
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 |  | 0 | 0 | 2500 | 20d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 111d | 1648.2168 | 1009.7184 | 68d | 0 | 0 | 1648.2168 | 1009.7184 | 62.01% | Started | 2173.0678 | 3504.3167 | 100 | 47.0339 | 62.0112 | 100 | 47.0339 | 62.0112
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 45d | [5 empty] | 8622.2208 |  | 22.14% |  | 8861.3041 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 6d | 1500 | 4750 | 19d | 0 | 0 | 1500 | 4750 | 24% | Started | 1800 | 7500 | 100 | 20 | 24 | 100 | 20 | 24
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 |  | 0 | 0 | 5000 | 20d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000 | 100 |  | 0 | 100 |  | 0
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 3500 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 6d | 1500 | 3500 | 14d | 0 | 0 | 1500 | 3500 | 30% | Started | 1500.0001 | 5000 | 100 | 30 | 30 | 100 | 30 | 30
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 16d | 622.2208 | 4938.8778 | 127d | 0 | 0 | 622.2208 | 4938.8778 | 11.19% | Started | 561.3041 | 5016.6554 | 100 | 12.4031 | 11.1888 | 100 | 12.4031 | 11.1888
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 45d | [5 empty] | 11872.9001 |  | 59.76% |  | 14934.1966 | 13426.4761
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 0 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 |  | 0 | 0 | 3000 | 25d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 45d | 926.46 | 1544.1 | 75d | 0 | 0 | 926.46 | 1544.1 | 37.5% | Started | 934.1805 | 926.46 | 100 | 37.1901 | 37.5 | 100 | 37.1901 | 37.5
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2012-10-01 08:00 |  | TP Name | 24
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 520d | [5 empty] | 334226.6883 |  | 70.82% |  | 265742.6864 | 301666.6387
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 365d | [5 empty] | 183877.5131 |  | 76.85% |  | 147296.8071 | 183220.7594
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 170d | [5 empty] | 26653.5164 |  | 62.91% |  | 28939.5994 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 11d | 1375 | 1125 | 9d | 0 | 0 | 1375 | 1125 | 55% | Started | 1375 | 2500 | 100 | 55 | 55 | 100 | 55 | 55
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 5000.0038 | 100 |  | 0 | 100 |  | 0
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 |  | 0 | 0 | 10000.0076 | 30d | 0 | 0 | 0 | 10000.0076 | 0% | Not Started | 0 | 10000.0076 | 100 |  | 0 | 100 |  | 0
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 131d | 1945.1928 | 712.7424 | 48d | 0 | 0 | 1945.1928 | 712.7424 | 73.18% | Started | 2564.6117 | 3504.3167 | 100 | 55.5085 | 73.1844 | 100 | 55.5085 | 73.1844
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 65d | [5 empty] | 18149.9969 |  | 48.35% |  | 19346.2676 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 1d | 250 | 2250 | 9d | 0 | 0 | 250 | 2250 | 10% | Started | 250 | 2500 | 100 | 10 | 10 | 100 | 10 | 10
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 1d | 250 | 3500 | 14d | 0 | 0 | 250 | 3500 | 6.667% | Started | 333.3334 | 5000 | 100 | 5 | 6.6667 | 100 | 5 | 6.6667
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 |  | 0 | 0 | 3500 | 10d | 0 | 0 | 0 | 3500 | 0% | Not Started | 0 | 3500 | 100 |  | 0 | 100 |  | 0
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 36d | 1399.9969 | 4161.1018 | 107d | 0 | 0 | 1399.9969 | 4161.1018 | 25.17% | Started | 1262.9343 | 5016.6554 | 100 | 27.907 | 25.1748 | 100 | 27.907 | 25.1748
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 65d | [5 empty] | 14684.6601 |  | 73.42% |  | 18349.388 | 16538.2361
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 1200 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 |  | 0 | 0 | 1500 | 20d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 65d | 1338.22 | 1132.34 | 55d | 0 | 0 | 1338.22 | 1132.34 | 54.17% | Started | 1349.3718 | 1338.22 | 100 | 53.719 | 54.1667 | 100 | 53.719 | 54.1667
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2012-11-05 08:00 |  | TP Name | T25
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 545d | [5 empty] | 352393.1657 |  | 76.51% |  | 287118.217 | 304731.3386
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 390d | [5 empty] | 202043.9905 |  | 88% |  | 168672.3378 | 186285.4594
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 195d | [5 empty] | 33483.0738 |  | 78.01% |  | 35887.3664 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 1d | 333.3336 | 9666.674 | 29d | 0 | 0 | 333.3336 | 9666.674 | 3.333% | Started | 333.3336 | 10000.0076 | 100 | 3.3333 | 3.3333 | 100 | 3.3333 | 3.3333
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 156d | 2316.4128 | 341.5224 | 23d | 0 | 0 | 2316.4128 | 341.5224 | 87.15% | Started | 3054.0413 | 3504.3167 | 100 | 66.1017 | 87.1508 | 100 | 66.1017 | 87.1508
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 90d | [5 empty] | 28222.2169 |  | 79.35% |  | 31755.0422 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 6d | 2100 | 1400 | 4d | 0 | 0 | 2100 | 1400 | 60% | Started | 2100.0001 | 3500 | 100 | 60 | 60 | 100 | 60 | 60
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500 | 100 |  | 0 | 100 |  | 0
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 61d | 2372.2169 | 3149.9929 | 81d | 0 | 0 | 2372.2169 | 3149.9929 | 42.96% | Started | 2155.0421 | 5016.6554 | 100 | 47.2868 | 42.9577 | 100 | 47.2868 | 42.9577
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 90d | [5 empty] | 15949.3601 |  | 81.5% |  | 20368.3771 | 19602.9361
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 750 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 90d | 1852.9199 | 617.64 | 30d | 0 | 0 | 1852.9199 | 617.64 | 75% | Started | 1868.3609 | 1852.9199 | 100 | 74.3802 | 75 | 100 | 74.3802 | 75
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2012-12-03 08:00 |  | TP Name | T26
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 565d | [5 empty] | 363946.3495 |  | 80.13% |  | 300678.1836 | 305893.0986
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 410d | [5 empty] | 213597.1742 |  | 95.07% |  | 182232.3044 | 187447.2194
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 215d | [5 empty] | 40446.7216 |  | 93.35% |  | 42945.5819 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 21d | 7000.0053 | 3000.0023 | 9d | 0 | 0 | 7000.0053 | 3000.0023 | 70% | Started | 7000.0052 | 10000.0076 | 100 | 70 | 70 | 100 | 70 | 70
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 176d | 2613.3887 | 44.5464 | 3d | 0 | 0 | 2613.3887 | 44.5464 | 98.32% | Started | 3445.5852 | 3504.3167 | 100 | 74.5763 | 98.324 | 100 | 74.5763 | 98.324
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 110d | [5 empty] | 32399.9929 |  | 94.56% |  | 37841.6019 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 81d | 3149.9929 | 2411.1057 | 62d | 0 | 0 | 3149.9929 | 2411.1057 | 56.64% | Started | 2841.6019 | 5016.6554 | 100 | 62.7907 | 56.6434 | 100 | 62.7907 | 56.6434
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 110d | [5 empty] | 16361.1201 |  | 83.16% |  | 20783.5685 | 20764.6961
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 |  | 0 | 0 | 1500 | 10d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 110d | 2264.6799 | 205.88 | 10d | 0 | 0 | 2264.6799 | 205.88 | 91.67% | Started | 2283.5523 | 2264.6799 | 100 | 90.9091 | 91.6667 | 100 | 90.9091 | 91.6667
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2013-01-07 08:00 |  | TP Name | T27
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 590d | [5 empty] | 375668.9982 |  | 83.23% |  | 312321.551 | 313619.5666
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 435d | [5 empty] | 221819.823 |  | 99.32% |  | 190375.6717 | 191673.6874
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 100% |  | 46004.3158 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 100 | 100 | 100 | 100 | 100
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 100% | Finished | 3504.3167 | 3504.3167 | 100 | 75.8475 | 100 | 100 | 75.8475 | 100
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 135d | [5 empty] | 33372.213 |  | 96.76% |  | 38718.6397 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 106d | 4122.213 | 1438.8857 | 37d | 0 | 0 | 4122.213 | 1438.8857 | 74.13% | Started | 3718.6397 | 5016.6554 | 100 | 82.1705 | 74.1259 | 100 | 82.1705 | 74.1259
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 100% |  | 24991.1641 | 24991.1641
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 100% | Finished | 2491.1479 | 2491.1479 | 100 | 99.1736 | 100 | 100 | 99.1736 | 100
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 10d | [5 empty] | 3500 |  | 5.374% |  | 3500.0001 | 3500
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 10d | [5 empty] | 3500 |  | 35% |  | 3500.0001 | 3500
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 5d | 2500 | 5000 | 10d | 0 | 0 | 2500 | 5000 | 33.33% | Started | 2500.0001 | 2500 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 |  | 0 | 0 | 1500 | 5d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 |  | 0 | 0 | 6483.7726 | 114d | 0 | 0 | 0 | 6483.7726 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2013-02-04 08:00 |  | TP Name | T28
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 610d | [5 empty] | 385731.1502 |  | 85.89% |  | 322307.5571 | 322903.9426
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 455d | [5 empty] | 222597.599 |  | 99.69% |  | 191077.3019 | 191673.6874
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 100% |  | 46004.3158 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 100 | 100 | 100 | 100 | 100
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 100% | Finished | 3504.3167 | 3504.3167 | 100 | 75.8475 | 100 | 100 | 75.8475 | 100
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 155d | [5 empty] | 34149.989 |  | 98.51% |  | 39420.2699 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 126d | 4899.989 | 661.1096 | 17d | 0 | 0 | 4899.989 | 661.1096 | 88.11% | Started | 4420.2699 | 5016.6554 | 100 | 97.6744 | 88.1119 | 100 | 97.6744 | 88.1119
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 100% |  | 24991.1641 | 24991.1641
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 100% | Finished | 2491.1479 | 2491.1479 | 100 | 99.1736 | 100 | 100 | 99.1736 | 100
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 30d | [5 empty] | 12784.376 |  | 19.63% |  | 12784.376 | 12784.376
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 25d | [5 empty] | 10000 |  | 100% |  | 10000 | 10000
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2013-01-21 08:00 | 5d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 5d | [5 empty] | 2784.376 |  | 5.05% |  | 2784.376 | 2784.376
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-01-28 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 |  | 0 | 0 | 16000 | 40d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 2013-01-28 08:00 | 5d | 284.376 | 6199.3966 | 109d | 0 | 0 | 284.376 | 6199.3966 | 4.386% | Started | 284.376 | 284.376 | 100 | 4.386 | 4.386 | 100 | 4.386 | 4.386
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP29
| TP Status Date | 2013-03-04 08:00 |  | TP Name | T29
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 630d | [5 empty] | 395529.7638 |  | 88.48% |  | 332041.4466 | 332041.4466
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 472d | [5 empty] | 223258.7086 |  | 100% |  | 191673.6874 | 191673.6874
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 100% |  | 46004.3158 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 100 | 100 | 100 | 100 | 100
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 100% | Finished | 3504.3167 | 3504.3167 | 100 | 75.8475 | 100 | 100 | 75.8475 | 100
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 172d | [5 empty] | 34811.0986 |  | 100% |  | 40016.6554 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 143d | 5561.0986 | 0 | 0 | 0 | 0 | 5561.0986 | 0 | 100% | Finished | 5016.6554 | 5016.6554 | 100 | 110.8527 | 100 | 100 | 110.8527 | 100
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-02-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 100% |  | 24991.1641 | 24991.1641
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 100% | Finished | 2491.1479 | 2491.1479 | 100 | 99.1736 | 100 | 100 | 99.1736 | 100
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 50d | [5 empty] | 21921.88 |  | 33.66% |  | 21921.8799 | 21921.88
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 25d | [5 empty] | 10000 |  | 100% |  | 10000 | 10000
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2013-01-21 08:00 | 5d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 25d | [5 empty] | 11921.88 |  | 21.62% |  | 11921.8799 | 11921.88
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-01-28 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 | 2013-02-04 08:00 | 20d | 8000 | 8000 | 20d | 0 | 0 | 8000 | 8000 | 50% | Started | 8000 | 8000 | 100 | 50 | 50 | 100 | 50 | 50
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 2013-01-28 08:00 | 25d | 1421.88 | 5061.8927 | 89d | 0 | 0 | 1421.88 | 5061.8927 | 21.93% | Started | 1421.8799 | 1421.88 | 100 | 21.9298 | 21.9298 | 100 | 21.9298 | 21.9298
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP30
| TP Status Date | 2013-04-01 08:00 |  | TP Name | T30
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 650d | [5 empty] | 404667.2678 |  | 90.92% |  | 341178.9506 | 341178.9506
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 472d | [5 empty] | 223258.7086 |  | 100% |  | 191673.6874 | 191673.6874
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 100% |  | 46004.3158 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 100 | 100 | 100 | 100 | 100
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 100% | Finished | 3504.3167 | 3504.3167 | 100 | 75.8475 | 100 | 100 | 75.8475 | 100
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 172d | [5 empty] | 34811.0986 |  | 100% |  | 40016.6554 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 143d | 5561.0986 | 0 | 0 | 0 | 0 | 5561.0986 | 0 | 100% | Finished | 5016.6554 | 5016.6554 | 100 | 110.8527 | 100 | 100 | 110.8527 | 100
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-02-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 100% |  | 24991.1641 | 24991.1641
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 100% | Finished | 2491.1479 | 2491.1479 | 100 | 99.1736 | 100 | 100 | 99.1736 | 100
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 70d | [5 empty] | 31059.3839 |  | 47.69% |  | 31059.384 | 31059.3839
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 25d | [5 empty] | 10000 |  | 100% |  | 10000 | 10000
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2013-01-21 08:00 | 5d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 45d | [5 empty] | 21059.3839 |  | 38.2% |  | 21059.384 | 21059.3839
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-01-28 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 | 2013-02-04 08:00 | 40d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 100 | 100 | 100 | 100 | 100 | 100
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 |  | 0 | 0 | 5000.0038 | 15d | 0 | 0 | 0 | 5000.0038 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 |  | 0 | 0 | 7500 | 15d | 0 | 0 | 0 | 7500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 2013-01-28 08:00 | 45d | 2559.3839 | 3924.3887 | 69d | 0 | 0 | 2559.3839 | 3924.3887 | 39.47% | Started | 2559.384 | 2559.3839 | 100 | 39.4737 | 39.4737 | 100 | 39.4737 | 39.4737
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP31
| TP Status Date | 2013-05-06 08:00 |  | TP Name | T31
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 675d | [5 empty] | 416089.1515 |  | 93.96% |  | 352600.8343 | 352600.8343
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 472d | [5 empty] | 223258.7086 |  | 100% |  | 191673.6874 | 191673.6874
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 100% |  | 46004.3158 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 100 | 100 | 100 | 100 | 100
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 100% | Finished | 3504.3167 | 3504.3167 | 100 | 75.8475 | 100 | 100 | 75.8475 | 100
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 172d | [5 empty] | 34811.0986 |  | 100% |  | 40016.6554 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 143d | 5561.0986 | 0 | 0 | 0 | 0 | 5561.0986 | 0 | 100% | Finished | 5016.6554 | 5016.6554 | 100 | 110.8527 | 100 | 100 | 110.8527 | 100
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-02-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 100% |  | 24991.1641 | 24991.1641
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 100% | Finished | 2491.1479 | 2491.1479 | 100 | 99.1736 | 100 | 100 | 99.1736 | 100
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 95d | [5 empty] | 42481.2677 |  | 65.22% |  | 42481.2677 | 42481.2677
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 25d | [5 empty] | 10000 |  | 100% |  | 10000 | 10000
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2013-01-21 08:00 | 5d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 70d | [5 empty] | 32481.2677 |  | 58.91% |  | 32481.2677 | 32481.2677
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-01-28 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 | 2013-02-04 08:00 | 40d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 100 | 100 | 100 | 100 | 100 | 100
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2013-04-01 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-04-22 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2013-04-29 08:00 | 5d | 2500 | 5000 | 10d | 0 | 0 | 2500 | 5000 | 33.33% | Started | 2500.0001 | 2500 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 5d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 2013-01-28 08:00 | 70d | 3981.2639 | 2502.5087 | 44d | 0 | 0 | 3981.2639 | 2502.5087 | 61.4% | Started | 3981.2638 | 3981.2639 | 100 | 61.4035 | 61.4035 | 100 | 61.4035 | 61.4035
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP32
| TP Status Date | 2013-06-03 08:00 |  | TP Name | T32
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 695d | [5 empty] | 427226.6555 |  | 96.93% |  | 363738.3385 | 363738.3383
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 472d | [5 empty] | 223258.7086 |  | 100% |  | 191673.6874 | 191673.6874
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 100% |  | 46004.3158 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 100 | 100 | 100 | 100 | 100
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 100% | Finished | 3504.3167 | 3504.3167 | 100 | 75.8475 | 100 | 100 | 75.8475 | 100
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 172d | [5 empty] | 34811.0986 |  | 100% |  | 40016.6554 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 143d | 5561.0986 | 0 | 0 | 0 | 0 | 5561.0986 | 0 | 100% | Finished | 5016.6554 | 5016.6554 | 100 | 110.8527 | 100 | 100 | 110.8527 | 100
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-02-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 100% |  | 24991.1641 | 24991.1641
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 100% | Finished | 2491.1479 | 2491.1479 | 100 | 99.1736 | 100 | 100 | 99.1736 | 100
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 115d | [5 empty] | 53618.7717 |  | 82.32% |  | 53618.7719 | 53618.7717
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 25d | [5 empty] | 10000 |  | 100% |  | 10000 | 10000
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2013-01-21 08:00 | 5d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 90d | [5 empty] | 43618.7717 |  | 79.11% |  | 43618.7719 | 43618.7717
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-01-28 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 | 2013-02-04 08:00 | 40d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 100 | 100 | 100 | 100 | 100 | 100
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2013-04-01 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-04-22 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2013-04-29 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-05-20 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-05-27 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 |  | 0 | 0 | 10150 | 29d | 0 | 0 | 0 | 10150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 2013-01-28 08:00 | 90d | 5118.7679 | 1365.0048 | 24d | 0 | 0 | 5118.7679 | 1365.0048 | 78.95% | Started | 5118.768 | 5118.7679 | 100 | 78.9474 | 78.9474 | 100 | 78.9474 | 78.9474
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP33
| TP Status Date | 2013-07-01 08:00 |  | TP Name | T33
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 715d | [5 empty] | 435364.1595 |  | 99.1% |  | 371875.8425 | 371875.8423
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 472d | [5 empty] | 223258.7086 |  | 100% |  | 191673.6874 | 191673.6874
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 100% |  | 46004.3158 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 100 | 100 | 100 | 100 | 100
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 100% | Finished | 3504.3167 | 3504.3167 | 100 | 75.8475 | 100 | 100 | 75.8475 | 100
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 172d | [5 empty] | 34811.0986 |  | 100% |  | 40016.6554 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 143d | 5561.0986 | 0 | 0 | 0 | 0 | 5561.0986 | 0 | 100% | Finished | 5016.6554 | 5016.6554 | 100 | 110.8527 | 100 | 100 | 110.8527 | 100
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-02-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 100% |  | 24991.1641 | 24991.1641
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 100% | Finished | 2491.1479 | 2491.1479 | 100 | 99.1736 | 100 | 100 | 99.1736 | 100
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 135d | [5 empty] | 61756.2756 |  | 94.81% |  | 61756.2759 | 61756.2756
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 25d | [5 empty] | 10000 |  | 100% |  | 10000 | 10000
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2013-01-21 08:00 | 5d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 110d | [5 empty] | 51756.2756 |  | 93.87% |  | 51756.2759 | 51756.2756
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-01-28 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 | 2013-02-04 08:00 | 40d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 100 | 100 | 100 | 100 | 100 | 100
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2013-04-01 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-04-22 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2013-04-29 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-05-20 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-05-27 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 | 2013-06-03 08:00 | 20d | 7000 | 3150 | 9d | 0 | 0 | 7000 | 3150 | 68.97% | Started | 7000.0001 | 7000 | 100 | 68.9655 | 68.9655 | 100 | 68.9655 | 68.9655
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 2013-01-28 08:00 | 110d | 6256.2718 | 227.5008 | 4d | 0 | 0 | 6256.2718 | 227.5008 | 96.49% | Started | 6256.2719 | 6256.2718 | 100 | 96.4912 | 96.4912 | 100 | 96.4912 | 96.4912
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP34
| TP Status Date | 2013-08-05 08:00 |  | TP Name | T34
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | SCM System | 2010-10-04 08:00 | 2013-07-12 17:00 | 725d |  |  | 0 |  |  | 375253.3431 |  | 725d | [5 empty] | 438741.6603 |  | 100% |  | 375253.3431 | 375253.3431
1 | Project has started | 2010-10-04 08:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
127 | Phase 1: Global Analysis and Analysis Early Validation | 2010-10-04 08:00 | 2010-12-24 17:00 | 60d |  |  | 0 |  |  | 44999.996 |  | 85d | [5 empty] | 69999.996 |  | 100% |  | 44999.996 | 44999.996
2 | Prepare next visit | 2010-10-04 08:00 | 2010-10-08 17:00 | 5d |  | 0 | 0 | 125 | 5000 | 5000 | 2010-10-04 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Global Analysis of the Planning Cycle | 2010-10-11 08:00 | 2010-11-05 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-10-11 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
4 | Analyse details for Integration by Excel | 2010-11-03 08:00 | 2010-11-09 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2010-11-08 08:00 | 20d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 2500 | 2500 | 100 | 400 | 100 | 100 | 400 | 100
5 | Analyse Master planning rules in detail for plant A | 2010-10-27 08:00 | 2010-11-09 17:00 | 10d |  | 0 | 0 | 93.75 | 7500 | 7500 | 2010-11-29 08:00 | 20d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 7500 | 7500 | 100 | 200 | 100 | 100 | 200 | 100
6 | Analyse gaps of Master planning rules in detail for plant B | 2010-11-29 08:00 | 2010-12-24 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2010-11-29 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
7 | Analyse gaps of Master planning rules for other plants | 2010-10-13 08:00 | 2010-11-09 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2010-11-29 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
8 | Analyse DRP for Early Validation (incl. deployment engine) | 2010-11-22 08:00 | 2010-12-10 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2010-11-22 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
9 | Validate concept internal + prepare document/presentation for next visit | 2010-11-10 08:00 | 2010-11-23 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2010-12-27 08:00 | 20d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 200 | 100 | 100 | 200 | 100
10 | Validate Analysis with Business and get acceptance | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 187.5 | 7500 | 7500 | 2011-01-24 08:00 | 5d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
11 | Phase 1: Global Analysis is accepted and phase is closed | 2010-11-30 17:00 | 2010-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
128 | Phase 1: Global Analysis and Analysis Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
135 | Minimum implementation needed for Early Validation | 2010-11-29 08:00 | 2011-03-11 17:00 | 75d |  |  | 0 |  |  | 73445.8833 |  | 70d | [5 empty] | 80349.1793 |  | 100% |  | 73445.8833 | 73445.8833
12 | Setup the environment | 2010-11-29 08:00 | 2010-12-10 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-01-31 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
13 | Received Master data for building the DRP model and MPS Model | 2010-12-31 17:00 | 2010-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
131 | Model integration | 2010-12-13 08:00 | 2010-12-31 17:00 | 15d |  |  | 0 |  |  | 11480 |  | 15d | [5 empty] | 11480 |  | 100% |  | 11480 | 11480
14 | Model integration of Operational forecast and Sales Orders | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-14 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Model integration of the DRP master data and network | 2010-12-15 08:00 | 2010-12-21 17:00 | 5d |  | 0 | 0 | 87.5 | 3500 | 3500 | 2011-02-16 08:00 | 5d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
16 | Model integration of the MPS Master data (routings, BOM's,…) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-02-21 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
17 | Model integration of the inventory | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-02-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Coordination | 2010-12-13 08:00 | 2010-12-30 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-02-14 08:00 | 14d | 980 | 0 | 0 | 0 | 0 | 980 | 0 | 100% | Finished | 980 | 980 | 100 | 100 | 100 | 100 | 100 | 100
19 | Build basic Order Allocation Model (Accept all orders, straightforward forecast netting) | 2010-12-20 08:00 | 2010-12-31 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2011-02-21 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
132 | Build basic DRP model (only pushing demand from DC to plant + manual planning) | 2011-01-03 08:00 | 2011-02-25 17:00 | 40d |  |  | 0 |  |  | 14989.0823 |  | 34d | [5 empty] | 13548.1744 |  | 100% |  | 14989.0823 | 14989.0823
20 | Check master data from Excel | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
21 | Build DRP model | 2011-01-17 08:00 | 2011-02-04 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2011-03-14 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Test off-line the DRP model | 2011-02-07 08:00 | 2011-02-11 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-03-28 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
23 | Validate DRP with Business | 2011-02-14 08:00 | 2011-02-25 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-04-04 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
24 | Coordination | 2011-01-03 08:00 | 2011-02-24 17:00 | 39d |  | 0 | 0 | 4.7727 | 1489.0823 | 1489.0823 | 2011-03-07 08:00 | 34d | 1298.1744 | 0 | 0 | 0 | 0 | 1298.1744 | 0 | 100% | Finished | 1489.0823 | 1489.0823 | 100 | 87.1795 | 100 | 100 | 87.1795 | 100
133 | Build Master Planning model for Early validation (no campaigns) | 2011-01-03 08:00 | 2011-03-11 17:00 | 50d |  |  | 0 |  |  | 38976.8009 |  | 45d | [5 empty] | 47321.0049 |  | 100% |  | 38976.8009 | 38976.8009
25 | Check master data for two test plants | 2011-01-03 08:00 | 2011-01-07 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-03-07 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
26 | Build Master Planning Model for two test plants | 2011-01-10 08:00 | 2011-02-04 17:00 | 20d |  | 0 | 0 | 93.75 | 15000 | 15000 | 2011-03-14 08:00 | 25d | 18750 | 0 | 0 | 0 | 0 | 18750 | 0 | 100% | Finished | 15000 | 15000 | 100 | 125 | 100 | 100 | 125 | 100
27 | Configure basic solvers (heuristics for capacity and inventory constraints) | 2011-02-07 08:00 | 2011-02-18 17:00 | 10d |  | 0 | 0 | 62.5 | 5000 | 5000 | 2011-04-04 08:00 | 10d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
28 | Test off-line the Master Planning | 2011-02-21 08:00 | 2011-02-25 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2011-04-11 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
29 | Validate Master Planning with Business | 2011-02-28 08:00 | 2011-03-11 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2011-04-18 08:00 | 15d | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 150 | 100
30 | Coordination | 2011-01-03 08:00 | 2011-03-10 17:00 | 49d |  | 0 | 0 | 10.1449 | 3976.8009 | 3976.8009 | 2011-03-07 08:00 | 44d | 3571.0049 | 0 | 0 | 0 | 0 | 3571.0049 | 0 | 100% | Finished | 3976.8009 | 3976.8009 | 100 | 89.7959 | 100 | 100 | 89.7959 | 100
31 | Phase 2: Early Validation is accepted | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | Phase 3: Full Implementation of DRP and Master Planning | 2011-03-11 17:00 | 2012-12-21 17:00 | 465d |  |  | 0 |  |  | 191673.6874 |  | 472d | [5 empty] | 223258.7086 |  | 100% |  | 191673.6874 | 191673.6874
32 | Purchase Order for Implementation is received | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
136 | Analyse DRP and Master Planing | 2011-03-11 17:00 | 2011-04-15 17:00 | 25d |  |  | 0 |  |  | 24000 |  | 35d | [5 empty] | 30112.5 |  | 100% |  | 24000 | 24000
33 | Analyze remaining details for Integration (final) | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 20 | 4000 | 4000 | 2011-05-09 08:00 | 35d | 5600 | 0 | 0 | 0 | 0 | 5600 | 0 | 100% | Finished | 4000 | 4000 | 100 | 140 | 100 | 100 | 140 | 100
34 | Analyze Order allocation rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
35 | Analyze DRP rules in detail | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 37.5 | 7500 | 7500 | 2011-05-09 08:00 | 35d | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 140 | 100 | 100 | 140 | 100
36 | Analyse shape Campaign rules in detail for plant A | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 25 | 5000 | 5000 | 2011-05-09 08:00 | 35d | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 140 | 100 | 100 | 140 | 100
37 | Analyse shape Campaign rules in detail for plant B | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 1h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 2500 | 2500 | 100 | 0.5 | 100 | 100 | 0.5 | 100
38 | Analyse gaps of Master planning rules in detail for remaining plants | 2011-03-14 08:00 | 2011-04-15 17:00 | 25d |  | 0 | 0 | 12.5 | 2500 | 2500 | 2011-05-09 08:00 | 35d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 140 | 100 | 100 | 140 | 100
39 | Analysis of DRP and Master Planning is finished | 2011-03-11 17:00 | 2011-03-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-05-09 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
137 | Implement Integration | 2011-03-14 08:00 | 2011-05-20 17:00 | 50d |  |  | 0 |  |  | 14669.8552 |  | 70d | [5 empty] | 28232.3552 |  | 100% |  | 14669.8552 | 14669.8552
148 | Model integration | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  |  | 0 |  |  | 3125 |  | 10d | [5 empty] | 11000 |  | 100% |  | 3125 | 3125
40 | Configure SAI2 | 2011-04-18 08:00 | 2011-04-18 09:00 | 1h |  | 0 | 0 | 125 | 125 | 125 | 2011-06-27 08:00 | 5d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 125 | 125 | 100 | 4000 | 100 | 100 | 4000 | 100
41 | Model integration of the feedback on Transport/Purchase orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
42 | Model integration of the feedback on Manufacturing Orders | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-06-27 08:00 | 10d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
145 | Model integration from DRP | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  |  | 0 |  |  | 6500 |  | 15d | [5 empty] | 9750 |  | 100% |  | 6500 | 6500
43 | Model integration of intercompany Transport orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
44 | Model integration of Purchase Orders | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-07-11 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 2500 | 2500 | 100 | 150 | 100 | 100 | 150 | 100
45 | Model Purchase requisitions to data warehouse | 2011-04-25 08:00 | 2011-05-06 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-07-11 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
144 | Model integration from Master Planning | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  |  | 0 |  |  | 3562.5 |  | 10d | [5 empty] | 6000 |  | 100% |  | 3562.5 | 3562.5
46 | Configure SAI3 and SAI4b | 2011-05-09 08:00 | 2011-05-09 09:00 | 1h |  | 0 | 0 | 62.5 | 62.5 | 62.5 | 2011-08-01 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 62.5 | 62.5 | 100 | 4000 | 100 | 100 | 4000 | 100
47 | Model integration of Manufacturing Orders to ASI and Excel | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 25 | 2000 | 2000 | 2011-08-01 08:00 | 10d | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 100% | Finished | 2000 | 2000 | 100 | 100 | 100 | 100 | 100 | 100
48 | Model integration of Manufacturing requisitions | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-08-01 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
49 | Coordination | 2011-03-14 08:00 | 2011-04-14 17:00 | 24d |  | 0 | 0 | 7.7206 | 1482.3552 | 1482.3552 | 2011-05-09 08:00 | 24d | 1482.3552 | 0 | 0 | 0 | 0 | 1482.3552 | 0 | 100% | Finished | 1482.3552 | 1482.3552 | 100 | 100 | 100 | 100 | 100 | 100
50 | Implementation of the Integration is finished | 2011-05-20 17:00 | 2011-05-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
138 | Implement Order Allocation | 2011-04-15 17:00 | 2011-05-06 17:00 | 15d |  |  | 0 |  |  | 4480 |  | 45d | [5 empty] | 13580 |  | 100% |  | 4480 | 4480
51 | Received Forecast and Customer Orders from customer for off-line application testing | 2011-04-15 17:00 | 2011-04-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | Complete Order Allocation model with rules | 2011-04-18 08:00 | 2011-04-22 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-03 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
53 | Off-line application testing + check data | 2011-04-25 08:00 | 2011-04-29 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2011-10-24 08:00 | 15d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 300 | 100 | 100 | 300 | 100
54 | Validate Order Allocation with Business | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2011-11-14 08:00 | 15d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 300 | 100 | 100 | 300 | 100
55 | Coordination | 2011-04-18 08:00 | 2011-05-05 17:00 | 14d |  | 0 | 0 | 8.75 | 980 | 980 | 2011-10-03 08:00 | 44d | 3080 | 0 | 0 | 0 | 0 | 3080 | 0 | 100% | Finished | 980 | 980 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
56 | Implementation of the Order Allocation is finished | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
139 | Implement DRP for complete US Market | 2011-05-06 17:00 | 2011-11-04 17:00 | 130d |  |  | 0 |  |  | 37511.6969 |  | 169d | [5 empty] | 52464.4845 |  | 100% |  | 37511.6969 | 37511.6969
57 | Received Master data for building the DRP model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
58 | Check master data | 2011-05-09 08:00 | 2011-05-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-09-12 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
59 | Complete Build DRP model | 2011-05-23 08:00 | 2011-06-10 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2011-09-26 08:00 | 50d | 16666.6794 | 0 | 0 | 0 | 0 | 16666.6794 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 333.3333 | 100 | 100 | 333.3333 | 100
60 | Configure basic solvers (heuristics for pulling inventory to RDC's) | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
61 | Model manufacturing requirements for Master Planning | 2011-06-13 08:00 | 2011-06-24 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2011-12-05 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
62 | Test off-line the DRP model | 2011-06-27 08:00 | 2011-07-08 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2011-12-19 08:00 | 20d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1500 | 1500 | 100 | 200 | 100 | 100 | 200 | 100
63 | Validate DRP with Business | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-01-16 08:00 | 25d | 8333.3397 | 0 | 0 | 0 | 0 | 8333.3397 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
64 | Integration test, Dry-run tests and GO-live of DRP | 2011-08-01 08:00 | 2011-08-19 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-02-20 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 200 | 100 | 100 | 200 | 100
65 | Interactive DRP with basic solvers is live | 2011-09-05 17:00 | 2011-09-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-03-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | Assistence after go-live | 2011-09-05 08:00 | 2011-09-23 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-03-30 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
67 | Adapt Solver for pushing surplus inventory to RDC's | 2011-09-26 08:00 | 2011-11-04 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-03-30 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 50 | 100 | 100 | 50 | 100
68 | Coordination | 2011-05-09 08:00 | 2011-11-03 17:00 | 129d |  | 0 | 0 | 3.4028 | 3511.6897 | 3511.6897 | 2011-08-29 08:00 | 164d | 4464.4737 | 0 | 0 | 0 | 0 | 4464.4737 | 0 | 100% | Finished | 3511.6897 | 3511.6897 | 100 | 127.1318 | 100 | 100 | 127.1318 | 100
69 | Implementation of DRP for the complete US Market is finished | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-04-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
140 | Complete Implemention Master Planning GO LIVE 1 | 2011-05-06 17:00 | 2012-10-04 17:00 | 369d |  |  | 0 |  |  | 46004.3158 |  | 224d | [5 empty] | 43491.2703 |  | 100% |  | 46004.3158 | 46004.3158
70 | Received Master Data for building the Master Planning model | 2011-05-06 17:00 | 2011-05-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-02-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Check master data of plant A | 2011-05-23 08:00 | 2011-06-03 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-03-30 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
72 | Test off-line the Master Planning | 2011-07-11 08:00 | 2011-07-29 17:00 | 15d |  | 0 | 0 | 20.8333 | 2499.996 | 2499.996 | 2012-04-13 08:00 | 15d | 2499.996 | 0 | 0 | 0 | 0 | 2499.996 | 0 | 100% | Finished | 2499.996 | 2499.996 | 100 | 100 | 100 | 100 | 100 | 100
73 | Validate Master Planning with Business + on the job training | 2011-08-01 08:00 | 2011-09-09 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-05-04 08:00 | 20d | 3333.3279 | 0 | 0 | 0 | 0 | 3333.3279 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
74 | Configure Shape Campaigns for plant A | 2011-09-12 08:00 | 2011-11-11 17:00 | 45d |  | 0 | 0 | 27.7778 | 10000.0079 | 10000.0079 | 2012-06-01 08:00 | 45d | 10000.0079 | 0 | 0 | 0 | 0 | 10000.0079 | 0 | 100% | Finished | 10000.0079 | 10000.0079 | 100 | 100 | 100 | 100 | 100 | 100
75 | Validate Shape campaigns with plant A Business + on the job training | 2011-11-14 08:00 | 2011-12-23 17:00 | 30d |  | 0 | 0 | 20.8333 | 4999.9919 | 4999.9919 | 2012-08-03 08:00 | 30d | 4999.9919 | 0 | 0 | 0 | 0 | 4999.9919 | 0 | 100% | Finished | 4999.9919 | 4999.9919 | 100 | 100 | 100 | 100 | 100 | 100
76 | Dry-run tests and GO-live of MPS in plant A | 2011-12-26 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-09-14 08:00 | 20d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
77 | Interactive MPS with basic solvers at plant A is live | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-10-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
78 | Assistence after go-live | 2012-02-06 08:00 | 2012-02-24 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2012-10-12 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
79 | Refine basic Solver | 2012-02-27 08:00 | 2012-04-06 17:00 | 30d |  | 0 | 0 | 41.6667 | 10000.0076 | 10000.0076 | 2012-11-02 08:00 | 30d | 10000.0076 | 0 | 0 | 0 | 0 | 10000.0076 | 0 | 100% | Finished | 10000.0076 | 10000.0076 | 100 | 100 | 100 | 100 | 100 | 100
80 | Coordination | 2011-05-09 08:00 | 2012-04-02 17:00 | 236d |  | 0 | 0 | 1.8561 | 3504.3167 | 3504.3167 | 2012-03-30 08:00 | 179d | 2657.9351 | 0 | 0 | 0 | 0 | 2657.9351 | 0 | 100% | Finished | 3504.3167 | 3504.3167 | 100 | 75.8475 | 100 | 100 | 75.8475 | 100
81 | Completion of the implementation of Master Planning in Pilot plant A is finished | 2012-10-04 17:00 | 2012-10-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
141 | Implement Master Planning GO LIVE 2 | 2012-02-03 17:00 | 2012-08-10 17:00 | 135d |  |  | 0 |  |  | 40016.6554 |  | 172d | [5 empty] | 34811.0986 |  | 100% |  | 40016.6554 | 40016.6554
82 | Received Master Data for building the Master Planning model | 2012-02-03 17:00 | 2012-02-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Check master data of go live 2 | 2012-02-06 08:00 | 2012-02-17 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
84 | Adapt Master Planning Model to go live 2 | 2012-02-20 08:00 | 2012-03-30 17:00 | 30d |  | 0 | 0 | 31.25 | 7500 | 7500 | 2012-08-24 08:00 | 25d | 6250 | 0 | 0 | 0 | 0 | 6250 | 0 | 100% | Finished | 7500 | 7500 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
85 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-04-02 08:00 | 2012-04-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-09-28 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
86 | Adapt Shape Campaigns configuration for plant B | 2012-04-02 08:00 | 2012-04-27 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-09-28 08:00 | 15d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 5000 | 5000 | 100 | 75 | 100 | 100 | 75 | 100
87 | Test off-line the Master Planning | 2012-04-30 08:00 | 2012-05-11 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-10-19 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
88 | Validate Master Planning with plant B Business | 2012-05-14 08:00 | 2012-05-25 17:00 | 10d |  | 0 | 0 | 43.75 | 3500 | 3500 | 2012-10-26 08:00 | 10d | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 100% | Finished | 3500 | 3500 | 100 | 100 | 100 | 100 | 100 | 100
89 | Validate Shape campaigns with plant B Business | 2012-05-28 08:00 | 2012-06-08 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-11-09 08:00 | 5d | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 100% | Finished | 2500 | 2500 | 100 | 50 | 100 | 100 | 50 | 100
90 | Dry-run tests and GO-live of MPS in plant B | 2012-06-11 08:00 | 2012-06-22 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-11-16 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
91 | Interactive MPS with basic solvers at plant B is live | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
92 | Assistence after go-live | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2012-08-10 08:00 | 10d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
93 | Refine basic Solver | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 31.25 | 5000 | 5000 | 2012-08-24 08:00 | 20d | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 100% | Finished | 5000 | 5000 | 100 | 100 | 100 | 100 | 100 | 100
94 | Coordination | 2012-02-06 08:00 | 2012-08-02 17:00 | 129d |  | 0 | 0 | 4.8611 | 5016.6554 | 5016.6554 | 2012-08-10 08:00 | 143d | 5561.0986 | 0 | 0 | 0 | 0 | 5561.0986 | 0 | 100% | Finished | 5016.6554 | 5016.6554 | 100 | 110.8527 | 100 | 100 | 110.8527 | 100
95 | Implementation of Master Planning in plant B with LUT is finished | 2012-08-10 17:00 | 2012-08-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-02-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
142 | Implement Master Planning GO LIVE 3 | 2012-06-29 17:00 | 2012-12-21 17:00 | 125d |  |  | 0 |  |  | 24991.1641 |  | 125d | [5 empty] | 20567 |  | 100% |  | 24991.1641 | 24991.1641
96 | Received Master Data for building the Master Planning model | 2012-06-29 17:00 | 2012-06-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
97 | Analyse Added Value planning process | 2012-07-02 08:00 | 2012-08-17 17:00 | 35d |  | 0 | 0 | 8.9286 | 2500.0081 | 2500.0081 | 2012-07-02 08:00 | 25d | 1785.7201 | 0 | 0 | 0 | 0 | 1785.7201 | 0 | 100% | Finished | 2500.0081 | 2500.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
98 | Check master data | 2012-07-02 08:00 | 2012-07-13 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-07-02 08:00 | 15d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 1500 | 1500 | 100 | 150 | 100 | 100 | 150 | 100
99 | Adapt Master Planning Model to remaining plants | 2012-07-16 08:00 | 2012-08-31 17:00 | 35d |  | 0 | 0 | 21.4286 | 6000.0081 | 6000.0081 | 2012-07-23 08:00 | 25d | 4285.7201 | 0 | 0 | 0 | 0 | 4285.7201 | 0 | 100% | Finished | 6000.0081 | 6000.0081 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
100 | Adapt basic solvers (heuristics for capacity and inventory constraints) | 2012-07-16 08:00 | 2012-08-10 17:00 | 20d |  | 0 | 0 | 15.625 | 2500 | 2500 | 2012-07-23 08:00 | 15d | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 2500 | 2500 | 100 | 75 | 100 | 100 | 75 | 100
101 | Test off-line the Master Planning | 2012-09-03 08:00 | 2012-09-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-08-27 08:00 | 5d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
102 | Validate Master Planning with remaining plants Business | 2012-09-17 08:00 | 2012-10-19 17:00 | 25d |  | 0 | 0 | 15 | 3000 | 3000 | 2012-09-03 08:00 | 20d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 3000 | 3000 | 100 | 80 | 100 | 100 | 80 | 100
103 | Dry-run tests and GO-live of MPS in remaining plants | 2012-10-22 08:00 | 2012-11-16 17:00 | 20d |  | 0 | 0 | 9.375 | 1500 | 1500 | 2012-10-01 08:00 | 10d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
104 | Interactive MPS with basic solvers at remaining plants is live | 2012-11-30 17:00 | 2012-11-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | Assistence after go-live | 2012-12-03 08:00 | 2012-12-14 17:00 | 10d |  | 0 | 0 | 18.75 | 1500 | 1500 | 2012-12-03 08:00 | 10d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
106 | Refine basic Solver | 2012-12-17 08:00 | 2012-12-21 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2012-12-17 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
107 | Coordination | 2012-07-02 08:00 | 2012-12-17 17:00 | 121d |  | 0 | 0 | 2.5735 | 2491.1479 | 2491.1479 | 2012-07-02 08:00 | 120d | 2470.5599 | 0 | 0 | 0 | 0 | 2470.5599 | 0 | 100% | Finished | 2491.1479 | 2491.1479 | 100 | 99.1736 | 100 | 100 | 99.1736 | 100
108 | Implementation of Master Planning in remaining plants is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
109 | Phase 3: Full Implementation of DRP and Master Planning is finished | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-24 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
130 | Phase 4: Implementation of S&OP Planning | 2012-12-24 08:00 | 2013-07-12 17:00 | 145d |  |  | 0 |  |  | 65133.7764 |  | 145d | [5 empty] | 65133.7764 |  | 100% |  | 65133.7764 | 65133.7764
152 | Analysis of S&OP Planning | 2012-12-24 08:00 | 2013-01-25 17:00 | 25d |  |  | 0 |  |  | 10000 |  | 25d | [5 empty] | 10000 |  | 100% |  | 10000 | 10000
110 | Analyze details for Integration with S&OP | 2012-12-24 08:00 | 2012-12-28 17:00 | 5d |  | 0 | 0 | 25 | 1000 | 1000 | 2012-12-24 08:00 | 5d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 100 | 100 | 100 | 100 | 100
111 | Analyze S&OP rules in detail | 2012-12-31 08:00 | 2013-01-18 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2012-12-31 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
112 | Analyze integration of S&OP in DRP and Master Planning | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 37.5 | 1500 | 1500 | 2013-01-21 08:00 | 5d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
113 | Analysis of S&OP Planning is finished | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Implementation of S&OP Planning | 2013-01-25 17:00 | 2013-07-12 17:00 | 120d |  |  | 0 |  |  | 55133.7764 |  | 120d | [5 empty] | 55133.7764 |  | 100% |  | 55133.7764 | 55133.7764
114 | Received Master data for building the S&OP model | 2013-01-25 17:00 | 2013-01-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-01-28 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | Check master data | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-01-28 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
116 | Build S&OP model | 2013-02-04 08:00 | 2013-03-29 17:00 | 40d |  | 0 | 0 | 50 | 16000 | 16000 | 2013-02-04 08:00 | 40d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 100 | 100 | 100 | 100 | 100 | 100
117 | Configure basic solvers | 2013-04-01 08:00 | 2013-04-19 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000.0038 | 5000.0038 | 2013-04-01 08:00 | 15d | 5000.0038 | 0 | 0 | 0 | 0 | 5000.0038 | 0 | 100% | Finished | 5000.0038 | 5000.0038 | 100 | 100 | 100 | 100 | 100 | 100
118 | Test off-line the S&OP model | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-04-22 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
119 | Validate S&OP with Business | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 62.5 | 7500 | 7500 | 2013-04-29 08:00 | 15d | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 100% | Finished | 7500 | 7500 | 100 | 100 | 100 | 100 | 100 | 100
120 | Integration test, Dry-run tests and GO-live of S&OP | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-05-20 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
121 | Interactive S&OP with basic solvers is live | 2013-05-24 17:00 | 2013-05-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
122 | Assistence after go-live | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 62.5 | 2500 | 2500 | 2013-05-27 08:00 | 5d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500 | 100 | 100 | 100 | 100 | 100 | 100
123 | Refine basic Solver for S&OP | 2013-06-03 08:00 | 2013-07-11 17:00 | 29d |  | 0 | 0 | 43.75 | 10150 | 10150 | 2013-06-03 08:00 | 29d | 10150 | 0 | 0 | 0 | 0 | 10150 | 0 | 100% | Finished | 10150 | 10150 | 100 | 100 | 100 | 100 | 100 | 100
124 | Coordination | 2013-01-28 08:00 | 2013-07-04 17:00 | 114d |  | 0 | 0 | 7.1094 | 6483.7726 | 6483.7726 | 2013-01-28 08:00 | 114d | 6483.7726 | 0 | 0 | 0 | 0 | 6483.7726 | 0 | 100% | Finished | 6483.7726 | 6483.7726 | 100 | 100 | 100 | 100 | 100 | 100
125 | Implementation of S&OP Planning is finished | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
126 | Project is closed | 2013-07-12 17:00 | 2013-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
T1 | 2010-10-04 08:00 | 2010-11-01 08:00 | 12375 | 6000 | 6000 | 2010-10-14 17:00 | -6375 | 48.48% | 1.4901e-05 | 100% | -11d | 45% | 91.67% | 2013-07-31 11:00 | 2016-06-27 10:00 | 2016-06-27 10:00 | 2013-07-29 10:00 | 2016-06-27 10:00 | 2016-06-27 10:00 | 2013-07-29 17:00 | 2016-12-06 09:00 | 2016-12-06 09:00 | 375253.343 | 375253.3421 | 767585.0181 | 826562.9845 | 767585.0162 | 826562.9825 | 417667.5774 | 420891.3957 | 0.45 | 1 | 0.48485 | 0.91667 | -11 | 1 | 1 | 0.45 | 1
T2 | 2010-11-01 08:00 | 2010-12-06 08:00 | 44791.664 | 14166.664 | 19791.664 | 2010-11-02 12:00 | -30625 | 31.63% | -5625 | 71.58% | -23d 4h | 47.78% | 72.44% | 2013-10-04 09:00 | 2019-07-17 10:00 | 2023-01-11 12:00 | 2013-08-26 15:00 | 2019-07-17 10:00 | 2022-12-16 14:00 | 2013-08-15 12:00 | 2016-07-27 12:00 | 2018-10-24 09:00 | 380878.343 | 524251.0205 | 1161462.926 | 775554.4806 | 1614773.6549 | 1075636.8288 | 587638.5879 | 560189.2203 | 0.47778 | 0.71579 | 0.31628 | 0.72444 | -23.5 | 0.71579 | 1 | 0.47778 | 1
T3 | 2010-12-06 08:00 | 2011-01-03 08:00 | 64479.996 | 29499.996 | 46499.996 | 2010-11-18 17:00 | -34980 | 45.75% | -17000 | 63.44% | -31d | 52.31% | 83.05% | 2013-10-16 14:00 | 2016-10-28 14:00 | 2020-04-29 16:00 | 2013-09-02 10:00 | 2016-10-28 14:00 | 2020-03-09 11:00 | 2013-08-26 17:00 | 2016-01-25 17:00 | 2018-12-26 10:00 | 392253.343 | 591501.0613 | 802234.8249 | 707499.0418 | 1237743.0899 | 1088413.7974 | 623690.5357 | 611325.1684 | 0.52308 | 0.63441 | 0.45751 | 0.83051 | -31 | 0.63441 | 1 | 0.52308 | 1
T4 | 2011-01-03 08:00 | 2011-02-07 08:00 | 94963.516 | 47499.996 | 72499.996 | 2010-12-09 11:00 | -47463.52 | 50.02% | -25000 | 65.52% | -41d 5h | 53.75% | 96.44% | 2013-11-19 15:00 | 2016-04-22 12:00 | 2019-03-27 10:00 | 2013-09-13 17:00 | 2016-04-22 12:00 | 2019-01-18 17:00 | 2013-09-10 14:00 | 2015-12-03 16:00 | 2018-06-19 11:00 | 400253.3431 | 572755.1194 | 727755.0037 | 682273.665 | 1072626.0897 | 1003207.2023 | 597597.3657 | 591394.3482 | 0.5375 | 0.65517 | 0.50019 | 0.96445 | -41.625 | 0.65517 | 1 | 0.5375 | 1
T5 | 2011-02-07 08:00 | 2011-03-07 08:00 | 113121.2424 | 64479.996 | 89479.996 | 2010-12-31 17:00 | -48641.2465 | 57% | -25000 | 72.06% | -45d | 59.09% | 100% | 2013-11-21 17:00 | 2015-08-18 16:00 | 2017-07-07 17:00 | 2013-09-18 10:00 | 2015-08-18 16:00 | 2017-05-10 11:00 | 2013-09-13 17:00 | 2015-06-16 16:00 | 2017-02-10 17:00 | 400253.3431 | 520745.4982 | 634688.8877 | 615404.1218 | 846075.7231 | 819313.9229 | 539557.884 | 536849.4867 | 0.59091 | 0.72061 | 0.57001 | 1 | -45 | 0.72061 | 1 | 0.59091 | 1
T6 | 2011-03-07 08:00 | 2011-04-04 08:00 | 133772.3512 | 89663.564 | 115366.812 | 2011-02-01 09:00 | -44108.7873 | 67.03% | -25703.248 | 77.72% | -43d 7h | 66.25% | 96.55% | 2013-11-11 10:00 | 2014-11-25 14:00 | 2016-02-02 15:00 | 2013-09-11 16:00 | 2014-11-25 14:00 | 2015-12-11 12:00 | 2013-09-12 16:00 | 2014-12-12 11:00 | 2016-01-04 15:00 | 400956.5911 | 482824.6832 | 541448.651 | 546445.7238 | 663590.6527 | 670020.2025 | 493222.4011 | 494000.8703 | 0.6625 | 0.7772 | 0.67027 | 0.96549 | -43.875 | 0.7772 | 1 | 0.6625 | 1
T7 | 2011-04-04 08:00 | 2011-05-02 08:00 | 153003.2345 | 114751.0188 | 145024.5384 | 2011-03-08 12:00 | -38252.2156 | 75% | -30273.5196 | 79.13% | -38d 4h | 74.33% | 99.86% | 2013-10-24 16:00 | 2014-06-17 14:00 | 2015-06-09 15:00 | 2013-09-04 12:00 | 2014-06-17 14:00 | 2015-04-15 09:00 | 2013-09-05 12:00 | 2014-06-30 11:00 | 2015-04-30 09:00 | 405526.8626 | 474252.3719 | 492365.2295 | 495476.0956 | 584000.3654 | 587931.9377 | 477722.225 | 478288.9421 | 0.74333 | 0.79125 | 0.74999 | 0.99862 | -38.5 | 0.79125 | 1 | 0.74333 | 1
T8 | 2011-05-02 08:00 | 2011-06-06 08:00 | 170770.4943 | 134405.1253 | 168735.2064 | 2011-04-04 12:00 | -36365.369 | 78.71% | -34330.0811 | 79.65% | -44d 4h | 74.57% | 99.22% | 2013-10-21 10:00 | 2014-04-15 09:00 | 2015-03-10 12:00 | 2013-09-04 10:00 | 2014-04-15 09:00 | 2015-01-06 15:00 | 2013-09-13 12:00 | 2014-06-25 10:00 | 2015-04-06 16:00 | 409583.4242 | 471101.4566 | 474748.6052 | 491711.7436 | 552911.2852 | 574207.1894 | 471823.9149 | 475010.359 | 0.74571 | 0.79654 | 0.78705 | 0.99222 | -44.5 | 0.79654 | 1 | 0.74571 | 1
T9 | 2011-06-06 08:00 | 2011-07-04 08:00 | 179028.5863 | 145553.2345 | 189944.0304 | 2011-04-19 14:00 | -33475.3518 | 81.3% | -44390.796 | 76.63% | -53d 3h | 72.63% | 99.7% | 2013-10-11 14:00 | 2014-03-04 15:00 | 2015-03-19 15:00 | 2013-09-03 12:00 | 2014-03-04 15:00 | 2014-12-26 10:00 | 2013-09-26 11:00 | 2014-07-31 10:00 | 2015-07-09 10:00 | 419644.139 | 489698.0317 | 472472.1781 | 506212.4942 | 558637.5554 | 602667.9863 | 486086.8427 | 492861.4955 | 0.72628 | 0.7663 | 0.81302 | 0.99698 | -53.375 | 0.7663 | 1 | 0.72628 | 1
T10 | 2011-07-04 08:00 | 2011-08-01 08:00 | 188120.0101 | 153553.2345 | 202694.0304 | 2011-05-02 12:00 | -34566.7756 | 81.63% | -49140.796 | 75.76% | -64d 4h | 70% | 98.12% | 2013-10-15 15:00 | 2014-02-27 10:00 | 2015-04-01 12:00 | 2013-09-06 12:00 | 2014-02-27 10:00 | 2014-12-25 14:00 | 2013-10-11 12:00 | 2014-09-22 15:00 | 2015-09-24 11:00 | 424394.139 | 495343.6039 | 474301.6381 | 519408.4713 | 561222.725 | 620764.8496 | 490878.3645 | 499859.5 | 0.7 | 0.75756 | 0.81625 | 0.98121 | -64.5 | 0.75756 | 1 | 0.7 | 1
T11 | 2011-08-01 08:00 | 2011-09-05 08:00 | 195838.446 | 157222.7982 | 208830.1425 | 2011-05-06 09:00 | -38615.6478 | 80.28% | -51607.3443 | 75.29% | -85d 7h | 64.22% | 97.32% | 2013-10-25 14:00 | 2014-03-20 09:00 | 2015-05-08 12:00 | 2013-09-18 11:00 | 2014-03-20 09:00 | 2015-01-19 15:00 | 2013-11-11 16:00 | 2015-01-29 17:00 | 2016-03-14 15:00 | 426860.6873 | 498427.7726 | 480411.3863 | 548342.4265 | 569556.1344 | 659785.0896 | 494635.7695 | 507200.9913 | 0.64219 | 0.75287 | 0.80282 | 0.97317 | -85.875 | 0.75287 | 1 | 0.64219 | 1
T12 | 2011-09-05 08:00 | 2011-10-03 08:00 | 205013.2018 | 160651.0534 | 213541.2584 | 2011-05-12 16:00 | -44362.1484 | 78.36% | -52890.205 | 75.23% | -101d 1h | 61.11% | 97.17% | 2013-11-11 15:00 | 2014-04-21 10:00 | 2015-06-19 15:00 | 2013-10-01 10:00 | 2014-04-21 10:00 | 2015-02-20 10:00 | 2013-12-03 09:00 | 2015-04-21 12:00 | 2016-06-21 12:00 | 428143.5481 | 498795.8024 | 487403.7796 | 564739.3406 | 577565.9327 | 680362.2274 | 496442.2025 | 509926.0818 | 0.61106 | 0.75232 | 0.78361 | 0.97174 | -101.125 | 0.75232 | 1 | 0.61106 | 1
T13 | 2011-10-03 08:00 | 2011-11-07 08:00 | 219926.659 | 165909.8589 | 229305.1581 | 2011-05-25 09:00 | -54016.8002 | 75.44% | -63395.2993 | 72.35% | -117d 7h | 58.64% | 98.21% | 2013-12-06 11:00 | 2014-06-09 17:00 | 2015-11-05 10:00 | 2013-10-18 17:00 | 2014-06-09 17:00 | 2015-06-05 11:00 | 2013-12-25 16:00 | 2015-06-30 11:00 | 2016-11-18 16:00 | 438648.6423 | 518640.2288 | 506806.5278 | 586300.7781 | 612841.7115 | 722711.2623 | 516193.4301 | 530039.7337 | 0.5864 | 0.72353 | 0.75439 | 0.9821 | -117.875 | 0.72353 | 1 | 0.5864 | 1
T14 | 2011-11-07 08:00 | 2011-12-05 08:00 | 223834.743 | 170594.6302 | 243346.2779 | 2011-06-03 14:00 | -53240.1127 | 76.21% | -72751.6476 | 70.1% | -130d 3h | 57.25% | 98.42% | 2013-12-04 16:00 | 2014-05-27 10:00 | 2015-12-15 16:00 | 2013-10-23 12:00 | 2014-05-27 10:00 | 2015-06-16 16:00 | 2014-01-13 11:00 | 2015-08-11 10:00 | 2017-03-07 10:00 | 448004.9907 | 535283.5793 | 511876.0101 | 600803.1564 | 626392.9819 | 753243.9268 | 530281.1918 | 546392.8832 | 0.57254 | 0.70104 | 0.76215 | 0.98418 | -130.375 | 0.70104 | 1 | 0.57254 | 1
T15 | 2011-12-05 08:00 | 2012-01-02 08:00 | 227256.7149 | 176772.8868 | 250390.7259 | 2011-06-22 12:00 | -50483.8281 | 77.79% | -73617.8391 | 70.6% | -137d 4h | 57.69% | 98.31% | 2013-11-27 12:00 | 2014-04-29 17:00 | 2015-10-26 10:00 | 2013-10-23 10:00 | 2014-04-29 17:00 | 2015-04-17 16:00 | 2014-01-22 12:00 | 2015-07-28 14:00 | 2017-01-20 14:00 | 448871.1822 | 531529.2332 | 505554.3841 | 594423.5168 | 611818.4017 | 737697.4719 | 525919.6398 | 542198.5922 | 0.57692 | 0.70599 | 0.77786 | 0.98312 | -137.5 | 0.70599 | 1 | 0.57692 | 1
T16 | 2012-01-02 08:00 | 2012-02-06 09:00 | 229582.5688 | 181058.206 | 257571.2897 | 2011-07-12 16:00 | -48524.3628 | 78.86% | -76513.0838 | 70.29% | -148d 2h | 57.66% | 98.06% | 2013-11-21 15:00 | 2014-04-11 10:00 | 2015-10-07 15:00 | 2013-10-24 17:00 | 2014-04-11 10:00 | 2015-03-13 16:00 | 2014-02-06 10:00 | 2015-07-29 11:00 | 2017-01-16 16:00 | 451766.4268 | 533831.0243 | 503811.5426 | 594376.6018 | 607869.7983 | 736706.5941 | 527255.5108 | 544133.766 | 0.57658 | 0.70294 | 0.78864 | 0.98062 | -148.25 | 0.70294 | 1 | 0.57658 | 1
T17 | 2012-02-06 09:00 | 2012-03-05 08:00 | 242244.3587 | 184319.7942 | 263115.7376 | 2011-07-20 16:00 | -57924.5644 | 76.09% | -78795.9434 | 70.05% | -162d 1h | 56.18% | 97.5% | 2013-12-17 16:00 | 2014-05-28 16:00 | 2015-12-21 09:00 | 2013-11-14 12:00 | 2014-05-28 16:00 | 2015-05-12 17:00 | 2014-02-26 09:00 | 2015-09-14 12:00 | 2017-03-16 16:00 | 454049.2864 | 535672.5823 | 514052.2975 | 602961.3807 | 621326.6303 | 748243.9759 | 531055.5311 | 546910.7584 | 0.56182 | 0.70053 | 0.76088 | 0.97505 | -162.125 | 0.70053 | 1 | 0.56182 | 1
T18 | 2012-03-05 08:00 | 2012-04-02 08:00 | 254985.7825 | 189767.6238 | 270008.3623 | 2011-08-05 11:00 | -65218.1586 | 74.42% | -80240.7385 | 70.28% | -170d 5h | 56.25% | 97.8% | 2014-01-06 17:00 | 2014-06-27 09:00 | 2016-01-26 09:00 | 2013-11-29 15:00 | 2014-06-27 09:00 | 2015-06-09 09:00 | 2014-03-10 14:00 | 2015-09-10 16:00 | 2017-02-23 17:00 | 455494.0815 | 533924.2731 | 519240.6618 | 599760.7521 | 624625.2546 | 739192.2037 | 530850.7484 | 544900.9708 | 0.5625 | 0.70282 | 0.74423 | 0.97805 | -170.625 | 0.70282 | 1 | 0.5625 | 1
T19 | 2012-04-02 08:00 | 2012-05-07 08:00 | 266389.5192 | 209616.4261 | 283457.9076 | 2011-10-12 14:00 | -56773.0932 | 78.69% | -73841.4815 | 73.95% | -147d 3h | 64.49% | 97.05% | 2013-12-13 14:00 | 2014-04-15 11:00 | 2015-07-13 16:00 | 2013-11-14 12:00 | 2014-04-15 11:00 | 2014-12-19 15:00 | 2014-02-05 11:00 | 2015-01-23 10:00 | 2016-01-08 09:00 | 449094.8246 | 507443.6648 | 493956.3858 | 540307.3071 | 568108.5874 | 630787.5264 | 504609.691 | 513325.9452 | 0.64488 | 0.7395 | 0.78688 | 0.97046 | -147.375 | 0.7395 | 1 | 0.64488 | 1
T20 | 2012-05-07 08:00 | 2012-06-04 08:00 | 273167.2953 | 210230.1923 | 283977.106 | 2011-10-13 14:00 | -62937.103 | 76.96% | -73746.9137 | 74.03% | -166d 3h | 61.75% | 97.23% | 2013-12-31 14:00 | 2014-05-13 17:00 | 2015-08-19 12:00 | 2013-12-02 10:00 | 2014-05-13 17:00 | 2015-01-16 16:00 | 2014-03-04 11:00 | 2015-04-02 17:00 | 2016-03-31 10:00 | 449000.2568 | 506888.9355 | 498403.6223 | 551208.6391 | 573622.5698 | 644951.1249 | 505138.5696 | 514536.4784 | 0.61753 | 0.74031 | 0.7696 | 0.97233 | -166.375 | 0.74031 | 1 | 0.61753 | 1
T21 | 2012-06-04 08:00 | 2012-07-02 08:00 | 276695.0713 | 214674.6402 | 288421.5539 | 2011-10-25 09:00 | -62020.4311 | 77.59% | -73746.9137 | 74.43% | -178d 7h | 60.69% | 98.53% | 2013-12-27 16:00 | 2014-05-02 12:00 | 2015-07-27 12:00 | 2013-12-03 17:00 | 2014-05-02 12:00 | 2014-12-19 09:00 | 2014-03-20 16:00 | 2015-05-01 14:00 | 2016-04-21 15:00 | 449000.2567 | 504163.66 | 495392.1378 | 553023.8528 | 566492.4865 | 643922.3534 | 502350.3768 | 512436.7755 | 0.60687 | 0.74431 | 0.77585 | 0.98533 | -178.875 | 0.74431 | 1 | 0.60687 | 1
T22 | 2012-07-02 08:00 | 2012-08-06 08:00 | 292125.2546 | 228926.9968 | 302104.4619 | 2012-01-17 16:00 | -63198.2578 | 78.37% | -73177.4651 | 75.78% | -143d 1h | 70.18% | 96.57% | 2014-01-01 09:00 | 2014-04-21 09:00 | 2015-06-08 16:00 | 2013-12-05 16:00 | 2014-04-21 09:00 | 2014-11-05 12:00 | 2014-01-30 09:00 | 2014-09-17 17:00 | 2015-05-22 15:00 | 448430.8082 | 495204.6324 | 488826.0883 | 510599.1445 | 548512.4315 | 577245.3356 | 493894.2968 | 498098.9406 | 0.70182 | 0.75777 | 0.78366 | 0.96566 | -143.125 | 0.75777 | 1 | 0.70182 | 1
23 | 2012-08-06 08:00 | 2012-09-03 08:00 | 298554.8787 | 248575.9899 | 318715.1787 | 2012-03-16 16:00 | -49978.8888 | 83.26% | -70139.1888 | 77.99% | -120d 1h | 75.98% | 92.4% | 2013-11-26 12:00 | 2014-02-03 15:00 | 2015-01-13 12:00 | 2013-11-07 15:00 | 2014-02-03 15:00 | 2014-06-30 11:00 | 2013-12-30 09:00 | 2014-05-30 10:00 | 2014-11-26 11:00 | 445392.5319 | 481136.3171 | 470862.3825 | 485450.7538 | 513792.842 | 532497.526 | 478972.0076 | 481981.2491 | 0.75975 | 0.77993 | 0.8326 | 0.92398 | -120.125 | 0.77993 | 1 | 0.75975 | 1
24 | 2012-09-03 08:00 | 2012-10-01 08:00 | 301666.6387 | 265742.6864 | 334226.6883 | 2012-05-02 15:00 | -35923.9523 | 88.09% | -68484.0019 | 79.51% | -107d 2h | 79.38% | 90.27% | 2013-10-18 11:00 | 2013-11-27 17:00 | 2014-09-22 09:00 | 2013-10-08 16:00 | 2013-11-27 17:00 | 2014-03-18 09:00 | 2013-12-11 10:00 | 2014-04-03 11:00 | 2014-08-22 15:00 | 443737.345 | 471959.1114 | 458541.3483 | 472192.8699 | 490578.224 | 507747.8512 | 469048.7381 | 472005.7997 | 0.79375 | 0.7951 | 0.88092 | 0.90274 | -107.25 | 0.7951 | 1 | 0.79375 | 1
T25 | 2012-10-01 08:00 | 2012-11-05 08:00 | 304731.3386 | 287118.217 | 352393.1657 | 2012-07-25 12:00 | -17613.1216 | 94.22% | -65274.9487 | 81.48% | -72d 4h | 86.7% | 93.69% | 2013-08-29 17:00 | 2013-09-13 12:00 | 2014-05-16 11:00 | 2013-08-27 12:00 | 2013-09-13 12:00 | 2013-11-25 12:00 | 2013-10-23 12:00 | 2013-12-17 10:00 | 2014-03-19 12:00 | 440528.2917 | 460565.3896 | 445934.8964 | 454051.6708 | 467201.1599 | 477163.2441 | 457284.2689 | 459196.7127 | 0.86697 | 0.81477 | 0.9422 | 0.93686 | -72.5 | 0.81477 | 1 | 0.86697 | 1
T26 | 2012-11-05 08:00 | 2012-12-03 08:00 | 305893.0986 | 300678.1836 | 363946.3495 | 2012-09-19 16:00 | -5214.915 | 98.3% | -63268.1658 | 82.62% | -52d 1h | 90.77% | 98.26% | 2013-07-29 09:00 | 2013-07-31 14:00 | 2014-03-05 15:00 | 2013-07-26 14:00 | 2013-07-31 14:00 | 2013-09-19 16:00 | 2013-09-25 09:00 | 2013-10-24 14:00 | 2014-01-01 16:00 | 438521.5089 | 454213.4806 | 439814.9287 | 446100.8024 | 455779.0595 | 463387.5955 | 450912.5429 | 452465.2483 | 0.90774 | 0.82616 | 0.98295 | 0.98259 | -52.125 | 0.82616 | 1 | 0.90774 | 1
T27 | 2012-12-03 08:00 | 2013-01-07 08:00 | 313619.5666 | 312321.551 | 375668.9982 | 2013-01-02 11:00 | -1298.0157 | 99.59% | -63347.4472 | 83.14% | -2d 5h | 99.56% | 99.58% | 2013-07-17 12:00 | 2013-07-17 17:00 | 2014-02-10 14:00 | 2013-07-17 12:00 | 2013-07-17 17:00 | 2013-08-26 17:00 | 2013-07-17 14:00 | 2013-07-18 10:00 | 2013-08-27 10:00 | 438600.7903 | 451365.098 | 438862.3363 | 438882.0347 | 451679.6927 | 451703.3866 | 448483.8246 | 448489.054 | 0.99555 | 0.83137 | 0.99586 | 0.99584 | -2.625 | 0.83137 | 1 | 0.99555 | 1
T28 | 2013-01-07 08:00 | 2013-02-04 08:00 | 322903.9426 | 322307.5571 | 385731.1502 | 2013-01-31 16:00 | -596.3855 | 99.82% | -63423.5931 | 83.56% | -1d 1h | 99.82% | 99.81% | 2013-07-16 09:00 | 2013-07-16 11:00 | 2014-01-31 10:00 | 2013-07-16 09:00 | 2013-07-16 11:00 | 2013-08-16 10:00 | 2013-07-16 09:00 | 2013-07-16 11:00 | 2013-08-16 10:00 | 438676.9362 | 449095.5935 | 438774.905 | 438774.7625 | 449212.8406 | 449212.6701 | 446722.196 | 446722.1583 | 0.99816 | 0.83558 | 0.99815 | 0.99815 | -1.125 | 0.83558 | 1 | 0.99816 | 1
T29 | 2013-02-04 08:00 | 2013-03-04 08:00 | 332041.4466 | 332041.4466 | 395529.7638 | 2013-03-01 17:00 | -1.356e-05 | 100% | -63488.3172 | 83.95% | 0 | 100% | 100% | 2013-07-12 17:00 | 2013-07-12 17:00 | 2014-01-23 14:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-08-08 09:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-08-08 09:00 | 438741.6603 | 447004.0342 | 438741.6603 | 438741.6603 | 447004.0342 | 447004.0342 | 445108.0992 | 445108.0992 | 1 | 0.83949 | 1 | 1 | 0 | 0.83949 | 1 | 1 | 1
T30 | 2013-03-04 08:00 | 2013-04-01 08:00 | 341178.9506 | 341178.9506 | 404667.2678 | 2013-03-29 17:00 | 9.1531e-05 | 100% | -63488.3171 | 84.31% | 0 | 100% | 100% | 2013-07-12 17:00 | 2013-07-12 17:00 | 2014-01-17 16:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-08-01 17:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-08-01 17:00 | 438741.6602 | 445082.3967 | 438741.6602 | 438741.6602 | 445082.3967 | 445082.3967 | 443632.2367 | 443632.2367 | 1 | 0.84311 | 1 | 1 | 0 | 0.84311 | 1 | 1 | 1
T31 | 2013-04-01 08:00 | 2013-05-06 08:00 | 352600.8343 | 352600.8343 | 416089.1515 | 2013-05-03 17:00 | -4.0755e-05 | 100% | -63488.3173 | 84.74% | 0 | 100% | 100% | 2013-07-12 17:00 | 2013-07-12 17:00 | 2014-01-13 12:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-25 17:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-25 17:00 | 438741.6603 | 442820.4075 | 438741.6603 | 438741.6603 | 442820.4075 | 442820.4075 | 441891.2373 | 441891.2373 | 1 | 0.84742 | 1 | 1 | 0 | 0.84742 | 1 | 1 | 1
T32 | 2013-05-06 08:00 | 2013-06-03 08:00 | 363738.3383 | 363738.3385 | 427226.6555 | 2013-05-31 17:00 | 0.00018306 | 100% | -63488.317 | 85.14% | 0 | 100% | 100% | 2013-07-12 17:00 | 2013-07-12 17:00 | 2014-01-07 12:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-22 10:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-22 10:00 | 438741.6601 | 440751.5342 | 438741.6601 | 438741.6601 | 440751.5342 | 440751.5342 | 440295.3229 | 440295.3229 | 1 | 0.85139 | 1 | 1 | 0 | 0.85139 | 1 | 1 | 1
T33 | 2013-06-03 08:00 | 2013-07-01 08:00 | 371875.8423 | 371875.8425 | 435364.1595 | 2013-06-28 17:00 | 0.00022009 | 100% | -63488.317 | 85.42% | 0 | 100% | 100% | 2013-07-12 17:00 | 2013-07-12 17:00 | 2014-01-02 15:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-16 15:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-16 15:00 | 438741.6601 | 439318.2821 | 438741.6601 | 438741.6601 | 439318.2821 | 439318.2821 | 439187.7268 | 439187.7268 | 1 | 0.85417 | 1 | 1 | 0 | 0.85417 | 1 | 1 | 1
T34 | 2013-07-01 08:00 | 2013-08-05 08:00 | 375253.3431 | 375253.3431 | 438741.6603 | 2013-07-12 17:00 | 0 | 100% | -63488.3172 | 85.53% | -15d | 97.97% | 100% | 2013-07-12 17:00 | 2013-07-12 17:00 | 2014-01-01 14:00 | 2013-08-02 17:00 | 2013-08-02 17:00 | 2013-08-02 17:00 | 2013-08-02 17:00 | 2013-08-02 17:00 | 2013-08-02 17:00 | 438741.6603 | 438741.6603 | 438741.6603 | 438741.6603 | 438741.6603 | 438741.6603 | 438741.6603 | 438741.6603 | 0.97973 | 0.85529 | 1 | 1 | -15 | 0.85529 | 1 | 0.97973 | 1