## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Biofuel Refinery | 1 |  |  | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 | 501.4167
1 | Tanks - Preparation | 1.1 |  | FS26 | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 346.4167
26 | Tanks - On Site | 1.2 | 13FS;1FS | FS16;FS18;FS20;FS22;FS5 | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 0.41667
2 | Skids - Preparation | 1.3 |  | FS11;FS15;FS3;FS8;FS21;FS17;FS19 | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 60.4167
3 | Skids - Lead Time 1 | 1.4 | 2FS | FS24;FS5 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 270.4167
24 | Skids - Lead Time 2 | 1.5 | 3FS |  | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 25.4167
5 | Skids - On Site 1 | 1.6 | 3FS;26FS | FS25;FS7 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 88.4167
25 | Skids - On Site 2 | 1.7 | 5FS |  | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 | 27.4167
7 | Skids - Commissioning | 1.8 | 16FS;18FS;5FS |  | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 | 60.4167
8 | Utilities - Preparation | 1.9 | 2FS | FS9;FS23 | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 60.4167
9 | Utilities - Lead Time | 1.10 | 8FS | FS18 | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 193.4167
10 | Tie-inns | 1.11 |  |  | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 4.4167
11 | Civil - Preparation | 1.12 | 2FS | FS13;FS14;FS23 | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 116.4167
13 | Civil - On Site | 1.13 | 11FS | FS16;FS18;FS26 | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 109.4167
14 | Labo Container | 1.14 | 11FS | FS18 | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 137.4167
15 | Piping - Preparation | 1.15 | 2FS | FS16 | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 242.4167
16 | Piping - On Site | 1.16 | 15FS;23FS;13FS;26FS | FS7 | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 74.4167
17 | Electrical - Preparation | 1.17 | 2FS | FS18 | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 186.4167
18 | Electrical - On Site | 1.18 | 17FS;13FS;14FS;26FS;9FS | FS7 | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 | 39.4167
19 | Automation - Preparation | 1.19 | 2FS | FS20 | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 305.4167
20 | Automation - On Site | 1.20 | 19FS;26FS | FS22 | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 | 25.4167
21 | Analytics - Preparation | 1.21 | 2FS | FS22 | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 361.4167
22 | Analytics - On Site | 1.22 | 21FS;20FS;26FS |  | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 | 32.4167
23 | Purchases | 1.23 | 11FS;8FS | FS16 | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 151.4167

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Biofuel Refinery | 3240h |  |  |  |  | 99 | 100 | 101
1 | Tanks - Preparation | 2241h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
26 | Tanks - On Site | 9h | manual - absolute | 7 | 9 | 45 | 77 | 100 | 500
2 | Skids - Preparation | 405h | manual - absolute | 364 | 405 | 446 | 89 | 100 | 110
3 | Skids - Lead Time 1 | 1755h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
24 | Skids - Lead Time 2 | 180h | manual - absolute | 165 | 180 | 195 | 91 | 100 | 108
5 | Skids - On Site 1 | 585h | manual - absolute | 559 | 590 | 825 | 95 | 100 | 141
25 | Skids - On Site 2 | 180h | manual - absolute | 173 | 180 | 228 | 96 | 100 | 126
7 | Skids - Commissioning | 405h | manual - absolute | 348 | 405 | 841 | 85 | 100 | 207
8 | Utilities - Preparation | 405h | manual - absolute | 391 | 405 | 419 | 96 | 100 | 103
9 | Utilities - Lead Time | 1260h | manual - absolute | 1218 | 1260 | 1301 | 96 | 100 | 103
10 | Tie-inns | 45h | manual - absolute | 39 | 45 | 53 | 86 | 100 | 117
11 | Civil - Preparation | 765h | manual - absolute | 739 | 765 | 792 | 96 | 100 | 103
13 | Civil - On Site | 720h | manual - absolute | 676 | 720 | 954 | 93 | 100 | 132
14 | Labo Container | 900h | manual - absolute | 864 | 900 | 936 | 96 | 100 | 104
15 | Piping - Preparation | 1575h | manual - absolute | 1523 | 1575 | 1637 | 96 | 100 | 103
16 | Piping - On Site | 495h | manual - absolute | 475 | 495 | 598 | 95 | 100 | 120
17 | Electrical - Preparation | 1215h | manual - absolute | 1175 | 1215 | 1257 | 96 | 100 | 103
18 | Electrical - On Site | 270h | manual - absolute | 248 | 270 | 363 | 91 | 100 | 134
19 | Automation - Preparation | 1980h | manual - absolute | 1902 | 1980 | 2060 | 96 | 100 | 104
20 | Automation - On Site | 180h | manual - absolute | 172 | 180 | 237 | 95 | 100 | 131
21 | Analytics - Preparation | 2340h | manual - absolute | 2261 | 2340 | 2419 | 96 | 100 | 103
22 | Analytics - On Site | 225h | manual - absolute | 216 | 225 | 300 | 96 | 100 | 133
23 | Purchases | 990h | manual - absolute | 949 | 990 | 1031 | 95 | 100 | 104

## Project Control - TP1
| TP Status Date | 2015-03-25 17:00 |  | TP Name | 3/25/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 18d | [5 empty] | 5808100 |  | 40.44% |  | 5808027.2351 | 5808100
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 18d | 5804050 | 53000 | 235d 5h | 0 | 0 | 5804050 | 53000 | 7.099% | Started | 5803977.235 | 5804050 | 100 | 7.2289 | 7.099 | 100 | 99.1125 | 7.099
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 18d | 4050 | 6075 | 27d | 0 | 0 | 4050 | 6075 | 40% | Started | 4050.0001 | 4050 | 100 | 40 | 40 | 100 | 40 | 40
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 |  | 0 | 0 | 500000 | 195d | 0 | 0 | 0 | 500000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 |  | 0 | 0 | 600000 | 45d | 0 | 0 | 0 | 600000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 |  | 0 | 0 | 94500 | 140d | 0 | 0 | 0 | 94500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 |  | 0 | 0 | 1338250 | 85d | 0 | 0 | 0 | 1338250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 |  | 0 | 0 | 360000 | 80d | 0 | 0 | 0 | 360000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 |  | 0 | 0 | 240000 | 100d | 0 | 0 | 0 | 240000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 |  | 0 | 0 | 800000 | 175d | 0 | 0 | 0 | 800000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 |  | 0 | 0 | 400000 | 135d | 0 | 0 | 0 | 400000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 |  | 0 | 0 | 129500 | 220d | 0 | 0 | 0 | 129500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 |  | 0 | 0 | 138500 | 260d | 0 | 0 | 0 | 138500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 |  | 0 | 0 | 3200000 | 110d | 0 | 0 | 0 | 3200000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2015-04-20 17:00 |  | TP Name | 4/20/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 36d | [5 empty] | 5816200 |  | 40.49% |  | 5816054.4701 | 5816200
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 36d | 5808100 | 48950 | 217d 5h | 0 | 0 | 5808100 | 48950 | 14.2% | Started | 5807954.47 | 5808100 | 100 | 14.4578 | 14.1981 | 100 | 99.1816 | 14.1981
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 36d | 8100 | 2025 | 9d | 0 | 0 | 8100 | 2025 | 80% | Started | 8100.0001 | 8100 | 100 | 80 | 80 | 100 | 80 | 80
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 |  | 0 | 0 | 500000 | 195d | 0 | 0 | 0 | 500000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 |  | 0 | 0 | 600000 | 45d | 0 | 0 | 0 | 600000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 |  | 0 | 0 | 94500 | 140d | 0 | 0 | 0 | 94500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 |  | 0 | 0 | 1338250 | 85d | 0 | 0 | 0 | 1338250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 |  | 0 | 0 | 360000 | 80d | 0 | 0 | 0 | 360000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 |  | 0 | 0 | 240000 | 100d | 0 | 0 | 0 | 240000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 |  | 0 | 0 | 800000 | 175d | 0 | 0 | 0 | 800000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 |  | 0 | 0 | 400000 | 135d | 0 | 0 | 0 | 400000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 |  | 0 | 0 | 129500 | 220d | 0 | 0 | 0 | 129500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 |  | 0 | 0 | 138500 | 260d | 0 | 0 | 0 | 138500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 |  | 0 | 0 | 3200000 | 110d | 0 | 0 | 0 | 3200000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2015-05-14 17:00 |  | TP Name | 5/14/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 54d | [5 empty] | 7926325 |  | 55.19% |  | 7926106.7046 | 7926325
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 54d | 5812150 | 44900 | 199d 5h | 0 | 0 | 5812150 | 44900 | 21.3% | Started | 5811931.7046 | 5812150 | 100 | 21.6867 | 21.2971 | 100 | 99.2508 | 21.2971
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 |  | 0 | 0 | 500000 | 195d | 0 | 0 | 0 | 500000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 |  | 0 | 0 | 600000 | 45d | 0 | 0 | 0 | 600000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 |  | 0 | 0 | 94500 | 140d | 0 | 0 | 0 | 94500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 9d | 1304050 | 34200 | 76d | 0 | 0 | 1304050 | 34200 | 10.59% | Started | 1304050 | 1304050 | 100 | 10.5882 | 10.5882 | 100 | 97.4444 | 10.5882
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 |  | 0 | 0 | 360000 | 80d | 0 | 0 | 0 | 360000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 |  | 0 | 0 | 240000 | 100d | 0 | 0 | 0 | 240000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 9d | 800000 | 0 | 166d | 0 | 0 | 800000 | 0 | 5.143% | Started | 800000 | 800000 | 100 | 5.1429 | 5.1429 | 100 | 100 | 5.1429
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 |  | 0 | 0 | 400000 | 135d | 0 | 0 | 0 | 400000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 |  | 0 | 0 | 129500 | 220d | 0 | 0 | 0 | 129500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 |  | 0 | 0 | 138500 | 260d | 0 | 0 | 0 | 138500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 |  | 0 | 0 | 3200000 | 110d | 0 | 0 | 0 | 3200000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2015-06-09 17:00 |  | TP Name | 6/9/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 72d | [5 empty] | 8520050 |  | 59.32% |  | 8519758.9404 | 8520050
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 72d | 5816200 | 40850 | 181d 5h | 0 | 0 | 5816200 | 40850 | 28.4% | Started | 5815908.94 | 5816200 | 100 | 28.9157 | 28.3961 | 100 | 99.3199 | 28.3961
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 17d | 500000 | 0 | 296d 7h | 0 | 0 | 500000 | 0 | 5.418% | Started | 500000 | 500000 | 100 | 8.7179 | 5.4178 | 100 | 100 | 5.4178
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 |  | 0 | 0 | 600000 | 45d | 0 | 0 | 0 | 600000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 |  | 0 | 0 | 94500 | 140d | 0 | 0 | 0 | 94500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 27d | 1312150 | 26100 | 58d | 0 | 0 | 1312150 | 26100 | 31.76% | Started | 1312150.0004 | 1312150 | 100 | 31.7647 | 31.7647 | 100 | 98.0497 | 31.7647
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 |  | 0 | 0 | 360000 | 80d | 0 | 0 | 0 | 360000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 |  | 0 | 0 | 240000 | 100d | 0 | 0 | 0 | 240000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 27d | 800000 | 0 | 148d | 0 | 0 | 800000 | 0 | 15.43% | Started | 800000 | 800000 | 100 | 15.4286 | 15.4286 | 100 | 100 | 15.4286
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 |  | 0 | 0 | 400000 | 135d | 0 | 0 | 0 | 400000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 |  | 0 | 0 | 129500 | 220d | 0 | 0 | 0 | 129500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 7d | 81575 | 56925 | 253d | 0 | 0 | 81575 | 56925 | 2.692% | Started | 81575 | 81575 | 100 | 2.6923 | 2.6923 | 100 | 58.8989 | 2.6923
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 |  | 0 | 0 | 3200000 | 110d | 0 | 0 | 0 | 3200000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2015-07-03 17:00 |  | TP Name | 7/3/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 90d | [5 empty] | 9617375 |  | 66.96% |  | 9617011.1757 | 9617375
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 90d | 5820250 | 36800 | 163d 5h | 0 | 0 | 5820250 | 36800 | 35.5% | Started | 5819886.1745 | 5820250 | 100 | 36.1446 | 35.4952 | 100 | 99.3891 | 35.4952
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 35d | 500000 | 0 | 278d 7h | 0 | 0 | 500000 | 0 | 11.15% | Started | 500000 | 500000 | 100 | 17.9487 | 11.1544 | 100 | 100 | 11.1544
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 5d | 600000 | 0 | 77d 1h | 0 | 0 | 600000 | 0 | 6.089% | Started | 600000 | 600000 | 100 | 11.1111 | 6.0893 | 100 | 100 | 6.0893
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 |  | 0 | 0 | 94500 | 140d | 0 | 0 | 0 | 94500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 45d | 1320250 | 18000 | 40d | 0 | 0 | 1320250 | 18000 | 52.94% | Started | 1320250.0011 | 1320250 | 100 | 52.9412 | 52.9412 | 100 | 98.655 | 52.9412
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 |  | 0 | 0 | 360000 | 80d | 0 | 0 | 0 | 360000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 |  | 0 | 0 | 240000 | 100d | 0 | 0 | 0 | 240000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 45d | 800000 | 0 | 130d | 0 | 0 | 800000 | 0 | 25.71% | Started | 800000 | 800000 | 100 | 25.7143 | 25.7143 | 100 | 100 | 25.7143
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 5d | 400000 | 0 | 130d | 0 | 0 | 400000 | 0 | 3.704% | Started | 400000 | 400000 | 100 | 3.7037 | 3.7037 | 100 | 100 | 3.7037
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 5d | 81125 | 48375 | 215d | 0 | 0 | 81125 | 48375 | 2.273% | Started | 81125 | 81125 | 100 | 2.2727 | 2.2727 | 100 | 62.6448 | 2.2727
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 25d | 85625 | 52875 | 235d | 0 | 0 | 85625 | 52875 | 9.615% | Started | 85625.0001 | 85625 | 100 | 9.6154 | 9.6154 | 100 | 61.8231 | 9.6154
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 |  | 0 | 0 | 3200000 | 110d | 0 | 0 | 0 | 3200000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2015-07-29 17:00 |  | TP Name | 7/29/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 108d | [5 empty] | 9637625 |  | 67.1% |  | 9637188.4099 | 9637625
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 108d | 5824300 | 32750 | 145d 5h | 0 | 0 | 5824300 | 32750 | 42.59% | Started | 5823863.4091 | 5824300 | 100 | 43.3735 | 42.5942 | 100 | 99.4583 | 42.5942
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 53d | 500000 | 0 | 260d 7h | 0 | 0 | 500000 | 0 | 16.89% | Started | 500000 | 500000 | 100 | 27.1795 | 16.8909 | 100 | 100 | 16.8909
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 23d | 600000 | 0 | 59d 1h | 0 | 0 | 600000 | 0 | 28.01% | Started | 600000 | 600000 | 100 | 51.1111 | 28.0108 | 100 | 100 | 28.0108
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 |  | 0 | 0 | 94500 | 140d | 0 | 0 | 0 | 94500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 63d | 1328350 | 9900 | 22d | 0 | 0 | 1328350 | 9900 | 74.12% | Started | 1328350.0006 | 1328350 | 100 | 74.1176 | 74.1176 | 100 | 99.2602 | 74.1176
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 |  | 0 | 0 | 360000 | 80d | 0 | 0 | 0 | 360000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 |  | 0 | 0 | 240000 | 100d | 0 | 0 | 0 | 240000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 63d | 800000 | 0 | 112d | 0 | 0 | 800000 | 0 | 36% | Started | 800000 | 800000 | 100 | 36 | 36 | 100 | 100 | 36
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 23d | 400000 | 0 | 112d | 0 | 0 | 400000 | 0 | 17.04% | Started | 400000 | 400000 | 100 | 17.037 | 17.037 | 100 | 100 | 17.037
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 23d | 85175 | 44325 | 197d | 0 | 0 | 85175 | 44325 | 10.45% | Started | 85174.9999 | 85175 | 100 | 10.4545 | 10.4545 | 100 | 65.7722 | 10.4545
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 43d | 89675 | 48825 | 217d | 0 | 0 | 89675 | 48825 | 16.54% | Started | 89675.0003 | 89675 | 100 | 16.5385 | 16.5385 | 100 | 64.7473 | 16.5385
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 |  | 0 | 0 | 3200000 | 110d | 0 | 0 | 0 | 3200000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2015-08-24 17:00 |  | TP Name | 8/24/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 126d | [5 empty] | 9657875 |  | 67.24% |  | 9657365.6439 | 9657875
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 126d | 5828350 | 28700 | 127d 5h | 0 | 0 | 5828350 | 28700 | 49.69% | Started | 5827840.6437 | 5828350 | 100 | 50.6024 | 49.6933 | 100 | 99.5274 | 49.6933
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 71d | 500000 | 0 | 242d 7h | 0 | 0 | 500000 | 0 | 22.63% | Started | 500000 | 500000 | 100 | 36.4103 | 22.6275 | 100 | 100 | 22.6275
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 41d | 600000 | 0 | 41d 1h | 0 | 0 | 600000 | 0 | 49.93% | Started | 600000 | 600000 | 100 | 91.1111 | 49.9323 | 100 | 100 | 49.9323
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 |  | 0 | 0 | 94500 | 140d | 0 | 0 | 0 | 94500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 81d | 1336450 | 1800 | 4d | 0 | 0 | 1336450 | 1800 | 95.29% | Started | 1336450.0001 | 1336450 | 100 | 95.2941 | 95.2941 | 100 | 99.8655 | 95.2941
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 |  | 0 | 0 | 360000 | 80d | 0 | 0 | 0 | 360000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 |  | 0 | 0 | 240000 | 100d | 0 | 0 | 0 | 240000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 81d | 800000 | 0 | 94d | 0 | 0 | 800000 | 0 | 46.29% | Started | 800000 | 800000 | 100 | 46.2857 | 46.2857 | 100 | 100 | 46.2857
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 41d | 400000 | 0 | 94d | 0 | 0 | 400000 | 0 | 30.37% | Started | 400000 | 400000 | 100 | 30.3704 | 30.3704 | 100 | 100 | 30.3704
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 41d | 89225 | 40275 | 179d | 0 | 0 | 89225 | 40275 | 18.64% | Started | 89225.0001 | 89225 | 100 | 18.6364 | 18.6364 | 100 | 68.8996 | 18.6364
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 61d | 93725 | 44775 | 199d | 0 | 0 | 93725 | 44775 | 23.46% | Started | 93725.0001 | 93725 | 100 | 23.4615 | 23.4615 | 100 | 67.6715 | 23.4615
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 |  | 0 | 0 | 3200000 | 110d | 0 | 0 | 0 | 3200000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2015-09-17 17:00 |  | TP Name | 9/17/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 144d | [5 empty] | 9681275 |  | 67.4% |  | 9679760.0479 | 9681275
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 144d | 5832400 | 24650 | 109d 5h | 0 | 0 | 5832400 | 24650 | 56.79% | Started | 5831817.8799 | 5832400 | 100 | 57.8313 | 56.7923 | 100 | 99.5966 | 56.7923
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 89d | 500000 | 0 | 224d 7h | 0 | 0 | 500000 | 0 | 28.36% | Started | 500000 | 500000 | 100 | 45.641 | 28.364 | 100 | 100 | 28.364
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 59d | 600000 | 0 | 23d 1h | 0 | 0 | 600000 | 0 | 71.85% | Started | 600000 | 600000 | 100 | 131.1111 | 71.8539 | 100 | 100 | 71.8539
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 14d | 9450 | 95400 | 141d 3h | 0 | 0 | 9450 | 95400 | 9.013% | Started | 8517.1675 | 9450 | 100 | 10 | 9.0129 | 100 | 10 | 9.0129
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 |  | 0 | 0 | 360000 | 80d | 0 | 0 | 0 | 360000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 |  | 0 | 0 | 240000 | 100d | 0 | 0 | 0 | 240000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 99d | 800000 | 0 | 76d | 0 | 0 | 800000 | 0 | 56.57% | Started | 800000 | 800000 | 100 | 56.5714 | 56.5714 | 100 | 100 | 56.5714
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 59d | 400000 | 0 | 76d | 0 | 0 | 400000 | 0 | 43.7% | Started | 400000 | 400000 | 100 | 43.7037 | 43.7037 | 100 | 100 | 43.7037
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 59d | 93275 | 36225 | 161d | 0 | 0 | 93275 | 36225 | 26.82% | Started | 93275.0006 | 93275 | 100 | 26.8182 | 26.8182 | 100 | 72.027 | 26.8182
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 79d | 97775 | 40725 | 181d | 0 | 0 | 97775 | 40725 | 30.38% | Started | 97774.9998 | 97775 | 100 | 30.3846 | 30.3846 | 100 | 70.5957 | 30.3846
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 |  | 0 | 0 | 3200000 | 110d | 0 | 0 | 0 | 3200000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2015-10-13 17:00 |  | TP Name | 10/13/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 162d | [5 empty] | 13066375 |  | 90.96% |  | 13063587.9233 | 13066375
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 162d | 5836450 | 20600 | 91d 5h | 0 | 0 | 5836450 | 20600 | 63.89% | Started | 5835795.1128 | 5836450 | 100 | 65.0602 | 63.8913 | 100 | 99.6657 | 63.8913
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 107d | 500000 | 0 | 206d 7h | 0 | 0 | 500000 | 0 | 34.1% | Started | 500000 | 500000 | 100 | 54.8718 | 34.1006 | 100 | 100 | 34.1006
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 77d | 600000 | 0 | 5d 1h | 0 | 0 | 600000 | 0 | 93.78% | Started | 600000 | 600000 | 100 | 171.1111 | 93.7754 | 100 | 100 | 93.7754
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 32d | 21600 | 83250 | 123d 3h | 0 | 0 | 21600 | 83250 | 20.6% | Started | 19467.8111 | 21600 | 100 | 22.8571 | 20.6009 | 100 | 22.8571 | 20.6009
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 2d | 9000 | 351000 | 78d | 0 | 0 | 9000 | 351000 | 2.5% | Started | 9000.0001 | 9000 | 100 | 2.5 | 2.5 | 100 | 2.5 | 2.5
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 2d | 151800 | 88200 | 98d | 0 | 0 | 151800 | 88200 | 2% | Started | 151800 | 151800 | 100 | 2 | 2 | 100 | 63.25 | 2
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 117d | 800000 | 0 | 58d | 0 | 0 | 800000 | 0 | 66.86% | Started | 800000 | 800000 | 100 | 66.8571 | 66.8571 | 100 | 100 | 66.8571
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 77d | 400000 | 0 | 58d | 0 | 0 | 400000 | 0 | 57.04% | Started | 400000 | 400000 | 100 | 57.037 | 57.037 | 100 | 100 | 57.037
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 77d | 97325 | 32175 | 143d | 0 | 0 | 97325 | 32175 | 35% | Started | 97324.9997 | 97325 | 100 | 35 | 35 | 100 | 75.1544 | 35
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 97d | 101825 | 36675 | 163d | 0 | 0 | 101825 | 36675 | 37.31% | Started | 101824.9996 | 101825 | 100 | 37.3077 | 37.3077 | 100 | 73.5199 | 37.3077
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 12d | 3200000 | 0 | 152d | 0 | 0 | 3200000 | 0 | 7.317% | Started | 3200000 | 3200000 | 100 | 10.9091 | 7.3171 | 100 | 100 | 7.3171

## TP10
| TP Status Date | 2015-11-06 17:00 |  | TP Name | 11/6/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 180d | [5 empty] | 13187875 |  | 91.79% |  | 13183815.8043 | 13187875
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 180d | 5840500 | 16550 | 73d 5h | 0 | 0 | 5840500 | 16550 | 70.99% | Started | 5839772.3491 | 5840500 | 100 | 72.2892 | 70.9904 | 100 | 99.7349 | 70.9904
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 125d | 500000 | 0 | 188d 7h | 0 | 0 | 500000 | 0 | 39.84% | Started | 500000 | 500000 | 100 | 64.1026 | 39.8371 | 100 | 100 | 39.8371
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 50d | 33750 | 71100 | 105d 3h | 0 | 0 | 33750 | 71100 | 32.19% | Started | 30418.4554 | 33750 | 100 | 35.7143 | 32.1888 | 100 | 35.7143 | 32.1888
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 |  | 0 | 0 | 87250 | 5d | 0 | 0 | 0 | 87250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 20d | 90000 | 270000 | 60d | 0 | 0 | 90000 | 270000 | 25% | Started | 90000 | 90000 | 100 | 25 | 25 | 100 | 25 | 25
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 20d | 168000 | 72000 | 80d | 0 | 0 | 168000 | 72000 | 20% | Started | 168000.0003 | 168000 | 100 | 20 | 20 | 100 | 70 | 20
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 135d | 800000 | 0 | 40d | 0 | 0 | 800000 | 0 | 77.14% | Started | 800000 | 800000 | 100 | 77.1429 | 77.1429 | 100 | 100 | 77.1429
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 95d | 400000 | 0 | 40d | 0 | 0 | 400000 | 0 | 70.37% | Started | 400000 | 400000 | 100 | 70.3704 | 70.3704 | 100 | 100 | 70.3704
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 95d | 101375 | 28125 | 125d | 0 | 0 | 101375 | 28125 | 43.18% | Started | 101375.0003 | 101375 | 100 | 43.1818 | 43.1818 | 100 | 78.2819 | 43.1818
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 115d | 105875 | 32625 | 145d | 0 | 0 | 105875 | 32625 | 44.23% | Started | 105874.9993 | 105875 | 100 | 44.2308 | 44.2308 | 100 | 76.444 | 44.2308
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 30d | 3200000 | 0 | 134d | 0 | 0 | 3200000 | 0 | 18.29% | Started | 3200000 | 3200000 | 100 | 27.2727 | 18.2927 | 100 | 100 | 18.2927

## TP11
| TP Status Date | 2015-12-02 17:00 |  | TP Name | 12/2/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 198d | [5 empty] | 13395725 |  | 93.23% |  | 13390007.9666 | 13395725
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 198d | 5844550 | 12500 | 55d 5h | 0 | 0 | 5844550 | 12500 | 78.09% | Started | 5843749.5853 | 5844550 | 100 | 79.5181 | 78.0894 | 100 | 99.804 | 78.0894
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 143d | 500000 | 0 | 170d 7h | 0 | 0 | 500000 | 0 | 45.57% | Started | 500000 | 500000 | 100 | 73.3333 | 45.5737 | 100 | 100 | 45.5737
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 68d | 45900 | 58950 | 87d 3h | 0 | 0 | 45900 | 58950 | 43.78% | Started | 41369.0997 | 45900 | 100 | 48.5714 | 43.7768 | 100 | 48.5714 | 43.7768
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 3d | 86350 | 1800 | 4d | 0 | 0 | 86350 | 1800 | 42.86% | Started | 85964.2857 | 86350 | 100 | 60 | 42.8571 | 100 | 98.9685 | 42.8571
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 38d | 171000 | 189000 | 42d | 0 | 0 | 171000 | 189000 | 47.5% | Started | 170999.9979 | 171000 | 100 | 47.5 | 47.5 | 100 | 47.5 | 47.5
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 38d | 184200 | 55800 | 62d | 0 | 0 | 184200 | 55800 | 38% | Started | 184199.9996 | 184200 | 100 | 38 | 38 | 100 | 76.75 | 38
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 153d | 800000 | 0 | 22d | 0 | 0 | 800000 | 0 | 87.43% | Started | 800000 | 800000 | 100 | 87.4286 | 87.4286 | 100 | 100 | 87.4286
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 113d | 400000 | 0 | 22d | 0 | 0 | 400000 | 0 | 83.7% | Started | 400000 | 400000 | 100 | 83.7037 | 83.7037 | 100 | 100 | 83.7037
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 113d | 105425 | 24075 | 107d | 0 | 0 | 105425 | 24075 | 51.36% | Started | 105424.9994 | 105425 | 100 | 51.3636 | 51.3636 | 100 | 81.4093 | 51.3636
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 133d | 109925 | 28575 | 127d | 0 | 0 | 109925 | 28575 | 51.15% | Started | 109924.9991 | 109925 | 100 | 51.1538 | 51.1538 | 100 | 79.3682 | 51.1538
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 48d | 3200000 | 0 | 116d | 0 | 0 | 3200000 | 0 | 29.27% | Started | 3200000 | 3200000 | 100 | 43.6364 | 29.2683 | 100 | 100 | 29.2683

## TP12
| TP Status Date | 2015-12-28 17:00 |  | TP Name | 12/28/2015 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 216d | [5 empty] | 13519025 |  | 94.07% |  | 13511521.5573 | 13518125
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 216d | 5848600 | 8450 | 37d 5h | 0 | 0 | 5848600 | 8450 | 85.19% | Started | 5847726.8182 | 5848600 | 100 | 86.747 | 85.1884 | 100 | 99.8732 | 85.1884
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 161d | 500000 | 0 | 152d 7h | 0 | 0 | 500000 | 0 | 51.31% | Started | 500000 | 500000 | 100 | 82.5641 | 51.3102 | 100 | 100 | 51.3102
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 86d | 58050 | 46800 | 69d 3h | 0 | 0 | 58050 | 46800 | 55.36% | Started | 52319.7412 | 58050 | 100 | 61.4286 | 55.3648 | 100 | 61.4286 | 55.3648
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 56d | 252000 | 108000 | 24d | 0 | 0 | 252000 | 108000 | 70% | Started | 251999.9957 | 252000 | 100 | 70 | 70 | 100 | 70 | 70
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 56d | 200400 | 39600 | 44d | 0 | 0 | 200400 | 39600 | 56% | Started | 200400.0002 | 200400 | 100 | 56 | 56 | 100 | 83.5 | 56
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 171d | 800000 | 0 | 4d | 0 | 0 | 800000 | 0 | 97.71% | Started | 800000 | 800000 | 100 | 97.7143 | 97.7143 | 100 | 100 | 97.7143
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 131d | 400000 | 0 | 4d | 0 | 0 | 400000 | 0 | 97.04% | Started | 400000 | 400000 | 100 | 97.037 | 97.037 | 100 | 100 | 97.037
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 131d | 109475 | 20025 | 89d | 0 | 0 | 109475 | 20025 | 59.55% | Started | 109475.0014 | 109475 | 100 | 59.5455 | 59.5455 | 100 | 84.5367 | 59.5455
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 151d | 113975 | 24525 | 109d | 0 | 0 | 113975 | 24525 | 58.08% | Started | 113975.0006 | 113975 | 100 | 58.0769 | 58.0769 | 100 | 82.2924 | 58.0769
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 66d | 3200000 | 0 | 98d | 0 | 0 | 3200000 | 0 | 40.24% | Started | 3200000 | 3200000 | 100 | 60 | 40.2439 | 100 | 100 | 40.2439

## TP13
| TP Status Date | 2016-01-21 17:00 |  | TP Name | 1/21/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 234d | [5 empty] | 13640525 |  | 94.91% |  | 13631749.4441 | 13639625
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 234d | 5852650 | 4400 | 19d 5h | 0 | 0 | 5852650 | 4400 | 92.29% | Started | 5851704.0545 | 5852650 | 100 | 93.9759 | 92.2875 | 100 | 99.9424 | 92.2875
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 |  | 0 | 0 | 1350 | 1d | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 179d | 500000 | 0 | 134d 7h | 0 | 0 | 500000 | 0 | 57.05% | Started | 500000 | 500000 | 100 | 91.7949 | 57.0467 | 100 | 100 | 57.0467
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 |  | 0 | 0 | 50000 | 20d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 |  | 0 | 0 | 237000 | 65d | 0 | 0 | 0 | 237000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 104d | 70200 | 34650 | 51d 3h | 0 | 0 | 70200 | 34650 | 66.95% | Started | 63270.3854 | 70200 | 100 | 74.2857 | 66.9528 | 100 | 74.2857 | 66.9528
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 74d | 333000 | 27000 | 6d | 0 | 0 | 333000 | 27000 | 92.5% | Started | 333000.0043 | 333000 | 100 | 92.5 | 92.5 | 100 | 92.5 | 92.5
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 74d | 216600 | 23400 | 26d | 0 | 0 | 216600 | 23400 | 74% | Started | 216600.0009 | 216600 | 100 | 74 | 74 | 100 | 90.25 | 74
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 149d | 113525 | 15975 | 71d | 0 | 0 | 113525 | 15975 | 67.73% | Started | 113525.0005 | 113525 | 100 | 67.7273 | 67.7273 | 100 | 87.6641 | 67.7273
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 169d | 118025 | 20475 | 91d | 0 | 0 | 118025 | 20475 | 65% | Started | 118024.9986 | 118025 | 100 | 65 | 65 | 100 | 85.2166 | 65
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 84d | 3200000 | 0 | 80d | 0 | 0 | 3200000 | 0 | 51.22% | Started | 3200000 | 3200000 | 100 | 76.3636 | 51.2195 | 100 | 100 | 51.2195

## TP14
| TP Status Date | 2016-02-16 17:00 |  | TP Name | 2/16/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 252d | [5 empty] | 13883725 |  | 96.58% |  | 13872098.371 | 13881400
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 252d | 5856700 | 350 | 1d 5h | 0 | 0 | 5856700 | 350 | 99.39% | Started | 5855681.2874 | 5856025 | 100 | 101.2048 | 99.3865 | 100 | 100.0115 | 99.3865
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 1350 | 1350 | 100 | 155.5556 | 100 | 100 | 155.5556 | 100
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 197d | 500000 | 0 | 116d 7h | 0 | 0 | 500000 | 0 | 62.78% | Started | 500000 | 500000 | 100 | 101.0256 | 62.7833 | 100 | 100 | 62.7833
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 2d | 50000 | 0 | 18d | 0 | 0 | 50000 | 0 | 10% | Started | 50000 | 50000 | 100 | 10 | 10 | 100 | 100 | 10
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 2d | 123600 | 148400 | 82d 4h | 0 | 0 | 123600 | 148400 | 2.368% | Started | 122771.0527 | 123600 | 100 | 3.0769 | 2.3684 | 100 | 52.1519 | 2.3684
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 122d | 82350 | 22500 | 33d 3h | 0 | 0 | 82350 | 22500 | 78.54% | Started | 74221.0297 | 82350 | 100 | 87.1429 | 78.5408 | 100 | 87.1429 | 78.5408
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 100% | Finished | 360000 | 360000 | 100 | 100 | 100 | 100 | 100 | 100
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 92d | 232800 | 7200 | 8d | 0 | 0 | 232800 | 7200 | 92% | Started | 232800.0015 | 232800 | 100 | 92 | 92 | 100 | 97 | 92
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 |  | 0 | 0 | 99000 | 55d | 0 | 0 | 0 | 99000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 167d | 117575 | 11925 | 53d | 0 | 0 | 117575 | 11925 | 75.91% | Started | 117574.9996 | 117575 | 100 | 75.9091 | 75.9091 | 100 | 90.7915 | 75.9091
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 187d | 122075 | 16425 | 73d | 0 | 0 | 122075 | 16425 | 71.92% | Started | 122075.0001 | 122075 | 100 | 71.9231 | 71.9231 | 100 | 88.1408 | 71.9231
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 102d | 3200000 | 0 | 62d | 0 | 0 | 3200000 | 0 | 62.2% | Started | 3200000 | 3200000 | 100 | 92.7273 | 62.1951 | 100 | 100 | 62.1951

## TP15
| TP Status Date | 2016-03-11 17:00 |  | TP Name | 3/11/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 270d | [5 empty] | 13961925 |  | 97.06% |  | 13941068.6003 | 13959250
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 253d 5h | 5857050 | 0 | 0 | 0 | 0 | 5857050 | 0 | 100% | Finished | 5856025 | 5856025 | 100 | 101.8295 | 100 | 100 | 100.0175 | 100
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 1350 | 1350 | 100 | 155.5556 | 100 | 100 | 155.5556 | 100
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 215d | 500000 | 0 | 98d 7h | 0 | 0 | 500000 | 0 | 68.52% | Started | 500000 | 500000 | 100 | 110.2564 | 68.5198 | 100 | 100 | 68.5198
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 20d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 20d | 156000 | 116000 | 64d 4h | 0 | 0 | 156000 | 116000 | 23.68% | Started | 147710.527 | 156000 | 100 | 30.7692 | 23.6842 | 100 | 65.8228 | 23.6842
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 140d | 94500 | 10350 | 15d 3h | 0 | 0 | 94500 | 10350 | 90.13% | Started | 85171.674 | 94500 | 100 | 100 | 90.1288 | 100 | 100 | 90.1288
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 100% | Finished | 360000 | 360000 | 100 | 100 | 100 | 100 | 100 | 100
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 100d | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 240000 | 240000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 2016-02-29 07:00 | 10d | 18000 | 84200 | 46d 7h | 0 | 0 | 18000 | 84200 | 17.61% | Started | 17436.3991 | 18000 | 100 | 18.1818 | 17.6125 | 100 | 18.1818 | 17.6125
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 |  | 0 | 0 | 13500 | 30d | 0 | 0 | 0 | 13500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 185d | 121625 | 7875 | 35d | 0 | 0 | 121625 | 7875 | 84.09% | Started | 121624.9987 | 121625 | 100 | 84.0909 | 84.0909 | 100 | 93.9189 | 84.0909
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 205d | 126125 | 12375 | 55d | 0 | 0 | 126125 | 12375 | 78.85% | Started | 126125.0016 | 126125 | 100 | 78.8462 | 78.8462 | 100 | 91.065 | 78.8462
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 120d | 3200000 | 0 | 44d | 0 | 0 | 3200000 | 0 | 73.17% | Started | 3200000 | 3200000 | 100 | 109.0909 | 73.1707 | 100 | 100 | 73.1707

## TP16
| TP Status Date | 2016-04-06 17:00 |  | TP Name | 4/6/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 288d | [5 empty] | 14046525 |  | 97.58% |  | 14015535.2236 | 14033500
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 253d 5h | 5857050 | 0 | 0 | 0 | 0 | 5857050 | 0 | 100% | Finished | 5856025 | 5856025 | 100 | 101.8295 | 100 | 100 | 100.0175 | 100
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 1350 | 1350 | 100 | 155.5556 | 100 | 100 | 155.5556 | 100
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 233d | 500000 | 0 | 80d 7h | 0 | 0 | 500000 | 0 | 74.26% | Started | 500000 | 500000 | 100 | 119.4872 | 74.2564 | 100 | 100 | 74.2564
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 20d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 38d | 188400 | 83600 | 46d 4h | 0 | 0 | 188400 | 83600 | 45% | Started | 172649.9986 | 188400 | 100 | 58.4615 | 45 | 100 | 79.4937 | 45
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 155d 3h | 104850 | 0 | 0 | 0 | 0 | 104850 | 0 | 100% | Finished | 94500 | 94500 | 100 | 110.9524 | 100 | 100 | 110.9524 | 100
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 100% | Finished | 360000 | 360000 | 100 | 100 | 100 | 100 | 100 | 100
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 100d | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 240000 | 240000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 2016-02-29 07:00 | 28d | 50400 | 51800 | 28d 7h | 0 | 0 | 50400 | 51800 | 49.32% | Started | 48821.9174 | 50400 | 100 | 50.9091 | 49.3151 | 100 | 50.9091 | 49.3151
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 | 2016-04-04 07:00 | 3d | 1350 | 24200 | 53d 7h | 0 | 0 | 1350 | 24200 | 5.284% | Started | 713.3072 | 1350 | 100 | 10 | 5.2838 | 100 | 10 | 5.2838
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 203d | 125675 | 3825 | 17d | 0 | 0 | 125675 | 3825 | 92.27% | Started | 125675.0007 | 125675 | 100 | 92.2727 | 92.2727 | 100 | 97.0463 | 92.2727
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 |  | 0 | 0 | 4500 | 20d | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 223d | 130175 | 8325 | 37d | 0 | 0 | 130175 | 8325 | 85.77% | Started | 130174.9996 | 130175 | 100 | 85.7692 | 85.7692 | 100 | 93.9892 | 85.7692
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 138d | 3200000 | 0 | 26d | 0 | 0 | 3200000 | 0 | 84.15% | Started | 3200000 | 3200000 | 100 | 125.4545 | 84.1463 | 100 | 100 | 84.1463

## TP17
| TP Status Date | 2016-05-02 17:00 |  | TP Name | 5/2/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 306d | [5 empty] | 14127525 |  | 98.06% |  | 14084240.0609 | 14114500
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 253d 5h | 5857050 | 0 | 0 | 0 | 0 | 5857050 | 0 | 100% | Finished | 5856025 | 5856025 | 100 | 101.8295 | 100 | 100 | 100.0175 | 100
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 1350 | 1350 | 100 | 155.5556 | 100 | 100 | 155.5556 | 100
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 251d | 500000 | 0 | 62d 7h | 0 | 0 | 500000 | 0 | 79.99% | Started | 500000 | 500000 | 100 | 128.7179 | 79.9929 | 100 | 100 | 79.9929
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 20d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 56d | 220800 | 51200 | 28d 4h | 0 | 0 | 220800 | 51200 | 66.32% | Started | 197589.472 | 220800 | 100 | 86.1538 | 66.3158 | 100 | 93.1646 | 66.3158
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 |  | 0 | 0 | 76000 | 20d | 0 | 0 | 0 | 76000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 |  | 0 | 0 | 121500 | 45d | 0 | 0 | 0 | 121500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 155d 3h | 104850 | 0 | 0 | 0 | 0 | 104850 | 0 | 100% | Finished | 94500 | 94500 | 100 | 110.9524 | 100 | 100 | 110.9524 | 100
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 100% | Finished | 360000 | 360000 | 100 | 100 | 100 | 100 | 100 | 100
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 100d | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 240000 | 240000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 2016-02-29 07:00 | 46d | 82800 | 19400 | 10d 7h | 0 | 0 | 82800 | 19400 | 81.02% | Started | 80207.4373 | 82800 | 100 | 83.6364 | 81.0176 | 100 | 83.6364 | 81.0176
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 | 2016-04-04 07:00 | 21d | 9450 | 16100 | 35d 7h | 0 | 0 | 9450 | 16100 | 36.99% | Started | 4993.1505 | 9450 | 100 | 70 | 36.9863 | 100 | 70 | 36.9863
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 220d | 129500 | 0 | 0 | 0 | 0 | 129500 | 0 | 100% | Finished | 129500 | 129500 | 100 | 100 | 100 | 100 | 100 | 100
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 | 2016-05-02 07:00 | 1d | 225 | 4275 | 19d | 0 | 0 | 225 | 4275 | 5% | Started | 225 | 225 | 100 | 5 | 5 | 100 | 5 | 5
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 241d | 134225 | 4275 | 19d | 0 | 0 | 134225 | 4275 | 92.69% | Started | 134225.0011 | 134225 | 100 | 92.6923 | 92.6923 | 100 | 96.9134 | 92.6923
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 156d | 3200000 | 0 | 8d | 0 | 0 | 3200000 | 0 | 95.12% | Started | 3200000 | 3200000 | 100 | 141.8182 | 95.1219 | 100 | 100 | 95.1219

## TP18
| TP Status Date | 2016-05-26 17:00 |  | TP Name | 5/26/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 324d | [5 empty] | 14274225 |  | 98.96% |  | 14213010.7523 | 14237750
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 253d 5h | 5857050 | 0 | 0 | 0 | 0 | 5857050 | 0 | 100% | Finished | 5856025 | 5856025 | 100 | 101.8295 | 100 | 100 | 100.0175 | 100
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 1350 | 1350 | 100 | 155.5556 | 100 | 100 | 155.5556 | 100
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 269d | 500000 | 0 | 44d 7h | 0 | 0 | 500000 | 0 | 85.73% | Started | 500000 | 500000 | 100 | 137.9487 | 85.7295 | 100 | 100 | 85.7295
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 20d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 74d | 253200 | 18800 | 10d 4h | 0 | 0 | 253200 | 18800 | 87.63% | Started | 222528.9454 | 237000 | 100 | 113.8462 | 87.6316 | 100 | 106.8354 | 87.6316
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 | 2016-05-17 07:00 | 8d | 54400 | 21600 | 12d | 0 | 0 | 54400 | 21600 | 40% | Started | 54400.0002 | 54400 | 100 | 40 | 40 | 100 | 71.5789 | 40
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 | 2016-05-16 07:00 | 9d | 24300 | 137400 | 50d 8h | 0 | 0 | 24300 | 137400 | 15.03% | Started | 18258.8135 | 24300 | 100 | 20 | 15.0278 | 100 | 20 | 15.0278
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 155d 3h | 104850 | 0 | 0 | 0 | 0 | 104850 | 0 | 100% | Finished | 94500 | 94500 | 100 | 110.9524 | 100 | 100 | 110.9524 | 100
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 100% | Finished | 360000 | 360000 | 100 | 100 | 100 | 100 | 100 | 100
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 100d | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 240000 | 240000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 2016-02-29 07:00 | 56d 7h | 102200 | 0 | 0 | 0 | 0 | 102200 | 0 | 100% | Finished | 99000 | 99000 | 100 | 103.2323 | 100 | 100 | 103.2323 | 100
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 | 2016-04-04 07:00 | 39d | 17550 | 8000 | 17d 7h | 0 | 0 | 17550 | 8000 | 68.69% | Started | 9272.9942 | 13500 | 100 | 130 | 68.6888 | 100 | 130 | 68.6888
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 220d | 129500 | 0 | 0 | 0 | 0 | 129500 | 0 | 100% | Finished | 129500 | 129500 | 100 | 100 | 100 | 100 | 100 | 100
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 | 2016-05-02 07:00 | 19d | 4275 | 225 | 1d | 0 | 0 | 4275 | 225 | 95% | Started | 4274.9999 | 4275 | 100 | 95 | 95 | 100 | 95 | 95
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 259d | 138275 | 225 | 1d | 0 | 0 | 138275 | 225 | 99.62% | Started | 138274.9991 | 138275 | 100 | 99.6154 | 99.6154 | 100 | 99.8375 | 99.6154
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 |  | 0 | 0 | 5625 | 25d | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 164d | 3200000 | 0 | 0 | 0 | 0 | 3200000 | 0 | 100% | Finished | 3200000 | 3200000 | 100 | 149.0909 | 100 | 100 | 100 | 100

## TP19
| TP Status Date | 2016-06-21 17:00 |  | TP Name | 6/21/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 342d | [5 empty] | 14375500 |  | 99.52% |  | 14294101.4368 | 14312225
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 253d 5h | 5857050 | 0 | 0 | 0 | 0 | 5857050 | 0 | 100% | Finished | 5856025 | 5856025 | 100 | 101.8295 | 100 | 100 | 100.0175 | 100
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 1350 | 1350 | 100 | 155.5556 | 100 | 100 | 155.5556 | 100
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 287d | 500000 | 0 | 26d 7h | 0 | 0 | 500000 | 0 | 91.47% | Started | 500000 | 500000 | 100 | 147.1795 | 91.466 | 100 | 100 | 91.466
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 20d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 84d 4h | 272000 | 0 | 0 | 0 | 0 | 272000 | 0 | 100% | Finished | 237000 | 237000 | 100 | 129.9145 | 100 | 100 | 114.7679 | 100
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 | 2016-05-17 07:00 | 20d | 76000 | 0 | 0 | 0 | 0 | 76000 | 0 | 100% | Finished | 76000 | 76000 | 100 | 100 | 100 | 100 | 100 | 100
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 | 2016-05-16 07:00 | 27d | 72900 | 88800 | 32d 8h | 0 | 0 | 72900 | 88800 | 45.08% | Started | 54776.4367 | 72900 | 100 | 60 | 45.0835 | 100 | 60 | 45.0835
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 155d 3h | 104850 | 0 | 0 | 0 | 0 | 104850 | 0 | 100% | Finished | 94500 | 94500 | 100 | 110.9524 | 100 | 100 | 110.9524 | 100
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 100% | Finished | 360000 | 360000 | 100 | 100 | 100 | 100 | 100 | 100
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 100d | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 240000 | 240000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 2016-02-29 07:00 | 56d 7h | 102200 | 0 | 0 | 0 | 0 | 102200 | 0 | 100% | Finished | 99000 | 99000 | 100 | 103.2323 | 100 | 100 | 103.2323 | 100
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 | 2016-04-04 07:00 | 56d 7h | 25550 | 0 | 0 | 0 | 0 | 25550 | 0 | 100% | Finished | 13500 | 13500 | 100 | 189.2593 | 100 | 100 | 189.2593 | 100
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 220d | 129500 | 0 | 0 | 0 | 0 | 129500 | 0 | 100% | Finished | 129500 | 129500 | 100 | 100 | 100 | 100 | 100 | 100
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 | 2016-05-02 07:00 | 20d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 4500 | 4500 | 100 | 100 | 100 | 100 | 100 | 100
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 260d | 138500 | 0 | 0 | 0 | 0 | 138500 | 0 | 100% | Finished | 138500 | 138500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 | 2016-05-30 07:00 | 17d | 3825 | 1800 | 8d | 0 | 0 | 3825 | 1800 | 68% | Started | 3825 | 3825 | 100 | 68 | 68 | 100 | 68 | 68
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 164d | 3200000 | 0 | 0 | 0 | 0 | 3200000 | 0 | 100% | Finished | 3200000 | 3200000 | 100 | 149.0909 | 100 | 100 | 100 | 100

## TP20
| TP Status Date | 2016-07-15 17:00 |  | TP Name | 7/15/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 360d | [5 empty] | 14425900 |  | 99.79% |  | 14332419.0637 | 14362625
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 253d 5h | 5857050 | 0 | 0 | 0 | 0 | 5857050 | 0 | 100% | Finished | 5856025 | 5856025 | 100 | 101.8295 | 100 | 100 | 100.0175 | 100
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 1350 | 1350 | 100 | 155.5556 | 100 | 100 | 155.5556 | 100
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 305d | 500000 | 0 | 8d 7h | 0 | 0 | 500000 | 0 | 97.2% | Started | 500000 | 500000 | 100 | 156.4103 | 97.2026 | 100 | 100 | 97.2026
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 20d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 84d 4h | 272000 | 0 | 0 | 0 | 0 | 272000 | 0 | 100% | Finished | 237000 | 237000 | 100 | 129.9145 | 100 | 100 | 114.7679 | 100
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 | 2016-05-17 07:00 | 20d | 76000 | 0 | 0 | 0 | 0 | 76000 | 0 | 100% | Finished | 76000 | 76000 | 100 | 100 | 100 | 100 | 100 | 100
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 | 2016-05-16 07:00 | 45d | 121500 | 40200 | 14d 8h | 0 | 0 | 121500 | 40200 | 75.14% | Started | 91294.0637 | 121500 | 100 | 100 | 75.1391 | 100 | 100 | 75.1391
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 155d 3h | 104850 | 0 | 0 | 0 | 0 | 104850 | 0 | 100% | Finished | 94500 | 94500 | 100 | 110.9524 | 100 | 100 | 110.9524 | 100
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 100% | Finished | 360000 | 360000 | 100 | 100 | 100 | 100 | 100 | 100
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 100d | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 240000 | 240000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 2016-02-29 07:00 | 56d 7h | 102200 | 0 | 0 | 0 | 0 | 102200 | 0 | 100% | Finished | 99000 | 99000 | 100 | 103.2323 | 100 | 100 | 103.2323 | 100
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 | 2016-04-04 07:00 | 56d 7h | 25550 | 0 | 0 | 0 | 0 | 25550 | 0 | 100% | Finished | 13500 | 13500 | 100 | 189.2593 | 100 | 100 | 189.2593 | 100
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 220d | 129500 | 0 | 0 | 0 | 0 | 129500 | 0 | 100% | Finished | 129500 | 129500 | 100 | 100 | 100 | 100 | 100 | 100
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 | 2016-05-02 07:00 | 20d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 4500 | 4500 | 100 | 100 | 100 | 100 | 100 | 100
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 260d | 138500 | 0 | 0 | 0 | 0 | 138500 | 0 | 100% | Finished | 138500 | 138500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 | 2016-05-30 07:00 | 25d | 5625 | 0 | 0 | 0 | 0 | 5625 | 0 | 100% | Finished | 5625 | 5625 | 100 | 100 | 100 | 100 | 100 | 100
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 164d | 3200000 | 0 | 0 | 0 | 0 | 3200000 | 0 | 100% | Finished | 3200000 | 3200000 | 100 | 149.0909 | 100 | 100 | 100 | 100

## TP21
| TP Status Date | 2016-08-10 17:00 |  | TP Name | 8/10/2016 5:00 PM
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Biofuel Refinery | 2015-03-02 07:00 | 2016-07-15 17:00 | 360d |  |  | 13205000 |  |  | 14362625 |  | 374d 8h | [5 empty] | 14466100 |  | 100% |  | 14362625 | 14362625
1 | Tanks - Preparation | 2015-03-02 07:00 | 2016-02-11 17:00 | 249d |  | 0 | 5800000 | 25 | 56025 | 5856025 | 2015-03-02 07:00 | 253d 5h | 5857050 | 0 | 0 | 0 | 0 | 5857050 | 0 | 100% | Finished | 5856025 | 5856025 | 100 | 101.8295 | 100 | 100 | 100.0175 | 100
26 | Tanks - On Site | 2016-02-12 07:00 | 2016-02-12 17:00 | 1d |  | 0 | 0 | 150 | 1350 | 1350 | 2016-02-12 07:00 | 1d 5h | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 100% | Finished | 1350 | 1350 | 100 | 155.5556 | 100 | 100 | 155.5556 | 100
2 | Skids - Preparation | 2015-03-02 07:00 | 2015-05-01 17:00 | 45d |  | 0 | 0 | 25 | 10125 | 10125 | 2015-03-02 07:00 | 45d | 10125 | 0 | 0 | 0 | 0 | 10125 | 0 | 100% | Finished | 10125 | 10125 | 100 | 100 | 100 | 100 | 100 | 100
3 | Skids - Lead Time 1 | 2015-05-18 07:00 | 2016-02-12 17:00 | 195d |  | 0 | 500000 | 0 | 0 | 500000 | 2015-05-18 07:00 | 313d 7h | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | 100% | Finished | 500000 | 500000 | 100 | 160.9117 | 100 | 100 | 100 | 100
24 | Skids - Lead Time 2 | 2016-02-15 07:00 | 2016-03-11 17:00 | 20d |  | 0 | 50000 | 0 | 0 | 50000 | 2016-02-15 07:00 | 20d | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 100% | Finished | 50000 | 50000 | 100 | 100 | 100 | 100 | 100 | 100
5 | Skids - On Site 1 | 2016-02-15 07:00 | 2016-05-13 17:00 | 65d |  | 0 | 120000 | 200 | 117000 | 237000 | 2016-02-15 07:00 | 84d 4h | 272000 | 0 | 0 | 0 | 0 | 272000 | 0 | 100% | Finished | 237000 | 237000 | 100 | 129.9145 | 100 | 100 | 114.7679 | 100
25 | Skids - On Site 2 | 2016-05-17 07:00 | 2016-06-13 17:00 | 20d |  | 0 | 40000 | 200 | 36000 | 76000 | 2016-05-17 07:00 | 20d | 76000 | 0 | 0 | 0 | 0 | 76000 | 0 | 100% | Finished | 76000 | 76000 | 100 | 100 | 100 | 100 | 100 | 100
7 | Skids - Commissioning | 2016-05-16 07:00 | 2016-07-15 17:00 | 45d |  | 0 | 0 | 300 | 121500 | 121500 | 2016-05-16 07:00 | 59d 8h | 161700 | 0 | 0 | 0 | 0 | 161700 | 0 | 100% | Finished | 121500 | 121500 | 100 | 133.0864 | 100 | 100 | 133.0864 | 100
8 | Utilities - Preparation | 2015-06-29 07:00 | 2015-08-28 17:00 | 45d |  | 0 | 600000 | 0 | 0 | 600000 | 2015-06-29 07:00 | 82d 1h | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | 100% | Finished | 600000 | 600000 | 100 | 182.4691 | 100 | 100 | 100 | 100
9 | Utilities - Lead Time | 2015-08-31 07:00 | 2016-03-11 17:00 | 140d |  | 0 | 0 | 75 | 94500 | 94500 | 2015-08-31 07:00 | 155d 3h | 104850 | 0 | 0 | 0 | 0 | 104850 | 0 | 100% | Finished | 94500 | 94500 | 100 | 110.9524 | 100 | 100 | 110.9524 | 100
10 | Tie-inns | 2015-11-30 07:00 | 2015-12-04 17:00 | 5d |  | 0 | 85000 | 50 | 2250 | 87250 | 2015-11-30 07:00 | 7d | 88150 | 0 | 0 | 0 | 0 | 88150 | 0 | 100% | Finished | 87250 | 87250 | 100 | 140 | 100 | 100 | 101.0315 | 100
11 | Civil - Preparation | 2015-05-04 07:00 | 2015-08-28 17:00 | 85d |  | 0 | 1300000 | 50 | 38250 | 1338250 | 2015-05-04 07:00 | 85d | 1338250 | 0 | 0 | 0 | 0 | 1338250 | 0 | 100% | Finished | 1338250 | 1338250 | 100 | 100 | 100 | 100 | 100 | 100
13 | Civil - On Site | 2015-10-12 07:00 | 2016-01-29 17:00 | 80d |  | 0 | 0 | 500 | 360000 | 360000 | 2015-10-12 07:00 | 80d | 360000 | 0 | 0 | 0 | 0 | 360000 | 0 | 100% | Finished | 360000 | 360000 | 100 | 100 | 100 | 100 | 100 | 100
14 | Labo Container | 2015-10-12 07:00 | 2016-02-26 17:00 | 100d |  | 0 | 150000 | 100 | 90000 | 240000 | 2015-10-12 07:00 | 100d | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 240000 | 240000 | 100 | 100 | 100 | 100 | 100 | 100
15 | Piping - Preparation | 2015-05-04 07:00 | 2016-01-01 17:00 | 175d |  | 0 | 800000 | 0 | 0 | 800000 | 2015-05-04 07:00 | 175d | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | 100% | Finished | 800000 | 800000 | 100 | 100 | 100 | 100 | 100 | 100
16 | Piping - On Site | 2016-02-29 07:00 | 2016-05-13 17:00 | 55d |  | 0 | 0 | 200 | 99000 | 99000 | 2016-02-29 07:00 | 56d 7h | 102200 | 0 | 0 | 0 | 0 | 102200 | 0 | 100% | Finished | 99000 | 99000 | 100 | 103.2323 | 100 | 100 | 103.2323 | 100
17 | Electrical - Preparation | 2015-06-29 07:00 | 2016-01-01 17:00 | 135d |  | 0 | 400000 | 0 | 0 | 400000 | 2015-06-29 07:00 | 135d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
18 | Electrical - On Site | 2016-04-04 07:00 | 2016-05-13 17:00 | 30d |  | 0 | 0 | 50 | 13500 | 13500 | 2016-04-04 07:00 | 56d 7h | 25550 | 0 | 0 | 0 | 0 | 25550 | 0 | 100% | Finished | 13500 | 13500 | 100 | 189.2593 | 100 | 100 | 189.2593 | 100
19 | Automation - Preparation | 2015-06-29 07:00 | 2016-04-29 17:00 | 220d |  | 0 | 80000 | 25 | 49500 | 129500 | 2015-06-29 07:00 | 220d | 129500 | 0 | 0 | 0 | 0 | 129500 | 0 | 100% | Finished | 129500 | 129500 | 100 | 100 | 100 | 100 | 100 | 100
20 | Automation - On Site | 2016-05-02 07:00 | 2016-05-27 17:00 | 20d |  | 0 | 0 | 25 | 4500 | 4500 | 2016-05-02 07:00 | 20d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 4500 | 4500 | 100 | 100 | 100 | 100 | 100 | 100
21 | Analytics - Preparation | 2015-06-01 07:00 | 2016-05-27 17:00 | 260d |  | 0 | 80000 | 25 | 58500 | 138500 | 2015-06-01 07:00 | 260d | 138500 | 0 | 0 | 0 | 0 | 138500 | 0 | 100% | Finished | 138500 | 138500 | 100 | 100 | 100 | 100 | 100 | 100
22 | Analytics - On Site | 2016-05-30 07:00 | 2016-07-01 17:00 | 25d |  | 0 | 0 | 25 | 5625 | 5625 | 2016-05-30 07:00 | 25d | 5625 | 0 | 0 | 0 | 0 | 5625 | 0 | 100% | Finished | 5625 | 5625 | 100 | 100 | 100 | 100 | 100 | 100
23 | Purchases | 2015-09-28 07:00 | 2016-02-26 17:00 | 110d |  | 0 | 3200000 | 0 | 0 | 3200000 | 2015-09-28 07:00 | 164d | 3200000 | 0 | 0 | 0 | 0 | 3200000 | 0 | 100% | Finished | 3200000 | 3200000 | 100 | 149.0909 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | Yes
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
3/25/2015 5:00 PM | 2015-03-02 07:00 | 2015-03-25 17:00 | 5808100 | 5808027.2351 | 5808100 | 2015-03-25 15:00 | -72.7649 | 100% | -72.7649 | 100% | -2h | 98.77% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 09:00 | 2016-07-22 11:00 | 2016-07-22 12:00 | 14362697.7649 | 14362804.9399 | 14362804.9399 | 14469630.237 | 14362912.1161 | 14469738.7516 | 14362804.9399 | 14383958.6766 | 0.98765 | 0.99999 | 0.99999 | 1 | -0.22222 | 0.99999 | 1 | 0.98765 | 1
4/20/2015 5:00 PM | 2015-03-25 17:00 | 2015-04-20 17:00 | 5816200 | 5816054.4701 | 5816200 | 2015-04-20 14:00 | -145.5299 | 100% | -145.5299 | 100% | -3h | 99.07% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 10:00 | 2016-07-21 10:00 | 2016-07-21 10:00 | 14362770.5299 | 14362984.383 | 14362984.383 | 14442645.0208 | 14363198.2415 | 14442860.8726 | 14362984.383 | 14378798.593 | 0.99074 | 0.99997 | 0.99997 | 0.99999 | -0.33333 | 0.99997 | 1 | 0.99074 | 1
5/14/2015 5:00 PM | 2015-04-20 17:00 | 2015-05-14 17:00 | 7926325 | 7926106.7046 | 7926325 | 2015-05-14 14:00 | -218.2954 | 100% | -218.2954 | 100% | -3h | 99.38% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 10:00 | 2016-07-20 09:00 | 2016-07-20 09:00 | 14362843.2954 | 14363020.5656 | 14363020.5656 | 14402821.6699 | 14363197.8406 | 14403000.0411 | 14363020.5656 | 14370941.6029 | 0.99383 | 0.99997 | 0.99997 | 0.99998 | -0.33333 | 0.99997 | 1 | 0.99383 | 1
6/9/2015 5:00 PM | 2015-05-14 17:00 | 2015-06-09 17:00 | 8520050 | 8519758.9404 | 8520050 | 2015-06-09 14:00 | -291.0596 | 100% | -291.0596 | 100% | -3h | 99.54% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 10:00 | 2016-07-19 14:00 | 2016-07-19 14:00 | 14362916.0596 | 14363115.6688 | 14363115.6688 | 14390092.1808 | 14363315.2848 | 14390292.7184 | 14363115.6688 | 14368491.1171 | 0.99537 | 0.99997 | 0.99997 | 0.99997 | -0.33333 | 0.99997 | 1 | 0.99537 | 1
7/3/2015 5:00 PM | 2015-06-09 17:00 | 2015-07-03 17:00 | 9617375 | 9617011.1757 | 9617375 | 2015-07-03 14:00 | -363.8243 | 100% | -363.8243 | 100% | -3h | 99.63% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 10:00 | 2016-07-19 10:00 | 2016-07-19 10:00 | 14362988.8243 | 14363168.3571 | 14363168.3571 | 14380630.5113 | 14363347.8968 | 14380810.7116 | 14363168.3571 | 14366650.5378 | 0.9963 | 0.99996 | 0.99996 | 0.99997 | -0.33333 | 0.99996 | 1 | 0.9963 | 1
7/29/2015 5:00 PM | 2015-07-03 17:00 | 2015-07-29 17:00 | 9637625 | 9637188.4099 | 9637625 | 2015-07-29 12:00 | -436.5901 | 100% | -436.5901 | 100% | -4h | 99.59% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 11:00 | 2016-07-19 11:00 | 2016-07-19 11:00 | 14363061.5901 | 14363275.6649 | 14363275.6649 | 14382588.1876 | 14363489.7494 | 14382803.147 | 14363275.6649 | 14367125.5826 | 0.99588 | 0.99995 | 0.99995 | 0.99997 | -0.44444 | 0.99995 | 1 | 0.99588 | 1
8/24/2015 5:00 PM | 2015-07-29 17:00 | 2015-08-24 17:00 | 9657875 | 9657365.6439 | 9657875 | 2015-08-24 11:00 | -509.3561 | 99.99% | -509.3561 | 99.99% | -5h | 99.56% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 12:00 | 2016-07-19 12:00 | 2016-07-19 12:00 | 14363134.3561 | 14363382.5245 | 14363382.5245 | 14383972.5286 | 14363630.7059 | 14384221.7961 | 14363382.5245 | 14367486.1602 | 0.99559 | 0.99995 | 0.99995 | 0.99996 | -0.55556 | 0.99995 | 1 | 0.99559 | 1
9/17/2015 5:00 PM | 2015-08-24 17:00 | 2015-09-17 17:00 | 9681275 | 9679760.0479 | 9681275 | 2015-09-16 15:00 | -1514.9521 | 99.98% | -1514.9521 | 99.98% | -1d 2h | 99.15% | 100% | 2016-07-15 17:00 | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-15 17:00 | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-19 09:00 | 2016-07-21 08:00 | 2016-07-21 08:00 | 14364139.9521 | 14364872.8542 | 14364872.8542 | 14404226.7338 | 14365605.8709 | 14404965.9097 | 14364872.8542 | 14372691.0761 | 0.99151 | 0.99984 | 0.99984 | 0.99996 | -1.2222 | 0.99984 | 1 | 0.99151 | 1
10/13/2015 5:00 PM | 2015-09-17 17:00 | 2015-10-13 17:00 | 13066375 | 13063587.9233 | 13066375 | 2015-10-13 12:00 | -2787.0767 | 99.98% | -2787.0767 | 99.98% | -4h | 99.73% | 99.98% | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-15 17:00 | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-18 11:00 | 2016-07-18 17:00 | 2016-07-18 17:00 | 14365412.0767 | 14365689.2223 | 14365689.2223 | 14368985.7688 | 14365966.427 | 14369263.6768 | 14365689.2223 | 14366347.1961 | 0.99726 | 0.99979 | 0.99979 | 0.99982 | -0.44444 | 0.99979 | 1 | 0.99726 | 1
11/6/2015 5:00 PM | 2015-10-13 17:00 | 2015-11-06 17:00 | 13187875 | 13183815.8043 | 13187875 | 2015-11-06 10:00 | -4059.1957 | 99.97% | -4059.1957 | 99.97% | -6h | 99.63% | 99.97% | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-18 09:00 | 2016-07-15 17:00 | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-18 14:00 | 2016-07-19 10:00 | 2016-07-19 11:00 | 14366684.1957 | 14367047.142 | 14367047.142 | 14371066.386 | 14367410.2 | 14371430.6815 | 14367047.142 | 14367848.8048 | 0.9963 | 0.99969 | 0.99969 | 0.99974 | -0.66667 | 0.99969 | 1 | 0.9963 | 1
12/2/2015 5:00 PM | 2015-11-06 17:00 | 2015-12-02 17:00 | 13395725 | 13390007.9666 | 13395725 | 2015-12-02 08:00 | -5717.0334 | 99.96% | -5717.0334 | 99.96% | -8h | 99.55% | 99.97% | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-18 10:00 | 2016-07-18 08:00 | 2016-07-18 08:00 | 2016-07-18 09:00 | 2016-07-18 16:00 | 2016-07-19 14:00 | 2016-07-19 14:00 | 14368342.0334 | 14368757.3046 | 14368757.3046 | 14372728.1305 | 14369172.753 | 14373145.2744 | 14368757.3046 | 14369548.8855 | 0.99551 | 0.99957 | 0.99957 | 0.99966 | -0.88889 | 0.99957 | 1 | 0.99551 | 1
12/28/2015 5:00 PM | 2015-12-02 17:00 | 2015-12-28 17:00 | 13518125 | 13511521.5573 | 13519025 | 2015-12-25 17:00 | -6603.4427 | 99.95% | -7503.4427 | 99.94% | -1d | 99.54% | 99.96% | 2016-07-18 08:00 | 2016-07-18 09:00 | 2016-07-18 10:00 | 2016-07-18 08:00 | 2016-07-18 09:00 | 2016-07-18 09:00 | 2016-07-18 17:00 | 2016-07-19 14:00 | 2016-07-19 15:00 | 14370128.4427 | 14370601.0916 | 14370544.3998 | 14374087.0634 | 14371017.2797 | 14374561.9107 | 14370589.7527 | 14371296.0102 | 0.99537 | 0.99944 | 0.99951 | 0.99958 | -1 | 0.99944 | 1 | 0.99537 | 1
1/21/2016 5:00 PM | 2015-12-28 17:00 | 2016-01-21 17:00 | 13639625 | 13631749.4441 | 13640525 | 2016-01-20 15:00 | -7875.5559 | 99.94% | -8775.5559 | 99.94% | -1d 2h | 99.48% | 99.95% | 2016-07-18 09:00 | 2016-07-18 09:00 | 2016-07-18 11:00 | 2016-07-18 08:00 | 2016-07-18 09:00 | 2016-07-18 10:00 | 2016-07-19 09:00 | 2016-07-19 16:00 | 2016-07-19 17:00 | 14371400.5559 | 14371871.0633 | 14371822.8092 | 14375238.0886 | 14372293.5884 | 14375711.0665 | 14371861.4119 | 14372541.9972 | 0.99478 | 0.99936 | 0.99942 | 0.9995 | -1.2222 | 0.99936 | 1 | 0.99478 | 1
2/16/2016 5:00 PM | 2016-01-21 17:00 | 2016-02-16 17:00 | 13881400 | 13872098.371 | 13883725 | 2016-02-12 17:00 | -9301.629 | 99.93% | -11626.629 | 99.92% | -2d | 99.21% | 99.95% | 2016-07-18 09:00 | 2016-07-18 09:00 | 2016-07-18 12:00 | 2016-07-18 09:00 | 2016-07-18 09:00 | 2016-07-18 10:00 | 2016-07-19 17:00 | 2016-07-20 16:00 | 2016-07-20 17:00 | 14374251.629 | 14374662.7544 | 14374580.5408 | 14378175.8421 | 14374991.9418 | 14378590.2564 | 14374646.3095 | 14375361.3725 | 0.99206 | 0.99916 | 0.99933 | 0.99948 | -2 | 0.99916 | 1 | 0.99206 | 1
3/11/2016 5:00 PM | 2016-02-16 17:00 | 2016-03-11 17:00 | 13959250 | 13941068.6003 | 13961925 | 2016-03-08 08:00 | -18181.3997 | 99.87% | -20856.3997 | 99.85% | -3d 8h | 98.56% | 99.94% | 2016-07-18 11:00 | 2016-07-18 11:00 | 2016-07-18 17:00 | 2016-07-18 10:00 | 2016-07-18 11:00 | 2016-07-18 12:00 | 2016-07-21 16:00 | 2016-07-25 09:00 | 2016-07-25 11:00 | 14383481.3997 | 14384112.065 | 14384031.1771 | 14389641.9316 | 14384662.665 | 14390281.8134 | 14384095.885 | 14385206.5696 | 0.9856 | 0.99851 | 0.9987 | 0.99943 | -3.8889 | 0.99851 | 1 | 0.9856 | 1
4/6/2016 5:00 PM | 2016-03-11 17:00 | 2016-04-06 17:00 | 14033500 | 14015535.2236 | 14046525 | 2016-03-31 16:00 | -17964.7764 | 99.87% | -30989.7764 | 99.78% | -4d 1h | 98.57% | 99.94% | 2016-07-18 11:00 | 2016-07-18 11:00 | 2016-07-19 09:00 | 2016-07-18 10:00 | 2016-07-18 11:00 | 2016-07-18 14:00 | 2016-07-22 08:00 | 2016-07-25 09:00 | 2016-07-25 10:00 | 14393614.7764 | 14394382.2273 | 14394059.6677 | 14398641.1254 | 14394828.1023 | 14399419.69 | 14394317.6675 | 14395225.745 | 0.98573 | 0.99779 | 0.99872 | 0.9994 | -4.1111 | 0.99779 | 1 | 0.98573 | 1
5/2/2016 5:00 PM | 2016-04-06 17:00 | 2016-05-02 17:00 | 14114500 | 14084240.0609 | 14127525 | 2016-04-22 09:00 | -30259.9391 | 99.79% | -43284.9391 | 99.69% | -6d 7h | 97.79% | 99.91% | 2016-07-18 15:00 | 2016-07-18 15:00 | 2016-07-19 16:00 | 2016-07-18 14:00 | 2016-07-18 15:00 | 2016-07-18 16:00 | 2016-07-26 15:00 | 2016-07-28 08:00 | 2016-07-28 10:00 | 14405909.9391 | 14406765.4964 | 14406508.0481 | 14412215.7249 | 14407365.4436 | 14413090.6617 | 14406713.9687 | 14407838.7833 | 0.97785 | 0.99694 | 0.99786 | 0.99912 | -6.7778 | 0.99694 | 1 | 0.97785 | 1
5/26/2016 5:00 PM | 2016-05-02 17:00 | 2016-05-26 17:00 | 14237750 | 14213010.7523 | 14274225 | 2016-05-19 17:00 | -24739.2477 | 99.83% | -61214.2477 | 99.57% | -5d | 98.46% | 99.87% | 2016-07-18 14:00 | 2016-07-18 14:00 | 2016-07-20 09:00 | 2016-07-18 12:00 | 2016-07-18 14:00 | 2016-07-18 15:00 | 2016-07-22 17:00 | 2016-07-25 14:00 | 2016-07-25 15:00 | 14423839.2477 | 14424483.6237 | 14424099.6671 | 14426184.2986 | 14424745.1648 | 14426838.7746 | 14424406.6751 | 14424820.7065 | 0.98457 | 0.99571 | 0.99826 | 0.99868 | -5 | 0.99571 | 1 | 0.98457 | 1
6/21/2016 5:00 PM | 2016-05-26 17:00 | 2016-06-21 17:00 | 14312225 | 14294101.4368 | 14375500 | 2016-06-13 15:00 | -18123.5632 | 99.87% | -81398.5632 | 99.43% | -6d 2h | 98.18% | 99.99% | 2016-07-18 11:00 | 2016-07-18 11:00 | 2016-07-20 12:00 | 2016-07-18 11:00 | 2016-07-18 11:00 | 2016-07-18 12:00 | 2016-07-26 09:00 | 2016-07-26 14:00 | 2016-07-26 15:00 | 14444023.5632 | 14444413.7745 | 14444110.4446 | 14445293.3579 | 14444501.1506 | 14445690.8001 | 14444352.8941 | 14444587.9131 | 0.98181 | 0.99434 | 0.99873 | 0.99991 | -6.2222 | 0.99434 | 1 | 0.98181 | 1
7/15/2016 5:00 PM | 2016-06-21 17:00 | 2016-07-15 17:00 | 14362625 | 14332419.0637 | 14425900 | 2016-06-30 16:00 | -30205.9363 | 99.79% | -93480.9363 | 99.35% | -11d 1h | 96.91% | 100% | 2016-07-18 15:00 | 2016-07-18 15:00 | 2016-07-21 08:00 | 2016-07-18 15:00 | 2016-07-18 15:00 | 2016-07-18 15:00 | 2016-08-02 08:00 | 2016-08-02 11:00 | 2016-08-02 12:00 | 14456105.9363 | 14456302.9498 | 14456169.5961 | 14457067.9088 | 14456367.0248 | 14457271.1966 | 14456276.1851 | 14456452.9229 | 0.96914 | 0.99352 | 0.9979 | 0.99999 | -11.1111 | 0.99352 | 1 | 0.96914 | 1
8/10/2016 5:00 PM | 2016-07-15 17:00 | 2016-08-10 17:00 | 14362625 | 14362625 | 14466100 | 2016-07-15 17:00 | 0 | 100% | -103475 | 99.28% | -18d | 95.24% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-20 12:00 | 2016-08-10 17:00 | 2016-08-10 17:00 | 2016-08-10 17:00 | 2016-08-10 17:00 | 2016-08-10 17:00 | 2016-08-10 17:00 | 14466100 | 14466100 | 14466100 | 14466100 | 14466100 | 14466100 | 14466100 | 14466100 | 0.95238 | 0.99285 | 1 | 1 | -18 | 0.99285 | 1 | 0.95238 | 1