## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House (4) | 1 |  |  | 2016-03-07 08:00 | 2017-05-29 17:00 | 321d |  |  | 218366 |  |  | 218366 | 448.375
49 | Voorbereiding | 1.1 |  |  | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  |  | 11265 |  |  | 11265 | 14.375
1 | Werfinrichting | 1.1.1 |  | FS5 | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 3642 | 0 | 0 | 3642 | 2.375
2 | Transportkosten | 1.1.2 |  | FS5 | 2016-03-07 08:00 | 2016-03-15 17:00 | 7d |  | 0 | 2202 | 0 | 0 | 2202 | 8.375
3 | Rijtijden ploegen | 1.1.3 |  | FS5 | 2016-03-07 08:00 | 2016-03-16 17:00 | 8d |  | 0 | 2190 | 0 | 0 | 2190 | 9.375
4 | Studiekosten | 1.1.4 |  | FS5 | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  | 0 | 3231 | 0 | 0 | 3231 | 14.375
50 | Funderingen | 1.2 |  |  | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  |  | 12319 |  |  | 12319 | 41.375
5 | Funderingen | 1.2.1 | 1FS;2FS;3FS;4FS | FS6 | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  | 0 | 12319 | 0 | 0 | 12319 | 41.375
51 | Ruwbouw | 1.3 |  |  | 2016-05-03 08:00 | 2016-08-25 17:00 | 83d |  |  | 48401 |  |  | 48401 | 114.375
6 | Gewa/metselwerk | 1.3.1 | 5FS | FS7;FS8 | 2016-05-03 08:00 | 2016-05-27 17:00 | 19d |  | 0 | 12997 | 0 | 0 | 12997 | 24.375
7 | Gewelven/Structuur | 1.3.2 | 6FS | FS9 | 2016-05-30 08:00 | 2016-06-07 17:00 | 7d |  | 0 | 5432 | 0 | 0 | 5432 | 8.375
8 | Uitbranden GEWA | 1.3.3 | 6FS | FS9 | 2016-05-30 08:00 | 2016-05-30 17:00 | 1d |  | 0 | 533 | 0 | 0 | 533 | 0.375
9 | Isolatie | 1.3.4 | 7FS;8FS | FS10 | 2016-06-08 08:00 | 2016-06-14 17:00 | 5d |  | 0 | 1324 | 0 | 0 | 1324 | 6.375
10 | Parament | 1.3.5 | 9FS | FS11 | 2016-06-15 08:00 | 2016-08-02 17:00 | 35d |  | 0 | 19883 | 0 | 0 | 19883 | 48.375
11 | Ytong | 1.3.6 | 10FS | FS12;FS13 | 2016-08-03 08:00 | 2016-08-08 17:00 | 4d |  | 0 | 2879 | 0 | 0 | 2879 | 5.375
12 | Dorpels | 1.3.7 | 11FS | FS14 | 2016-08-09 08:00 | 2016-08-11 17:00 | 3d |  | 0 | 1934 | 0 | 0 | 1934 | 2.375
13 | Voegwerk | 1.3.8 | 11FS | FS14 | 2016-08-09 08:00 | 2016-08-16 17:00 | 6d |  | 0 | 1493 | 0 | 0 | 1493 | 7.375
14 | Stelling | 1.3.9 | 12FS;13FS | FS15 | 2016-08-17 08:00 | 2016-08-22 17:00 | 4d |  | 0 | 1392 | 0 | 0 | 1392 | 5.375
15 | Crepi+Isolatie | 1.3.10 | 14FS | FS16 | 2016-08-23 08:00 | 2016-08-24 17:00 | 2d |  | 0 | 334 | 0 | 0 | 334 | 1.375
16 | Karweien | 1.3.11 | 15FS | FS17 | 2016-08-25 08:00 | 2016-08-25 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 0.375
52 | Dakwerken | 1.4 |  |  | 2016-08-26 08:00 | 2016-12-05 17:00 | 72d |  |  | 39200 |  |  | 39200 | 101.375
17 | Daktimmer traditioneel/prefabkap | 1.4.1 | 16FS | FS18 | 2016-08-26 08:00 | 2016-10-13 17:00 | 35d |  | 0 | 13456 | 0 | 0 | 13456 | 48.375
18 | Dakdekken | 1.4.2 | 17FS | FS19;FS20 | 2016-10-14 08:00 | 2016-11-10 17:00 | 20d |  | 0 | 15873 | 0 | 0 | 15873 | 27.375
19 | Goten & Afleiders | 1.4.3 | 18FS |  | 2016-11-11 08:00 | 2016-11-15 17:00 | 3d |  | 0 | 1282 | 0 | 0 | 1282 | 4.375
20 | Oversteken/Gevelbekleding | 1.4.4 | 18FS | FS21 | 2016-11-11 08:00 | 2016-12-02 17:00 | 16d |  | 0 | 6265 | 0 | 0 | 6265 | 21.375
21 | Dakvlakramen | 1.4.5 | 20FS | FS22 | 2016-12-05 08:00 | 2016-12-05 17:00 | 1d |  | 0 | 2324 | 0 | 0 | 2324 | 0.375
53 | Buitenschrijnwerk | 1.5 |  |  | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  |  | 23493 |  |  | 23493 | 20.375
22 | Buitenschrijnwerk plaatsen | 1.5.1 | 21FS | FS32;FS33 | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  | 0 | 23493 | 0 | 0 | 23493 | 20.375
54 | Binnenafwerking | 1.6 |  |  | 2017-01-23 08:00 | 2017-04-05 17:00 | 53d |  |  | 30237 |  |  | 30237 | 72.375
23 | Plakwerken | 1.6.1 | 41FS | FS24 | 2017-01-23 08:00 | 2017-02-07 17:00 | 12d |  | 0 | 9564 | 0 | 0 | 9564 | 15.375
24 | Chapes/uitvullingen | 1.6.2 | 23FS | FS35 | 2017-02-08 08:00 | 2017-02-14 17:00 | 5d |  | 0 | 2432 | 0 | 0 | 2432 | 6.375
25 | Vloerisolatie | 1.6.3 | 35FS | FS26 | 2017-02-16 08:00 | 2017-03-01 17:00 | 10d |  | 0 | 2739 | 0 | 0 | 2739 | 13.375
26 | Tegelwerken | 1.6.4 | 25FS | FS27;FS28;FS38 | 2017-03-02 08:00 | 2017-03-10 17:00 | 7d |  | 0 | 3633 | 0 | 0 | 3633 | 8.375
27 | Voorbereiding+Gyplat | 1.6.5 | 26FS | FS29;FS30;FS31 | 2017-03-13 08:00 | 2017-03-22 17:00 | 8d |  | 0 | 2792 | 0 | 0 | 2792 | 9.375
28 | Buisbek/Zoldluik/Platen zold/Stijl | 1.6.6 | 26FS | FS29;FS30;FS31 | 2017-03-13 08:00 | 2017-03-16 17:00 | 4d |  | 0 | 837 | 0 | 0 | 837 | 3.375
29 | Binnendeuren/Uitbekleding | 1.6.7 | 27FS;28FS |  | 2017-03-23 08:00 | 2017-03-28 17:00 | 4d |  | 0 | 1021 | 0 | 0 | 1021 | 5.375
30 | Trap | 1.6.8 | 27FS;28FS |  | 2017-03-23 08:00 | 2017-03-30 17:00 | 6d |  | 0 | 1650 | 0 | 0 | 1650 | 7.375
31 | Luchtdichten | 1.6.9 | 27FS;28FS |  | 2017-03-23 08:00 | 2017-04-05 17:00 | 10d |  | 0 | 5569 | 0 | 0 | 5569 | 13.375
55 | Technieken | 1.7 |  |  | 2016-12-27 08:00 | 2017-04-07 17:00 | 74d |  |  | 38827 |  |  | 38827 | 101.375
32 | UZL | 1.7.1 | 22FS | FS34 | 2016-12-27 08:00 | 2016-12-29 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2.375
33 | Betonplexplaten | 1.7.2 | 22FS | FS34 | 2016-12-27 08:00 | 2016-12-27 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 0.375
34 | Slijpen technieken/Boringen | 1.7.3 | 32FS;33FS | FS36 | 2016-12-30 08:00 | 2017-01-04 17:00 | 4d |  | 0 | 1296 | 0 | 0 | 1296 | 5.375
35 | Bad &amp; douche | 1.7.4 | 24FS | FS25 | 2017-02-15 08:00 | 2017-02-15 17:00 | 1d |  | 0 | 320 | 0 | 0 | 320 | 0.375
36 | Leidingen vent | 1.7.5 | 34FS | FS37 | 2017-01-05 08:00 | 2017-01-09 17:00 | 3d |  | 0 | 2580 | 0 | 0 | 2580 | 4.375
37 | Leidingen san/WP/CV | 1.7.6 | 36FS | FS41 | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d |  | 0 | 3711 | 0 | 0 | 3711 | 6.375
38 | Afwerken ventilatie | 1.7.7 | 26FS | FS39 | 2017-03-13 08:00 | 2017-03-14 17:00 | 2d |  | 0 | 2317 | 0 | 0 | 2317 | 1.375
39 | Afwerken sanitair | 1.7.8 | 38FS | FS40 | 2017-03-15 08:00 | 2017-03-17 17:00 | 3d |  | 0 | 6472 | 0 | 0 | 6472 | 2.375
40 | Afwerken CV/WP | 1.7.9 | 39FS | FS42 | 2017-03-20 08:00 | 2017-03-21 17:00 | 2d |  | 0 | 5903 | 0 | 0 | 5903 | 1.375
41 | Leidingen electro | 1.7.10 | 37FS | FS23 | 2017-01-17 08:00 | 2017-01-20 17:00 | 4d |  | 0 | 2701 | 0 | 0 | 2701 | 3.375
42 | Afwerken electro | 1.7.11 | 40FS | FS43;FS44;FS45;FS46 | 2017-03-22 08:00 | 2017-03-27 17:00 | 4d |  | 0 | 3807 | 0 | 0 | 3807 | 5.375
43 | Zonneboiler | 1.7.12 | 42FS |  | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 455 | 0 | 0 | 455 | 0.375
44 | PV panelen | 1.7.13 | 42FS |  | 2017-03-28 08:00 | 2017-03-30 17:00 | 3d |  | 0 | 4950 | 0 | 0 | 4950 | 2.375
45 | Verlichting | 1.7.14 | 42FS |  | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 0.375
46 | Karweien | 1.7.15 | 42FS | FS47 | 2017-03-28 08:00 | 2017-04-07 17:00 | 9d |  | 0 | 3227 | 0 | 0 | 3227 | 10.375
56 | Omgevingswerken | 1.8 |  |  | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  |  | 1406 |  |  | 1406 | 4.375
47 | Opkuis werf (afvoeren puin & afval) | 1.8.1 | 46FS | FS48 | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  | 0 | 1406 | 0 | 0 | 1406 | 4.375
57 | Restklasse | 1.9 |  |  | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  |  | 13218 |  |  | 13218 | 42.375
48 | Rest | 1.9.1 | 47FS |  | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  | 0 | 13218 | 0 | 0 | 13218 | 42.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House (4) | 2568h |  |  |  |  | 99 | 100 | 101
49 | Voorbereiding | 88h |  |  |  |  | 99 | 100 | 101
1 | Werfinrichting | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Transportkosten | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Rijtijden ploegen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Studiekosten | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Funderingen | 240h |  |  |  |  | 99 | 100 | 101
5 | Funderingen | 240h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
51 | Ruwbouw | 664h |  |  |  |  | 99 | 100 | 101
6 | Gewa/metselwerk | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Gewelven/Structuur | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Uitbranden GEWA | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Isolatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Parament | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Ytong | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Dorpels | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Voegwerk | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Stelling | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Crepi+Isolatie | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Karweien | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Dakwerken | 576h |  |  |  |  | 99 | 100 | 101
17 | Daktimmer traditioneel/prefabkap | 280h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
18 | Dakdekken | 160h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
19 | Goten & Afleiders | 24h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Oversteken/Gevelbekleding | 128h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
21 | Dakvlakramen | 8h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
53 | Buitenschrijnwerk | 120h |  |  |  |  | 99 | 100 | 101
22 | Buitenschrijnwerk plaatsen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Binnenafwerking | 424h |  |  |  |  | 99 | 100 | 101
23 | Plakwerken | 96h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
24 | Chapes/uitvullingen | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | Vloerisolatie | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
26 | Tegelwerken | 56h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
27 | Voorbereiding+Gyplat | 64h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
28 | Buisbek/Zoldluik/Platen zold/Stijl | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
29 | Binnendeuren/Uitbekleding | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
30 | Trap | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
31 | Luchtdichten | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
55 | Technieken | 592h |  |  |  |  | 99 | 100 | 101
32 | UZL | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
33 | Betonplexplaten | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
34 | Slijpen technieken/Boringen | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
35 | Bad &amp; douche | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
36 | Leidingen vent | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
37 | Leidingen san/WP/CV | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
38 | Afwerken ventilatie | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
39 | Afwerken sanitair | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
40 | Afwerken CV/WP | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
41 | Leidingen electro | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
42 | Afwerken electro | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
43 | Zonneboiler | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
44 | PV panelen | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
45 | Verlichting | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
46 | Karweien | 72h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
56 | Omgevingswerken | 40h |  |  |  |  | 99 | 100 | 101
47 | Opkuis werf (afvoeren puin & afval) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Restklasse | 248h |  |  |  |  | 99 | 100 | 101
48 | Rest | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2016-05-02 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (4) | 2016-03-07 08:00 | 2017-05-29 17:00 | 321d |  |  | 218366 |  |  | 218366 |  | 40d | [5 empty] | 25353 |  | 10.8% |  | 23584 | 23584
49 | Voorbereiding | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  |  | 11265 |  |  | 11265 |  | 10d | [5 empty] | 12992 |  | 100% |  | 11265 | 11265
1 | Werfinrichting | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 3642 | 0 | 0 | 3642 | 2016-03-07 08:00 | 6d | 3642 | 0 | 0 | 1721 | 0 | 5363 | 0 | 100% | Finished | 3642 | 3642 | 100 | 200 | 100 | 100 | 147.2543 | 100
2 | Transportkosten | 2016-03-07 08:00 | 2016-03-15 17:00 | 7d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-07 08:00 | 8d | 2202 | 0 | 0 | -56 | 0 | 2146 | 0 | 100% | Finished | 2202 | 2202 | 100 | 114.2857 | 100 | 100 | 97.4569 | 100
3 | Rijtijden ploegen | 2016-03-07 08:00 | 2016-03-16 17:00 | 8d |  | 0 | 2190 | 0 | 0 | 2190 | 2016-03-07 08:00 | 7d | 2190 | 0 | 0 | -154 | 0 | 2036 | 0 | 100% | Finished | 2190 | 2190 | 100 | 87.5 | 100 | 100 | 92.968 | 100
4 | Studiekosten | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  | 0 | 3231 | 0 | 0 | 3231 | 2016-03-07 08:00 | 10d | 3231 | 0 | 0 | 216 | 0 | 3447 | 0 | 100% | Finished | 3231 | 3231 | 100 | 90.9091 | 100 | 100 | 106.6852 | 100
50 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  |  | 12319 |  |  | 12319 |  | 30d | [5 empty] | 12361 |  | 100% |  | 12319 | 12319
5 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  | 0 | 12319 | 0 | 0 | 12319 | 2016-03-21 08:00 | 30d | 12319 | 0 | 0 | 42 | 0 | 12361 | 0 | 100% | Finished | 12319 | 12319 | 100 | 100 | 100 | 100 | 100.3409 | 100
51 | Ruwbouw | 2016-05-03 08:00 | 2016-08-25 17:00 | 83d |  |  | 48401 |  |  | 48401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
6 | Gewa/metselwerk | 2016-05-03 08:00 | 2016-05-27 17:00 | 19d |  | 0 | 12997 | 0 | 0 | 12997 |  | 0 | 0 | 12997 | 19d | 0 | 0 | 0 | 12997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Gewelven/Structuur | 2016-05-30 08:00 | 2016-06-07 17:00 | 7d |  | 0 | 5432 | 0 | 0 | 5432 |  | 0 | 0 | 5432 | 7d | 0 | 0 | 0 | 5432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Uitbranden GEWA | 2016-05-30 08:00 | 2016-05-30 17:00 | 1d |  | 0 | 533 | 0 | 0 | 533 |  | 0 | 0 | 533 | 1d | 0 | 0 | 0 | 533 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Isolatie | 2016-06-08 08:00 | 2016-06-14 17:00 | 5d |  | 0 | 1324 | 0 | 0 | 1324 |  | 0 | 0 | 1324 | 5d | 0 | 0 | 0 | 1324 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Parament | 2016-06-15 08:00 | 2016-08-02 17:00 | 35d |  | 0 | 19883 | 0 | 0 | 19883 |  | 0 | 0 | 19883 | 35d | 0 | 0 | 0 | 19883 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Ytong | 2016-08-03 08:00 | 2016-08-08 17:00 | 4d |  | 0 | 2879 | 0 | 0 | 2879 |  | 0 | 0 | 2879 | 4d | 0 | 0 | 0 | 2879 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Dorpels | 2016-08-09 08:00 | 2016-08-11 17:00 | 3d |  | 0 | 1934 | 0 | 0 | 1934 |  | 0 | 0 | 1934 | 3d | 0 | 0 | 0 | 1934 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Voegwerk | 2016-08-09 08:00 | 2016-08-16 17:00 | 6d |  | 0 | 1493 | 0 | 0 | 1493 |  | 0 | 0 | 1493 | 6d | 0 | 0 | 0 | 1493 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Stelling | 2016-08-17 08:00 | 2016-08-22 17:00 | 4d |  | 0 | 1392 | 0 | 0 | 1392 |  | 0 | 0 | 1392 | 4d | 0 | 0 | 0 | 1392 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Crepi+Isolatie | 2016-08-23 08:00 | 2016-08-24 17:00 | 2d |  | 0 | 334 | 0 | 0 | 334 |  | 0 | 0 | 334 | 2d | 0 | 0 | 0 | 334 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Karweien | 2016-08-25 08:00 | 2016-08-25 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Dakwerken | 2016-08-26 08:00 | 2016-12-05 17:00 | 72d |  |  | 39200 |  |  | 39200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Daktimmer traditioneel/prefabkap | 2016-08-26 08:00 | 2016-10-13 17:00 | 35d |  | 0 | 13456 | 0 | 0 | 13456 |  | 0 | 0 | 13456 | 35d | 0 | 0 | 0 | 13456 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Dakdekken | 2016-10-14 08:00 | 2016-11-10 17:00 | 20d |  | 0 | 15873 | 0 | 0 | 15873 |  | 0 | 0 | 15873 | 20d | 0 | 0 | 0 | 15873 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Goten & Afleiders | 2016-11-11 08:00 | 2016-11-15 17:00 | 3d |  | 0 | 1282 | 0 | 0 | 1282 |  | 0 | 0 | 1282 | 3d | 0 | 0 | 0 | 1282 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Oversteken/Gevelbekleding | 2016-11-11 08:00 | 2016-12-02 17:00 | 16d |  | 0 | 6265 | 0 | 0 | 6265 |  | 0 | 0 | 6265 | 16d | 0 | 0 | 0 | 6265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Dakvlakramen | 2016-12-05 08:00 | 2016-12-05 17:00 | 1d |  | 0 | 2324 | 0 | 0 | 2324 |  | 0 | 0 | 2324 | 1d | 0 | 0 | 0 | 2324 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Buitenschrijnwerk | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  |  | 23493 |  |  | 23493 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Buitenschrijnwerk plaatsen | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  | 0 | 23493 | 0 | 0 | 23493 |  | 0 | 0 | 23493 | 15d | 0 | 0 | 0 | 23493 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Binnenafwerking | 2017-01-23 08:00 | 2017-04-05 17:00 | 53d |  |  | 30237 |  |  | 30237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | Plakwerken | 2017-01-23 08:00 | 2017-02-07 17:00 | 12d |  | 0 | 9564 | 0 | 0 | 9564 |  | 0 | 0 | 9564 | 12d | 0 | 0 | 0 | 9564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Chapes/uitvullingen | 2017-02-08 08:00 | 2017-02-14 17:00 | 5d |  | 0 | 2432 | 0 | 0 | 2432 |  | 0 | 0 | 2432 | 5d | 0 | 0 | 0 | 2432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Vloerisolatie | 2017-02-16 08:00 | 2017-03-01 17:00 | 10d |  | 0 | 2739 | 0 | 0 | 2739 |  | 0 | 0 | 2739 | 10d | 0 | 0 | 0 | 2739 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Tegelwerken | 2017-03-02 08:00 | 2017-03-10 17:00 | 7d |  | 0 | 3633 | 0 | 0 | 3633 |  | 0 | 0 | 3633 | 7d | 0 | 0 | 0 | 3633 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Voorbereiding+Gyplat | 2017-03-13 08:00 | 2017-03-22 17:00 | 8d |  | 0 | 2792 | 0 | 0 | 2792 |  | 0 | 0 | 2792 | 8d | 0 | 0 | 0 | 2792 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-13 08:00 | 2017-03-16 17:00 | 4d |  | 0 | 837 | 0 | 0 | 837 |  | 0 | 0 | 837 | 4d | 0 | 0 | 0 | 837 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Binnendeuren/Uitbekleding | 2017-03-23 08:00 | 2017-03-28 17:00 | 4d |  | 0 | 1021 | 0 | 0 | 1021 |  | 0 | 0 | 1021 | 4d | 0 | 0 | 0 | 1021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Trap | 2017-03-23 08:00 | 2017-03-30 17:00 | 6d |  | 0 | 1650 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 6d | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-05 17:00 | 10d |  | 0 | 5569 | 0 | 0 | 5569 |  | 0 | 0 | 5569 | 10d | 0 | 0 | 0 | 5569 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Technieken | 2016-12-27 08:00 | 2017-04-07 17:00 | 74d |  |  | 38827 |  |  | 38827 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | UZL | 2016-12-27 08:00 | 2016-12-29 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Betonplexplaten | 2016-12-27 08:00 | 2016-12-27 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Slijpen technieken/Boringen | 2016-12-30 08:00 | 2017-01-04 17:00 | 4d |  | 0 | 1296 | 0 | 0 | 1296 |  | 0 | 0 | 1296 | 4d | 0 | 0 | 0 | 1296 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bad &amp; douche | 2017-02-15 08:00 | 2017-02-15 17:00 | 1d |  | 0 | 320 | 0 | 0 | 320 |  | 0 | 0 | 320 | 1d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Leidingen vent | 2017-01-05 08:00 | 2017-01-09 17:00 | 3d |  | 0 | 2580 | 0 | 0 | 2580 |  | 0 | 0 | 2580 | 3d | 0 | 0 | 0 | 2580 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Leidingen san/WP/CV | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d |  | 0 | 3711 | 0 | 0 | 3711 |  | 0 | 0 | 3711 | 5d | 0 | 0 | 0 | 3711 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken ventilatie | 2017-03-13 08:00 | 2017-03-14 17:00 | 2d |  | 0 | 2317 | 0 | 0 | 2317 |  | 0 | 0 | 2317 | 2d | 0 | 0 | 0 | 2317 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerken sanitair | 2017-03-15 08:00 | 2017-03-17 17:00 | 3d |  | 0 | 6472 | 0 | 0 | 6472 |  | 0 | 0 | 6472 | 3d | 0 | 0 | 0 | 6472 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Afwerken CV/WP | 2017-03-20 08:00 | 2017-03-21 17:00 | 2d |  | 0 | 5903 | 0 | 0 | 5903 |  | 0 | 0 | 5903 | 2d | 0 | 0 | 0 | 5903 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Leidingen electro | 2017-01-17 08:00 | 2017-01-20 17:00 | 4d |  | 0 | 2701 | 0 | 0 | 2701 |  | 0 | 0 | 2701 | 4d | 0 | 0 | 0 | 2701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afwerken electro | 2017-03-22 08:00 | 2017-03-27 17:00 | 4d |  | 0 | 3807 | 0 | 0 | 3807 |  | 0 | 0 | 3807 | 4d | 0 | 0 | 0 | 3807 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Zonneboiler | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 455 | 0 | 0 | 455 |  | 0 | 0 | 455 | 1d | 0 | 0 | 0 | 455 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | PV panelen | 2017-03-28 08:00 | 2017-03-30 17:00 | 3d |  | 0 | 4950 | 0 | 0 | 4950 |  | 0 | 0 | 4950 | 3d | 0 | 0 | 0 | 4950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Verlichting | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Karweien | 2017-03-28 08:00 | 2017-04-07 17:00 | 9d |  | 0 | 3227 | 0 | 0 | 3227 |  | 0 | 0 | 3227 | 9d | 0 | 0 | 0 | 3227 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Omgevingswerken | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  |  | 1406 |  |  | 1406 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Opkuis werf (afvoeren puin & afval) | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  | 0 | 1406 | 0 | 0 | 1406 |  | 0 | 0 | 1406 | 5d | 0 | 0 | 0 | 1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Restklasse | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  |  | 13218 |  |  | 13218 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | Rest | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  | 0 | 13218 | 0 | 0 | 13218 |  | 0 | 0 | 13218 | 31d | 0 | 0 | 0 | 13218 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-09-06 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (4) | 2016-03-07 08:00 | 2017-05-29 17:00 | 321d |  |  | 218366 |  |  | 218366 |  | 131d | [5 empty] | 77847 |  | 32.97% |  | 71985 | 85441
49 | Voorbereiding | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  |  | 11265 |  |  | 11265 |  | 10d | [5 empty] | 12992 |  | 100% |  | 11265 | 11265
1 | Werfinrichting | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 3642 | 0 | 0 | 3642 | 2016-03-07 08:00 | 6d | 3642 | 0 | 0 | 1721 | 0 | 5363 | 0 | 100% | Finished | 3642 | 3642 | 100 | 200 | 100 | 100 | 147.2543 | 100
2 | Transportkosten | 2016-03-07 08:00 | 2016-03-15 17:00 | 7d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-07 08:00 | 8d | 2202 | 0 | 0 | -56 | 0 | 2146 | 0 | 100% | Finished | 2202 | 2202 | 100 | 114.2857 | 100 | 100 | 97.4569 | 100
3 | Rijtijden ploegen | 2016-03-07 08:00 | 2016-03-16 17:00 | 8d |  | 0 | 2190 | 0 | 0 | 2190 | 2016-03-07 08:00 | 7d | 2190 | 0 | 0 | -154 | 0 | 2036 | 0 | 100% | Finished | 2190 | 2190 | 100 | 87.5 | 100 | 100 | 92.968 | 100
4 | Studiekosten | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  | 0 | 3231 | 0 | 0 | 3231 | 2016-03-07 08:00 | 10d | 3231 | 0 | 0 | 216 | 0 | 3447 | 0 | 100% | Finished | 3231 | 3231 | 100 | 90.9091 | 100 | 100 | 106.6852 | 100
50 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  |  | 12319 |  |  | 12319 |  | 30d | [5 empty] | 12361 |  | 100% |  | 12319 | 12319
5 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  | 0 | 12319 | 0 | 0 | 12319 | 2016-03-21 08:00 | 30d | 12319 | 0 | 0 | 42 | 0 | 12361 | 0 | 100% | Finished | 12319 | 12319 | 100 | 100 | 100 | 100 | 100.3409 | 100
51 | Ruwbouw | 2016-05-03 08:00 | 2016-08-25 17:00 | 83d |  |  | 48401 |  |  | 48401 |  | 91d | [5 empty] | 52494 |  | 100% |  | 48401 | 48401
6 | Gewa/metselwerk | 2016-05-03 08:00 | 2016-05-27 17:00 | 19d |  | 0 | 12997 | 0 | 0 | 12997 | 2016-05-02 08:00 | 19d | 12997 | 0 | 0 | 580 | 0 | 13577 | 0 | 100% | Finished | 12997 | 12997 | 100 | 100 | 100 | 100 | 104.4626 | 100
7 | Gewelven/Structuur | 2016-05-30 08:00 | 2016-06-07 17:00 | 7d |  | 0 | 5432 | 0 | 0 | 5432 | 2016-05-27 08:00 | 7d | 5432 | 0 | 0 | 0 | 0 | 5432 | 0 | 100% | Finished | 5432 | 5432 | 100 | 100 | 100 | 100 | 100 | 100
8 | Uitbranden GEWA | 2016-05-30 08:00 | 2016-05-30 17:00 | 1d |  | 0 | 533 | 0 | 0 | 533 | 2016-05-27 08:00 | 1d | 533 | 0 | 0 | 819 | 0 | 1352 | 0 | 100% | Finished | 533 | 533 | 100 | 100 | 100 | 100 | 253.6585 | 100
9 | Isolatie | 2016-06-08 08:00 | 2016-06-14 17:00 | 5d |  | 0 | 1324 | 0 | 0 | 1324 | 2016-06-07 08:00 | 6d | 1324 | 0 | 0 | 292 | 0 | 1616 | 0 | 100% | Finished | 1324 | 1324 | 100 | 120 | 100 | 100 | 122.0544 | 100
10 | Parament | 2016-06-15 08:00 | 2016-08-02 17:00 | 35d |  | 0 | 19883 | 0 | 0 | 19883 | 2016-06-15 08:00 | 33d | 19883 | 0 | 0 | 464 | 0 | 20347 | 0 | 100% | Finished | 19883 | 19883 | 100 | 94.2857 | 100 | 100 | 102.3337 | 100
11 | Ytong | 2016-08-03 08:00 | 2016-08-08 17:00 | 4d |  | 0 | 2879 | 0 | 0 | 2879 | 2016-08-01 08:00 | 5d | 2879 | 0 | 0 | 7 | 0 | 2886 | 0 | 100% | Finished | 2879 | 2879 | 100 | 125 | 100 | 100 | 100.2431 | 100
12 | Dorpels | 2016-08-09 08:00 | 2016-08-11 17:00 | 3d |  | 0 | 1934 | 0 | 0 | 1934 | 2016-08-08 08:00 | 2d | 1934 | 0 | 0 | -637 | 0 | 1297 | 0 | 100% | Finished | 1934 | 1934 | 100 | 66.6667 | 100 | 100 | 67.0631 | 100
13 | Voegwerk | 2016-08-09 08:00 | 2016-08-16 17:00 | 6d |  | 0 | 1493 | 0 | 0 | 1493 | 2016-08-08 08:00 | 7d | 1493 | 0 | 0 | 568 | 0 | 2061 | 0 | 100% | Finished | 1493 | 1493 | 100 | 116.6667 | 100 | 100 | 138.0442 | 100
14 | Stelling | 2016-08-17 08:00 | 2016-08-22 17:00 | 4d |  | 0 | 1392 | 0 | 0 | 1392 | 2016-08-17 08:00 | 9d | 1392 | 0 | 0 | 1258 | 0 | 2650 | 0 | 100% | Finished | 1392 | 1392 | 100 | 225 | 100 | 100 | 190.3736 | 100
15 | Crepi+Isolatie | 2016-08-23 08:00 | 2016-08-24 17:00 | 2d |  | 0 | 334 | 0 | 0 | 334 | 2016-08-30 08:00 | 1d | 334 | 0 | 0 | -234 | 0 | 100 | 0 | 100% | Finished | 334 | 334 | 100 | 50 | 100 | 100 | 29.9401 | 100
16 | Karweien | 2016-08-25 08:00 | 2016-08-25 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-08-31 08:00 | 4d | 200 | 0 | 0 | 976 | 0 | 1176 | 0 | 100% | Finished | 200 | 200 | 100 | 400 | 100 | 100 | 588 | 100
52 | Dakwerken | 2016-08-26 08:00 | 2016-12-05 17:00 | 72d |  |  | 39200 |  |  | 39200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 13456
17 | Daktimmer traditioneel/prefabkap | 2016-08-26 08:00 | 2016-10-13 17:00 | 35d |  | 0 | 13456 | 0 | 0 | 13456 |  | 0 | 0 | 13456 | 35d | 0 | 0 | 0 | 13456 | 0% | Not Started | 0 | 13456 | 100 |  | 0 | 100 |  | 0
18 | Dakdekken | 2016-10-14 08:00 | 2016-11-10 17:00 | 20d |  | 0 | 15873 | 0 | 0 | 15873 |  | 0 | 0 | 15873 | 20d | 0 | 0 | 0 | 15873 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Goten & Afleiders | 2016-11-11 08:00 | 2016-11-15 17:00 | 3d |  | 0 | 1282 | 0 | 0 | 1282 |  | 0 | 0 | 1282 | 3d | 0 | 0 | 0 | 1282 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Oversteken/Gevelbekleding | 2016-11-11 08:00 | 2016-12-02 17:00 | 16d |  | 0 | 6265 | 0 | 0 | 6265 |  | 0 | 0 | 6265 | 16d | 0 | 0 | 0 | 6265 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Dakvlakramen | 2016-12-05 08:00 | 2016-12-05 17:00 | 1d |  | 0 | 2324 | 0 | 0 | 2324 |  | 0 | 0 | 2324 | 1d | 0 | 0 | 0 | 2324 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Buitenschrijnwerk | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  |  | 23493 |  |  | 23493 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Buitenschrijnwerk plaatsen | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  | 0 | 23493 | 0 | 0 | 23493 |  | 0 | 0 | 23493 | 15d | 0 | 0 | 0 | 23493 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Binnenafwerking | 2017-01-23 08:00 | 2017-04-05 17:00 | 53d |  |  | 30237 |  |  | 30237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | Plakwerken | 2017-01-23 08:00 | 2017-02-07 17:00 | 12d |  | 0 | 9564 | 0 | 0 | 9564 |  | 0 | 0 | 9564 | 12d | 0 | 0 | 0 | 9564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Chapes/uitvullingen | 2017-02-08 08:00 | 2017-02-14 17:00 | 5d |  | 0 | 2432 | 0 | 0 | 2432 |  | 0 | 0 | 2432 | 5d | 0 | 0 | 0 | 2432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Vloerisolatie | 2017-02-16 08:00 | 2017-03-01 17:00 | 10d |  | 0 | 2739 | 0 | 0 | 2739 |  | 0 | 0 | 2739 | 10d | 0 | 0 | 0 | 2739 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Tegelwerken | 2017-03-02 08:00 | 2017-03-10 17:00 | 7d |  | 0 | 3633 | 0 | 0 | 3633 |  | 0 | 0 | 3633 | 7d | 0 | 0 | 0 | 3633 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Voorbereiding+Gyplat | 2017-03-13 08:00 | 2017-03-22 17:00 | 8d |  | 0 | 2792 | 0 | 0 | 2792 |  | 0 | 0 | 2792 | 8d | 0 | 0 | 0 | 2792 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-13 08:00 | 2017-03-16 17:00 | 4d |  | 0 | 837 | 0 | 0 | 837 |  | 0 | 0 | 837 | 4d | 0 | 0 | 0 | 837 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Binnendeuren/Uitbekleding | 2017-03-23 08:00 | 2017-03-28 17:00 | 4d |  | 0 | 1021 | 0 | 0 | 1021 |  | 0 | 0 | 1021 | 4d | 0 | 0 | 0 | 1021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Trap | 2017-03-23 08:00 | 2017-03-30 17:00 | 6d |  | 0 | 1650 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 6d | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-05 17:00 | 10d |  | 0 | 5569 | 0 | 0 | 5569 |  | 0 | 0 | 5569 | 10d | 0 | 0 | 0 | 5569 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Technieken | 2016-12-27 08:00 | 2017-04-07 17:00 | 74d |  |  | 38827 |  |  | 38827 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | UZL | 2016-12-27 08:00 | 2016-12-29 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Betonplexplaten | 2016-12-27 08:00 | 2016-12-27 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Slijpen technieken/Boringen | 2016-12-30 08:00 | 2017-01-04 17:00 | 4d |  | 0 | 1296 | 0 | 0 | 1296 |  | 0 | 0 | 1296 | 4d | 0 | 0 | 0 | 1296 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bad &amp; douche | 2017-02-15 08:00 | 2017-02-15 17:00 | 1d |  | 0 | 320 | 0 | 0 | 320 |  | 0 | 0 | 320 | 1d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Leidingen vent | 2017-01-05 08:00 | 2017-01-09 17:00 | 3d |  | 0 | 2580 | 0 | 0 | 2580 |  | 0 | 0 | 2580 | 3d | 0 | 0 | 0 | 2580 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Leidingen san/WP/CV | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d |  | 0 | 3711 | 0 | 0 | 3711 |  | 0 | 0 | 3711 | 5d | 0 | 0 | 0 | 3711 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken ventilatie | 2017-03-13 08:00 | 2017-03-14 17:00 | 2d |  | 0 | 2317 | 0 | 0 | 2317 |  | 0 | 0 | 2317 | 2d | 0 | 0 | 0 | 2317 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerken sanitair | 2017-03-15 08:00 | 2017-03-17 17:00 | 3d |  | 0 | 6472 | 0 | 0 | 6472 |  | 0 | 0 | 6472 | 3d | 0 | 0 | 0 | 6472 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Afwerken CV/WP | 2017-03-20 08:00 | 2017-03-21 17:00 | 2d |  | 0 | 5903 | 0 | 0 | 5903 |  | 0 | 0 | 5903 | 2d | 0 | 0 | 0 | 5903 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Leidingen electro | 2017-01-17 08:00 | 2017-01-20 17:00 | 4d |  | 0 | 2701 | 0 | 0 | 2701 |  | 0 | 0 | 2701 | 4d | 0 | 0 | 0 | 2701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afwerken electro | 2017-03-22 08:00 | 2017-03-27 17:00 | 4d |  | 0 | 3807 | 0 | 0 | 3807 |  | 0 | 0 | 3807 | 4d | 0 | 0 | 0 | 3807 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Zonneboiler | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 455 | 0 | 0 | 455 |  | 0 | 0 | 455 | 1d | 0 | 0 | 0 | 455 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | PV panelen | 2017-03-28 08:00 | 2017-03-30 17:00 | 3d |  | 0 | 4950 | 0 | 0 | 4950 |  | 0 | 0 | 4950 | 3d | 0 | 0 | 0 | 4950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Verlichting | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Karweien | 2017-03-28 08:00 | 2017-04-07 17:00 | 9d |  | 0 | 3227 | 0 | 0 | 3227 |  | 0 | 0 | 3227 | 9d | 0 | 0 | 0 | 3227 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Omgevingswerken | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  |  | 1406 |  |  | 1406 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Opkuis werf (afvoeren puin & afval) | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  | 0 | 1406 | 0 | 0 | 1406 |  | 0 | 0 | 1406 | 5d | 0 | 0 | 0 | 1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Restklasse | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  |  | 13218 |  |  | 13218 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | Rest | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  | 0 | 13218 | 0 | 0 | 13218 |  | 0 | 0 | 13218 | 31d | 0 | 0 | 0 | 13218 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-12-06 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (4) | 2016-03-07 08:00 | 2017-05-29 17:00 | 321d |  |  | 218366 |  |  | 218366 |  | 196d | [5 empty] | 115724.78 |  | 50.92% |  | 111185 | 111185
49 | Voorbereiding | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  |  | 11265 |  |  | 11265 |  | 10d | [5 empty] | 12992 |  | 100% |  | 11265 | 11265
1 | Werfinrichting | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 3642 | 0 | 0 | 3642 | 2016-03-07 08:00 | 6d | 3642 | 0 | 0 | 1721 | 0 | 5363 | 0 | 100% | Finished | 3642 | 3642 | 100 | 200 | 100 | 100 | 147.2543 | 100
2 | Transportkosten | 2016-03-07 08:00 | 2016-03-15 17:00 | 7d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-07 08:00 | 8d | 2202 | 0 | 0 | -56 | 0 | 2146 | 0 | 100% | Finished | 2202 | 2202 | 100 | 114.2857 | 100 | 100 | 97.4569 | 100
3 | Rijtijden ploegen | 2016-03-07 08:00 | 2016-03-16 17:00 | 8d |  | 0 | 2190 | 0 | 0 | 2190 | 2016-03-07 08:00 | 7d | 2190 | 0 | 0 | -154 | 0 | 2036 | 0 | 100% | Finished | 2190 | 2190 | 100 | 87.5 | 100 | 100 | 92.968 | 100
4 | Studiekosten | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  | 0 | 3231 | 0 | 0 | 3231 | 2016-03-07 08:00 | 10d | 3231 | 0 | 0 | 216 | 0 | 3447 | 0 | 100% | Finished | 3231 | 3231 | 100 | 90.9091 | 100 | 100 | 106.6852 | 100
50 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  |  | 12319 |  |  | 12319 |  | 30d | [5 empty] | 12361 |  | 100% |  | 12319 | 12319
5 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  | 0 | 12319 | 0 | 0 | 12319 | 2016-03-21 08:00 | 30d | 12319 | 0 | 0 | 42 | 0 | 12361 | 0 | 100% | Finished | 12319 | 12319 | 100 | 100 | 100 | 100 | 100.3409 | 100
51 | Ruwbouw | 2016-05-03 08:00 | 2016-08-25 17:00 | 83d |  |  | 48401 |  |  | 48401 |  | 91d | [5 empty] | 52494 |  | 100% |  | 48401 | 48401
6 | Gewa/metselwerk | 2016-05-03 08:00 | 2016-05-27 17:00 | 19d |  | 0 | 12997 | 0 | 0 | 12997 | 2016-05-02 08:00 | 19d | 12997 | 0 | 0 | 580 | 0 | 13577 | 0 | 100% | Finished | 12997 | 12997 | 100 | 100 | 100 | 100 | 104.4626 | 100
7 | Gewelven/Structuur | 2016-05-30 08:00 | 2016-06-07 17:00 | 7d |  | 0 | 5432 | 0 | 0 | 5432 | 2016-05-27 08:00 | 7d | 5432 | 0 | 0 | 0 | 0 | 5432 | 0 | 100% | Finished | 5432 | 5432 | 100 | 100 | 100 | 100 | 100 | 100
8 | Uitbranden GEWA | 2016-05-30 08:00 | 2016-05-30 17:00 | 1d |  | 0 | 533 | 0 | 0 | 533 | 2016-05-27 08:00 | 1d | 533 | 0 | 0 | 819 | 0 | 1352 | 0 | 100% | Finished | 533 | 533 | 100 | 100 | 100 | 100 | 253.6585 | 100
9 | Isolatie | 2016-06-08 08:00 | 2016-06-14 17:00 | 5d |  | 0 | 1324 | 0 | 0 | 1324 | 2016-06-07 08:00 | 6d | 1324 | 0 | 0 | 292 | 0 | 1616 | 0 | 100% | Finished | 1324 | 1324 | 100 | 120 | 100 | 100 | 122.0544 | 100
10 | Parament | 2016-06-15 08:00 | 2016-08-02 17:00 | 35d |  | 0 | 19883 | 0 | 0 | 19883 | 2016-06-15 08:00 | 33d | 19883 | 0 | 0 | 464 | 0 | 20347 | 0 | 100% | Finished | 19883 | 19883 | 100 | 94.2857 | 100 | 100 | 102.3337 | 100
11 | Ytong | 2016-08-03 08:00 | 2016-08-08 17:00 | 4d |  | 0 | 2879 | 0 | 0 | 2879 | 2016-08-01 08:00 | 5d | 2879 | 0 | 0 | 7 | 0 | 2886 | 0 | 100% | Finished | 2879 | 2879 | 100 | 125 | 100 | 100 | 100.2431 | 100
12 | Dorpels | 2016-08-09 08:00 | 2016-08-11 17:00 | 3d |  | 0 | 1934 | 0 | 0 | 1934 | 2016-08-08 08:00 | 2d | 1934 | 0 | 0 | -637 | 0 | 1297 | 0 | 100% | Finished | 1934 | 1934 | 100 | 66.6667 | 100 | 100 | 67.0631 | 100
13 | Voegwerk | 2016-08-09 08:00 | 2016-08-16 17:00 | 6d |  | 0 | 1493 | 0 | 0 | 1493 | 2016-08-08 08:00 | 7d | 1493 | 0 | 0 | 568 | 0 | 2061 | 0 | 100% | Finished | 1493 | 1493 | 100 | 116.6667 | 100 | 100 | 138.0442 | 100
14 | Stelling | 2016-08-17 08:00 | 2016-08-22 17:00 | 4d |  | 0 | 1392 | 0 | 0 | 1392 | 2016-08-17 08:00 | 9d | 1392 | 0 | 0 | 1258 | 0 | 2650 | 0 | 100% | Finished | 1392 | 1392 | 100 | 225 | 100 | 100 | 190.3736 | 100
15 | Crepi+Isolatie | 2016-08-23 08:00 | 2016-08-24 17:00 | 2d |  | 0 | 334 | 0 | 0 | 334 | 2016-08-30 08:00 | 1d | 334 | 0 | 0 | -234 | 0 | 100 | 0 | 100% | Finished | 334 | 334 | 100 | 50 | 100 | 100 | 29.9401 | 100
16 | Karweien | 2016-08-25 08:00 | 2016-08-25 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-08-31 08:00 | 4d | 200 | 0 | 0 | 976 | 0 | 1176 | 0 | 100% | Finished | 200 | 200 | 100 | 400 | 100 | 100 | 588 | 100
52 | Dakwerken | 2016-08-26 08:00 | 2016-12-05 17:00 | 72d |  |  | 39200 |  |  | 39200 |  | 65d | [5 empty] | 37877.78 |  | 100% |  | 39200 | 39200
17 | Daktimmer traditioneel/prefabkap | 2016-08-26 08:00 | 2016-10-13 17:00 | 35d |  | 0 | 13456 | 0 | 0 | 13456 | 2016-09-06 08:00 | 34d | 13456 | 0 | 0 | -809.22 | 0 | 12646.78 | 0 | 100% | Finished | 13456 | 13456 | 100 | 97.1429 | 100 | 100 | 93.9862 | 100
18 | Dakdekken | 2016-10-14 08:00 | 2016-11-10 17:00 | 20d |  | 0 | 15873 | 0 | 0 | 15873 | 2016-10-24 08:00 | 18d | 15873 | 0 | 0 | -584 | 0 | 15289 | 0 | 100% | Finished | 15873 | 15873 | 100 | 90 | 100 | 100 | 96.3208 | 100
19 | Goten & Afleiders | 2016-11-11 08:00 | 2016-11-15 17:00 | 3d |  | 0 | 1282 | 0 | 0 | 1282 | 2016-11-17 08:00 | 3d | 1282 | 0 | 0 | 52 | 0 | 1334 | 0 | 100% | Finished | 1282 | 1282 | 100 | 100 | 100 | 100 | 104.0562 | 100
20 | Oversteken/Gevelbekleding | 2016-11-11 08:00 | 2016-12-02 17:00 | 16d |  | 0 | 6265 | 0 | 0 | 6265 | 2016-11-17 08:00 | 12d | 6265 | 0 | 0 | -178 | 0 | 6087 | 0 | 100% | Finished | 6265 | 6265 | 100 | 75 | 100 | 100 | 97.1588 | 100
21 | Dakvlakramen | 2016-12-05 08:00 | 2016-12-05 17:00 | 1d |  | 0 | 2324 | 0 | 0 | 2324 | 2016-12-05 08:00 | 1d | 2324 | 0 | 0 | 197 | 0 | 2521 | 0 | 100% | Finished | 2324 | 2324 | 100 | 100 | 100 | 100 | 108.4768 | 100
53 | Buitenschrijnwerk | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  |  | 23493 |  |  | 23493 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Buitenschrijnwerk plaatsen | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  | 0 | 23493 | 0 | 0 | 23493 |  | 0 | 0 | 23493 | 15d | 0 | 0 | 0 | 23493 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Binnenafwerking | 2017-01-23 08:00 | 2017-04-05 17:00 | 53d |  |  | 30237 |  |  | 30237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | Plakwerken | 2017-01-23 08:00 | 2017-02-07 17:00 | 12d |  | 0 | 9564 | 0 | 0 | 9564 |  | 0 | 0 | 9564 | 12d | 0 | 0 | 0 | 9564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Chapes/uitvullingen | 2017-02-08 08:00 | 2017-02-14 17:00 | 5d |  | 0 | 2432 | 0 | 0 | 2432 |  | 0 | 0 | 2432 | 5d | 0 | 0 | 0 | 2432 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Vloerisolatie | 2017-02-16 08:00 | 2017-03-01 17:00 | 10d |  | 0 | 2739 | 0 | 0 | 2739 |  | 0 | 0 | 2739 | 10d | 0 | 0 | 0 | 2739 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Tegelwerken | 2017-03-02 08:00 | 2017-03-10 17:00 | 7d |  | 0 | 3633 | 0 | 0 | 3633 |  | 0 | 0 | 3633 | 7d | 0 | 0 | 0 | 3633 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Voorbereiding+Gyplat | 2017-03-13 08:00 | 2017-03-22 17:00 | 8d |  | 0 | 2792 | 0 | 0 | 2792 |  | 0 | 0 | 2792 | 8d | 0 | 0 | 0 | 2792 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-13 08:00 | 2017-03-16 17:00 | 4d |  | 0 | 837 | 0 | 0 | 837 |  | 0 | 0 | 837 | 4d | 0 | 0 | 0 | 837 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Binnendeuren/Uitbekleding | 2017-03-23 08:00 | 2017-03-28 17:00 | 4d |  | 0 | 1021 | 0 | 0 | 1021 |  | 0 | 0 | 1021 | 4d | 0 | 0 | 0 | 1021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Trap | 2017-03-23 08:00 | 2017-03-30 17:00 | 6d |  | 0 | 1650 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 6d | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-05 17:00 | 10d |  | 0 | 5569 | 0 | 0 | 5569 |  | 0 | 0 | 5569 | 10d | 0 | 0 | 0 | 5569 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Technieken | 2016-12-27 08:00 | 2017-04-07 17:00 | 74d |  |  | 38827 |  |  | 38827 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | UZL | 2016-12-27 08:00 | 2016-12-29 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Betonplexplaten | 2016-12-27 08:00 | 2016-12-27 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Slijpen technieken/Boringen | 2016-12-30 08:00 | 2017-01-04 17:00 | 4d |  | 0 | 1296 | 0 | 0 | 1296 |  | 0 | 0 | 1296 | 4d | 0 | 0 | 0 | 1296 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Bad &amp; douche | 2017-02-15 08:00 | 2017-02-15 17:00 | 1d |  | 0 | 320 | 0 | 0 | 320 |  | 0 | 0 | 320 | 1d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Leidingen vent | 2017-01-05 08:00 | 2017-01-09 17:00 | 3d |  | 0 | 2580 | 0 | 0 | 2580 |  | 0 | 0 | 2580 | 3d | 0 | 0 | 0 | 2580 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Leidingen san/WP/CV | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d |  | 0 | 3711 | 0 | 0 | 3711 |  | 0 | 0 | 3711 | 5d | 0 | 0 | 0 | 3711 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Afwerken ventilatie | 2017-03-13 08:00 | 2017-03-14 17:00 | 2d |  | 0 | 2317 | 0 | 0 | 2317 |  | 0 | 0 | 2317 | 2d | 0 | 0 | 0 | 2317 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Afwerken sanitair | 2017-03-15 08:00 | 2017-03-17 17:00 | 3d |  | 0 | 6472 | 0 | 0 | 6472 |  | 0 | 0 | 6472 | 3d | 0 | 0 | 0 | 6472 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Afwerken CV/WP | 2017-03-20 08:00 | 2017-03-21 17:00 | 2d |  | 0 | 5903 | 0 | 0 | 5903 |  | 0 | 0 | 5903 | 2d | 0 | 0 | 0 | 5903 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Leidingen electro | 2017-01-17 08:00 | 2017-01-20 17:00 | 4d |  | 0 | 2701 | 0 | 0 | 2701 |  | 0 | 0 | 2701 | 4d | 0 | 0 | 0 | 2701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afwerken electro | 2017-03-22 08:00 | 2017-03-27 17:00 | 4d |  | 0 | 3807 | 0 | 0 | 3807 |  | 0 | 0 | 3807 | 4d | 0 | 0 | 0 | 3807 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Zonneboiler | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 455 | 0 | 0 | 455 |  | 0 | 0 | 455 | 1d | 0 | 0 | 0 | 455 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | PV panelen | 2017-03-28 08:00 | 2017-03-30 17:00 | 3d |  | 0 | 4950 | 0 | 0 | 4950 |  | 0 | 0 | 4950 | 3d | 0 | 0 | 0 | 4950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Verlichting | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 1d | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Karweien | 2017-03-28 08:00 | 2017-04-07 17:00 | 9d |  | 0 | 3227 | 0 | 0 | 3227 |  | 0 | 0 | 3227 | 9d | 0 | 0 | 0 | 3227 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Omgevingswerken | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  |  | 1406 |  |  | 1406 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Opkuis werf (afvoeren puin & afval) | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  | 0 | 1406 | 0 | 0 | 1406 |  | 0 | 0 | 1406 | 5d | 0 | 0 | 0 | 1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Restklasse | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  |  | 13218 |  |  | 13218 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | Rest | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  | 0 | 13218 | 0 | 0 | 13218 |  | 0 | 0 | 13218 | 31d | 0 | 0 | 0 | 13218 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2017-04-14 08:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (4) | 2016-03-07 08:00 | 2017-05-29 17:00 | 321d |  |  | 218366 |  |  | 218366 |  | 289d | [5 empty] | 208803.78 |  | 93.95% |  | 205148 | 205148
49 | Voorbereiding | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  |  | 11265 |  |  | 11265 |  | 10d | [5 empty] | 12992 |  | 100% |  | 11265 | 11265
1 | Werfinrichting | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 3642 | 0 | 0 | 3642 | 2016-03-07 08:00 | 6d | 3642 | 0 | 0 | 1721 | 0 | 5363 | 0 | 100% | Finished | 3642 | 3642 | 100 | 200 | 100 | 100 | 147.2543 | 100
2 | Transportkosten | 2016-03-07 08:00 | 2016-03-15 17:00 | 7d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-07 08:00 | 8d | 2202 | 0 | 0 | -56 | 0 | 2146 | 0 | 100% | Finished | 2202 | 2202 | 100 | 114.2857 | 100 | 100 | 97.4569 | 100
3 | Rijtijden ploegen | 2016-03-07 08:00 | 2016-03-16 17:00 | 8d |  | 0 | 2190 | 0 | 0 | 2190 | 2016-03-07 08:00 | 7d | 2190 | 0 | 0 | -154 | 0 | 2036 | 0 | 100% | Finished | 2190 | 2190 | 100 | 87.5 | 100 | 100 | 92.968 | 100
4 | Studiekosten | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  | 0 | 3231 | 0 | 0 | 3231 | 2016-03-07 08:00 | 10d | 3231 | 0 | 0 | 216 | 0 | 3447 | 0 | 100% | Finished | 3231 | 3231 | 100 | 90.9091 | 100 | 100 | 106.6852 | 100
50 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  |  | 12319 |  |  | 12319 |  | 30d | [5 empty] | 12361 |  | 100% |  | 12319 | 12319
5 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  | 0 | 12319 | 0 | 0 | 12319 | 2016-03-21 08:00 | 30d | 12319 | 0 | 0 | 42 | 0 | 12361 | 0 | 100% | Finished | 12319 | 12319 | 100 | 100 | 100 | 100 | 100.3409 | 100
51 | Ruwbouw | 2016-05-03 08:00 | 2016-08-25 17:00 | 83d |  |  | 48401 |  |  | 48401 |  | 91d | [5 empty] | 52494 |  | 100% |  | 48401 | 48401
6 | Gewa/metselwerk | 2016-05-03 08:00 | 2016-05-27 17:00 | 19d |  | 0 | 12997 | 0 | 0 | 12997 | 2016-05-02 08:00 | 19d | 12997 | 0 | 0 | 580 | 0 | 13577 | 0 | 100% | Finished | 12997 | 12997 | 100 | 100 | 100 | 100 | 104.4626 | 100
7 | Gewelven/Structuur | 2016-05-30 08:00 | 2016-06-07 17:00 | 7d |  | 0 | 5432 | 0 | 0 | 5432 | 2016-05-27 08:00 | 7d | 5432 | 0 | 0 | 0 | 0 | 5432 | 0 | 100% | Finished | 5432 | 5432 | 100 | 100 | 100 | 100 | 100 | 100
8 | Uitbranden GEWA | 2016-05-30 08:00 | 2016-05-30 17:00 | 1d |  | 0 | 533 | 0 | 0 | 533 | 2016-05-27 08:00 | 1d | 533 | 0 | 0 | 819 | 0 | 1352 | 0 | 100% | Finished | 533 | 533 | 100 | 100 | 100 | 100 | 253.6585 | 100
9 | Isolatie | 2016-06-08 08:00 | 2016-06-14 17:00 | 5d |  | 0 | 1324 | 0 | 0 | 1324 | 2016-06-07 08:00 | 6d | 1324 | 0 | 0 | 292 | 0 | 1616 | 0 | 100% | Finished | 1324 | 1324 | 100 | 120 | 100 | 100 | 122.0544 | 100
10 | Parament | 2016-06-15 08:00 | 2016-08-02 17:00 | 35d |  | 0 | 19883 | 0 | 0 | 19883 | 2016-06-15 08:00 | 33d | 19883 | 0 | 0 | 464 | 0 | 20347 | 0 | 100% | Finished | 19883 | 19883 | 100 | 94.2857 | 100 | 100 | 102.3337 | 100
11 | Ytong | 2016-08-03 08:00 | 2016-08-08 17:00 | 4d |  | 0 | 2879 | 0 | 0 | 2879 | 2016-08-01 08:00 | 5d | 2879 | 0 | 0 | 7 | 0 | 2886 | 0 | 100% | Finished | 2879 | 2879 | 100 | 125 | 100 | 100 | 100.2431 | 100
12 | Dorpels | 2016-08-09 08:00 | 2016-08-11 17:00 | 3d |  | 0 | 1934 | 0 | 0 | 1934 | 2016-08-08 08:00 | 2d | 1934 | 0 | 0 | -637 | 0 | 1297 | 0 | 100% | Finished | 1934 | 1934 | 100 | 66.6667 | 100 | 100 | 67.0631 | 100
13 | Voegwerk | 2016-08-09 08:00 | 2016-08-16 17:00 | 6d |  | 0 | 1493 | 0 | 0 | 1493 | 2016-08-08 08:00 | 7d | 1493 | 0 | 0 | 568 | 0 | 2061 | 0 | 100% | Finished | 1493 | 1493 | 100 | 116.6667 | 100 | 100 | 138.0442 | 100
14 | Stelling | 2016-08-17 08:00 | 2016-08-22 17:00 | 4d |  | 0 | 1392 | 0 | 0 | 1392 | 2016-08-17 08:00 | 9d | 1392 | 0 | 0 | 1258 | 0 | 2650 | 0 | 100% | Finished | 1392 | 1392 | 100 | 225 | 100 | 100 | 190.3736 | 100
15 | Crepi+Isolatie | 2016-08-23 08:00 | 2016-08-24 17:00 | 2d |  | 0 | 334 | 0 | 0 | 334 | 2016-08-30 08:00 | 1d | 334 | 0 | 0 | -234 | 0 | 100 | 0 | 100% | Finished | 334 | 334 | 100 | 50 | 100 | 100 | 29.9401 | 100
16 | Karweien | 2016-08-25 08:00 | 2016-08-25 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-08-31 08:00 | 4d | 200 | 0 | 0 | 976 | 0 | 1176 | 0 | 100% | Finished | 200 | 200 | 100 | 400 | 100 | 100 | 588 | 100
52 | Dakwerken | 2016-08-26 08:00 | 2016-12-05 17:00 | 72d |  |  | 39200 |  |  | 39200 |  | 65d | [5 empty] | 37877.78 |  | 100% |  | 39200 | 39200
17 | Daktimmer traditioneel/prefabkap | 2016-08-26 08:00 | 2016-10-13 17:00 | 35d |  | 0 | 13456 | 0 | 0 | 13456 | 2016-09-06 08:00 | 34d | 13456 | 0 | 0 | -809.22 | 0 | 12646.78 | 0 | 100% | Finished | 13456 | 13456 | 100 | 97.1429 | 100 | 100 | 93.9862 | 100
18 | Dakdekken | 2016-10-14 08:00 | 2016-11-10 17:00 | 20d |  | 0 | 15873 | 0 | 0 | 15873 | 2016-10-24 08:00 | 18d | 15873 | 0 | 0 | -584 | 0 | 15289 | 0 | 100% | Finished | 15873 | 15873 | 100 | 90 | 100 | 100 | 96.3208 | 100
19 | Goten & Afleiders | 2016-11-11 08:00 | 2016-11-15 17:00 | 3d |  | 0 | 1282 | 0 | 0 | 1282 | 2016-11-17 08:00 | 3d | 1282 | 0 | 0 | 52 | 0 | 1334 | 0 | 100% | Finished | 1282 | 1282 | 100 | 100 | 100 | 100 | 104.0562 | 100
20 | Oversteken/Gevelbekleding | 2016-11-11 08:00 | 2016-12-02 17:00 | 16d |  | 0 | 6265 | 0 | 0 | 6265 | 2016-11-17 08:00 | 12d | 6265 | 0 | 0 | -178 | 0 | 6087 | 0 | 100% | Finished | 6265 | 6265 | 100 | 75 | 100 | 100 | 97.1588 | 100
21 | Dakvlakramen | 2016-12-05 08:00 | 2016-12-05 17:00 | 1d |  | 0 | 2324 | 0 | 0 | 2324 | 2016-12-05 08:00 | 1d | 2324 | 0 | 0 | 197 | 0 | 2521 | 0 | 100% | Finished | 2324 | 2324 | 100 | 100 | 100 | 100 | 108.4768 | 100
53 | Buitenschrijnwerk | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  |  | 23493 |  |  | 23493 |  | 16d | [5 empty] | 23840 |  | 100% |  | 23493 | 23493
22 | Buitenschrijnwerk plaatsen | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  | 0 | 23493 | 0 | 0 | 23493 | 2016-12-06 08:00 | 16d | 23493 | 0 | 0 | 347 | 0 | 23840 | 0 | 100% | Finished | 23493 | 23493 | 100 | 106.6667 | 100 | 100 | 101.477 | 100
54 | Binnenafwerking | 2017-01-23 08:00 | 2017-04-05 17:00 | 53d |  |  | 30237 |  |  | 30237 |  | 53d | [5 empty] | 31324 |  | 100% |  | 30237 | 30237
23 | Plakwerken | 2017-01-23 08:00 | 2017-02-07 17:00 | 12d |  | 0 | 9564 | 0 | 0 | 9564 | 2017-01-26 08:00 | 12d | 9564 | 0 | 0 | 10 | 0 | 9574 | 0 | 100% | Finished | 9564 | 9564 | 100 | 100 | 100 | 100 | 100.1046 | 100
24 | Chapes/uitvullingen | 2017-02-08 08:00 | 2017-02-14 17:00 | 5d |  | 0 | 2432 | 0 | 0 | 2432 | 2017-02-13 08:00 | 5d | 2432 | 0 | 0 | 1 | 0 | 2433 | 0 | 100% | Finished | 2432 | 2432 | 100 | 100 | 100 | 100 | 100.0411 | 100
25 | Vloerisolatie | 2017-02-16 08:00 | 2017-03-01 17:00 | 10d |  | 0 | 2739 | 0 | 0 | 2739 | 2017-02-21 08:00 | 10d | 2739 | 0 | 0 | 2 | 0 | 2741 | 0 | 100% | Finished | 2739 | 2739 | 100 | 100 | 100 | 100 | 100.073 | 100
26 | Tegelwerken | 2017-03-02 08:00 | 2017-03-10 17:00 | 7d |  | 0 | 3633 | 0 | 0 | 3633 | 2017-03-07 08:00 | 7d | 3633 | 0 | 0 | 705 | 0 | 4338 | 0 | 100% | Finished | 3633 | 3633 | 100 | 100 | 100 | 100 | 119.4055 | 100
27 | Voorbereiding+Gyplat | 2017-03-13 08:00 | 2017-03-22 17:00 | 8d |  | 0 | 2792 | 0 | 0 | 2792 | 2017-03-16 08:00 | 6d | 2792 | 0 | 0 | -1102 | 0 | 1690 | 0 | 100% | Finished | 2792 | 2792 | 100 | 75 | 100 | 100 | 60.5301 | 100
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-13 08:00 | 2017-03-16 17:00 | 4d |  | 0 | 837 | 0 | 0 | 837 | 2017-03-16 08:00 | 4d | 837 | 0 | 0 | 258 | 0 | 1095 | 0 | 100% | Finished | 837 | 837 | 100 | 100 | 100 | 100 | 130.8244 | 100
29 | Binnendeuren/Uitbekleding | 2017-03-23 08:00 | 2017-03-28 17:00 | 4d |  | 0 | 1021 | 0 | 0 | 1021 | 2017-03-24 08:00 | 3d | 1021 | 0 | 0 | -133 | 0 | 888 | 0 | 100% | Finished | 1021 | 1021 | 100 | 75 | 100 | 100 | 86.9736 | 100
30 | Trap | 2017-03-23 08:00 | 2017-03-30 17:00 | 6d |  | 0 | 1650 | 0 | 0 | 1650 | 2017-03-24 08:00 | 6d | 1650 | 0 | 0 | 68 | 0 | 1718 | 0 | 100% | Finished | 1650 | 1650 | 100 | 100 | 100 | 100 | 104.1212 | 100
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-05 17:00 | 10d |  | 0 | 5569 | 0 | 0 | 5569 | 2017-03-24 08:00 | 12d | 5569 | 0 | 0 | 1278 | 0 | 6847 | 0 | 100% | Finished | 5569 | 5569 | 100 | 120 | 100 | 100 | 122.9485 | 100
55 | Technieken | 2016-12-27 08:00 | 2017-04-07 17:00 | 74d |  |  | 38827 |  |  | 38827 |  | 72d | [5 empty] | 36416 |  | 100% |  | 38827 | 38827
32 | UZL | 2016-12-27 08:00 | 2016-12-29 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-12-28 08:00 | 3d | 888 | 0 | 0 | -56 | 0 | 832 | 0 | 100% | Finished | 888 | 888 | 100 | 100 | 100 | 100 | 93.6937 | 100
33 | Betonplexplaten | 2016-12-27 08:00 | 2016-12-27 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-12-28 08:00 | 1d | 100 | 0 | 0 | 149 | 0 | 249 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 249 | 100
34 | Slijpen technieken/Boringen | 2016-12-30 08:00 | 2017-01-04 17:00 | 4d |  | 0 | 1296 | 0 | 0 | 1296 | 2017-01-02 08:00 | 7d | 1296 | 0 | 0 | 603 | 0 | 1899 | 0 | 100% | Finished | 1296 | 1296 | 100 | 175 | 100 | 100 | 146.5278 | 100
35 | Bad &amp; douche | 2017-02-15 08:00 | 2017-02-15 17:00 | 1d |  | 0 | 320 | 0 | 0 | 320 | 2017-02-20 08:00 | 1d | 320 | 0 | 0 | 90 | 0 | 410 | 0 | 100% | Finished | 320 | 320 | 100 | 100 | 100 | 100 | 128.125 | 100
36 | Leidingen vent | 2017-01-05 08:00 | 2017-01-09 17:00 | 3d |  | 0 | 2580 | 0 | 0 | 2580 | 2017-01-11 08:00 | 2d | 2580 | 0 | 0 | -1280 | 0 | 1300 | 0 | 100% | Finished | 2580 | 2580 | 100 | 66.6667 | 100 | 100 | 50.3876 | 100
37 | Leidingen san/WP/CV | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d |  | 0 | 3711 | 0 | 0 | 3711 | 2017-01-13 08:00 | 6d | 3711 | 0 | 0 | -443 | 0 | 3268 | 0 | 100% | Finished | 3711 | 3711 | 100 | 120 | 100 | 100 | 88.0625 | 100
38 | Afwerken ventilatie | 2017-03-13 08:00 | 2017-03-14 17:00 | 2d |  | 0 | 2317 | 0 | 0 | 2317 | 2017-03-16 08:00 | 3d | 2317 | 0 | 0 | -266 | 0 | 2051 | 0 | 100% | Finished | 2317 | 2317 | 100 | 150 | 100 | 100 | 88.5196 | 100
39 | Afwerken sanitair | 2017-03-15 08:00 | 2017-03-17 17:00 | 3d |  | 0 | 6472 | 0 | 0 | 6472 | 2017-03-21 08:00 | 1d | 6472 | 0 | 0 | -460 | 0 | 6012 | 0 | 100% | Finished | 6472 | 6472 | 100 | 33.3333 | 100 | 100 | 92.8925 | 100
40 | Afwerken CV/WP | 2017-03-20 08:00 | 2017-03-21 17:00 | 2d |  | 0 | 5903 | 0 | 0 | 5903 | 2017-03-22 08:00 | 1d | 5903 | 0 | 0 | -281 | 0 | 5622 | 0 | 100% | Finished | 5903 | 5903 | 100 | 50 | 100 | 100 | 95.2397 | 100
41 | Leidingen electro | 2017-01-17 08:00 | 2017-01-20 17:00 | 4d |  | 0 | 2701 | 0 | 0 | 2701 | 2017-01-23 08:00 | 3d | 2701 | 0 | 0 | -153 | 0 | 2548 | 0 | 100% | Finished | 2701 | 2701 | 100 | 75 | 100 | 100 | 94.3354 | 100
42 | Afwerken electro | 2017-03-22 08:00 | 2017-03-27 17:00 | 4d |  | 0 | 3807 | 0 | 0 | 3807 | 2017-03-23 08:00 | 3d | 3807 | 0 | 0 | -229 | 0 | 3578 | 0 | 100% | Finished | 3807 | 3807 | 100 | 75 | 100 | 100 | 93.9848 | 100
43 | Zonneboiler | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 455 | 0 | 0 | 455 | 2017-03-28 08:00 | 2d | 455 | 0 | 0 | 0 | 0 | 455 | 0 | 100% | Finished | 455 | 455 | 100 | 200 | 100 | 100 | 100 | 100
44 | PV panelen | 2017-03-28 08:00 | 2017-03-30 17:00 | 3d |  | 0 | 4950 | 0 | 0 | 4950 | 2017-03-28 08:00 | 3d | 4950 | 0 | 0 | 0 | 0 | 4950 | 0 | 100% | Finished | 4950 | 4950 | 100 | 100 | 100 | 100 | 100 | 100
45 | Verlichting | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2017-03-28 08:00 | 1d | 100 | 0 | 0 | 22 | 0 | 122 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 122 | 100
46 | Karweien | 2017-03-28 08:00 | 2017-04-07 17:00 | 9d |  | 0 | 3227 | 0 | 0 | 3227 | 2017-03-28 08:00 | 8d | 3227 | 0 | 0 | -107 | 0 | 3120 | 0 | 100% | Finished | 3227 | 3227 | 100 | 88.8889 | 100 | 100 | 96.6842 | 100
56 | Omgevingswerken | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  |  | 1406 |  |  | 1406 |  | 5d | [5 empty] | 1499 |  | 100% |  | 1406 | 1406
47 | Opkuis werf (afvoeren puin & afval) | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  | 0 | 1406 | 0 | 0 | 1406 | 2017-04-07 08:00 | 5d | 1406 | 0 | 0 | 93 | 0 | 1499 | 0 | 100% | Finished | 1406 | 1406 | 100 | 100 | 100 | 100 | 106.6145 | 100
57 | Restklasse | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  |  | 13218 |  |  | 13218 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | Rest | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  | 0 | 13218 | 0 | 0 | 13218 |  | 0 | 0 | 13218 | 31d | 0 | 0 | 0 | 13218 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2017-05-26 17:00 |  | TP Name | Tracking Period 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (4) | 2016-03-07 08:00 | 2017-05-29 17:00 | 321d |  |  | 218366 |  |  | 218366 |  | 320d | [5 empty] | 222021.78 |  | 100% |  | 218366 | 218366
49 | Voorbereiding | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  |  | 11265 |  |  | 11265 |  | 10d | [5 empty] | 12992 |  | 100% |  | 11265 | 11265
1 | Werfinrichting | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 3642 | 0 | 0 | 3642 | 2016-03-07 08:00 | 6d | 3642 | 0 | 0 | 1721 | 0 | 5363 | 0 | 100% | Finished | 3642 | 3642 | 100 | 200 | 100 | 100 | 147.2543 | 100
2 | Transportkosten | 2016-03-07 08:00 | 2016-03-15 17:00 | 7d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-07 08:00 | 8d | 2202 | 0 | 0 | -56 | 0 | 2146 | 0 | 100% | Finished | 2202 | 2202 | 100 | 114.2857 | 100 | 100 | 97.4569 | 100
3 | Rijtijden ploegen | 2016-03-07 08:00 | 2016-03-16 17:00 | 8d |  | 0 | 2190 | 0 | 0 | 2190 | 2016-03-07 08:00 | 7d | 2190 | 0 | 0 | -154 | 0 | 2036 | 0 | 100% | Finished | 2190 | 2190 | 100 | 87.5 | 100 | 100 | 92.968 | 100
4 | Studiekosten | 2016-03-07 08:00 | 2016-03-21 17:00 | 11d |  | 0 | 3231 | 0 | 0 | 3231 | 2016-03-07 08:00 | 10d | 3231 | 0 | 0 | 216 | 0 | 3447 | 0 | 100% | Finished | 3231 | 3231 | 100 | 90.9091 | 100 | 100 | 106.6852 | 100
50 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  |  | 12319 |  |  | 12319 |  | 30d | [5 empty] | 12361 |  | 100% |  | 12319 | 12319
5 | Funderingen | 2016-03-22 08:00 | 2016-05-02 17:00 | 30d |  | 0 | 12319 | 0 | 0 | 12319 | 2016-03-21 08:00 | 30d | 12319 | 0 | 0 | 42 | 0 | 12361 | 0 | 100% | Finished | 12319 | 12319 | 100 | 100 | 100 | 100 | 100.3409 | 100
51 | Ruwbouw | 2016-05-03 08:00 | 2016-08-25 17:00 | 83d |  |  | 48401 |  |  | 48401 |  | 91d | [5 empty] | 52494 |  | 100% |  | 48401 | 48401
6 | Gewa/metselwerk | 2016-05-03 08:00 | 2016-05-27 17:00 | 19d |  | 0 | 12997 | 0 | 0 | 12997 | 2016-05-02 08:00 | 19d | 12997 | 0 | 0 | 580 | 0 | 13577 | 0 | 100% | Finished | 12997 | 12997 | 100 | 100 | 100 | 100 | 104.4626 | 100
7 | Gewelven/Structuur | 2016-05-30 08:00 | 2016-06-07 17:00 | 7d |  | 0 | 5432 | 0 | 0 | 5432 | 2016-05-27 08:00 | 7d | 5432 | 0 | 0 | 0 | 0 | 5432 | 0 | 100% | Finished | 5432 | 5432 | 100 | 100 | 100 | 100 | 100 | 100
8 | Uitbranden GEWA | 2016-05-30 08:00 | 2016-05-30 17:00 | 1d |  | 0 | 533 | 0 | 0 | 533 | 2016-05-27 08:00 | 1d | 533 | 0 | 0 | 819 | 0 | 1352 | 0 | 100% | Finished | 533 | 533 | 100 | 100 | 100 | 100 | 253.6585 | 100
9 | Isolatie | 2016-06-08 08:00 | 2016-06-14 17:00 | 5d |  | 0 | 1324 | 0 | 0 | 1324 | 2016-06-07 08:00 | 6d | 1324 | 0 | 0 | 292 | 0 | 1616 | 0 | 100% | Finished | 1324 | 1324 | 100 | 120 | 100 | 100 | 122.0544 | 100
10 | Parament | 2016-06-15 08:00 | 2016-08-02 17:00 | 35d |  | 0 | 19883 | 0 | 0 | 19883 | 2016-06-15 08:00 | 33d | 19883 | 0 | 0 | 464 | 0 | 20347 | 0 | 100% | Finished | 19883 | 19883 | 100 | 94.2857 | 100 | 100 | 102.3337 | 100
11 | Ytong | 2016-08-03 08:00 | 2016-08-08 17:00 | 4d |  | 0 | 2879 | 0 | 0 | 2879 | 2016-08-01 08:00 | 5d | 2879 | 0 | 0 | 7 | 0 | 2886 | 0 | 100% | Finished | 2879 | 2879 | 100 | 125 | 100 | 100 | 100.2431 | 100
12 | Dorpels | 2016-08-09 08:00 | 2016-08-11 17:00 | 3d |  | 0 | 1934 | 0 | 0 | 1934 | 2016-08-08 08:00 | 2d | 1934 | 0 | 0 | -637 | 0 | 1297 | 0 | 100% | Finished | 1934 | 1934 | 100 | 66.6667 | 100 | 100 | 67.0631 | 100
13 | Voegwerk | 2016-08-09 08:00 | 2016-08-16 17:00 | 6d |  | 0 | 1493 | 0 | 0 | 1493 | 2016-08-08 08:00 | 7d | 1493 | 0 | 0 | 568 | 0 | 2061 | 0 | 100% | Finished | 1493 | 1493 | 100 | 116.6667 | 100 | 100 | 138.0442 | 100
14 | Stelling | 2016-08-17 08:00 | 2016-08-22 17:00 | 4d |  | 0 | 1392 | 0 | 0 | 1392 | 2016-08-17 08:00 | 9d | 1392 | 0 | 0 | 1258 | 0 | 2650 | 0 | 100% | Finished | 1392 | 1392 | 100 | 225 | 100 | 100 | 190.3736 | 100
15 | Crepi+Isolatie | 2016-08-23 08:00 | 2016-08-24 17:00 | 2d |  | 0 | 334 | 0 | 0 | 334 | 2016-08-30 08:00 | 1d | 334 | 0 | 0 | -234 | 0 | 100 | 0 | 100% | Finished | 334 | 334 | 100 | 50 | 100 | 100 | 29.9401 | 100
16 | Karweien | 2016-08-25 08:00 | 2016-08-25 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-08-31 08:00 | 4d | 200 | 0 | 0 | 976 | 0 | 1176 | 0 | 100% | Finished | 200 | 200 | 100 | 400 | 100 | 100 | 588 | 100
52 | Dakwerken | 2016-08-26 08:00 | 2016-12-05 17:00 | 72d |  |  | 39200 |  |  | 39200 |  | 65d | [5 empty] | 37877.78 |  | 100% |  | 39200 | 39200
17 | Daktimmer traditioneel/prefabkap | 2016-08-26 08:00 | 2016-10-13 17:00 | 35d |  | 0 | 13456 | 0 | 0 | 13456 | 2016-09-06 08:00 | 34d | 13456 | 0 | 0 | -809.22 | 0 | 12646.78 | 0 | 100% | Finished | 13456 | 13456 | 100 | 97.1429 | 100 | 100 | 93.9862 | 100
18 | Dakdekken | 2016-10-14 08:00 | 2016-11-10 17:00 | 20d |  | 0 | 15873 | 0 | 0 | 15873 | 2016-10-24 08:00 | 18d | 15873 | 0 | 0 | -584 | 0 | 15289 | 0 | 100% | Finished | 15873 | 15873 | 100 | 90 | 100 | 100 | 96.3208 | 100
19 | Goten & Afleiders | 2016-11-11 08:00 | 2016-11-15 17:00 | 3d |  | 0 | 1282 | 0 | 0 | 1282 | 2016-11-17 08:00 | 3d | 1282 | 0 | 0 | 52 | 0 | 1334 | 0 | 100% | Finished | 1282 | 1282 | 100 | 100 | 100 | 100 | 104.0562 | 100
20 | Oversteken/Gevelbekleding | 2016-11-11 08:00 | 2016-12-02 17:00 | 16d |  | 0 | 6265 | 0 | 0 | 6265 | 2016-11-17 08:00 | 12d | 6265 | 0 | 0 | -178 | 0 | 6087 | 0 | 100% | Finished | 6265 | 6265 | 100 | 75 | 100 | 100 | 97.1588 | 100
21 | Dakvlakramen | 2016-12-05 08:00 | 2016-12-05 17:00 | 1d |  | 0 | 2324 | 0 | 0 | 2324 | 2016-12-05 08:00 | 1d | 2324 | 0 | 0 | 197 | 0 | 2521 | 0 | 100% | Finished | 2324 | 2324 | 100 | 100 | 100 | 100 | 108.4768 | 100
53 | Buitenschrijnwerk | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  |  | 23493 |  |  | 23493 |  | 16d | [5 empty] | 23840 |  | 100% |  | 23493 | 23493
22 | Buitenschrijnwerk plaatsen | 2016-12-06 08:00 | 2016-12-26 17:00 | 15d |  | 0 | 23493 | 0 | 0 | 23493 | 2016-12-06 08:00 | 16d | 23493 | 0 | 0 | 347 | 0 | 23840 | 0 | 100% | Finished | 23493 | 23493 | 100 | 106.6667 | 100 | 100 | 101.477 | 100
54 | Binnenafwerking | 2017-01-23 08:00 | 2017-04-05 17:00 | 53d |  |  | 30237 |  |  | 30237 |  | 53d | [5 empty] | 31324 |  | 100% |  | 30237 | 30237
23 | Plakwerken | 2017-01-23 08:00 | 2017-02-07 17:00 | 12d |  | 0 | 9564 | 0 | 0 | 9564 | 2017-01-26 08:00 | 12d | 9564 | 0 | 0 | 10 | 0 | 9574 | 0 | 100% | Finished | 9564 | 9564 | 100 | 100 | 100 | 100 | 100.1046 | 100
24 | Chapes/uitvullingen | 2017-02-08 08:00 | 2017-02-14 17:00 | 5d |  | 0 | 2432 | 0 | 0 | 2432 | 2017-02-13 08:00 | 5d | 2432 | 0 | 0 | 1 | 0 | 2433 | 0 | 100% | Finished | 2432 | 2432 | 100 | 100 | 100 | 100 | 100.0411 | 100
25 | Vloerisolatie | 2017-02-16 08:00 | 2017-03-01 17:00 | 10d |  | 0 | 2739 | 0 | 0 | 2739 | 2017-02-21 08:00 | 10d | 2739 | 0 | 0 | 2 | 0 | 2741 | 0 | 100% | Finished | 2739 | 2739 | 100 | 100 | 100 | 100 | 100.073 | 100
26 | Tegelwerken | 2017-03-02 08:00 | 2017-03-10 17:00 | 7d |  | 0 | 3633 | 0 | 0 | 3633 | 2017-03-07 08:00 | 7d | 3633 | 0 | 0 | 705 | 0 | 4338 | 0 | 100% | Finished | 3633 | 3633 | 100 | 100 | 100 | 100 | 119.4055 | 100
27 | Voorbereiding+Gyplat | 2017-03-13 08:00 | 2017-03-22 17:00 | 8d |  | 0 | 2792 | 0 | 0 | 2792 | 2017-03-16 08:00 | 6d | 2792 | 0 | 0 | -1102 | 0 | 1690 | 0 | 100% | Finished | 2792 | 2792 | 100 | 75 | 100 | 100 | 60.5301 | 100
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-13 08:00 | 2017-03-16 17:00 | 4d |  | 0 | 837 | 0 | 0 | 837 | 2017-03-16 08:00 | 4d | 837 | 0 | 0 | 258 | 0 | 1095 | 0 | 100% | Finished | 837 | 837 | 100 | 100 | 100 | 100 | 130.8244 | 100
29 | Binnendeuren/Uitbekleding | 2017-03-23 08:00 | 2017-03-28 17:00 | 4d |  | 0 | 1021 | 0 | 0 | 1021 | 2017-03-24 08:00 | 3d | 1021 | 0 | 0 | -133 | 0 | 888 | 0 | 100% | Finished | 1021 | 1021 | 100 | 75 | 100 | 100 | 86.9736 | 100
30 | Trap | 2017-03-23 08:00 | 2017-03-30 17:00 | 6d |  | 0 | 1650 | 0 | 0 | 1650 | 2017-03-24 08:00 | 6d | 1650 | 0 | 0 | 68 | 0 | 1718 | 0 | 100% | Finished | 1650 | 1650 | 100 | 100 | 100 | 100 | 104.1212 | 100
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-05 17:00 | 10d |  | 0 | 5569 | 0 | 0 | 5569 | 2017-03-24 08:00 | 12d | 5569 | 0 | 0 | 1278 | 0 | 6847 | 0 | 100% | Finished | 5569 | 5569 | 100 | 120 | 100 | 100 | 122.9485 | 100
55 | Technieken | 2016-12-27 08:00 | 2017-04-07 17:00 | 74d |  |  | 38827 |  |  | 38827 |  | 72d | [5 empty] | 36416 |  | 100% |  | 38827 | 38827
32 | UZL | 2016-12-27 08:00 | 2016-12-29 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-12-28 08:00 | 3d | 888 | 0 | 0 | -56 | 0 | 832 | 0 | 100% | Finished | 888 | 888 | 100 | 100 | 100 | 100 | 93.6937 | 100
33 | Betonplexplaten | 2016-12-27 08:00 | 2016-12-27 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2016-12-28 08:00 | 1d | 100 | 0 | 0 | 149 | 0 | 249 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 249 | 100
34 | Slijpen technieken/Boringen | 2016-12-30 08:00 | 2017-01-04 17:00 | 4d |  | 0 | 1296 | 0 | 0 | 1296 | 2017-01-02 08:00 | 7d | 1296 | 0 | 0 | 603 | 0 | 1899 | 0 | 100% | Finished | 1296 | 1296 | 100 | 175 | 100 | 100 | 146.5278 | 100
35 | Bad &amp; douche | 2017-02-15 08:00 | 2017-02-15 17:00 | 1d |  | 0 | 320 | 0 | 0 | 320 | 2017-02-20 08:00 | 1d | 320 | 0 | 0 | 90 | 0 | 410 | 0 | 100% | Finished | 320 | 320 | 100 | 100 | 100 | 100 | 128.125 | 100
36 | Leidingen vent | 2017-01-05 08:00 | 2017-01-09 17:00 | 3d |  | 0 | 2580 | 0 | 0 | 2580 | 2017-01-11 08:00 | 2d | 2580 | 0 | 0 | -1280 | 0 | 1300 | 0 | 100% | Finished | 2580 | 2580 | 100 | 66.6667 | 100 | 100 | 50.3876 | 100
37 | Leidingen san/WP/CV | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d |  | 0 | 3711 | 0 | 0 | 3711 | 2017-01-13 08:00 | 6d | 3711 | 0 | 0 | -443 | 0 | 3268 | 0 | 100% | Finished | 3711 | 3711 | 100 | 120 | 100 | 100 | 88.0625 | 100
38 | Afwerken ventilatie | 2017-03-13 08:00 | 2017-03-14 17:00 | 2d |  | 0 | 2317 | 0 | 0 | 2317 | 2017-03-16 08:00 | 3d | 2317 | 0 | 0 | -266 | 0 | 2051 | 0 | 100% | Finished | 2317 | 2317 | 100 | 150 | 100 | 100 | 88.5196 | 100
39 | Afwerken sanitair | 2017-03-15 08:00 | 2017-03-17 17:00 | 3d |  | 0 | 6472 | 0 | 0 | 6472 | 2017-03-21 08:00 | 1d | 6472 | 0 | 0 | -460 | 0 | 6012 | 0 | 100% | Finished | 6472 | 6472 | 100 | 33.3333 | 100 | 100 | 92.8925 | 100
40 | Afwerken CV/WP | 2017-03-20 08:00 | 2017-03-21 17:00 | 2d |  | 0 | 5903 | 0 | 0 | 5903 | 2017-03-22 08:00 | 1d | 5903 | 0 | 0 | -281 | 0 | 5622 | 0 | 100% | Finished | 5903 | 5903 | 100 | 50 | 100 | 100 | 95.2397 | 100
41 | Leidingen electro | 2017-01-17 08:00 | 2017-01-20 17:00 | 4d |  | 0 | 2701 | 0 | 0 | 2701 | 2017-01-23 08:00 | 3d | 2701 | 0 | 0 | -153 | 0 | 2548 | 0 | 100% | Finished | 2701 | 2701 | 100 | 75 | 100 | 100 | 94.3354 | 100
42 | Afwerken electro | 2017-03-22 08:00 | 2017-03-27 17:00 | 4d |  | 0 | 3807 | 0 | 0 | 3807 | 2017-03-23 08:00 | 3d | 3807 | 0 | 0 | -229 | 0 | 3578 | 0 | 100% | Finished | 3807 | 3807 | 100 | 75 | 100 | 100 | 93.9848 | 100
43 | Zonneboiler | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 455 | 0 | 0 | 455 | 2017-03-28 08:00 | 2d | 455 | 0 | 0 | 0 | 0 | 455 | 0 | 100% | Finished | 455 | 455 | 100 | 200 | 100 | 100 | 100 | 100
44 | PV panelen | 2017-03-28 08:00 | 2017-03-30 17:00 | 3d |  | 0 | 4950 | 0 | 0 | 4950 | 2017-03-28 08:00 | 3d | 4950 | 0 | 0 | 0 | 0 | 4950 | 0 | 100% | Finished | 4950 | 4950 | 100 | 100 | 100 | 100 | 100 | 100
45 | Verlichting | 2017-03-28 08:00 | 2017-03-28 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100 | 2017-03-28 08:00 | 1d | 100 | 0 | 0 | 22 | 0 | 122 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 122 | 100
46 | Karweien | 2017-03-28 08:00 | 2017-04-07 17:00 | 9d |  | 0 | 3227 | 0 | 0 | 3227 | 2017-03-28 08:00 | 8d | 3227 | 0 | 0 | -107 | 0 | 3120 | 0 | 100% | Finished | 3227 | 3227 | 100 | 88.8889 | 100 | 100 | 96.6842 | 100
56 | Omgevingswerken | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  |  | 1406 |  |  | 1406 |  | 5d | [5 empty] | 1499 |  | 100% |  | 1406 | 1406
47 | Opkuis werf (afvoeren puin & afval) | 2017-04-10 08:00 | 2017-04-14 17:00 | 5d |  | 0 | 1406 | 0 | 0 | 1406 | 2017-04-07 08:00 | 5d | 1406 | 0 | 0 | 93 | 0 | 1499 | 0 | 100% | Finished | 1406 | 1406 | 100 | 100 | 100 | 100 | 106.6145 | 100
57 | Restklasse | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  |  | 13218 |  |  | 13218 |  | 31d | [5 empty] | 13218 |  | 100% |  | 13218 | 13218
48 | Rest | 2017-04-17 08:00 | 2017-05-29 17:00 | 31d |  | 0 | 13218 | 0 | 0 | 13218 | 2017-04-14 08:00 | 31d | 13218 | 0 | 0 | 0 | 0 | 13218 | 0 | 100% | Finished | 13218 | 13218 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-07 08:00 | 2016-05-02 08:00 | 23584 | 23584 | 25353 | 2016-04-29 17:00 | 0 | 100% | -1769 | 93.02% | 0 | 100% | 100% | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-07-03 09:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-06-28 09:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-06-28 09:00 | 220135 | 234745.3018 | 220135 | 220135 | 234745.3018 | 234745.3018 | 231650.4896 | 231650.4896 | 1 | 0.93023 | 1 | 1 | 0 | 0.93023 | 1 | 1 | 1
Tracking Period 2 | 2016-05-02 08:00 | 2016-09-06 08:00 | 85441 | 71985 | 77847 | 2016-08-25 17:00 | -13456 | 84.25% | -5862 | 92.47% | -7d | 94.66% | 100% | 2017-06-26 15:00 | 2017-08-21 17:00 | 2017-10-03 17:00 | 2017-06-27 14:00 | 2017-08-21 17:00 | 2017-09-19 11:00 | 2017-06-07 17:00 | 2017-06-23 09:00 | 2017-07-18 09:00 | 224228 | 236148.3365 | 251590.683 | 232491.4435 | 265739.2621 | 245084.7023 | 239013.2288 | 235403.187 | 0.94656 | 0.9247 | 0.84251 | 1 | -7 | 0.9247 | 1 | 0.94656 | 1
Tracking Period 3 | 2016-09-06 08:00 | 2016-12-06 08:00 | 111185 | 111185 | 115724.78 | 2016-12-05 17:00 | 0 | 100% | -4539.78 | 96.08% | 0 | 100% | 100% | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-06-16 09:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-06-06 09:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-06-06 09:00 | 222905.78 | 227282.0733 | 222905.78 | 222905.78 | 227282.0733 | 227282.0733 | 226378.4561 | 226378.4561 | 1 | 0.96077 | 1 | 1 | 0 | 0.96077 | 1 | 1 | 1
Tracking Period 4 | 2016-12-06 08:00 | 2017-04-14 08:00 | 205148 | 205148 | 208803.78 | 2017-04-13 17:00 | 0 | 100% | -3655.78 | 98.25% | 0 | 100% | 100% | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-06-06 15:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-05-30 14:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-05-30 14:00 | 222021.78 | 222257.3275 | 222021.78 | 222021.78 | 222257.3275 | 222257.3275 | 222209.5488 | 222209.5488 | 1 | 0.98249 | 1 | 1 | 0 | 0.98249 | 1 | 1 | 1
Tracking Period 5 | 2017-04-14 08:00 | 2017-05-26 17:00 | 218366 | 218366 | 222021.78 | 2017-05-26 17:00 | 0 | 100% | -3655.78 | 98.35% | 0 | 100% | 100% | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-06-06 11:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 2017-05-29 17:00 | 222021.78 | 222021.78 | 222021.78 | 222021.78 | 222021.78 | 222021.78 | 222021.78 | 222021.78 | 1 | 0.98353 | 1 | 1 | 0 | 0.98353 | 1 | 1 | 1