## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House Structural Work | 1 |  |  | 2016-03-07 08:00 | 2016-08-29 17:00 | 126d |  |  | 95694 |  |  | 95694 | 175.375
20 | Voorbereiding | 1.1 |  |  | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  |  | 6220 |  |  | 6220 | 24.375
1 | Transportkosten | 1.1.1 |  | FS3 | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 750 | 0 | 0 | 750 | 2.375
2 | Studiekosten | 1.1.2 |  | FS3 | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  | 0 | 5470 | 0 | 0 | 5470 | 24.375
21 | Funderingen | 1.2 |  |  | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  |  | 12241 |  |  | 12241 | 38.375
3 | Funderingen | 1.2.1 | 1FS;2FS | FS4 | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  | 0 | 12241 | 0 | 0 | 12241 | 38.375
22 | Ruwbouw | 1.3 |  |  | 2016-05-10 08:00 | 2016-08-29 17:00 | 80d |  |  | 77233 |  |  | 77233 | 111.375
4 | Gewa/Metselwerk | 1.3.1 | 3FS | FS5;FS6 | 2016-05-10 08:00 | 2016-06-09 17:00 | 23d |  | 0 | 22982 | 0 | 0 | 22982 | 30.375
5 | Gewelven/Structuur | 1.3.2 | 4FS | FS7 | 2016-06-10 08:00 | 2016-06-21 17:00 | 8d |  | 0 | 10216 | 0 | 0 | 10216 | 11.375
6 | Uitbranden GEWA | 1.3.3 | 4FS | FS7 | 2016-06-10 08:00 | 2016-06-13 17:00 | 2d |  | 0 | 528 | 0 | 0 | 528 | 3.375
7 | Isolatie | 1.3.4 | 5FS;6FS | FS8 | 2016-06-22 08:00 | 2016-07-01 17:00 | 8d |  | 0 | 5773 | 0 | 0 | 5773 | 9.375
8 | Parament | 1.3.5 | 7FS | FS9 | 2016-07-04 08:00 | 2016-08-03 17:00 | 23d |  | 0 | 27764 | 0 | 0 | 27764 | 30.375
9 | Ytong | 1.3.6 | 8FS | FS10;FS11;FS12 | 2016-08-04 08:00 | 2016-08-15 17:00 | 8d |  | 0 | 2276 | 0 | 0 | 2276 | 11.375
10 | Dorpels | 1.3.7 | 9FS | FS13 | 2016-08-16 08:00 | 2016-08-17 17:00 | 2d |  | 0 | 2878 | 0 | 0 | 2878 | 1.375
11 | Voegwerk | 1.3.8 | 9FS | FS13 | 2016-08-16 08:00 | 2016-08-25 17:00 | 8d |  | 0 | 2191 | 0 | 0 | 2191 | 9.375
12 | Stelling | 1.3.9 | 9FS | FS13 | 2016-08-16 08:00 | 2016-08-26 17:00 | 9d |  | 0 | 2425 | 0 | 0 | 2425 | 10.375
13 | Karweien | 1.3.10 | 10FS;11FS;12FS |  | 2016-08-29 08:00 | 2016-08-29 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House Structural Work | 1008h |  |  |  |  | 99 | 100 | 101
20 | Voorbereiding | 152h |  |  |  |  | 99 | 100 | 101
1 | Transportkosten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Studiekosten | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Funderingen | 216h |  |  |  |  | 99 | 100 | 101
3 | Funderingen | 216h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
22 | Ruwbouw | 640h |  |  |  |  | 99 | 100 | 101
4 | Gewa/Metselwerk | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Gewelven/Structuur | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Uitbranden GEWA | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Isolatie | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Parament | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Ytong | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Dorpels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Voegwerk | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Stelling | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Karweien | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2016-05-03 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Structural Work | 2016-03-07 08:00 | 2016-08-29 17:00 | 126d |  |  | 95694 |  |  | 95694 |  | 41d | [5 empty] | 20690 |  | 19.29% |  | 18461 | 18461
20 | Voorbereiding | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  |  | 6220 |  |  | 6220 |  | 10d | [5 empty] | 6799 |  | 100% |  | 6220 | 6220
1 | Transportkosten | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 750 | 0 | 0 | 750 | 2016-03-07 08:00 | 10d | 750 | 0 | 0 | 2131 | 0 | 2881 | 0 | 100% | Finished | 750 | 750 | 100 | 333.3333 | 100 | 100 | 384.1333 | 100
2 | Studiekosten | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  | 0 | 5470 | 0 | 0 | 5470 | 2016-03-07 08:00 | 10d | 5470 | 0 | 0 | -1552 | 0 | 3918 | 0 | 100% | Finished | 5470 | 5470 | 100 | 52.6316 | 100 | 100 | 71.6271 | 100
21 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  |  | 12241 |  |  | 12241 |  | 31d | [5 empty] | 13891 |  | 100% |  | 12241 | 12241
3 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  | 0 | 12241 | 0 | 0 | 12241 | 2016-03-21 08:00 | 31d | 12241 | 0 | 0 | 1650 | 0 | 13891 | 0 | 100% | Finished | 12241 | 12241 | 100 | 114.8148 | 100 | 100 | 113.4793 | 100
22 | Ruwbouw | 2016-05-10 08:00 | 2016-08-29 17:00 | 80d |  |  | 77233 |  |  | 77233 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | Gewa/Metselwerk | 2016-05-10 08:00 | 2016-06-09 17:00 | 23d |  | 0 | 22982 | 0 | 0 | 22982 |  | 0 | 0 | 22982 | 23d | 0 | 0 | 0 | 22982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Gewelven/Structuur | 2016-06-10 08:00 | 2016-06-21 17:00 | 8d |  | 0 | 10216 | 0 | 0 | 10216 |  | 0 | 0 | 10216 | 8d | 0 | 0 | 0 | 10216 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Uitbranden GEWA | 2016-06-10 08:00 | 2016-06-13 17:00 | 2d |  | 0 | 528 | 0 | 0 | 528 |  | 0 | 0 | 528 | 2d | 0 | 0 | 0 | 528 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Isolatie | 2016-06-22 08:00 | 2016-07-01 17:00 | 8d |  | 0 | 5773 | 0 | 0 | 5773 |  | 0 | 0 | 5773 | 8d | 0 | 0 | 0 | 5773 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Parament | 2016-07-04 08:00 | 2016-08-03 17:00 | 23d |  | 0 | 27764 | 0 | 0 | 27764 |  | 0 | 0 | 27764 | 23d | 0 | 0 | 0 | 27764 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Ytong | 2016-08-04 08:00 | 2016-08-15 17:00 | 8d |  | 0 | 2276 | 0 | 0 | 2276 |  | 0 | 0 | 2276 | 8d | 0 | 0 | 0 | 2276 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Dorpels | 2016-08-16 08:00 | 2016-08-17 17:00 | 2d |  | 0 | 2878 | 0 | 0 | 2878 |  | 0 | 0 | 2878 | 2d | 0 | 0 | 0 | 2878 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Voegwerk | 2016-08-16 08:00 | 2016-08-25 17:00 | 8d |  | 0 | 2191 | 0 | 0 | 2191 |  | 0 | 0 | 2191 | 8d | 0 | 0 | 0 | 2191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Stelling | 2016-08-16 08:00 | 2016-08-26 17:00 | 9d |  | 0 | 2425 | 0 | 0 | 2425 |  | 0 | 0 | 2425 | 9d | 0 | 0 | 0 | 2425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Karweien | 2016-08-29 08:00 | 2016-08-29 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-06-23 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Structural Work | 2016-03-07 08:00 | 2016-08-29 17:00 | 126d |  |  | 95694 |  |  | 95694 |  | 78d | [5 empty] | 58998 |  | 60.57% |  | 57960 | 57960
20 | Voorbereiding | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  |  | 6220 |  |  | 6220 |  | 10d | [5 empty] | 6799 |  | 100% |  | 6220 | 6220
1 | Transportkosten | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 750 | 0 | 0 | 750 | 2016-03-07 08:00 | 10d | 750 | 0 | 0 | 2131 | 0 | 2881 | 0 | 100% | Finished | 750 | 750 | 100 | 333.3333 | 100 | 100 | 384.1333 | 100
2 | Studiekosten | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  | 0 | 5470 | 0 | 0 | 5470 | 2016-03-07 08:00 | 10d | 5470 | 0 | 0 | -1552 | 0 | 3918 | 0 | 100% | Finished | 5470 | 5470 | 100 | 52.6316 | 100 | 100 | 71.6271 | 100
21 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  |  | 12241 |  |  | 12241 |  | 31d | [5 empty] | 13891 |  | 100% |  | 12241 | 12241
3 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  | 0 | 12241 | 0 | 0 | 12241 | 2016-03-21 08:00 | 31d | 12241 | 0 | 0 | 1650 | 0 | 13891 | 0 | 100% | Finished | 12241 | 12241 | 100 | 114.8148 | 100 | 100 | 113.4793 | 100
22 | Ruwbouw | 2016-05-10 08:00 | 2016-08-29 17:00 | 80d |  |  | 77233 |  |  | 77233 |  | 37d | [5 empty] | 38308 |  | 51.14% |  | 39499 | 39499
4 | Gewa/Metselwerk | 2016-05-10 08:00 | 2016-06-09 17:00 | 23d |  | 0 | 22982 | 0 | 0 | 22982 | 2016-05-03 08:00 | 26d | 22982 | 0 | 0 | 827 | 0 | 23809 | 0 | 100% | Finished | 22982 | 22982 | 100 | 113.0435 | 100 | 100 | 103.5985 | 100
5 | Gewelven/Structuur | 2016-06-10 08:00 | 2016-06-21 17:00 | 8d |  | 0 | 10216 | 0 | 0 | 10216 | 2016-06-08 08:00 | 3d | 10216 | 0 | 0 | -2411 | 0 | 7805 | 0 | 100% | Finished | 10216 | 10216 | 100 | 37.5 | 100 | 100 | 76.3998 | 100
6 | Uitbranden GEWA | 2016-06-10 08:00 | 2016-06-13 17:00 | 2d |  | 0 | 528 | 0 | 0 | 528 | 2016-06-08 08:00 | 2d | 528 | 0 | 0 | -162 | 0 | 366 | 0 | 100% | Finished | 528 | 528 | 100 | 100 | 100 | 100 | 69.3182 | 100
7 | Isolatie | 2016-06-22 08:00 | 2016-07-01 17:00 | 8d |  | 0 | 5773 | 0 | 0 | 5773 | 2016-06-13 08:00 | 8d | 5773 | 0 | 0 | 555 | 0 | 6328 | 0 | 100% | Finished | 5773 | 5773 | 100 | 100 | 100 | 100 | 109.6137 | 100
8 | Parament | 2016-07-04 08:00 | 2016-08-03 17:00 | 23d |  | 0 | 27764 | 0 | 0 | 27764 |  | 0 | 0 | 27764 | 23d | 0 | 0 | 0 | 27764 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Ytong | 2016-08-04 08:00 | 2016-08-15 17:00 | 8d |  | 0 | 2276 | 0 | 0 | 2276 |  | 0 | 0 | 2276 | 8d | 0 | 0 | 0 | 2276 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Dorpels | 2016-08-16 08:00 | 2016-08-17 17:00 | 2d |  | 0 | 2878 | 0 | 0 | 2878 |  | 0 | 0 | 2878 | 2d | 0 | 0 | 0 | 2878 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Voegwerk | 2016-08-16 08:00 | 2016-08-25 17:00 | 8d |  | 0 | 2191 | 0 | 0 | 2191 |  | 0 | 0 | 2191 | 8d | 0 | 0 | 0 | 2191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Stelling | 2016-08-16 08:00 | 2016-08-26 17:00 | 9d |  | 0 | 2425 | 0 | 0 | 2425 |  | 0 | 0 | 2425 | 9d | 0 | 0 | 0 | 2425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Karweien | 2016-08-29 08:00 | 2016-08-29 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-08-17 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Structural Work | 2016-03-07 08:00 | 2016-08-29 17:00 | 126d |  |  | 95694 |  |  | 95694 |  | 117d | [5 empty] | 92123 |  | 91.96% |  | 88000 | 95494
20 | Voorbereiding | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  |  | 6220 |  |  | 6220 |  | 10d | [5 empty] | 6799 |  | 100% |  | 6220 | 6220
1 | Transportkosten | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 750 | 0 | 0 | 750 | 2016-03-07 08:00 | 10d | 750 | 0 | 0 | 2131 | 0 | 2881 | 0 | 100% | Finished | 750 | 750 | 100 | 333.3333 | 100 | 100 | 384.1333 | 100
2 | Studiekosten | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  | 0 | 5470 | 0 | 0 | 5470 | 2016-03-07 08:00 | 10d | 5470 | 0 | 0 | -1552 | 0 | 3918 | 0 | 100% | Finished | 5470 | 5470 | 100 | 52.6316 | 100 | 100 | 71.6271 | 100
21 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  |  | 12241 |  |  | 12241 |  | 31d | [5 empty] | 13891 |  | 100% |  | 12241 | 12241
3 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  | 0 | 12241 | 0 | 0 | 12241 | 2016-03-21 08:00 | 31d | 12241 | 0 | 0 | 1650 | 0 | 13891 | 0 | 100% | Finished | 12241 | 12241 | 100 | 114.8148 | 100 | 100 | 113.4793 | 100
22 | Ruwbouw | 2016-05-10 08:00 | 2016-08-29 17:00 | 80d |  |  | 77233 |  |  | 77233 |  | 76d | [5 empty] | 71433 |  | 90.04% |  | 69539 | 77033
4 | Gewa/Metselwerk | 2016-05-10 08:00 | 2016-06-09 17:00 | 23d |  | 0 | 22982 | 0 | 0 | 22982 | 2016-05-03 08:00 | 26d | 22982 | 0 | 0 | 827 | 0 | 23809 | 0 | 100% | Finished | 22982 | 22982 | 100 | 113.0435 | 100 | 100 | 103.5985 | 100
5 | Gewelven/Structuur | 2016-06-10 08:00 | 2016-06-21 17:00 | 8d |  | 0 | 10216 | 0 | 0 | 10216 | 2016-06-08 08:00 | 3d | 10216 | 0 | 0 | -2411 | 0 | 7805 | 0 | 100% | Finished | 10216 | 10216 | 100 | 37.5 | 100 | 100 | 76.3998 | 100
6 | Uitbranden GEWA | 2016-06-10 08:00 | 2016-06-13 17:00 | 2d |  | 0 | 528 | 0 | 0 | 528 | 2016-06-08 08:00 | 2d | 528 | 0 | 0 | -162 | 0 | 366 | 0 | 100% | Finished | 528 | 528 | 100 | 100 | 100 | 100 | 69.3182 | 100
7 | Isolatie | 2016-06-22 08:00 | 2016-07-01 17:00 | 8d |  | 0 | 5773 | 0 | 0 | 5773 | 2016-06-13 08:00 | 8d | 5773 | 0 | 0 | 555 | 0 | 6328 | 0 | 100% | Finished | 5773 | 5773 | 100 | 100 | 100 | 100 | 109.6137 | 100
8 | Parament | 2016-07-04 08:00 | 2016-08-03 17:00 | 23d |  | 0 | 27764 | 0 | 0 | 27764 | 2016-06-23 08:00 | 25d | 27764 | 0 | 0 | 1221 | 0 | 28985 | 0 | 100% | Finished | 27764 | 27764 | 100 | 108.6957 | 100 | 100 | 104.3978 | 100
9 | Ytong | 2016-08-04 08:00 | 2016-08-15 17:00 | 8d |  | 0 | 2276 | 0 | 0 | 2276 | 2016-07-28 08:00 | 14d | 2276 | 0 | 0 | 1864 | 0 | 4140 | 0 | 100% | Finished | 2276 | 2276 | 100 | 175 | 100 | 100 | 181.8981 | 100
10 | Dorpels | 2016-08-16 08:00 | 2016-08-17 17:00 | 2d |  | 0 | 2878 | 0 | 0 | 2878 |  | 0 | 0 | 2878 | 2d | 0 | 0 | 0 | 2878 | 0% | Not Started | 0 | 2878 | 100 |  | 0 | 100 |  | 0
11 | Voegwerk | 2016-08-16 08:00 | 2016-08-25 17:00 | 8d |  | 0 | 2191 | 0 | 0 | 2191 |  | 0 | 0 | 2191 | 8d | 0 | 0 | 0 | 2191 | 0% | Not Started | 0 | 2191 | 100 |  | 0 | 100 |  | 0
12 | Stelling | 2016-08-16 08:00 | 2016-08-26 17:00 | 9d |  | 0 | 2425 | 0 | 0 | 2425 |  | 0 | 0 | 2425 | 9d | 0 | 0 | 0 | 2425 | 0% | Not Started | 0 | 2425 | 100 |  | 0 | 100 |  | 0
13 | Karweien | 2016-08-29 08:00 | 2016-08-29 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-09-02 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Structural Work | 2016-03-07 08:00 | 2016-08-29 17:00 | 126d |  |  | 95694 |  |  | 95694 |  | 130d | [5 empty] | 100763 |  | 100% |  | 95694 | 95694
20 | Voorbereiding | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  |  | 6220 |  |  | 6220 |  | 10d | [5 empty] | 6799 |  | 100% |  | 6220 | 6220
1 | Transportkosten | 2016-03-07 08:00 | 2016-03-09 17:00 | 3d |  | 0 | 750 | 0 | 0 | 750 | 2016-03-07 08:00 | 10d | 750 | 0 | 0 | 2131 | 0 | 2881 | 0 | 100% | Finished | 750 | 750 | 100 | 333.3333 | 100 | 100 | 384.1333 | 100
2 | Studiekosten | 2016-03-07 08:00 | 2016-03-31 17:00 | 19d |  | 0 | 5470 | 0 | 0 | 5470 | 2016-03-07 08:00 | 10d | 5470 | 0 | 0 | -1552 | 0 | 3918 | 0 | 100% | Finished | 5470 | 5470 | 100 | 52.6316 | 100 | 100 | 71.6271 | 100
21 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  |  | 12241 |  |  | 12241 |  | 31d | [5 empty] | 13891 |  | 100% |  | 12241 | 12241
3 | Funderingen | 2016-04-01 08:00 | 2016-05-09 17:00 | 27d |  | 0 | 12241 | 0 | 0 | 12241 | 2016-03-21 08:00 | 31d | 12241 | 0 | 0 | 1650 | 0 | 13891 | 0 | 100% | Finished | 12241 | 12241 | 100 | 114.8148 | 100 | 100 | 113.4793 | 100
22 | Ruwbouw | 2016-05-10 08:00 | 2016-08-29 17:00 | 80d |  |  | 77233 |  |  | 77233 |  | 89d | [5 empty] | 80073 |  | 100% |  | 77233 | 77233
4 | Gewa/Metselwerk | 2016-05-10 08:00 | 2016-06-09 17:00 | 23d |  | 0 | 22982 | 0 | 0 | 22982 | 2016-05-03 08:00 | 26d | 22982 | 0 | 0 | 827 | 0 | 23809 | 0 | 100% | Finished | 22982 | 22982 | 100 | 113.0435 | 100 | 100 | 103.5985 | 100
5 | Gewelven/Structuur | 2016-06-10 08:00 | 2016-06-21 17:00 | 8d |  | 0 | 10216 | 0 | 0 | 10216 | 2016-06-08 08:00 | 3d | 10216 | 0 | 0 | -2411 | 0 | 7805 | 0 | 100% | Finished | 10216 | 10216 | 100 | 37.5 | 100 | 100 | 76.3998 | 100
6 | Uitbranden GEWA | 2016-06-10 08:00 | 2016-06-13 17:00 | 2d |  | 0 | 528 | 0 | 0 | 528 | 2016-06-08 08:00 | 2d | 528 | 0 | 0 | -162 | 0 | 366 | 0 | 100% | Finished | 528 | 528 | 100 | 100 | 100 | 100 | 69.3182 | 100
7 | Isolatie | 2016-06-22 08:00 | 2016-07-01 17:00 | 8d |  | 0 | 5773 | 0 | 0 | 5773 | 2016-06-13 08:00 | 8d | 5773 | 0 | 0 | 555 | 0 | 6328 | 0 | 100% | Finished | 5773 | 5773 | 100 | 100 | 100 | 100 | 109.6137 | 100
8 | Parament | 2016-07-04 08:00 | 2016-08-03 17:00 | 23d |  | 0 | 27764 | 0 | 0 | 27764 | 2016-06-23 08:00 | 25d | 27764 | 0 | 0 | 1221 | 0 | 28985 | 0 | 100% | Finished | 27764 | 27764 | 100 | 108.6957 | 100 | 100 | 104.3978 | 100
9 | Ytong | 2016-08-04 08:00 | 2016-08-15 17:00 | 8d |  | 0 | 2276 | 0 | 0 | 2276 | 2016-07-28 08:00 | 14d | 2276 | 0 | 0 | 1864 | 0 | 4140 | 0 | 100% | Finished | 2276 | 2276 | 100 | 175 | 100 | 100 | 181.8981 | 100
10 | Dorpels | 2016-08-16 08:00 | 2016-08-17 17:00 | 2d |  | 0 | 2878 | 0 | 0 | 2878 | 2016-08-17 08:00 | 4d | 2878 | 0 | 0 | 201 | 0 | 3079 | 0 | 100% | Finished | 2878 | 2878 | 100 | 200 | 100 | 100 | 106.984 | 100
11 | Voegwerk | 2016-08-16 08:00 | 2016-08-25 17:00 | 8d |  | 0 | 2191 | 0 | 0 | 2191 | 2016-08-17 08:00 | 5d | 2191 | 0 | 0 | -178 | 0 | 2013 | 0 | 100% | Finished | 2191 | 2191 | 100 | 62.5 | 100 | 100 | 91.8759 | 100
12 | Stelling | 2016-08-16 08:00 | 2016-08-26 17:00 | 9d |  | 0 | 2425 | 0 | 0 | 2425 | 2016-08-17 08:00 | 11d | 2425 | 0 | 0 | 686 | 0 | 3111 | 0 | 100% | Finished | 2425 | 2425 | 100 | 122.2222 | 100 | 100 | 128.2887 | 100
13 | Karweien | 2016-08-29 08:00 | 2016-08-29 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-09-01 08:00 | 2d | 200 | 0 | 0 | 237 | 0 | 437 | 0 | 100% | Finished | 200 | 200 | 100 | 200 | 100 | 100 | 218.5 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-07 08:00 | 2016-05-03 08:00 | 18461 | 18461 | 20690 | 2016-05-02 17:00 | 0 | 100% | -2229 | 89.23% | 0 | 100% | 100% | 2016-08-29 17:00 | 2016-08-29 17:00 | 2016-09-20 10:00 | 2016-08-29 17:00 | 2016-08-29 17:00 | 2016-09-13 10:00 | 2016-08-29 17:00 | 2016-08-29 17:00 | 2016-09-13 10:00 | 97923 | 107248.1913 | 97923 | 97923 | 107248.1913 | 107248.1913 | 105207.2515 | 105207.2515 | 1 | 0.89227 | 1 | 1 | 0 | 0.89227 | 1 | 1 | 1
Tracking Period 2 | 2016-05-03 08:00 | 2016-06-23 08:00 | 57960 | 57960 | 58998 | 2016-06-22 17:00 | 0 | 100% | -1038 | 98.24% | 0 | 100% | 100% | 2016-08-29 17:00 | 2016-08-29 17:00 | 2016-09-01 10:00 | 2016-08-29 17:00 | 2016-08-29 17:00 | 2016-08-30 16:00 | 2016-08-29 17:00 | 2016-08-29 17:00 | 2016-08-30 16:00 | 96732 | 97407.7745 | 96732 | 96732 | 97407.7745 | 97407.7745 | 97270.6902 | 97270.6902 | 1 | 0.98241 | 1 | 1 | 0 | 0.98241 | 1 | 1 | 1
Tracking Period 3 | 2016-06-23 08:00 | 2016-08-17 08:00 | 95494 | 88000 | 92123 | 2016-08-15 17:00 | -7494 | 92.15% | -4123 | 95.52% | -1d | 99.15% | 100% | 2016-09-12 16:00 | 2016-09-13 15:00 | 2016-09-22 09:00 | 2016-09-12 09:00 | 2016-09-13 15:00 | 2016-09-14 14:00 | 2016-08-30 17:00 | 2016-08-31 09:00 | 2016-08-31 12:00 | 99817 | 100177.4814 | 100472.214 | 99883.3276 | 100863.3937 | 100246.9166 | 100234.7514 | 100116.8801 | 0.99145 | 0.95524 | 0.92152 | 1 | -1 | 0.95524 | 1 | 0.99145 | 1
Tracking Period 4 | 2016-08-17 08:00 | 2016-09-02 17:00 | 95694 | 95694 | 100763 | 2016-08-29 17:00 | 0 | 100% | -5069 | 94.97% | -4d | 96.92% | 100% | 2016-08-29 17:00 | 2016-08-29 17:00 | 2016-09-07 14:00 | 2016-09-02 17:00 | 2016-09-02 17:00 | 2016-09-02 17:00 | 2016-09-02 17:00 | 2016-09-02 17:00 | 2016-09-02 17:00 | 100763 | 100763 | 100763 | 100763 | 100763 | 100763 | 100763 | 100763 | 0.96923 | 0.94969 | 1 | 1 | -4 | 0.94969 | 1 | 0.96923 | 1