## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House Finishing Works (3) | 1 |  |  | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 51115.5195 |  |  | 51115.5195 | 126.375
28 | Start uitv afwerking | 1.1 |  |  | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 8068.52 |  |  | 8068.52 | 41.375
1 | F1 ventilatie | 1.1.1 |  | FS2 | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 6.375
2 | F1 san/cv | 1.1.2 | 1FS | FS3 | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 6.375
3 | F1 elektr | 1.1.3 | 2FS | FS4;FS5 | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 804.51 | 0 | 0 | 804.51 | 6.375
4 | Aansluiting water | 1.1.4 | 3FS |  | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 6.375
5 | Dakisolatie | 1.1.5 | 3FS | FS6 | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 6.375
6 | F1 pleister | 1.1.6 | 5FS | FS7;FS25 | 2016-04-08 08:00 | 2016-04-21 17:00 | 10d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 13.375
29 | Fase 2 | 1.2 |  |  | 2016-04-22 08:00 | 2016-05-27 17:00 | 26d |  |  | 12773.3098 |  |  | 12773.3098 | 35.375
7 | Opm keuken | 1.2.1 | 6FS | FS8;FS9 | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 6.375
25 | F2 san/cv | 1.2.2 | 6FS | FS8;FS9 | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 6.375
8 | F2 ventilatie | 1.2.3 | 7FS;25FS |  | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 6.375
9 | Vloerisolatie | 1.2.4 | 7FS;25FS | FS27 | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 6.375
27 | Vloerverwarming | 1.2.5 | 9FS | FS10 | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 6.375
10 | Chape | 1.2.6 | 27FS | FS11;FS12 | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1511.08 | 0 | 0 | 1511.08 | 6.375
11 | Opm Binnenschr | 1.2.7 | 10FS |  | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 | 6.375
12 | F2 elektr | 1.2.8 | 10FS | FS13 | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1206.77 | 0 | 0 | 1206.77 | 6.375
13 | openen E/G/W | 1.2.9 | 12FS | FS14 | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 0.375
30 | Fase 3 | 1.3 |  |  | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13196.6399 |  |  | 13196.6399 | 32.375
14 | F3 san/cv | 1.3.1 | 13FS | FS15 | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 4.375
15 | Vloerwerken | 1.3.2 | 14FS | FS16 | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1287.71 | 0 | 0 | 1287.71 | 4.375
16 | Trappen | 1.3.3 | 15FS | FS17 | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 4.375
17 | Binnenschrijnwerk | 1.3.4 | 16FS | FS18 | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 | 4.375
18 | Keuken | 1.3.5 | 17FS | FS19;FS20 | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 4.375
31 | Finale afwerking | 1.4 |  |  | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17077.0498 |  |  | 17077.0498 | 11.375
19 | Afw ventilatie | 1.4.1 | 18FS | FS21;FS24;FS26 | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 4.375
20 | Afw elektr | 1.4.2 | 18FS | FS21;FS24 | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2011.29 | 0 | 0 | 2011.29 | 4.375
21 | Afw san/cv | 1.4.3 | 19FS;20FS |  | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 4.375
26 | Afw vloer | 1.4.4 | 19FS |  | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 3863.1299 | 0 | 0 | 3863.1299 | 4.375
24 | Afw pleister | 1.4.5 | 19FS;20FS |  | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2828.6299 | 0 | 0 | 2828.6299 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House Finishing Works (3) | 728h |  |  |  |  | 99 | 100 | 101
28 | Start uitv afwerking | 240h |  |  |  |  | 99 | 100 | 101
1 | F1 ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
2 | F1 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | F1 elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
4 | Aansluiting water | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Dakisolatie | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
6 | F1 pleister | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
29 | Fase 2 | 208h |  |  |  |  | 99 | 100 | 101
7 | Opm keuken | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | F2 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | F2 ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
9 | Vloerisolatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
27 | Vloerverwarming | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
10 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Opm Binnenschr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | F2 elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
13 | openen E/G/W | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
30 | Fase 3 | 200h |  |  |  |  | 99 | 100 | 101
14 | F3 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Vloerwerken | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
16 | Trappen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Binnenschrijnwerk | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
18 | Keuken | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
31 | Finale afwerking | 80h |  |  |  |  | 99 | 100 | 101
19 | Afw ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Afw elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | Afw san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Afw vloer | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
24 | Afw pleister | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120

## Project Control - TP1
| TP Status Date | 2016-04-22 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (3) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 51115.5195 |  |  | 51115.5195 |  | 30d | [5 empty] | 10544.52 |  | 15.78% |  | 8068.52 | 8068.52
28 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 8068.52 |  |  | 8068.52 |  | 30d | [5 empty] | 10544.52 |  | 100% |  | 8068.52 | 8068.52
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 110.0113 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 804.51 | 0 | 0 | 804.51 | 2016-03-25 08:00 | 5d | 804.51 | 0 | 0 | 449 | 0 | 1253.51 | 0 | 100% | Finished | 804.51 | 804.51 | 100 | 100 | 100 | 100 | 155.8104 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 163.0208 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-01 08:00 | 5d | 2121.48 | 0 | 0 | 748 | 0 | 2869.48 | 0 | 100% | Finished | 2121.48 | 2121.48 | 100 | 100 | 100 | 100 | 135.2584 | 100
6 | F1 pleister | 2016-04-08 08:00 | 2016-04-21 17:00 | 10d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-08 08:00 | 10d | 2121.48 | 0 | 0 | 567 | 0 | 2688.48 | 0 | 100% | Finished | 2121.48 | 2121.48 | 100 | 100 | 100 | 100 | 126.7266 | 100
29 | Fase 2 | 2016-04-22 08:00 | 2016-05-27 17:00 | 26d |  |  | 12773.3098 |  |  | 12773.3098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 |  | 0 | 0 | 2231.25 | 5d | 0 | 0 | 0 | 2231.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 |  | 0 | 0 | 1932.83 | 5d | 0 | 0 | 0 | 1932.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 |  | 0 | 0 | 1158.75 | 5d | 0 | 0 | 0 | 1158.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 |  | 0 | 0 | 1716.95 | 5d | 0 | 0 | 0 | 1716.95 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Vloerverwarming | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 |  | 0 | 0 | 1716.95 | 5d | 0 | 0 | 0 | 1716.95 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1511.08 | 0 | 0 | 1511.08 |  | 0 | 0 | 1511.08 | 5d | 0 | 0 | 0 | 1511.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 |  | 0 | 0 | 979.98 | 5d | 0 | 0 | 0 | 979.98 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1206.77 | 0 | 0 | 1206.77 |  | 0 | 0 | 1206.77 | 5d | 0 | 0 | 0 | 1206.77 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 |  | 0 | 0 | 318.75 | 1d | 0 | 0 | 0 | 318.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13196.6399 |  |  | 13196.6399 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 |  | 0 | 0 | 3221.3799 | 5d | 0 | 0 | 0 | 3221.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1287.71 | 0 | 0 | 1287.71 |  | 0 | 0 | 1287.71 | 5d | 0 | 0 | 0 | 1287.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 |  | 0 | 0 | 3392.5801 | 5d | 0 | 0 | 0 | 3392.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 |  | 0 | 0 | 1469.97 | 5d | 0 | 0 | 0 | 1469.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 |  | 0 | 0 | 3825 | 5d | 0 | 0 | 0 | 3825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17077.0498 |  |  | 17077.0498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2011.29 | 0 | 0 | 2011.29 |  | 0 | 0 | 2011.29 | 5d | 0 | 0 | 0 | 2011.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 3863.1299 | 0 | 0 | 3863.1299 |  | 0 | 0 | 3863.1299 | 5d | 0 | 0 | 0 | 3863.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2828.6299 | 0 | 0 | 2828.6299 |  | 0 | 0 | 2828.6299 | 5d | 0 | 0 | 0 | 2828.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-05-30 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (3) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 51115.5195 |  |  | 51115.5195 |  | 56d | [5 empty] | 25989.8298 |  | 40.77% |  | 20841.8298 | 20841.8298
28 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 8068.52 |  |  | 8068.52 |  | 30d | [5 empty] | 10544.52 |  | 100% |  | 8068.52 | 8068.52
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 110.0113 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 804.51 | 0 | 0 | 804.51 | 2016-03-25 08:00 | 5d | 804.51 | 0 | 0 | 449 | 0 | 1253.51 | 0 | 100% | Finished | 804.51 | 804.51 | 100 | 100 | 100 | 100 | 155.8104 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 163.0208 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-01 08:00 | 5d | 2121.48 | 0 | 0 | 748 | 0 | 2869.48 | 0 | 100% | Finished | 2121.48 | 2121.48 | 100 | 100 | 100 | 100 | 135.2584 | 100
6 | F1 pleister | 2016-04-08 08:00 | 2016-04-21 17:00 | 10d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-08 08:00 | 10d | 2121.48 | 0 | 0 | 567 | 0 | 2688.48 | 0 | 100% | Finished | 2121.48 | 2121.48 | 100 | 100 | 100 | 100 | 126.7266 | 100
29 | Fase 2 | 2016-04-22 08:00 | 2016-05-27 17:00 | 26d |  |  | 12773.3098 |  |  | 12773.3098 |  | 26d | [5 empty] | 15445.3098 |  | 100% |  | 12773.3098 | 12773.3098
7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 126.084 | 100
25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 110.0371 | 100
8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 2016-04-29 08:00 | 5d | 1716.95 | 0 | 0 | 202 | 0 | 1918.95 | 0 | 100% | Finished | 1716.95 | 1716.95 | 100 | 100 | 100 | 100 | 111.765 | 100
27 | Vloerverwarming | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 2016-05-06 08:00 | 5d | 1716.95 | 0 | 0 | 172 | 0 | 1888.95 | 0 | 100% | Finished | 1716.95 | 1716.95 | 100 | 100 | 100 | 100 | 110.0178 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1511.08 | 0 | 0 | 1511.08 | 2016-05-13 08:00 | 5d | 1511.08 | 0 | 0 | 381 | 0 | 1892.08 | 0 | 100% | Finished | 1511.08 | 1511.08 | 100 | 100 | 100 | 100 | 125.2138 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 | 2016-05-20 08:00 | 5d | 979.98 | 0 | 0 | 299 | 0 | 1278.98 | 0 | 100% | Finished | 979.98 | 979.98 | 100 | 100 | 100 | 100 | 130.5108 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1206.77 | 0 | 0 | 1206.77 | 2016-05-20 08:00 | 5d | 1206.77 | 0 | 0 | 674 | 0 | 1880.77 | 0 | 100% | Finished | 1206.77 | 1206.77 | 100 | 100 | 100 | 100 | 155.8516 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 163.0588 | 100
30 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13196.6399 |  |  | 13196.6399 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 |  | 0 | 0 | 3221.3799 | 5d | 0 | 0 | 0 | 3221.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1287.71 | 0 | 0 | 1287.71 |  | 0 | 0 | 1287.71 | 5d | 0 | 0 | 0 | 1287.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 |  | 0 | 0 | 3392.5801 | 5d | 0 | 0 | 0 | 3392.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 |  | 0 | 0 | 1469.97 | 5d | 0 | 0 | 0 | 1469.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 |  | 0 | 0 | 3825 | 5d | 0 | 0 | 0 | 3825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17077.0498 |  |  | 17077.0498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2011.29 | 0 | 0 | 2011.29 |  | 0 | 0 | 2011.29 | 5d | 0 | 0 | 0 | 2011.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 3863.1299 | 0 | 0 | 3863.1299 |  | 0 | 0 | 3863.1299 | 5d | 0 | 0 | 0 | 3863.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2828.6299 | 0 | 0 | 2828.6299 |  | 0 | 0 | 2828.6299 | 5d | 0 | 0 | 0 | 2828.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-07-04 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (3) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 51115.5195 |  |  | 51115.5195 |  | 81d | [5 empty] | 41815.4697 |  | 66.59% |  | 34038.4697 | 34038.4697
28 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 8068.52 |  |  | 8068.52 |  | 30d | [5 empty] | 10544.52 |  | 100% |  | 8068.52 | 8068.52
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 110.0113 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 804.51 | 0 | 0 | 804.51 | 2016-03-25 08:00 | 5d | 804.51 | 0 | 0 | 449 | 0 | 1253.51 | 0 | 100% | Finished | 804.51 | 804.51 | 100 | 100 | 100 | 100 | 155.8104 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 163.0208 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-01 08:00 | 5d | 2121.48 | 0 | 0 | 748 | 0 | 2869.48 | 0 | 100% | Finished | 2121.48 | 2121.48 | 100 | 100 | 100 | 100 | 135.2584 | 100
6 | F1 pleister | 2016-04-08 08:00 | 2016-04-21 17:00 | 10d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-08 08:00 | 10d | 2121.48 | 0 | 0 | 567 | 0 | 2688.48 | 0 | 100% | Finished | 2121.48 | 2121.48 | 100 | 100 | 100 | 100 | 126.7266 | 100
29 | Fase 2 | 2016-04-22 08:00 | 2016-05-27 17:00 | 26d |  |  | 12773.3098 |  |  | 12773.3098 |  | 26d | [5 empty] | 15445.3098 |  | 100% |  | 12773.3098 | 12773.3098
7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 126.084 | 100
25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 110.0371 | 100
8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 2016-04-29 08:00 | 5d | 1716.95 | 0 | 0 | 202 | 0 | 1918.95 | 0 | 100% | Finished | 1716.95 | 1716.95 | 100 | 100 | 100 | 100 | 111.765 | 100
27 | Vloerverwarming | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 2016-05-06 08:00 | 5d | 1716.95 | 0 | 0 | 172 | 0 | 1888.95 | 0 | 100% | Finished | 1716.95 | 1716.95 | 100 | 100 | 100 | 100 | 110.0178 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1511.08 | 0 | 0 | 1511.08 | 2016-05-13 08:00 | 5d | 1511.08 | 0 | 0 | 381 | 0 | 1892.08 | 0 | 100% | Finished | 1511.08 | 1511.08 | 100 | 100 | 100 | 100 | 125.2138 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 | 2016-05-20 08:00 | 5d | 979.98 | 0 | 0 | 299 | 0 | 1278.98 | 0 | 100% | Finished | 979.98 | 979.98 | 100 | 100 | 100 | 100 | 130.5108 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1206.77 | 0 | 0 | 1206.77 | 2016-05-20 08:00 | 5d | 1206.77 | 0 | 0 | 674 | 0 | 1880.77 | 0 | 100% | Finished | 1206.77 | 1206.77 | 100 | 100 | 100 | 100 | 155.8516 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 163.0588 | 100
30 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13196.6399 |  |  | 13196.6399 |  | 25d | [5 empty] | 15825.6399 |  | 100% |  | 13196.6399 | 13196.6399
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | 323 | 0 | 3544.3799 | 0 | 100% | Finished | 3221.3799 | 3221.3799 | 100 | 100 | 100 | 100 | 110.0268 | 100
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1287.71 | 0 | 0 | 1287.71 | 2016-06-06 08:00 | 5d | 1287.71 | 0 | 0 | -178 | 0 | 1109.71 | 0 | 100% | Finished | 1287.71 | 1287.71 | 100 | 100 | 100 | 100 | 86.177 | 100
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 2016-06-13 08:00 | 5d | 3392.5801 | 0 | 0 | 1036 | 0 | 4428.5801 | 0 | 100% | Finished | 3392.5801 | 3392.5801 | 100 | 100 | 100 | 100 | 130.5372 | 100
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 | 2016-06-20 08:00 | 5d | 1469.97 | 0 | 0 | 449 | 0 | 1918.97 | 0 | 100% | Finished | 1469.97 | 1469.97 | 100 | 100 | 100 | 100 | 130.5448 | 100
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 999 | 0 | 4824 | 0 | 100% | Finished | 3825 | 3825 | 100 | 100 | 100 | 100 | 126.1176 | 100
31 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17077.0498 |  |  | 17077.0498 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2011.29 | 0 | 0 | 2011.29 |  | 0 | 0 | 2011.29 | 5d | 0 | 0 | 0 | 2011.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 3863.1299 | 0 | 0 | 3863.1299 |  | 0 | 0 | 3863.1299 | 5d | 0 | 0 | 0 | 3863.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2828.6299 | 0 | 0 | 2828.6299 |  | 0 | 0 | 2828.6299 | 5d | 0 | 0 | 0 | 2828.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-07-15 16:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (3) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 51115.5195 |  |  | 51115.5195 |  | 91d | [5 empty] | 60829.5195 |  | 100% |  | 51115.5195 | 51115.5195
28 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 8068.52 |  |  | 8068.52 |  | 30d | [5 empty] | 10544.52 |  | 100% |  | 8068.52 | 8068.52
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 110.0113 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 804.51 | 0 | 0 | 804.51 | 2016-03-25 08:00 | 5d | 804.51 | 0 | 0 | 449 | 0 | 1253.51 | 0 | 100% | Finished | 804.51 | 804.51 | 100 | 100 | 100 | 100 | 155.8104 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 163.0208 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-01 08:00 | 5d | 2121.48 | 0 | 0 | 748 | 0 | 2869.48 | 0 | 100% | Finished | 2121.48 | 2121.48 | 100 | 100 | 100 | 100 | 135.2584 | 100
6 | F1 pleister | 2016-04-08 08:00 | 2016-04-21 17:00 | 10d |  | 0 | 2121.48 | 0 | 0 | 2121.48 | 2016-04-08 08:00 | 10d | 2121.48 | 0 | 0 | 567 | 0 | 2688.48 | 0 | 100% | Finished | 2121.48 | 2121.48 | 100 | 100 | 100 | 100 | 126.7266 | 100
29 | Fase 2 | 2016-04-22 08:00 | 2016-05-27 17:00 | 26d |  |  | 12773.3098 |  |  | 12773.3098 |  | 26d | [5 empty] | 15445.3098 |  | 100% |  | 12773.3098 | 12773.3098
7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 126.084 | 100
25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 110.0371 | 100
8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 2016-04-29 08:00 | 5d | 1716.95 | 0 | 0 | 202 | 0 | 1918.95 | 0 | 100% | Finished | 1716.95 | 1716.95 | 100 | 100 | 100 | 100 | 111.765 | 100
27 | Vloerverwarming | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1716.95 | 0 | 0 | 1716.95 | 2016-05-06 08:00 | 5d | 1716.95 | 0 | 0 | 172 | 0 | 1888.95 | 0 | 100% | Finished | 1716.95 | 1716.95 | 100 | 100 | 100 | 100 | 110.0178 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1511.08 | 0 | 0 | 1511.08 | 2016-05-13 08:00 | 5d | 1511.08 | 0 | 0 | 381 | 0 | 1892.08 | 0 | 100% | Finished | 1511.08 | 1511.08 | 100 | 100 | 100 | 100 | 125.2138 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 979.98 | 0 | 0 | 979.98 | 2016-05-20 08:00 | 5d | 979.98 | 0 | 0 | 299 | 0 | 1278.98 | 0 | 100% | Finished | 979.98 | 979.98 | 100 | 100 | 100 | 100 | 130.5108 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1206.77 | 0 | 0 | 1206.77 | 2016-05-20 08:00 | 5d | 1206.77 | 0 | 0 | 674 | 0 | 1880.77 | 0 | 100% | Finished | 1206.77 | 1206.77 | 100 | 100 | 100 | 100 | 155.8516 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 163.0588 | 100
30 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13196.6399 |  |  | 13196.6399 |  | 25d | [5 empty] | 15825.6399 |  | 100% |  | 13196.6399 | 13196.6399
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | 323 | 0 | 3544.3799 | 0 | 100% | Finished | 3221.3799 | 3221.3799 | 100 | 100 | 100 | 100 | 110.0268 | 100
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 1287.71 | 0 | 0 | 1287.71 | 2016-06-06 08:00 | 5d | 1287.71 | 0 | 0 | -178 | 0 | 1109.71 | 0 | 100% | Finished | 1287.71 | 1287.71 | 100 | 100 | 100 | 100 | 86.177 | 100
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 2016-06-13 08:00 | 5d | 3392.5801 | 0 | 0 | 1036 | 0 | 4428.5801 | 0 | 100% | Finished | 3392.5801 | 3392.5801 | 100 | 100 | 100 | 100 | 130.5372 | 100
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1469.97 | 0 | 0 | 1469.97 | 2016-06-20 08:00 | 5d | 1469.97 | 0 | 0 | 449 | 0 | 1918.97 | 0 | 100% | Finished | 1469.97 | 1469.97 | 100 | 100 | 100 | 100 | 130.5448 | 100
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 999 | 0 | 4824 | 0 | 100% | Finished | 3825 | 3825 | 100 | 100 | 100 | 100 | 126.1176 | 100
31 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 17077.0498 |  |  | 17077.0498 |  | 10d | [5 empty] | 19014.0498 |  | 100% |  | 17077.0498 | 17077.0498
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 100% | Finished | 1931.25 | 1931.25 | 100 | 100 | 100 | 100 | 97.1003 | 100
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2011.29 | 0 | 0 | 2011.29 | 2016-07-04 08:00 | 5d | 2011.29 | 0 | 0 | 1124 | 0 | 3135.29 | 0 | 100% | Finished | 2011.29 | 2011.29 | 100 | 100 | 100 | 100 | 155.8845 | 100
21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-11 08:00 | 5d | 6442.75 | 0 | 0 | 647 | 0 | 7089.75 | 0 | 100% | Finished | 6442.75 | 6442.75 | 100 | 100 | 100 | 100 | 110.0423 | 100
26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 3863.1299 | 0 | 0 | 3863.1299 | 2016-07-11 08:00 | 5d | 3863.1299 | 0 | 0 | -534 | 0 | 3329.1299 | 0 | 100% | Finished | 3863.1299 | 3863.1299 | 100 | 100 | 100 | 100 | 86.177 | 100
24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2828.6299 | 0 | 0 | 2828.6299 | 2016-07-11 08:00 | 5d | 2828.6299 | 0 | 0 | 756 | 0 | 3584.6299 | 0 | 100% | Finished | 2828.6299 | 2828.6299 | 100 | 100 | 100 | 100 | 126.7267 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-11 08:00 | 2016-04-22 08:00 | 8068.52 | 8068.52 | 10544.52 | 2016-04-21 17:00 | 0 | 100% | -2476 | 76.52% | 0 | 100% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-08-24 16:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-08-11 15:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-08-11 15:00 | 53591.5195 | 66801.423 | 53591.5195 | 53591.5195 | 66801.423 | 66801.423 | 63548.3486 | 63548.3486 | 1 | 0.76519 | 1 | 1 | 0 | 0.76519 | 1 | 1 | 1
Tracking Period 2 | 2016-04-22 08:00 | 2016-05-30 08:00 | 20841.8298 | 20841.8298 | 25989.8298 | 2016-05-27 17:00 | 0 | 100% | -5148 | 80.19% | 0 | 100% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-08-17 12:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-28 14:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-28 14:00 | 56263.5195 | 63741.2197 | 56263.5195 | 56263.5195 | 63741.2197 | 63741.2197 | 61964.0688 | 61964.0688 | 1 | 0.80192 | 1 | 1 | 0 | 0.80192 | 1 | 1 | 1
Tracking Period 3 | 2016-05-30 08:00 | 2016-07-04 08:00 | 34038.4697 | 34038.4697 | 41815.4697 | 2016-07-01 17:00 | 0 | 100% | -7777 | 81.4% | 0 | 100% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-08-15 15:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-20 10:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-20 10:00 | 58892.5195 | 62794.2289 | 58892.5195 | 58892.5195 | 62794.2289 | 62794.2289 | 61877.4878 | 61877.4878 | 1 | 0.81402 | 1 | 1 | 0 | 0.81402 | 1 | 1 | 1
Tracking Period 4 | 2016-07-04 08:00 | 2016-07-15 16:00 | 51115.5195 | 51115.5195 | 60829.5195 | 2016-07-15 16:00 | 0 | 100% | -9714 | 84.03% | 0 | 100% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-08-10 10:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 60829.5195 | 60829.5195 | 60829.5195 | 60829.5195 | 60829.5195 | 60829.5195 | 60829.5195 | 60829.5195 | 1 | 0.84031 | 1 | 1 | 0 | 0.84031 | 1 | 1 | 1