## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House Finishing Works (10) | 1 |  |  | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 54580.3294 |  |  | 54580.3294 | 126.375
27 | Start uitv afwerking | 1.1 |  |  | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8362.4698 |  |  | 8362.4698 | 48.375
1 | F1 ventilatie | 1.1.1 |  | FS2 | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 6.375
2 | F1 san/cv | 1.1.2 | 1FS | FS3 | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 6.375
3 | F1 elektr | 1.1.3 | 2FS | FS4;FS5 | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 876.16 | 0 | 0 | 876.16 | 6.375
4 | Aansluiting water | 1.1.4 | 3FS |  | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 6.375
5 | Dakisolatie | 1.1.5 | 3FS | FS6 | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 13.375
6 | F1 pleister | 1.1.6 | 5FS | FS7;FS25 | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 13.375
28 | Fase 2 | 1.2 |  |  | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13673.3699 |  |  | 13673.3699 | 28.375
7 | Opm keuken | 1.2.1 | 6FS | FS8;FS9 | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 6.375
25 | F2 san/cv | 1.2.2 | 6FS | FS8;FS9 | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 6.375
8 | F2 ventilatie | 1.2.3 | 7FS;25FS |  | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 6.375
9 | Vloerisolatie | 1.2.4 | 7FS;25FS | FS10 | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3230.24 | 0 | 0 | 3230.24 | 6.375
10 | Chape | 1.2.5 | 9FS | FS11;FS12 | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 2200.1399 | 0 | 0 | 2200.1399 | 6.375
11 | Opm Binnenschr | 1.2.6 | 10FS |  | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1287.17 | 0 | 0 | 1287.17 | 6.375
12 | F2 elektr | 1.2.7 | 10FS | FS13 | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1314.24 | 0 | 0 | 1314.24 | 6.375
13 | openen E/G/W | 1.2.8 | 12FS | FS14 | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 0.375
29 | Fase 3 | 1.3 |  |  | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13619.5198 |  |  | 13619.5198 | 32.375
14 | F3 san/cv | 1.3.1 | 13FS | FS15 | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 4.375
15 | Vloerwerken | 1.3.2 | 14FS | FS16 | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2153.49 | 0 | 0 | 2153.49 | 4.375
16 | Trappen | 1.3.3 | 15FS | FS17 | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2488.8899 | 0 | 0 | 2488.8899 | 4.375
17 | Binnenschrijnwerk | 1.3.4 | 16FS | FS18 | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1930.76 | 0 | 0 | 1930.76 | 4.375
18 | Keuken | 1.3.5 | 17FS | FS19;FS20 | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 4.375
30 | Finale afwerking | 1.4 |  |  | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 18924.97 |  |  | 18924.97 | 11.375
19 | Afw ventilatie | 1.4.1 | 18FS | FS21;FS24;FS26 | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 4.375
20 | Afw elektr | 1.4.2 | 18FS | FS21;FS24 | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2190.3999 | 0 | 0 | 2190.3999 | 4.375
21 | Afw san/cv | 1.4.3 | 19FS;20FS |  | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 4.375
26 | Afw vloer | 1.4.4 | 19FS |  | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 5383.73 | 0 | 0 | 5383.73 | 4.375
24 | Afw pleister | 1.4.5 | 19FS;20FS |  | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2976.8401 | 0 | 0 | 2976.8401 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House Finishing Works (10) | 728h |  |  |  |  | 99 | 100 | 101
27 | Start uitv afwerking | 280h |  |  |  |  | 99 | 100 | 101
1 | F1 ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
2 | F1 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | F1 elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
4 | Aansluiting water | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Dakisolatie | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
6 | F1 pleister | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
28 | Fase 2 | 168h |  |  |  |  | 99 | 100 | 101
7 | Opm keuken | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | F2 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | F2 ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
9 | Vloerisolatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
10 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Opm Binnenschr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | F2 elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
13 | openen E/G/W | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
29 | Fase 3 | 200h |  |  |  |  | 99 | 100 | 101
14 | F3 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Vloerwerken | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
16 | Trappen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Binnenschrijnwerk | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
18 | Keuken | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
30 | Finale afwerking | 80h |  |  |  |  | 99 | 100 | 101
19 | Afw ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Afw elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | Afw san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Afw vloer | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
24 | Afw pleister | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120

## Project Control - TP1
| TP Status Date | 2016-04-29 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (10) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 54580.3294 |  |  | 54580.3294 |  | 35d | [5 empty] | 9795.4698 |  | 15.32% |  | 8362.4698 | 8362.4698
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8362.4698 |  |  | 8362.4698 |  | 35d | [5 empty] | 9795.4698 |  | 100% |  | 8362.4698 | 8362.4698
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -35 | 0 | 1253.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 97.2838 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 876.16 | 0 | 0 | 876.16 | 2016-03-25 08:00 | 5d | 876.16 | 0 | 0 | 100 | 0 | 976.16 | 0 | 100% | Finished | 876.16 | 876.16 | 100 | 100 | 100 | 100 | 111.4134 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 193 | 0 | 1153 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 120.1042 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-01 08:00 | 10d | 2232.6299 | 0 | 0 | 206 | 0 | 2438.6299 | 0 | 100% | Finished | 2232.6299 | 2232.6299 | 100 | 100 | 100 | 100 | 109.2268 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-15 08:00 | 10d | 2232.6299 | 0 | 0 | 991 | 0 | 3223.6299 | 0 | 100% | Finished | 2232.6299 | 2232.6299 | 100 | 100 | 100 | 100 | 144.3871 | 100
28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13673.3699 |  |  | 13673.3699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 |  | 0 | 0 | 2231.25 | 5d | 0 | 0 | 0 | 2231.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 |  | 0 | 0 | 1932.83 | 5d | 0 | 0 | 0 | 1932.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 |  | 0 | 0 | 1158.75 | 5d | 0 | 0 | 0 | 1158.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3230.24 | 0 | 0 | 3230.24 |  | 0 | 0 | 3230.24 | 5d | 0 | 0 | 0 | 3230.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 2200.1399 | 0 | 0 | 2200.1399 |  | 0 | 0 | 2200.1399 | 5d | 0 | 0 | 0 | 2200.1399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1287.17 | 0 | 0 | 1287.17 |  | 0 | 0 | 1287.17 | 5d | 0 | 0 | 0 | 1287.17 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1314.24 | 0 | 0 | 1314.24 |  | 0 | 0 | 1314.24 | 5d | 0 | 0 | 0 | 1314.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 |  | 0 | 0 | 318.75 | 1d | 0 | 0 | 0 | 318.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13619.5198 |  |  | 13619.5198 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 |  | 0 | 0 | 3221.3799 | 5d | 0 | 0 | 0 | 3221.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2153.49 | 0 | 0 | 2153.49 |  | 0 | 0 | 2153.49 | 5d | 0 | 0 | 0 | 2153.49 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2488.8899 | 0 | 0 | 2488.8899 |  | 0 | 0 | 2488.8899 | 5d | 0 | 0 | 0 | 2488.8899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1930.76 | 0 | 0 | 1930.76 |  | 0 | 0 | 1930.76 | 5d | 0 | 0 | 0 | 1930.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 |  | 0 | 0 | 3825 | 5d | 0 | 0 | 0 | 3825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 18924.97 |  |  | 18924.97 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2190.3999 | 0 | 0 | 2190.3999 |  | 0 | 0 | 2190.3999 | 5d | 0 | 0 | 0 | 2190.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 5383.73 | 0 | 0 | 5383.73 |  | 0 | 0 | 5383.73 | 5d | 0 | 0 | 0 | 5383.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2976.8401 | 0 | 0 | 2976.8401 |  | 0 | 0 | 2976.8401 | 5d | 0 | 0 | 0 | 2976.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-05-30 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (10) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 54580.3294 |  |  | 54580.3294 |  | 56d | [5 empty] | 21623.8397 |  | 40.37% |  | 22035.8397 | 22035.8397
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8362.4698 |  |  | 8362.4698 |  | 35d | [5 empty] | 9795.4698 |  | 100% |  | 8362.4698 | 8362.4698
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -35 | 0 | 1253.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 97.2838 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 876.16 | 0 | 0 | 876.16 | 2016-03-25 08:00 | 5d | 876.16 | 0 | 0 | 100 | 0 | 976.16 | 0 | 100% | Finished | 876.16 | 876.16 | 100 | 100 | 100 | 100 | 111.4134 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 193 | 0 | 1153 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 120.1042 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-01 08:00 | 10d | 2232.6299 | 0 | 0 | 206 | 0 | 2438.6299 | 0 | 100% | Finished | 2232.6299 | 2232.6299 | 100 | 100 | 100 | 100 | 109.2268 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-15 08:00 | 10d | 2232.6299 | 0 | 0 | 991 | 0 | 3223.6299 | 0 | 100% | Finished | 2232.6299 | 2232.6299 | 100 | 100 | 100 | 100 | 144.3871 | 100
28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13673.3699 |  |  | 13673.3699 |  | 21d | [5 empty] | 11828.3699 |  | 100% |  | 13673.3699 | 13673.3699
7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | -464 | 0 | 1767.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 79.2045 | 100
25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -53 | 0 | 1879.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 97.2579 | 100
8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3230.24 | 0 | 0 | 3230.24 | 2016-05-06 08:00 | 5d | 3230.24 | 0 | 0 | -2325 | 0 | 905.24 | 0 | 100% | Finished | 3230.24 | 3230.24 | 100 | 100 | 100 | 100 | 28.0239 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 2200.1399 | 0 | 0 | 2200.1399 | 2016-05-13 08:00 | 5d | 2200.1399 | 0 | 0 | 247 | 0 | 2447.1399 | 0 | 100% | Finished | 2200.1399 | 2200.1399 | 100 | 100 | 100 | 100 | 111.2266 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1287.17 | 0 | 0 | 1287.17 | 2016-05-20 08:00 | 5d | 1287.17 | 0 | 0 | 569 | 0 | 1856.17 | 0 | 100% | Finished | 1287.17 | 1287.17 | 100 | 100 | 100 | 100 | 144.2055 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1314.24 | 0 | 0 | 1314.24 | 2016-05-20 08:00 | 5d | 1314.24 | 0 | 0 | 150 | 0 | 1464.24 | 0 | 100% | Finished | 1314.24 | 1314.24 | 100 | 100 | 100 | 100 | 111.4134 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 64 | 0 | 382.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 120.0784 | 100
29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13619.5198 |  |  | 13619.5198 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 |  | 0 | 0 | 3221.3799 | 5d | 0 | 0 | 0 | 3221.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2153.49 | 0 | 0 | 2153.49 |  | 0 | 0 | 2153.49 | 5d | 0 | 0 | 0 | 2153.49 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2488.8899 | 0 | 0 | 2488.8899 |  | 0 | 0 | 2488.8899 | 5d | 0 | 0 | 0 | 2488.8899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1930.76 | 0 | 0 | 1930.76 |  | 0 | 0 | 1930.76 | 5d | 0 | 0 | 0 | 1930.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 |  | 0 | 0 | 3825 | 5d | 0 | 0 | 0 | 3825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 18924.97 |  |  | 18924.97 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2190.3999 | 0 | 0 | 2190.3999 |  | 0 | 0 | 2190.3999 | 5d | 0 | 0 | 0 | 2190.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 5383.73 | 0 | 0 | 5383.73 |  | 0 | 0 | 5383.73 | 5d | 0 | 0 | 0 | 5383.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2976.8401 | 0 | 0 | 2976.8401 |  | 0 | 0 | 2976.8401 | 5d | 0 | 0 | 0 | 2976.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-07-04 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (10) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 54580.3294 |  |  | 54580.3294 |  | 81d | [5 empty] | 36361.3594 |  | 65.33% |  | 35655.3594 | 35655.3594
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8362.4698 |  |  | 8362.4698 |  | 35d | [5 empty] | 9795.4698 |  | 100% |  | 8362.4698 | 8362.4698
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -35 | 0 | 1253.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 97.2838 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 876.16 | 0 | 0 | 876.16 | 2016-03-25 08:00 | 5d | 876.16 | 0 | 0 | 100 | 0 | 976.16 | 0 | 100% | Finished | 876.16 | 876.16 | 100 | 100 | 100 | 100 | 111.4134 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 193 | 0 | 1153 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 120.1042 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-01 08:00 | 10d | 2232.6299 | 0 | 0 | 206 | 0 | 2438.6299 | 0 | 100% | Finished | 2232.6299 | 2232.6299 | 100 | 100 | 100 | 100 | 109.2268 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-15 08:00 | 10d | 2232.6299 | 0 | 0 | 991 | 0 | 3223.6299 | 0 | 100% | Finished | 2232.6299 | 2232.6299 | 100 | 100 | 100 | 100 | 144.3871 | 100
28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13673.3699 |  |  | 13673.3699 |  | 21d | [5 empty] | 11828.3699 |  | 100% |  | 13673.3699 | 13673.3699
7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | -464 | 0 | 1767.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 79.2045 | 100
25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -53 | 0 | 1879.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 97.2579 | 100
8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3230.24 | 0 | 0 | 3230.24 | 2016-05-06 08:00 | 5d | 3230.24 | 0 | 0 | -2325 | 0 | 905.24 | 0 | 100% | Finished | 3230.24 | 3230.24 | 100 | 100 | 100 | 100 | 28.0239 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 2200.1399 | 0 | 0 | 2200.1399 | 2016-05-13 08:00 | 5d | 2200.1399 | 0 | 0 | 247 | 0 | 2447.1399 | 0 | 100% | Finished | 2200.1399 | 2200.1399 | 100 | 100 | 100 | 100 | 111.2266 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1287.17 | 0 | 0 | 1287.17 | 2016-05-20 08:00 | 5d | 1287.17 | 0 | 0 | 569 | 0 | 1856.17 | 0 | 100% | Finished | 1287.17 | 1287.17 | 100 | 100 | 100 | 100 | 144.2055 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1314.24 | 0 | 0 | 1314.24 | 2016-05-20 08:00 | 5d | 1314.24 | 0 | 0 | 150 | 0 | 1464.24 | 0 | 100% | Finished | 1314.24 | 1314.24 | 100 | 100 | 100 | 100 | 111.4134 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 64 | 0 | 382.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 120.0784 | 100
29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13619.5198 |  |  | 13619.5198 |  | 25d | [5 empty] | 14737.5198 |  | 100% |  | 13619.5198 | 13619.5198
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -89 | 0 | 3132.3799 | 0 | 100% | Finished | 3221.3799 | 3221.3799 | 100 | 100 | 100 | 100 | 97.2372 | 100
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2153.49 | 0 | 0 | 2153.49 | 2016-06-06 08:00 | 5d | 2153.49 | 0 | 0 | 50 | 0 | 2203.49 | 0 | 100% | Finished | 2153.49 | 2153.49 | 100 | 100 | 100 | 100 | 102.3218 | 100
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2488.8899 | 0 | 0 | 2488.8899 | 2016-06-13 08:00 | 5d | 2488.8899 | 0 | 0 | 1100 | 0 | 3588.8899 | 0 | 100% | Finished | 2488.8899 | 2488.8899 | 100 | 100 | 100 | 100 | 144.1964 | 100
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1930.76 | 0 | 0 | 1930.76 | 2016-06-20 08:00 | 5d | 1930.76 | 0 | 0 | 853 | 0 | 2783.76 | 0 | 100% | Finished | 1930.76 | 1930.76 | 100 | 100 | 100 | 100 | 144.1795 | 100
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | -796 | 0 | 3029 | 0 | 100% | Finished | 3825 | 3825 | 100 | 100 | 100 | 100 | 79.1895 | 100
30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 18924.97 |  |  | 18924.97 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2190.3999 | 0 | 0 | 2190.3999 |  | 0 | 0 | 2190.3999 | 5d | 0 | 0 | 0 | 2190.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 5383.73 | 0 | 0 | 5383.73 |  | 0 | 0 | 5383.73 | 5d | 0 | 0 | 0 | 5383.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2976.8401 | 0 | 0 | 2976.8401 |  | 0 | 0 | 2976.8401 | 5d | 0 | 0 | 0 | 2976.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-07-15 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (10) | 2016-03-11 08:00 | 2016-07-15 17:00 | 91d |  |  | 54580.3294 |  |  | 54580.3294 |  | 91d | [5 empty] | 56748.3294 |  | 100% |  | 54580.3294 | 54580.3294
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8362.4698 |  |  | 8362.4698 |  | 35d | [5 empty] | 9795.4698 |  | 100% |  | 8362.4698 | 8362.4698
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -35 | 0 | 1253.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 97.2838 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 876.16 | 0 | 0 | 876.16 | 2016-03-25 08:00 | 5d | 876.16 | 0 | 0 | 100 | 0 | 976.16 | 0 | 100% | Finished | 876.16 | 876.16 | 100 | 100 | 100 | 100 | 111.4134 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 193 | 0 | 1153 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 120.1042 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-01 08:00 | 10d | 2232.6299 | 0 | 0 | 206 | 0 | 2438.6299 | 0 | 100% | Finished | 2232.6299 | 2232.6299 | 100 | 100 | 100 | 100 | 109.2268 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2232.6299 | 0 | 0 | 2232.6299 | 2016-04-15 08:00 | 10d | 2232.6299 | 0 | 0 | 991 | 0 | 3223.6299 | 0 | 100% | Finished | 2232.6299 | 2232.6299 | 100 | 100 | 100 | 100 | 144.3871 | 100
28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13673.3699 |  |  | 13673.3699 |  | 21d | [5 empty] | 11828.3699 |  | 100% |  | 13673.3699 | 13673.3699
7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | -464 | 0 | 1767.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 79.2045 | 100
25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -53 | 0 | 1879.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 97.2579 | 100
8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3230.24 | 0 | 0 | 3230.24 | 2016-05-06 08:00 | 5d | 3230.24 | 0 | 0 | -2325 | 0 | 905.24 | 0 | 100% | Finished | 3230.24 | 3230.24 | 100 | 100 | 100 | 100 | 28.0239 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 2200.1399 | 0 | 0 | 2200.1399 | 2016-05-13 08:00 | 5d | 2200.1399 | 0 | 0 | 247 | 0 | 2447.1399 | 0 | 100% | Finished | 2200.1399 | 2200.1399 | 100 | 100 | 100 | 100 | 111.2266 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1287.17 | 0 | 0 | 1287.17 | 2016-05-20 08:00 | 5d | 1287.17 | 0 | 0 | 569 | 0 | 1856.17 | 0 | 100% | Finished | 1287.17 | 1287.17 | 100 | 100 | 100 | 100 | 144.2055 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1314.24 | 0 | 0 | 1314.24 | 2016-05-20 08:00 | 5d | 1314.24 | 0 | 0 | 150 | 0 | 1464.24 | 0 | 100% | Finished | 1314.24 | 1314.24 | 100 | 100 | 100 | 100 | 111.4134 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | 64 | 0 | 382.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 120.0784 | 100
29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 13619.5198 |  |  | 13619.5198 |  | 25d | [5 empty] | 14737.5198 |  | 100% |  | 13619.5198 | 13619.5198
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -89 | 0 | 3132.3799 | 0 | 100% | Finished | 3221.3799 | 3221.3799 | 100 | 100 | 100 | 100 | 97.2372 | 100
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2153.49 | 0 | 0 | 2153.49 | 2016-06-06 08:00 | 5d | 2153.49 | 0 | 0 | 50 | 0 | 2203.49 | 0 | 100% | Finished | 2153.49 | 2153.49 | 100 | 100 | 100 | 100 | 102.3218 | 100
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 2488.8899 | 0 | 0 | 2488.8899 | 2016-06-13 08:00 | 5d | 2488.8899 | 0 | 0 | 1100 | 0 | 3588.8899 | 0 | 100% | Finished | 2488.8899 | 2488.8899 | 100 | 100 | 100 | 100 | 144.1964 | 100
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1930.76 | 0 | 0 | 1930.76 | 2016-06-20 08:00 | 5d | 1930.76 | 0 | 0 | 853 | 0 | 2783.76 | 0 | 100% | Finished | 1930.76 | 1930.76 | 100 | 100 | 100 | 100 | 144.1795 | 100
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | -796 | 0 | 3029 | 0 | 100% | Finished | 3825 | 3825 | 100 | 100 | 100 | 100 | 79.1895 | 100
30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  |  | 18924.97 |  |  | 18924.97 |  | 10d | [5 empty] | 20386.97 |  | 100% |  | 18924.97 | 18924.97
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 100% | Finished | 1931.25 | 1931.25 | 100 | 100 | 100 | 100 | 97.1003 | 100
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d |  | 0 | 2190.3999 | 0 | 0 | 2190.3999 | 2016-07-04 08:00 | 5d | 2190.3999 | 0 | 0 | 251 | 0 | 2441.3999 | 0 | 100% | Finished | 2190.3999 | 2190.3999 | 100 | 100 | 100 | 100 | 111.4591 | 100
21 | Afw san/cv | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-11 08:00 | 5d | 6442.75 | 0 | 0 | -179 | 0 | 6263.75 | 0 | 100% | Finished | 6442.75 | 6442.75 | 100 | 100 | 100 | 100 | 97.2217 | 100
26 | Afw vloer | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 5383.73 | 0 | 0 | 5383.73 | 2016-07-11 08:00 | 5d | 5383.73 | 0 | 0 | 125 | 0 | 5508.73 | 0 | 100% | Finished | 5383.73 | 5383.73 | 100 | 100 | 100 | 100 | 102.3218 | 100
24 | Afw pleister | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 2976.8401 | 0 | 0 | 2976.8401 | 2016-07-11 08:00 | 5d | 2976.8401 | 0 | 0 | 1321 | 0 | 4297.8401 | 0 | 100% | Finished | 2976.8401 | 2976.8401 | 100 | 100 | 100 | 100 | 144.3759 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-11 08:00 | 2016-04-29 08:00 | 8362.4698 | 8362.4698 | 9795.4698 | 2016-04-28 17:00 | 0 | 100% | -1433 | 85.37% | 0 | 100% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-08-08 14:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-29 14:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-29 14:00 | 56013.3294 | 63933.2615 | 56013.3294 | 56013.3294 | 63933.2615 | 63933.2615 | 62139.3239 | 62139.3239 | 1 | 0.85371 | 1 | 1 | 0 | 0.85371 | 1 | 1 | 1
Tracking Period 2 | 2016-04-29 08:00 | 2016-05-30 08:00 | 22035.8397 | 22035.8397 | 21623.8397 | 2016-05-27 17:00 | 0 | 100% | 412 | 101.9% | 0 | 100% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-14 10:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 11:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 11:00 | 54168.3294 | 53559.8511 | 54168.3294 | 54168.3294 | 53559.8511 | 53559.8511 | 53679.7197 | 53679.7197 | 1 | 1.0191 | 1 | 1 | 0 | 1.0191 | 1 | 1 | 1
Tracking Period 3 | 2016-05-30 08:00 | 2016-07-04 08:00 | 35655.3594 | 35655.3594 | 36361.3594 | 2016-07-01 17:00 | 0 | 100% | -706 | 98.06% | 0 | 100% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-19 15:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 10:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-18 10:00 | 55286.3294 | 55661.0565 | 55286.3294 | 55286.3294 | 55661.0565 | 55661.0565 | 55584.9286 | 55584.9286 | 1 | 0.98058 | 1 | 1 | 0 | 0.98058 | 1 | 1 | 1
Tracking Period 4 | 2016-07-04 08:00 | 2016-07-15 17:00 | 54580.3294 | 54580.3294 | 56748.3294 | 2016-07-15 17:00 | 0 | 100% | -2168 | 96.18% | 0 | 100% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-21 14:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-15 17:00 | 56748.3294 | 56748.3294 | 56748.3294 | 56748.3294 | 56748.3294 | 56748.3294 | 56748.3294 | 56748.3294 | 1 | 0.9618 | 1 | 1 | 0 | 0.9618 | 1 | 1 | 1