## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building Foundations | 1 |  |  | 2016-03-21 08:00 | 2016-07-06 17:00 | 78d |  |  | 813663.0605 |  |  | 813663.0605 | 107.375
21 | Voorbereidende werken | 1.1 |  |  | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  |  | 20245 |  |  | 20245 | 4.375
2 | rooien bomen en struiken terrein + afvoer | 1.1.1 |  | FS6;SS3;FS8 | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 18345 | 0 | 0 | 18345 | 4.375
3 | werfinrichting : hekkens, keten, signalisatie | 1.1.2 | 2SS | FS6;FS8 | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 1900 | 0 | 0 | 1900 | 4.375
24 | Afbraak, realisatie bouwput en beschoeiing | 1.2 |  |  | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 793418.0605 |  |  | 793418.0605 | 100.375
22 | sloopwerken | 1.2.1 |  |  | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  |  | 79341 |  |  | 79341 | 18.375
6 | afbraak herenhuis, scheimuur midden | 1.2.1.1 | 2FS;3FS |  | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  | 0 | 79341 | 0 | 0 | 79341 | 18.375
23 | Grondwerken, beschoeiing en funderingspalen | 1.2.2 |  |  | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 714077.0605 |  |  | 714077.0605 | 100.375
8 | voorafgraving terrein voor beschoeiing + geleidebalken | 1.2.2.1 | 2FS;3FS | SS9+3d;SS10+1w 3d | 2016-03-28 08:00 | 2016-04-22 17:00 | 20d |  | 0 | 16046.6797 | 0 | 0 | 16046.6797 | 25.375
9 | installatie bemaling rondom bouwput | 1.2.2.2 | 8SS+3d |  | 2016-03-31 08:00 | 2016-04-04 17:00 | 3d |  | 0 | 24070.0098 | 0 | 0 | 24070.0098 | 4.375
10 | werfinstallatie beschoeiing | 1.2.2.3 | 8SS+1w 3d | FS11 | 2016-04-07 08:00 | 2016-04-08 17:00 | 2d |  | 0 | 40116.6914 | 0 | 0 | 40116.6914 | 1.375
11 | uitvoering beschoeiing tussen as Ab-Hb (zone blok B) | 1.2.2.4 | 10FS | FS12;FS13+1w 2d | 2016-04-11 08:00 | 2016-04-26 17:00 | 12d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 15.375
12 | uitvoering beschoeiing tussen as Aa-Ab (zone blok A) | 1.2.2.5 | 11FS | FS14+2w | 2016-04-27 08:00 | 2016-05-10 17:00 | 10d |  | 0 | 96280.0469 | 0 | 0 | 96280.0469 | 13.375
13 | uitgraving bouwput zone as Ab-Hb | 1.2.2.6 | 11FS+1w 2d |  | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 64186.6992 | 0 | 0 | 64186.6992 | 11.375
14 | uitgraving bouwput zone as Aa-Ab | 1.2.2.7 | 12FS+2w | FS15;FS16-2d | 2016-05-25 08:00 | 2016-06-14 17:00 | 15d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 20.375
15 | uitgraving inrit garage | 1.2.2.8 | 14FS |  | 2016-06-15 08:00 | 2016-06-20 17:00 | 4d |  | 0 | 20058.3398 | 0 | 0 | 20058.3398 | 5.375
16 | werfinstallatie palenmachine | 1.2.2.9 | 14FS-2d | FS17 | 2016-06-13 08:00 | 2016-06-14 17:00 | 2d |  | 0 | 28081.6797 | 0 | 0 | 28081.6797 | 1.375
17 | uitvoering funderingspalen tussen as Ab-Hb | 1.2.2.10 | 16FS | FS18;FS19+4d | 2016-06-15 08:00 | 2016-06-21 17:00 | 5d |  | 0 | 72210.0391 | 0 | 0 | 72210.0391 | 6.375
18 | uitvoering funderingspalen tussen as Aa-Ab | 1.2.2.11 | 17FS |  | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 88256.7188 | 0 | 0 | 88256.7188 | 6.375
19 | Uitgraven paalkoppen as Ab-Hb | 1.2.2.12 | 17FS+4d | FS20 | 2016-06-28 08:00 | 2016-06-29 17:00 | 2d |  | 0 | 44128.3594 | 0 | 0 | 44128.3594 | 1.375
20 | Uitgraven paalkoppen as Aa-Ab | 1.2.2.13 | 19FS |  | 2016-06-30 08:00 | 2016-07-06 17:00 | 5d |  | 0 | 60175.0312 | 0 | 0 | 60175.0312 | 6.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building Foundations | 624h |  |  |  |  | 99 | 100 | 101
21 | Voorbereidende werken | 40h |  |  |  |  | 99 | 100 | 101
2 | rooien bomen en struiken terrein + afvoer | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
3 | werfinrichting : hekkens, keten, signalisatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Afbraak, realisatie bouwput en beschoeiing | 584h |  |  |  |  | 99 | 100 | 101
22 | sloopwerken | 120h |  |  |  |  | 99 | 100 | 101
6 | afbraak herenhuis, scheimuur midden | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Grondwerken, beschoeiing en funderingspalen | 584h |  |  |  |  | 99 | 100 | 101
8 | voorafgraving terrein voor beschoeiing + geleidebalken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | installatie bemaling rondom bouwput | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
10 | werfinstallatie beschoeiing | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
11 | uitvoering beschoeiing tussen as Ab-Hb (zone blok B) | 96h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
12 | uitvoering beschoeiing tussen as Aa-Ab (zone blok A) | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
13 | uitgraving bouwput zone as Ab-Hb | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | uitgraving bouwput zone as Aa-Ab | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | uitgraving inrit garage | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
16 | werfinstallatie palenmachine | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
17 | uitvoering funderingspalen tussen as Ab-Hb | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
18 | uitvoering funderingspalen tussen as Aa-Ab | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
19 | Uitgraven paalkoppen as Ab-Hb | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
20 | Uitgraven paalkoppen as Aa-Ab | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120

## Project Control - TP1
| TP Status Date | 2016-03-29 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Foundations | 2016-03-21 08:00 | 2016-07-06 17:00 | 78d |  |  | 813663.0605 |  |  | 813663.0605 |  | 6d | [5 empty] | 18869 |  | 2.488% |  | 20245 | 115632.6797
21 | Voorbereidende werken | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  |  | 20245 |  |  | 20245 |  | 6d | [5 empty] | 18869 |  | 100% |  | 20245 | 20245
2 | rooien bomen en struiken terrein + afvoer | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 18345 | 0 | 0 | 18345 | 2016-03-21 08:00 | 5d | 18345 | 0 | 0 | -1392 | 0 | 16953 | 0 | 100% | Finished | 18345 | 18345 | 100 | 100 | 100 | 100 | 92.4121 | 100
3 | werfinrichting : hekkens, keten, signalisatie | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 1900 | 0 | 0 | 1900 | 2016-03-21 08:00 | 6d | 1900 | 0 | 0 | 16 | 0 | 1916 | 0 | 100% | Finished | 1900 | 1900 | 100 | 120 | 100 | 100 | 100.8421 | 100
24 | Afbraak, realisatie bouwput en beschoeiing | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 793418.0605 |  |  | 793418.0605 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 95387.6797
22 | sloopwerken | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  |  | 79341 |  |  | 79341 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 79341
6 | afbraak herenhuis, scheimuur midden | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  | 0 | 79341 | 0 | 0 | 79341 |  | 0 | 0 | 79341 | 15d | 0 | 0 | 0 | 79341 | 0% | Not Started | 0 | 79341 | 100 |  | 0 | 100 |  | 0
23 | Grondwerken, beschoeiing en funderingspalen | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 714077.0605 |  |  | 714077.0605 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 16046.6797
8 | voorafgraving terrein voor beschoeiing + geleidebalken | 2016-03-28 08:00 | 2016-04-22 17:00 | 20d |  | 0 | 16046.6797 | 0 | 0 | 16046.6797 |  | 0 | 0 | 16046.6797 | 20d | 0 | 0 | 0 | 16046.6797 | 0% | Not Started | 0 | 16046.6797 | 100 |  | 0 | 100 |  | 0
9 | installatie bemaling rondom bouwput | 2016-03-31 08:00 | 2016-04-04 17:00 | 3d |  | 0 | 24070.0098 | 0 | 0 | 24070.0098 |  | 0 | 0 | 24070.0098 | 3d | 0 | 0 | 0 | 24070.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | werfinstallatie beschoeiing | 2016-04-07 08:00 | 2016-04-08 17:00 | 2d |  | 0 | 40116.6914 | 0 | 0 | 40116.6914 |  | 0 | 0 | 40116.6914 | 2d | 0 | 0 | 0 | 40116.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | uitvoering beschoeiing tussen as Ab-Hb (zone blok B) | 2016-04-11 08:00 | 2016-04-26 17:00 | 12d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 |  | 0 | 0 | 80233.3828 | 12d | 0 | 0 | 0 | 80233.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitvoering beschoeiing tussen as Aa-Ab (zone blok A) | 2016-04-27 08:00 | 2016-05-10 17:00 | 10d |  | 0 | 96280.0469 | 0 | 0 | 96280.0469 |  | 0 | 0 | 96280.0469 | 10d | 0 | 0 | 0 | 96280.0469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | uitgraving bouwput zone as Ab-Hb | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 64186.6992 | 0 | 0 | 64186.6992 |  | 0 | 0 | 64186.6992 | 8d | 0 | 0 | 0 | 64186.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | uitgraving bouwput zone as Aa-Ab | 2016-05-25 08:00 | 2016-06-14 17:00 | 15d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 |  | 0 | 0 | 80233.3828 | 15d | 0 | 0 | 0 | 80233.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitgraving inrit garage | 2016-06-15 08:00 | 2016-06-20 17:00 | 4d |  | 0 | 20058.3398 | 0 | 0 | 20058.3398 |  | 0 | 0 | 20058.3398 | 4d | 0 | 0 | 0 | 20058.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | werfinstallatie palenmachine | 2016-06-13 08:00 | 2016-06-14 17:00 | 2d |  | 0 | 28081.6797 | 0 | 0 | 28081.6797 |  | 0 | 0 | 28081.6797 | 2d | 0 | 0 | 0 | 28081.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | uitvoering funderingspalen tussen as Ab-Hb | 2016-06-15 08:00 | 2016-06-21 17:00 | 5d |  | 0 | 72210.0391 | 0 | 0 | 72210.0391 |  | 0 | 0 | 72210.0391 | 5d | 0 | 0 | 0 | 72210.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | uitvoering funderingspalen tussen as Aa-Ab | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 88256.7188 | 0 | 0 | 88256.7188 |  | 0 | 0 | 88256.7188 | 5d | 0 | 0 | 0 | 88256.7188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Uitgraven paalkoppen as Ab-Hb | 2016-06-28 08:00 | 2016-06-29 17:00 | 2d |  | 0 | 44128.3594 | 0 | 0 | 44128.3594 |  | 0 | 0 | 44128.3594 | 2d | 0 | 0 | 0 | 44128.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Uitgraven paalkoppen as Aa-Ab | 2016-06-30 08:00 | 2016-07-06 17:00 | 5d |  | 0 | 60175.0312 | 0 | 0 | 60175.0312 |  | 0 | 0 | 60175.0312 | 5d | 0 | 0 | 0 | 60175.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-05-03 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Foundations | 2016-03-21 08:00 | 2016-07-06 17:00 | 78d |  |  | 813663.0605 |  |  | 813663.0605 |  | 31d | [5 empty] | 281671.7637 |  | 31.96% |  | 260052.7637 | 356332.8105
21 | Voorbereidende werken | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  |  | 20245 |  |  | 20245 |  | 6d | [5 empty] | 18869 |  | 100% |  | 20245 | 20245
2 | rooien bomen en struiken terrein + afvoer | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 18345 | 0 | 0 | 18345 | 2016-03-21 08:00 | 5d | 18345 | 0 | 0 | -1392 | 0 | 16953 | 0 | 100% | Finished | 18345 | 18345 | 100 | 100 | 100 | 100 | 92.4121 | 100
3 | werfinrichting : hekkens, keten, signalisatie | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 1900 | 0 | 0 | 1900 | 2016-03-21 08:00 | 6d | 1900 | 0 | 0 | 16 | 0 | 1916 | 0 | 100% | Finished | 1900 | 1900 | 100 | 120 | 100 | 100 | 100.8421 | 100
24 | Afbraak, realisatie bouwput en beschoeiing | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 793418.0605 |  |  | 793418.0605 |  | 25d | [5 empty] | 262802.7637 |  | 30.22% |  | 239807.7637 | 336087.8105
22 | sloopwerken | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  |  | 79341 |  |  | 79341 |  | 18d | [5 empty] | 78521 |  | 100% |  | 79341 | 79341
6 | afbraak herenhuis, scheimuur midden | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  | 0 | 79341 | 0 | 0 | 79341 | 2016-03-29 08:00 | 18d | 79341 | 0 | 0 | -820 | 0 | 78521 | 0 | 100% | Finished | 79341 | 79341 | 100 | 120 | 100 | 100 | 98.9665 | 100
23 | Grondwerken, beschoeiing en funderingspalen | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 714077.0605 |  |  | 714077.0605 |  | 25d | [5 empty] | 184281.7637 |  | 22.47% |  | 160466.7637 | 256746.8105
8 | voorafgraving terrein voor beschoeiing + geleidebalken | 2016-03-28 08:00 | 2016-04-22 17:00 | 20d |  | 0 | 16046.6797 | 0 | 0 | 16046.6797 | 2016-03-29 08:00 | 20d | 16046.6797 | 0 | 0 | -251 | 0 | 15795.6797 | 0 | 100% | Finished | 16046.6797 | 16046.6797 | 100 | 100 | 100 | 100 | 98.4358 | 100
9 | installatie bemaling rondom bouwput | 2016-03-31 08:00 | 2016-04-04 17:00 | 3d |  | 0 | 24070.0098 | 0 | 0 | 24070.0098 | 2016-04-01 08:00 | 4d | 24070.0098 | 0 | 0 | 3876 | 0 | 27946.0098 | 0 | 100% | Finished | 24070.0098 | 24070.0098 | 100 | 133.3333 | 100 | 100 | 116.103 | 100
10 | werfinstallatie beschoeiing | 2016-04-07 08:00 | 2016-04-08 17:00 | 2d |  | 0 | 40116.6914 | 0 | 0 | 40116.6914 | 2016-04-08 08:00 | 3d | 40116.6914 | 0 | 0 | 9056 | 0 | 49172.6914 | 0 | 100% | Finished | 40116.6914 | 40116.6914 | 100 | 150 | 100 | 100 | 122.5741 | 100
11 | uitvoering beschoeiing tussen as Ab-Hb (zone blok B) | 2016-04-11 08:00 | 2016-04-26 17:00 | 12d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 2016-04-13 08:00 | 14d | 80233.3828 | 0 | 0 | 11134 | 0 | 91367.3828 | 0 | 100% | Finished | 80233.3828 | 80233.3828 | 100 | 116.6667 | 100 | 100 | 113.877 | 100
12 | uitvoering beschoeiing tussen as Aa-Ab (zone blok A) | 2016-04-27 08:00 | 2016-05-10 17:00 | 10d |  | 0 | 96280.0469 | 0 | 0 | 96280.0469 |  | 0 | 0 | 96280.0469 | 10d | 0 | 0 | 0 | 96280.0469 | 0% | Not Started | 0 | 96280.0469 | 100 |  | 0 | 100 |  | 0
13 | uitgraving bouwput zone as Ab-Hb | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 64186.6992 | 0 | 0 | 64186.6992 |  | 0 | 0 | 64186.6992 | 8d | 0 | 0 | 0 | 64186.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | uitgraving bouwput zone as Aa-Ab | 2016-05-25 08:00 | 2016-06-14 17:00 | 15d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 |  | 0 | 0 | 80233.3828 | 15d | 0 | 0 | 0 | 80233.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitgraving inrit garage | 2016-06-15 08:00 | 2016-06-20 17:00 | 4d |  | 0 | 20058.3398 | 0 | 0 | 20058.3398 |  | 0 | 0 | 20058.3398 | 4d | 0 | 0 | 0 | 20058.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | werfinstallatie palenmachine | 2016-06-13 08:00 | 2016-06-14 17:00 | 2d |  | 0 | 28081.6797 | 0 | 0 | 28081.6797 |  | 0 | 0 | 28081.6797 | 2d | 0 | 0 | 0 | 28081.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | uitvoering funderingspalen tussen as Ab-Hb | 2016-06-15 08:00 | 2016-06-21 17:00 | 5d |  | 0 | 72210.0391 | 0 | 0 | 72210.0391 |  | 0 | 0 | 72210.0391 | 5d | 0 | 0 | 0 | 72210.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | uitvoering funderingspalen tussen as Aa-Ab | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 88256.7188 | 0 | 0 | 88256.7188 |  | 0 | 0 | 88256.7188 | 5d | 0 | 0 | 0 | 88256.7188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Uitgraven paalkoppen as Ab-Hb | 2016-06-28 08:00 | 2016-06-29 17:00 | 2d |  | 0 | 44128.3594 | 0 | 0 | 44128.3594 |  | 0 | 0 | 44128.3594 | 2d | 0 | 0 | 0 | 44128.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Uitgraven paalkoppen as Aa-Ab | 2016-06-30 08:00 | 2016-07-06 17:00 | 5d |  | 0 | 60175.0312 | 0 | 0 | 60175.0312 |  | 0 | 0 | 60175.0312 | 5d | 0 | 0 | 0 | 60175.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-07-01 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Foundations | 2016-03-21 08:00 | 2016-07-06 17:00 | 78d |  |  | 813663.0605 |  |  | 813663.0605 |  | 74d | [5 empty] | 654818.9512 |  | 76.33% |  | 621102.9512 | 813663.0605
21 | Voorbereidende werken | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  |  | 20245 |  |  | 20245 |  | 6d | [5 empty] | 18869 |  | 100% |  | 20245 | 20245
2 | rooien bomen en struiken terrein + afvoer | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 18345 | 0 | 0 | 18345 | 2016-03-21 08:00 | 5d | 18345 | 0 | 0 | -1392 | 0 | 16953 | 0 | 100% | Finished | 18345 | 18345 | 100 | 100 | 100 | 100 | 92.4121 | 100
3 | werfinrichting : hekkens, keten, signalisatie | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 1900 | 0 | 0 | 1900 | 2016-03-21 08:00 | 6d | 1900 | 0 | 0 | 16 | 0 | 1916 | 0 | 100% | Finished | 1900 | 1900 | 100 | 120 | 100 | 100 | 100.8421 | 100
24 | Afbraak, realisatie bouwput en beschoeiing | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 793418.0605 |  |  | 793418.0605 |  | 68d | [5 empty] | 635949.9512 |  | 75.73% |  | 600857.9512 | 793418.0605
22 | sloopwerken | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  |  | 79341 |  |  | 79341 |  | 18d | [5 empty] | 78521 |  | 100% |  | 79341 | 79341
6 | afbraak herenhuis, scheimuur midden | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  | 0 | 79341 | 0 | 0 | 79341 | 2016-03-29 08:00 | 18d | 79341 | 0 | 0 | -820 | 0 | 78521 | 0 | 100% | Finished | 79341 | 79341 | 100 | 120 | 100 | 100 | 98.9665 | 100
23 | Grondwerken, beschoeiing en funderingspalen | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 714077.0605 |  |  | 714077.0605 |  | 68d | [5 empty] | 557428.9512 |  | 73.03% |  | 521516.9512 | 714077.0605
8 | voorafgraving terrein voor beschoeiing + geleidebalken | 2016-03-28 08:00 | 2016-04-22 17:00 | 20d |  | 0 | 16046.6797 | 0 | 0 | 16046.6797 | 2016-03-29 08:00 | 20d | 16046.6797 | 0 | 0 | -251 | 0 | 15795.6797 | 0 | 100% | Finished | 16046.6797 | 16046.6797 | 100 | 100 | 100 | 100 | 98.4358 | 100
9 | installatie bemaling rondom bouwput | 2016-03-31 08:00 | 2016-04-04 17:00 | 3d |  | 0 | 24070.0098 | 0 | 0 | 24070.0098 | 2016-04-01 08:00 | 4d | 24070.0098 | 0 | 0 | 3876 | 0 | 27946.0098 | 0 | 100% | Finished | 24070.0098 | 24070.0098 | 100 | 133.3333 | 100 | 100 | 116.103 | 100
10 | werfinstallatie beschoeiing | 2016-04-07 08:00 | 2016-04-08 17:00 | 2d |  | 0 | 40116.6914 | 0 | 0 | 40116.6914 | 2016-04-08 08:00 | 3d | 40116.6914 | 0 | 0 | 9056 | 0 | 49172.6914 | 0 | 100% | Finished | 40116.6914 | 40116.6914 | 100 | 150 | 100 | 100 | 122.5741 | 100
11 | uitvoering beschoeiing tussen as Ab-Hb (zone blok B) | 2016-04-11 08:00 | 2016-04-26 17:00 | 12d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 2016-04-13 08:00 | 14d | 80233.3828 | 0 | 0 | 11134 | 0 | 91367.3828 | 0 | 100% | Finished | 80233.3828 | 80233.3828 | 100 | 116.6667 | 100 | 100 | 113.877 | 100
12 | uitvoering beschoeiing tussen as Aa-Ab (zone blok A) | 2016-04-27 08:00 | 2016-05-10 17:00 | 10d |  | 0 | 96280.0469 | 0 | 0 | 96280.0469 | 2016-05-03 08:00 | 11d | 96280.0469 | 0 | 0 | -4799 | 0 | 91481.0469 | 0 | 100% | Finished | 96280.0469 | 96280.0469 | 100 | 110 | 100 | 100 | 95.0156 | 100
13 | uitgraving bouwput zone as Ab-Hb | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 64186.6992 | 0 | 0 | 64186.6992 | 2016-05-06 08:00 | 8d | 64186.6992 | 0 | 0 | 2627 | 0 | 66813.6992 | 0 | 100% | Finished | 64186.6992 | 64186.6992 | 100 | 100 | 100 | 100 | 104.0927 | 100
14 | uitgraving bouwput zone as Aa-Ab | 2016-05-25 08:00 | 2016-06-14 17:00 | 15d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 2016-06-01 08:00 | 15d | 80233.3828 | 0 | 0 | 3881 | 0 | 84114.3828 | 0 | 100% | Finished | 80233.3828 | 80233.3828 | 100 | 100 | 100 | 100 | 104.8371 | 100
15 | uitgraving inrit garage | 2016-06-15 08:00 | 2016-06-20 17:00 | 4d |  | 0 | 20058.3398 | 0 | 0 | 20058.3398 | 2016-06-22 08:00 | 4d | 20058.3398 | 0 | 0 | -1687 | 0 | 18371.3398 | 0 | 100% | Finished | 20058.3398 | 20058.3398 | 100 | 100 | 100 | 100 | 91.5895 | 100
16 | werfinstallatie palenmachine | 2016-06-13 08:00 | 2016-06-14 17:00 | 2d |  | 0 | 28081.6797 | 0 | 0 | 28081.6797 | 2016-06-20 08:00 | 2d | 28081.6797 | 0 | 0 | 2275 | 0 | 30356.6797 | 0 | 100% | Finished | 28081.6797 | 28081.6797 | 100 | 100 | 100 | 100 | 108.1014 | 100
17 | uitvoering funderingspalen tussen as Ab-Hb | 2016-06-15 08:00 | 2016-06-21 17:00 | 5d |  | 0 | 72210.0391 | 0 | 0 | 72210.0391 | 2016-06-22 08:00 | 7d | 72210.0391 | 0 | 0 | 9800 | 0 | 82010.0391 | 0 | 100% | Finished | 72210.0391 | 72210.0391 | 100 | 140 | 100 | 100 | 113.5715 | 100
18 | uitvoering funderingspalen tussen as Aa-Ab | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 88256.7188 | 0 | 0 | 88256.7188 |  | 0 | 0 | 88256.7188 | 5d | 0 | 0 | 0 | 88256.7188 | 0% | Not Started | 0 | 88256.7188 | 100 |  | 0 | 100 |  | 0
19 | Uitgraven paalkoppen as Ab-Hb | 2016-06-28 08:00 | 2016-06-29 17:00 | 2d |  | 0 | 44128.3594 | 0 | 0 | 44128.3594 |  | 0 | 0 | 44128.3594 | 2d | 0 | 0 | 0 | 44128.3594 | 0% | Not Started | 0 | 44128.3594 | 100 |  | 0 | 100 |  | 0
20 | Uitgraven paalkoppen as Aa-Ab | 2016-06-30 08:00 | 2016-07-06 17:00 | 5d |  | 0 | 60175.0312 | 0 | 0 | 60175.0312 |  | 0 | 0 | 60175.0312 | 5d | 0 | 0 | 0 | 60175.0312 | 0% | Not Started | 0 | 60175.0312 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-07-20 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Foundations | 2016-03-21 08:00 | 2016-07-06 17:00 | 78d |  |  | 813663.0605 |  |  | 813663.0605 |  | 88d | [5 empty] | 879701.0605 |  | 100% |  | 813663.0605 | 813663.0605
21 | Voorbereidende werken | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  |  | 20245 |  |  | 20245 |  | 6d | [5 empty] | 18869 |  | 100% |  | 20245 | 20245
2 | rooien bomen en struiken terrein + afvoer | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 18345 | 0 | 0 | 18345 | 2016-03-21 08:00 | 5d | 18345 | 0 | 0 | -1392 | 0 | 16953 | 0 | 100% | Finished | 18345 | 18345 | 100 | 100 | 100 | 100 | 92.4121 | 100
3 | werfinrichting : hekkens, keten, signalisatie | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 1900 | 0 | 0 | 1900 | 2016-03-21 08:00 | 6d | 1900 | 0 | 0 | 16 | 0 | 1916 | 0 | 100% | Finished | 1900 | 1900 | 100 | 120 | 100 | 100 | 100.8421 | 100
24 | Afbraak, realisatie bouwput en beschoeiing | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 793418.0605 |  |  | 793418.0605 |  | 82d | [5 empty] | 860832.0605 |  | 100% |  | 793418.0605 | 793418.0605
22 | sloopwerken | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  |  | 79341 |  |  | 79341 |  | 18d | [5 empty] | 78521 |  | 100% |  | 79341 | 79341
6 | afbraak herenhuis, scheimuur midden | 2016-03-28 08:00 | 2016-04-15 17:00 | 15d |  | 0 | 79341 | 0 | 0 | 79341 | 2016-03-29 08:00 | 18d | 79341 | 0 | 0 | -820 | 0 | 78521 | 0 | 100% | Finished | 79341 | 79341 | 100 | 120 | 100 | 100 | 98.9665 | 100
23 | Grondwerken, beschoeiing en funderingspalen | 2016-03-28 08:00 | 2016-07-06 17:00 | 73d |  |  | 714077.0605 |  |  | 714077.0605 |  | 82d | [5 empty] | 782311.0605 |  | 100% |  | 714077.0605 | 714077.0605
8 | voorafgraving terrein voor beschoeiing + geleidebalken | 2016-03-28 08:00 | 2016-04-22 17:00 | 20d |  | 0 | 16046.6797 | 0 | 0 | 16046.6797 | 2016-03-29 08:00 | 20d | 16046.6797 | 0 | 0 | -251 | 0 | 15795.6797 | 0 | 100% | Finished | 16046.6797 | 16046.6797 | 100 | 100 | 100 | 100 | 98.4358 | 100
9 | installatie bemaling rondom bouwput | 2016-03-31 08:00 | 2016-04-04 17:00 | 3d |  | 0 | 24070.0098 | 0 | 0 | 24070.0098 | 2016-04-01 08:00 | 4d | 24070.0098 | 0 | 0 | 3876 | 0 | 27946.0098 | 0 | 100% | Finished | 24070.0098 | 24070.0098 | 100 | 133.3333 | 100 | 100 | 116.103 | 100
10 | werfinstallatie beschoeiing | 2016-04-07 08:00 | 2016-04-08 17:00 | 2d |  | 0 | 40116.6914 | 0 | 0 | 40116.6914 | 2016-04-08 08:00 | 3d | 40116.6914 | 0 | 0 | 9056 | 0 | 49172.6914 | 0 | 100% | Finished | 40116.6914 | 40116.6914 | 100 | 150 | 100 | 100 | 122.5741 | 100
11 | uitvoering beschoeiing tussen as Ab-Hb (zone blok B) | 2016-04-11 08:00 | 2016-04-26 17:00 | 12d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 2016-04-13 08:00 | 14d | 80233.3828 | 0 | 0 | 11134 | 0 | 91367.3828 | 0 | 100% | Finished | 80233.3828 | 80233.3828 | 100 | 116.6667 | 100 | 100 | 113.877 | 100
12 | uitvoering beschoeiing tussen as Aa-Ab (zone blok A) | 2016-04-27 08:00 | 2016-05-10 17:00 | 10d |  | 0 | 96280.0469 | 0 | 0 | 96280.0469 | 2016-05-03 08:00 | 11d | 96280.0469 | 0 | 0 | -4799 | 0 | 91481.0469 | 0 | 100% | Finished | 96280.0469 | 96280.0469 | 100 | 110 | 100 | 100 | 95.0156 | 100
13 | uitgraving bouwput zone as Ab-Hb | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 64186.6992 | 0 | 0 | 64186.6992 | 2016-05-06 08:00 | 8d | 64186.6992 | 0 | 0 | 2627 | 0 | 66813.6992 | 0 | 100% | Finished | 64186.6992 | 64186.6992 | 100 | 100 | 100 | 100 | 104.0927 | 100
14 | uitgraving bouwput zone as Aa-Ab | 2016-05-25 08:00 | 2016-06-14 17:00 | 15d |  | 0 | 80233.3828 | 0 | 0 | 80233.3828 | 2016-06-01 08:00 | 15d | 80233.3828 | 0 | 0 | 3881 | 0 | 84114.3828 | 0 | 100% | Finished | 80233.3828 | 80233.3828 | 100 | 100 | 100 | 100 | 104.8371 | 100
15 | uitgraving inrit garage | 2016-06-15 08:00 | 2016-06-20 17:00 | 4d |  | 0 | 20058.3398 | 0 | 0 | 20058.3398 | 2016-06-22 08:00 | 4d | 20058.3398 | 0 | 0 | -1687 | 0 | 18371.3398 | 0 | 100% | Finished | 20058.3398 | 20058.3398 | 100 | 100 | 100 | 100 | 91.5895 | 100
16 | werfinstallatie palenmachine | 2016-06-13 08:00 | 2016-06-14 17:00 | 2d |  | 0 | 28081.6797 | 0 | 0 | 28081.6797 | 2016-06-20 08:00 | 2d | 28081.6797 | 0 | 0 | 2275 | 0 | 30356.6797 | 0 | 100% | Finished | 28081.6797 | 28081.6797 | 100 | 100 | 100 | 100 | 108.1014 | 100
17 | uitvoering funderingspalen tussen as Ab-Hb | 2016-06-15 08:00 | 2016-06-21 17:00 | 5d |  | 0 | 72210.0391 | 0 | 0 | 72210.0391 | 2016-06-22 08:00 | 7d | 72210.0391 | 0 | 0 | 9800 | 0 | 82010.0391 | 0 | 100% | Finished | 72210.0391 | 72210.0391 | 100 | 140 | 100 | 100 | 113.5715 | 100
18 | uitvoering funderingspalen tussen as Aa-Ab | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 88256.7188 | 0 | 0 | 88256.7188 | 2016-07-01 08:00 | 7d | 88256.7188 | 0 | 0 | 17452 | 0 | 105708.7188 | 0 | 100% | Finished | 88256.7188 | 88256.7188 | 100 | 140 | 100 | 100 | 119.7741 | 100
19 | Uitgraven paalkoppen as Ab-Hb | 2016-06-28 08:00 | 2016-06-29 17:00 | 2d |  | 0 | 44128.3594 | 0 | 0 | 44128.3594 | 2016-07-07 08:00 | 3d | 44128.3594 | 0 | 0 | 8561 | 0 | 52689.3594 | 0 | 100% | Finished | 44128.3594 | 44128.3594 | 100 | 150 | 100 | 100 | 119.4002 | 100
20 | Uitgraven paalkoppen as Aa-Ab | 2016-06-30 08:00 | 2016-07-06 17:00 | 5d |  | 0 | 60175.0312 | 0 | 0 | 60175.0312 | 2016-07-12 08:00 | 7d | 60175.0312 | 0 | 0 | 6309 | 0 | 66484.0312 | 0 | 100% | Finished | 60175.0312 | 60175.0312 | 100 | 140 | 100 | 100 | 110.4844 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-21 08:00 | 2016-03-29 08:00 | 115632.6797 | 20245 | 18869 | 2016-03-25 17:00 | -95387.6797 | 17.51% | 1376 | 107.3% | -1d | 83.33% | 100% | 2016-07-20 09:00 | 2017-12-04 12:00 | 2017-10-23 10:00 | 2016-07-13 17:00 | 2017-12-04 12:00 | 2017-10-23 14:00 | 2016-07-07 17:00 | 2016-07-28 14:00 | 2016-07-20 14:00 | 812287.0605 | 758360.4984 | 4550608.0197 | 970970.6727 | 4242597.5039 | 906258.798 | 907001.8783 | 792931.0648 | 0.83333 | 1.0729 | 0.17508 | 1 | -1 | 1.0729 | 1 | 0.83333 | 1
Tracking Period 2 | 2016-03-29 08:00 | 2016-05-03 08:00 | 356332.8105 | 260052.7637 | 281671.7637 | 2016-04-26 17:00 | -96280.0469 | 72.98% | -21619 | 92.32% | -4d | 87.1% | 100% | 2016-07-20 10:00 | 2016-08-16 16:00 | 2016-08-29 15:00 | 2016-07-19 11:00 | 2016-08-16 16:00 | 2016-08-25 09:00 | 2016-07-12 17:00 | 2016-07-22 12:00 | 2016-07-29 11:00 | 835282.0605 | 881305.4169 | 1040246.7169 | 917298.4008 | 1103309.4265 | 970140.0322 | 907532.2461 | 888174.1761 | 0.87097 | 0.92325 | 0.7298 | 1 | -4 | 0.92325 | 1 | 0.87097 | 1
Tracking Period 3 | 2016-05-03 08:00 | 2016-07-01 08:00 | 813663.0605 | 621102.9512 | 654818.9512 | 2016-06-21 17:00 | -192560.1094 | 76.33% | -33716 | 94.85% | -7d | 90.54% | 100% | 2016-08-02 12:00 | 2016-08-10 09:00 | 2016-08-17 15:00 | 2016-08-01 12:00 | 2016-08-10 09:00 | 2016-08-11 15:00 | 2016-07-15 17:00 | 2016-07-19 09:00 | 2016-07-19 15:00 | 847379.0605 | 857832.0082 | 907078.3353 | 867497.2809 | 920772.0029 | 879042.3276 | 866080.5479 | 859694.1392 | 0.90541 | 0.94851 | 0.76334 | 1 | -7 | 0.94851 | 1 | 0.90541 | 1
Tracking Period 4 | 2016-07-01 08:00 | 2016-07-20 17:00 | 813663.0605 | 813663.0605 | 879701.0605 | 2016-07-06 17:00 | 0 | 100% | -66038 | 92.49% | -10d | 88.64% | 100% | 2016-07-06 17:00 | 2016-07-06 17:00 | 2016-07-15 11:00 | 2016-07-20 17:00 | 2016-07-20 17:00 | 2016-07-20 17:00 | 2016-07-20 17:00 | 2016-07-20 17:00 | 2016-07-20 17:00 | 879701.0605 | 879701.0605 | 879701.0605 | 879701.0605 | 879701.0605 | 879701.0605 | 879701.0605 | 879701.0605 | 0.88636 | 0.92493 | 1 | 1 | -10 | 0.92493 | 1 | 0.88636 | 1