## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building Structural Work (2) | 1 |  |  | 2016-03-21 08:00 | 2016-09-15 17:00 | 129d |  |  | 1797873.6172 |  |  | 1797873.6172 | 178.375
20 | betonstructuur blok A gelijkvloers | 1.1 |  |  | 2016-03-21 08:00 | 2016-05-17 17:00 | 42d |  |  | 468163.2734 |  |  | 468163.2734 | 57.375
1 | kolommen gelijkvloers blok A | 1.1.1 |  | SS2 | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 78027.2109 | 0 | 0 | 78027.2109 | 11.375
2 | wanden gelijkvloers blok A | 1.1.2 | 1SS | FS3-2w | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 93632.6484 | 0 | 0 | 93632.6484 | 18.375
3 | balken/liggers boven gelijkvloers blok A | 1.1.3 | 2FS-2w | FS4 | 2016-03-28 08:00 | 2016-04-29 17:00 | 25d |  | 0 | 101435.3828 | 0 | 0 | 101435.3828 | 32.375
4 | afdek gelijkvloers blok A welfsels + opstort druklaag | 1.1.4 | 3FS | FS5;FS7 | 2016-05-02 08:00 | 2016-05-17 17:00 | 12d |  | 0 | 195068.0312 | 0 | 0 | 195068.0312 | 15.375
21 | betonstructuur blok A nivo +1 | 1.2 |  |  | 2016-05-18 08:00 | 2016-06-20 17:00 | 24d |  |  | 355516.9922 |  |  | 355516.9922 | 33.375
5 | kolommen +1 blok A | 1.2.1 | 4FS | SS6 | 2016-05-18 08:00 | 2016-05-24 17:00 | 5d |  | 0 | 39904.9688 | 0 | 0 | 39904.9688 | 6.375
6 | wanden kernen +1 blok A | 1.2.2 | 5SS |  | 2016-05-18 08:00 | 2016-05-31 17:00 | 10d |  | 0 | 47160.4219 | 0 | 0 | 47160.4219 | 13.375
7 | dragend metselwerk snelbouw +1 blok A | 1.2.3 | 4FS | FS8-1w | 2016-05-18 08:00 | 2016-06-10 17:00 | 18d |  | 0 | 119714.8984 | 0 | 0 | 119714.8984 | 23.375
8 | balken/liggers boven +1 blok A | 1.2.4 | 7FS-1w | FS9 | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 50788.1406 | 0 | 0 | 50788.1406 | 4.375
9 | afdek verdieping +1 blok A welfsels + opstort druklaag | 1.2.5 | 8FS | FS10+2w | 2016-06-13 08:00 | 2016-06-20 17:00 | 6d |  | 0 | 97948.5625 | 0 | 0 | 97948.5625 | 7.375
22 | betonstructuur blok A nivo +2 | 1.3 |  |  | 2016-07-05 08:00 | 2016-08-09 17:00 | 26d |  |  | 386431.4922 |  |  | 386431.4922 | 35.375
10 | kolommen +2 blok A | 1.3.1 | 9FS+2w | SS11;SS12 | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 43374.9609 | 0 | 0 | 43374.9609 | 6.375
11 | wanden kernen +2 blok A | 1.3.2 | 10SS |  | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 51261.3203 | 0 | 0 | 51261.3203 | 6.375
12 | dragend metselwerk snelbouw +2 blok A | 1.3.3 | 10SS | FS13-1w | 2016-07-05 08:00 | 2016-07-26 17:00 | 16d |  | 0 | 130124.8906 | 0 | 0 | 130124.8906 | 21.375
13 | balken/liggers boven +2 blok A | 1.3.4 | 12FS-1w | FS14 | 2016-07-20 08:00 | 2016-08-01 17:00 | 9d |  | 0 | 55204.5 | 0 | 0 | 55204.5 | 12.375
14 | afdek verdieping +2 blok A welfsels + opstort druklaag | 1.3.5 | 13FS | FS15;FS17 | 2016-08-02 08:00 | 2016-08-09 17:00 | 6d |  | 0 | 106465.8203 | 0 | 0 | 106465.8203 | 7.375
23 | betonstructuur blok A nivo +3 | 1.4 |  |  | 2016-08-10 08:00 | 2016-09-15 17:00 | 27d |  |  | 587761.8594 |  |  | 587761.8594 | 36.375
15 | kolommen +3 blok A | 1.4.1 | 14FS | SS16 | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 65973.2734 | 0 | 0 | 65973.2734 | 2.375
16 | wanden kernen +3 blok A | 1.4.2 | 15SS |  | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 77968.4062 | 0 | 0 | 77968.4062 | 2.375
17 | dragend metselwerk snelbouw +3 blok A | 1.4.3 | 14FS | FS18-4d | 2016-08-10 08:00 | 2016-08-31 17:00 | 16d |  | 0 | 197919.8125 | 0 | 0 | 197919.8125 | 21.375
18 | balken/liggers boven +3 blok A | 1.4.4 | 17FS-4d | FS19 | 2016-08-26 08:00 | 2016-09-07 17:00 | 9d |  | 0 | 83965.9766 | 0 | 0 | 83965.9766 | 12.375
19 | afdek verdieping +3 blok A welfsels + opstort druklaag | 1.4.5 | 18FS |  | 2016-09-08 08:00 | 2016-09-15 17:00 | 6d |  | 0 | 161934.3906 | 0 | 0 | 161934.3906 | 7.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building Structural Work (2) | 1032h |  |  |  |  | 99 | 100 | 101
20 | betonstructuur blok A gelijkvloers | 336h |  |  |  |  | 99 | 100 | 101
1 | kolommen gelijkvloers blok A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | wanden gelijkvloers blok A | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | balken/liggers boven gelijkvloers blok A | 200h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
4 | afdek gelijkvloers blok A welfsels + opstort druklaag | 96h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | betonstructuur blok A nivo +1 | 192h |  |  |  |  | 99 | 100 | 101
5 | kolommen +1 blok A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | wanden kernen +1 blok A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | dragend metselwerk snelbouw +1 blok A | 144h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
8 | balken/liggers boven +1 blok A | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
9 | afdek verdieping +1 blok A welfsels + opstort druklaag | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
22 | betonstructuur blok A nivo +2 | 208h |  |  |  |  | 99 | 100 | 101
10 | kolommen +2 blok A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | wanden kernen +2 blok A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | dragend metselwerk snelbouw +2 blok A | 128h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
13 | balken/liggers boven +2 blok A | 72h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
14 | afdek verdieping +2 blok A welfsels + opstort druklaag | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
23 | betonstructuur blok A nivo +3 | 216h |  |  |  |  | 99 | 100 | 101
15 | kolommen +3 blok A | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | wanden kernen +3 blok A | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | dragend metselwerk snelbouw +3 blok A | 128h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
18 | balken/liggers boven +3 blok A | 72h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
19 | afdek verdieping +3 blok A welfsels + opstort druklaag | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120

## Project Control - TP1
| TP Status Date | 2016-05-24 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Structural Work (2) | 2016-03-21 08:00 | 2016-09-15 17:00 | 129d |  |  | 1797873.6172 |  |  | 1797873.6172 |  | 46d | [5 empty] | 465147.2734 |  | 26.04% |  | 468163.2734 | 674943.5625
20 | betonstructuur blok A gelijkvloers | 2016-03-21 08:00 | 2016-05-17 17:00 | 42d |  |  | 468163.2734 |  |  | 468163.2734 |  | 46d | [5 empty] | 465147.2734 |  | 100% |  | 468163.2734 | 468163.2734
1 | kolommen gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 78027.2109 | 0 | 0 | 78027.2109 | 2016-03-21 08:00 | 10d | 78027.2109 | 0 | 0 | 7245 | 0 | 85272.2109 | 0 | 100% | Finished | 78027.2109 | 78027.2109 | 100 | 100 | 100 | 100 | 109.2852 | 100
2 | wanden gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 93632.6484 | 0 | 0 | 93632.6484 | 2016-03-21 08:00 | 15d | 93632.6484 | 0 | 0 | -5585 | 0 | 88047.6484 | 0 | 100% | Finished | 93632.6484 | 93632.6484 | 100 | 100 | 100 | 100 | 94.0352 | 100
3 | balken/liggers boven gelijkvloers blok A | 2016-03-28 08:00 | 2016-04-29 17:00 | 25d |  | 0 | 101435.3828 | 0 | 0 | 101435.3828 | 2016-03-28 08:00 | 29d | 101435.3828 | 0 | 0 | 12833 | 0 | 114268.3828 | 0 | 100% | Finished | 101435.3828 | 101435.3828 | 100 | 116 | 100 | 100 | 112.6514 | 100
4 | afdek gelijkvloers blok A welfsels + opstort druklaag | 2016-05-02 08:00 | 2016-05-17 17:00 | 12d |  | 0 | 195068.0312 | 0 | 0 | 195068.0312 | 2016-05-06 08:00 | 12d | 195068.0312 | 0 | 0 | -17509 | 0 | 177559.0312 | 0 | 100% | Finished | 195068.0312 | 195068.0312 | 100 | 100 | 100 | 100 | 91.0242 | 100
21 | betonstructuur blok A nivo +1 | 2016-05-18 08:00 | 2016-06-20 17:00 | 24d |  |  | 355516.9922 |  |  | 355516.9922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 206780.2891
5 | kolommen +1 blok A | 2016-05-18 08:00 | 2016-05-24 17:00 | 5d |  | 0 | 39904.9688 | 0 | 0 | 39904.9688 |  | 0 | 0 | 39904.9688 | 5d | 0 | 0 | 0 | 39904.9688 | 0% | Not Started | 0 | 39904.9688 | 100 |  | 0 | 100 |  | 0
6 | wanden kernen +1 blok A | 2016-05-18 08:00 | 2016-05-31 17:00 | 10d |  | 0 | 47160.4219 | 0 | 0 | 47160.4219 |  | 0 | 0 | 47160.4219 | 10d | 0 | 0 | 0 | 47160.4219 | 0% | Not Started | 0 | 47160.4219 | 100 |  | 0 | 100 |  | 0
7 | dragend metselwerk snelbouw +1 blok A | 2016-05-18 08:00 | 2016-06-10 17:00 | 18d |  | 0 | 119714.8984 | 0 | 0 | 119714.8984 |  | 0 | 0 | 119714.8984 | 18d | 0 | 0 | 0 | 119714.8984 | 0% | Not Started | 0 | 119714.8984 | 100 |  | 0 | 100 |  | 0
8 | balken/liggers boven +1 blok A | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 50788.1406 | 0 | 0 | 50788.1406 |  | 0 | 0 | 50788.1406 | 5d | 0 | 0 | 0 | 50788.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | afdek verdieping +1 blok A welfsels + opstort druklaag | 2016-06-13 08:00 | 2016-06-20 17:00 | 6d |  | 0 | 97948.5625 | 0 | 0 | 97948.5625 |  | 0 | 0 | 97948.5625 | 6d | 0 | 0 | 0 | 97948.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | betonstructuur blok A nivo +2 | 2016-07-05 08:00 | 2016-08-09 17:00 | 26d |  |  | 386431.4922 |  |  | 386431.4922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | kolommen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 43374.9609 | 0 | 0 | 43374.9609 |  | 0 | 0 | 43374.9609 | 5d | 0 | 0 | 0 | 43374.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | wanden kernen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 51261.3203 | 0 | 0 | 51261.3203 |  | 0 | 0 | 51261.3203 | 5d | 0 | 0 | 0 | 51261.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | dragend metselwerk snelbouw +2 blok A | 2016-07-05 08:00 | 2016-07-26 17:00 | 16d |  | 0 | 130124.8906 | 0 | 0 | 130124.8906 |  | 0 | 0 | 130124.8906 | 16d | 0 | 0 | 0 | 130124.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | balken/liggers boven +2 blok A | 2016-07-20 08:00 | 2016-08-01 17:00 | 9d |  | 0 | 55204.5 | 0 | 0 | 55204.5 |  | 0 | 0 | 55204.5 | 9d | 0 | 0 | 0 | 55204.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | afdek verdieping +2 blok A welfsels + opstort druklaag | 2016-08-02 08:00 | 2016-08-09 17:00 | 6d |  | 0 | 106465.8203 | 0 | 0 | 106465.8203 |  | 0 | 0 | 106465.8203 | 6d | 0 | 0 | 0 | 106465.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | betonstructuur blok A nivo +3 | 2016-08-10 08:00 | 2016-09-15 17:00 | 27d |  |  | 587761.8594 |  |  | 587761.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | kolommen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 65973.2734 | 0 | 0 | 65973.2734 |  | 0 | 0 | 65973.2734 | 3d | 0 | 0 | 0 | 65973.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | wanden kernen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 77968.4062 | 0 | 0 | 77968.4062 |  | 0 | 0 | 77968.4062 | 3d | 0 | 0 | 0 | 77968.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | dragend metselwerk snelbouw +3 blok A | 2016-08-10 08:00 | 2016-08-31 17:00 | 16d |  | 0 | 197919.8125 | 0 | 0 | 197919.8125 |  | 0 | 0 | 197919.8125 | 16d | 0 | 0 | 0 | 197919.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | balken/liggers boven +3 blok A | 2016-08-26 08:00 | 2016-09-07 17:00 | 9d |  | 0 | 83965.9766 | 0 | 0 | 83965.9766 |  | 0 | 0 | 83965.9766 | 9d | 0 | 0 | 0 | 83965.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | afdek verdieping +3 blok A welfsels + opstort druklaag | 2016-09-08 08:00 | 2016-09-15 17:00 | 6d |  | 0 | 161934.3906 | 0 | 0 | 161934.3906 |  | 0 | 0 | 161934.3906 | 6d | 0 | 0 | 0 | 161934.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-07-18 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Structural Work (2) | 2016-03-21 08:00 | 2016-09-15 17:00 | 129d |  |  | 1797873.6172 |  |  | 1797873.6172 |  | 85d | [5 empty] | 845599.2656 |  | 45.81% |  | 823680.2656 | 1048441.4375
20 | betonstructuur blok A gelijkvloers | 2016-03-21 08:00 | 2016-05-17 17:00 | 42d |  |  | 468163.2734 |  |  | 468163.2734 |  | 46d | [5 empty] | 465147.2734 |  | 100% |  | 468163.2734 | 468163.2734
1 | kolommen gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 78027.2109 | 0 | 0 | 78027.2109 | 2016-03-21 08:00 | 10d | 78027.2109 | 0 | 0 | 7245 | 0 | 85272.2109 | 0 | 100% | Finished | 78027.2109 | 78027.2109 | 100 | 100 | 100 | 100 | 109.2852 | 100
2 | wanden gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 93632.6484 | 0 | 0 | 93632.6484 | 2016-03-21 08:00 | 15d | 93632.6484 | 0 | 0 | -5585 | 0 | 88047.6484 | 0 | 100% | Finished | 93632.6484 | 93632.6484 | 100 | 100 | 100 | 100 | 94.0352 | 100
3 | balken/liggers boven gelijkvloers blok A | 2016-03-28 08:00 | 2016-04-29 17:00 | 25d |  | 0 | 101435.3828 | 0 | 0 | 101435.3828 | 2016-03-28 08:00 | 29d | 101435.3828 | 0 | 0 | 12833 | 0 | 114268.3828 | 0 | 100% | Finished | 101435.3828 | 101435.3828 | 100 | 116 | 100 | 100 | 112.6514 | 100
4 | afdek gelijkvloers blok A welfsels + opstort druklaag | 2016-05-02 08:00 | 2016-05-17 17:00 | 12d |  | 0 | 195068.0312 | 0 | 0 | 195068.0312 | 2016-05-06 08:00 | 12d | 195068.0312 | 0 | 0 | -17509 | 0 | 177559.0312 | 0 | 100% | Finished | 195068.0312 | 195068.0312 | 100 | 100 | 100 | 100 | 91.0242 | 100
21 | betonstructuur blok A nivo +1 | 2016-05-18 08:00 | 2016-06-20 17:00 | 24d |  |  | 355516.9922 |  |  | 355516.9922 |  | 29d | [5 empty] | 380451.9922 |  | 100% |  | 355516.9922 | 355516.9922
5 | kolommen +1 blok A | 2016-05-18 08:00 | 2016-05-24 17:00 | 5d |  | 0 | 39904.9688 | 0 | 0 | 39904.9688 | 2016-05-24 08:00 | 5d | 39904.9688 | 0 | 0 | 2082 | 0 | 41986.9688 | 0 | 100% | Finished | 39904.9688 | 39904.9688 | 100 | 100 | 100 | 100 | 105.2174 | 100
6 | wanden kernen +1 blok A | 2016-05-18 08:00 | 2016-05-31 17:00 | 10d |  | 0 | 47160.4219 | 0 | 0 | 47160.4219 | 2016-05-24 08:00 | 10d | 47160.4219 | 0 | 0 | 3191 | 0 | 50351.4219 | 0 | 100% | Finished | 47160.4219 | 47160.4219 | 100 | 100 | 100 | 100 | 106.7663 | 100
7 | dragend metselwerk snelbouw +1 blok A | 2016-05-18 08:00 | 2016-06-10 17:00 | 18d |  | 0 | 119714.8984 | 0 | 0 | 119714.8984 | 2016-05-24 08:00 | 22d | 119714.8984 | 0 | 0 | 11258 | 0 | 130972.8984 | 0 | 100% | Finished | 119714.8984 | 119714.8984 | 100 | 122.2222 | 100 | 100 | 109.404 | 100
8 | balken/liggers boven +1 blok A | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 50788.1406 | 0 | 0 | 50788.1406 | 2016-06-16 08:00 | 6d | 50788.1406 | 0 | 0 | 2533 | 0 | 53321.1406 | 0 | 100% | Finished | 50788.1406 | 50788.1406 | 100 | 120 | 100 | 100 | 104.9874 | 100
9 | afdek verdieping +1 blok A welfsels + opstort druklaag | 2016-06-13 08:00 | 2016-06-20 17:00 | 6d |  | 0 | 97948.5625 | 0 | 0 | 97948.5625 | 2016-06-24 08:00 | 6d | 97948.5625 | 0 | 0 | 5871 | 0 | 103819.5625 | 0 | 100% | Finished | 97948.5625 | 97948.5625 | 100 | 100 | 100 | 100 | 105.994 | 100
22 | betonstructuur blok A nivo +2 | 2016-07-05 08:00 | 2016-08-09 17:00 | 26d |  |  | 386431.4922 |  |  | 386431.4922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 224761.1719
10 | kolommen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 43374.9609 | 0 | 0 | 43374.9609 |  | 0 | 0 | 43374.9609 | 5d | 0 | 0 | 0 | 43374.9609 | 0% | Not Started | 0 | 43374.9609 | 100 |  | 0 | 100 |  | 0
11 | wanden kernen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 51261.3203 | 0 | 0 | 51261.3203 |  | 0 | 0 | 51261.3203 | 5d | 0 | 0 | 0 | 51261.3203 | 0% | Not Started | 0 | 51261.3203 | 100 |  | 0 | 100 |  | 0
12 | dragend metselwerk snelbouw +2 blok A | 2016-07-05 08:00 | 2016-07-26 17:00 | 16d |  | 0 | 130124.8906 | 0 | 0 | 130124.8906 |  | 0 | 0 | 130124.8906 | 16d | 0 | 0 | 0 | 130124.8906 | 0% | Not Started | 0 | 130124.8906 | 100 |  | 0 | 100 |  | 0
13 | balken/liggers boven +2 blok A | 2016-07-20 08:00 | 2016-08-01 17:00 | 9d |  | 0 | 55204.5 | 0 | 0 | 55204.5 |  | 0 | 0 | 55204.5 | 9d | 0 | 0 | 0 | 55204.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | afdek verdieping +2 blok A welfsels + opstort druklaag | 2016-08-02 08:00 | 2016-08-09 17:00 | 6d |  | 0 | 106465.8203 | 0 | 0 | 106465.8203 |  | 0 | 0 | 106465.8203 | 6d | 0 | 0 | 0 | 106465.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | betonstructuur blok A nivo +3 | 2016-08-10 08:00 | 2016-09-15 17:00 | 27d |  |  | 587761.8594 |  |  | 587761.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | kolommen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 65973.2734 | 0 | 0 | 65973.2734 |  | 0 | 0 | 65973.2734 | 3d | 0 | 0 | 0 | 65973.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | wanden kernen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 77968.4062 | 0 | 0 | 77968.4062 |  | 0 | 0 | 77968.4062 | 3d | 0 | 0 | 0 | 77968.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | dragend metselwerk snelbouw +3 blok A | 2016-08-10 08:00 | 2016-08-31 17:00 | 16d |  | 0 | 197919.8125 | 0 | 0 | 197919.8125 |  | 0 | 0 | 197919.8125 | 16d | 0 | 0 | 0 | 197919.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | balken/liggers boven +3 blok A | 2016-08-26 08:00 | 2016-09-07 17:00 | 9d |  | 0 | 83965.9766 | 0 | 0 | 83965.9766 |  | 0 | 0 | 83965.9766 | 9d | 0 | 0 | 0 | 83965.9766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | afdek verdieping +3 blok A welfsels + opstort druklaag | 2016-09-08 08:00 | 2016-09-15 17:00 | 6d |  | 0 | 161934.3906 | 0 | 0 | 161934.3906 |  | 0 | 0 | 161934.3906 | 6d | 0 | 0 | 0 | 161934.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-08-30 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Structural Work (2) | 2016-03-21 08:00 | 2016-09-15 17:00 | 129d |  |  | 1797873.6172 |  |  | 1797873.6172 |  | 116d | [5 empty] | 1252692.7578 |  | 67.31% |  | 1210111.7578 | 1635939.2266
20 | betonstructuur blok A gelijkvloers | 2016-03-21 08:00 | 2016-05-17 17:00 | 42d |  |  | 468163.2734 |  |  | 468163.2734 |  | 46d | [5 empty] | 465147.2734 |  | 100% |  | 468163.2734 | 468163.2734
1 | kolommen gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 78027.2109 | 0 | 0 | 78027.2109 | 2016-03-21 08:00 | 10d | 78027.2109 | 0 | 0 | 7245 | 0 | 85272.2109 | 0 | 100% | Finished | 78027.2109 | 78027.2109 | 100 | 100 | 100 | 100 | 109.2852 | 100
2 | wanden gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 93632.6484 | 0 | 0 | 93632.6484 | 2016-03-21 08:00 | 15d | 93632.6484 | 0 | 0 | -5585 | 0 | 88047.6484 | 0 | 100% | Finished | 93632.6484 | 93632.6484 | 100 | 100 | 100 | 100 | 94.0352 | 100
3 | balken/liggers boven gelijkvloers blok A | 2016-03-28 08:00 | 2016-04-29 17:00 | 25d |  | 0 | 101435.3828 | 0 | 0 | 101435.3828 | 2016-03-28 08:00 | 29d | 101435.3828 | 0 | 0 | 12833 | 0 | 114268.3828 | 0 | 100% | Finished | 101435.3828 | 101435.3828 | 100 | 116 | 100 | 100 | 112.6514 | 100
4 | afdek gelijkvloers blok A welfsels + opstort druklaag | 2016-05-02 08:00 | 2016-05-17 17:00 | 12d |  | 0 | 195068.0312 | 0 | 0 | 195068.0312 | 2016-05-06 08:00 | 12d | 195068.0312 | 0 | 0 | -17509 | 0 | 177559.0312 | 0 | 100% | Finished | 195068.0312 | 195068.0312 | 100 | 100 | 100 | 100 | 91.0242 | 100
21 | betonstructuur blok A nivo +1 | 2016-05-18 08:00 | 2016-06-20 17:00 | 24d |  |  | 355516.9922 |  |  | 355516.9922 |  | 29d | [5 empty] | 380451.9922 |  | 100% |  | 355516.9922 | 355516.9922
5 | kolommen +1 blok A | 2016-05-18 08:00 | 2016-05-24 17:00 | 5d |  | 0 | 39904.9688 | 0 | 0 | 39904.9688 | 2016-05-24 08:00 | 5d | 39904.9688 | 0 | 0 | 2082 | 0 | 41986.9688 | 0 | 100% | Finished | 39904.9688 | 39904.9688 | 100 | 100 | 100 | 100 | 105.2174 | 100
6 | wanden kernen +1 blok A | 2016-05-18 08:00 | 2016-05-31 17:00 | 10d |  | 0 | 47160.4219 | 0 | 0 | 47160.4219 | 2016-05-24 08:00 | 10d | 47160.4219 | 0 | 0 | 3191 | 0 | 50351.4219 | 0 | 100% | Finished | 47160.4219 | 47160.4219 | 100 | 100 | 100 | 100 | 106.7663 | 100
7 | dragend metselwerk snelbouw +1 blok A | 2016-05-18 08:00 | 2016-06-10 17:00 | 18d |  | 0 | 119714.8984 | 0 | 0 | 119714.8984 | 2016-05-24 08:00 | 22d | 119714.8984 | 0 | 0 | 11258 | 0 | 130972.8984 | 0 | 100% | Finished | 119714.8984 | 119714.8984 | 100 | 122.2222 | 100 | 100 | 109.404 | 100
8 | balken/liggers boven +1 blok A | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 50788.1406 | 0 | 0 | 50788.1406 | 2016-06-16 08:00 | 6d | 50788.1406 | 0 | 0 | 2533 | 0 | 53321.1406 | 0 | 100% | Finished | 50788.1406 | 50788.1406 | 100 | 120 | 100 | 100 | 104.9874 | 100
9 | afdek verdieping +1 blok A welfsels + opstort druklaag | 2016-06-13 08:00 | 2016-06-20 17:00 | 6d |  | 0 | 97948.5625 | 0 | 0 | 97948.5625 | 2016-06-24 08:00 | 6d | 97948.5625 | 0 | 0 | 5871 | 0 | 103819.5625 | 0 | 100% | Finished | 97948.5625 | 97948.5625 | 100 | 100 | 100 | 100 | 105.994 | 100
22 | betonstructuur blok A nivo +2 | 2016-07-05 08:00 | 2016-08-09 17:00 | 26d |  |  | 386431.4922 |  |  | 386431.4922 |  | 31d | [5 empty] | 407093.4922 |  | 100% |  | 386431.4922 | 386431.4922
10 | kolommen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 43374.9609 | 0 | 0 | 43374.9609 | 2016-07-18 08:00 | 5d | 43374.9609 | 0 | 0 | 3848 | 0 | 47222.9609 | 0 | 100% | Finished | 43374.9609 | 43374.9609 | 100 | 100 | 100 | 100 | 108.8715 | 100
11 | wanden kernen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 51261.3203 | 0 | 0 | 51261.3203 | 2016-07-18 08:00 | 5d | 51261.3203 | 0 | 0 | 3207 | 0 | 54468.3203 | 0 | 100% | Finished | 51261.3203 | 51261.3203 | 100 | 100 | 100 | 100 | 106.2562 | 100
12 | dragend metselwerk snelbouw +2 blok A | 2016-07-05 08:00 | 2016-07-26 17:00 | 16d |  | 0 | 130124.8906 | 0 | 0 | 130124.8906 | 2016-07-18 08:00 | 20d | 130124.8906 | 0 | 0 | 13412 | 0 | 143536.8906 | 0 | 100% | Finished | 130124.8906 | 130124.8906 | 100 | 125 | 100 | 100 | 110.307 | 100
13 | balken/liggers boven +2 blok A | 2016-07-20 08:00 | 2016-08-01 17:00 | 9d |  | 0 | 55204.5 | 0 | 0 | 55204.5 | 2016-08-08 08:00 | 10d | 55204.5 | 0 | 0 | 7243 | 0 | 62447.5 | 0 | 100% | Finished | 55204.5 | 55204.5 | 100 | 111.1111 | 100 | 100 | 113.1203 | 100
14 | afdek verdieping +2 blok A welfsels + opstort druklaag | 2016-08-02 08:00 | 2016-08-09 17:00 | 6d |  | 0 | 106465.8203 | 0 | 0 | 106465.8203 | 2016-08-22 08:00 | 6d | 106465.8203 | 0 | 0 | -7048 | 0 | 99417.8203 | 0 | 100% | Finished | 106465.8203 | 106465.8203 | 100 | 100 | 100 | 100 | 93.38 | 100
23 | betonstructuur blok A nivo +3 | 2016-08-10 08:00 | 2016-09-15 17:00 | 27d |  |  | 587761.8594 |  |  | 587761.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 425827.4688
15 | kolommen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 65973.2734 | 0 | 0 | 65973.2734 |  | 0 | 0 | 65973.2734 | 3d | 0 | 0 | 0 | 65973.2734 | 0% | Not Started | 0 | 65973.2734 | 100 |  | 0 | 100 |  | 0
16 | wanden kernen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 77968.4062 | 0 | 0 | 77968.4062 |  | 0 | 0 | 77968.4062 | 3d | 0 | 0 | 0 | 77968.4062 | 0% | Not Started | 0 | 77968.4062 | 100 |  | 0 | 100 |  | 0
17 | dragend metselwerk snelbouw +3 blok A | 2016-08-10 08:00 | 2016-08-31 17:00 | 16d |  | 0 | 197919.8125 | 0 | 0 | 197919.8125 |  | 0 | 0 | 197919.8125 | 16d | 0 | 0 | 0 | 197919.8125 | 0% | Not Started | 0 | 197919.8125 | 100 |  | 0 | 100 |  | 0
18 | balken/liggers boven +3 blok A | 2016-08-26 08:00 | 2016-09-07 17:00 | 9d |  | 0 | 83965.9766 | 0 | 0 | 83965.9766 |  | 0 | 0 | 83965.9766 | 9d | 0 | 0 | 0 | 83965.9766 | 0% | Not Started | 0 | 83965.9766 | 100 |  | 0 | 100 |  | 0
19 | afdek verdieping +3 blok A welfsels + opstort druklaag | 2016-09-08 08:00 | 2016-09-15 17:00 | 6d |  | 0 | 161934.3906 | 0 | 0 | 161934.3906 |  | 0 | 0 | 161934.3906 | 6d | 0 | 0 | 0 | 161934.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-10-12 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Structural Work (2) | 2016-03-21 08:00 | 2016-09-15 17:00 | 129d |  |  | 1797873.6172 |  |  | 1797873.6172 |  | 148d | [5 empty] | 1860330.6172 |  | 100% |  | 1797873.6172 | 1797873.6172
20 | betonstructuur blok A gelijkvloers | 2016-03-21 08:00 | 2016-05-17 17:00 | 42d |  |  | 468163.2734 |  |  | 468163.2734 |  | 46d | [5 empty] | 465147.2734 |  | 100% |  | 468163.2734 | 468163.2734
1 | kolommen gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 78027.2109 | 0 | 0 | 78027.2109 | 2016-03-21 08:00 | 10d | 78027.2109 | 0 | 0 | 7245 | 0 | 85272.2109 | 0 | 100% | Finished | 78027.2109 | 78027.2109 | 100 | 100 | 100 | 100 | 109.2852 | 100
2 | wanden gelijkvloers blok A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 93632.6484 | 0 | 0 | 93632.6484 | 2016-03-21 08:00 | 15d | 93632.6484 | 0 | 0 | -5585 | 0 | 88047.6484 | 0 | 100% | Finished | 93632.6484 | 93632.6484 | 100 | 100 | 100 | 100 | 94.0352 | 100
3 | balken/liggers boven gelijkvloers blok A | 2016-03-28 08:00 | 2016-04-29 17:00 | 25d |  | 0 | 101435.3828 | 0 | 0 | 101435.3828 | 2016-03-28 08:00 | 29d | 101435.3828 | 0 | 0 | 12833 | 0 | 114268.3828 | 0 | 100% | Finished | 101435.3828 | 101435.3828 | 100 | 116 | 100 | 100 | 112.6514 | 100
4 | afdek gelijkvloers blok A welfsels + opstort druklaag | 2016-05-02 08:00 | 2016-05-17 17:00 | 12d |  | 0 | 195068.0312 | 0 | 0 | 195068.0312 | 2016-05-06 08:00 | 12d | 195068.0312 | 0 | 0 | -17509 | 0 | 177559.0312 | 0 | 100% | Finished | 195068.0312 | 195068.0312 | 100 | 100 | 100 | 100 | 91.0242 | 100
21 | betonstructuur blok A nivo +1 | 2016-05-18 08:00 | 2016-06-20 17:00 | 24d |  |  | 355516.9922 |  |  | 355516.9922 |  | 29d | [5 empty] | 380451.9922 |  | 100% |  | 355516.9922 | 355516.9922
5 | kolommen +1 blok A | 2016-05-18 08:00 | 2016-05-24 17:00 | 5d |  | 0 | 39904.9688 | 0 | 0 | 39904.9688 | 2016-05-24 08:00 | 5d | 39904.9688 | 0 | 0 | 2082 | 0 | 41986.9688 | 0 | 100% | Finished | 39904.9688 | 39904.9688 | 100 | 100 | 100 | 100 | 105.2174 | 100
6 | wanden kernen +1 blok A | 2016-05-18 08:00 | 2016-05-31 17:00 | 10d |  | 0 | 47160.4219 | 0 | 0 | 47160.4219 | 2016-05-24 08:00 | 10d | 47160.4219 | 0 | 0 | 3191 | 0 | 50351.4219 | 0 | 100% | Finished | 47160.4219 | 47160.4219 | 100 | 100 | 100 | 100 | 106.7663 | 100
7 | dragend metselwerk snelbouw +1 blok A | 2016-05-18 08:00 | 2016-06-10 17:00 | 18d |  | 0 | 119714.8984 | 0 | 0 | 119714.8984 | 2016-05-24 08:00 | 22d | 119714.8984 | 0 | 0 | 11258 | 0 | 130972.8984 | 0 | 100% | Finished | 119714.8984 | 119714.8984 | 100 | 122.2222 | 100 | 100 | 109.404 | 100
8 | balken/liggers boven +1 blok A | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 50788.1406 | 0 | 0 | 50788.1406 | 2016-06-16 08:00 | 6d | 50788.1406 | 0 | 0 | 2533 | 0 | 53321.1406 | 0 | 100% | Finished | 50788.1406 | 50788.1406 | 100 | 120 | 100 | 100 | 104.9874 | 100
9 | afdek verdieping +1 blok A welfsels + opstort druklaag | 2016-06-13 08:00 | 2016-06-20 17:00 | 6d |  | 0 | 97948.5625 | 0 | 0 | 97948.5625 | 2016-06-24 08:00 | 6d | 97948.5625 | 0 | 0 | 5871 | 0 | 103819.5625 | 0 | 100% | Finished | 97948.5625 | 97948.5625 | 100 | 100 | 100 | 100 | 105.994 | 100
22 | betonstructuur blok A nivo +2 | 2016-07-05 08:00 | 2016-08-09 17:00 | 26d |  |  | 386431.4922 |  |  | 386431.4922 |  | 31d | [5 empty] | 407093.4922 |  | 100% |  | 386431.4922 | 386431.4922
10 | kolommen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 43374.9609 | 0 | 0 | 43374.9609 | 2016-07-18 08:00 | 5d | 43374.9609 | 0 | 0 | 3848 | 0 | 47222.9609 | 0 | 100% | Finished | 43374.9609 | 43374.9609 | 100 | 100 | 100 | 100 | 108.8715 | 100
11 | wanden kernen +2 blok A | 2016-07-05 08:00 | 2016-07-11 17:00 | 5d |  | 0 | 51261.3203 | 0 | 0 | 51261.3203 | 2016-07-18 08:00 | 5d | 51261.3203 | 0 | 0 | 3207 | 0 | 54468.3203 | 0 | 100% | Finished | 51261.3203 | 51261.3203 | 100 | 100 | 100 | 100 | 106.2562 | 100
12 | dragend metselwerk snelbouw +2 blok A | 2016-07-05 08:00 | 2016-07-26 17:00 | 16d |  | 0 | 130124.8906 | 0 | 0 | 130124.8906 | 2016-07-18 08:00 | 20d | 130124.8906 | 0 | 0 | 13412 | 0 | 143536.8906 | 0 | 100% | Finished | 130124.8906 | 130124.8906 | 100 | 125 | 100 | 100 | 110.307 | 100
13 | balken/liggers boven +2 blok A | 2016-07-20 08:00 | 2016-08-01 17:00 | 9d |  | 0 | 55204.5 | 0 | 0 | 55204.5 | 2016-08-08 08:00 | 10d | 55204.5 | 0 | 0 | 7243 | 0 | 62447.5 | 0 | 100% | Finished | 55204.5 | 55204.5 | 100 | 111.1111 | 100 | 100 | 113.1203 | 100
14 | afdek verdieping +2 blok A welfsels + opstort druklaag | 2016-08-02 08:00 | 2016-08-09 17:00 | 6d |  | 0 | 106465.8203 | 0 | 0 | 106465.8203 | 2016-08-22 08:00 | 6d | 106465.8203 | 0 | 0 | -7048 | 0 | 99417.8203 | 0 | 100% | Finished | 106465.8203 | 106465.8203 | 100 | 100 | 100 | 100 | 93.38 | 100
23 | betonstructuur blok A nivo +3 | 2016-08-10 08:00 | 2016-09-15 17:00 | 27d |  |  | 587761.8594 |  |  | 587761.8594 |  | 32d | [5 empty] | 607637.8594 |  | 100% |  | 587761.8594 | 587761.8594
15 | kolommen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 65973.2734 | 0 | 0 | 65973.2734 | 2016-08-30 08:00 | 3d | 65973.2734 | 0 | 0 | 6166 | 0 | 72139.2734 | 0 | 100% | Finished | 65973.2734 | 65973.2734 | 100 | 100 | 100 | 100 | 109.3462 | 100
16 | wanden kernen +3 blok A | 2016-08-10 08:00 | 2016-08-12 17:00 | 3d |  | 0 | 77968.4062 | 0 | 0 | 77968.4062 | 2016-08-30 08:00 | 3d | 77968.4062 | 0 | 0 | -342 | 0 | 77626.4062 | 0 | 100% | Finished | 77968.4062 | 77968.4062 | 100 | 100 | 100 | 100 | 99.5614 | 100
17 | dragend metselwerk snelbouw +3 blok A | 2016-08-10 08:00 | 2016-08-31 17:00 | 16d |  | 0 | 197919.8125 | 0 | 0 | 197919.8125 | 2016-08-30 08:00 | 16d | 197919.8125 | 0 | 0 | 30192 | 0 | 228111.8125 | 0 | 100% | Finished | 197919.8125 | 197919.8125 | 100 | 100 | 100 | 100 | 115.2547 | 100
18 | balken/liggers boven +3 blok A | 2016-08-26 08:00 | 2016-09-07 17:00 | 9d |  | 0 | 83965.9766 | 0 | 0 | 83965.9766 | 2016-09-21 08:00 | 10d | 83965.9766 | 0 | 0 | -1552 | 0 | 82413.9766 | 0 | 100% | Finished | 83965.9766 | 83965.9766 | 100 | 111.1111 | 100 | 100 | 98.1516 | 100
19 | afdek verdieping +3 blok A welfsels + opstort druklaag | 2016-09-08 08:00 | 2016-09-15 17:00 | 6d |  | 0 | 161934.3906 | 0 | 0 | 161934.3906 | 2016-10-05 08:00 | 6d | 161934.3906 | 0 | 0 | -14588 | 0 | 147346.3906 | 0 | 100% | Finished | 161934.3906 | 161934.3906 | 100 | 100 | 100 | 100 | 90.9914 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-21 08:00 | 2016-05-24 08:00 | 674943.5625 | 468163.2734 | 465147.2734 | 2016-05-17 17:00 | -206780.2891 | 69.36% | 3016 | 100.6% | -4d | 91.3% | 100% | 2016-10-06 16:00 | 2016-12-05 17:00 | 2016-12-02 15:00 | 2016-10-06 09:00 | 2016-12-05 17:00 | 2016-12-05 09:00 | 2016-09-21 17:00 | 2016-10-04 10:00 | 2016-10-03 14:00 | 1794857.6172 | 1786291.3613 | 2382169.5762 | 1921496.6975 | 2369819.741 | 1912114.6078 | 1873867.3485 | 1811286.0701 | 0.91304 | 1.0065 | 0.69363 | 1 | -4 | 1.0065 | 1 | 0.91304 | 1
Tracking Period 2 | 2016-05-24 08:00 | 2016-07-18 08:00 | 1048441.4375 | 823680.2656 | 845599.2656 | 2016-07-04 17:00 | -224761.1719 | 78.56% | -21919 | 97.41% | -9d | 89.41% | 100% | 2016-10-10 09:00 | 2016-11-04 10:00 | 2016-11-10 14:00 | 2016-10-12 10:00 | 2016-11-04 10:00 | 2016-11-08 10:00 | 2016-09-28 17:00 | 2016-10-07 10:00 | 2016-10-10 16:00 | 1819792.6172 | 1845716.929 | 2085624.9413 | 1935157.6193 | 2118623.3315 | 1964151.9155 | 1885973.1991 | 1862410.724 | 0.89412 | 0.97408 | 0.78562 | 1 | -9 | 0.97408 | 1 | 0.89412 | 1
Tracking Period 3 | 2016-07-18 08:00 | 2016-08-30 08:00 | 1635939.2266 | 1210111.7578 | 1252692.7578 | 2016-08-09 17:00 | -425827.4688 | 73.97% | -42581 | 96.6% | -14d | 87.93% | 100% | 2016-10-28 12:00 | 2016-11-18 11:00 | 2016-11-28 12:00 | 2016-10-28 10:00 | 2016-11-18 11:00 | 2016-11-22 12:00 | 2016-10-05 17:00 | 2016-10-11 15:00 | 2016-10-12 15:00 | 1840454.6172 | 1861136.5811 | 2047282.7413 | 1921127.8136 | 2075242.5027 | 1944648.4784 | 1891045.5726 | 1872257.6195 | 0.87931 | 0.96601 | 0.7397 | 1 | -14 | 0.96601 | 1 | 0.87931 | 1
Tracking Period 4 | 2016-08-30 08:00 | 2016-10-12 17:00 | 1797873.6172 | 1797873.6172 | 1860330.6172 | 2016-09-15 17:00 | 0 | 100% | -62457 | 96.64% | -19d | 87.16% | 100% | 2016-09-15 17:00 | 2016-09-15 17:00 | 2016-09-22 12:00 | 2016-10-12 17:00 | 2016-10-12 17:00 | 2016-10-12 17:00 | 2016-10-12 17:00 | 2016-10-12 17:00 | 2016-10-12 17:00 | 1860330.6172 | 1860330.6172 | 1860330.6172 | 1860330.6172 | 1860330.6172 | 1860330.6172 | 1860330.6172 | 1860330.6172 | 0.87162 | 0.96643 | 1 | 1 | -19 | 0.96643 | 1 | 0.87162 | 1