## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building Structural Work (3) | 1 |  |  | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 1319736.291 |  |  | 1319736.291 | 116.375
24 | betonstructuur blok B gelijkvloers | 1.1 |  |  | 2016-03-21 08:00 | 2016-04-22 17:00 | 25d |  |  | 350722.9453 |  |  | 350722.9453 | 32.375
1 | kolommen gelijkvloers blok B | 1.1.1 |  | SS2 | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 38969.2188 | 0 | 0 | 38969.2188 | 4.375
2 | wanden gelijkvloers blok B | 1.1.2 | 1SS | SS3 | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 46763.0586 | 0 | 0 | 46763.0586 | 4.375
3 | dragend metselwerk snelbouw gelijkvloers blok B | 1.1.3 | 2SS | FS4-4d | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 116907.6484 | 0 | 0 | 116907.6484 | 18.375
4 | balken/liggers boven gelijkvloers blok B | 1.1.4 | 3FS-4d | FS5 | 2016-04-05 08:00 | 2016-04-15 17:00 | 9d |  | 0 | 50659.9805 | 0 | 0 | 50659.9805 | 10.375
5 | afdek gelijkvloers blok B welfsels + opstort druklaag | 1.1.5 | 4FS | FS6 | 2016-04-18 08:00 | 2016-04-22 17:00 | 5d |  | 0 | 97423.0391 | 0 | 0 | 97423.0391 | 4.375
25 | betonstructuur blok B nivo +1 | 1.2 |  |  | 2016-04-25 08:00 | 2016-05-30 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 | 35.375
6 | kolommen +1 blok B | 1.2.1 | 5FS | SS7 | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 4.375
7 | wanden kernen +1 blok B | 1.2.2 | 6SS | SS8 | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 4.375
8 | dragend metselwerk snelbouw +1 blok B | 1.2.3 | 7SS | FS9-4d | 2016-04-25 08:00 | 2016-05-13 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 18.375
9 | balken/liggers boven +1 blok B | 1.2.4 | 8FS-4d | FS10 | 2016-05-10 08:00 | 2016-05-20 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 10.375
10 | afdek verdieping +1 blok B welfsels + opstort druklaag | 1.2.5 | 9FS | FF11;FS12 | 2016-05-23 08:00 | 2016-05-30 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 7.375
11 | platen tpg d=17 en d=21 boven +1 | 1.2.6 | 10FF |  | 2016-05-25 08:00 | 2016-05-30 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 5.375
26 | betonstructuur blok B nivo +2 | 1.3 |  |  | 2016-05-31 08:00 | 2016-07-05 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 | 35.375
12 | kolommen +2 blok B | 1.3.1 | 10FS | SS13;SS14 | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 6.375
13 | wanden kernen +2 blok B | 1.3.2 | 12SS |  | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 6.375
14 | dragend metselwerk snelbouw +2 blok B | 1.3.3 | 12SS | FS15-4d | 2016-05-31 08:00 | 2016-06-20 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 20.375
15 | balken/liggers boven +2 blok B | 1.3.4 | 14FS-4d | FS16 | 2016-06-15 08:00 | 2016-06-27 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 12.375
16 | afdek verdieping +2 blok B welfsels + opstort druklaag | 1.3.5 | 15FS | FF17;FS18 | 2016-06-28 08:00 | 2016-07-05 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 7.375
17 | platen tpg d=17 en d=21 boven +2 | 1.3.6 | 16FF |  | 2016-06-30 08:00 | 2016-07-05 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 5.375
27 | betonstructuur blok B nivo +3 | 1.4 |  |  | 2016-07-06 08:00 | 2016-07-15 17:00 | 8d |  |  | 350722.9443 |  |  | 350722.9443 | 9.375
18 | kolommen +3 blok B | 1.4.1 | 16FS | SS19;SS20 | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 38579.5195 | 0 | 0 | 38579.5195 | 2.375
19 | wanden kernen +3 blok B | 1.4.2 | 18SS |  | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 45593.9805 | 0 | 0 | 45593.9805 | 2.375
20 | dragend metselwerk snelbouw +3 blok B | 1.4.3 | 18SS | FS21-4d | 2016-07-06 08:00 | 2016-07-14 17:00 | 7d |  | 0 | 115738.5703 | 0 | 0 | 115738.5703 | 8.375
21 | balken/liggers boven +3 blok B | 1.4.4 | 20FS-4d | SS22 | 2016-07-11 08:00 | 2016-07-13 17:00 | 3d |  | 0 | 49101.2109 | 0 | 0 | 49101.2109 | 2.375
22 | afdek verdieping +3 blok B welfsels + opstort druklaag | 1.4.5 | 21SS | FF23 | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 94695.2031 | 0 | 0 | 94695.2031 | 4.375
23 | platen tpg d=15 boven +3 | 1.4.6 | 22FF |  | 2016-07-13 08:00 | 2016-07-15 17:00 | 3d |  | 0 | 7014.46 | 0 | 0 | 7014.46 | 2.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building Structural Work (3) | 680h |  |  |  |  | 99 | 100 | 101
24 | betonstructuur blok B gelijkvloers | 200h |  |  |  |  | 99 | 100 | 101
1 | kolommen gelijkvloers blok B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | wanden gelijkvloers blok B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | dragend metselwerk snelbouw gelijkvloers blok B | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | balken/liggers boven gelijkvloers blok B | 72h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
5 | afdek gelijkvloers blok B welfsels + opstort druklaag | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | betonstructuur blok B nivo +1 | 208h |  |  |  |  | 99 | 100 | 101
6 | kolommen +1 blok B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | wanden kernen +1 blok B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | dragend metselwerk snelbouw +1 blok B | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | balken/liggers boven +1 blok B | 72h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
10 | afdek verdieping +1 blok B welfsels + opstort druklaag | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
11 | platen tpg d=17 en d=21 boven +1 | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
26 | betonstructuur blok B nivo +2 | 208h |  |  |  |  | 99 | 100 | 101
12 | kolommen +2 blok B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | wanden kernen +2 blok B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | dragend metselwerk snelbouw +2 blok B | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | balken/liggers boven +2 blok B | 72h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
16 | afdek verdieping +2 blok B welfsels + opstort druklaag | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
17 | platen tpg d=17 en d=21 boven +2 | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
27 | betonstructuur blok B nivo +3 | 64h |  |  |  |  | 99 | 100 | 101
18 | kolommen +3 blok B | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | wanden kernen +3 blok B | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | dragend metselwerk snelbouw +3 blok B | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | balken/liggers boven +3 blok B | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
22 | afdek verdieping +3 blok B welfsels + opstort druklaag | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
23 | platen tpg d=15 boven +3 | 24h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120

## Project Control - TP1
| TP Status Date | 2016-04-28 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Structural Work (3) | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 1319736.291 |  |  | 1319736.291 |  | 28d | [5 empty] | 348020.9453 |  | 26.58% |  | 350722.9453 | 526935.7148
24 | betonstructuur blok B gelijkvloers | 2016-03-21 08:00 | 2016-04-22 17:00 | 25d |  |  | 350722.9453 |  |  | 350722.9453 |  | 28d | [5 empty] | 348020.9453 |  | 100% |  | 350722.9453 | 350722.9453
1 | kolommen gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 38969.2188 | 0 | 0 | 38969.2188 | 2016-03-21 08:00 | 5d | 38969.2188 | 0 | 0 | -3776 | 0 | 35193.2188 | 0 | 100% | Finished | 38969.2188 | 38969.2188 | 100 | 100 | 100 | 100 | 90.3103 | 100
2 | wanden gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 46763.0586 | 0 | 0 | 46763.0586 | 2016-03-21 08:00 | 4d | 46763.0586 | 0 | 0 | -3558 | 0 | 43205.0586 | 0 | 100% | Finished | 46763.0586 | 46763.0586 | 100 | 80 | 100 | 100 | 92.3914 | 100
3 | dragend metselwerk snelbouw gelijkvloers blok B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 116907.6484 | 0 | 0 | 116907.6484 | 2016-03-21 08:00 | 17d | 116907.6484 | 0 | 0 | 190 | 0 | 117097.6484 | 0 | 100% | Finished | 116907.6484 | 116907.6484 | 100 | 113.3333 | 100 | 100 | 100.1625 | 100
4 | balken/liggers boven gelijkvloers blok B | 2016-04-05 08:00 | 2016-04-15 17:00 | 9d |  | 0 | 50659.9805 | 0 | 0 | 50659.9805 | 2016-04-07 08:00 | 10d | 50659.9805 | 0 | 0 | 6783 | 0 | 57442.9805 | 0 | 100% | Finished | 50659.9805 | 50659.9805 | 100 | 111.1111 | 100 | 100 | 113.3893 | 100
5 | afdek gelijkvloers blok B welfsels + opstort druklaag | 2016-04-18 08:00 | 2016-04-22 17:00 | 5d |  | 0 | 97423.0391 | 0 | 0 | 97423.0391 | 2016-04-21 08:00 | 5d | 97423.0391 | 0 | 0 | -2341 | 0 | 95082.0391 | 0 | 100% | Finished | 97423.0391 | 97423.0391 | 100 | 100 | 100 | 100 | 97.5971 | 100
25 | betonstructuur blok B nivo +1 | 2016-04-25 08:00 | 2016-05-30 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 176212.7695
6 | kolommen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 |  | 0 | 0 | 34005.9688 | 5d | 0 | 0 | 0 | 34005.9688 | 0% | Not Started | 0 | 34005.9688 | 100 |  | 0 | 100 |  | 0
7 | wanden kernen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 |  | 0 | 0 | 40188.8789 | 5d | 0 | 0 | 0 | 40188.8789 | 0% | Not Started | 0 | 40188.8789 | 100 |  | 0 | 100 |  | 0
8 | dragend metselwerk snelbouw +1 blok B | 2016-04-25 08:00 | 2016-05-13 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 |  | 0 | 0 | 102017.9219 | 15d | 0 | 0 | 0 | 102017.9219 | 0% | Not Started | 0 | 102017.9219 | 100 |  | 0 | 100 |  | 0
9 | balken/liggers boven +1 blok B | 2016-05-10 08:00 | 2016-05-20 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 |  | 0 | 0 | 43280.3281 | 9d | 0 | 0 | 0 | 43280.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | afdek verdieping +1 blok B welfsels + opstort druklaag | 2016-05-23 08:00 | 2016-05-30 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 |  | 0 | 0 | 83469.2031 | 6d | 0 | 0 | 0 | 83469.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | platen tpg d=17 en d=21 boven +1 | 2016-05-25 08:00 | 2016-05-30 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 |  | 0 | 0 | 6182.8999 | 4d | 0 | 0 | 0 | 6182.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | betonstructuur blok B nivo +2 | 2016-05-31 08:00 | 2016-07-05 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | kolommen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 |  | 0 | 0 | 34005.9688 | 5d | 0 | 0 | 0 | 34005.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | wanden kernen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 |  | 0 | 0 | 40188.8789 | 5d | 0 | 0 | 0 | 40188.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | dragend metselwerk snelbouw +2 blok B | 2016-05-31 08:00 | 2016-06-20 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 |  | 0 | 0 | 102017.9219 | 15d | 0 | 0 | 0 | 102017.9219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | balken/liggers boven +2 blok B | 2016-06-15 08:00 | 2016-06-27 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 |  | 0 | 0 | 43280.3281 | 9d | 0 | 0 | 0 | 43280.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | afdek verdieping +2 blok B welfsels + opstort druklaag | 2016-06-28 08:00 | 2016-07-05 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 |  | 0 | 0 | 83469.2031 | 6d | 0 | 0 | 0 | 83469.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | platen tpg d=17 en d=21 boven +2 | 2016-06-30 08:00 | 2016-07-05 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 |  | 0 | 0 | 6182.8999 | 4d | 0 | 0 | 0 | 6182.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | betonstructuur blok B nivo +3 | 2016-07-06 08:00 | 2016-07-15 17:00 | 8d |  |  | 350722.9443 |  |  | 350722.9443 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | kolommen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 38579.5195 | 0 | 0 | 38579.5195 |  | 0 | 0 | 38579.5195 | 3d | 0 | 0 | 0 | 38579.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | wanden kernen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 45593.9805 | 0 | 0 | 45593.9805 |  | 0 | 0 | 45593.9805 | 3d | 0 | 0 | 0 | 45593.9805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | dragend metselwerk snelbouw +3 blok B | 2016-07-06 08:00 | 2016-07-14 17:00 | 7d |  | 0 | 115738.5703 | 0 | 0 | 115738.5703 |  | 0 | 0 | 115738.5703 | 7d | 0 | 0 | 0 | 115738.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | balken/liggers boven +3 blok B | 2016-07-11 08:00 | 2016-07-13 17:00 | 3d |  | 0 | 49101.2109 | 0 | 0 | 49101.2109 |  | 0 | 0 | 49101.2109 | 3d | 0 | 0 | 0 | 49101.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | afdek verdieping +3 blok B welfsels + opstort druklaag | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 94695.2031 | 0 | 0 | 94695.2031 |  | 0 | 0 | 94695.2031 | 5d | 0 | 0 | 0 | 94695.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | platen tpg d=15 boven +3 | 2016-07-13 08:00 | 2016-07-15 17:00 | 3d |  | 0 | 7014.46 | 0 | 0 | 7014.46 |  | 0 | 0 | 7014.46 | 3d | 0 | 0 | 0 | 7014.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-06-08 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Structural Work (3) | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 1319736.291 |  |  | 1319736.291 |  | 57d | [5 empty] | 656604.146 |  | 50% |  | 659868.146 | 836080.9155
24 | betonstructuur blok B gelijkvloers | 2016-03-21 08:00 | 2016-04-22 17:00 | 25d |  |  | 350722.9453 |  |  | 350722.9453 |  | 28d | [5 empty] | 348020.9453 |  | 100% |  | 350722.9453 | 350722.9453
1 | kolommen gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 38969.2188 | 0 | 0 | 38969.2188 | 2016-03-21 08:00 | 5d | 38969.2188 | 0 | 0 | -3776 | 0 | 35193.2188 | 0 | 100% | Finished | 38969.2188 | 38969.2188 | 100 | 100 | 100 | 100 | 90.3103 | 100
2 | wanden gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 46763.0586 | 0 | 0 | 46763.0586 | 2016-03-21 08:00 | 4d | 46763.0586 | 0 | 0 | -3558 | 0 | 43205.0586 | 0 | 100% | Finished | 46763.0586 | 46763.0586 | 100 | 80 | 100 | 100 | 92.3914 | 100
3 | dragend metselwerk snelbouw gelijkvloers blok B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 116907.6484 | 0 | 0 | 116907.6484 | 2016-03-21 08:00 | 17d | 116907.6484 | 0 | 0 | 190 | 0 | 117097.6484 | 0 | 100% | Finished | 116907.6484 | 116907.6484 | 100 | 113.3333 | 100 | 100 | 100.1625 | 100
4 | balken/liggers boven gelijkvloers blok B | 2016-04-05 08:00 | 2016-04-15 17:00 | 9d |  | 0 | 50659.9805 | 0 | 0 | 50659.9805 | 2016-04-07 08:00 | 10d | 50659.9805 | 0 | 0 | 6783 | 0 | 57442.9805 | 0 | 100% | Finished | 50659.9805 | 50659.9805 | 100 | 111.1111 | 100 | 100 | 113.3893 | 100
5 | afdek gelijkvloers blok B welfsels + opstort druklaag | 2016-04-18 08:00 | 2016-04-22 17:00 | 5d |  | 0 | 97423.0391 | 0 | 0 | 97423.0391 | 2016-04-21 08:00 | 5d | 97423.0391 | 0 | 0 | -2341 | 0 | 95082.0391 | 0 | 100% | Finished | 97423.0391 | 97423.0391 | 100 | 100 | 100 | 100 | 97.5971 | 100
25 | betonstructuur blok B nivo +1 | 2016-04-25 08:00 | 2016-05-30 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 29d | [5 empty] | 308583.2007 |  | 100% |  | 309145.2007 | 309145.2007
6 | kolommen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 2016-04-28 08:00 | 5d | 34005.9688 | 0 | 0 | 823 | 0 | 34828.9688 | 0 | 100% | Finished | 34005.9688 | 34005.9688 | 100 | 100 | 100 | 100 | 102.4202 | 100
7 | wanden kernen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 2016-04-28 08:00 | 4d | 40188.8789 | 0 | 0 | -6113 | 0 | 34075.8789 | 0 | 100% | Finished | 40188.8789 | 40188.8789 | 100 | 80 | 100 | 100 | 84.7893 | 100
8 | dragend metselwerk snelbouw +1 blok B | 2016-04-25 08:00 | 2016-05-13 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 2016-04-28 08:00 | 17d | 102017.9219 | 0 | 0 | -310 | 0 | 101707.9219 | 0 | 100% | Finished | 102017.9219 | 102017.9219 | 100 | 113.3333 | 100 | 100 | 99.6961 | 100
9 | balken/liggers boven +1 blok B | 2016-05-10 08:00 | 2016-05-20 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 2016-05-17 08:00 | 10d | 43280.3281 | 0 | 0 | 3524 | 0 | 46804.3281 | 0 | 100% | Finished | 43280.3281 | 43280.3281 | 100 | 111.1111 | 100 | 100 | 108.1423 | 100
10 | afdek verdieping +1 blok B welfsels + opstort druklaag | 2016-05-23 08:00 | 2016-05-30 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 2016-05-31 08:00 | 6d | 83469.2031 | 0 | 0 | 2038 | 0 | 85507.2031 | 0 | 100% | Finished | 83469.2031 | 83469.2031 | 100 | 100 | 100 | 100 | 102.4416 | 100
11 | platen tpg d=17 en d=21 boven +1 | 2016-05-25 08:00 | 2016-05-30 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 2016-06-02 08:00 | 4d | 6182.8999 | 0 | 0 | -524 | 0 | 5658.8999 | 0 | 100% | Finished | 6182.8999 | 6182.8999 | 100 | 100 | 100 | 100 | 91.525 | 100
26 | betonstructuur blok B nivo +2 | 2016-05-31 08:00 | 2016-07-05 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 176212.7695
12 | kolommen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 |  | 0 | 0 | 34005.9688 | 5d | 0 | 0 | 0 | 34005.9688 | 0% | Not Started | 0 | 34005.9688 | 100 |  | 0 | 100 |  | 0
13 | wanden kernen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 |  | 0 | 0 | 40188.8789 | 5d | 0 | 0 | 0 | 40188.8789 | 0% | Not Started | 0 | 40188.8789 | 100 |  | 0 | 100 |  | 0
14 | dragend metselwerk snelbouw +2 blok B | 2016-05-31 08:00 | 2016-06-20 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 |  | 0 | 0 | 102017.9219 | 15d | 0 | 0 | 0 | 102017.9219 | 0% | Not Started | 0 | 102017.9219 | 100 |  | 0 | 100 |  | 0
15 | balken/liggers boven +2 blok B | 2016-06-15 08:00 | 2016-06-27 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 |  | 0 | 0 | 43280.3281 | 9d | 0 | 0 | 0 | 43280.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | afdek verdieping +2 blok B welfsels + opstort druklaag | 2016-06-28 08:00 | 2016-07-05 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 |  | 0 | 0 | 83469.2031 | 6d | 0 | 0 | 0 | 83469.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | platen tpg d=17 en d=21 boven +2 | 2016-06-30 08:00 | 2016-07-05 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 |  | 0 | 0 | 6182.8999 | 4d | 0 | 0 | 0 | 6182.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | betonstructuur blok B nivo +3 | 2016-07-06 08:00 | 2016-07-15 17:00 | 8d |  |  | 350722.9443 |  |  | 350722.9443 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | kolommen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 38579.5195 | 0 | 0 | 38579.5195 |  | 0 | 0 | 38579.5195 | 3d | 0 | 0 | 0 | 38579.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | wanden kernen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 45593.9805 | 0 | 0 | 45593.9805 |  | 0 | 0 | 45593.9805 | 3d | 0 | 0 | 0 | 45593.9805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | dragend metselwerk snelbouw +3 blok B | 2016-07-06 08:00 | 2016-07-14 17:00 | 7d |  | 0 | 115738.5703 | 0 | 0 | 115738.5703 |  | 0 | 0 | 115738.5703 | 7d | 0 | 0 | 0 | 115738.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | balken/liggers boven +3 blok B | 2016-07-11 08:00 | 2016-07-13 17:00 | 3d |  | 0 | 49101.2109 | 0 | 0 | 49101.2109 |  | 0 | 0 | 49101.2109 | 3d | 0 | 0 | 0 | 49101.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | afdek verdieping +3 blok B welfsels + opstort druklaag | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 94695.2031 | 0 | 0 | 94695.2031 |  | 0 | 0 | 94695.2031 | 5d | 0 | 0 | 0 | 94695.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | platen tpg d=15 boven +3 | 2016-07-13 08:00 | 2016-07-15 17:00 | 3d |  | 0 | 7014.46 | 0 | 0 | 7014.46 |  | 0 | 0 | 7014.46 | 3d | 0 | 0 | 0 | 7014.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-07-19 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Structural Work (3) | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 1319736.291 |  |  | 1319736.291 |  | 86d | [5 empty] | 984866.3467 |  | 73.42% |  | 969013.3467 | 1319736.291
24 | betonstructuur blok B gelijkvloers | 2016-03-21 08:00 | 2016-04-22 17:00 | 25d |  |  | 350722.9453 |  |  | 350722.9453 |  | 28d | [5 empty] | 348020.9453 |  | 100% |  | 350722.9453 | 350722.9453
1 | kolommen gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 38969.2188 | 0 | 0 | 38969.2188 | 2016-03-21 08:00 | 5d | 38969.2188 | 0 | 0 | -3776 | 0 | 35193.2188 | 0 | 100% | Finished | 38969.2188 | 38969.2188 | 100 | 100 | 100 | 100 | 90.3103 | 100
2 | wanden gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 46763.0586 | 0 | 0 | 46763.0586 | 2016-03-21 08:00 | 4d | 46763.0586 | 0 | 0 | -3558 | 0 | 43205.0586 | 0 | 100% | Finished | 46763.0586 | 46763.0586 | 100 | 80 | 100 | 100 | 92.3914 | 100
3 | dragend metselwerk snelbouw gelijkvloers blok B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 116907.6484 | 0 | 0 | 116907.6484 | 2016-03-21 08:00 | 17d | 116907.6484 | 0 | 0 | 190 | 0 | 117097.6484 | 0 | 100% | Finished | 116907.6484 | 116907.6484 | 100 | 113.3333 | 100 | 100 | 100.1625 | 100
4 | balken/liggers boven gelijkvloers blok B | 2016-04-05 08:00 | 2016-04-15 17:00 | 9d |  | 0 | 50659.9805 | 0 | 0 | 50659.9805 | 2016-04-07 08:00 | 10d | 50659.9805 | 0 | 0 | 6783 | 0 | 57442.9805 | 0 | 100% | Finished | 50659.9805 | 50659.9805 | 100 | 111.1111 | 100 | 100 | 113.3893 | 100
5 | afdek gelijkvloers blok B welfsels + opstort druklaag | 2016-04-18 08:00 | 2016-04-22 17:00 | 5d |  | 0 | 97423.0391 | 0 | 0 | 97423.0391 | 2016-04-21 08:00 | 5d | 97423.0391 | 0 | 0 | -2341 | 0 | 95082.0391 | 0 | 100% | Finished | 97423.0391 | 97423.0391 | 100 | 100 | 100 | 100 | 97.5971 | 100
25 | betonstructuur blok B nivo +1 | 2016-04-25 08:00 | 2016-05-30 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 29d | [5 empty] | 308583.2007 |  | 100% |  | 309145.2007 | 309145.2007
6 | kolommen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 2016-04-28 08:00 | 5d | 34005.9688 | 0 | 0 | 823 | 0 | 34828.9688 | 0 | 100% | Finished | 34005.9688 | 34005.9688 | 100 | 100 | 100 | 100 | 102.4202 | 100
7 | wanden kernen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 2016-04-28 08:00 | 4d | 40188.8789 | 0 | 0 | -6113 | 0 | 34075.8789 | 0 | 100% | Finished | 40188.8789 | 40188.8789 | 100 | 80 | 100 | 100 | 84.7893 | 100
8 | dragend metselwerk snelbouw +1 blok B | 2016-04-25 08:00 | 2016-05-13 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 2016-04-28 08:00 | 17d | 102017.9219 | 0 | 0 | -310 | 0 | 101707.9219 | 0 | 100% | Finished | 102017.9219 | 102017.9219 | 100 | 113.3333 | 100 | 100 | 99.6961 | 100
9 | balken/liggers boven +1 blok B | 2016-05-10 08:00 | 2016-05-20 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 2016-05-17 08:00 | 10d | 43280.3281 | 0 | 0 | 3524 | 0 | 46804.3281 | 0 | 100% | Finished | 43280.3281 | 43280.3281 | 100 | 111.1111 | 100 | 100 | 108.1423 | 100
10 | afdek verdieping +1 blok B welfsels + opstort druklaag | 2016-05-23 08:00 | 2016-05-30 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 2016-05-31 08:00 | 6d | 83469.2031 | 0 | 0 | 2038 | 0 | 85507.2031 | 0 | 100% | Finished | 83469.2031 | 83469.2031 | 100 | 100 | 100 | 100 | 102.4416 | 100
11 | platen tpg d=17 en d=21 boven +1 | 2016-05-25 08:00 | 2016-05-30 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 2016-06-02 08:00 | 4d | 6182.8999 | 0 | 0 | -524 | 0 | 5658.8999 | 0 | 100% | Finished | 6182.8999 | 6182.8999 | 100 | 100 | 100 | 100 | 91.525 | 100
26 | betonstructuur blok B nivo +2 | 2016-05-31 08:00 | 2016-07-05 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 29d | [5 empty] | 328262.2007 |  | 100% |  | 309145.2007 | 309145.2007
12 | kolommen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 2016-06-08 08:00 | 5d | 34005.9688 | 0 | 0 | 254 | 0 | 34259.9688 | 0 | 100% | Finished | 34005.9688 | 34005.9688 | 100 | 100 | 100 | 100 | 100.7469 | 100
13 | wanden kernen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 2016-06-08 08:00 | 4d | 40188.8789 | 0 | 0 | 454 | 0 | 40642.8789 | 0 | 100% | Finished | 40188.8789 | 40188.8789 | 100 | 80 | 100 | 100 | 101.1297 | 100
14 | dragend metselwerk snelbouw +2 blok B | 2016-05-31 08:00 | 2016-06-20 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 2016-06-08 08:00 | 17d | 102017.9219 | 0 | 0 | 12063 | 0 | 114080.9219 | 0 | 100% | Finished | 102017.9219 | 102017.9219 | 100 | 113.3333 | 100 | 100 | 111.8244 | 100
15 | balken/liggers boven +2 blok B | 2016-06-15 08:00 | 2016-06-27 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 2016-06-27 08:00 | 10d | 43280.3281 | 0 | 0 | 4649 | 0 | 47929.3281 | 0 | 100% | Finished | 43280.3281 | 43280.3281 | 100 | 111.1111 | 100 | 100 | 110.7416 | 100
16 | afdek verdieping +2 blok B welfsels + opstort druklaag | 2016-06-28 08:00 | 2016-07-05 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 2016-07-11 08:00 | 6d | 83469.2031 | 0 | 0 | 2197 | 0 | 85666.2031 | 0 | 100% | Finished | 83469.2031 | 83469.2031 | 100 | 100 | 100 | 100 | 102.6321 | 100
17 | platen tpg d=17 en d=21 boven +2 | 2016-06-30 08:00 | 2016-07-05 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 2016-07-13 08:00 | 4d | 6182.8999 | 0 | 0 | -500 | 0 | 5682.8999 | 0 | 100% | Finished | 6182.8999 | 6182.8999 | 100 | 100 | 100 | 100 | 91.9132 | 100
27 | betonstructuur blok B nivo +3 | 2016-07-06 08:00 | 2016-07-15 17:00 | 8d |  |  | 350722.9443 |  |  | 350722.9443 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 350722.9443
18 | kolommen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 38579.5195 | 0 | 0 | 38579.5195 |  | 0 | 0 | 38579.5195 | 3d | 0 | 0 | 0 | 38579.5195 | 0% | Not Started | 0 | 38579.5195 | 100 |  | 0 | 100 |  | 0
19 | wanden kernen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 45593.9805 | 0 | 0 | 45593.9805 |  | 0 | 0 | 45593.9805 | 3d | 0 | 0 | 0 | 45593.9805 | 0% | Not Started | 0 | 45593.9805 | 100 |  | 0 | 100 |  | 0
20 | dragend metselwerk snelbouw +3 blok B | 2016-07-06 08:00 | 2016-07-14 17:00 | 7d |  | 0 | 115738.5703 | 0 | 0 | 115738.5703 |  | 0 | 0 | 115738.5703 | 7d | 0 | 0 | 0 | 115738.5703 | 0% | Not Started | 0 | 115738.5703 | 100 |  | 0 | 100 |  | 0
21 | balken/liggers boven +3 blok B | 2016-07-11 08:00 | 2016-07-13 17:00 | 3d |  | 0 | 49101.2109 | 0 | 0 | 49101.2109 |  | 0 | 0 | 49101.2109 | 3d | 0 | 0 | 0 | 49101.2109 | 0% | Not Started | 0 | 49101.2109 | 100 |  | 0 | 100 |  | 0
22 | afdek verdieping +3 blok B welfsels + opstort druklaag | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 94695.2031 | 0 | 0 | 94695.2031 |  | 0 | 0 | 94695.2031 | 5d | 0 | 0 | 0 | 94695.2031 | 0% | Not Started | 0 | 94695.2031 | 100 |  | 0 | 100 |  | 0
23 | platen tpg d=15 boven +3 | 2016-07-13 08:00 | 2016-07-15 17:00 | 3d |  | 0 | 7014.46 | 0 | 0 | 7014.46 |  | 0 | 0 | 7014.46 | 3d | 0 | 0 | 0 | 7014.46 | 0% | Not Started | 0 | 7014.46 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-08-01 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Structural Work (3) | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 1319736.291 |  |  | 1319736.291 |  | 96d | [5 empty] | 1353361.291 |  | 100% |  | 1319736.291 | 1319736.291
24 | betonstructuur blok B gelijkvloers | 2016-03-21 08:00 | 2016-04-22 17:00 | 25d |  |  | 350722.9453 |  |  | 350722.9453 |  | 28d | [5 empty] | 348020.9453 |  | 100% |  | 350722.9453 | 350722.9453
1 | kolommen gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 38969.2188 | 0 | 0 | 38969.2188 | 2016-03-21 08:00 | 5d | 38969.2188 | 0 | 0 | -3776 | 0 | 35193.2188 | 0 | 100% | Finished | 38969.2188 | 38969.2188 | 100 | 100 | 100 | 100 | 90.3103 | 100
2 | wanden gelijkvloers blok B | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 46763.0586 | 0 | 0 | 46763.0586 | 2016-03-21 08:00 | 4d | 46763.0586 | 0 | 0 | -3558 | 0 | 43205.0586 | 0 | 100% | Finished | 46763.0586 | 46763.0586 | 100 | 80 | 100 | 100 | 92.3914 | 100
3 | dragend metselwerk snelbouw gelijkvloers blok B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 116907.6484 | 0 | 0 | 116907.6484 | 2016-03-21 08:00 | 17d | 116907.6484 | 0 | 0 | 190 | 0 | 117097.6484 | 0 | 100% | Finished | 116907.6484 | 116907.6484 | 100 | 113.3333 | 100 | 100 | 100.1625 | 100
4 | balken/liggers boven gelijkvloers blok B | 2016-04-05 08:00 | 2016-04-15 17:00 | 9d |  | 0 | 50659.9805 | 0 | 0 | 50659.9805 | 2016-04-07 08:00 | 10d | 50659.9805 | 0 | 0 | 6783 | 0 | 57442.9805 | 0 | 100% | Finished | 50659.9805 | 50659.9805 | 100 | 111.1111 | 100 | 100 | 113.3893 | 100
5 | afdek gelijkvloers blok B welfsels + opstort druklaag | 2016-04-18 08:00 | 2016-04-22 17:00 | 5d |  | 0 | 97423.0391 | 0 | 0 | 97423.0391 | 2016-04-21 08:00 | 5d | 97423.0391 | 0 | 0 | -2341 | 0 | 95082.0391 | 0 | 100% | Finished | 97423.0391 | 97423.0391 | 100 | 100 | 100 | 100 | 97.5971 | 100
25 | betonstructuur blok B nivo +1 | 2016-04-25 08:00 | 2016-05-30 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 29d | [5 empty] | 308583.2007 |  | 100% |  | 309145.2007 | 309145.2007
6 | kolommen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 2016-04-28 08:00 | 5d | 34005.9688 | 0 | 0 | 823 | 0 | 34828.9688 | 0 | 100% | Finished | 34005.9688 | 34005.9688 | 100 | 100 | 100 | 100 | 102.4202 | 100
7 | wanden kernen +1 blok B | 2016-04-25 08:00 | 2016-04-29 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 2016-04-28 08:00 | 4d | 40188.8789 | 0 | 0 | -6113 | 0 | 34075.8789 | 0 | 100% | Finished | 40188.8789 | 40188.8789 | 100 | 80 | 100 | 100 | 84.7893 | 100
8 | dragend metselwerk snelbouw +1 blok B | 2016-04-25 08:00 | 2016-05-13 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 2016-04-28 08:00 | 17d | 102017.9219 | 0 | 0 | -310 | 0 | 101707.9219 | 0 | 100% | Finished | 102017.9219 | 102017.9219 | 100 | 113.3333 | 100 | 100 | 99.6961 | 100
9 | balken/liggers boven +1 blok B | 2016-05-10 08:00 | 2016-05-20 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 2016-05-17 08:00 | 10d | 43280.3281 | 0 | 0 | 3524 | 0 | 46804.3281 | 0 | 100% | Finished | 43280.3281 | 43280.3281 | 100 | 111.1111 | 100 | 100 | 108.1423 | 100
10 | afdek verdieping +1 blok B welfsels + opstort druklaag | 2016-05-23 08:00 | 2016-05-30 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 2016-05-31 08:00 | 6d | 83469.2031 | 0 | 0 | 2038 | 0 | 85507.2031 | 0 | 100% | Finished | 83469.2031 | 83469.2031 | 100 | 100 | 100 | 100 | 102.4416 | 100
11 | platen tpg d=17 en d=21 boven +1 | 2016-05-25 08:00 | 2016-05-30 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 2016-06-02 08:00 | 4d | 6182.8999 | 0 | 0 | -524 | 0 | 5658.8999 | 0 | 100% | Finished | 6182.8999 | 6182.8999 | 100 | 100 | 100 | 100 | 91.525 | 100
26 | betonstructuur blok B nivo +2 | 2016-05-31 08:00 | 2016-07-05 17:00 | 26d |  |  | 309145.2007 |  |  | 309145.2007 |  | 29d | [5 empty] | 328262.2007 |  | 100% |  | 309145.2007 | 309145.2007
12 | kolommen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 34005.9688 | 0 | 0 | 34005.9688 | 2016-06-08 08:00 | 5d | 34005.9688 | 0 | 0 | 254 | 0 | 34259.9688 | 0 | 100% | Finished | 34005.9688 | 34005.9688 | 100 | 100 | 100 | 100 | 100.7469 | 100
13 | wanden kernen +2 blok B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 40188.8789 | 0 | 0 | 40188.8789 | 2016-06-08 08:00 | 4d | 40188.8789 | 0 | 0 | 454 | 0 | 40642.8789 | 0 | 100% | Finished | 40188.8789 | 40188.8789 | 100 | 80 | 100 | 100 | 101.1297 | 100
14 | dragend metselwerk snelbouw +2 blok B | 2016-05-31 08:00 | 2016-06-20 17:00 | 15d |  | 0 | 102017.9219 | 0 | 0 | 102017.9219 | 2016-06-08 08:00 | 17d | 102017.9219 | 0 | 0 | 12063 | 0 | 114080.9219 | 0 | 100% | Finished | 102017.9219 | 102017.9219 | 100 | 113.3333 | 100 | 100 | 111.8244 | 100
15 | balken/liggers boven +2 blok B | 2016-06-15 08:00 | 2016-06-27 17:00 | 9d |  | 0 | 43280.3281 | 0 | 0 | 43280.3281 | 2016-06-27 08:00 | 10d | 43280.3281 | 0 | 0 | 4649 | 0 | 47929.3281 | 0 | 100% | Finished | 43280.3281 | 43280.3281 | 100 | 111.1111 | 100 | 100 | 110.7416 | 100
16 | afdek verdieping +2 blok B welfsels + opstort druklaag | 2016-06-28 08:00 | 2016-07-05 17:00 | 6d |  | 0 | 83469.2031 | 0 | 0 | 83469.2031 | 2016-07-11 08:00 | 6d | 83469.2031 | 0 | 0 | 2197 | 0 | 85666.2031 | 0 | 100% | Finished | 83469.2031 | 83469.2031 | 100 | 100 | 100 | 100 | 102.6321 | 100
17 | platen tpg d=17 en d=21 boven +2 | 2016-06-30 08:00 | 2016-07-05 17:00 | 4d |  | 0 | 6182.8999 | 0 | 0 | 6182.8999 | 2016-07-13 08:00 | 4d | 6182.8999 | 0 | 0 | -500 | 0 | 5682.8999 | 0 | 100% | Finished | 6182.8999 | 6182.8999 | 100 | 100 | 100 | 100 | 91.9132 | 100
27 | betonstructuur blok B nivo +3 | 2016-07-06 08:00 | 2016-07-15 17:00 | 8d |  |  | 350722.9443 |  |  | 350722.9443 |  | 10d | [5 empty] | 368494.9443 |  | 100% |  | 350722.9443 | 350722.9443
18 | kolommen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 38579.5195 | 0 | 0 | 38579.5195 | 2016-07-19 08:00 | 3d | 38579.5195 | 0 | 0 | 2544 | 0 | 41123.5195 | 0 | 100% | Finished | 38579.5195 | 38579.5195 | 100 | 100 | 100 | 100 | 106.5942 | 100
19 | wanden kernen +3 blok B | 2016-07-06 08:00 | 2016-07-08 17:00 | 3d |  | 0 | 45593.9805 | 0 | 0 | 45593.9805 | 2016-07-19 08:00 | 4d | 45593.9805 | 0 | 0 | 0 | 0 | 45593.9805 | 0 | 100% | Finished | 45593.9805 | 45593.9805 | 100 | 133.3333 | 100 | 100 | 100 | 100
20 | dragend metselwerk snelbouw +3 blok B | 2016-07-06 08:00 | 2016-07-14 17:00 | 7d |  | 0 | 115738.5703 | 0 | 0 | 115738.5703 | 2016-07-19 08:00 | 9d | 115738.5703 | 0 | 0 | 1617 | 0 | 117355.5703 | 0 | 100% | Finished | 115738.5703 | 115738.5703 | 100 | 128.5714 | 100 | 100 | 101.3971 | 100
21 | balken/liggers boven +3 blok B | 2016-07-11 08:00 | 2016-07-13 17:00 | 3d |  | 0 | 49101.2109 | 0 | 0 | 49101.2109 | 2016-07-26 08:00 | 3d | 49101.2109 | 0 | 0 | 6738 | 0 | 55839.2109 | 0 | 100% | Finished | 49101.2109 | 49101.2109 | 100 | 100 | 100 | 100 | 113.7227 | 100
22 | afdek verdieping +3 blok B welfsels + opstort druklaag | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d |  | 0 | 94695.2031 | 0 | 0 | 94695.2031 | 2016-07-26 08:00 | 5d | 94695.2031 | 0 | 0 | 7014 | 0 | 101709.2031 | 0 | 100% | Finished | 94695.2031 | 94695.2031 | 100 | 100 | 100 | 100 | 107.4069 | 100
23 | platen tpg d=15 boven +3 | 2016-07-13 08:00 | 2016-07-15 17:00 | 3d |  | 0 | 7014.46 | 0 | 0 | 7014.46 | 2016-07-28 08:00 | 3d | 7014.46 | 0 | 0 | -141 | 0 | 6873.46 | 0 | 100% | Finished | 7014.46 | 7014.46 | 100 | 100 | 100 | 100 | 97.9899 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-21 08:00 | 2016-04-28 08:00 | 526935.7148 | 350722.9453 | 348020.9453 | 2016-04-22 17:00 | -176212.7695 | 66.56% | 2702 | 100.8% | -3d | 89.29% | 100% | 2016-08-02 11:00 | 2016-09-14 15:00 | 2016-09-13 15:00 | 2016-07-29 11:00 | 2016-09-14 15:00 | 2016-09-13 17:00 | 2016-07-20 17:00 | 2016-08-01 10:00 | 2016-07-29 14:00 | 1317034.291 | 1309568.9281 | 1803893.0142 | 1433315.8925 | 1792676.8495 | 1424954.6861 | 1379622.5446 | 1332008.0668 | 0.89286 | 1.0078 | 0.66559 | 1 | -3 | 1.0078 | 1 | 0.89286 | 1
Tracking Period 2 | 2016-04-28 08:00 | 2016-06-08 08:00 | 836080.9155 | 659868.146 | 656604.146 | 2016-05-30 17:00 | -176212.7695 | 78.92% | 3264 | 100.5% | -6d | 89.47% | 100% | 2016-08-02 11:00 | 2016-08-17 15:00 | 2016-08-17 09:00 | 2016-08-02 17:00 | 2016-08-17 15:00 | 2016-08-17 12:00 | 2016-07-25 17:00 | 2016-07-29 17:00 | 2016-07-29 15:00 | 1316472.291 | 1313208.291 | 1492685.0603 | 1394103.8375 | 1488549.4339 | 1390455.8375 | 1342662.7567 | 1327935.8206 | 0.89474 | 1.005 | 0.78924 | 1 | -6 | 1.005 | 1 | 0.89474 | 1
Tracking Period 3 | 2016-06-08 08:00 | 2016-07-19 08:00 | 1319736.291 | 969013.3467 | 984866.3467 | 2016-07-05 17:00 | -350722.9443 | 73.42% | -15853 | 98.39% | -9d | 89.53% | 100% | 2016-08-17 14:00 | 2016-08-29 15:00 | 2016-08-31 14:00 | 2016-08-18 16:00 | 2016-08-31 09:00 | 2016-08-31 14:00 | 2016-07-28 17:00 | 2016-07-29 16:00 | 2016-08-01 09:00 | 1335589.291 | 1341327.0973 | 1462529.3214 | 1376582.8819 | 1470343.8589 | 1382991.3408 | 1360383.8635 | 1347861.2457 | 0.89535 | 0.9839 | 0.73425 | 1 | -9 | 0.9839 | 1 | 0.89535 | 1
Tracking Period 4 | 2016-07-19 08:00 | 2016-08-01 17:00 | 1319736.291 | 1319736.291 | 1353361.291 | 2016-07-15 17:00 | 0 | 100% | -33625 | 97.52% | -11d | 88.54% | 100% | 2016-07-15 17:00 | 2016-07-15 17:00 | 2016-07-20 09:00 | 2016-08-01 17:00 | 2016-08-01 17:00 | 2016-08-01 17:00 | 2016-08-01 17:00 | 2016-08-01 17:00 | 2016-08-01 17:00 | 1353361.291 | 1353361.291 | 1353361.291 | 1353361.291 | 1353361.291 | 1353361.291 | 1353361.291 | 1353361.291 | 0.88542 | 0.97515 | 1 | 1 | -11 | 0.97515 | 1 | 0.88542 | 1