## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | PROJECT SOCIAL HOUSING | 1 |  |  | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 | 493.375
1 | Ruwbouw | 1.1 |  |  | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 238.375
2 | Buitenriolering | 1.2 |  |  | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 18.375
3 | Daktimmer | 1.3 |  |  | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 18.375
4 | Dakbedekking | 1.4 |  |  | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 25.375
5 | dakisolatie | 1.5 |  |  | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 | 10.375
6 | Buitenschrijnwerk | 1.6 |  |  | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 | 4.375
7 | Aansluiting watermaatschappij | 1.7 |  |  | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
8 | Pleisterwerken | 1.8 |  |  | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 | 60.375
9 | Chape fase1 (2woningen) | 1.9 |  |  | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 | 4.375
10 | Chape fase2 (3woningen) | 1.10 |  |  | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 | 4.375
11 | Technieken voor chape fase1 | 1.11 |  |  | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 4.375
12 | Technieken voor chape fase2 | 1.12 |  |  | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 6.375
13 | afwerking technieken sanitair / elektriciteit | 1.13 |  |  | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 | 42.375
14 | vloer en tegelwerken | 1.14 |  |  | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 | 53.375
15 | binnenschrijnwerk (deuren, trappen, keukens) | 1.15 |  |  | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 | 28.375
16 | buitenaanleg | 1.16 |  |  | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 | 32.375
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 1.17 |  |  | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 | 26.375
18 | oplevering | 1.18 |  |  | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT SOCIAL HOUSING | 2816h
1 | Ruwbouw | 1368h | standard - no risk | 99 | 100 | 101
2 | Buitenriolering | 120h | standard - no risk | 99 | 100 | 101
3 | Daktimmer | 120h | standard - no risk | 99 | 100 | 101
4 | Dakbedekking | 160h | standard - no risk | 99 | 100 | 101
5 | dakisolatie | 72h | standard - no risk | 99 | 100 | 101
6 | Buitenschrijnwerk | 40h | standard - no risk | 99 | 100 | 101
7 | Aansluiting watermaatschappij | 8h | standard - no risk | 99 | 100 | 101
8 | Pleisterwerken | 360h | standard - no risk | 99 | 100 | 101
9 | Chape fase1 (2woningen) | 40h | standard - no risk | 99 | 100 | 101
10 | Chape fase2 (3woningen) | 40h | standard - no risk | 99 | 100 | 101
11 | Technieken voor chape fase1 | 40h | standard - no risk | 99 | 100 | 101
12 | Technieken voor chape fase2 | 40h | standard - no risk | 99 | 100 | 101
13 | afwerking technieken sanitair / elektriciteit | 248h | standard - no risk | 99 | 100 | 101
14 | vloer en tegelwerken | 320h | standard - no risk | 99 | 100 | 101
15 | binnenschrijnwerk (deuren, trappen, keukens) | 168h | standard - no risk | 99 | 100 | 101
16 | buitenaanleg | 200h | standard - no risk | 99 | 100 | 101
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 152h | standard - no risk | 99 | 100 | 101
18 | oplevering | 8h | standard - no risk | 99 | 100 | 101

## Project Control - TP1
| TP Status Date | 2017-09-10 17:00 |  | TP Name | TP1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 166d | [5 empty] | 248029.5892 |  | 33.62% |  | 246956.5292 | 247150.0805
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 166d | 247150.0805 | 7630.3865 | 5d 1h | 879.5088 | 0 | 248029.5892 | 7630.3865 | 97% | Started | 246956.5292 | 247150.0805
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 |  | 0 | 0 | 29485 | 15d | 0 | 0 | 0 | 29485 | 0% | Not Started | 0 | 0
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 |  | 0 | 0 | 33214.25 | 15d | 0 | 0 | 0 | 33214.25 | 0% | Not Started | 0 | 0
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 |  | 0 | 0 | 40046.63 | 20d | 0 | 0 | 0 | 40046.63 | 0% | Not Started | 0 | 0
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 |  | 0 | 0 | 6250 | 9d | 0 | 0 | 0 | 6250 | 0% | Not Started | 0 | 0
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 |  | 0 | 0 | 51095.44 | 5d | 0 | 0 | 0 | 51095.44 | 0% | Not Started | 0 | 0
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 |  | 0 | 0 | 26890.93 | 45d | 0 | 0 | 0 | 26890.93 | 0% | Not Started | 0 | 0
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 |  | 0 | 0 | 7736.592 | 5d | 0 | 0 | 0 | 7736.592 | 0% | Not Started | 0 | 0
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 |  | 0 | 0 | 11604.888 | 5d | 0 | 0 | 0 | 11604.888 | 0% | Not Started | 0 | 0
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 |  | 0 | 0 | 42927.02 | 31d | 0 | 0 | 0 | 42927.02 | 0% | Not Started | 0 | 0
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 |  | 0 | 0 | 34940.91 | 40d | 0 | 0 | 0 | 34940.91 | 0% | Not Started | 0 | 0
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 |  | 0 | 0 | 78515.2 | 21d | 0 | 0 | 0 | 78515.2 | 0% | Not Started | 0 | 0
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 |  | 0 | 0 | 22183.65 | 25d | 0 | 0 | 0 | 22183.65 | 0% | Not Started | 0 | 0
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 |  | 0 | 0 | 35117.24 | 19d | 0 | 0 | 0 | 35117.24 | 0% | Not Started | 0 | 0
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2017-10-19 17:00 |  | TP Name | TP2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 195d | [5 empty] | 320253.362 |  | 42.99% |  | 315841.251 | 345326.251
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 |  | 0 | 0 | 29485 | 15d | 0 | 0 | 0 | 29485 | 0% | Not Started | 0 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 14d | 28032.641 | 12013.989 | 6d | 3506.111 | 0 | 31538.752 | 12013.989 | 70% | Started | 28032.641 | 28032.641
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 |  | 0 | 0 | 6250 | 9d | 0 | 0 | 0 | 6250 | 0% | Not Started | 0 | 0
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 |  | 0 | 0 | 51095.44 | 5d | 0 | 0 | 0 | 51095.44 | 0% | Not Started | 0 | 0
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 |  | 0 | 0 | 26890.93 | 45d | 0 | 0 | 0 | 26890.93 | 0% | Not Started | 0 | 0
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 |  | 0 | 0 | 7736.592 | 5d | 0 | 0 | 0 | 7736.592 | 0% | Not Started | 0 | 0
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 |  | 0 | 0 | 11604.888 | 5d | 0 | 0 | 0 | 11604.888 | 0% | Not Started | 0 | 0
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 |  | 0 | 0 | 42927.02 | 31d | 0 | 0 | 0 | 42927.02 | 0% | Not Started | 0 | 0
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 |  | 0 | 0 | 34940.91 | 40d | 0 | 0 | 0 | 34940.91 | 0% | Not Started | 0 | 0
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 |  | 0 | 0 | 78515.2 | 21d | 0 | 0 | 0 | 78515.2 | 0% | Not Started | 0 | 0
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 |  | 0 | 0 | 22183.65 | 25d | 0 | 0 | 0 | 22183.65 | 0% | Not Started | 0 | 0
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 |  | 0 | 0 | 35117.24 | 19d | 0 | 0 | 0 | 35117.24 | 0% | Not Started | 0 | 0
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2017-11-04 17:00 |  | TP Name | TP3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 206d | [5 empty] | 333769.97 |  | 44.63% |  | 327855.24 | 357340.24
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 |  | 0 | 0 | 29485 | 15d | 0 | 0 | 0 | 29485 | 0% | Not Started | 0 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 100% | Finished | 40046.63 | 40046.63
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 |  | 0 | 0 | 6250 | 9d | 0 | 0 | 0 | 6250 | 0% | Not Started | 0 | 0
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 |  | 0 | 0 | 51095.44 | 5d | 0 | 0 | 0 | 51095.44 | 0% | Not Started | 0 | 0
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 |  | 0 | 0 | 26890.93 | 45d | 0 | 0 | 0 | 26890.93 | 0% | Not Started | 0 | 0
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 |  | 0 | 0 | 7736.592 | 5d | 0 | 0 | 0 | 7736.592 | 0% | Not Started | 0 | 0
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 |  | 0 | 0 | 11604.888 | 5d | 0 | 0 | 0 | 11604.888 | 0% | Not Started | 0 | 0
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 |  | 0 | 0 | 42927.02 | 31d | 0 | 0 | 0 | 42927.02 | 0% | Not Started | 0 | 0
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 |  | 0 | 0 | 34940.91 | 40d | 0 | 0 | 0 | 34940.91 | 0% | Not Started | 0 | 0
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 |  | 0 | 0 | 78515.2 | 21d | 0 | 0 | 0 | 78515.2 | 0% | Not Started | 0 | 0
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 |  | 0 | 0 | 22183.65 | 25d | 0 | 0 | 0 | 22183.65 | 0% | Not Started | 0 | 0
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 |  | 0 | 0 | 35117.24 | 19d | 0 | 0 | 0 | 35117.24 | 0% | Not Started | 0 | 0
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2017-11-08 17:00 |  | TP Name | TP4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 209d | [5 empty] | 340830.07 |  | 45.43% |  | 333752.24 | 357340.24
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 2017-11-04 08:00 | 0 | 0 | 29485 | 15d | 7060.1 | 0 | 7060.1 | 29485 | 20% | Started | 5897 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 100% | Finished | 40046.63 | 40046.63
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 |  | 0 | 0 | 6250 | 9d | 0 | 0 | 0 | 6250 | 0% | Not Started | 0 | 0
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 |  | 0 | 0 | 51095.44 | 5d | 0 | 0 | 0 | 51095.44 | 0% | Not Started | 0 | 0
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 |  | 0 | 0 | 26890.93 | 45d | 0 | 0 | 0 | 26890.93 | 0% | Not Started | 0 | 0
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 |  | 0 | 0 | 7736.592 | 5d | 0 | 0 | 0 | 7736.592 | 0% | Not Started | 0 | 0
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 |  | 0 | 0 | 11604.888 | 5d | 0 | 0 | 0 | 11604.888 | 0% | Not Started | 0 | 0
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 |  | 0 | 0 | 42927.02 | 31d | 0 | 0 | 0 | 42927.02 | 0% | Not Started | 0 | 0
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 |  | 0 | 0 | 34940.91 | 40d | 0 | 0 | 0 | 34940.91 | 0% | Not Started | 0 | 0
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 |  | 0 | 0 | 78515.2 | 21d | 0 | 0 | 0 | 78515.2 | 0% | Not Started | 0 | 0
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 |  | 0 | 0 | 22183.65 | 25d | 0 | 0 | 0 | 22183.65 | 0% | Not Started | 0 | 0
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 |  | 0 | 0 | 35117.24 | 19d | 0 | 0 | 0 | 35117.24 | 0% | Not Started | 0 | 0
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2017-11-21 17:00 |  | TP Name | TP5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 218d | [5 empty] | 392076.7435 |  | 51.57% |  | 378854.0532 | 379167.3049
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 2017-11-04 08:00 | 12d | 23588 | 0 | 0 | 11712.5 | 0 | 35300.5 | 0 | 100% | Finished | 29485 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 100% | Finished | 40046.63 | 40046.63
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 |  | 0 | 0 | 6250 | 9d | 0 | 0 | 0 | 6250 | 0% | Not Started | 0 | 1388.8889
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 | 2017-11-20 08:00 | 2d | 20438.176 | 30657.264 | 3d | 1600.024 | 0 | 22038.2 | 30657.264 | 40% | Started | 20438.176 | 20438.176
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 | 2017-11-21 08:00 | 1d | 597.5762 | 14341.8293 | 24d | 370.4973 | 0 | 968.0735 | 14341.8293 | 4% | Started | 1075.6372 | 0
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 |  | 0 | 0 | 7736.592 | 5d | 0 | 0 | 0 | 7736.592 | 0% | Not Started | 0 | 0
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 |  | 0 | 0 | 11604.888 | 5d | 0 | 0 | 0 | 11604.888 | 0% | Not Started | 0 | 0
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 |  | 0 | 0 | 42927.02 | 31d | 0 | 0 | 0 | 42927.02 | 0% | Not Started | 0 | 0
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 |  | 0 | 0 | 34940.91 | 40d | 0 | 0 | 0 | 34940.91 | 0% | Not Started | 0 | 0
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 |  | 0 | 0 | 78515.2 | 21d | 0 | 0 | 0 | 78515.2 | 0% | Not Started | 0 | 0
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 |  | 0 | 0 | 22183.65 | 25d | 0 | 0 | 0 | 22183.65 | 0% | Not Started | 0 | 0
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 |  | 0 | 0 | 35117.24 | 19d | 0 | 0 | 0 | 35117.24 | 0% | Not Started | 0 | 0
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP6
| TP Status Date | 2018-01-04 17:00 |  | TP Name | TP6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 250d | [5 empty] | 481955.6049 |  | 63.79% |  | 468618.6077 | 462015.3904
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 2017-11-04 08:00 | 12d | 23588 | 0 | 0 | 11712.5 | 0 | 35300.5 | 0 | 100% | Finished | 29485 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 100% | Finished | 40046.63 | 40046.63
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 | 2018-01-04 08:00 | 1d | 694.4444 | 0 | 0 | 5555.5556 | 0 | 6250 | 0 | 100% | Finished | 6250 | 6250
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 | 2017-11-20 08:00 | 34d | 347448.992 | 0 | 0 | -292353.492 | 0 | 55095.5 | 0 | 100% | Finished | 51095.44 | 51095.44
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-21 08:00 | 33d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 | 2017-11-21 08:00 | 33d | 19720.0153 | 2465.0019 | 4d 1h | 1819.6196 | 0 | 21539.6349 | 2465.0019 | 89% | Started | 23932.9277 | 17329.7104
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 |  | 0 | 0 | 7736.592 | 5d | 0 | 0 | 0 | 7736.592 | 0% | Not Started | 0 | 0
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 |  | 0 | 0 | 11604.888 | 5d | 0 | 0 | 0 | 11604.888 | 0% | Not Started | 0 | 0
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2017-12-18 08:00 | 14d | 84000 | 0 | 0 | -54000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 |  | 0 | 0 | 30000 | 5d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 |  | 0 | 0 | 42927.02 | 31d | 0 | 0 | 0 | 42927.02 | 0% | Not Started | 0 | 0
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 |  | 0 | 0 | 34940.91 | 40d | 0 | 0 | 0 | 34940.91 | 0% | Not Started | 0 | 0
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 |  | 0 | 0 | 78515.2 | 21d | 0 | 0 | 0 | 78515.2 | 0% | Not Started | 0 | 0
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 |  | 0 | 0 | 22183.65 | 25d | 0 | 0 | 0 | 22183.65 | 0% | Not Started | 0 | 0
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 |  | 0 | 0 | 35117.24 | 19d | 0 | 0 | 0 | 35117.24 | 0% | Not Started | 0 | 0
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP7
| TP Status Date | 2018-01-18 17:00 |  | TP Name | TP7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 260d | [5 empty] | 532556.7798 |  | 70.87% |  | 520649.1807 | 505727.7447
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 2017-11-04 08:00 | 12d | 23588 | 0 | 0 | 11712.5 | 0 | 35300.5 | 0 | 100% | Finished | 29485 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 100% | Finished | 40046.63 | 40046.63
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 | 2018-01-04 08:00 | 1d | 694.4444 | 0 | 0 | 5555.5556 | 0 | 6250 | 0 | 100% | Finished | 6250 | 6250
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 | 2017-11-20 08:00 | 34d | 347448.992 | 0 | 0 | -292353.492 | 0 | 55095.5 | 0 | 100% | Finished | 51095.44 | 51095.44
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-21 08:00 | 33d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 | 2017-11-21 08:00 | 43d | 25695.7776 | 224.0911 | 3h | -1735.9589 | 0 | 23959.8186 | 224.0911 | 99% | Started | 26622.0207 | 23305.4727
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 | 2018-01-08 08:00 | 9d | 13925.8656 | 0 | 0 | -6189.2736 | 0 | 7736.592 | 0 | 100% | Finished | 7736.592 | 7736.592
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 | 2018-01-04 08:00 | 11d | 25530.7536 | 0 | 0 | -15086.3544 | 0 | 10444.3992 | 0 | 100% | Finished | 11604.888 | 0
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2017-12-18 08:00 | 14d | 84000 | 0 | 0 | -54000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2018-01-09 08:00 | 8d | 48000 | 0 | 0 | -18000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 |  | 0 | 0 | 42927.02 | 31d | 0 | 0 | 0 | 42927.02 | 0% | Not Started | 0 | 0
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 |  | 0 | 0 | 34940.91 | 40d | 0 | 0 | 0 | 34940.91 | 0% | Not Started | 0 | 0
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 |  | 0 | 0 | 78515.2 | 21d | 0 | 0 | 0 | 78515.2 | 0% | Not Started | 0 | 0
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 |  | 0 | 0 | 22183.65 | 25d | 0 | 0 | 0 | 22183.65 | 0% | Not Started | 0 | 0
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 |  | 0 | 0 | 35117.24 | 19d | 0 | 0 | 0 | 35117.24 | 0% | Not Started | 0 | 0
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP8
| TP Status Date | 2018-04-06 17:00 |  | TP Name | TP8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 316d | [5 empty] | 702158.1618 |  | 93.97% |  | 690277.4536 | 633402.1876
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 2017-11-04 08:00 | 12d | 23588 | 0 | 0 | 11712.5 | 0 | 35300.5 | 0 | 100% | Finished | 29485 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 100% | Finished | 40046.63 | 40046.63
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 | 2018-01-04 08:00 | 1d | 694.4444 | 0 | 0 | 5555.5556 | 0 | 6250 | 0 | 100% | Finished | 6250 | 6250
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 | 2017-11-20 08:00 | 34d | 347448.992 | 0 | 0 | -292353.492 | 0 | 55095.5 | 0 | 100% | Finished | 51095.44 | 51095.44
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-21 08:00 | 33d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 | 2017-11-21 08:00 | 99d | 59160.046 | 0 | 0 | -34958.209 | 0 | 24201.837 | 0 | 100% | Finished | 26890.93 | 26890.93
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 | 2018-01-08 08:00 | 9d | 13925.8656 | 0 | 0 | -6189.2736 | 0 | 7736.592 | 0 | 100% | Finished | 7736.592 | 7736.592
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 | 2018-01-04 08:00 | 11d | 25530.7536 | 0 | 0 | -15086.3544 | 0 | 10444.3992 | 0 | 100% | Finished | 11604.888 | 11604.888
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2017-12-18 08:00 | 14d | 84000 | 0 | 0 | -54000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2018-01-09 08:00 | 8d | 48000 | 0 | 0 | -18000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 |  | 0 | 0 | 42927.02 | 31d | 0 | 0 | 0 | 42927.02 | 0% | Not Started | 0 | 20771.1387
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 | 2018-02-05 08:00 | 45d | 39308.5238 | 1637.8552 | 1d 7h | -5765.2502 | 0 | 33543.2736 | 1637.8552 | 96% | Started | 33543.2736 | 34940.91
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 | 2018-01-18 08:00 | 57d | 213112.6857 | 0 | 0 | -134597.4857 | 0 | 78515.2 | 0 | 100% | Finished | 78515.2 | 18694.0952
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 | 2018-03-12 08:00 | 20d | 17746.92 | 0 | 0 | 4436.73 | 0 | 22183.65 | 0 | 100% | Finished | 22183.65 | 17746.92
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 | 2018-03-23 08:00 | 11d | 20331.0337 | 0 | 0 | 14786.2063 | 0 | 35117.24 | 0 | 100% | Finished | 35117.24 | 20331.0337
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP9
| TP Status Date | 2018-05-02 17:00 |  | TP Name | TP9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 334d | [5 empty] | 748555.7982 |  | 100% |  | 734602.11 | 734602.11
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 2017-11-04 08:00 | 12d | 23588 | 0 | 0 | 11712.5 | 0 | 35300.5 | 0 | 100% | Finished | 29485 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 100% | Finished | 40046.63 | 40046.63
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 | 2018-01-04 08:00 | 1d | 694.4444 | 0 | 0 | 5555.5556 | 0 | 6250 | 0 | 100% | Finished | 6250 | 6250
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 | 2017-11-20 08:00 | 34d | 347448.992 | 0 | 0 | -292353.492 | 0 | 55095.5 | 0 | 100% | Finished | 51095.44 | 51095.44
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-21 08:00 | 33d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 | 2017-11-21 08:00 | 99d | 59160.046 | 0 | 0 | -34958.209 | 0 | 24201.837 | 0 | 100% | Finished | 26890.93 | 26890.93
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 | 2018-01-08 08:00 | 9d | 13925.8656 | 0 | 0 | -6189.2736 | 0 | 7736.592 | 0 | 100% | Finished | 7736.592 | 7736.592
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 | 2018-01-04 08:00 | 11d | 25530.7536 | 0 | 0 | -15086.3544 | 0 | 10444.3992 | 0 | 100% | Finished | 11604.888 | 11604.888
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2017-12-18 08:00 | 14d | 84000 | 0 | 0 | -54000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2018-01-09 08:00 | 8d | 48000 | 0 | 0 | -18000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 | 2018-04-06 08:00 | 19d | 26310.109 | 0 | 0 | 18689.891 | 0 | 45000 | 0 | 100% | Finished | 42927.02 | 42927.02
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 | 2018-02-05 08:00 | 63d | 55031.9333 | 0 | 0 | -20091.0232 | 0 | 34940.91 | 0 | 100% | Finished | 34940.91 | 34940.91
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 | 2018-01-18 08:00 | 57d | 213112.6857 | 0 | 0 | -134597.4857 | 0 | 78515.2 | 0 | 100% | Finished | 78515.2 | 78515.2
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 | 2018-03-12 08:00 | 20d | 17746.92 | 0 | 0 | 4436.73 | 0 | 22183.65 | 0 | 100% | Finished | 22183.65 | 22183.65
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 | 2018-03-23 08:00 | 11d | 20331.0337 | 0 | 0 | 14786.2063 | 0 | 35117.24 | 0 | 100% | Finished | 35117.24 | 35117.24
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP10
| TP Status Date | 2018-05-31 17:00 |  | TP Name | TP10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT SOCIAL HOUSING | 2017-01-20 08:00 | 2018-05-28 17:00 | 352d |  |  | 0 |  |  | 734602.11 |  | 355d | [5 empty] | 748555.7982 |  | 100% |  | 734602.11 | 734602.11
1 | Ruwbouw | 2017-01-20 08:00 | 2017-09-15 17:00 | 171d |  | 0 | 0 | 186.107 | 254594.36 | 254594.36 | 2017-01-20 08:00 | 195d | 290326.9018 | 0 | 0 | -34826.5418 | 0 | 255500.36 | 0 | 100% | Finished | 254594.36 | 254594.36
2 | Buitenriolering | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 245.7083 | 29485 | 29485 | 2017-11-04 08:00 | 12d | 23588 | 0 | 0 | 11712.5 | 0 | 35300.5 | 0 | 100% | Finished | 29485 | 29485
3 | Daktimmer | 2017-09-11 08:00 | 2017-09-29 17:00 | 15d |  | 0 | 0 | 276.7854 | 33214.25 | 33214.25 | 2017-09-11 08:00 | 29d | 64214.2167 | 0 | 0 | -30999.9667 | 0 | 33214.25 | 0 | 100% | Finished | 33214.25 | 33214.25
4 | Dakbedekking | 2017-10-02 08:00 | 2017-10-27 17:00 | 20d |  | 0 | 0 | 250.2914 | 40046.63 | 40046.63 | 2017-10-02 08:00 | 25d | 50058.2875 | 0 | 0 | -5002.9275 | 0 | 45055.36 | 0 | 100% | Finished | 40046.63 | 40046.63
5 | dakisolatie | 2017-11-20 08:00 | 2017-11-30 17:00 | 9d |  | 0 | 0 | 86.8056 | 6250 | 6250 | 2018-01-04 08:00 | 1d | 694.4444 | 0 | 0 | 5555.5556 | 0 | 6250 | 0 | 100% | Finished | 6250 | 6250
6 | Buitenschrijnwerk | 2017-11-20 08:00 | 2017-11-24 17:00 | 5d |  | 0 | 0 | 1277.386 | 51095.44 | 51095.44 | 2017-11-20 08:00 | 34d | 347448.992 | 0 | 0 | -292353.492 | 0 | 55095.5 | 0 | 100% | Finished | 51095.44 | 51095.44
7 | Aansluiting watermaatschappij | 2017-11-20 08:00 | 2017-11-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-21 08:00 | 33d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
8 | Pleisterwerken | 2017-11-27 08:00 | 2018-01-26 17:00 | 45d |  | 0 | 0 | 74.697 | 26890.93 | 26890.93 | 2017-11-21 08:00 | 99d | 59160.046 | 0 | 0 | -34958.209 | 0 | 24201.837 | 0 | 100% | Finished | 26890.93 | 26890.93
9 | Chape fase1 (2woningen) | 2018-01-08 08:00 | 2018-01-12 17:00 | 5d |  | 0 | 0 | 193.4148 | 7736.592 | 7736.592 | 2018-01-08 08:00 | 9d | 13925.8656 | 0 | 0 | -6189.2736 | 0 | 7736.592 | 0 | 100% | Finished | 7736.592 | 7736.592
10 | Chape fase2 (3woningen) | 2018-02-05 08:00 | 2018-02-09 17:00 | 5d |  | 0 | 0 | 290.1222 | 11604.888 | 11604.888 | 2018-01-04 08:00 | 11d | 25530.7536 | 0 | 0 | -15086.3544 | 0 | 10444.3992 | 0 | 100% | Finished | 11604.888 | 11604.888
11 | Technieken voor chape fase1 | 2017-12-18 08:00 | 2017-12-22 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2017-12-18 08:00 | 14d | 84000 | 0 | 0 | -54000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
12 | Technieken voor chape fase2 | 2018-01-09 08:00 | 2018-01-15 17:00 | 5d |  | 0 | 0 | 750 | 30000 | 30000 | 2018-01-09 08:00 | 8d | 48000 | 0 | 0 | -18000 | 0 | 30000 | 0 | 100% | Finished | 30000 | 30000
13 | afwerking technieken sanitair / elektriciteit | 2018-03-19 08:00 | 2018-04-30 17:00 | 31d |  | 0 | 0 | 173.0928 | 42927.02 | 42927.02 | 2018-04-06 08:00 | 19d | 26310.109 | 0 | 0 | 18689.891 | 0 | 45000 | 0 | 100% | Finished | 42927.02 | 42927.02
14 | vloer en tegelwerken | 2018-02-05 08:00 | 2018-03-30 17:00 | 40d |  | 0 | 0 | 109.1903 | 34940.91 | 34940.91 | 2018-02-05 08:00 | 63d | 55031.9333 | 0 | 0 | -20091.0232 | 0 | 34940.91 | 0 | 100% | Finished | 34940.91 | 34940.91
15 | binnenschrijnwerk (deuren, trappen, keukens) | 2018-04-02 08:00 | 2018-04-30 17:00 | 21d |  | 0 | 0 | 467.3524 | 78515.2 | 78515.2 | 2018-01-18 08:00 | 57d | 213112.6857 | 0 | 0 | -134597.4857 | 0 | 78515.2 | 0 | 100% | Finished | 78515.2 | 78515.2
16 | buitenaanleg | 2018-03-12 08:00 | 2018-04-13 17:00 | 25d |  | 0 | 0 | 110.9183 | 22183.65 | 22183.65 | 2018-03-12 08:00 | 20d | 17746.92 | 0 | 0 | 4436.73 | 0 | 22183.65 | 0 | 100% | Finished | 22183.65 | 22183.65
17 | afwerken diversen (fietsenstalling, afwerking buitenschrijnwerk, brievenbussen, …) | 2018-03-23 08:00 | 2018-04-18 17:00 | 19d |  | 0 | 0 | 231.0345 | 35117.24 | 35117.24 | 2018-03-23 08:00 | 11d | 20331.0337 | 0 | 0 | 14786.2063 | 0 | 35117.24 | 0 | 100% | Finished | 35117.24 | 35117.24
18 | oplevering | 2018-05-28 08:00 | 2018-05-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-05-31 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | SPI | p-factor
TP1 | 2017-01-20 08:00 | 2017-09-10 17:00 | 247150.0805 | 246956.5292 | 248029.5892 | 2017-09-08 15:00 | -193.5513 | 99.92% | -1073.06 | 99.57% | -2h | 99.85% | 100% | 2018-05-29 09:00 | 2018-05-29 10:00 | 2018-05-30 15:00 | 2018-05-29 09:00 | 2018-05-29 10:00 | 2018-05-30 09:00 | 2018-05-29 10:00 | 2018-05-29 12:00 | 2018-05-30 11:00 | 735675.17 | 737794.0571 | 736057.3605 | 736410.6837 | 738177.9082 | 738532.7667 | 737445.7296 | 737516.7558 | 0.99849 | 0.99922 | 1
TP2 | 2017-09-10 17:00 | 2017-10-19 17:00 | 345326.251 | 315841.251 | 320253.362 | 2017-09-29 14:00 | -29485 | 91.46% | -4412.111 | 98.62% | -14d 3h | 92.63% | 90.89% | 2018-06-18 09:00 | 2018-07-12 16:00 | 2018-07-20 10:00 | 2018-06-20 14:00 | 2018-07-12 16:00 | 2018-07-17 12:00 | 2018-06-18 11:00 | 2018-07-05 17:00 | 2018-07-10 14:00 | 739014.221 | 744864.0566 | 778107.1637 | 772341.2098 | 784503.104 | 778656.6032 | 751120.8016 | 750088.9967 | 0.92628 | 0.91462 | 0.90895
TP3 | 2017-10-19 17:00 | 2017-11-04 17:00 | 357340.24 | 327855.24 | 333769.97 | 2017-10-09 10:00 | -29485 | 91.75% | -5914.73 | 98.23% | -19d 6h | 90.41% | 91.01% | 2018-06-18 09:00 | 2018-07-11 14:00 | 2018-07-20 14:00 | 2018-06-20 17:00 | 2018-07-11 14:00 | 2018-07-16 16:00 | 2018-06-25 15:00 | 2018-07-19 11:00 | 2018-07-24 14:00 | 740516.84 | 747854.8283 | 777096.7997 | 783648.3873 | 785094.7152 | 791764.4978 | 753390.4875 | 754550.5189 | 0.90413 | 0.91749 | 0.91005
TP4 | 2017-11-04 17:00 | 2017-11-08 17:00 | 357340.24 | 333752.24 | 340830.07 | 2017-10-12 09:00 | -23588 | 93.4% | -7077.83 | 97.92% | -19d 7h | 90.49% | 92.93% | 2018-06-13 10:00 | 2018-07-02 16:00 | 2018-07-12 16:00 | 2018-06-15 15:00 | 2018-07-02 16:00 | 2018-07-06 12:00 | 2018-06-25 16:00 | 2018-07-18 17:00 | 2018-07-24 15:00 | 741679.94 | 750180.6986 | 770010.0772 | 783804.9429 | 779111.6284 | 793199.0396 | 753998.619 | 756490.8899 | 0.9049 | 0.93399 | 0.92928
TP5 | 2017-11-08 17:00 | 2017-11-21 17:00 | 379167.3049 | 378854.0532 | 392076.7435 | 2017-11-21 16:00 | -313.2517 | 99.92% | -13222.6903 | 96.63% | -1h | 99.94% | 99.66% | 2018-05-29 09:00 | 2018-05-29 10:00 | 2018-06-14 14:00 | 2018-05-29 09:00 | 2018-05-29 10:00 | 2018-06-04 17:00 | 2018-05-29 09:00 | 2018-05-29 10:00 | 2018-06-04 16:00 | 747824.8003 | 760241.0496 | 748118.947 | 748028.9013 | 760545.4626 | 760452.2741 | 757751.0406 | 757732.0401 | 0.99943 | 0.99917 | 0.99655
TP6 | 2017-11-21 17:00 | 2018-01-04 17:00 | 462015.3904 | 468618.6077 | 481955.6049 | 2018-01-09 12:00 | 6603.2173 | 101.4% | -13336.9972 | 97.23% | 2d 4h | 101% | 98.87% | 2018-05-23 16:00 | 2018-05-21 17:00 | 2018-06-04 16:00 | 2018-05-23 11:00 | 2018-05-21 17:00 | 2018-05-24 15:00 | 2018-05-24 12:00 | 2018-05-23 12:00 | 2018-05-28 11:00 | 747939.1072 | 755509.0611 | 744191.1834 | 745305.6072 | 751654.4704 | 752800.611 | 753167.9991 | 753405.6037 | 1.01 | 1.0143 | 0.98865
TP7 | 2018-01-04 17:00 | 2018-01-18 17:00 | 505727.7447 | 520649.1807 | 532556.7798 | 2018-02-08 14:00 | 14921.436 | 103% | -11907.5991 | 97.76% | 14d 5h | 105.6% | 99.34% | 2018-05-17 16:00 | 2018-05-14 16:00 | 2018-05-24 15:00 | 2018-05-17 11:00 | 2018-05-14 16:00 | 2018-05-16 15:00 | 2018-05-08 11:00 | 2018-05-02 10:00 | 2018-05-03 16:00 | 746509.7091 | 751402.9574 | 740377.97 | 735115.7661 | 745130.9813 | 739748.4273 | 749105.3617 | 747939.2984 | 1.0562 | 1.0295 | 0.9934
TP8 | 2018-01-18 17:00 | 2018-04-06 17:00 | 633402.1876 | 690277.4536 | 702158.1618 | 2018-04-18 14:00 | 56875.266 | 109% | -11880.7082 | 98.31% | 7d 5h | 102.4% | 95.26% | 2018-04-19 15:00 | 2018-04-17 17:00 | 2018-04-25 12:00 | 2018-04-18 14:00 | 2018-04-17 17:00 | 2018-04-18 09:00 | 2018-05-17 11:00 | 2018-05-16 15:00 | 2018-05-17 09:00 | 746482.8182 | 747245.7119 | 742830.6974 | 745438.4752 | 743530.7327 | 746183.3942 | 746287.6582 | 746872.2903 | 1.0241 | 1.0898 | 0.95264
TP9 | 2018-04-06 17:00 | 2018-05-02 17:00 | 734602.11 | 734602.11 | 748555.7982 | 2018-05-02 17:00 | 0 | 100% | -13953.6882 | 98.14% | 0 | 100% | 100% | 2018-05-28 17:00 | 2018-05-28 17:00 | 2018-06-06 14:00 | 2018-05-28 17:00 | 2018-05-28 17:00 | 2018-05-29 11:00 | 2018-05-28 17:00 | 2018-05-28 17:00 | 2018-05-29 11:00 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 1 | 1 | 1
TP10 | 2018-05-02 17:00 | 2018-05-31 17:00 | 734602.11 | 734602.11 | 748555.7982 | 2018-05-28 17:00 | 0 | 100% | -13953.6882 | 98.14% | -3d | 99.15% | 100% | 2018-05-28 17:00 | 2018-05-28 17:00 | 2018-06-06 14:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 748555.7982 | 0.99155 | 1 | 1

## Corrective actions Overview
General |  |  | Corrective actions
Name | Start Tracking Period | Status date | Category | Description
TP1 | 2017-01-20 08:00 | 2017-09-10 17:00 | - | -
TP2 | 2017-09-10 17:00 | 2017-10-19 17:00 | - | -
TP3 | 2017-10-19 17:00 | 2017-11-04 17:00 | - | -
TP4 | 2017-11-04 17:00 | 2017-11-08 17:00 | C2 | Status update call subcontractor
TP5 | 2017-11-08 17:00 | 2017-11-21 17:00 | - | -
TP6 | 2017-11-21 17:00 | 2018-01-04 17:00 | - | -
TP7 | 2018-01-04 17:00 | 2018-01-18 17:00 | - | -
TP8 | 2018-01-18 17:00 | 2018-04-06 17:00 | - | -
TP9 | 2018-04-06 17:00 | 2018-05-02 17:00 | - | -
TP10 | 2018-05-02 17:00 | 2018-05-31 17:00 | - | -