## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | PROJECT GLUING MACHINE | 1 |  |  | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 | 207.375
1 | test PU lijm | 1.1 |  | SS2;SS7 | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 11.375
2 | aankoop rollenwals + vatsmelter | 1.2 | 1SS | FS3;FS4 | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 116.375
3 | voorbereidende werken afzuiging | 1.3 | 2FS |  | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 13.375
4 | voorbereidende werken (elektrisch) | 1.4 | 2FS | FS5;FS6 | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 13.375
5 | testfase productie, opleiding, eerste keer in MTO | 1.5 | 4FS |  | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 | 18.375
6 | haalbaarheidsstudie | 1.6 | 4FS |  | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 | 18.375
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 1.7 | 1SS | FS8 | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 21.375
8 | volledige implementatie en opstart in productie | 1.8 | 7FS |  | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 | 16.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT GLUING MACHINE | 1200h
1 | test PU lijm | 80h | standard - no risk | 99 | 100 | 101
2 | aankoop rollenwals + vatsmelter | 680h | standard - no risk | 99 | 100 | 101
3 | voorbereidende werken afzuiging | 80h | standard - no risk | 99 | 100 | 101
4 | voorbereidende werken (elektrisch) | 80h | standard - no risk | 99 | 100 | 101
5 | testfase productie, opleiding, eerste keer in MTO | 120h | standard - no risk | 99 | 100 | 101
6 | haalbaarheidsstudie | 120h | standard - no risk | 99 | 100 | 101
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 128h | standard - no risk | 99 | 100 | 101
8 | volledige implementatie en opstart in productie | 104h | standard - no risk | 99 | 100 | 101

## Project Control - TP1
| TP Status Date | 2017-09-22 17:00 |  | TP Name | TP1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 10d | [5 empty] | 1750 |  | 0.4651% |  | 500 | 1000
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 10d | 1000 | 1000 | 10d | 750 | 0 | 1750 | 1000 | 50% | Started | 500 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 |  | 0 | 0 | 92000 | 85d | 0 | 0 | 0 | 92000 | 0% | Not Started | 0 | 0
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 |  | 0 | 0 | 3000 | 15d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 |  | 0 | 0 | 2000 | 15d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 |  | 0 | 0 | 1000 | 16d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2017-10-06 17:00 |  | TP Name | TP2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 20d | [5 empty] | 4000 |  | 1.302% |  | 1400 | 11823.5294
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 20d | 2000 | 225 | 2d 2h | 1150 | 0 | 3150 | 225 | 90% | Started | 900 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 |  | 0 | 0 | 92000 | 85d | 0 | 0 | 0 | 92000 | 0% | Not Started | 0 | 10823.5294
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 |  | 0 | 0 | 3000 | 15d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 |  | 0 | 0 | 2000 | 15d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 11d | 687.5 | 687.5 | 11d | 162.5 | 0 | 850 | 687.5 | 50% | Started | 500 | 0
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2017-11-15 17:00 |  | TP Name | TP3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 48d | [5 empty] | 32500 |  | 26.98% |  | 29000 | 42129.4118
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 48d | 4800 | 537.5 | 5d 3h | -1650 | 0 | 3150 | 537.5 | 90% | Started | 900 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 29d | 31388.2353 | 73194.1176 | 67d 5h | -2888.2353 | 0 | 28500 | 73194.1176 | 30% | Started | 27600 | 41129.4118
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 |  | 0 | 0 | 3000 | 15d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 |  | 0 | 0 | 2000 | 15d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 39d | 2437.5 | 2437.5 | 39d | -1587.5 | 0 | 850 | 2437.5 | 50% | Started | 500 | 0
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2017-12-18 17:00 |  | TP Name | TP4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 71d | [5 empty] | 61175 |  | 52.7% |  | 56650 | 71423.5294
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 71d | 7100 | 375 | 3d 6h | -3775 | 0 | 3325 | 375 | 95% | Started | 950 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 52d | 56282.3529 | 37476.4706 | 34d 5h | 717.6471 | 0 | 57000 | 37476.4706 | 60% | Started | 55200 | 66023.5294
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2000
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 2400
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 |  | 0 | 0 | 3000 | 15d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 |  | 0 | 0 | 2000 | 15d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 62d | 3875 | 3875 | 62d | -3025 | 0 | 850 | 3875 | 50% | Started | 500 | 0
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2018-01-26 17:00 |  | TP Name | TP5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 100d | [5 empty] | 94600 |  | 82.7% |  | 88900 | 100166.6667
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 100d | 10000 | 0 | 0 | -6500 | 0 | 3500 | 0 | 100% | Finished | 1000 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 81d | 87670.5882 | 4600 | 4d 2h | 2579.4118 | 0 | 90250 | 4600 | 95% | Started | 87400 | 92000
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 |  | 0 | 0 | 3000 | 15d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 1000
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 |  | 0 | 0 | 2000 | 15d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 666.6667
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 91d | 5687.5 | 5687.5 | 91d | -4837.5 | 0 | 850 | 5687.5 | 50% | Started | 500 | 0
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP6
| TP Status Date | 2018-02-15 17:00 |  | TP Name | TP6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 114d | [5 empty] | 99350 |  | 86.98% |  | 93500 | 103500
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 100d | 10000 | 0 | 0 | -6500 | 0 | 3500 | 0 | 100% | Finished | 1000 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 95d | 102823.5294 | 0 | 0 | -7823.5294 | 0 | 95000 | 0 | 100% | Finished | 92000 | 92000
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 |  | 0 | 0 | 2500 | 10d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 2500
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 |  | 0 | 0 | 3000 | 10d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 |  | 0 | 0 | 3000 | 15d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 |  | 0 | 0 | 2000 | 15d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 105d | 6562.5 | 6562.5 | 105d | -5712.5 | 0 | 850 | 6562.5 | 50% | Started | 500 | 0
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP7
| TP Status Date | 2018-03-21 17:00 |  | TP Name | TP7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 138d | [5 empty] | 102690 |  | 89.72% |  | 96450 | 104293.2692
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 100d | 10000 | 0 | 0 | -6500 | 0 | 3500 | 0 | 100% | Finished | 1000 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 95d | 102823.5294 | 0 | 0 | -7823.5294 | 0 | 95000 | 0 | 100% | Finished | 92000 | 92000
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2018-02-15 08:00 | 25d | 6250 | 6250 | 25d | -5000 | 0 | 1250 | 6250 | 50% | Started | 1250 | 2500
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2018-02-15 08:00 | 25d | 7500 | 7500 | 25d | -5750 | 0 | 1750 | 7500 | 50% | Started | 1500 | 3000
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 |  | 0 | 0 | 3000 | 15d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 |  | 0 | 0 | 2000 | 15d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 129d | 8062.5 | 3453.125 | 55d 2h | -6872.5 | 0 | 1190 | 3453.125 | 70% | Started | 700 | 562.5
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 230.7692

## TP8
| TP Status Date | 2018-04-20 17:00 |  | TP Name | TP8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 160d | [5 empty] | 106830 |  | 93.21% |  | 100200 | 107500
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 100d | 10000 | 0 | 0 | -6500 | 0 | 3500 | 0 | 100% | Finished | 1000 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 95d | 102823.5294 | 0 | 0 | -7823.5294 | 0 | 95000 | 0 | 100% | Finished | 92000 | 92000
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2018-02-15 08:00 | 47d | 11750 | 0 | 0 | -9250 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2018-02-15 08:00 | 47d | 14100 | 0 | 0 | -10600 | 0 | 3500 | 0 | 100% | Finished | 3000 | 3000
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 | 2018-03-21 08:00 | 23d | 4600 | 18400 | 92d | -3960 | 0 | 640 | 18400 | 20% | Started | 600 | 3000
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 | 2018-03-21 08:00 | 23d | 3066.6667 | 12266.6667 | 92d | -2566.6667 | 0 | 500 | 12266.6667 | 20% | Started | 400 | 2000
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 151d | 9437.5 | 4046.875 | 64d 6h | -8247.5 | 0 | 1190 | 4046.875 | 70% | Started | 700 | 1000
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000

## TP9
| TP Status Date | 2018-05-15 17:00 |  | TP Name | TP9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 177d | [5 empty] | 111560 |  | 97.02% |  | 104300 | 107500
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 100d | 10000 | 0 | 0 | -6500 | 0 | 3500 | 0 | 100% | Finished | 1000 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 95d | 102823.5294 | 0 | 0 | -7823.5294 | 0 | 95000 | 0 | 100% | Finished | 92000 | 92000
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2018-02-15 08:00 | 47d | 11750 | 0 | 0 | -9250 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2018-02-15 08:00 | 47d | 14100 | 0 | 0 | -10600 | 0 | 3500 | 0 | 100% | Finished | 3000 | 3000
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 | 2018-03-21 08:00 | 40d | 8000 | 0 | 0 | -4800 | 0 | 3200 | 0 | 100% | Finished | 3000 | 3000
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 | 2018-03-21 08:00 | 40d | 5333.3333 | 0 | 0 | -2833.3333 | 0 | 2500 | 0 | 100% | Finished | 2000 | 2000
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 168d | 10500 | 2625 | 42d | -9140 | 0 | 1360 | 2625 | 80% | Started | 800 | 1000
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 |  | 0 | 0 | 3000 | 13d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000

## TP10
| TP Status Date | 2018-05-31 17:00 |  | TP Name | TP10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT GLUING MACHINE | 2017-09-11 08:00 | 2018-04-06 17:00 | 150d |  |  | 0 |  |  | 107500 |  | 189d | [5 empty] | 116800 |  | 100% |  | 107500 | 107500
1 | test PU lijm | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-11 08:00 | 100d | 10000 | 0 | 0 | -6500 | 0 | 3500 | 0 | 100% | Finished | 1000 | 1000
2 | aankoop rollenwals + vatsmelter | 2017-09-25 08:00 | 2018-01-19 17:00 | 85d |  | 0 | 0 | 135.2941 | 92000 | 92000 | 2017-10-06 08:00 | 95d | 102823.5294 | 0 | 0 | -7823.5294 | 0 | 95000 | 0 | 100% | Finished | 92000 | 92000
3 | voorbereidende werken afzuiging | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 31.25 | 2500 | 2500 | 2018-02-15 08:00 | 47d | 11750 | 0 | 0 | -9250 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
4 | voorbereidende werken (elektrisch) | 2017-12-07 08:00 | 2017-12-20 17:00 | 10d |  | 0 | 0 | 37.5 | 3000 | 3000 | 2018-02-15 08:00 | 47d | 14100 | 0 | 0 | -10600 | 0 | 3500 | 0 | 100% | Finished | 3000 | 3000
5 | testfase productie, opleiding, eerste keer in MTO | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 25 | 3000 | 3000 | 2018-03-21 08:00 | 40d | 8000 | 0 | 0 | -4800 | 0 | 3200 | 0 | 100% | Finished | 3000 | 3000
6 | haalbaarheidsstudie | 2018-01-22 08:00 | 2018-02-09 17:00 | 15d |  | 0 | 0 | 16.6667 | 2000 | 2000 | 2018-03-21 08:00 | 40d | 5333.3333 | 0 | 0 | -2833.3333 | 0 | 2500 | 0 | 100% | Finished | 2000 | 2000
7 | bijkomend onderzoek naar belijmde mdf panelen met release coat | 2018-03-09 08:00 | 2018-03-30 17:00 | 16d |  | 0 | 0 | 7.8125 | 1000 | 1000 | 2017-09-22 08:00 | 180d | 11250 | 0 | 0 | -9550 | 0 | 1700 | 0 | 100% | Finished | 1000 | 1000
8 | volledige implementatie en opstart in productie | 2018-03-21 08:00 | 2018-04-06 17:00 | 13d |  | 0 | 0 | 28.8462 | 3000 | 3000 | 2018-05-15 08:00 | 13d | 3000 | 0 | 0 | 1900 | 0 | 4900 | 0 | 100% | Finished | 3000 | 3000

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | SPI | p-factor
TP1 | 2017-09-11 08:00 | 2017-09-22 17:00 | 1000 | 500 | 1750 | 2017-09-15 17:00 | -500 | 50% | -1250 | 28.57% | -5d | 50% | 100% | 2018-04-09 15:00 | 2018-11-02 17:00 | 2021-09-17 17:00 | 2018-04-13 17:00 | 2018-11-02 17:00 | 2021-08-13 17:00 | 2018-04-13 17:00 | 2018-11-02 17:00 | 2021-08-13 17:00 | 108750 | 376250 | 215750 | 215750 | 750750 | 750750 | 327402.1739 | 327402.1739 | 0.5 | 0.5 | 1
TP2 | 2017-09-22 17:00 | 2017-10-06 17:00 | 11823.5294 | 1400 | 4000 | 2017-09-25 10:00 | -10423.5294 | 11.84% | -2600 | 35% | -9d 6h | 51.25% | 70.83% | 2018-04-27 12:00 | 2022-07-19 15:00 | 2031-07-25 12:00 | 2018-05-02 14:00 | 2022-07-19 15:00 | 2031-06-04 10:00 | 2018-04-20 15:00 | 2018-10-24 14:00 | 2020-10-02 09:00 | 110100 | 307142.8571 | 900054.6218 | 211024.3902 | 2564156.0624 | 595498.2578 | 353379.0957 | 281385.6209 | 0.5125 | 0.11841 | 0.70833
TP3 | 2017-10-06 17:00 | 2017-11-15 17:00 | 42129.4118 | 29000 | 32500 | 2017-10-30 15:00 | -13129.4118 | 68.84% | -3500 | 89.23% | -12d 2h | 74.48% | 98.72% | 2018-05-03 11:00 | 2018-07-11 16:00 | 2018-08-17 10:00 | 2018-04-27 17:00 | 2018-07-11 16:00 | 2018-08-09 11:00 | 2018-04-25 10:00 | 2018-06-19 11:00 | 2018-07-13 16:00 | 111000 | 120474.1379 | 146539.9594 | 137898.6014 | 160303.4028 | 150619.1223 | 124688.3908 | 123482.3734 | 0.74479 | 0.68836 | 0.98716
TP4 | 2017-11-15 17:00 | 2017-12-18 17:00 | 71423.5294 | 56650 | 61175 | 2017-12-05 11:00 | -14773.5294 | 79.32% | -4525 | 92.6% | -9d 5h | 86.44% | 99.19% | 2018-05-07 14:00 | 2018-06-01 09:00 | 2018-06-22 10:00 | 2018-04-27 14:00 | 2018-06-01 09:00 | 2018-06-14 12:00 | 2018-04-20 14:00 | 2018-05-10 12:00 | 2018-05-22 15:00 | 112025 | 116086.7167 | 125285.9704 | 119999.4399 | 130406.9261 | 124698.1264 | 117709.1279 | 116827.059 | 0.86444 | 0.79316 | 0.99195
TP5 | 2017-12-18 17:00 | 2018-01-26 17:00 | 100166.6667 | 88900 | 94600 | 2018-01-09 09:00 | -11266.6667 | 88.75% | -5700 | 93.97% | -13d 7h | 86.12% | 93.81% | 2018-04-30 15:00 | 2018-05-03 17:00 | 2018-05-18 16:00 | 2018-04-24 10:00 | 2018-05-03 17:00 | 2018-05-10 11:00 | 2018-04-26 16:00 | 2018-05-11 09:00 | 2018-05-17 16:00 | 113200 | 114392.5759 | 115557.2553 | 116196.5167 | 116900.9714 | 117581.2202 | 114615.0393 | 114728.8454 | 0.86125 | 0.88752 | 0.93813
TP6 | 2018-01-26 17:00 | 2018-02-15 17:00 | 103500 | 93500 | 99350 | 2018-01-15 11:00 | -10000 | 90.34% | -5850 | 94.11% | -23d 5h | 79.28% | 94.12% | 2018-04-26 17:00 | 2018-04-30 17:00 | 2018-05-15 11:00 | 2018-04-23 17:00 | 2018-04-30 17:00 | 2018-05-04 10:00 | 2018-05-10 14:00 | 2018-06-01 10:00 | 2018-06-07 16:00 | 113350 | 114225.9358 | 114847.3262 | 117009.751 | 115816.945 | 118114.6659 | 114346.1952 | 114710.2004 | 0.79276 | 0.90338 | 0.94117
TP7 | 2018-02-15 17:00 | 2018-03-21 17:00 | 104293.2692 | 96450 | 102690 | 2018-01-17 17:00 | -7843.2692 | 92.48% | -6240 | 93.92% | -45d | 67.39% | 97.15% | 2018-04-23 17:00 | 2018-04-25 10:00 | 2018-05-09 15:00 | 2018-04-23 11:00 | 2018-04-25 10:00 | 2018-04-26 15:00 | 2018-06-08 17:00 | 2018-07-18 14:00 | 2018-07-25 17:00 | 113740 | 114454.8989 | 114638.5809 | 119086.7742 | 115411.615 | 120147.5919 | 114491.1821 | 115159.3868 | 0.67391 | 0.9248 | 0.97145
TP8 | 2018-03-21 17:00 | 2018-04-20 17:00 | 107500 | 100200 | 106830 | 2018-01-26 17:00 | -7300 | 93.21% | -6630 | 93.79% | -60d | 62.5% | 99.33% | 2018-04-23 09:00 | 2018-04-23 16:00 | 2018-05-08 14:00 | 2018-05-07 16:00 | 2018-05-08 14:00 | 2018-05-09 11:00 | 2018-06-29 17:00 | 2018-08-10 17:00 | 2018-08-20 10:00 | 114130 | 114613.024 | 114661.8363 | 118510 | 115180.0506 | 119282.8383 | 114622.7377 | 115169.5116 | 0.625 | 0.93209 | 0.99334
TP9 | 2018-04-20 17:00 | 2018-05-15 17:00 | 107500 | 104300 | 111560 | 2018-03-21 17:00 | -3200 | 97.02% | -7260 | 93.49% | -39d | 77.97% | 99.78% | 2018-04-13 12:00 | 2018-04-13 14:00 | 2018-04-30 11:00 | 2018-05-23 10:00 | 2018-05-23 11:00 | 2018-05-23 15:00 | 2018-05-31 17:00 | 2018-06-06 11:00 | 2018-06-07 12:00 | 114760 | 114982.7421 | 114858.1783 | 115664.3478 | 115087.7543 | 115950.0388 | 114957.0823 | 115100.33 | 0.77966 | 0.97023 | 0.99779
TP10 | 2018-05-15 17:00 | 2018-05-31 17:00 | 107500 | 107500 | 116800 | 2018-04-06 17:00 | 0 | 100% | -9300 | 92.04% | -39d | 79.37% | 100% | 2018-04-06 17:00 | 2018-04-06 17:00 | 2018-04-25 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 2018-05-31 17:00 | 116800 | 116800 | 116800 | 116800 | 116800 | 116800 | 116800 | 116800 | 0.79365 | 1 | 1
5
11
36
62
87
91
93
100
138
150

## Corrective actions Overview
General |  |  | Corrective actions
Name | Start Tracking Period | Status date | Category | Description
TP1 | 2017-09-11 08:00 | 2017-09-22 17:00 | C1 | Status update call employees
TP2 | 2017-09-22 17:00 | 2017-10-06 17:00 | - | -
TP3 | 2017-10-06 17:00 | 2017-11-15 17:00 | - | -
TP4 | 2017-11-15 17:00 | 2017-12-18 17:00 | - | -
TP5 | 2017-12-18 17:00 | 2018-01-26 17:00 | - | -
TP6 | 2018-01-26 17:00 | 2018-02-15 17:00 | - | -
TP7 | 2018-02-15 17:00 | 2018-03-21 17:00 | C5 | Involve higher management
TP8 | 2018-03-21 17:00 | 2018-04-20 17:00 | - | -
TP9 | 2018-04-20 17:00 | 2018-05-15 17:00 | - | -
TP10 | 2018-05-15 17:00 | 2018-05-31 17:00 | - | -