## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | PROJECT Labeling MACHINE | 1 |  |  | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 | 158.375
1 | Vereenvoudigen huidige werkpost | 1.1 |  | FS2 | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 11.375
2 | vastleggen instructies en procedures | 1.2 | 1FS |  | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 | 18.375
3 | ontwerp semi automatische applicatie unit | 1.3 |  | SS4 | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 11.375
4 | bestellen print &amp; apply | 1.4 | 3SS | SS5 | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 77.375
5 | voorbereiden werken (hardwarde, dataconnectie) | 1.5 | 4SS | FS6 | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 | 18.375
6 | integratie met shopfloor software (printbaar maken) | 1.6 | 5FS | FS7 | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 | 10.375
7 | implementatie in productie, opstart en opleiding | 1.7 | 6FS |  | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 | 17.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT Labeling MACHINE | 920h
1 | Vereenvoudigen huidige werkpost | 80h | standard - no risk | 99 | 100 | 101
2 | vastleggen instructies en procedures | 104h | standard - no risk | 99 | 100 | 101
3 | ontwerp semi automatische applicatie unit | 80h | standard - no risk | 99 | 100 | 101
4 | bestellen print &amp; apply | 448h | standard - no risk | 99 | 100 | 101
5 | voorbereiden werken (hardwarde, dataconnectie) | 120h | standard - no risk | 99 | 100 | 101
6 | integratie met shopfloor software (printbaar maken) | 72h | standard - no risk | 99 | 100 | 101
7 | implementatie in productie, opstart en opleiding | 112h | standard - no risk | 99 | 100 | 101

## Project Control - TP1
| TP Status Date | 2017-09-22 17:00 |  | TP Name | TP1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 15d | [5 empty] | 6050 |  | 4.969% |  | 5700 | 11107.6923
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 15d | 1500 | 637.5 | 6d 3h | -450 | 0 | 1050 | 637.5 | 70% | Started | 700 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 |  | 0 | 0 | 700 | 13d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 107.6923
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 10d | 10000 | 10000 | 10d | -5000 | 0 | 5000 | 10000 | 50% | Started | 5000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 |  | 0 | 0 | 90000 | 56d | 0 | 0 | 0 | 90000 | 0% | Not Started | 0 | 0
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 |  | 0 | 0 | 5000 | 15d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 |  | 0 | 0 | 5000 | 9d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 |  | 0 | 0 | 3000 | 14d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2017-10-06 17:00 |  | TP Name | TP2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 25d | [5 empty] | 56050 |  | 44.2% |  | 50700 | 27717.5824
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 25d | 2500 | 1075 | 10d 6h | -1450 | 0 | 1050 | 1075 | 70% | Started | 700 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 |  | 0 | 0 | 700 | 13d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 646.1538
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 20d | 20000 | 20000 | 20d | -15000 | 0 | 5000 | 20000 | 50% | Started | 5000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 10d | 16071.4286 | 16071.4286 | 10d | 33928.5714 | 0 | 50000 | 16071.4286 | 50% | Started | 45000 | 16071.4286
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 |  | 0 | 0 | 5000 | 15d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 |  | 0 | 0 | 5000 | 9d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 |  | 0 | 0 | 3000 | 14d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2017-11-15 17:00 |  | TP Name | TP3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 53d | [5 empty] | 98050 |  | 77.33% |  | 88700 | 72771.4286
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 53d | 5300 | 2275 | 22d 6h | -4250 | 0 | 1050 | 2275 | 70% | Started | 700 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 |  | 0 | 0 | 700 | 13d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 700
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 48d | 48000 | 20625 | 20d 5h | -41000 | 0 | 7000 | 20625 | 70% | Started | 7000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 38d | 61071.4286 | 6830.3571 | 4d 2h | 28928.5714 | 0 | 90000 | 6830.3571 | 90% | Started | 81000 | 61071.4286
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 |  | 0 | 0 | 5000 | 15d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 |  | 0 | 0 | 5000 | 9d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 |  | 0 | 0 | 3000 | 14d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2017-12-18 17:00 |  | TP Name | TP4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 76d | [5 empty] | 104150 |  | 82.3% |  | 94400 | 102033.3333
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 76d | 7600 | 850 | 8d 4h | -6250 | 0 | 1350 | 850 | 90% | Started | 900 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 |  | 0 | 0 | 700 | 13d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 700
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 71d | 71000 | 0 | 0 | -61000 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 61d | 98035.7143 | 10848.2143 | 6d 6h | -8035.7143 | 0 | 90000 | 10848.2143 | 90% | Started | 81000 | 90000
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 | 2017-11-15 08:00 | 24d | 8000 | 8000 | 24d | -5200 | 0 | 2800 | 8000 | 50% | Started | 2500 | 333.3333
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 |  | 0 | 0 | 5000 | 9d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 |  | 0 | 0 | 3000 | 14d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2018-01-26 17:00 |  | TP Name | TP5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 105d | [5 empty] | 115300 |  | 90.85% |  | 104200 | 112557.1429
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 105d | 10500 | 0 | 0 | -9000 | 0 | 1500 | 0 | 100% | Finished | 1000 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 | 2017-12-18 08:00 | 30d | 1615.3846 | 0 | 0 | -615.3846 | 0 | 1000 | 0 | 100% | Finished | 700 | 700
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 71d | 71000 | 0 | 0 | -61000 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 90d | 144642.8571 | 0 | 0 | -44642.8571 | 0 | 100000 | 0 | 100% | Finished | 90000 | 90000
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 | 2017-11-15 08:00 | 53d | 17666.6667 | 17666.6667 | 53d | -14866.6667 | 0 | 2800 | 17666.6667 | 50% | Started | 2500 | 5000
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 |  | 0 | 0 | 5000 | 9d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 |  | 0 | 0 | 3000 | 14d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 857.1429

## TP6
| TP Status Date | 2018-02-15 17:00 |  | TP Name | TP6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 119d | [5 empty] | 115300 |  | 90.85% |  | 104200 | 114700
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 105d | 10500 | 0 | 0 | -9000 | 0 | 1500 | 0 | 100% | Finished | 1000 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 | 2017-12-18 08:00 | 30d | 1615.3846 | 0 | 0 | -615.3846 | 0 | 1000 | 0 | 100% | Finished | 700 | 700
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 71d | 71000 | 0 | 0 | -61000 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 90d | 144642.8571 | 0 | 0 | -44642.8571 | 0 | 100000 | 0 | 100% | Finished | 90000 | 90000
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 | 2017-11-15 08:00 | 67d | 22333.3333 | 22333.3333 | 67d | -19533.3333 | 0 | 2800 | 22333.3333 | 50% | Started | 2500 | 5000
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 |  | 0 | 0 | 5000 | 9d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 |  | 0 | 0 | 3000 | 14d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000

## TP7
| TP Status Date | 2018-03-21 17:00 |  | TP Name | TP7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 143d | [5 empty] | 116420 |  | 91.72% |  | 105200 | 114700
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 105d | 10500 | 0 | 0 | -9000 | 0 | 1500 | 0 | 100% | Finished | 1000 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 | 2017-12-18 08:00 | 30d | 1615.3846 | 0 | 0 | -615.3846 | 0 | 1000 | 0 | 100% | Finished | 700 | 700
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 71d | 71000 | 0 | 0 | -61000 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 90d | 144642.8571 | 0 | 0 | -44642.8571 | 0 | 100000 | 0 | 100% | Finished | 90000 | 90000
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 | 2017-11-15 08:00 | 91d | 30333.3333 | 13000 | 39d | -26413.3333 | 0 | 3920 | 13000 | 70% | Started | 3500 | 5000
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 |  | 0 | 0 | 5000 | 9d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 5000
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 |  | 0 | 0 | 3000 | 14d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000

## TP8
| TP Status Date | 2018-04-20 17:00 |  | TP Name | TP8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 165d | [5 empty] | 122800 |  | 97.38% |  | 111700 | 114700
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 105d | 10500 | 0 | 0 | -9000 | 0 | 1500 | 0 | 100% | Finished | 1000 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 | 2017-12-18 08:00 | 30d | 1615.3846 | 0 | 0 | -615.3846 | 0 | 1000 | 0 | 100% | Finished | 700 | 700
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 71d | 71000 | 0 | 0 | -61000 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 90d | 144642.8571 | 0 | 0 | -44642.8571 | 0 | 100000 | 0 | 100% | Finished | 90000 | 90000
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 | 2017-11-15 08:00 | 113d | 37666.6667 | 0 | 0 | -32066.6667 | 0 | 5600 | 0 | 100% | Finished | 5000 | 5000
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 | 2018-03-21 08:00 | 23d | 12777.7778 | 0 | 0 | -8077.7778 | 0 | 4700 | 0 | 100% | Finished | 5000 | 5000
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 |  | 0 | 0 | 3000 | 14d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000

## TP9
| TP Status Date | 2018-05-15 17:00 |  | TP Name | TP9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Labeling MACHINE | 2017-09-04 08:00 | 2018-02-09 17:00 | 115d |  |  | 0 |  |  | 114700 |  | 182d | [5 empty] | 128200 |  | 100% |  | 114700 | 114700
1 | Vereenvoudigen huidige werkpost | 2017-09-04 08:00 | 2017-09-15 17:00 | 10d |  | 0 | 0 | 12.5 | 1000 | 1000 | 2017-09-04 08:00 | 105d | 10500 | 0 | 0 | -9000 | 0 | 1500 | 0 | 100% | Finished | 1000 | 1000
2 | vastleggen instructies en procedures | 2017-09-21 08:00 | 2017-10-09 17:00 | 13d |  | 0 | 0 | 6.7308 | 700 | 700 | 2017-12-18 08:00 | 30d | 1615.3846 | 0 | 0 | -615.3846 | 0 | 1000 | 0 | 100% | Finished | 700 | 700
3 | ontwerp semi automatische applicatie unit | 2017-09-11 08:00 | 2017-09-22 17:00 | 10d |  | 0 | 0 | 125 | 10000 | 10000 | 2017-09-11 08:00 | 71d | 71000 | 0 | 0 | -61000 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000
4 | bestellen print &amp; apply | 2017-09-25 08:00 | 2017-12-11 17:00 | 56d |  | 0 | 0 | 200.8929 | 90000 | 90000 | 2017-09-25 08:00 | 90d | 144642.8571 | 0 | 0 | -44642.8571 | 0 | 100000 | 0 | 100% | Finished | 90000 | 90000
5 | voorbereiden werken (hardwarde, dataconnectie) | 2017-12-18 08:00 | 2018-01-05 17:00 | 15d |  | 0 | 0 | 41.6667 | 5000 | 5000 | 2017-11-15 08:00 | 113d | 37666.6667 | 0 | 0 | -32066.6667 | 0 | 5600 | 0 | 100% | Finished | 5000 | 5000
6 | integratie met shopfloor software (printbaar maken) | 2018-01-08 08:00 | 2018-01-18 17:00 | 9d |  | 0 | 0 | 69.4444 | 5000 | 5000 | 2018-03-21 08:00 | 23d | 12777.7778 | 0 | 0 | -8077.7778 | 0 | 4700 | 0 | 100% | Finished | 5000 | 5000
7 | implementatie in productie, opstart en opleiding | 2018-01-23 08:00 | 2018-02-09 17:00 | 14d |  | 0 | 0 | 26.7857 | 3000 | 3000 | 2018-04-20 08:00 | 18d | 3857.1429 | 0 | 0 | 1542.8571 | 0 | 5400 | 0 | 100% | Finished | 3000 | 3000

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | SPI | p-factor
TP1 | 2017-09-04 08:00 | 2017-09-22 17:00 | 11107.6923 | 5700 | 6050 | 2017-09-15 14:00 | -5407.6923 | 51.32% | -350 | 94.21% | -5d 3h | 64.17% | 95.3% | 2018-02-19 11:00 | 2018-07-13 09:00 | 2018-08-01 16:00 | 2018-02-21 10:00 | 2018-07-13 09:00 | 2018-07-31 17:00 | 2018-02-19 11:00 | 2018-05-11 10:00 | 2018-05-25 10:00 | 115050 | 121742.9825 | 218460.2564 | 175920.1299 | 231502.9915 | 186350.7519 | 133334.3175 | 129625.433 | 0.64167 | 0.51316 | 0.95302
TP2 | 2017-09-22 17:00 | 2017-10-06 17:00 | 27717.5824 | 50700 | 56050 | 2017-10-27 11:00 | 22982.4176 | 182.9% | -5350 | 90.45% | 14d 3h | 157.5% | 88.21% | 2018-01-09 17:00 | 2017-11-29 16:00 | 2017-12-08 12:00 | 2018-01-12 10:00 | 2017-11-29 16:00 | 2017-12-05 16:00 | 2018-01-22 14:00 | 2017-12-13 17:00 | 2017-12-21 09:00 | 120050 | 126803.4517 | 91038.6642 | 96684.9206 | 94730.7619 | 100972.8265 | 114794.0317 | 117669.0636 | 1.575 | 1.8292 | 0.88206
TP3 | 2017-10-06 17:00 | 2017-11-15 17:00 | 72771.4286 | 88700 | 98050 | 2017-11-29 17:00 | 15928.5714 | 121.9% | -9350 | 90.46% | 10d | 118.9% | 95.5% | 2018-01-18 17:00 | 2018-01-12 11:00 | 2018-01-26 10:00 | 2018-01-25 11:00 | 2018-01-12 11:00 | 2018-01-18 15:00 | 2018-01-26 17:00 | 2018-01-16 15:00 | 2018-01-23 11:00 | 124050 | 126790.699 | 119380.9712 | 119923.0159 | 121629.5008 | 122228.6833 | 124923.6799 | 125092.5374 | 1.1887 | 1.2189 | 0.95498
TP4 | 2017-11-15 17:00 | 2017-12-18 17:00 | 102033.3333 | 94400 | 104150 | 2017-12-05 11:00 | -7633.3333 | 92.52% | -9750 | 90.64% | -9d 5h | 87.34% | 97.49% | 2018-02-21 14:00 | 2018-02-23 10:00 | 2018-03-14 09:00 | 2018-02-19 14:00 | 2018-02-23 10:00 | 2018-03-02 10:00 | 2018-02-23 14:00 | 2018-03-06 14:00 | 2018-03-14 11:00 | 124450 | 126546.6631 | 126091.4901 | 127393.6911 | 128357.6927 | 129794.3902 | 126454.124 | 126711.0938 | 0.87336 | 0.92519 | 0.97489
TP5 | 2017-12-18 17:00 | 2018-01-26 17:00 | 112557.1429 | 104200 | 115300 | 2017-12-27 12:00 | -8357.1429 | 92.58% | -11100 | 90.37% | -22d 4h | 78.57% | 100% | 2018-02-22 11:00 | 2018-02-23 10:00 | 2018-03-14 12:00 | 2018-02-21 15:00 | 2018-02-23 10:00 | 2018-02-27 10:00 | 2018-03-14 12:00 | 2018-03-27 11:00 | 2018-04-02 15:00 | 125800 | 126918.5221 | 126642.1305 | 128663.6364 | 127850.3613 | 130087.2099 | 126862.1713 | 127230.1049 | 0.78571 | 0.92575 | 1
TP6 | 2018-01-26 17:00 | 2018-02-15 17:00 | 114700 | 104200 | 115300 | 2017-12-27 12:00 | -10500 | 90.85% | -11100 | 90.37% | -36d 4h | 69.33% | 100% | 2018-02-26 12:00 | 2018-02-27 14:00 | 2018-03-19 09:00 | 2018-03-02 16:00 | 2018-03-05 17:00 | 2018-03-07 10:00 | 2018-04-03 12:00 | 2018-04-23 16:00 | 2018-04-30 16:00 | 125800 | 126918.5221 | 126858.0614 | 130445.4545 | 128089.2945 | 132058.8379 | 126906.3794 | 127486.0782 | 0.69328 | 0.90846 | 1
TP7 | 2018-02-15 17:00 | 2018-03-21 17:00 | 114700 | 105200 | 116420 | 2018-01-01 12:00 | -9500 | 91.72% | -11220 | 90.36% | -57d 4h | 59.79% | 100% | 2018-02-23 12:00 | 2018-02-26 11:00 | 2018-03-15 15:00 | 2018-04-06 16:00 | 2018-04-09 16:00 | 2018-04-11 10:00 | 2018-05-02 12:00 | 2018-05-30 11:00 | 2018-06-06 14:00 | 125920 | 126933.2129 | 126777.8897 | 132308.8889 | 127882.6 | 134003.5023 | 126901.7767 | 127696.2285 | 0.5979 | 0.91718 | 1
TP8 | 2018-03-21 17:00 | 2018-04-20 17:00 | 114700 | 111700 | 122800 | 2018-01-22 17:00 | -3000 | 97.38% | -11100 | 90.96% | -64d | 61.21% | 100% | 2018-02-14 17:00 | 2018-02-15 09:00 | 2018-03-02 16:00 | 2018-04-27 11:00 | 2018-04-27 11:00 | 2018-04-27 16:00 | 2018-05-10 17:00 | 2018-05-23 16:00 | 2018-05-28 09:00 | 125800 | 126098.12 | 125880.573 | 127700.9901 | 126186.6997 | 128188.0178 | 126052.1867 | 126328.9487 | 0.61212 | 0.97384 | 1
TP9 | 2018-04-20 17:00 | 2018-05-15 17:00 | 114700 | 114700 | 128200 | 2018-02-09 17:00 | 0 | 100% | -13500 | 89.47% | -67d | 63.19% | 100% | 2018-02-09 17:00 | 2018-02-09 17:00 | 2018-03-01 12:00 | 2018-05-15 17:00 | 2018-05-15 17:00 | 2018-05-15 17:00 | 2018-05-15 17:00 | 2018-05-15 17:00 | 2018-05-15 17:00 | 128200 | 128200 | 128200 | 128200 | 128200 | 128200 | 128200 | 128200 | 0.63187 | 1 | 1
10
40
63
67
83
83
86
101
115
-30701
-30701
-30695
-30673
-30656
-30654
-30642
-30642
-30641
-30630
-30620
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!

## Corrective actions Overview
General |  |  | Corrective actions
Name | Start Tracking Period | Status date | Category | Description
TP1 | 2017-09-04 08:00 | 2017-09-22 17:00 | - | -
TP2 | 2017-09-22 17:00 | 2017-10-06 17:00 | - | -
TP3 | 2017-10-06 17:00 | 2017-11-15 17:00 | - | -
TP4 | 2017-11-15 17:00 | 2017-12-18 17:00 | C2 | Status update call subcontractor
TP5 | 2017-12-18 17:00 | 2018-01-26 17:00 | - | -
TP6 | 2018-01-26 17:00 | 2018-02-15 17:00 | - | -
TP7 | 2018-02-15 17:00 | 2018-03-21 17:00 | C3 | Use new resource/supplier
TP8 | 2018-03-21 17:00 | 2018-04-20 17:00 | - | -
TP9 | 2018-04-20 17:00 | 2018-05-15 17:00 | - | -